## Actual Finish
 | time axis 2015-08-06 to 2019-04-26
TASK CODE | TASK NAME | WA-01A | WA-01B | WA-02A | WA-02B | WA-03A | WA-03B | WA-04A | WA-04B | WA-05A | WA-05B | WA-06A | WA-06B | WA-07A | WA-07B | WA-08A | WA-08B | WA-09A | WA-09B | WA-10A | WA-10B | WA-11A | WA-11B | WA-12A | WA-12B | WA-13A | WA-13B | WA-14A | WA-14B | WA-15A | WA-15B | WA-16A | WA-16B | WA-17A | WA-17B | WA-18A | WA-18B | WA-19A | WA-19B | WA-20A | WA-20B | WA-21A | WA-21B | WA-22A | WA-22B | WA-23A | WA-23B | CHECK 1 | CHECK 2 | CHECK 3
WET-DE06-A1000 | [20 empty] | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23
WET-DE05-A1000 | [10 empty] | 2016-05-16 | 2016-05-16 | 2016-05-16 | 2016-05-16 | 2016-05-16 | 2016-05-16 | 2016-05-16 | 2016-05-16 | 2016-05-16 | 2016-05-16 | 2016-05-16 | 2016-05-16 | 2016-05-16 | 2016-05-16 | 2016-05-16 | 2016-05-16 | 2016-05-16 | 2016-05-16 | 2016-05-16 | 2016-05-16 | 2016-05-16 | 2016-05-16 | 2016-05-16 | 2016-05-16 | 2016-05-16 | 2016-05-16 | 2016-05-16 | 2016-05-16 | 2016-05-16 | 2016-05-16 | 2016-05-16 | 2016-05-16 | 2016-05-16 | 2016-05-16 | 2016-05-16 | 2016-05-16 | 2016-05-16
WET-DE04-A1070 | [10 empty] | 2016-05-16: 2018-11-24; 2016-05-16: 2018-11-24; 2016-05-16: 2018-11-24; 2016-05-16: 2018-11-24; 2016-05-16: 2018-11-24
WET-DE04-A1060 | [10 empty] | 2016-05-16: 2018-11-09; 2016-05-16: 2018-11-09; 2016-05-16: 2018-11-09; 2016-05-16: 2018-11-09; 2016-05-16: 2018-11-09; 2016-05-16: 2018-11-09; 2016-05-16: 2018-11-09
WET-DE04-A1050 | [10 empty] | 2016-05-16: 2018-11-06; 2016-05-16: 2018-11-06; 2016-05-16: 2018-11-06; 2016-05-16: 2018-11-06; 2016-05-16: 2018-11-06; 2016-05-16: 2018-11-06; 2016-05-16: 2018-11-06
WET-DE04-A1040 | [38 empty] | 2018-07-28 | 2018-07-28 | 2018-07-28 | 2018-07-28 | 2018-07-28 | 2018-07-28 | 2018-07-28 | 2018-07-28 | 2018-07-28
WET-DE04-A1030 | [36 empty] | 2018-07-27 | 2018-07-27 | 2018-07-27 | 2018-07-27 | 2018-07-27 | 2018-07-27 | 2018-07-27 | 2018-07-27 | 2018-07-27 | 2018-07-27 | 2018-07-27
WET-DE04-A1020 | [36 empty] | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21
WET-DE04-A1010 | [32 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
WET-DE04-A1000 | [30 empty] | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27
WET-DE03-A1020 | [30 empty] | 2017-11-30 | 2017-11-30 | 2017-11-30 | 2017-11-30 | 2017-11-30 | 2017-11-30 | 2017-11-30 | 2017-11-30 | 2017-11-30 | 2017-11-30 | 2017-11-30 | 2017-11-30 | 2017-11-30 | 2017-11-30 | 2017-11-30 | 2017-11-30 | 2017-11-30
WET-DE03-A1010 | [30 empty] | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27
WET-DE03-A1000 | [20 empty] | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13
WET-DE02-A1100 | [24 empty] | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10
WET-DE02-A1090 | [24 empty] | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09
WET-DE02-A1080 | [24 empty] | 2017-07-08 | 2017-07-08 | 2017-07-08 | 2017-07-08 | 2017-07-08 | 2017-07-08 | 2017-07-08 | 2017-07-08 | 2017-07-08 | 2017-07-08 | 2017-07-08 | 2017-07-08 | 2017-07-08 | 2017-07-08 | 2017-07-08 | 2017-07-08 | 2017-07-08 | 2017-07-08 | 2017-07-08 | 2017-07-08 | 2017-07-08 | 2017-07-08 | 2017-07-08
WET-DE02-A1070 | [22 empty] | 2017-05-24 | 2017-05-24 | 2017-05-24 | 2017-05-24 | 2017-05-24 | 2017-05-24 | 2017-05-24 | 2017-05-24 | 2017-05-24 | 2017-05-24 | 2017-05-24 | 2017-05-24 | 2017-05-24 | 2017-05-24 | 2017-05-24 | 2017-05-24 | 2017-05-24 | 2017-05-24 | 2017-05-24 | 2017-05-24 | 2017-05-24 | 2017-05-24 | 2017-05-24 | 2017-05-24 | 2017-05-24
WET-DE02-A1060 | [22 empty] | 2017-05-05 | 2017-05-05 | 2017-05-05 | 2017-05-05 | 2017-05-05 | 2017-05-05 | 2017-05-05 | 2017-05-05 | 2017-05-05 | 2017-05-05 | 2017-05-05 | 2017-05-05 | 2017-05-05 | 2017-05-05 | 2017-05-05 | 2017-05-05 | 2017-05-05 | 2017-05-05 | 2017-05-05 | 2017-05-05 | 2017-05-05 | 2017-05-05 | 2017-05-05 | 2017-05-05 | 2017-05-05
WET-DE02-A1050 | [22 empty] | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15
WET-DE02-A1040 | [22 empty] | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25
WET-DE02-A1030 | [20 empty] | 2017-03-24 |  | 2017-03-24 | 2017-03-24 | 2017-03-24 | 2017-03-24 | 2017-03-24 | 2017-03-24 | 2017-03-24 | 2017-03-24 | 2017-03-24 | 2017-03-24 | 2017-03-24 | 2017-03-24 | 2017-03-24 | 2017-03-24 | 2017-03-24 | 2017-03-24 | 2017-03-24 | 2017-03-24 | 2017-03-24 | 2017-03-24 | 2017-03-24 | 2017-03-24 | 2017-03-24 | 2017-03-24 | 2017-03-24
WET-DE02-A1020 | [20 empty] | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23
WET-DE02-A1010 | [20 empty] | 2017-03-19 | 2017-03-19 | 2017-03-19 | 2017-03-19 | 2017-03-19 | 2017-03-19 | 2017-03-19 | 2017-03-19 | 2017-03-19 | 2017-03-19 | 2017-03-19 | 2017-03-19 | 2017-03-19 | 2017-03-19 | 2017-03-19 | 2017-03-19 | 2017-03-19 | 2017-03-19 | 2017-03-19 | 2017-03-19 | 2017-03-19 | 2017-03-19 | 2017-03-19 | 2017-03-19 | 2017-03-19 | 2017-03-19 | 2017-03-19
WET-DE02-A1000 | [8 empty] | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18
WET-DE01-A1090 | [8 empty] | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17
WET-DE01-A1080 | [8 empty] | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17
WET-DE01-A1070 | [8 empty] | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17
WET-DE01-A1060 | [8 empty] | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17
WET-DE01-A1050 | [18 empty] | 2016-12-03 | 2016-12-03 | 2016-12-03 | 2016-12-03 | 2016-12-03 | 2016-12-03 | 2016-12-03 | 2016-12-03 | 2016-12-03 | 2016-12-03 | 2016-12-03 | 2016-12-03 | 2016-12-03 | 2016-12-03 | 2016-12-03 | 2016-12-03 | 2016-12-03 | 2016-12-03 | 2016-12-03 | 2016-12-03 | 2016-12-03 | 2016-12-03 | 2016-12-03 | 2016-12-03 | 2016-12-03 | 2016-12-03 | 2016-12-03 | 2016-12-03 | 2016-12-03
WET-DE01-A1040 | [18 empty] | 2016-12-02 | 2016-12-02 | 2016-12-02 | 2016-12-02 | 2016-12-02 | 2016-12-02 | 2016-12-02 | 2016-12-02 | 2016-12-02 | 2016-12-02 | 2016-12-02 | 2016-12-02 | 2016-12-02 | 2016-12-02 | 2016-12-02 | 2016-12-02 | 2016-12-02 | 2016-12-02 | 2016-12-02 | 2016-12-02 | 2016-12-02 | 2016-12-02 | 2016-12-02 | 2016-12-02 | 2016-12-02 | 2016-12-02 | 2016-12-02 | 2016-12-02 | 2016-12-02
WET-DE01-A1030 | [18 empty] | 2016-12-01 | 2016-12-01 | 2016-12-01 | 2016-12-01 | 2016-12-01 | 2016-12-01 | 2016-12-01 | 2016-12-01 | 2016-12-01 | 2016-12-01 | 2016-12-01 | 2016-12-01 | 2016-12-01 | 2016-12-01 | 2016-12-01 | 2016-12-01 | 2016-12-01 | 2016-12-01 | 2016-12-01 | 2016-12-01 | 2016-12-01 | 2016-12-01 | 2016-12-01 | 2016-12-01 | 2016-12-01 | 2016-12-01 | 2016-12-01 | 2016-12-01 | 2016-12-01
WET-DE01-A1020 | [18 empty] | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30
WET-DE01-A1010 | [14 empty] | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23
WET-DE01-A1000 | [10 empty] | 2016-05-15 | 2016-05-15 | 2016-05-15 | 2016-05-15 | 2016-05-15 | 2016-05-15 | 2016-05-15 | 2016-05-15 | 2016-05-15 | 2016-05-15 | 2016-05-15 | 2016-05-15 | 2016-05-15 | 2016-05-15 | 2016-05-15 | 2016-05-15 | 2016-05-15 | 2016-05-15 | 2016-05-15 | 2016-05-15 | 2016-05-15 | 2016-05-15 | 2016-05-15 | 2016-05-15 | 2016-05-15 | 2016-05-15 | 2016-05-15 | 2016-05-15 | 2016-05-15 | 2016-05-15 | 2016-05-15 | 2016-05-15 | 2016-05-15 | 2016-05-15 | 2016-05-15 | 2016-05-15 | 2016-05-15
TEL-DE09-1002 | [24 empty] | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31
TEL-DE09-1001 | [24 empty] | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24
TEL-DE09-1000 | [24 empty] | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24
PRO-ELE-DE02-1026 | [30 empty] | 2017-12-20 | 2017-12-20 | 2017-12-20 | 2017-12-20 | 2017-12-20 | 2017-12-20 | 2017-12-20 | 2017-12-20 | 2017-12-20 | 2017-12-20 | 2017-12-20 | 2017-12-20 | 2017-12-20 | 2017-12-20 | 2017-12-20 | 2017-12-20 | 2017-12-20
PRO-ELE-DE02-1021 | [30 empty] | 2017-12-20 | 2017-12-20 | 2017-12-20 | 2017-12-20 | 2017-12-20 | 2017-12-20 | 2017-12-20 | 2017-12-20 | 2017-12-20 | 2017-12-20 | 2017-12-20 | 2017-12-20 | 2017-12-20 | 2017-12-20 | 2017-12-20 | 2017-12-20 | 2017-12-20
PRO-ELE-DE02-1020 | [30 empty] | 2017-12-20: 2018-12-23; 2017-12-20: 2018-12-23; 2017-12-20: 2018-12-23; 2017-12-20: 2018-12-23; 2017-12-20: 2018-12-23
PRO-ELE-DE02-1019 | [30 empty] | 2017-12-20: 2018-12-23; 2017-12-20: 2018-12-23; 2017-12-20: 2018-12-23; 2017-12-20: 2018-12-23; 2017-12-20: 2018-12-23
PRO-ELE-DE02-1017 | [32 empty] | 2018-03-11 | 2018-03-11 | 2018-03-11 | 2018-03-11 | 2018-03-11 | 2018-03-11 | 2018-03-11 | 2018-03-11 | 2018-03-11 | 2018-03-11 | 2018-03-11 | 2018-03-11 | 2018-03-11 | 2018-03-11 | 2018-03-11
PRO-ELE-DE02-1016 | [32 empty] | 2018-03-11 | 2018-03-11 | 2018-03-11 | 2018-03-11 | 2018-03-11 | 2018-03-11 | 2018-03-11 | 2018-03-11 | 2018-03-11 | 2018-03-11 | 2018-03-11 | 2018-03-11 | 2018-03-11 | 2018-03-11 | 2018-03-11
PRO-ELE-DE02-1014 | [32 empty] | 2018-02-13 | 2018-02-13 | 2018-02-13 | 2018-02-13 | 2018-02-13 | 2018-02-13 | 2018-02-13 | 2018-02-13 | 2018-02-13 | 2018-02-13 | 2018-02-13 | 2018-02-13 | 2018-02-13 | 2018-02-13 | 2018-02-13
PRO-ELE-DE02-1013 | [32 empty] | 2018-03-06 | 2018-03-06 | 2018-03-06 | 2018-03-06 | 2018-03-06 | 2018-03-06 | 2018-03-06 | 2018-03-06 | 2018-03-06 | 2018-03-06 | 2018-03-06 | 2018-03-06 | 2018-03-06 | 2018-03-06 | 2018-03-06
PRO-ELE-DE02-1011 | [38 empty] | 2018-09-17 | 2018-09-17 | 2018-09-17 | 2018-09-17 | 2018-09-17 | 2018-09-17 | 2018-09-17 | 2018-09-17 | 2018-09-17
PRO-ELE-DE02-1010 | [30 empty] | 2017-12-11 | 2017-12-11 | 2017-12-11 | 2017-12-11 | 2017-12-11 | 2017-12-11 | 2017-12-11 | 2017-12-11 | 2017-12-11 | 2017-12-11 | 2017-12-11 | 2017-12-11 | 2017-12-11 | 2017-12-11 | 2017-12-11 | 2017-12-11 | 2017-12-11
PRO-ELE-DE02-1008 | [24 empty] | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27
PRO-ELE-DE02-1007 | [24 empty] | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27
PRO-ELE-DE02-1005 | [22 empty] | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15
PRO-ELE-DE02-1004 | [22 empty] | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09
PRO-ELE-DE02-1002 | [26 empty] | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18
PRO-ELE-CP-DE01-1001 | [22 empty] | 2017-04-23 | 2017-04-23 | 2017-04-23 | 2017-04-23 | 2017-04-23 | 2017-04-23 | 2017-04-23 | 2017-04-23 | 2017-04-23 | 2017-04-23 | 2017-04-23 | 2017-04-23 | 2017-04-23 | 2017-04-23 | 2017-04-23 | 2017-04-23 | 2017-04-23 | 2017-04-23 | 2017-04-23 | 2017-04-23 | 2017-04-23 | 2017-04-23 | 2017-04-23 | 2017-04-23 | 2017-04-23
PRO-ELE-CP-DE01-1000 | [38 empty] | 2018-09-18 | 2018-09-18 | 2018-09-18 | 2018-09-18 | 2018-09-18 | 2018-09-18 | 2018-09-18 | 2018-09-18 | 2018-09-18
PRO-E&I-DE03-1001 | [32 empty] | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27
PRO-E&I-DE03-1000 | [32 empty] | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27
PRO-DE01-1167 | [28 empty] | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22
PRO-DE01-1165 | [28 empty] | 2017-10-31 | 2017-10-31 | 2017-10-31 | 2017-10-31 | 2017-10-31 | 2017-10-31 | 2017-10-31 | 2017-10-31 | 2017-10-31 | 2017-10-31 | 2017-10-31 | 2017-10-31 | 2017-10-31 | 2017-10-31 | 2017-10-31 | 2017-10-31 | 2017-10-31 | 2017-10-31 | 2017-10-31
PRO-DE01-1163 | [28 empty] | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05
PRO-DE01-1112 | [26 empty] | 2017-09-09 | 2017-09-09 | 2017-09-09 | 2017-09-09 | 2017-09-09 | 2017-09-09 | 2017-09-09 | 2017-09-09 | 2017-09-09 | 2017-09-09 | 2017-09-09 | 2017-09-09 | 2017-09-09 | 2017-09-09 | 2017-09-09 | 2017-09-09 | 2017-09-09 | 2017-09-09 | 2017-09-09 | 2017-09-09 | 2017-09-09
PRO-DE01-1097 | [28 empty] | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22
PRO-DE01-1088 | [24 empty] | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30
PRO-DE01-1076 | [24 empty] | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01
PRO-DE01-1075 | [34 empty] | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07
PRO-DE01-1074 | [34 empty] | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07
PRO-DE01-1022 | [22 empty] | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18
PRO-DE01-1019 | [22 empty] | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16
PRO-DE01-1017 | [32 empty] | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28
PRO-DE01-1016 | [32 empty] | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28
PRO-DE01-1015 | [32 empty] | 2018-03-03 | 2018-03-03 | 2018-03-03 | 2018-03-03 | 2018-03-03 | 2018-03-03 | 2018-03-03 | 2018-03-03 | 2018-03-03 | 2018-03-03 | 2018-03-03 | 2018-03-03 | 2018-03-03 | 2018-03-03 | 2018-03-03
PRO-DE01-1014 | [32 empty] | 2018-03-03 | 2018-03-03 | 2018-03-03 | 2018-03-03 | 2018-03-03 | 2018-03-03 | 2018-03-03 | 2018-03-03 | 2018-03-03 | 2018-03-03 | 2018-03-03 | 2018-03-03 | 2018-03-03 | 2018-03-03 | 2018-03-03
PRO-DE01-1013 | [34 empty] | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18
PRO-DE01-1012 | [34 empty] | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18
PRO-DE01-1011 | [34 empty] | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07
PRO-DE01-1010 | [34 empty] | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07
PRO-DE01-1009 | [34 empty] | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07
PRO-DE01-1008 | [34 empty] | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07
PRO-DE01-1007 | [34 empty] | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15
PRO-DE01-1006 | [28 empty] | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16
PRO-DE01-1005 | [28 empty] | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16
PRO-DE01-1004 | [28 empty] | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16
PRO-DE01-1003 | [28 empty] | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02
PRO-DE01-1002 | [28 empty] | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02
PRO-DE01-1001 | [28 empty] | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02
PRO-DE01-1000 | [28 empty] | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02
PR0-TEL-DE05-1001 | [32 empty] | 2018-02-06 | 2018-02-06 | 2018-02-06 | 2018-02-06 | 2018-02-06 | 2018-02-06 | 2018-02-06 | 2018-02-06 | 2018-02-06 | 2018-02-06 | 2018-02-06 | 2018-02-06 | 2018-02-06 | 2018-02-06 | 2018-02-06
PR0-INSTR-DE04-1027 | [38 empty] | 2018-08-05 | 2018-08-05 | 2018-08-05 | 2018-08-05 | 2018-08-05 | 2018-08-05 | 2018-08-05 | 2018-08-05 | 2018-08-05
PR0-INSTR-DE04-1026 | [38 empty] | 2018-08-05 | 2018-08-05 | 2018-08-05 | 2018-08-05 | 2018-08-05 | 2018-08-05 | 2018-08-05 | 2018-08-05 | 2018-08-05
PR0-INSTR-DE04-1025 | [32 empty] | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27
PR0-INSTR-DE04-1023 | [34 empty] | 2018-04-12 | 2018-04-12 | 2018-04-12 | 2018-04-12 | 2018-04-12 | 2018-04-12 | 2018-04-12 | 2018-04-12 | 2018-04-12 | 2018-04-12 | 2018-04-12 | 2018-04-12 | 2018-04-12
PR0-INSTR-DE04-1019 | [30 empty] | 2018-01-07 | 2018-01-07 | 2018-01-07 | 2018-01-07 | 2018-01-07 | 2018-01-07 | 2018-01-07 | 2018-01-07 | 2018-01-07 | 2018-01-07 | 2018-01-07 | 2018-01-07 | 2018-01-07 | 2018-01-07 | 2018-01-07 | 2018-01-07 | 2018-01-07
PR0-INSTR-DE04-1018 | [36 empty] | 2018-07-19 | 2018-07-19 | 2018-07-19 | 2018-07-19 | 2018-07-19 | 2018-07-19 | 2018-07-19 | 2018-07-19 | 2018-07-19 | 2018-07-19 | 2018-07-19
PR0-INSTR-DE04-1013 | [38 empty] | 2018-08-11 | 2018-08-11 | 2018-08-11 | 2018-08-11 | 2018-08-11 | 2018-08-11 | 2018-08-11 | 2018-08-11 | 2018-08-11
PR0-INSTR-DE04-1006 | [38 empty] | 2018-09-25 | 2018-09-25 | 2018-09-25 | 2018-09-25 | 2018-09-25 | 2018-09-25 | 2018-09-25 | 2018-09-25 | 2018-09-25
PR0-INSTR-DE04-1003 | [36 empty] | 2018-07-08 | 2018-07-08 | 2018-07-08 | 2018-07-08 | 2018-07-08 | 2018-07-08 | 2018-07-08 | 2018-07-08 | 2018-07-08 | 2018-07-08 | 2018-07-08
PMT-DE04-A1000 | [10 empty] | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13
PMT-DE03-A1010 | [26 empty] | 2017-08-04 | 2017-08-04 | 2017-08-04 | 2017-08-04 | 2017-08-04 | 2017-08-04 | 2017-08-04 | 2017-08-04 | 2017-08-04 | 2017-08-04 | 2017-08-04 | 2017-08-04 | 2017-08-04 | 2017-08-04 | 2017-08-04 | 2017-08-04 | 2017-08-04 | 2017-08-04 | 2017-08-04 | 2017-08-04 | 2017-08-04
PMT-DE03-A1000 | [20 empty] | 2017-02-21 | 2017-02-21 | 2017-02-21 | 2017-02-21 | 2017-02-21 | 2017-02-21 | 2017-02-21 | 2017-02-21 | 2017-02-21 | 2017-02-21 | 2017-02-21 | 2017-02-21 | 2017-02-21 | 2017-02-21 | 2017-02-21 | 2017-02-21 | 2017-02-21 | 2017-02-21 | 2017-02-21 | 2017-02-21 | 2017-02-21 | 2017-02-21 | 2017-02-21 | 2017-02-21 | 2017-02-21 | 2017-02-21 | 2017-02-21
PMT-DE02-A1000 | [12 empty] | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21
PMT-DE01-A1000 | [10 empty] | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17
PIP-DE09-1003 | [24 empty] | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01
PIP-DE09-1002 | [28 empty] | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20
PIP-DE09-1001 | [28 empty] | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18
PIP-CIV-DE02-1014 | [28 empty] | 2017-10-18: 2018-12-24; 2017-10-18: 2018-12-24; 2017-10-18: 2018-12-24; 2017-10-18: 2018-12-24; 2017-10-18: 2018-12-24
PIP-CIV-DE02-1008 | [22 empty] | 2017-05-25 | 2017-05-25 | 2017-05-25 | 2017-05-25 | 2017-05-25 | 2017-05-25 | 2017-05-25 | 2017-05-25 | 2017-05-25 | 2017-05-25 | 2017-05-25 | 2017-05-25 | 2017-05-25 | 2017-05-25 | 2017-05-25 | 2017-05-25 | 2017-05-25 | 2017-05-25 | 2017-05-25 | 2017-05-25 | 2017-05-25 | 2017-05-25 | 2017-05-25 | 2017-05-25 | 2017-05-25
PIP-CIV-DE02-1007 | [22 empty] | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20
PIP-CIV-DE02-1006 | [22 empty] | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20
PIP-CIV-DE02-1005 | [22 empty] | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20
PIP-CIV-DE02-1004 | [22 empty] | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20
PIP-CIV-DE02-1003 | [22 empty] | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20
PIP-CIV-DE02-1002 | [22 empty] | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20
PIP-CIV-DE02-1001 | [22 empty] | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20
PIP-CIV-DE02-1000 | [26 empty] | 2017-08-19 | 2017-08-19 | 2017-08-19 | 2017-08-19 | 2017-08-19 | 2017-08-19 | 2017-08-19 | 2017-08-19 | 2017-08-19 | 2017-08-19 | 2017-08-19 | 2017-08-19 | 2017-08-19 | 2017-08-19 | 2017-08-19 | 2017-08-19 | 2017-08-19 | 2017-08-19 | 2017-08-19 | 2017-08-19 | 2017-08-19
PIP-CIV-DE01-1001 | [26 empty] | 2017-08-19: 2018-12-24; 2017-08-19: 2018-12-24; 2017-08-19: 2018-12-24; 2017-08-19: 2018-12-24; 2017-08-19: 2018-12-24
PIP-CIV-DE01-1000 | [18 empty] | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29
INST-DE08-1002 | [24 empty] | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01
INST-DE08-1001 | [28 empty] | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17
INST-DE08-1000 | [24 empty] | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01
GEN-DE02-A1000 | [8 empty] | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24
GEN-DE01-A1000 | time axis 2015-10-20 to 2015-10-20
EOD-DE02-A1000 | [10 empty] | 2016-04-28 | 2016-04-28 | 2016-04-28 | 2016-04-28 | 2016-04-28 | 2016-04-28 | 2016-04-28 | 2016-04-28 | 2016-04-28 | 2016-04-28 | 2016-04-28 | 2016-04-28 | 2016-04-28 | 2016-04-28 | 2016-04-28 | 2016-04-28 | 2016-04-28 | 2016-04-28 | 2016-04-28 | 2016-04-28 | 2016-04-28 | 2016-04-28 | 2016-04-28 | 2016-04-28 | 2016-04-28 | 2016-04-28 | 2016-04-28 | 2016-04-28 | 2016-04-28 | 2016-04-28 | 2016-04-28 | 2016-04-28 | 2016-04-28 | 2016-04-28 | 2016-04-28 | 2016-04-28 | 2016-04-28
EOD-DE01-A1040 | [8 empty] | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17
EOD-DE01-A1030 | [8 empty] | 2016-02-07 | 2016-02-07 | 2016-02-07 | 2016-02-07 | 2016-02-07 | 2016-02-07 | 2016-02-07 | 2016-02-07 | 2016-02-07 | 2016-02-07 | 2016-02-07 | 2016-02-07 | 2016-02-07 | 2016-02-07 | 2016-02-07 | 2016-02-07 | 2016-02-07 | 2016-02-07 | 2016-02-07 | 2016-02-07 | 2016-02-07 | 2016-02-07 | 2016-02-07 | 2016-02-07 | 2016-02-07 | 2016-02-07 | 2016-02-07 | 2016-02-07 | 2016-02-07 | 2016-02-07 | 2016-02-07 | 2016-02-07 | 2016-02-07 | 2016-02-07 | 2016-02-07 | 2016-02-07 | 2016-02-07 | 2016-02-07 | 2016-02-07
EOD-DE01-A1020 | [8 empty] | 2016-02-05 | 2016-02-05 | 2016-02-05 | 2016-02-05 | 2016-02-05 | 2016-02-05 | 2016-02-05 | 2016-02-05 | 2016-02-05 | 2016-02-05 | 2016-02-05 | 2016-02-05 | 2016-02-05 | 2016-02-05 | 2016-02-05 | 2016-02-05 | 2016-02-05 | 2016-02-05 | 2016-02-05 | 2016-02-05 | 2016-02-05 | 2016-02-05 | 2016-02-05 | 2016-02-05 | 2016-02-05 | 2016-02-05 | 2016-02-05 | 2016-02-05 | 2016-02-05 | 2016-02-05 | 2016-02-05 | 2016-02-05 | 2016-02-05 | 2016-02-05 | 2016-02-05 | 2016-02-05 | 2016-02-05 | 2016-02-05 | 2016-02-05
EOD-DE01-A1010 | [8 empty] | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30
EOD-DE01-A1000 | [6 empty] | 2016-01-10 | 2016-01-10 | 2016-01-10 | 2016-01-10 | 2016-01-10 | 2016-01-10 | 2016-01-10 | 2016-01-10 | 2016-01-10 | 2016-01-10 | 2016-01-10 | 2016-01-10 | 2016-01-10 | 2016-01-10 | 2016-01-10 | 2016-01-10 | 2016-01-10 | 2016-01-10 | 2016-01-10 | 2016-01-10 | 2016-01-10 | 2016-01-10 | 2016-01-10 | 2016-01-10 | 2016-01-10 | 2016-01-10 | 2016-01-10 | 2016-01-10 | 2016-01-10 | 2016-01-10 | 2016-01-10 | 2016-01-10 | 2016-01-10 | 2016-01-10 | 2016-01-10 | 2016-01-10 | 2016-01-10 | 2016-01-10 | 2016-01-10 | 2016-01-10 | 2016-01-10
ELC-STF-DE05-1002 | [28 empty] | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18
ELC-STF-DE05-1001 | [24 empty] | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07
ELC-SBTN-DE06-1011 | [26 empty] | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19
ELC-SBTN-DE06-1010 | [24 empty] | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24
ELC-SBTN-DE06-1009 | [26 empty] | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19
ELC-SBTN-DE06-1008 | [24 empty] | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24
ELC-SBTN-DE06-1007 | [26 empty] | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19
ELC-SBTN-DE06-1006 | [28 empty] | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30
ELC-SBTN-DE06-1005 | [28 empty] | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17
ELC-SBTN-DE06-1004 | [26 empty] | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20
ELC-SBTN-DE06-1003 | [28 empty] | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11
ELC-SBTN-DE06-1002 | [22 empty] | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04
ELC-SBTN-DE06-1001 | [26 empty] | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20
ELC-SBTN-DE06-1000 | [28 empty] | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11
ELC-MG1-DE07-1000 | [24 empty] | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07
ELC-COO-DE04-1003 | [24 empty] | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31
ELC-COO-DE04-1002 | [28 empty] | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17
ELC-COO-DE04-1001 | [22 empty] | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04
ELC-COO-DE04-1000 | [24 empty] | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31
EI&T-S303-DE07-1010 | [24 empty] | 2017-06-13 | 2017-06-13 | 2017-06-13 | 2017-06-13 | 2017-06-13 | 2017-06-13 | 2017-06-13 | 2017-06-13 | 2017-06-13 | 2017-06-13 | 2017-06-13 | 2017-06-13 | 2017-06-13 | 2017-06-13 | 2017-06-13 | 2017-06-13 | 2017-06-13 | 2017-06-13 | 2017-06-13 | 2017-06-13 | 2017-06-13 | 2017-06-13 | 2017-06-13
EI&T-S303-DE07-1000 | [28 empty] | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15
EI&T-S302-DE06-1010 | [36 empty] | 2018-07-12 | 2018-07-12 | 2018-07-12 | 2018-07-12 | 2018-07-12 | 2018-07-12 | 2018-07-12 | 2018-07-12 | 2018-07-12 | 2018-07-12 | 2018-07-12
EI&T-S302-DE06-1000 | [30 empty] | 2018-01-08 | 2018-01-08 | 2018-01-08 | 2018-01-08 | 2018-01-08 | 2018-01-08 | 2018-01-08 | 2018-01-08 | 2018-01-08 | 2018-01-08 | 2018-01-08 | 2018-01-08 | 2018-01-08 | 2018-01-08 | 2018-01-08 | 2018-01-08 | 2018-01-08
EI&T-S301-DE05-1010 | [36 empty] | 2018-06-25 | 2018-06-25 | 2018-06-25 | 2018-06-25 | 2018-06-25 | 2018-06-25 | 2018-06-25 | 2018-06-25 | 2018-06-25 | 2018-06-25 | 2018-06-25
EI&T-S301-DE05-1000 | [30 empty] | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01
EI&T-COCC-DE04-1020 | [36 empty] | 2018-07-23 | 2018-07-23 | 2018-07-23 | 2018-07-23 | 2018-07-23 | 2018-07-23 | 2018-07-23 | 2018-07-23 | 2018-07-23 | 2018-07-23 | 2018-07-23
EI&T-COCC-DE04-1010 | [30 empty] | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20
EI&T-COCC-DE04-1000 | [32 empty] | 2018-03-06 | 2018-03-06 | 2018-03-06 | 2018-03-06 | 2018-03-06 | 2018-03-06 | 2018-03-06 | 2018-03-06 | 2018-03-06 | 2018-03-06 | 2018-03-06 | 2018-03-06 | 2018-03-06 | 2018-03-06 | 2018-03-06
DW-TEL-DE05-1000 | [24 empty] | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19
DW-SS-DE02-1019 | [28 empty] | 2017-10-10 | 2017-10-10 | 2017-10-10 | 2017-10-10 | 2017-10-10 | 2017-10-10 | 2017-10-10 | 2017-10-10 | 2017-10-10 | 2017-10-10 | 2017-10-10 | 2017-10-10 | 2017-10-10 | 2017-10-10 | 2017-10-10 | 2017-10-10 | 2017-10-10 | 2017-10-10 | 2017-10-10
DW-SS-DE02-1018 | [34 empty] | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05
DW-SS-DE02-1017 | [22 empty] | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04
DW-SS-DE02-1016 | [24 empty] | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20
DW-SS-DE02-1015 | [24 empty] | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31
DW-SS-DE02-1014 | [20 empty] | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23
DW-SS-DE02-1013 | [20 empty] | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23
DW-SS-DE02-1012 | [26 empty] | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19
DW-SS-DE02-1011 | [24 empty] | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20
DW-SS-DE02-1010 | [24 empty] | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20
DW-SS-DE02-1009 | [22 empty] | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18
DW-SS-DE02-1008 | [22 empty] | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18
DW-SS-DE02-1007 | [18 empty] | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05
DW-SS-DE02-1006 | [24 empty] | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20
DW-SS-DE02-1005 | [24 empty] | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20
DW-SS-DE02-1004 | [20 empty] | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12
DW-SS-DE02-1003 | [20 empty] | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12
DW-SS-DE02-1002 | [34 empty] | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05
DW-SS-DE02-1001 | [24 empty] | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20
DW-SS-DE02-1000 | [24 empty] | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20
DW-INST-DE04-1002 | [24 empty] | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01
DW-INST-DE04-1001 | [24 empty] | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01
DW-INST-DE04-1000 | [22 empty] | 2017-05-17 | 2017-05-17 | 2017-05-17 | 2017-05-17 | 2017-05-17 | 2017-05-17 | 2017-05-17 | 2017-05-17 | 2017-05-17 | 2017-05-17 | 2017-05-17 | 2017-05-17 | 2017-05-17 | 2017-05-17 | 2017-05-17 | 2017-05-17 | 2017-05-17 | 2017-05-17 | 2017-05-17 | 2017-05-17 | 2017-05-17 | 2017-05-17 | 2017-05-17 | 2017-05-17 | 2017-05-17
DW-EDG-DE03-1016 | [20 empty] | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23
DW-EDG-DE03-1015 | [20 empty] | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23
DW-EDG-DE03-1014 | [26 empty] | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19
DW-EDG-DE03-1013 | [24 empty] | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20
DW-EDG-DE03-1012 | [22 empty] | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18
DW-EDG-DE03-1011 | [22 empty] | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18
DW-EDG-DE03-1010 | [26 empty] | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19
DW-EDG-DE03-1009 | [24 empty] | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20
DW-EDG-DE03-1008 | [28 empty] | 2017-10-10 | 2017-10-10 | 2017-10-10 | 2017-10-10 | 2017-10-10 | 2017-10-10 | 2017-10-10 | 2017-10-10 | 2017-10-10 | 2017-10-10 | 2017-10-10 | 2017-10-10 | 2017-10-10 | 2017-10-10 | 2017-10-10 | 2017-10-10 | 2017-10-10 | 2017-10-10 | 2017-10-10
DW-EDG-DE03-1007 | [34 empty] | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05
DW-EDG-DE03-1006 | [26 empty] | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19
DW-EDG-DE03-1005 | [24 empty] | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20
DW-EDG-DE03-1004 | [20 empty] | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12
DW-EDG-DE03-1003 | [20 empty] | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12
DW-EDG-DE03-1002 | [26 empty] | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19
DW-EDG-DE03-1001 | [34 empty] | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05
DW-EDG-DE03-1000 | [24 empty] | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24
DW-CP-DE06-1001 | [14 empty] | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31
DW-CP-DE06-1000 | [20 empty] | 2017-03-19 | 2017-03-19 | 2017-03-19 | 2017-03-19 | 2017-03-19 | 2017-03-19 | 2017-03-19 | 2017-03-19 | 2017-03-19 | 2017-03-19 | 2017-03-19 | 2017-03-19 | 2017-03-19 | 2017-03-19 | 2017-03-19 | 2017-03-19 | 2017-03-19 | 2017-03-19 | 2017-03-19 | 2017-03-19 | 2017-03-19 | 2017-03-19 | 2017-03-19 | 2017-03-19 | 2017-03-19 | 2017-03-19 | 2017-03-19
DW-COCC-DE01-1004 | [20 empty] | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02
DW-COCC-DE01-1003 | [26 empty] | 2017-08-30 | 2017-08-30 | 2017-08-30 | 2017-08-30 | 2017-08-30 | 2017-08-30 | 2017-08-30 | 2017-08-30 | 2017-08-30 | 2017-08-30 | 2017-08-30 | 2017-08-30 | 2017-08-30 | 2017-08-30 | 2017-08-30 | 2017-08-30 | 2017-08-30 | 2017-08-30 | 2017-08-30 | 2017-08-30 | 2017-08-30
DW-COCC-DE01-1002 | [34 empty] | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05
DW-COCC-DE01-1001 | [26 empty] | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19
DW-COCC-DE01-1000 | [22 empty] | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04
DE36-1040 | [28 empty] | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22
DE36-1030 | [36 empty] | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21
DE36-1020 | [36 empty] | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21
DE36-1010 | [36 empty] | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21
DE36-1000 | [36 empty] | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21
DE35-1000 | [22 empty] | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12
DE34-1060 | [22 empty] | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12
DE34-1050 | [36 empty] | 2018-06-18 | 2018-06-18 | 2018-06-18 | 2018-06-18 | 2018-06-18 | 2018-06-18 | 2018-06-18 | 2018-06-18 | 2018-06-18 | 2018-06-18 | 2018-06-18
DE34-1040 | [36 empty] | 2018-06-18 | 2018-06-18 | 2018-06-18 | 2018-06-18 | 2018-06-18 | 2018-06-18 | 2018-06-18 | 2018-06-18 | 2018-06-18 | 2018-06-18 | 2018-06-18
DE34-1030 | [36 empty] | 2018-06-18 | 2018-06-18 | 2018-06-18 | 2018-06-18 | 2018-06-18 | 2018-06-18 | 2018-06-18 | 2018-06-18 | 2018-06-18 | 2018-06-18 | 2018-06-18
DE34-1020 | [36 empty] | 2018-06-18 | 2018-06-18 | 2018-06-18 | 2018-06-18 | 2018-06-18 | 2018-06-18 | 2018-06-18 | 2018-06-18 | 2018-06-18 | 2018-06-18 | 2018-06-18
DE34-1010 | [36 empty] | 2018-06-18 | 2018-06-18 | 2018-06-18 | 2018-06-18 | 2018-06-18 | 2018-06-18 | 2018-06-18 | 2018-06-18 | 2018-06-18 | 2018-06-18 | 2018-06-18
DE34-1000 | [36 empty] | 2018-06-12 | 2018-06-12 | 2018-06-12 | 2018-06-12 | 2018-06-12 | 2018-06-12 | 2018-06-12 | 2018-06-12 | 2018-06-12 | 2018-06-12 | 2018-06-12
DE33-1010 | [36 empty] | 2018-06-12: 2019-04-10
DE33-1000 | [36 empty] | 2018-06-12: 2019-04-10
DE32-1020 | [36 empty] | 2018-06-12: 2019-02-15; 2018-06-12: 2019-02-15; 2018-06-12: 2019-02-15
DE32-1010 | [36 empty] | 2018-06-12: 2019-02-12; 2018-06-12: 2019-02-12; 2018-06-12: 2019-02-12
DE32-1000 | [36 empty] | 2018-06-12: 2019-02-06; 2018-06-12: 2019-02-06; 2018-06-12: 2019-02-06
DE31-1030 | [36 empty] | 2018-06-12: 2019-01-18; 2018-06-12: 2019-01-18; 2018-06-12: 2019-01-18; 2018-06-12: 2019-01-18; 2018-06-12: 2019-01-18
DE31-1020 | [36 empty] | 2018-06-12: 2019-01-18; 2018-06-12: 2019-01-18; 2018-06-12: 2019-01-18; 2018-06-12: 2019-01-18; 2018-06-12: 2019-01-18
DE31-1010 | [36 empty] | 2018-06-12: 2019-01-17; 2018-06-12: 2019-01-17; 2018-06-12: 2019-01-17; 2018-06-12: 2019-01-17; 2018-06-12: 2019-01-17
DE31-1000 | [36 empty] | 2018-06-12: 2019-01-16; 2018-06-12: 2019-01-16; 2018-06-12: 2019-01-16; 2018-06-12: 2019-01-16; 2018-06-12: 2019-01-16
DE30-1010 | [34 empty] | 2018-05-03 | 2018-05-03 | 2018-05-03 | 2018-05-03 | 2018-05-03 | 2018-05-03 | 2018-05-03 | 2018-05-03 | 2018-05-03 | 2018-05-03 | 2018-05-03 | 2018-05-03 | 2018-05-03
DE30-1000 | [34 empty] | 2018-05-03 | 2018-05-03 | 2018-05-03 | 2018-05-03 | 2018-05-03 | 2018-05-03 | 2018-05-03 | 2018-05-03 | 2018-05-03 | 2018-05-03 | 2018-05-03 | 2018-05-03 | 2018-05-03
DE29-1000 | [34 empty] | 2018-05-03: 2018-10-22; 2018-05-03: 2018-10-22; 2018-05-03: 2018-10-22; 2018-05-03: 2018-10-22; 2018-05-03: 2018-10-22; 2018-05-03: 2018-10-22; 2018-05-03: 2018-10-22
DE28-1000 | [34 empty] | 2018-05-03: 2019-01-27; 2018-05-03: 2019-01-27; 2018-05-03: 2019-01-27
DE27-1000 | [22 empty] | 2017-05-22 | 2017-05-22 | 2017-05-22 | 2017-05-22 | 2017-05-22 | 2017-05-22 | 2017-05-22 | 2017-05-22 | 2017-05-22 | 2017-05-22 | 2017-05-22 | 2017-05-22 | 2017-05-22 | 2017-05-22 | 2017-05-22 | 2017-05-22 | 2017-05-22 | 2017-05-22 | 2017-05-22 | 2017-05-22 | 2017-05-22 | 2017-05-22 | 2017-05-22 | 2017-05-22 | 2017-05-22
DE26-1000 | [24 empty] | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31
DE25-1000 | [34 empty] | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06
CP-STF-DE03-A1000 | [14 empty] | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31
CIV-STF-DE02-1270 | [10 empty] | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11
CIV-STF-DE02-1260 | [22 empty] | 2017-05-22 | 2017-05-22 | 2017-05-22 | 2017-05-22 | 2017-05-22 | 2017-05-22 | 2017-05-22 | 2017-05-22 | 2017-05-22 | 2017-05-22 | 2017-05-22 | 2017-05-22 | 2017-05-22 | 2017-05-22 | 2017-05-22 | 2017-05-22 | 2017-05-22 | 2017-05-22 | 2017-05-22 | 2017-05-22 | 2017-05-22 | 2017-05-22 | 2017-05-22 | 2017-05-22 | 2017-05-22
CIV-STF-DE02-1250 | [24 empty] | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01
CIV-STF-DE02-1240 | [28 empty] | 2017-10-24 | 2017-10-24 | 2017-10-24 | 2017-10-24 | 2017-10-24 | 2017-10-24 | 2017-10-24 | 2017-10-24 | 2017-10-24 | 2017-10-24 | 2017-10-24 | 2017-10-24 | 2017-10-24 | 2017-10-24 | 2017-10-24 | 2017-10-24 | 2017-10-24 | 2017-10-24 | 2017-10-24
CIV-STF-DE02-1230 | [14 empty] | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25
CIV-STF-DE02-1220 | [28 empty] | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18
CIV-STF-DE02-1210 | [24 empty] | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31
CIV-STF-DE02-1190 | [20 empty] | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21
CIV-STF-DE02-1180 | [24 empty] | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01
CIV-STF-DE02-1170 | [24 empty] | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31
CIV-STF-DE02-1160 | [20 empty] | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21
CIV-STF-DE02-1150 | [18 empty] | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17
CIV-STF-DE02-1140 | [20 empty] | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21
CIV-STF-DE02-1130 | [24 empty] | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24
CIV-STF-DE02-1120 | [24 empty] | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24
CIV-STF-DE02-1110 | [28 empty] | 2017-11-18 | 2017-11-18 | 2017-11-18 | 2017-11-18 | 2017-11-18 | 2017-11-18 | 2017-11-18 | 2017-11-18 | 2017-11-18 | 2017-11-18 | 2017-11-18 | 2017-11-18 | 2017-11-18 | 2017-11-18 | 2017-11-18 | 2017-11-18 | 2017-11-18 | 2017-11-18 | 2017-11-18
CIV-STF-DE02-1100 | [24 empty] | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09
CIV-STF-DE02-1090 | [28 empty] | 2017-10-23 | 2017-10-23 | 2017-10-23 | 2017-10-23 | 2017-10-23 | 2017-10-23 | 2017-10-23 | 2017-10-23 | 2017-10-23 | 2017-10-23 | 2017-10-23 | 2017-10-23 | 2017-10-23 | 2017-10-23 | 2017-10-23 | 2017-10-23 | 2017-10-23 | 2017-10-23 | 2017-10-23
CIV-STF-DE02-1080 | [24 empty] | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24
CIV-STF-DE02-1070 | [20 empty] | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21
CIV-STF-DE02-1060 | [34 empty] | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06
CIV-STF-DE02-1050 | [24 empty] | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27
CIV-STF-DE02-1040 | [30 empty] | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06
CIV-STF-DE02-1030 | [20 empty] | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21
CIV-STF-DE02-1020 | [10 empty] | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25
CIV-STF-DE02-1010 | [10 empty] | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25
CIV-STF-DE02-1000 | [28 empty] | 2017-10-24 | 2017-10-24 | 2017-10-24 | 2017-10-24 | 2017-10-24 | 2017-10-24 | 2017-10-24 | 2017-10-24 | 2017-10-24 | 2017-10-24 | 2017-10-24 | 2017-10-24 | 2017-10-24 | 2017-10-24 | 2017-10-24 | 2017-10-24 | 2017-10-24 | 2017-10-24 | 2017-10-24
CIV-PIP-DE03-A1030 | [28 empty] | 2017-10-24: 2018-09-30; 2017-10-24: 2018-09-30; 2017-10-24: 2018-09-30; 2017-10-24: 2018-09-30; 2017-10-24: 2018-09-30; 2017-10-24: 2018-09-30; 2017-10-24: 2018-09-30
CIV-PIP-DE03-A1020 | [38 empty] | 2018-09-15 | 2018-09-15 | 2018-09-15 | 2018-09-15 | 2018-09-15 | 2018-09-15 | 2018-09-15 | 2018-09-15 | 2018-09-15
CIV-PIP-DE03-A1010 | [38 empty] | 2018-08-24 | 2018-08-24 | 2018-08-24 | 2018-08-24 | 2018-08-24 | 2018-08-24 | 2018-08-24 | 2018-08-24 | 2018-08-24
CIV-PIP-DE03-A1000 | [36 empty] | 2018-07-25 | 2018-07-25 | 2018-07-25 | 2018-07-25 | 2018-07-25 | 2018-07-25 | 2018-07-25 | 2018-07-25 | 2018-07-25 | 2018-07-25 | 2018-07-25
CIV-CON-DE02-1024 | [24 empty] | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19
CIV-CON-DE02-1023 | [22 empty] | 2017-05-16 | 2017-05-16 | 2017-05-16 | 2017-05-16 | 2017-05-16 | 2017-05-16 | 2017-05-16 | 2017-05-16 | 2017-05-16 | 2017-05-16 | 2017-05-16 | 2017-05-16 | 2017-05-16 | 2017-05-16 | 2017-05-16 | 2017-05-16 | 2017-05-16 | 2017-05-16 | 2017-05-16 | 2017-05-16 | 2017-05-16 | 2017-05-16 | 2017-05-16 | 2017-05-16 | 2017-05-16
CIV-CON-DE02-1022 | [22 empty] | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14
CIV-CON-DE02-1021 | [22 empty] | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14
CIV-CON-DE02-1020 | [22 empty] | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14
CIV-CON-DE02-1019 | [22 empty] | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14
CIV-CON-DE02-1018 | [22 empty] | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14
CIV-CON-DE02-1016 | [22 empty] | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14
CIV-CON-DE02-1015 | [24 empty] | 2017-07-08 | 2017-07-08 | 2017-07-08 | 2017-07-08 | 2017-07-08 | 2017-07-08 | 2017-07-08 | 2017-07-08 | 2017-07-08 | 2017-07-08 | 2017-07-08 | 2017-07-08 | 2017-07-08 | 2017-07-08 | 2017-07-08 | 2017-07-08 | 2017-07-08 | 2017-07-08 | 2017-07-08 | 2017-07-08 | 2017-07-08 | 2017-07-08 | 2017-07-08
CIV-CON-DE02-1014 | [22 empty] | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06
CIV-CON-DE02-1013 | [22 empty] | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06
CIV-CON-DE02-1012 | [22 empty] | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06
CIV-CON-DE02-1010 | [24 empty] | 2017-06-15 | 2017-06-15 | 2017-06-15 | 2017-06-15 | 2017-06-15 | 2017-06-15 | 2017-06-15 | 2017-06-15 | 2017-06-15 | 2017-06-15 | 2017-06-15 | 2017-06-15 | 2017-06-15 | 2017-06-15 | 2017-06-15 | 2017-06-15 | 2017-06-15 | 2017-06-15 | 2017-06-15 | 2017-06-15 | 2017-06-15 | 2017-06-15 | 2017-06-15
CIV-CON-DE02-1009 | [34 empty] | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06
CIV-CON-DE02-1008 | [34 empty] | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06
CIV-CON-DE02-1007 | [34 empty] | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06
CIV-CON-DE02-1006 | [34 empty] | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06
CIV-CON-DE02-1005 | [34 empty] | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06
CIV-CON-DE02-1004 | [12 empty] | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02
CIV-CON-DE02-1003 | [10 empty] | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19
CIV-CON-DE02-1002 | [10 empty] | 2016-04-03 | 2016-04-03 | 2016-04-03 | 2016-04-03 | 2016-04-03 | 2016-04-03 | 2016-04-03 | 2016-04-03 | 2016-04-03 | 2016-04-03 | 2016-04-03 | 2016-04-03 | 2016-04-03 | 2016-04-03 | 2016-04-03 | 2016-04-03 | 2016-04-03 | 2016-04-03 | 2016-04-03 | 2016-04-03 | 2016-04-03 | 2016-04-03 | 2016-04-03 | 2016-04-03 | 2016-04-03 | 2016-04-03 | 2016-04-03 | 2016-04-03 | 2016-04-03 | 2016-04-03 | 2016-04-03 | 2016-04-03 | 2016-04-03 | 2016-04-03 | 2016-04-03 | 2016-04-03 | 2016-04-03
CIV-CON-DE02-1001 | [10 empty] | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28
CIV-CON-DE02-1000 | [8 empty] | 2016-03-09 | 2016-03-09 | 2016-03-09 | 2016-03-09 | 2016-03-09 | 2016-03-09 | 2016-03-09 | 2016-03-09 | 2016-03-09 | 2016-03-09 | 2016-03-09 | 2016-03-09 | 2016-03-09 | 2016-03-09 | 2016-03-09 | 2016-03-09 | 2016-03-09 | 2016-03-09 | 2016-03-09 | 2016-03-09 | 2016-03-09 | 2016-03-09 | 2016-03-09 | 2016-03-09 | 2016-03-09 | 2016-03-09 | 2016-03-09 | 2016-03-09 | 2016-03-09 | 2016-03-09 | 2016-03-09 | 2016-03-09 | 2016-03-09 | 2016-03-09 | 2016-03-09 | 2016-03-09 | 2016-03-09 | 2016-03-09 | 2016-03-09
CIV-CON-DE01-1016 | [24 empty] | 2017-07-15 | 2017-07-15 | 2017-07-15 | 2017-07-15 | 2017-07-15 | 2017-07-15 | 2017-07-15 | 2017-07-15 | 2017-07-15 | 2017-07-15 | 2017-07-15 | 2017-07-15 | 2017-07-15 | 2017-07-15 | 2017-07-15 | 2017-07-15 | 2017-07-15 | 2017-07-15 | 2017-07-15 | 2017-07-15 | 2017-07-15 | 2017-07-15 | 2017-07-15
CIV-CON-DE01-1015 | [18 empty] | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29
CIV-CON-DE01-1013 | [18 empty] | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07
CIV-CON-DE01-1012 | [26 empty] | 2017-08-15 | 2017-08-15 | 2017-08-15 | 2017-08-15 | 2017-08-15 | 2017-08-15 | 2017-08-15 | 2017-08-15 | 2017-08-15 | 2017-08-15 | 2017-08-15 | 2017-08-15 | 2017-08-15 | 2017-08-15 | 2017-08-15 | 2017-08-15 | 2017-08-15 | 2017-08-15 | 2017-08-15 | 2017-08-15 | 2017-08-15
CIV-CON-DE01-1011 | [20 empty] | 2017-03-20 | 2017-03-20 | 2017-03-20 | 2017-03-20 | 2017-03-20 | 2017-03-20 | 2017-03-20 | 2017-03-20 | 2017-03-20 | 2017-03-20 | 2017-03-20 | 2017-03-20 | 2017-03-20 | 2017-03-20 | 2017-03-20 | 2017-03-20 | 2017-03-20 | 2017-03-20 | 2017-03-20 | 2017-03-20 | 2017-03-20 | 2017-03-20 | 2017-03-20 | 2017-03-20 | 2017-03-20 | 2017-03-20 | 2017-03-20
CIV-CON-DE01-1010 | [20 empty] | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21
CIV-CON-DE01-1009 | [18 empty] | 2016-12-18 | 2016-12-18 | 2016-12-18 | 2016-12-18 | 2016-12-18 | 2016-12-18 | 2016-12-18 | 2016-12-18 | 2016-12-18 | 2016-12-18 | 2016-12-18 | 2016-12-18 | 2016-12-18 | 2016-12-18 | 2016-12-18 | 2016-12-18 | 2016-12-18 | 2016-12-18 | 2016-12-18 | 2016-12-18 | 2016-12-18 | 2016-12-18 | 2016-12-18 | 2016-12-18 | 2016-12-18 | 2016-12-18 | 2016-12-18 | 2016-12-18 | 2016-12-18
CIV-CON-DE01-1008 | [16 empty] | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07
CIV-CON-DE01-1007 | [18 empty] | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24
CIV-CON-DE01-1004 | [16 empty] | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20
CIV-CON-DE01-1003 | [16 empty] | 2016-11-14 | 2016-11-14 | 2016-11-14 | 2016-11-14 | 2016-11-14 | 2016-11-14 | 2016-11-14 | 2016-11-14 | 2016-11-14 | 2016-11-14 | 2016-11-14 | 2016-11-14 | 2016-11-14 | 2016-11-14 | 2016-11-14 | 2016-11-14 | 2016-11-14 | 2016-11-14 | 2016-11-14 | 2016-11-14 | 2016-11-14 | 2016-11-14 | 2016-11-14 | 2016-11-14 | 2016-11-14 | 2016-11-14 | 2016-11-14 | 2016-11-14 | 2016-11-14 | 2016-11-14 | 2016-11-14
CIV-CON-DE01-1002 | [16 empty] | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18
CIV-CON-DE01-1001 | [16 empty] | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18
CIV-CON-DE01-1000 | [14 empty] | 2016-08-31 | 2016-08-31 | 2016-08-31 | 2016-08-31 | 2016-08-31 | 2016-08-31 | 2016-08-31 | 2016-08-31 | 2016-08-31 | 2016-08-31 | 2016-08-31 | 2016-08-31 | 2016-08-31 | 2016-08-31 | 2016-08-31 | 2016-08-31 | 2016-08-31 | 2016-08-31 | 2016-08-31 | 2016-08-31 | 2016-08-31 | 2016-08-31 | 2016-08-31 | 2016-08-31 | 2016-08-31 | 2016-08-31 | 2016-08-31 | 2016-08-31 | 2016-08-31 | 2016-08-31 | 2016-08-31 | 2016-08-31 | 2016-08-31
CIV-COCC-DE01-1040 | [20 empty] | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21
CIV-COCC-DE01-1020 | [24 empty] | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31
CIV-COCC-DE01-1010 | [24 empty] | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31
CIV-COCC-DE01-1000 | [24 empty] | 2017-05-31: 2018-11-27; 2017-05-31: 2018-11-27; 2017-05-31: 2018-11-27; 2017-05-31: 2018-11-27; 2017-05-31: 2018-11-27
BLK-TEL-DE03-1005 | [30 empty] | 2017-12-30 | 2017-12-30 | 2017-12-30 | 2017-12-30 | 2017-12-30 | 2017-12-30 | 2017-12-30 | 2017-12-30 | 2017-12-30 | 2017-12-30 | 2017-12-30 | 2017-12-30 | 2017-12-30 | 2017-12-30 | 2017-12-30 | 2017-12-30 | 2017-12-30
BLK-TEL-DE03-1003 | [28 empty] | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05
BLK-TEL-DE03-1001 | [26 empty] | 2017-09-01 | 2017-09-01 | 2017-09-01 | 2017-09-01 | 2017-09-01 | 2017-09-01 | 2017-09-01 | 2017-09-01 | 2017-09-01 | 2017-09-01 | 2017-09-01 | 2017-09-01 | 2017-09-01 | 2017-09-01 | 2017-09-01 | 2017-09-01 | 2017-09-01 | 2017-09-01 | 2017-09-01 | 2017-09-01 | 2017-09-01
BLK-INSTR-DE02-1027 | [38 empty] | 2018-08-05 | 2018-08-05 | 2018-08-05 | 2018-08-05 | 2018-08-05 | 2018-08-05 | 2018-08-05 | 2018-08-05 | 2018-08-05
BLK-INSTR-DE02-1026 | [38 empty] | 2018-08-05 | 2018-08-05 | 2018-08-05 | 2018-08-05 | 2018-08-05 | 2018-08-05 | 2018-08-05 | 2018-08-05 | 2018-08-05
BLK-INSTR-DE02-1025 | [38 empty] | 2018-08-05 | 2018-08-05 | 2018-08-05 | 2018-08-05 | 2018-08-05 | 2018-08-05 | 2018-08-05 | 2018-08-05 | 2018-08-05
BLK-INSTR-DE02-1024 | [38 empty] | 2018-08-25 | 2018-08-25 | 2018-08-25 | 2018-08-25 | 2018-08-25 | 2018-08-25 | 2018-08-25 | 2018-08-25 | 2018-08-25
BLK-INSTR-DE02-1023 | [38 empty] | 2018-08-25: 2018-12-12; 2018-08-25: 2018-12-12; 2018-08-25: 2018-12-12; 2018-08-25: 2018-12-12; 2018-08-25: 2018-12-12
BLK-INSTR-DE02-1022 | [38 empty] | 2018-08-25: 2018-12-12; 2018-08-25: 2018-12-12; 2018-08-25: 2018-12-12; 2018-08-25: 2018-12-12; 2018-08-25: 2018-12-12
BLK-INSTR-DE02-1021 | [38 empty] | 2018-08-25: 2018-12-12; 2018-08-25: 2018-12-12; 2018-08-25: 2018-12-12; 2018-08-25: 2018-12-12; 2018-08-25: 2018-12-12
BLK-INSTR-DE02-1020 | [34 empty] | 2018-04-12 | 2018-04-12 | 2018-04-12 | 2018-04-12 | 2018-04-12 | 2018-04-12 | 2018-04-12 | 2018-04-12 | 2018-04-12 | 2018-04-12 | 2018-04-12 | 2018-04-12 | 2018-04-12
BLK-INSTR-DE02-1017 | [34 empty] | 2018-04-12: 2018-12-23; 2018-04-12: 2018-12-23; 2018-04-12: 2018-12-23; 2018-04-12: 2018-12-23; 2018-04-12: 2018-12-23
BLK-INSTR-DE02-1014 | [30 empty] | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27
BLK-INSTR-DE02-1011 | [30 empty] | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06
BLK-INSTR-DE02-1008 | [30 empty] | 2018-01-18 | 2018-01-18 | 2018-01-18 | 2018-01-18 | 2018-01-18 | 2018-01-18 | 2018-01-18 | 2018-01-18 | 2018-01-18 | 2018-01-18 | 2018-01-18 | 2018-01-18 | 2018-01-18 | 2018-01-18 | 2018-01-18 | 2018-01-18 | 2018-01-18
BLK-INSTR-DE02-1005 | [24 empty] | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09
BLK-INSTR-DE02-1004 | [30 empty] | 2017-12-02 | 2017-12-02 | 2017-12-02 | 2017-12-02 | 2017-12-02 | 2017-12-02 | 2017-12-02 | 2017-12-02 | 2017-12-02 | 2017-12-02 | 2017-12-02 | 2017-12-02 | 2017-12-02 | 2017-12-02 | 2017-12-02 | 2017-12-02 | 2017-12-02
BLK-INSTR-DE02-1002 | [24 empty] | 2017-07-12 | 2017-07-12 | 2017-07-12 | 2017-07-12 | 2017-07-12 | 2017-07-12 | 2017-07-12 | 2017-07-12 | 2017-07-12 | 2017-07-12 | 2017-07-12 | 2017-07-12 | 2017-07-12 | 2017-07-12 | 2017-07-12 | 2017-07-12 | 2017-07-12 | 2017-07-12 | 2017-07-12 | 2017-07-12 | 2017-07-12 | 2017-07-12 | 2017-07-12
BLK-ELE-DE01-1031 | [36 empty] | 2018-06-28 | 2018-06-28 | 2018-06-28 | 2018-06-28 | 2018-06-28 | 2018-06-28 | 2018-06-28 | 2018-06-28 | 2018-06-28 | 2018-06-28 | 2018-06-28
BLK-ELE-DE01-1030 | [40 empty] | 2018-10-13 | 2018-10-13 | 2018-10-13 | 2018-10-13 | 2018-10-13 | 2018-10-13 | 2018-10-13
BLK-ELE-DE01-1029 | [38 empty] | 2018-08-20 | 2018-08-20 | 2018-08-20 | 2018-08-20 | 2018-08-20 | 2018-08-20 | 2018-08-20 | 2018-08-20 | 2018-08-20
BLK-ELE-DE01-1028 | [38 empty] | 2018-08-20: 2018-12-12; 2018-08-20: 2018-12-12; 2018-08-20: 2018-12-12; 2018-08-20: 2018-12-12; 2018-08-20: 2018-12-12
BLK-ELE-DE01-1027 | [38 empty] | 2018-08-20: 2018-12-12; 2018-08-20: 2018-12-12; 2018-08-20: 2018-12-12; 2018-08-20: 2018-12-12; 2018-08-20: 2018-12-12
BLK-ELE-DE01-1026 | [24 empty] | 2017-07-26 | 2017-07-26 | 2017-07-26 | 2017-07-26 | 2017-07-26 | 2017-07-26 | 2017-07-26 | 2017-07-26 | 2017-07-26 | 2017-07-26 | 2017-07-26 | 2017-07-26 | 2017-07-26 | 2017-07-26 | 2017-07-26 | 2017-07-26 | 2017-07-26 | 2017-07-26 | 2017-07-26 | 2017-07-26 | 2017-07-26 | 2017-07-26 | 2017-07-26
BLK-ELE-DE01-1025 | [34 empty] | 2018-05-08 | 2018-05-08 | 2018-05-08 | 2018-05-08 | 2018-05-08 | 2018-05-08 | 2018-05-08 | 2018-05-08 | 2018-05-08 | 2018-05-08 | 2018-05-08 | 2018-05-08 | 2018-05-08
BLK-ELE-DE01-1023 | [28 empty] | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06
BLK-ELE-DE01-1017 | [28 empty] | 2017-11-06: 2018-10-31; 2017-11-06: 2018-10-31; 2017-11-06: 2018-10-31; 2017-11-06: 2018-10-31; 2017-11-06: 2018-10-31; 2017-11-06: 2018-10-31; 2017-11-06: 2018-10-31
BLK-ELE-DE01-1014 | [28 empty] | 2017-11-19 | 2017-11-19 | 2017-11-19 | 2017-11-19 | 2017-11-19 | 2017-11-19 | 2017-11-19 | 2017-11-19 | 2017-11-19 | 2017-11-19 | 2017-11-19 | 2017-11-19 | 2017-11-19 | 2017-11-19 | 2017-11-19 | 2017-11-19 | 2017-11-19 | 2017-11-19 | 2017-11-19
BLK-ELE-DE01-1011 | [30 empty] | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05
BLK-ELE-DE01-1010 | [32 empty] | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27
BLK-ELE-DE01-1008 | [28 empty] | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05
BLK-ELE-DE01-1007 | [28 empty] | 2017-10-06 | 2017-10-06 | 2017-10-06 | 2017-10-06 | 2017-10-06 | 2017-10-06 | 2017-10-06 | 2017-10-06 | 2017-10-06 | 2017-10-06 | 2017-10-06 | 2017-10-06 | 2017-10-06 | 2017-10-06 | 2017-10-06 | 2017-10-06 | 2017-10-06 | 2017-10-06 | 2017-10-06
BLK-ELE-DE01-1005 | [26 empty] | 2017-08-07 | 2017-08-07 | 2017-08-07 | 2017-08-07 | 2017-08-07 | 2017-08-07 | 2017-08-07 | 2017-08-07 | 2017-08-07 | 2017-08-07 | 2017-08-07 | 2017-08-07 | 2017-08-07 | 2017-08-07 | 2017-08-07 | 2017-08-07 | 2017-08-07 | 2017-08-07 | 2017-08-07 | 2017-08-07 | 2017-08-07
BLK-ELE-DE01-1002 | [22 empty] | 2017-05-03 | 2017-05-03 | 2017-05-03 | 2017-05-03 | 2017-05-03 | 2017-05-03 | 2017-05-03 | 2017-05-03 | 2017-05-03 | 2017-05-03 | 2017-05-03 | 2017-05-03 | 2017-05-03 | 2017-05-03 | 2017-05-03 | 2017-05-03 | 2017-05-03 | 2017-05-03 | 2017-05-03 | 2017-05-03 | 2017-05-03 | 2017-05-03 | 2017-05-03 | 2017-05-03 | 2017-05-03
BLK-ELE-DE01-1001 | [24 empty] | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25
BLK-CP-DE04-1002 | [34 empty] | 2018-04-12 | 2018-04-12 | 2018-04-12 | 2018-04-12 | 2018-04-12 | 2018-04-12 | 2018-04-12 | 2018-04-12 | 2018-04-12 | 2018-04-12 | 2018-04-12 | 2018-04-12 | 2018-04-12
BLK-CP-DE04-1001 | [38 empty] | 2018-08-05 | 2018-08-05 | 2018-08-05 | 2018-08-05 | 2018-08-05 | 2018-08-05 | 2018-08-05 | 2018-08-05 | 2018-08-05
BLK-CP-DE04-1000 | [38 empty] | 2018-09-25 | 2018-09-25 | 2018-09-25 | 2018-09-25 | 2018-09-25 | 2018-09-25 | 2018-09-25 | 2018-09-25 | 2018-09-25
2AR000TF10001-08040 | Electrical Load Schedule | time axis 2015-09-13 to 2015-09-13
2AR000TF10001-08035 | Electrical Single Line Diagram | time axis 2015-09-13 to 2015-09-13
2AR000TF10001-08030 | Fire Alarm Layout for Sub Contractor Main Site office | time axis 2015-09-13 to 2015-09-13
2AR000TF10001-08025 | Small Power Layout for Contractor Main Site office | time axis 2015-09-13 to 2015-09-13
2AR000TF10001-08020 | Lighting Layout for sub-contractor Main Site office | time axis 2015-09-13 to 2015-09-13
2AR000TF10001-08015 | External Electrical Service Layout for Site office & Laydown Area | time axis 2015-09-13 to 2015-09-13
2AR000TF10001-08010 | Sub-contractor Site office Layout | time axis 2015-08-30 to 2015-08-30
2AR000TF10001-08005 | Sanitary & Plumbing Layout | time axis 2015-08-30 to 2015-08-30
2AR000TF10001-08000 | Layout for Sub-contractor Site office & laydown Area | time axis 2015-08-30 to 2015-08-30
2AP100MS08100-08125 | Submition & Approval of RAM for Pipe Insulation Material (Personnel Protection) | [35 empty] | 2018-07-23 | 2018-07-23 | 2018-07-23 | 2018-07-23 | 2018-07-23 | 2018-07-23 | 2018-07-23 | 2018-07-23 | 2018-07-23 | 2018-07-23 | 2018-07-23
2AP100MS08100-08115 | Submition & Approval of RAM for Pipe Insulation Material (Heat Conservation) | [33 empty] | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04
2AP100MS08100-08105 | Submition & Approval of RAM for Fireproofing Meerial | [33 empty] | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27
2AP100MS08100-08095 | Submition & Approval of RAM for Abrasive Blasting Material (Garnet) | [9 empty] | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27
2AP100MS08100-08090 | Submition & Approval of RAM for Painting Material | [9 empty] | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27
2AP100MS08100-08085 | Submition & Approval of RAM for Coating Material | [11 empty] | 2016-06-23 | 2016-06-23 | 2016-06-23 | 2016-06-23 | 2016-06-23 | 2016-06-23 | 2016-06-23 | 2016-06-23 | 2016-06-23 | 2016-06-23 | 2016-06-23 | 2016-06-23 | 2016-06-23 | 2016-06-23 | 2016-06-23 | 2016-06-23 | 2016-06-23 | 2016-06-23 | 2016-06-23 | 2016-06-23 | 2016-06-23 | 2016-06-23 | 2016-06-23 | 2016-06-23 | 2016-06-23 | 2016-06-23 | 2016-06-23 | 2016-06-23 | 2016-06-23 | 2016-06-23 | 2016-06-23 | 2016-06-23 | 2016-06-23 | 2016-06-23 | 2016-06-23
2AP100MS08100-08080 | Submition & Approval of RAM for Welding Consumables | [9 empty] | 2016-04-10 | 2016-04-10 | 2016-04-10 | 2016-04-10 | 2016-04-10 | 2016-04-10 | 2016-04-10 | 2016-04-10 | 2016-04-10 | 2016-04-10 | 2016-04-10 | 2016-04-10 | 2016-04-10 | 2016-04-10 | 2016-04-10 | 2016-04-10 | 2016-04-10 | 2016-04-10 | 2016-04-10 | 2016-04-10 | 2016-04-10 | 2016-04-10 | 2016-04-10 | 2016-04-10 | 2016-04-10 | 2016-04-10 | 2016-04-10 | 2016-04-10 | 2016-04-10 | 2016-04-10 | 2016-04-10 | 2016-04-10 | 2016-04-10 | 2016-04-10 | 2016-04-10 | 2016-04-10 | 2016-04-10
2AP100EL08100-08100 | Submition & Approval of RAM FOR CONCRETE CABLE TILE {FOR U/G CABLE PROTECTION) | [7 empty] | 2016-02-09 | 2016-02-09 | 2016-02-09 | 2016-02-09 | 2016-02-09 | 2016-02-09 | 2016-02-09 | 2016-02-09 | 2016-02-09 | 2016-02-09 | 2016-02-09 | 2016-02-09 | 2016-02-09 | 2016-02-09 | 2016-02-09 | 2016-02-09 | 2016-02-09 | 2016-02-09 | 2016-02-09 | 2016-02-09 | 2016-02-09 | 2016-02-09 | 2016-02-09 | 2016-02-09 | 2016-02-09 | 2016-02-09 | 2016-02-09 | 2016-02-09 | 2016-02-09 | 2016-02-09 | 2016-02-09 | 2016-02-09 | 2016-02-09 | 2016-02-09 | 2016-02-09 | 2016-02-09 | 2016-02-09 | 2016-02-09 | 2016-02-09
2AP100CV08100-08075 | Submition & Approval of RAM FOR ROAD ASPHALT | [17 empty] | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24
2AP100CV08100-08070 | Submition & Approval of RAM FOR HAND HOLE AND MANHOLE COVERS | [17 empty] | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02
2AP100CV08100-08065 | Submition & Approval of RAM FOR HIGH SECURITY FENCE | [15 empty] | 2016-11-08 | 2016-11-08 | 2016-11-08 | 2016-11-08 | 2016-11-08 | 2016-11-08 | 2016-11-08 | 2016-11-08 | 2016-11-08 | 2016-11-08 | 2016-11-08 | 2016-11-08 | 2016-11-08 | 2016-11-08 | 2016-11-08 | 2016-11-08 | 2016-11-08 | 2016-11-08 | 2016-11-08 | 2016-11-08 | 2016-11-08 | 2016-11-08 | 2016-11-08 | 2016-11-08 | 2016-11-08 | 2016-11-08 | 2016-11-08 | 2016-11-08 | 2016-11-08 | 2016-11-08 | 2016-11-08
2AP100CV08100-08060 | Submition & Approval of RAM FOR CHAIN LINK FENCE | [13 empty] | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07
2AP100CV08100-08055 | Submition & Approval of RAM FOR BINDING WIRE FOR REINFORCEMENT | [5 empty] | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28
2AP100CV08100-08050 | Submition & Approval of RAM FOR CONBEXTRA GP (NON-SHRINK GROUT) | [7 empty] | 2016-02-20 | 2016-02-20 | 2016-02-20 | 2016-02-20 | 2016-02-20 | 2016-02-20 | 2016-02-20 | 2016-02-20 | 2016-02-20 | 2016-02-20 | 2016-02-20 | 2016-02-20 | 2016-02-20 | 2016-02-20 | 2016-02-20 | 2016-02-20 | 2016-02-20 | 2016-02-20 | 2016-02-20 | 2016-02-20 | 2016-02-20 | 2016-02-20 | 2016-02-20 | 2016-02-20 | 2016-02-20 | 2016-02-20 | 2016-02-20 | 2016-02-20 | 2016-02-20 | 2016-02-20 | 2016-02-20 | 2016-02-20 | 2016-02-20 | 2016-02-20 | 2016-02-20 | 2016-02-20 | 2016-02-20 | 2016-02-20 | 2016-02-20
2AP100CV08100-08045 | Submition & Approval of RAM FOR HEMPADUR MASTIC 45881/45880 | [5 empty] | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11
2AP100CV08100-08040 | Submition & Approval of RAM FOR PG-10 (POLYSHILPIDE SEALENT) | [5 empty] | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11
2AP100CV08100-08035 | Submition & Approval of RAM FOR HEMPADUR 85671 (EPOXY COATING) | [5 empty] | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11
2AP100CV08100-08030 | Submition & Approval of RAM FOR REPAIR CEMENT/CHEMICAL etc (FORSOC) | [5 empty] | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11
2AP100CV08100-08025 | Submition & Approval of RAM FOR RELEASEFORM | [5 empty] | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11
2AP100CV08100-08020 | Submition & Approval of RAM FOR BITUMENT FILLER BOARD (Jolly Bitulex) | [5 empty] | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11
2AP100CV08100-08015 | Submition & Approval of RAM FOR POLYTHENE SHEET | [5 empty] | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11
2AP100CV08100-08010 | Submition & Approval of RAM FOR CEMENT (OPC & SRPC) | time axis 2015-11-26 to 2015-11-26
2AP100CV08100-08005 | Submition & Approval of RAM FOR CAP PRIME & CAP SEAL | [5 empty] | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09
2AP100CV08100-08000 | Submition & Approval of RAM FOR HYSD BARS | [5 empty] | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11
2AP000TE00207-08025 | EOF: Miscellaneous Telecom Items-Last Lot | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AP000TE00207-08020 | EOF: Miscellaneous Telecom Items - First Lot | [27 empty] | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22
2AP000TE00207-08015 | EOF:Delivery of Fibre Optic Cables-Last Lot | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AP000TE00207-08010 | EOF:Delivery of Fibre Optic Cables - First Lot | [27 empty] | 2017-10-31 | 2017-10-31 | 2017-10-31 | 2017-10-31 | 2017-10-31 | 2017-10-31 | 2017-10-31 | 2017-10-31 | 2017-10-31 | 2017-10-31 | 2017-10-31 | 2017-10-31 | 2017-10-31 | 2017-10-31 | 2017-10-31 | 2017-10-31 | 2017-10-31 | 2017-10-31 | 2017-10-31
2AP000TE00207-08005 | EOF:Telecom Cable -Last Lot | [37 empty] | 2018-08-16 | 2018-08-16 | 2018-08-16 | 2018-08-16 | 2018-08-16 | 2018-08-16 | 2018-08-16 | 2018-08-16 | 2018-08-16
2AP000TE00207-08000 | EOF:Telecom Cable - First Lot | [27 empty] | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05
2AP000TE00107-08005 | EOF : Delivery of Telecom Equipments - Last Lot | [27 empty] | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16
2AP000TE00107-08000 | EOF : Delivery of Telecom Equipments - First Lot | [23 empty] | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17
2AP000ST00807-08015 | Gate & Crash Barrier Lot - 3 | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AP000ST00807-08010 | Gate & Crash Barrier Lot - 2 | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AP000ST00807-08005 | Gate & Crash Barrier Lot - 1 | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AP000ST00707-08030 | Fencing & Gate Material Lot - 3 | [27 empty] | 2017-10-26 | 2017-10-26 | 2017-10-26 | 2017-10-26 | 2017-10-26 | 2017-10-26 | 2017-10-26 | 2017-10-26 | 2017-10-26 | 2017-10-26 | 2017-10-26 | 2017-10-26 | 2017-10-26 | 2017-10-26 | 2017-10-26 | 2017-10-26 | 2017-10-26 | 2017-10-26 | 2017-10-26
2AP000ST00707-08025 | Fencing & Gate Material Lot - 2 | [27 empty] | 2017-10-26 | 2017-10-26 | 2017-10-26 | 2017-10-26 | 2017-10-26 | 2017-10-26 | 2017-10-26 | 2017-10-26 | 2017-10-26 | 2017-10-26 | 2017-10-26 | 2017-10-26 | 2017-10-26 | 2017-10-26 | 2017-10-26 | 2017-10-26 | 2017-10-26 | 2017-10-26 | 2017-10-26
2AP000ST00707-08020 | Fencing & Gate Material Lot - 1 | [27 empty] | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20
2AP000ST00200-08025 | Steel Building material Lot - 3 | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AP000ST00200-08020 | Steel Building material Lot - 2 | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AP000ST00200-08015 | Steel Building material Lot - 1 | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AP000ST00200-08010 | Structural Steel Lot - 3 | [35 empty] | 2018-06-27 | 2018-06-27 | 2018-06-27 | 2018-06-27 | 2018-06-27 | 2018-06-27 | 2018-06-27 | 2018-06-27 | 2018-06-27 | 2018-06-27 | 2018-06-27
2AP000ST00200-08005 | Structural Steel Lot - 2 | [35 empty] | 2018-05-28 | 2018-05-28 | 2018-05-28 | 2018-05-28 | 2018-05-28 | 2018-05-28 | 2018-05-28 | 2018-05-28 | 2018-05-28 | 2018-05-28 | 2018-05-28
2AP000ST00200-08000 | Structural Steel Lot - 1 | [23 empty] | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01
2AP000SE00607-08010 | EOF : Delivery of Safety Signs - Last Lot 3
2AP000SE00607-08005 | EOF : Delivery of Safety Signs - Lot 2
2AP000SE00607-08000 | EOF : Delivery of Safety Signs - First Lot 1
2AP000PI00507-08025 | EOF : Delivery Of Misc. Piping Items (Gaskets/Fasteners/Springs/Strut/Hanger /Sliding Plate/Etc) - Lot -3
2AP000PI00507-08020 | EOF : Delivery Of Misc. Piping Items (Gaskets/Fasteners/Springs/Strut/Hanger /Sliding Plate/Etc) - Lot -2
2AP000PI00507-08015 | EOF : Delivery Of Misc. Piping Items (Gaskets/Fasteners/Springs/Strut/Hanger /Sliding Plate/Etc) - Lot -1 | [25 empty] | 2017-09-09 | 2017-09-09 | 2017-09-09 | 2017-09-09 | 2017-09-09 | 2017-09-09 | 2017-09-09 | 2017-09-09 | 2017-09-09 | 2017-09-09 | 2017-09-09 | 2017-09-09 | 2017-09-09 | 2017-09-09 | 2017-09-09 | 2017-09-09 | 2017-09-09 | 2017-09-09 | 2017-09-09 | 2017-09-09 | 2017-09-09
2AP000PI00507-08010 | EOF : Delivery of Piping supports (Primary) - Lot -3 | [25 empty] | 2017-09-09: 2018-12-09; 2017-09-09: 2018-12-09; 2017-09-09: 2018-12-09; 2017-09-09: 2018-12-09; 2017-09-09: 2018-12-09
2AP000PI00507-08005 | EOF : Delivery of Piping supports (Primary) - Lot -2 | [25 empty] | 2017-09-09: 2018-10-10; 2017-09-09: 2018-10-10; 2017-09-09: 2018-10-10; 2017-09-09: 2018-10-10; 2017-09-09: 2018-10-10; 2017-09-09: 2018-10-10; 2017-09-09: 2018-10-10
2AP000PI00507-08000 | EOF : Delivery of Piping supports (Primary) - Lot -1 | [37 empty] | 2018-08-04 | 2018-08-04 | 2018-08-04 | 2018-08-04 | 2018-08-04 | 2018-08-04 | 2018-08-04 | 2018-08-04 | 2018-08-04
2AP000PI00407-08025 | EOF : Delivery of Other Piping Valves (Butterfly/Plug/Check/Special type) - Lot -3 | [39 empty] | 2018-10-11 | 2018-10-11 | 2018-10-11 | 2018-10-11 | 2018-10-11 | 2018-10-11 | 2018-10-11
2AP000PI00407-08020 | EOF : Delivery of Other Piping Valves (Butterfly/Plug/Check/Special type) - Lot -2 | [35 empty] | 2018-06-05 | 2018-06-05 | 2018-06-05 | 2018-06-05 | 2018-06-05 | 2018-06-05 | 2018-06-05 | 2018-06-05 | 2018-06-05 | 2018-06-05 | 2018-06-05
2AP000PI00407-08015 | EOF : Delivery of Other Piping Valves (Butterfly/Plug/Check/Special type) - Lot -1 | [27 empty] | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22
2AP000PI00407-08010 | EOF : Delivery of Piping Valves (Ball/GGC type) - Lot -3 | [27 empty] | 2017-10-22: 2018-10-27; 2017-10-22: 2018-10-27; 2017-10-22: 2018-10-27; 2017-10-22: 2018-10-27; 2017-10-22: 2018-10-27; 2017-10-22: 2018-10-27; 2017-10-22: 2018-10-27
2AP000PI00407-08005 | EOF : Delivery of Piping Valves (Ball/GGC type) - Lot -2 | [37 empty] | 2018-08-19 | 2018-08-19 | 2018-08-19 | 2018-08-19 | 2018-08-19 | 2018-08-19 | 2018-08-19 | 2018-08-19 | 2018-08-19
2AP000PI00407-08000 | EOF : Delivery of Piping Valves (Ball/GGC type) - Lot -1 | [33 empty] | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28
2AP000PI00307-08025 | EOF : Delivery of Pipe Fittings, Flanges and Blinds - Lot -3
2AP000PI00307-08020 | EOF : Delivery of Pipe Fittings, Flanges and Blinds - Lot -2 | [29 empty] | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22
2AP000PI00307-08015 | EOF : Delivery of Pipe Fittings, Flanges and Blinds - Lot -1 | [23 empty] | 2017-06-03 | 2017-06-03 | 2017-06-03 | 2017-06-03 | 2017-06-03 | 2017-06-03 | 2017-06-03 | 2017-06-03 | 2017-06-03 | 2017-06-03 | 2017-06-03 | 2017-06-03 | 2017-06-03 | 2017-06-03 | 2017-06-03 | 2017-06-03 | 2017-06-03 | 2017-06-03 | 2017-06-03 | 2017-06-03 | 2017-06-03 | 2017-06-03 | 2017-06-03
2AP000PI00207-08010 | EOF : Delivery of non-metallic pipes & fitting (GRE/ FBE/HBE) - Lot -3 | [23 empty] | 2017-06-03: 2019-01-27; 2017-06-03: 2019-01-27; 2017-06-03: 2019-01-27
2AP000PI00207-08005 | EOF : Delivery of non-metallic pipes & fitting (GRE/ FBE/HBE) - Lot -2 | [23 empty] | 2017-06-03: 2019-01-27; 2017-06-03: 2019-01-27; 2017-06-03: 2019-01-27
2AP000PI00207-08000 | EOF : Delivery of non-metallic pipes & fitting (GRE/ FBE/HBE) - Lot -1 | [27 empty] | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22
2AP000PI00107-08055 | EOF : Delivery of SS/SDSS Pipes (Welded) - Lot -3 | [35 empty] | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21
2AP000PI00107-08050 | EOF : Delivery of SS/SDSS Pipes (Welded) - Lot -2 | [35 empty] | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21
2AP000PI00107-08045 | EOF : Delivery of SS/SDSS Pipes (Welded) - Lot -1 | [35 empty] | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21
2AP000PI00107-08040 | EOF : Delivery of SS/SDSS Pipes (Seemless) - Lot -3 | [35 empty] | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21
2AP000PI00107-08035 | EOF : Delivery of SS/SDSS Pipes (Seemless) - Lot -2 | [35 empty] | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21
2AP000PI00107-08030 | EOF : Delivery of SS/SDSS Pipes (Seemless) - Lot -1 | [35 empty] | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21
2AP000PI00107-08025 | EOF : Delivery of CS/LTCS Pipes (Welded) - Lot -3 | [37 empty] | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03
2AP000PI00107-08020 | EOF : Delivery of CS/LTCS Pipes (Welded) - Lot -2 | [37 empty] | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03
2AP000PI00107-08015 | EOF : Delivery of CS/LTCS Pipes (Welded) - Lot -1 | [23 empty] | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30
2AP000PI00107-08010 | EOF : Delivery of CS/LTCS Pipes (Seamless) - Lot -3 | [37 empty] | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03
2AP000PI00107-08005 | EOF : Delivery of CS/LTCS Pipes (Seamless) - Lot -2 | [37 empty] | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03
2AP000PI00107-08000 | EOF : Delivery of CS/LTCS Pipes (Seamless) - Lot -1 | [37 empty] | 2018-08-27 | 2018-08-27 | 2018-08-27 | 2018-08-27 | 2018-08-27 | 2018-08-27 | 2018-08-27 | 2018-08-27 | 2018-08-27
2AP000MS00507-08105 | EG Building 50-R-002 : Diesel Day Tank | [33 empty] | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15
2AP000MS00507-08095 | EG Building 52-R-302 : Diesel Day Tank | [29 empty] | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20
2AP000MS00507-08085 | EG Building 52-R-303 : Diesel Day Tank | [29 empty] | 2017-12-21 | 2017-12-21 | 2017-12-21 | 2017-12-21 | 2017-12-21 | 2017-12-21 | 2017-12-21 | 2017-12-21 | 2017-12-21 | 2017-12-21 | 2017-12-21 | 2017-12-21 | 2017-12-21 | 2017-12-21 | 2017-12-21 | 2017-12-21 | 2017-12-21
2AP000MS00507-08075 | EG Building 52-R-301 : Diesel Day Tank | [29 empty] | 2017-12-30 | 2017-12-30 | 2017-12-30 | 2017-12-30 | 2017-12-30 | 2017-12-30 | 2017-12-30 | 2017-12-30 | 2017-12-30 | 2017-12-30 | 2017-12-30 | 2017-12-30 | 2017-12-30 | 2017-12-30 | 2017-12-30 | 2017-12-30 | 2017-12-30
2AP000MS00507-08065 | EOF: Diesel Fuel Tank 621-D307 D | [27 empty] | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02
2AP000MS00507-08060 | EOF: Diesel Fuel Tank 621-D307 C | [27 empty] | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02
2AP000MS00507-08055 | EOF: Diesel Fuel Tank 621-D307 B | [27 empty] | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02
2AP000MS00507-08050 | EOF: Diesel Fuel Tank 621-D307 A | [27 empty] | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02
2AP000MS00507-08045 | EOF: Water drain tank-52-D-308 B | [19 empty] | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16
2AP000MS00507-08040 | EOF: Water drain tank-52-D-308 A | [19 empty] | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16
2AP000MS00507-08035 | EOF: Flushing Water drain tank-52-D-306B | [21 empty] | 2017-04-17 | 2017-04-17 | 2017-04-17 | 2017-04-17 | 2017-04-17 | 2017-04-17 | 2017-04-17 | 2017-04-17 | 2017-04-17 | 2017-04-17 | 2017-04-17 | 2017-04-17 | 2017-04-17 | 2017-04-17 | 2017-04-17 | 2017-04-17 | 2017-04-17 | 2017-04-17 | 2017-04-17 | 2017-04-17 | 2017-04-17 | 2017-04-17 | 2017-04-17 | 2017-04-17 | 2017-04-17
2AP000MS00507-08030 | EOF: Flushing Water drain tank-52-D-306A | [21 empty] | 2017-04-17 | 2017-04-17 | 2017-04-17 | 2017-04-17 | 2017-04-17 | 2017-04-17 | 2017-04-17 | 2017-04-17 | 2017-04-17 | 2017-04-17 | 2017-04-17 | 2017-04-17 | 2017-04-17 | 2017-04-17 | 2017-04-17 | 2017-04-17 | 2017-04-17 | 2017-04-17 | 2017-04-17 | 2017-04-17 | 2017-04-17 | 2017-04-17 | 2017-04-17 | 2017-04-17 | 2017-04-17
2AP000MS00507-08015 | EOF: Diesel Engine drain tank-52-D-304B | [19 empty] | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16
2AP000MS00507-08010 | EOF: Diesel Engine drain tank-52-D-304A | [19 empty] | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16
2AP000MS00507-08005 | EOF: Overhead Water Tank (52-D-309 B) | [19 empty] | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16
2AP000MS00507-08000 | EOF: Overhead Water Tank (52-D-309 A) | [19 empty] | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16
2AP000MS00107-08000 | EOF: 621-V-301 Oily Water Collection Vessell | [21 empty] | 2017-04-24 | 2017-04-24 | 2017-04-24 | 2017-04-24 | 2017-04-24 | 2017-04-24 | 2017-04-24 | 2017-04-24 | 2017-04-24 | 2017-04-24 | 2017-04-24 | 2017-04-24 | 2017-04-24 | 2017-04-24 | 2017-04-24 | 2017-04-24 | 2017-04-24 | 2017-04-24 | 2017-04-24 | 2017-04-24 | 2017-04-24 | 2017-04-24 | 2017-04-24 | 2017-04-24 | 2017-04-24
2AP000MR01807-08015 | 52-GM-301B:Variable Speed Drives | [31 empty] | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28
2AP000MR01807-08010 | 52-GM-301A:Variable Speed Drives | [31 empty] | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28
2AP000MR01807-08005 | EOF: 621-G-301 B Trim Pump | [31 empty] | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28
2AP000MR01807-08000 | EOF: 621-G-301 A Trim Pump | [31 empty] | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28
2AP000MR00307-08045 | EOF: 621-G-303 B Oily Water Transfer Pump | [33 empty] | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18
2AP000MR00307-08040 | EOF: 621-G-303 A Oily Water Transfer Pump | [33 empty] | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18
2AP000IC06807-08100 | EOF : Delivery of Integrated Control And Safety System (ICSS) - First Lot | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AP000IC05507-08005 | EOF : Delivery of Flowmeters - Last Lot-3 | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AP000IC04407-08010 | EOF : Delivery of Instrumentation Cable Tray- Lot-3 | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AP000IC04407-08005 | EOF : Delivery of Instrumentation Cable Tray- Lot-2 | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AP000IC04407-08000 | EOF : Delivery of Instrumentation Cable Tray- Lot-1 | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AP000IC04307-08010 | EOF : Delivery of Sunshade-Lot-3 | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AP000IC04307-08005 | EOF : Delivery of Sunshade-Lot-2 | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AP000IC04307-08000 | EOF : Delivery of Sunshade-Lot-1 | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AP000IC04207-08010 | EOF : Delivery of Instrumentation Tubes & Fittings-Lot-3 | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AP000IC04207-08005 | EOF : Delivery of Instrumentation Tubes & Fittings-Lot-2 | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AP000IC04207-08000 | EOF : Delivery of Instrumentation Tubes & Fittings-Lot-1 | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AP000IC04007-08010 | EOF : Delivery of Instrumentation other misc Bulk Materials- Lot-3 | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AP000IC04007-08005 | EOF : Delivery of Instrumentation other misc Bulk Materials- Lot-2 | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AP000IC04007-08000 | EOF : Delivery of Instrumentation other misc Bulk Materials- Lot-1 | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AP000IC03507-08010 | EOF : Delivery of Instrument Cable Glands - Lot-3 | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AP000IC03507-08005 | EOF : Delivery of Instrument Cable Glands - Lot-2 | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AP000IC03507-08000 | EOF : Delivery of Instrument Cable Glands - Lot-1 | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AP000IC03407-08010 | EOF : Delivery of Instrument Junction Boxes - Lot-3 | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AP000IC03407-08005 | EOF : Delivery of Instrument Junction Boxes - Lot-2 | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AP000IC03407-08000 | EOF : Delivery of Instrument Junction Boxes - Lot-1 | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AP000IC03307-08010 | EOF : Delivery of Instrumentation Cable- Lot-3 | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AP000IC03307-08005 | EOF : Delivery of Instrumentation Cable- Lot-2 | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AP000IC03307-08000 | EOF : Delivery of Instrumentation Cable- Lot-1 | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AP000IC02607-08005 | EOF : Delivery of Flowmeters - Lot-2 | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AP000IC02207-08005 | EOF : Delivery of Flowmeters - First Lot-1 | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AP000IC01807-08015 | EOF : Delivery of Level Transmitters & Level Switches - Last Lot -3 | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AP000IC01707-08010 | EOF : Delivery of Level Transmitters & Level Switches - Lot - 2 | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AP000IC01407-08010 | EOF : Delivery of Level Transmitters & Level Switches - First Lot - 1 | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AP000IC01307-08000 | EOF : Delivery of Level Gauges, Pressure Gauges & Temperature Guages - Last Lot-3 | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AP000IC01007-08000 | EOF : Delivery of Level Gauges, Pressure Gauges & Temperature Guages - Lot-2 | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AP000IC00907-08000 | EOF : Delivery of Level Gauges, Pressure Gauges & Temperature Guages - First Lot-1 | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AP000IC00407-08010 | EOF : Delivery of Motor Operated Valves (Ball/Butterfly/Gate Type) - Last Lot-3 | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AP000IC00407-08005 | EOF : Delivery of Motor Operated Valves (Ball/Butterfly/Gate Type) - Lot-2 | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AP000IC00407-08000 | EOF : Delivery of Motor Operated Valves (Ball/Butterfly/Gate Type) - First Lot-1 | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AP000IC00207-08010 | EOF : Delivery of Shutdown Valves (Ball/Butterfly Type) & ESD Valves - Last Lot-3 | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AP000IC00207-08005 | EOF : Delivery of Shutdown Valves (Ball/Butterfly Type) & ESD Valves - Lot-2 | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AP000IC00207-08000 | EOF : Delivery of Shutdown Valves (Ball/Butterfly Type) & ESD Valves - First Lot-1 | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AP000IC00107-08010 | EOF : Delivery of Control Valves - Last Lot-3 | [33 empty] | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05
2AP000IC00107-08005 | EOF : Delivery of Control Valves - Lot-2 | [33 empty] | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05
2AP000IC00107-08000 | EOF : Delivery of Control Valves - First Lot-1 | [33 empty] | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05
2AP000HS00507-08035 | EOF: 621-G-302 D Foam Pump | [33 empty] | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07
2AP000HS00507-08030 | EOF: 621-G-302 C Foam Pump | [33 empty] | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07
2AP000HS00507-08025 | EOF: 621-G-302 B Foam Pump | [33 empty] | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07
2AP000HS00507-08020 | EOF: 621-G-302 A Foam Pump | [33 empty] | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07
2AP000HS00507-08015 | EOF: Foam drain tank-52-D-305B | [21 empty] | 2017-04-17 | 2017-04-17 | 2017-04-17 | 2017-04-17 | 2017-04-17 | 2017-04-17 | 2017-04-17 | 2017-04-17 | 2017-04-17 | 2017-04-17 | 2017-04-17 | 2017-04-17 | 2017-04-17 | 2017-04-17 | 2017-04-17 | 2017-04-17 | 2017-04-17 | 2017-04-17 | 2017-04-17 | 2017-04-17 | 2017-04-17 | 2017-04-17 | 2017-04-17 | 2017-04-17 | 2017-04-17
2AP000HS00507-08010 | EOF: Foam drain tank-52-D-305A | [21 empty] | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16
2AP000HS00507-08005 | 52-Z-301 B: Foam System Package Incl. 52-D-303 A/B; 52-D-307 A-D; 52-G-302 A-D | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AP000HS00507-08000 | 52-Z-301 A: Foam System Package Incl. 52-D-303 A/B; 52-D-307 A-D; 52-G-302 A-D | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AP000HS00207-08105 | EOF: Delivery of Safety Equipments - Last Lot
2AP000HS00207-08100 | EOF: Delivery of Safety Equipments - First Lot
2AP000HS00107-08105 | EOF: Delivery of Fire fighting Equipments - Last Lot
2AP000HS00107-08100 | EOF: Delivery of Fire fighting Equipments - First Lot
2AP000EL02607-08005 | ELECTRICAL HEAT TRACING SYSTEM- Final Lot | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AP000EL02607-08000 | ELECTRICAL HEAT TRACING SYSTEM - First Lot | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AP000EL02407-08010 | EOF : Delivery of Cable Glands - Last Lot - 3 | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AP000EL02407-08005 | EOF : Delivery of Cable Glands - Lot - 2 | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AP000EL02407-08000 | EOF : Delivery of Cable Glands - First Lot - 1 | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AP000EL02307-08010 | EOF : Delivery of Cable Termination & Jointing Kits - Last Lot - 3 | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AP000EL02307-08005 | EOF : Delivery of Cable Termination & Jointing Kits - Lot - 2 | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AP000EL02307-08000 | EOF : Delivery of Cable Termination & Jointing Kits - First Lot - 1 | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AP000EL02207-08010 | EOF : Delivery of Electrical Cable Trays, Cable Ladders & Accessories - Last Lot-3 | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AP000EL02207-08005 | EOF : Delivery of Electrical Cable Trays, Cable Ladders & Accessories - Lot-2 | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AP000EL02207-08000 | EOF : Delivery of Electrical Cable Trays, Cable Ladders & Accessories - First Lot-1 | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AP000EL02107-08010 | EOF : Delivery of Earthing & Lightning Protection Materials - Last Lot-3 | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AP000EL02107-08005 | EOF : Delivery of Earthing & Lightning Protection Materials - Lot-2 | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AP000EL02107-08000 | EOF : Delivery of Earthing & Lightning Protection Materials - First Lot-1 | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AP000EL01907-08010 | EOF : Delivery of Receptacles & Sockets - Last Lot-3 | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AP000EL01907-08005 | EOF : Delivery of Receptacles & Sockets - Lot-2 | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AP000EL01907-08000 | EOF : Delivery of Receptacles & Sockets - First Lot-1 | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AP000EL01807-08010 | EOF : Delivery of Junction Box - Last Lot-3 | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AP000EL01807-08005 | EOF : Delivery of Junction Box - Lot-2 | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AP000EL01807-08000 | EOF : Delivery of Junction Box - First Lot-1 | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AP000EL01707-08010 | EOF : Delivery of Junction Box - Last Lot-3 | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AP000EL01707-08005 | EOF : Delivery of Junction Box - Lot-2 | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AP000EL01707-08000 | EOF : Delivery of Junction Box - First Lot-1 | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AP000EL01407-08010 | EOF : Delivery of Lighting Poles & Lighting Fixtures - Last Lot-3 | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AP000EL01407-08005 | EOF : Delivery of Lighting Poles & Lighting Fixtures - Lot-2 | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AP000EL01407-08000 | EOF : Delivery of Lighting Poles & Lighting Fixtures - First Lot-1 | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AP000EL01007-08020 | HAZARDOUS TYPE LIGHTING & POWER PANELS- Final Lot | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AP000EL01007-08015 | HAZARDOUS TYPE LIGHTING & POWER PANELS - First Lot | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AP000EL01007-08011 | EOF : Delivery of Interposing Relay Panel | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AP000EL01007-08010 | INDUSTRIAL TYPE LIGHTING & POWER PANELS- Final Lot | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AP000EL01007-08005 | INDUSTRIAL TYPE LIGHTING & POWER PANELS - First Lot | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AP000EL00907-08010 | EOF : Delivery of HV & LV (Power, Control & Earthing) Cable - Last Lot-3 | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AP000EL00907-08005 | EOF : Delivery of HV & LV (Power, Control & Earthing) Cable - Lot-2 | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AP000EL00907-08000 | EOF : Delivery of HV & LV (Power, Control & Earthing) Cable - First Lot-1 | [31 empty] | 2018-02-25 | 2018-02-25 | 2018-02-25 | 2018-02-25 | 2018-02-25 | 2018-02-25 | 2018-02-25 | 2018-02-25 | 2018-02-25 | 2018-02-25 | 2018-02-25 | 2018-02-25 | 2018-02-25 | 2018-02-25 | 2018-02-25
2AP000EL00807-08005 | E-SCADA SYSTEM lot 2 | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AP000EL00807-08000 | E-SCADA SYSTEM Lot 1 | [31 empty] | 2018-03-11 | 2018-03-11 | 2018-03-11 | 2018-03-11 | 2018-03-11 | 2018-03-11 | 2018-03-11 | 2018-03-11 | 2018-03-11 | 2018-03-11 | 2018-03-11 | 2018-03-11 | 2018-03-11 | 2018-03-11 | 2018-03-11
2AP000EL00707-08005 | AC UPS & DC UPS- Final Lot | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AP000EL00707-08000 | AC UPS & DC UPS - First Lot | [29 empty] | 2018-01-24 | 2018-01-24 | 2018-01-24 | 2018-01-24 | 2018-01-24 | 2018-01-24 | 2018-01-24 | 2018-01-24 | 2018-01-24 | 2018-01-24 | 2018-01-24 | 2018-01-24 | 2018-01-24 | 2018-01-24 | 2018-01-24 | 2018-01-24 | 2018-01-24
2AP000EL00607-08005 | 440V LV SWITCHGEAR & LV BUSDUCT- Final Lot | [29 empty] | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26
2AP000EL00607-08000 | 440V LV SWITCHGEAR & LV BUSDUCT - First Lot | [25 empty] | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18
2AP000EL00507-08005 | EMERGENCY DIESEL GENERATOR SETS- Final Lot | [31 empty] | 2018-03-08 | 2018-03-08 | 2018-03-08 | 2018-03-08 | 2018-03-08 | 2018-03-08 | 2018-03-08 | 2018-03-08 | 2018-03-08 | 2018-03-08 | 2018-03-08 | 2018-03-08 | 2018-03-08 | 2018-03-08 | 2018-03-08
2AP000EL00507-08000 | EMERGENCY DIESEL GENERATOR SETS - First Lot | [33 empty] | 2018-03-29 | 2018-03-29 | 2018-03-29 | 2018-03-29 | 2018-03-29 | 2018-03-29 | 2018-03-29 | 2018-03-29 | 2018-03-29 | 2018-03-29 | 2018-03-29 | 2018-03-29 | 2018-03-29
2AP000EL00207-08010 | Transformer Rectifier | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AP000EL00207-08005 | DISTRIBUTION & LIGHTING TRANSFORMER- Final Lot | [29 empty] | 2018-01-14 | 2018-01-14 | 2018-01-14 | 2018-01-14 | 2018-01-14 | 2018-01-14 | 2018-01-14 | 2018-01-14 | 2018-01-14 | 2018-01-14 | 2018-01-14 | 2018-01-14 | 2018-01-14 | 2018-01-14 | 2018-01-14 | 2018-01-14 | 2018-01-14
2AP000EL00207-08000 | DISTRIBUTION & LIGHTING TRANSFORMER - First Lot | [21 empty] | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09
2AP000EL00107-08005 | 11KV & 3.3KV SWITCHGEAR & HV BUSDUCT- Final Lot | [29 empty] | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26
2AP000EL00107-08000 | 11KV & 3.3KV SWITCHGEAR & HV BUSDUCT - First Lot | [25 empty] | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18
2AI151CV99940-08010 | EOF: Delivery of steel for Pipesupports, EIT/HSE supports & misc steel (handrails, ladders,etc) - Lot-3 | [33 empty] | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15
2AI151CV99940-08005 | EOF: Delivery of Structural steel for Ground Support Platforms - Lot-3 | [33 empty] | 2018-04-22 | 2018-04-22 | 2018-04-22 | 2018-04-22 | 2018-04-22 | 2018-04-22 | 2018-04-22 | 2018-04-22 | 2018-04-22 | 2018-04-22 | 2018-04-22 | 2018-04-22 | 2018-04-22
2AI151CV99940-08000 | EOF: Delivery of Structural steel for Shelters - Lot-3 | [29 empty] | 2018-01-04 | 2018-01-04 | 2018-01-04 | 2018-01-04 | 2018-01-04 | 2018-01-04 | 2018-01-04 | 2018-01-04 | 2018-01-04 | 2018-01-04 | 2018-01-04 | 2018-01-04 | 2018-01-04 | 2018-01-04 | 2018-01-04 | 2018-01-04 | 2018-01-04
2AI151CV99930-08010 | EOF: Delivery of steel for Pipesupports, EIT/HSE supports & misc steel (handrails, ladders,etc) - Lot-2 | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AI151CV99930-08005 | EOF: Delivery of Structural steel for Ground Support Platforms - Lot-2 | [21 empty] | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18
2AI151CV99930-08000 | EOF: Delivery of Structural steel for Shelters - Lot-2 | [29 empty] | 2018-01-04 | 2018-01-04 | 2018-01-04 | 2018-01-04 | 2018-01-04 | 2018-01-04 | 2018-01-04 | 2018-01-04 | 2018-01-04 | 2018-01-04 | 2018-01-04 | 2018-01-04 | 2018-01-04 | 2018-01-04 | 2018-01-04 | 2018-01-04 | 2018-01-04
2AI151CV99920-08010 | EOF: Delivery of steel for Pipesupports, EIT/HSE supports & misc steel (handrails, ladders,etc) - Lot-1 | [33 empty] | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15
2AI151CV99920-08005 | EOF: Delivery of Structural steel for Ground Support Platforms - Lot-1 | [21 empty] | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16
2AI151CV99920-08000 | EOF: Delivery of Structural steel for Shelters - Lot-1 | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AI141TE01200-08010 | Leveling & Grouting | [29 empty] | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03
2AI141TE01200-08005 | Installation of Equipment/Panels | [29 empty] | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03
2AI141TE01200-08001 | Installation of Support Structures (wherever applicable) | [29 empty] | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03
2AI141TE01200-08000 | COCC CCR Building : Eqipment Inst. (CCTV, Access Control) | [29 empty] | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03
2AI141TE01200 | COCC CCR Building : Outdoor Eqipment Inst. (CCTV, Access Control) | [29 empty] | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03
2AI141TE01100-08035 | Tagging | [29 empty] | 2018-01-03: 2019-04-10
2AI141TE01100-08025 | Continuity Checks & Terminations | [29 empty] | 2018-01-03: 2019-04-10
2AI141TE01100-08015 | Glanding | [29 empty] | 2018-01-03: 2019-04-10
2AI141TE01100-08010 | COCC: Splicing of FO Cable | [29 empty] | 2018-01-03: 2019-04-10
2AI141TE01100-08006 | COCC: Cable Laying (FO, Coaxial, bare etc) | [29 empty] | 2018-01-03: 2019-04-10
2AI141TE01100-08005 | COCC CCR Building : Cable Terminations & continuity checks | [29 empty] | 2018-01-03: 2019-04-10
2AI141TE01100-08001 | Cable Drum Checks & Transport to Site | [29 empty] | 2018-01-03: 2019-04-10
2AI141TE01100-08000 | COCC CCR Building : FO & Telephone Cabling works | [29 empty] | 2018-01-03: 2019-04-10
2AI141TE01100 | COCC CCR Building : FO & Telephone Cabling, Cable Terminations & continuity checks | [29 empty] | 2018-01-03: 2019-04-10
2AI141TE01000-08020 | Leveling & Grouting | [35 empty] | 2018-06-06 | 2018-06-06 | 2018-06-06 | 2018-06-06 | 2018-06-06 | 2018-06-06 | 2018-06-06 | 2018-06-06 | 2018-06-06 | 2018-06-06 | 2018-06-06
2AI141TE01000-08015 | Installation of Equipment/Panels | [35 empty] | 2018-06-06 | 2018-06-06 | 2018-06-06 | 2018-06-06 | 2018-06-06 | 2018-06-06 | 2018-06-06 | 2018-06-06 | 2018-06-06 | 2018-06-06 | 2018-06-06
2AI141TE01000-08001 | Fabrication & Installation of Supports / Frames | [35 empty] | 2018-06-06 | 2018-06-06 | 2018-06-06 | 2018-06-06 | 2018-06-06 | 2018-06-06 | 2018-06-06 | 2018-06-06 | 2018-06-06 | 2018-06-06 | 2018-06-06
2AI141TE01000-08000 | COCC CCR Building : Cabinet and Panel Installation | [35 empty] | 2018-06-06 | 2018-06-06 | 2018-06-06 | 2018-06-06 | 2018-06-06 | 2018-06-06 | 2018-06-06 | 2018-06-06 | 2018-06-06 | 2018-06-06 | 2018-06-06
2AI141TE01000 | COCC CCR Building : Cabinet and Panel Installation | [35 empty] | 2018-06-06 | 2018-06-06 | 2018-06-06 | 2018-06-06 | 2018-06-06 | 2018-06-06 | 2018-06-06 | 2018-06-06 | 2018-06-06 | 2018-06-06 | 2018-06-06
2AI141PC03100-08005 | COCC: Lux testing | [25 empty] | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14
2AI141PC03100-08001 | COCC: Continuity & IR testing | [25 empty] | 2017-08-12 | 2017-08-12 | 2017-08-12 | 2017-08-12 | 2017-08-12 | 2017-08-12 | 2017-08-12 | 2017-08-12 | 2017-08-12 | 2017-08-12 | 2017-08-12 | 2017-08-12 | 2017-08-12 | 2017-08-12 | 2017-08-12 | 2017-08-12 | 2017-08-12 | 2017-08-12 | 2017-08-12 | 2017-08-12 | 2017-08-12
2AI141PC03100-08000 | COCC: EOF SS 50-SUBST-001 : Lighting & Small Power | [25 empty] | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14
2AI141PC03100 | COCC: EOF SS 50-SUBST-001 : Lighting & Small Power | [25 empty] | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14
2AI141PC03000-08010 | COCC: EOF SS 50-SUBST-001 : Energize EDG Building 50-R-002
2AI141PC03000-08001 | COCC: GCP Testing, Switch Gear Testing | [25 empty] | 2017-08-14: 2019-04-10
2AI141PC03000-08000 | COCC: EOF SS 50-SUBST-001 : Energize EDG Building 50-R-002
2AI141PC03000 | COCC: EOF SS 50-SUBST-001 : Energize EDG Building 50-R-002
2AI141PC02900-08015 | EOF: Ready for Energisation of Substation 50-SUBST-001 | [25 empty] | 2017-08-14: 2019-04-20
2AI141PC02900-08010 | EOF: Cable Termination | [25 empty] | 2017-08-14: 2019-04-19
2AI141PC02900-08005 | COCC: Incoming HV cables hipot testing | [25 empty] | 2017-08-14: 2019-04-17
2AI141PC02900-08001 | COCC: Incoming cables IR and continuity test | [25 empty] | 2017-08-14: 2019-04-15
2AI141PC02900-08000 | COCC: EOF SS 50-SUBST-001 : Electrical Tie-ins for Permanent Power & Energize | [25 empty] | 2017-08-14: 2019-04-20
2AI141PC02900 | COCC: EOF SS 50-SUBST-001 : Electrical Tie-ins for Permanent Power & Energize | [25 empty] | 2017-08-14: 2019-04-20
2AI141PC02700-08010 | EOF:BDV Testing | [25 empty] | 2017-08-14: 2018-12-28; 2017-08-14: 2018-12-28; 2017-08-14: 2018-12-28; 2017-08-14: 2018-12-28; 2017-08-14: 2018-12-28
2AI141PC02700-08005 | EOF:Functional Test | [25 empty] | 2017-08-14: 2018-12-27; 2017-08-14: 2018-12-27; 2017-08-14: 2018-12-27; 2017-08-14: 2018-12-27; 2017-08-14: 2018-12-27
2AI141PC02700-08001 | EOF:IR testing/WR testing/Turns ratio testing | [25 empty] | 2017-08-14: 2018-12-26; 2017-08-14: 2018-12-26; 2017-08-14: 2018-12-26; 2017-08-14: 2018-12-26; 2017-08-14: 2018-12-26
2AI141PC02700-08000 | COCC: EOF SS 50-SUBST-001 : Transformer Testing | [25 empty] | 2017-08-14: 2018-12-28; 2017-08-14: 2018-12-28; 2017-08-14: 2018-12-28; 2017-08-14: 2018-12-28; 2017-08-14: 2018-12-28
2AI141PC02700 | COCC: EOF SS 50-SUBST-001 : Transformer Testing | [25 empty] | 2017-08-14: 2018-12-28; 2017-08-14: 2018-12-28; 2017-08-14: 2018-12-28; 2017-08-14: 2018-12-28; 2017-08-14: 2018-12-28
2AI141PC02600-08010 | COCC: Discharging test | [25 empty] | 2017-08-14: 2019-02-02; 2017-08-14: 2019-02-02; 2017-08-14: 2019-02-02
2AI141PC02600-08005 | COCC: Charging test | [25 empty] | 2017-08-14: 2019-02-01; 2017-08-14: 2019-02-01; 2017-08-14: 2019-02-01
2AI141PC02600-08001 | COCC: Polarity check | [25 empty] | 2017-08-14: 2019-02-01; 2017-08-14: 2019-02-01; 2017-08-14: 2019-02-01
2AI141PC02600-08000 | COCC: EOF SS 50-SUBST-001 : 110V AC UPS | [25 empty] | 2017-08-14: 2019-02-02; 2017-08-14: 2019-02-02; 2017-08-14: 2019-02-02
2AI141PC02600 | COCC: EOF SS 50-SUBST-001 : 110V AC UPS | [25 empty] | 2017-08-14: 2019-02-02; 2017-08-14: 2019-02-02; 2017-08-14: 2019-02-02
2AI141PC02400-08025 | EOF: Stability Testing | [25 empty] | 2017-08-14: 2019-02-01; 2017-08-14: 2019-02-01; 2017-08-14: 2019-02-01
2AI141PC02400-08020 | EOF: Hi-pot Test | [25 empty] | 2017-08-14: 2019-02-01; 2017-08-14: 2019-02-01; 2017-08-14: 2019-02-01
2AI141PC02400-08015 | EOF Primary Injection Testing | [25 empty] | 2017-08-14: 2019-01-13; 2017-08-14: 2019-01-13; 2017-08-14: 2019-01-13
2AI141PC02400-08010 | EOF: Relay & Functional Testing | [25 empty] | 2017-08-14: 2018-12-26; 2017-08-14: 2018-12-26; 2017-08-14: 2018-12-26; 2017-08-14: 2018-12-26; 2017-08-14: 2018-12-26
2AI141PC02400-08005 | EOF: IR, Ductor testing | [25 empty] | 2017-08-14: 2019-01-11; 2017-08-14: 2019-01-11; 2017-08-14: 2019-01-11; 2017-08-14: 2019-01-11; 2017-08-14: 2019-01-11
2AI141PC02400-08001 | EOF: CT,PT Testing | [25 empty] | 2017-08-14: 2018-12-26; 2017-08-14: 2018-12-26; 2017-08-14: 2018-12-26; 2017-08-14: 2018-12-26; 2017-08-14: 2018-12-26
2AI141PC02400-08000 | COCC: EOF SS 50-SUBST-001 : LV Switchgear testing | [25 empty] | 2017-08-14: 2019-02-01; 2017-08-14: 2019-02-01; 2017-08-14: 2019-02-01
2AI141PC02400 | COCC: EOF SS 50-SUBST-001 : LV Switchgear testing | [25 empty] | 2017-08-14: 2019-02-01; 2017-08-14: 2019-02-01; 2017-08-14: 2019-02-01
2AI141PC02300-08010 | COCC: Discharging test | [25 empty] | 2017-08-14: 2019-03-29; 2017-08-14: 2019-03-29; 2017-08-14: 2019-03-29
2AI141PC02300-08005 | COCC: Charging test | [25 empty] | 2017-08-14: 2019-03-26; 2017-08-14: 2019-03-26; 2017-08-14: 2019-03-26
2AI141PC02300-08001 | COCC: Polarity check | [25 empty] | 2017-08-14: 2019-03-25; 2017-08-14: 2019-03-25; 2017-08-14: 2019-03-25
2AI141PC02300-08000 | COCC: EOF SS 50-SUBST-001 : 24V DC Battery Charger | [25 empty] | 2017-08-14: 2019-03-29; 2017-08-14: 2019-03-29; 2017-08-14: 2019-03-29
2AI141PC02300 | COCC: EOF SS 50-SUBST-001 : 24V DC Battery Charger | [25 empty] | 2017-08-14: 2019-03-29; 2017-08-14: 2019-03-29; 2017-08-14: 2019-03-29
2AI141PC02200-08025 | EOF: Stability Testing | [25 empty] | 2017-08-14: 2019-01-11; 2017-08-14: 2019-01-11; 2017-08-14: 2019-01-11; 2017-08-14: 2019-01-11; 2017-08-14: 2019-01-11
2AI141PC02200-08020 | EOF: Hi-pot Test | [25 empty] | 2017-08-14: 2019-01-11; 2017-08-14: 2019-01-11; 2017-08-14: 2019-01-11; 2017-08-14: 2019-01-11; 2017-08-14: 2019-01-11
2AI141PC02200-08015 | EOF Primary Injection Testing | [25 empty] | 2017-08-14: 2019-01-11; 2017-08-14: 2019-01-11; 2017-08-14: 2019-01-11; 2017-08-14: 2019-01-11; 2017-08-14: 2019-01-11
2AI141PC02200-08010 | EOF: Relay & Functional Testing | [25 empty] | 2017-08-14: 2019-01-10; 2017-08-14: 2019-01-10; 2017-08-14: 2019-01-10; 2017-08-14: 2019-01-10; 2017-08-14: 2019-01-10
2AI141PC02200-08005 | EOF: IR, Ductor testing | [25 empty] | 2017-08-14: 2019-01-10; 2017-08-14: 2019-01-10; 2017-08-14: 2019-01-10; 2017-08-14: 2019-01-10; 2017-08-14: 2019-01-10
2AI141PC02200-08001 | EOF: CT,PT,Breaker Testing | [25 empty] | 2017-08-14: 2019-01-10; 2017-08-14: 2019-01-10; 2017-08-14: 2019-01-10; 2017-08-14: 2019-01-10; 2017-08-14: 2019-01-10
2AI141PC02200-08000 | COCC: EOF SS 50-SUBST-001 : HV Switchgear testing | [25 empty] | 2017-08-14: 2019-01-11; 2017-08-14: 2019-01-11; 2017-08-14: 2019-01-11; 2017-08-14: 2019-01-11; 2017-08-14: 2019-01-11
2AI141PC02200 | COCC: EOF SS 50-SUBST-001 : HV Switchgear testing | [25 empty] | 2017-08-14: 2019-01-11; 2017-08-14: 2019-01-11; 2017-08-14: 2019-01-11; 2017-08-14: 2019-01-11; 2017-08-14: 2019-01-11
2AI141PC02100-08005 | COCC: Earth resistance measurement | [25 empty] | 2017-08-14: 2019-02-01; 2017-08-14: 2019-02-01; 2017-08-14: 2019-02-01
2AI141PC02100-08001 | COCC: Continuity testing | [25 empty] | 2017-08-14: 2019-04-10
2AI141PC02100-08000 | COCC: EOF SS 50-SUBST-001 : SS Earthing & Lightning | [25 empty] | 2017-08-14: 2019-04-10
2AI141PC02100 | COCC: EOF SS 50-SUBST-001 : SS Earthing & Lightning | [25 empty] | 2017-08-14: 2019-04-10
2AI141PC02000-08010 | COCC: Discharging test | [25 empty] | 2017-08-14: 2019-03-26; 2017-08-14: 2019-03-26; 2017-08-14: 2019-03-26
2AI141PC02000-08005 | COCC: Charging test | [25 empty] | 2017-08-14: 2019-03-25; 2017-08-14: 2019-03-25; 2017-08-14: 2019-03-25
2AI141PC02000-08001 | COCC: Polarity check | [25 empty] | 2017-08-14: 2019-03-25; 2017-08-14: 2019-03-25; 2017-08-14: 2019-03-25
2AI141PC02000-08000 | COCC: EOF SS 50-SUBST-001 : 110V DC Battery Charger | [25 empty] | 2017-08-14: 2019-03-26; 2017-08-14: 2019-03-26; 2017-08-14: 2019-03-26
2AI141PC02000 | COCC: EOF SS 50-SUBST-001 : 110V DC Battery Charger | [25 empty] | 2017-08-14: 2019-03-26; 2017-08-14: 2019-03-26; 2017-08-14: 2019-03-26
2AI141PC01000-08000 | COCC CCR Building : ICSS SAT
2AI141PC01000 | COCC CCR Building : ICSS SAT
2AI141IC01500-08005 | COCC CCR Building : Other Equipment & Panels Installation | [25 empty] | 2017-08-14: 2019-04-10
2AI141IC01500-08000 | COCC CCR Building : ICSS installation | [35 empty] | 2018-06-22 | 2018-06-22 | 2018-06-22 | 2018-06-22 | 2018-06-22 | 2018-06-22 | 2018-06-22 | 2018-06-22 | 2018-06-22 | 2018-06-22 | 2018-06-22
2AI141IC01500 | COCC CCR Building : Equipment & Panels Installation (ICSS) | [35 empty] | 2018-06-22: 2019-04-10
2AI141IC01300-08000 | COCC CCR Building : Panel base frame Installation | [35 empty] | 2018-06-22 | 2018-06-22 | 2018-06-22 | 2018-06-22 | 2018-06-22 | 2018-06-22 | 2018-06-22 | 2018-06-22 | 2018-06-22 | 2018-06-22 | 2018-06-22
2AI141IC01300 | COCC CCR Building : Panel base frame Installation | [35 empty] | 2018-06-22 | 2018-06-22 | 2018-06-22 | 2018-06-22 | 2018-06-22 | 2018-06-22 | 2018-06-22 | 2018-06-22 | 2018-06-22 | 2018-06-22 | 2018-06-22
2AI141IC01200-08005 | COCC: Cable Glanding and Termination | [39 empty] | 2018-10-19 | 2018-10-19 | 2018-10-19 | 2018-10-19 | 2018-10-19 | 2018-10-19 | 2018-10-19
2AI141IC01200-08000 | COCC: Instrument Cable Laying | [39 empty] | 2018-09-29 | 2018-09-29 | 2018-09-29 | 2018-09-29 | 2018-09-29 | 2018-09-29 | 2018-09-29
2AI141IC01200 | COCC CCR Building : Field & Building Cable laying, glanding & termination | [39 empty] | 2018-10-19 | 2018-10-19 | 2018-10-19 | 2018-10-19 | 2018-10-19 | 2018-10-19 | 2018-10-19
2AI141IC01100-08010 | COCC:Leveling & Grouting | [35 empty] | 2018-06-22: 2019-04-10
2AI141IC01100-08005 | COCC: Installation of Junction Boxes | [37 empty] | 2018-08-17 | 2018-08-17 | 2018-08-17 | 2018-08-17 | 2018-08-17 | 2018-08-17 | 2018-08-17 | 2018-08-17 | 2018-08-17
2AI141IC01100-08001 | COCC: Installation of supports | [35 empty] | 2018-07-27 | 2018-07-27 | 2018-07-27 | 2018-07-27 | 2018-07-27 | 2018-07-27 | 2018-07-27 | 2018-07-27 | 2018-07-27 | 2018-07-27 | 2018-07-27
2AI141IC01100-08000 | COCC CCR Field & Building : Junction Boxes | [35 empty] | 2018-07-27: 2019-04-10
2AI141IC01100 | COCC CCR Building : Field Junction Boxes | [35 empty] | 2018-07-27: 2019-04-10
2AI141IC01000-08005 | COCC: Field & Building Conduits Installation | [35 empty] | 2018-05-28 | 2018-05-28 | 2018-05-28 | 2018-05-28 | 2018-05-28 | 2018-05-28 | 2018-05-28 | 2018-05-28 | 2018-05-28 | 2018-05-28 | 2018-05-28
2AI141IC01000-08001 | COCC: Field & Building Cable Trays Installation | [37 empty] | 2018-08-02 | 2018-08-02 | 2018-08-02 | 2018-08-02 | 2018-08-02 | 2018-08-02 | 2018-08-02 | 2018-08-02 | 2018-08-02
2AI141IC01000-08000 | COCC CCR Field & Building : Field & Building Cable Trays and Conduits | [37 empty] | 2018-08-02 | 2018-08-02 | 2018-08-02 | 2018-08-02 | 2018-08-02 | 2018-08-02 | 2018-08-02 | 2018-08-02 | 2018-08-02
2AI141IC01000 | COCC CCR Building : Field & Building Cable Trays and Conduits | [37 empty] | 2018-08-02 | 2018-08-02 | 2018-08-02 | 2018-08-02 | 2018-08-02 | 2018-08-02 | 2018-08-02 | 2018-08-02 | 2018-08-02
2AI141EL01200-08005 | COCC: Electrical Panels Installation | [37 empty] | 2018-08-02: 2019-03-06; 2018-08-02: 2019-03-06; 2018-08-02: 2019-03-06
2AI141EL01200-08000 | COCC: Electrical Equipment Installation | [37 empty] | 2018-08-02: 2019-03-06; 2018-08-02: 2019-03-06; 2018-08-02: 2019-03-06
2AI141EL01200 | COCC CCR Building : Electrical Equipment & Panels Installation | [37 empty] | 2018-08-02: 2019-03-06; 2018-08-02: 2019-03-06; 2018-08-02: 2019-03-06
2AI141EL01100-08040 | COCC: Tagging for HV cables | [33 empty] | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24
2AI141EL01100-08035 | COCC: Continuity Checks & Terminations for HV cables | [33 empty] | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24
2AI141EL01100-08030 | COCC: Cable Glanding for HV cables | [33 empty] | 2018-04-23 | 2018-04-23 | 2018-04-23 | 2018-04-23 | 2018-04-23 | 2018-04-23 | 2018-04-23 | 2018-04-23 | 2018-04-23 | 2018-04-23 | 2018-04-23 | 2018-04-23 | 2018-04-23
2AI141EL01100-08028 | COCC: Cable Laying - HV | [33 empty] | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04
2AI141EL01100-08025 | COCC: Tagging for LV cables | [33 empty] | 2018-04-04: 2019-03-16; 2018-04-04: 2019-03-16; 2018-04-04: 2019-03-16
2AI141EL01100-08020 | COCC: Continuity Checks & Terminations for LV cables | [33 empty] | 2018-04-04: 2019-03-16; 2018-04-04: 2019-03-16; 2018-04-04: 2019-03-16
2AI141EL01100-08015 | COCC: Cable Glanding for LV cables | [33 empty] | 2018-04-04: 2019-03-15; 2018-04-04: 2019-03-15; 2018-04-04: 2019-03-15
2AI141EL01100-08011 | COCC: Installcable trays covers | [35 empty] | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04
2AI141EL01100-08010 | COCC CCR Field & Building : Electrical Cable Laying | [35 empty] | 2018-07-04: 2019-03-16; 2018-07-04: 2019-03-16; 2018-07-04: 2019-03-16
2AI141EL01100-08007 | COCC: Install cable trays | [35 empty] | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04
2AI141EL01100-08006 | COCC: Cable Laying - LV | [39 empty] | 2018-11-01 | 2018-11-01 | 2018-11-01 | 2018-11-01 | 2018-11-01 | 2018-11-01 | 2018-11-01
2AI141EL01100-08005 | COCC CCR Field & Building : Electrical Cable Laying | [39 empty] | 2018-11-01 | 2018-11-01 | 2018-11-01 | 2018-11-01 | 2018-11-01 | 2018-11-01 | 2018-11-01
2AI141EL01100-08002 | COCC: Install Tray support | [35 empty] | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04
2AI141EL01100-08001 | COCC:Fabricate Tray Supports | [35 empty] | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04
2AI141EL01100-08000 | COCC CCR Field & Building : Install Electrical Cable trays & Supports | [35 empty] | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04
2AI141EL01100 | COCC CCR Building : Cable laying, glanding & termination | [35 empty] | 2018-07-04: 2019-03-16; 2018-07-04: 2019-03-16; 2018-07-04: 2019-03-16
2AI141EL01000-08028 | COCC: Earth Pit Installation | [39 empty] | 2018-10-14 | 2018-10-14 | 2018-10-14 | 2018-10-14 | 2018-10-14 | 2018-10-14 | 2018-10-14
2AI141EL01000-08025 | COCC: Earth cable Termination | [37 empty] | 2018-09-07 | 2018-09-07 | 2018-09-07 | 2018-09-07 | 2018-09-07 | 2018-09-07 | 2018-09-07 | 2018-09-07 | 2018-09-07
2AI141EL01000-08020 | COCC: Earth Boss Installation | [35 empty] | 2018-07-23 | 2018-07-23 | 2018-07-23 | 2018-07-23 | 2018-07-23 | 2018-07-23 | 2018-07-23 | 2018-07-23 | 2018-07-23 | 2018-07-23 | 2018-07-23
2AI141EL01000-08015 | COCC: Earth Bus Installation | [37 empty] | 2018-08-28 | 2018-08-28 | 2018-08-28 | 2018-08-28 | 2018-08-28 | 2018-08-28 | 2018-08-28 | 2018-08-28 | 2018-08-28
2AI141EL01000-08010 | COCC: Cad welding | [37 empty] | 2018-08-28: 2019-03-22; 2018-08-28: 2019-03-22; 2018-08-28: 2019-03-22
2AI141EL01000-08005 | COCC: Earth Cable Laying | [37 empty] | 2018-08-24 | 2018-08-24 | 2018-08-24 | 2018-08-24 | 2018-08-24 | 2018-08-24 | 2018-08-24 | 2018-08-24 | 2018-08-24
2AI141EL01000-08001 | COCC: Earth rod Installation | [39 empty] | 2018-10-18 | 2018-10-18 | 2018-10-18 | 2018-10-18 | 2018-10-18 | 2018-10-18 | 2018-10-18
2AI141EL01000-08000 | COCC CCR Field & Building : Earthing & Lightning Protection Works(outside the Building) | [37 empty] | 2018-08-24: 2019-03-22; 2018-08-24: 2019-03-22; 2018-08-24: 2019-03-22
2AI141EL01000 | COCC CCR Field & Building : Earthing & Lightning Protection Works | [37 empty] | 2018-08-24: 2019-03-22; 2018-08-24: 2019-03-22; 2018-08-24: 2019-03-22
2AI141CV01100-08190 | COCC: Gate Installation & Speed bumbs | [15 empty] | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07
2AI141CV01100-08180 | COCC: Fix Railing/wire mesh installation | [19 empty] | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23
2AI141CV01100-08170 | COCC: Install/Cast insitu fencing fnds (including tie beams - if any) | [19 empty] | 2017-02-21 | 2017-02-21 | 2017-02-21 | 2017-02-21 | 2017-02-21 | 2017-02-21 | 2017-02-21 | 2017-02-21 | 2017-02-21 | 2017-02-21 | 2017-02-21 | 2017-02-21 | 2017-02-21 | 2017-02-21 | 2017-02-21 | 2017-02-21 | 2017-02-21 | 2017-02-21 | 2017-02-21 | 2017-02-21 | 2017-02-21 | 2017-02-21 | 2017-02-21 | 2017-02-21 | 2017-02-21 | 2017-02-21 | 2017-02-21
2AI141CV01100-08160 | COCC: Sub grade & Blinding | [19 empty] | 2017-02-19 | 2017-02-19 | 2017-02-19 | 2017-02-19 | 2017-02-19 | 2017-02-19 | 2017-02-19 | 2017-02-19 | 2017-02-19 | 2017-02-19 | 2017-02-19 | 2017-02-19 | 2017-02-19 | 2017-02-19 | 2017-02-19 | 2017-02-19 | 2017-02-19 | 2017-02-19 | 2017-02-19 | 2017-02-19 | 2017-02-19 | 2017-02-19 | 2017-02-19 | 2017-02-19 | 2017-02-19 | 2017-02-19 | 2017-02-19
2AI141CV01100-08150 | COCC: Survey marking & Excavation | [19 empty] | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18
2AI141CV01100-08145 | COCC : Backfill and Compaction (wherever applicable) | [19 empty] | 2017-02-18: 2019-03-08; 2017-02-18: 2019-03-08; 2017-02-18: 2019-03-08
2AI141CV01100-08140 | COCC : Installation of pre-cast foundations and Leveling | [19 empty] | 2017-02-18: 2019-03-06; 2017-02-18: 2019-03-06; 2017-02-18: 2019-03-06
2AI141CV01100-08135 | COCC: Backfill and Compaction | [31 empty] | 2018-01-28 | 2018-01-28 | 2018-01-28 | 2018-01-28 | 2018-01-28 | 2018-01-28 | 2018-01-28 | 2018-01-28 | 2018-01-28 | 2018-01-28 | 2018-01-28 | 2018-01-28 | 2018-01-28 | 2018-01-28 | 2018-01-28
2AI141CV01100-08130 | COCC : Blinding/PCC | [31 empty] | 2018-01-28: 2019-03-04; 2018-01-28: 2019-03-04; 2018-01-28: 2019-03-04
2AI141CV01100-08125 | COCC: Coating | [31 empty] | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27
2AI141CV01100-08120 | COCC : Survey Marking, Excavation & Subgrade preparation | [31 empty] | 2018-01-27: 2019-03-30
2AI141CV01100-08115 | COCC: Concrete Pouring | [29 empty] | 2018-01-13 | 2018-01-13 | 2018-01-13 | 2018-01-13 | 2018-01-13 | 2018-01-13 | 2018-01-13 | 2018-01-13 | 2018-01-13 | 2018-01-13 | 2018-01-13 | 2018-01-13 | 2018-01-13 | 2018-01-13 | 2018-01-13 | 2018-01-13 | 2018-01-13
2AI141CV01100-08110 | COCC : Concrete Protection | [31 empty] | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07
2AI141CV01100-08105 | COCC: Rebar, Formwork & PVC conduits installation(duct bank) | [29 empty] | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20
2AI141CV01100-08100 | COCC : Concrete Pouring | [25 empty] | 2017-08-01 | 2017-08-01 | 2017-08-01 | 2017-08-01 | 2017-08-01 | 2017-08-01 | 2017-08-01 | 2017-08-01 | 2017-08-01 | 2017-08-01 | 2017-08-01 | 2017-08-01 | 2017-08-01 | 2017-08-01 | 2017-08-01 | 2017-08-01 | 2017-08-01 | 2017-08-01 | 2017-08-01 | 2017-08-01 | 2017-08-01
2AI141CV01100-08095 | COCC: Subgrade and Blinding | [29 empty] | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22
2AI141CV01100-08090 | COCC : Prepare Mould/Formwork, Rebar & Insert embedments (at Pre-cast Yard) | [25 empty] | 2017-07-31 | 2017-07-31 | 2017-07-31 | 2017-07-31 | 2017-07-31 | 2017-07-31 | 2017-07-31 | 2017-07-31 | 2017-07-31 | 2017-07-31 | 2017-07-31 | 2017-07-31 | 2017-07-31 | 2017-07-31 | 2017-07-31 | 2017-07-31 | 2017-07-31 | 2017-07-31 | 2017-07-31 | 2017-07-31 | 2017-07-31
2AI141CV01100-08085 | COCC: Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material | [29 empty] | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22
2AI141CV01100-08080 | COCC : Backfill and Compaction (wherever applicable) | [29 empty] | 2018-01-22: 2019-04-13
2AI141CV01100-08075 | COCC:Install Route/saftey Markers
2AI141CV01100-08070 | COCC : Installation of pre-cast foundations and Leveling | [29 empty] | 2018-01-22: 2019-04-12
2AI141CV01100-08065 | COCC:Backfilling and Compaction | [29 empty] | 2018-01-22: 2018-11-22; 2018-01-22: 2018-11-22; 2018-01-22: 2018-11-22; 2018-01-22: 2018-11-22; 2018-01-22: 2018-11-22; 2018-01-22: 2018-11-22; 2018-01-22: 2018-11-22
2AI141CV01100-08060 | COCC : Blinding/PCC | [29 empty] | 2018-01-22: 2019-02-16; 2018-01-22: 2019-02-16; 2018-01-22: 2019-02-16
2AI141CV01100-08055 | COCC:Install Cable Tiles & Warning Tapes | [29 empty] | 2018-01-22: 2018-11-18; 2018-01-22: 2018-11-18; 2018-01-22: 2018-11-18; 2018-01-22: 2018-11-18; 2018-01-22: 2018-11-18; 2018-01-22: 2018-11-18; 2018-01-22: 2018-11-18
2AI141CV01100-08050 | COCC : Survey Marking, Excavation & Subgrade preparation | [29 empty] | 2018-01-22: 2019-02-16; 2018-01-22: 2019-02-16; 2018-01-22: 2019-02-16
2AI141CV01100-08045 | COCC:Backfilling with clean sand layer | [29 empty] | 2018-01-22: 2018-11-14; 2018-01-22: 2018-11-14; 2018-01-22: 2018-11-14; 2018-01-22: 2018-11-14; 2018-01-22: 2018-11-14; 2018-01-22: 2018-11-14; 2018-01-22: 2018-11-14
2AI141CV01100-08040 | COCC : Concrete Protection | [29 empty] | 2017-12-01 | 2017-12-01 | 2017-12-01 | 2017-12-01 | 2017-12-01 | 2017-12-01 | 2017-12-01 | 2017-12-01 | 2017-12-01 | 2017-12-01 | 2017-12-01 | 2017-12-01 | 2017-12-01 | 2017-12-01 | 2017-12-01 | 2017-12-01 | 2017-12-01
2AI141CV01100-08035 | COCC:Bedding (incl. clean sand layer) | [29 empty] | 2017-12-01: 2018-11-10; 2017-12-01: 2018-11-10; 2017-12-01: 2018-11-10; 2017-12-01: 2018-11-10; 2017-12-01: 2018-11-10; 2017-12-01: 2018-11-10; 2017-12-01: 2018-11-10
2AI141CV01100-08030 | COCC : Concrete Pouring | [27 empty] | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2017-11-24
2AI141CV01100-08025 | COCC: Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material | [27 empty] | 2017-11-24: 2018-11-07; 2017-11-24: 2018-11-07; 2017-11-24: 2018-11-07; 2017-11-24: 2018-11-07; 2017-11-24: 2018-11-07; 2017-11-24: 2018-11-07; 2017-11-24: 2018-11-07
2AI141CV01100-08021 | COCC : Prepare Mould/Formwork, Rebar & Insert embedments (at Pre-cast Yard) | [27 empty] | 2017-11-14 | 2017-11-14 | 2017-11-14 | 2017-11-14 | 2017-11-14 | 2017-11-14 | 2017-11-14 | 2017-11-14 | 2017-11-14 | 2017-11-14 | 2017-11-14 | 2017-11-14 | 2017-11-14 | 2017-11-14 | 2017-11-14 | 2017-11-14 | 2017-11-14 | 2017-11-14 | 2017-11-14
2AI141CV01100-08020 | COCC : Fence Works | [19 empty] | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23
2AI141CV01100-08015 | COCC : EIT Supports | [19 empty] | 2017-02-23: 2019-03-30
2AI141CV01100-08010 | COCC : Pipe Supports | [19 empty] | 2017-02-23: 2019-04-13
2AI141CV01100-08005 | COCC : EIT Duct banks | [31 empty] | 2018-01-28 | 2018-01-28 | 2018-01-28 | 2018-01-28 | 2018-01-28 | 2018-01-28 | 2018-01-28 | 2018-01-28 | 2018-01-28 | 2018-01-28 | 2018-01-28 | 2018-01-28 | 2018-01-28 | 2018-01-28 | 2018-01-28
2AI141CV01100-08000 | COCC : Trench (Manual Excavation)
2AI141CV01100 | COCC : Trench & other Civil Works (including construction scope for migration readiness)
2AI141CV01000-08100 | COCC : Site preparation (Including COCC Buliding,Carparking & Subsatation) | [21 empty] | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12
2AI141CV01000-08030 | COCC : Disposal of Surplus Material | [21 empty] | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29
2AI141CV01000-08025 | COCC : Grading, Filling & Compaction | [21 empty] | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12
2AI141CV01000-08020 | COCC : Grading, Cutting & Stockpiling | [21 empty] | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12
2AI141CV01000-08015 | COCC : Site clearance & Stripping & disposal of Contaminated material(If any) | [21 empty] | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29
2AI141CV01000-08005 | COCC :Excavation Notification | [9 empty] | 2016-04-24 | 2016-04-24 | 2016-04-24 | 2016-04-24 | 2016-04-24 | 2016-04-24 | 2016-04-24 | 2016-04-24 | 2016-04-24 | 2016-04-24 | 2016-04-24 | 2016-04-24 | 2016-04-24 | 2016-04-24 | 2016-04-24 | 2016-04-24 | 2016-04-24 | 2016-04-24 | 2016-04-24 | 2016-04-24 | 2016-04-24 | 2016-04-24 | 2016-04-24 | 2016-04-24 | 2016-04-24 | 2016-04-24 | 2016-04-24 | 2016-04-24 | 2016-04-24 | 2016-04-24 | 2016-04-24 | 2016-04-24 | 2016-04-24 | 2016-04-24 | 2016-04-24 | 2016-04-24 | 2016-04-24
2AI141CV01000-08001 | COCC :Verification of Survey for existing grade Level & Marking | [5 empty] | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18
2AI141CV01000 | COCC : Site preparation | [21 empty] | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12
2AI133TE41000-08010 | EOF:Cable Terminations & continuity checks | [21 empty] | 2017-05-12: 2019-04-10
2AI133TE41000-08005 | EOF:Installation - Telecom System | [29 empty] | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03
2AI133TE41000-08000 | EOF:FO & Telephone Cable Laying | [29 empty] | 2018-01-03: 2019-04-10
2AI133TE41000 | EOF EG Building 52-R-303 : FO & Telephone Cabling, Telecom System install, Cable Terminations & continuity checks | [29 empty] | 2018-01-03: 2019-04-10
2AI133TE31000-08010 | EOF:Cable Terminations & continuity checks | [29 empty] | 2018-01-03: 2019-04-10
2AI133TE31000-08005 | EOF:Installation - Telecom System | [29 empty] | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03
2AI133TE31000-08000 | EOF:FO & Telephone Cable Laying | [29 empty] | 2018-01-03: 2019-04-10
2AI133TE31000 | EOF EG Building 52-R-302 : FO & Telephone Cabling, Telecom System install, Cable Terminations & continuity checks | [29 empty] | 2018-01-03: 2019-04-10
2AI133TE21000-08005 | EOF EG Building 52-R-301 : Telecom system install, Cable Terminations & continuity checks | [29 empty] | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03
2AI133TE21000-08000 | EOF:FO & Telephone Cable Laying | [33 empty] | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24
2AI133TE21000 | EOF EG Building 52-R-301 : FO & Telephone Cabling, Telecom System install, Cable Terminations & continuity checks | [33 empty] | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24
2AI133TE11000-08010 | EOF:Cable Terminations & continuity checks | [33 empty] | 2018-04-24: 2019-04-10
2AI133TE11000-08005 | EOF:Installation - Telecom System | [29 empty] | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03
2AI133TE11000-08000 | EOF:FO & Telephone Cable Laying | [29 empty] | 2018-01-03: 2019-04-10
2AI133TE11000 | EOF EG Building 50-R-002 : FO & Telephone Cabling, Telecom System install, Cable Terminations & continuity checks | [29 empty] | 2018-01-03: 2019-04-10
2AI133TE07000-08010 | EOF:Cable Terminations & continuity checks | [33 empty] | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04
2AI133TE07000-08005 | EOF:Installation - Telecom System | [29 empty] | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03
2AI133TE07000-08000 | EOF:FO & Telephone Cable Laying | [29 empty] | 2018-01-03: 2019-04-10
2AI133TE07000 | EOF SS 52-SUBST-303 : FO & Telephone Cabling, Telecom System install, Cable Terminations & continuity checks | [29 empty] | 2018-01-03: 2019-04-10
2AI133TE05000-08010 | EOF:Cable Terminations & continuity checks | [33 empty] | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24
2AI133TE05000-08005 | EOF:Installation - Telecom System | [33 empty] | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04
2AI133TE05000-08000 | EOF:FO & Telephone Cable Laying | [33 empty] | 2018-04-04: 2019-04-10
2AI133TE05000 | EOF SS 52-SUBST-302 : FO & Telephone Cabling, Telecom System install, Cable Terminations & continuity checks | [33 empty] | 2018-04-04: 2019-04-10
2AI133TE03000-08010 | 621-SUBST-301 : Cable Terminations | [33 empty] | 2018-04-04: 2019-04-10
2AI133TE03000-08005 | 621-SUBST-301 : Installation - Telecom System | [29 empty] | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03
2AI133TE03000-08000 | 621-SUBST-301 : FO & Telephone Cable Laying | [35 empty] | 2018-06-06 | 2018-06-06 | 2018-06-06 | 2018-06-06 | 2018-06-06 | 2018-06-06 | 2018-06-06 | 2018-06-06 | 2018-06-06 | 2018-06-06 | 2018-06-06
2AI133TE03000 | EOF SS 52-SUBST-301 : FO & Telephone Cabling, Telecom System install, Cable Terminations & continuity checks | [35 empty] | 2018-06-06: 2019-04-10
2AI133TE01000-08025 | COCC: Cable Terminations & continuity checks | [35 empty] | 2018-06-06: 2019-04-10
2AI133TE01000-08021 | Cable Marking | [35 empty] | 2018-06-06: 2019-04-10
2AI133TE01000-08015 | COCC: Installation - Telecom System | [29 empty] | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03
2AI133TE01000-08011 | Cable Dressing & Fastening | [29 empty] | 2018-01-03: 2019-04-10
2AI133TE01000-08010 | 621-SUBST-0301 : Cable Terminations | [29 empty] | 2018-01-03: 2019-04-10
2AI133TE01000-08006 | Cable Pulling | [29 empty] | 2018-01-03: 2019-04-10
2AI133TE01000-08005 | 621-SUBST-0301 : Telephone System Installation | [29 empty] | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03
2AI133TE01000-08001 | Cable Drum Checks & Transport to Site | [29 empty] | 2018-01-03: 2019-04-10
2AI133TE01000-08000 | 621-SUBST-0301 : FO & Telephone Cabling Works | [29 empty] | 2018-01-03: 2019-04-10
2AI133TE01000 | COCC: SS 50-SUBST-001 : FO & Telephone Cabling, Telecom System install, Cable Terminations & continuity checks | [29 empty] | 2018-01-03: 2019-04-10
2AI133PC01500-08000 | EOF/COCC: Liquidation of pre-comm punch points ('B' items)
2AI133PC01500 | EOF/COCC: Liquidation of pre-comm punch points ('B' items)
2AI133PC01400-08000 | EOF:Floating Tanks / Mixers / Oily Water collection System / Drain / Oily Water transfer Pump
2AI133PC01400 | EOF:Floating Tanks / Mixers / Oily Water collection System / Drain / Oily Water transfer Pump
2AI133PC01300-08000 | EOF:Loading Mixing manifold / Trim Pumps / Auto sampling Package / drain Sump & Pump
2AI133PC01300 | EOF:Loading Mixing manifold / Trim Pumps / Auto sampling Package / drain Sump & Pump
2AI133PC01200-08000 | EOF:Filling / mixing manifold / Auto sampling Package / Pig receiver /Drain
2AI133PC01200 | EOF:Filling / mixing manifold / Auto sampling Package / Pig receiver /Drain
2AI133PC01100-08000 | EOF:Foam System Package / Overhead Water tank / Foam Concentrate tank / drains / Diesel Tanks/ Foam Pumps
2AI133PC01100 | EOF:Foam System Package / Overhead Water tank / Foam Concentrate tank / drains / Diesel Tanks/ Foam Pumps
2AI133PC01000-08000 | EOF:Fire Water Tie-In / Ring main & hydrants /Deluge System
2AI133PC01000 | EOF:Fire Water Tie-In / Ring main & hydrants /Deluge System
2AI133MS41000-08010 | EOF:Final Allignment & Grouting of Equipment | [33 empty] | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06
2AI133MS41000-08005 | EOF:Preliminary Allignment & Grouting of Equipment | [29 empty] | 2018-01-23 | 2018-01-23 | 2018-01-23 | 2018-01-23 | 2018-01-23 | 2018-01-23 | 2018-01-23 | 2018-01-23 | 2018-01-23 | 2018-01-23 | 2018-01-23 | 2018-01-23 | 2018-01-23 | 2018-01-23 | 2018-01-23 | 2018-01-23 | 2018-01-23
2AI133MS41000-08001 | EOF:Installation of Diesel Day Tank Installation | [29 empty] | 2017-12-22 | 2017-12-22 | 2017-12-22 | 2017-12-22 | 2017-12-22 | 2017-12-22 | 2017-12-22 | 2017-12-22 | 2017-12-22 | 2017-12-22 | 2017-12-22 | 2017-12-22 | 2017-12-22 | 2017-12-22 | 2017-12-22 | 2017-12-22 | 2017-12-22
2AI133MS41000-08000 | EOF EG Building 52-R-303 : Diesel Day Tank Installation | [29 empty] | 2017-12-22: 2018-09-30; 2017-12-22: 2018-09-30; 2017-12-22: 2018-09-30; 2017-12-22: 2018-09-30; 2017-12-22: 2018-09-30; 2017-12-22: 2018-09-30; 2017-12-22: 2018-09-30
2AI133MS41000 | EOF EG Building 52-R-303 : Diesel Day Tank Installation | [33 empty] | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06
2AI133MS31000-08010 | EOF:Final Allignment & Grouting of Equipment | [33 empty] | 2018-05-06: 2019-03-05; 2018-05-06: 2019-03-05; 2018-05-06: 2019-03-05
2AI133MS31000-08005 | EOF:Preliminary Allignment & Grouting of Equipment | [37 empty] | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03
2AI133MS31000-08001 | EOF:Installation of Diesel Day Tank Installation | [31 empty] | 2018-01-31 | 2018-01-31 | 2018-01-31 | 2018-01-31 | 2018-01-31 | 2018-01-31 | 2018-01-31 | 2018-01-31 | 2018-01-31 | 2018-01-31 | 2018-01-31 | 2018-01-31 | 2018-01-31 | 2018-01-31 | 2018-01-31
2AI133MS31000-08000 | EOF EG Building 52-R-302 : Diesel Day Tank Installation | [31 empty] | 2018-01-31: 2019-03-05; 2018-01-31: 2019-03-05; 2018-01-31: 2019-03-05
2AI133MS31000 | EOF EG Building 52-R-302 : Diesel Day Tank Installation | [31 empty] | 2018-01-31: 2019-03-05; 2018-01-31: 2019-03-05; 2018-01-31: 2019-03-05
2AI133MS21000-08020 | EOF:Final Allignment & Grouting of Equipment | [31 empty] | 2018-02-22 | 2018-02-22 | 2018-02-22 | 2018-02-22 | 2018-02-22 | 2018-02-22 | 2018-02-22 | 2018-02-22 | 2018-02-22 | 2018-02-22 | 2018-02-22 | 2018-02-22 | 2018-02-22 | 2018-02-22 | 2018-02-22
2AI133MS21000-08010 | EOF:Preliminary Allignment & Grouting of Equipment | [31 empty] | 2018-02-08 | 2018-02-08 | 2018-02-08 | 2018-02-08 | 2018-02-08 | 2018-02-08 | 2018-02-08 | 2018-02-08 | 2018-02-08 | 2018-02-08 | 2018-02-08 | 2018-02-08 | 2018-02-08 | 2018-02-08 | 2018-02-08
2AI133MS21000-08001 | EOF:Installation of Equipment | [31 empty] | 2018-02-08 | 2018-02-08 | 2018-02-08 | 2018-02-08 | 2018-02-08 | 2018-02-08 | 2018-02-08 | 2018-02-08 | 2018-02-08 | 2018-02-08 | 2018-02-08 | 2018-02-08 | 2018-02-08 | 2018-02-08 | 2018-02-08
2AI133MS21000-08000 | EOF EG Building 52-R-301 : Diesel Day Tank Installation | [31 empty] | 2018-02-22 | 2018-02-22 | 2018-02-22 | 2018-02-22 | 2018-02-22 | 2018-02-22 | 2018-02-22 | 2018-02-22 | 2018-02-22 | 2018-02-22 | 2018-02-22 | 2018-02-22 | 2018-02-22 | 2018-02-22 | 2018-02-22
2AI133MS21000 | EOF EG Building 52-R-301 : Diesel Day Tank Installation | [31 empty] | 2018-02-22 | 2018-02-22 | 2018-02-22 | 2018-02-22 | 2018-02-22 | 2018-02-22 | 2018-02-22 | 2018-02-22 | 2018-02-22 | 2018-02-22 | 2018-02-22 | 2018-02-22 | 2018-02-22 | 2018-02-22 | 2018-02-22
2AI133MS11000-08010 | EOF:Final Allignment & Grouting of Equipment | [31 empty] | 2018-02-22: 2018-12-05; 2018-02-22: 2018-12-05; 2018-02-22: 2018-12-05; 2018-02-22: 2018-12-05; 2018-02-22: 2018-12-05
2AI133MS11000-08005 | EOF:Preliminary Allignment & Grouting of Equipment | [35 empty] | 2018-06-24 | 2018-06-24 | 2018-06-24 | 2018-06-24 | 2018-06-24 | 2018-06-24 | 2018-06-24 | 2018-06-24 | 2018-06-24 | 2018-06-24 | 2018-06-24
2AI133MS11000-08001 | EOF:Installation of Equipment | [35 empty] | 2018-06-22 | 2018-06-22 | 2018-06-22 | 2018-06-22 | 2018-06-22 | 2018-06-22 | 2018-06-22 | 2018-06-22 | 2018-06-22 | 2018-06-22 | 2018-06-22
2AI133MS11000-08000 | EOF EG Building 50-R-002 : Diesel Day Tank Foundation | [35 empty] | 2018-06-22: 2018-12-05; 2018-06-22: 2018-12-05; 2018-06-22: 2018-12-05; 2018-06-22: 2018-12-05; 2018-06-22: 2018-12-05
2AI133MS11000 | EOF EG Building 50-R-002 : Diesel Day Tank Installation | [35 empty] | 2018-06-22: 2018-12-05; 2018-06-22: 2018-12-05; 2018-06-22: 2018-12-05; 2018-06-22: 2018-12-05; 2018-06-22: 2018-12-05
2AI133IC41000-08010 | EOF:Continuity check | [35 empty] | 2018-06-22: 2019-02-20; 2018-06-22: 2019-02-20; 2018-06-22: 2019-02-20
2AI133IC41000-08006 | EOF:Glanding & termination | [35 empty] | 2018-06-22: 2019-02-19; 2018-06-22: 2019-02-19; 2018-06-22: 2019-02-19
2AI133IC41000-08005 | EOF EG Building 52-R-303 : Instrument Cable glanding, termination & continuity checks | [35 empty] | 2018-06-22: 2019-02-20; 2018-06-22: 2019-02-20; 2018-06-22: 2019-02-20
2AI133IC41000-08001 | EOF:Cable laying | [39 empty] | 2018-11-23 | 2018-11-23 | 2018-11-23 | 2018-11-23 | 2018-11-23 | 2018-11-23 | 2018-11-23
2AI133IC41000-08000 | EOF EG Building 52-R-303 : Instrument Cable laying | [35 empty] | 2018-06-22: 2019-02-20; 2018-06-22: 2019-02-20; 2018-06-22: 2019-02-20
2AI133IC41000 | EOF EG Building 52-R-303 : Instrument Cable laying, glanding, termination & continuity checks | [35 empty] | 2018-06-22: 2019-02-20; 2018-06-22: 2019-02-20; 2018-06-22: 2019-02-20
2AI133IC31000-08010 | EOF:Continuity check | [35 empty] | 2018-06-22: 2019-04-18
2AI133IC31000-08006 | EOF:Glanding & termination | [35 empty] | 2018-06-22: 2019-04-18
2AI133IC31000-08005 | EOF EG Building 52-R-302 : Instrument Cable glanding, termination & continuity checks | [35 empty] | 2018-06-22: 2019-04-18
2AI133IC31000-08001 | EOF:Cable laying | [39 empty] | 2018-11-22 | 2018-11-22 | 2018-11-22 | 2018-11-22 | 2018-11-22 | 2018-11-22 | 2018-11-22
2AI133IC31000-08000 | EOF EG Building 52-R-302 : Instrument Cable laying | [35 empty] | 2018-06-22: 2019-04-18
2AI133IC31000 | EOF EG Building 52-R-302 : Instrument Cable laying, glanding, termination & continuity checks | [35 empty] | 2018-06-22: 2019-04-18
2AI133IC21000-08010 | EOF:Continuity check | [35 empty] | 2018-06-22: 2019-04-10
2AI133IC21000-08006 | EOF:Glanding & termination | [35 empty] | 2018-06-22: 2019-04-10
2AI133IC21000-08005 | EOF EG Building 52-R-301 : Instrument Cable glanding, termination & continuity checks | [35 empty] | 2018-06-22: 2019-04-10
2AI133IC21000-08001 | EOF:Cable laying | [39 empty] | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30
2AI133IC21000-08000 | EOF EG Building 52-R-301 : Instrument Cable laying | [35 empty] | 2018-06-22: 2019-04-10
2AI133IC21000 | EOF EG Building 52-R-301 : Instrument Cable laying, glanding, termination & continuity checks | [35 empty] | 2018-06-22: 2019-04-10
2AI133IC11000-08010 | EOF:Continuity check | [39 empty] | 2018-10-20 | 2018-10-20 | 2018-10-20 | 2018-10-20 | 2018-10-20 | 2018-10-20 | 2018-10-20
2AI133IC11000-08006 | EOF:Glanding & termination | [39 empty] | 2018-10-19 | 2018-10-19 | 2018-10-19 | 2018-10-19 | 2018-10-19 | 2018-10-19 | 2018-10-19
2AI133IC11000-08005 | EOF:Cable laying | [39 empty] | 2018-10-20 | 2018-10-20 | 2018-10-20 | 2018-10-20 | 2018-10-20 | 2018-10-20 | 2018-10-20
2AI133IC11000-08001 | EOF:Cable laying | [39 empty] | 2018-10-12 | 2018-10-12 | 2018-10-12 | 2018-10-12 | 2018-10-12 | 2018-10-12 | 2018-10-12
2AI133IC11000-08000 | EOF EG Building 50-R-002 : Instrument Cable laying | [39 empty] | 2018-10-20 | 2018-10-20 | 2018-10-20 | 2018-10-20 | 2018-10-20 | 2018-10-20 | 2018-10-20
2AI133IC11000 | EOF EG Building 50-R-002 : Instrument Cable laying, glanding, termination & continuity checks | [39 empty] | 2018-10-20 | 2018-10-20 | 2018-10-20 | 2018-10-20 | 2018-10-20 | 2018-10-20 | 2018-10-20
2AI133IC07200-08000 | EOF SS 52-SUBST-303 : Install - ICSS related equipments | [35 empty] | 2018-06-22: 2019-02-15; 2018-06-22: 2019-02-15; 2018-06-22: 2019-02-15
2AI133IC07200 | EOF SS 52-SUBST-303 : Install - ICSS related equipments | [35 empty] | 2018-06-22: 2019-02-15; 2018-06-22: 2019-02-15; 2018-06-22: 2019-02-15
2AI133IC07100-08000 | EOF SS 52-SUBST-303 : Install - IRP Cabinets
2AI133IC07100 | EOF SS 52-SUBST-303 : Install - IRP Cabinets
2AI133IC07000-08020 | EOF:Continuity check | [35 empty] | 2018-06-22: 2019-04-10
2AI133IC07000-08015 | EOF:Glanding & termination | [35 empty] | 2018-06-22: 2019-04-10
2AI133IC07000-08010 | EOF:Cable laying | [35 empty] | 2018-06-22: 2019-04-10
2AI133IC07000-08006 | EOF: Install cable trays | [33 empty] | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04
2AI133IC07000-08005 | 621-SUBST-0303 : Cable glanding, termination & continuity check | [33 empty] | 2018-04-04: 2019-04-10
2AI133IC07000-08001 | EOF: Install Tray support and Hangers | [33 empty] | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04
2AI133IC07000-08000 | 621-SUBST-0303 : Cable laying | [33 empty] | 2018-04-04: 2019-04-10
2AI133IC07000 | EOF SS 52-SUBST-303 : Cable laying, glanding, termination & continuity check | [33 empty] | 2018-04-04: 2019-04-10
2AI133IC05200-08000 | EOF SS 52-SUBST-302 : Install - ICSS related equipments | [33 empty] | 2018-04-04: 2019-04-10
2AI133IC05200 | EOF SS 52-SUBST-302 : Install - ICSS related equipments | [33 empty] | 2018-04-04: 2019-04-10
2AI133IC05100-08000 | EOF SS 52-SUBST-302 : Install - IRP Cabinets | [31 empty] | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18
2AI133IC05100 | EOF SS 52-SUBST-302 : Install - IRP Cabinets | [31 empty] | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18
2AI133IC05000-08020 | EOF:Tagging | [37 empty] | 2018-08-03 | 2018-08-03 | 2018-08-03 | 2018-08-03 | 2018-08-03 | 2018-08-03 | 2018-08-03 | 2018-08-03 | 2018-08-03
2AI133IC05000-08010 | EOF:Continuity check & termination | [37 empty] | 2018-08-03 | 2018-08-03 | 2018-08-03 | 2018-08-03 | 2018-08-03 | 2018-08-03 | 2018-08-03 | 2018-08-03 | 2018-08-03
2AI133IC05000-08006 | EOF:Glanding | [37 empty] | 2018-08-02 | 2018-08-02 | 2018-08-02 | 2018-08-02 | 2018-08-02 | 2018-08-02 | 2018-08-02 | 2018-08-02 | 2018-08-02
2AI133IC05000-08005 | 621-SUBST-0302 : Cable glanding, termination & continuity check | [37 empty] | 2018-08-03 | 2018-08-03 | 2018-08-03 | 2018-08-03 | 2018-08-03 | 2018-08-03 | 2018-08-03 | 2018-08-03 | 2018-08-03
2AI133IC05000-08003 | EOF:Cable laying | [39 empty] | 2018-10-04 | 2018-10-04 | 2018-10-04 | 2018-10-04 | 2018-10-04 | 2018-10-04 | 2018-10-04
2AI133IC05000-08001 | EOF:Cable Tray Installation | [39 empty] | 2018-10-02 | 2018-10-02 | 2018-10-02 | 2018-10-02 | 2018-10-02 | 2018-10-02 | 2018-10-02
2AI133IC05000-08000 | 621-SUBST-0302 : Cable laying | [39 empty] | 2018-10-04 | 2018-10-04 | 2018-10-04 | 2018-10-04 | 2018-10-04 | 2018-10-04 | 2018-10-04
2AI133IC05000 | EOF SS 52-SUBST-302 : Cable laying, glanding, termination & continuity check | [39 empty] | 2018-10-04 | 2018-10-04 | 2018-10-04 | 2018-10-04 | 2018-10-04 | 2018-10-04 | 2018-10-04
2AI133IC03200-08000 | EOF SS 52-SUBST-301 : Install - ICSS related equipments & Other Instrument/Equipment | [37 empty] | 2018-08-03: 2019-04-10
2AI133IC03200 | EOF SS 52-SUBST-301 : Install - ICSS related equipments | [37 empty] | 2018-08-03: 2019-04-10
2AI133IC03100-08000 | EOF SS 52-SUBST-301 : Install - IRP Cabinets | [37 empty] | 2018-08-03: 2019-04-10
2AI133IC03100 | EOF SS 52-SUBST-301 : Install - IRP Cabinets | [37 empty] | 2018-08-03: 2019-04-10
2AI133IC03000-08015 | EOF:Continuity check | [35 empty] | 2018-06-27 | 2018-06-27 | 2018-06-27 | 2018-06-27 | 2018-06-27 | 2018-06-27 | 2018-06-27 | 2018-06-27 | 2018-06-27 | 2018-06-27 | 2018-06-27
2AI133IC03000-08010 | EOF:Glanding & termination | [35 empty] | 2018-06-26 | 2018-06-26 | 2018-06-26 | 2018-06-26 | 2018-06-26 | 2018-06-26 | 2018-06-26 | 2018-06-26 | 2018-06-26 | 2018-06-26 | 2018-06-26
2AI133IC03000-08006 | EOF:Cable laying | [33 empty] | 2018-05-11 | 2018-05-11 | 2018-05-11 | 2018-05-11 | 2018-05-11 | 2018-05-11 | 2018-05-11 | 2018-05-11 | 2018-05-11 | 2018-05-11 | 2018-05-11 | 2018-05-11 | 2018-05-11
2AI133IC03000-08005 | 621-SUBST-301 : Glanding, termination & continuity check | [35 empty] | 2018-06-27 | 2018-06-27 | 2018-06-27 | 2018-06-27 | 2018-06-27 | 2018-06-27 | 2018-06-27 | 2018-06-27 | 2018-06-27 | 2018-06-27 | 2018-06-27
2AI133IC03000-08001 | EOF:Cable Tray Installation | [35 empty] | 2018-06-14 | 2018-06-14 | 2018-06-14 | 2018-06-14 | 2018-06-14 | 2018-06-14 | 2018-06-14 | 2018-06-14 | 2018-06-14 | 2018-06-14 | 2018-06-14
2AI133IC03000-08000 | 621-SUBST-301 : Cable laying | [35 empty] | 2018-06-14 | 2018-06-14 | 2018-06-14 | 2018-06-14 | 2018-06-14 | 2018-06-14 | 2018-06-14 | 2018-06-14 | 2018-06-14 | 2018-06-14 | 2018-06-14
2AI133IC03000 | EOF SS 52-SUBST-301 : Cable laying, glanding, termination & continuity check | [35 empty] | 2018-06-27 | 2018-06-27 | 2018-06-27 | 2018-06-27 | 2018-06-27 | 2018-06-27 | 2018-06-27 | 2018-06-27 | 2018-06-27 | 2018-06-27 | 2018-06-27
2AI133IC01200-08000 | EOF SS 52-SUBST-302 : Install - ICSS related equipments | [35 empty] | 2018-06-27: 2019-04-10
2AI133IC01200 | EOF SS 50-SUBST-001 : Install - ICSS related equipments | [35 empty] | 2018-06-27: 2019-04-10
2AI133IC01100-08000 | EOF SS 52-SUBST-302 : Install - IRP Cabinets | [33 empty] | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15
2AI133IC01100 | EOF SS 50-SUBST-001 : Install - IRP Cabinets | [33 empty] | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15
2AI133IC01000-08015 | EOF:Continuity check | [33 empty] | 2018-05-15: 2018-10-20; 2018-05-15: 2018-10-20; 2018-05-15: 2018-10-20; 2018-05-15: 2018-10-20; 2018-05-15: 2018-10-20; 2018-05-15: 2018-10-20; 2018-05-15: 2018-10-20
2AI133IC01000-08010 | EOF:Glanding & termination | [33 empty] | 2018-05-15: 2018-10-19; 2018-05-15: 2018-10-19; 2018-05-15: 2018-10-19; 2018-05-15: 2018-10-19; 2018-05-15: 2018-10-19; 2018-05-15: 2018-10-19; 2018-05-15: 2018-10-19
2AI133IC01000-08006 | EOF:Cable laying | [33 empty] | 2018-05-18 | 2018-05-18 | 2018-05-18 | 2018-05-18 | 2018-05-18 | 2018-05-18 | 2018-05-18 | 2018-05-18 | 2018-05-18 | 2018-05-18 | 2018-05-18 | 2018-05-18 | 2018-05-18
2AI133IC01000-08005 | EOF SS 50-SUBST-001 : Cable laying, glanding, termination & continuity check | [33 empty] | 2018-05-18: 2018-10-20; 2018-05-18: 2018-10-20; 2018-05-18: 2018-10-20; 2018-05-18: 2018-10-20; 2018-05-18: 2018-10-20; 2018-05-18: 2018-10-20; 2018-05-18: 2018-10-20
2AI133IC01000-08001 | EOF:Cable Tray Installation | [33 empty] | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15
2AI133IC01000-08000 | EOF SS 50-SUBST-001 : Cable laying, glanding, termination & continuity check | [33 empty] | 2018-05-15: 2018-10-20; 2018-05-15: 2018-10-20; 2018-05-15: 2018-10-20; 2018-05-15: 2018-10-20; 2018-05-15: 2018-10-20; 2018-05-15: 2018-10-20; 2018-05-15: 2018-10-20
2AI133IC01000 | EOF SS 50-SUBST-001 : Cable laying, glanding, termination & continuity check | [33 empty] | 2018-05-15: 2018-10-20; 2018-05-15: 2018-10-20; 2018-05-15: 2018-10-20; 2018-05-15: 2018-10-20; 2018-05-15: 2018-10-20; 2018-05-15: 2018-10-20; 2018-05-15: 2018-10-20
2AI133HS01160-08015 | Alignment/Levelling and grouting
2AI133HS01160-08005 | Installation of Instruments on Support Structures
2AI133HS01160-08001 | Fabrication & Installation of Support Structures
2AI133HS01160-08000 | EOF SS: Installation of Safety Sign Boards
2AI133HS01160 | EOF SS: Installation of Safety Sign Boards
2AI133HS01150-08010 | Alignment/Levelling and grouting
2AI133HS01150-08005 | Installation of Instruments on Support Structures
2AI133HS01150-08001 | Fabrication & Installation of Support Structures
2AI133HS01150-08000 | EOF SS: Installation of Fire fighting & Safety Equipments
2AI133HS01150 | EOF SS: Installation of Fire fighting & Safety Equipments
2AI133EL41200-08010 | EOF:Allignment | [33 empty] | 2018-05-15: 2018-11-23; 2018-05-15: 2018-11-23; 2018-05-15: 2018-11-23; 2018-05-15: 2018-11-23; 2018-05-15: 2018-11-23; 2018-05-15: 2018-11-23; 2018-05-15: 2018-11-23
2AI133EL41200-08005 | EOF:Installation of Distribution Board | [33 empty] | 2018-05-15: 2018-11-23; 2018-05-15: 2018-11-23; 2018-05-15: 2018-11-23; 2018-05-15: 2018-11-23; 2018-05-15: 2018-11-23; 2018-05-15: 2018-11-23; 2018-05-15: 2018-11-23
2AI133EL41200-08001 | EOF:Installation of Supports | [33 empty] | 2018-05-15: 2018-11-22; 2018-05-15: 2018-11-22; 2018-05-15: 2018-11-22; 2018-05-15: 2018-11-22; 2018-05-15: 2018-11-22; 2018-05-15: 2018-11-22; 2018-05-15: 2018-11-22
2AI133EL41200-08000 | EOF EG Building 52-R-303 : Install Distribution boards, Lighting & small power | [33 empty] | 2018-05-15: 2018-11-23; 2018-05-15: 2018-11-23; 2018-05-15: 2018-11-23; 2018-05-15: 2018-11-23; 2018-05-15: 2018-11-23; 2018-05-15: 2018-11-23; 2018-05-15: 2018-11-23
2AI133EL41200 | EOF EG Building 52-R-303 : Install Distribution boards, Lighting & small power | [33 empty] | 2018-05-15: 2018-11-23; 2018-05-15: 2018-11-23; 2018-05-15: 2018-11-23; 2018-05-15: 2018-11-23; 2018-05-15: 2018-11-23; 2018-05-15: 2018-11-23; 2018-05-15: 2018-11-23
2AI133EL41100-08025 | EOF: Tagging | [33 empty] | 2018-05-15: 2019-04-10
2AI133EL41100-08020 | EOF: Continuity Checks & Terminations | [33 empty] | 2018-05-15: 2019-04-10
2AI133EL41100-08015 | EOF: Cable Glanding | [33 empty] | 2018-05-15: 2018-10-19; 2018-05-15: 2018-10-19; 2018-05-15: 2018-10-19; 2018-05-15: 2018-10-19; 2018-05-15: 2018-10-19; 2018-05-15: 2018-10-19; 2018-05-15: 2018-10-19
2AI133EL41100-08010 | EOF: Installcable trays covers | [33 empty] | 2018-05-15: 2018-11-07; 2018-05-15: 2018-11-07; 2018-05-15: 2018-11-07; 2018-05-15: 2018-11-07; 2018-05-15: 2018-11-07; 2018-05-15: 2018-11-07; 2018-05-15: 2018-11-07
2AI133EL41100-08009 | EOF: Cable Laying | [33 empty] | 2018-05-15: 2018-10-10; 2018-05-15: 2018-10-10; 2018-05-15: 2018-10-10; 2018-05-15: 2018-10-10; 2018-05-15: 2018-10-10; 2018-05-15: 2018-10-10; 2018-05-15: 2018-10-10
2AI133EL41100-08006 | EOF: Install cable trays | [33 empty] | 2018-05-15: 2018-10-10; 2018-05-15: 2018-10-10; 2018-05-15: 2018-10-10; 2018-05-15: 2018-10-10; 2018-05-15: 2018-10-10; 2018-05-15: 2018-10-10; 2018-05-15: 2018-10-10
2AI133EL41100-08005 | EOF EG Building 52-R-303 : Cableglanding, termination & continuity check | [33 empty] | 2018-05-15: 2019-04-10
2AI133EL41100-08004 | EOF: Install Tray support and Hangers | [33 empty] | 2018-05-15: 2019-04-10
2AI133EL41100-08001 | EOF:Fabricate Tray Supports | [33 empty] | 2018-05-15: 2019-04-10
2AI133EL41100-08000 | EOF EG Building 52-R-303 : Cable laying | [33 empty] | 2018-05-15: 2019-04-10
2AI133EL41100 | EOF EG Building 52-R-303 : Cable laying, glanding, termination & continuity check | [33 empty] | 2018-05-15: 2019-04-10
2AI133EL41000-08005 | EOF:Allignment | [35 empty] | 2018-06-21 | 2018-06-21 | 2018-06-21 | 2018-06-21 | 2018-06-21 | 2018-06-21 | 2018-06-21 | 2018-06-21 | 2018-06-21 | 2018-06-21 | 2018-06-21
2AI133EL41000-08001 | EOF:Installation of Generators | [35 empty] | 2018-06-20 | 2018-06-20 | 2018-06-20 | 2018-06-20 | 2018-06-20 | 2018-06-20 | 2018-06-20 | 2018-06-20 | 2018-06-20 | 2018-06-20 | 2018-06-20
2AI133EL41000-08000 | EOF EG Building 52-R-303 : Install Emergency Generator | [39 empty] | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30
2AI133EL41000 | EOF EG Building 52-R-303 : Install Emergency Generator | [35 empty] | 2018-06-21 | 2018-06-21 | 2018-06-21 | 2018-06-21 | 2018-06-21 | 2018-06-21 | 2018-06-21 | 2018-06-21 | 2018-06-21 | 2018-06-21 | 2018-06-21
2AI133EL31200-08025 | EOF: Tagging | [35 empty] | 2018-06-21: 2019-04-10
2AI133EL31200-08020 | EOF: Continuity Checks & Terminations | [35 empty] | 2018-06-21: 2019-03-06; 2018-06-21: 2019-03-06; 2018-06-21: 2019-03-06
2AI133EL31200-08015 | EOF: Cable Glanding | [39 empty] | 2018-10-10 | 2018-10-10 | 2018-10-10 | 2018-10-10 | 2018-10-10 | 2018-10-10 | 2018-10-10
2AI133EL31200-08009 | Cable Marking | [35 empty] | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04
2AI133EL31200-08006 | Cable Dressing & Fastening | [35 empty] | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04
2AI133EL31200-08005 | EOF EG Building 52-R-302 : Cableglanding, termination & continuity check | [35 empty] | 2018-07-04: 2019-04-10
2AI133EL31200-08004 | Cable Pulling | [35 empty] | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04
2AI133EL31200-08001 | Cable Drum Checks & Transport to Site | [35 empty] | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04
2AI133EL31200-08000 | EOF EG Building 52-R-302 :Cable laying | [35 empty] | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04
2AI133EL31200 | EOF EG Building 52-R-302 : Cable laying, glanding, termination & continuity check | [35 empty] | 2018-07-04: 2019-04-10
2AI133EL31100-08010 | EOF:Allignment | [37 empty] | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28
2AI133EL31100-08005 | EOF:Installation of Distribution Board | [37 empty] | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28
2AI133EL31100-08001 | EOF:Installation of Supports | [37 empty] | 2018-09-27 | 2018-09-27 | 2018-09-27 | 2018-09-27 | 2018-09-27 | 2018-09-27 | 2018-09-27 | 2018-09-27 | 2018-09-27
2AI133EL31100-08000 | EOF EG Building 52-R-302 : Install Distribution boards, Lighting & small power | [37 empty] | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28
2AI133EL31100 | EOF EG Building 52-R-302 : Install Distribution boards, Lighting & small power | [37 empty] | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28
2AI133EL31000-08005 | EOF:Allignment | [35 empty] | 2018-07-15 | 2018-07-15 | 2018-07-15 | 2018-07-15 | 2018-07-15 | 2018-07-15 | 2018-07-15 | 2018-07-15 | 2018-07-15 | 2018-07-15 | 2018-07-15
2AI133EL31000-08001 | EOF:Installation of Generators | [35 empty] | 2018-07-13 | 2018-07-13 | 2018-07-13 | 2018-07-13 | 2018-07-13 | 2018-07-13 | 2018-07-13 | 2018-07-13 | 2018-07-13 | 2018-07-13 | 2018-07-13
2AI133EL31000-08000 | EOF:Installation of Generators | [35 empty] | 2018-07-15 | 2018-07-15 | 2018-07-15 | 2018-07-15 | 2018-07-15 | 2018-07-15 | 2018-07-15 | 2018-07-15 | 2018-07-15 | 2018-07-15 | 2018-07-15
2AI133EL31000 | EOF EG Building 52-R-302 : Install Emergency Generator | [35 empty] | 2018-07-15 | 2018-07-15 | 2018-07-15 | 2018-07-15 | 2018-07-15 | 2018-07-15 | 2018-07-15 | 2018-07-15 | 2018-07-15 | 2018-07-15 | 2018-07-15
2AI133EL21200-08030 | EOF: Tagging | [35 empty] | 2018-07-15: 2018-11-30; 2018-07-15: 2018-11-30; 2018-07-15: 2018-11-30; 2018-07-15: 2018-11-30; 2018-07-15: 2018-11-30
2AI133EL21200-08025 | EOF: Continuity Checks & Terminations | [35 empty] | 2018-07-15: 2018-11-29; 2018-07-15: 2018-11-29; 2018-07-15: 2018-11-29; 2018-07-15: 2018-11-29; 2018-07-15: 2018-11-29
2AI133EL21200-08020 | EOF: Cable Glanding | [35 empty] | 2018-07-15: 2018-11-28; 2018-07-15: 2018-11-28; 2018-07-15: 2018-11-28; 2018-07-15: 2018-11-28; 2018-07-15: 2018-11-28
2AI133EL21200-08015 | EOF: Installcable trays covers | [35 empty] | 2018-07-14 | 2018-07-14 | 2018-07-14 | 2018-07-14 | 2018-07-14 | 2018-07-14 | 2018-07-14 | 2018-07-14 | 2018-07-14 | 2018-07-14 | 2018-07-14
2AI133EL21200-08014 | EOF: Cable Laying | [35 empty] | 2018-07-14: 2019-04-10
2AI133EL21200-08010 | EOF: Install cable trays | [35 empty] | 2018-07-13 | 2018-07-13 | 2018-07-13 | 2018-07-13 | 2018-07-13 | 2018-07-13 | 2018-07-13 | 2018-07-13 | 2018-07-13 | 2018-07-13 | 2018-07-13
2AI133EL21200-08006 | EOF: Install Tray support and Hangers | [33 empty] | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04
2AI133EL21200-08005 | EOF EG Building 52-R-301 : Cable glanding, termination & continuity check | [33 empty] | 2018-04-04: 2018-11-30; 2018-04-04: 2018-11-30; 2018-04-04: 2018-11-30; 2018-04-04: 2018-11-30; 2018-04-04: 2018-11-30
2AI133EL21200-08001 | EOF:Fabricate Tray Supports | [33 empty] | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04
2AI133EL21200-08000 | EOF EG Building 52-R-301 : Cable laying | [33 empty] | 2018-04-04: 2019-04-10
2AI133EL21200 | EOF EG Building 52-R-301 : Cable laying, glanding, termination & continuity check | [33 empty] | 2018-04-04: 2019-04-10
2AI133EL21100-08010 | EOF:Allignment | [33 empty] | 2018-04-04: 2019-04-10
2AI133EL21100-08005 | EOF:Installation of Distribution Board | [33 empty] | 2018-04-04: 2019-04-10
2AI133EL21100-08001 | EOF:Installation of Supports | [33 empty] | 2018-04-04: 2019-04-10
2AI133EL21100-08000 | EOF EG Building 52-R-301 : Install Distribution boards | [33 empty] | 2018-04-04: 2019-04-10
2AI133EL21100 | EOF EG Building 52-R-301 : Install Distribution boards, Lighting & small power | [33 empty] | 2018-04-04: 2019-04-10
2AI133EL21000-08005 | EOF:Allignment | [35 empty] | 2018-06-28 | 2018-06-28 | 2018-06-28 | 2018-06-28 | 2018-06-28 | 2018-06-28 | 2018-06-28 | 2018-06-28 | 2018-06-28 | 2018-06-28 | 2018-06-28
2AI133EL21000-08001 | EOF:Installation of Generators | [35 empty] | 2018-06-27 | 2018-06-27 | 2018-06-27 | 2018-06-27 | 2018-06-27 | 2018-06-27 | 2018-06-27 | 2018-06-27 | 2018-06-27 | 2018-06-27 | 2018-06-27
2AI133EL21000-08000 | EOF EG Building 52-R-301 : Install Emergency Generator | [35 empty] | 2018-06-28 | 2018-06-28 | 2018-06-28 | 2018-06-28 | 2018-06-28 | 2018-06-28 | 2018-06-28 | 2018-06-28 | 2018-06-28 | 2018-06-28 | 2018-06-28
2AI133EL21000 | EOF EG Building 52-R-301 : Install Emergency Generator | [35 empty] | 2018-06-28 | 2018-06-28 | 2018-06-28 | 2018-06-28 | 2018-06-28 | 2018-06-28 | 2018-06-28 | 2018-06-28 | 2018-06-28 | 2018-06-28 | 2018-06-28
2AI133EL11200-08010 | EOF:Allignment | [39 empty] | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30
2AI133EL11200-08005 | EOF:Installation of Distribution Board | [37 empty] | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28
2AI133EL11200-08001 | EOF:Installation of Supports | [37 empty] | 2018-09-27 | 2018-09-27 | 2018-09-27 | 2018-09-27 | 2018-09-27 | 2018-09-27 | 2018-09-27 | 2018-09-27 | 2018-09-27
2AI133EL11200-08000 | EOF EG Building 50-R-002 : Install Distribution boards, Lighting & small power | [39 empty] | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30
2AI133EL11200 | EOF EG Building 50-R-002 : Install Distribution boards, Lighting & small power | [39 empty] | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30
2AI133EL11100-08030 | EOF: Tagging for LV cables | [37 empty] | 2018-09-27: 2019-03-16; 2018-09-27: 2019-03-16; 2018-09-27: 2019-03-16
2AI133EL11100-08025 | EOF: Continuity Checks & Terminations for LV cables | [37 empty] | 2018-09-27: 2019-03-15; 2018-09-27: 2019-03-15; 2018-09-27: 2019-03-15
2AI133EL11100-08020 | EOF: Cable Glanding for LV cables | [37 empty] | 2018-09-27: 2019-03-14; 2018-09-27: 2019-03-14; 2018-09-27: 2019-03-14
2AI133EL11100-08015 | EOF: Installcable trays covers | [37 empty] | 2018-09-27: 2019-04-10
2AI133EL11100-08014 | EOF: Cable Laying - LV | [39 empty] | 2018-10-02 | 2018-10-02 | 2018-10-02 | 2018-10-02 | 2018-10-02 | 2018-10-02 | 2018-10-02
2AI133EL11100-08010 | EOF: Install cable trays | [39 empty] | 2018-10-02 | 2018-10-02 | 2018-10-02 | 2018-10-02 | 2018-10-02 | 2018-10-02 | 2018-10-02
2AI133EL11100-08006 | EOF:Fabricate Tray Supports | [39 empty] | 2018-10-10 | 2018-10-10 | 2018-10-10 | 2018-10-10 | 2018-10-10 | 2018-10-10 | 2018-10-10
2AI133EL11100-08005 | EOF EG Building 50-R-002 : Cable glanding, termination & continuity check | [37 empty] | 2018-09-27: 2019-03-16; 2018-09-27: 2019-03-16; 2018-09-27: 2019-03-16
2AI133EL11100-08000 | EOF EG Building 50-R-002 : Cable laying | [37 empty] | 2018-09-27: 2019-04-10
2AI133EL11100 | EOF EG Building 50-R-002 : Cable laying, glanding, termination & continuity check | [37 empty] | 2018-09-27: 2019-04-10
2AI133EL11000-08005 | EOF:Allignment | [37 empty] | 2018-08-13 | 2018-08-13 | 2018-08-13 | 2018-08-13 | 2018-08-13 | 2018-08-13 | 2018-08-13 | 2018-08-13 | 2018-08-13
2AI133EL11000-08001 | EOF:Installation of Generators | [37 empty] | 2018-08-09 | 2018-08-09 | 2018-08-09 | 2018-08-09 | 2018-08-09 | 2018-08-09 | 2018-08-09 | 2018-08-09 | 2018-08-09
2AI133EL11000-08000 | EOF EG Building 50-R-002 : Install Emergency Generator | [37 empty] | 2018-08-13 | 2018-08-13 | 2018-08-13 | 2018-08-13 | 2018-08-13 | 2018-08-13 | 2018-08-13 | 2018-08-13 | 2018-08-13
2AI133EL11000 | EOF EG Building 50-R-002 : Install Emergency Generator | [37 empty] | 2018-08-13 | 2018-08-13 | 2018-08-13 | 2018-08-13 | 2018-08-13 | 2018-08-13 | 2018-08-13 | 2018-08-13 | 2018-08-13
2AI133EL07700-08000 | EOF:Installation of E-SCADA Cabinet/Panel/Cabling | [33 empty] | 2018-04-27 | 2018-04-27 | 2018-04-27 | 2018-04-27 | 2018-04-27 | 2018-04-27 | 2018-04-27 | 2018-04-27 | 2018-04-27 | 2018-04-27 | 2018-04-27 | 2018-04-27 | 2018-04-27
2AI133EL07700 | EOF SS 52-SUBST-303 : Install E-SCADA | [33 empty] | 2018-04-27 | 2018-04-27 | 2018-04-27 | 2018-04-27 | 2018-04-27 | 2018-04-27 | 2018-04-27 | 2018-04-27 | 2018-04-27 | 2018-04-27 | 2018-04-27 | 2018-04-27 | 2018-04-27
2AI133EL07600-08015 | EOF:Installation of Batteries | [33 empty] | 2018-04-27: 2019-04-10
2AI133EL07600-08010 | EOF:Installation of Isolator Switch | [33 empty] | 2018-04-27: 2019-04-10
2AI133EL07600-08005 | EOF:Installation of UPS | [33 empty] | 2018-04-27: 2019-04-10
2AI133EL07600-08001 | EOF:Installation of Supports | [29 empty] | 2018-01-24 | 2018-01-24 | 2018-01-24 | 2018-01-24 | 2018-01-24 | 2018-01-24 | 2018-01-24 | 2018-01-24 | 2018-01-24 | 2018-01-24 | 2018-01-24 | 2018-01-24 | 2018-01-24 | 2018-01-24 | 2018-01-24 | 2018-01-24 | 2018-01-24
2AI133EL07600-08000 | EOF SS 52-SUBST-303 : Install UPS with Battery bank and Isolator Switch | [29 empty] | 2018-01-24: 2019-04-10
2AI133EL07600 | EOF SS 52-SUBST-303 : Install UPS with Battery bank and Isolator Switch | [29 empty] | 2018-01-24: 2019-04-10
2AI133EL07500-08025 | EOF:Allignment of Annunciator Panels | [29 empty] | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03
2AI133EL07500-08015 | EOF:Allignment of Distribution Board | [29 empty] | 2018-01-03: 2019-04-10
2AI133EL07500-08010 | EOF:Installation of Annunciator Panels | [29 empty] | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03
2AI133EL07500-08005 | EOF:Installation of Distribution Board | [29 empty] | 2018-01-03: 2019-04-10
2AI133EL07500-08001 | EOF:Installation of Supports | [29 empty] | 2018-01-03: 2019-04-10
2AI133EL07500-08000 | EOF SS 52-SUBST-303 : Install Distribution boards and Annunciator Panels | [29 empty] | 2018-01-03: 2019-04-10
2AI133EL07500 | EOF SS 52-SUBST-303 : Install Distribution boards and Annunciator Panels | [29 empty] | 2018-01-03: 2019-04-10
2AI133EL07400-08025 | EOF:Allignment of Bus duct | [29 empty] | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03
2AI133EL07400-08015 | EOF:Installation of Bus duct | [29 empty] | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03
2AI133EL07400-08010 | EOF:Allignment of LV Switchgear, MCC | [29 empty] | 2018-01-03: 2018-12-12; 2018-01-03: 2018-12-12; 2018-01-03: 2018-12-12; 2018-01-03: 2018-12-12; 2018-01-03: 2018-12-12
2AI133EL07400-08005 | EOF:Installation of LV Switchgear, MCC | [29 empty] | 2018-01-03: 2018-12-12; 2018-01-03: 2018-12-12; 2018-01-03: 2018-12-12; 2018-01-03: 2018-12-12; 2018-01-03: 2018-12-12
2AI133EL07400-08001 | EOF:Installation of Supports | [29 empty] | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03
2AI133EL07400-08000 | EOF SS 52-SUBST-303 : Install LV Switchboards with RCP, MCC & Bus Ducts(incl. Lighting/small power) | [29 empty] | 2018-01-03: 2018-12-12; 2018-01-03: 2018-12-12; 2018-01-03: 2018-12-12; 2018-01-03: 2018-12-12; 2018-01-03: 2018-12-12
2AI133EL07400 | EOF SS 52-SUBST-303 : Install LV Switchboards with RCP, MCC & Bus Ducts(incl. Lighting/small power) | [29 empty] | 2018-01-03: 2018-12-12; 2018-01-03: 2018-12-12; 2018-01-03: 2018-12-12; 2018-01-03: 2018-12-12; 2018-01-03: 2018-12-12
2AI133EL07300-08015 | Final Alignment | [31 empty] | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07
2AI133EL07300-08010 | Preliminary Alignment & Grouting | [29 empty] | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06
2AI133EL07300-08005 | Installation on Foundation | [29 empty] | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06
2AI133EL07300-08001 | Foundation Checks/Preparation | [29 empty] | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06
2AI133EL07300-08000 | EOF SS 52-SUBST-303 : Install HV Switchboard with RCP, Power Factor & Bus Ducts | [31 empty] | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07
2AI133EL07300 | EOF SS 52-SUBST-303 : Install HV Switchboard with RCP, Power Factor & Bus Ducts | [31 empty] | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07
2AI133EL07200-08030 | COCC: Earth Pit Installation | [31 empty] | 2018-02-07: 2019-04-25
2AI133EL07200-08025 | COCC: Earth cable Termination | [31 empty] | 2018-02-07: 2019-04-25
2AI133EL07200-08020 | COCC: Earth Boss Installation | [31 empty] | 2018-02-07: 2019-04-25
2AI133EL07200-08015 | COCC: Earth Bus Installation | [31 empty] | 2018-02-07: 2018-11-29; 2018-02-07: 2018-11-29; 2018-02-07: 2018-11-29; 2018-02-07: 2018-11-29; 2018-02-07: 2018-11-29
2AI133EL07200-08010 | COCC: Cad welding | [37 empty] | 2018-08-24 | 2018-08-24 | 2018-08-24 | 2018-08-24 | 2018-08-24 | 2018-08-24 | 2018-08-24 | 2018-08-24 | 2018-08-24
2AI133EL07200-08005 | COCC: Earth Cable Laying | [33 empty] | 2018-05-23 | 2018-05-23 | 2018-05-23 | 2018-05-23 | 2018-05-23 | 2018-05-23 | 2018-05-23 | 2018-05-23 | 2018-05-23 | 2018-05-23 | 2018-05-23 | 2018-05-23 | 2018-05-23
2AI133EL07200-08001 | COCC: Earth rod Installation | [29 empty] | 2018-01-19 | 2018-01-19 | 2018-01-19 | 2018-01-19 | 2018-01-19 | 2018-01-19 | 2018-01-19 | 2018-01-19 | 2018-01-19 | 2018-01-19 | 2018-01-19 | 2018-01-19 | 2018-01-19 | 2018-01-19 | 2018-01-19 | 2018-01-19 | 2018-01-19
2AI133EL07200-08000 | EOF:Earthing Work | [29 empty] | 2018-01-19: 2019-04-25
2AI133EL07200 | EOF SS 52-SUBST-303 : Earthing Lightning Protection Works | [29 empty] | 2018-01-19: 2019-04-25
2AI133EL07100-08120 | EOF: Tagging for HV cables | [29 empty] | 2018-01-19: 2019-04-10
2AI133EL07100-08115 | EOF: Continuity Checks & Terminations for HV cables | [29 empty] | 2018-01-19: 2019-04-10
2AI133EL07100-08111 | EOF: Installcable trays covers | [29 empty] | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22
2AI133EL07100-08110 | EOF: Cable Glanding for HV cables | [29 empty] | 2018-01-22: 2019-04-10
2AI133EL07100-08109 | EOF: Cable Laying - HV | [29 empty] | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22
2AI133EL07100-08100 | EOF: Tagging for LV cables | [29 empty] | 2018-01-22: 2019-04-10
2AI133EL07100-08095 | EOF: Continuity Checks & Terminations for LV cables | [29 empty] | 2018-01-22: 2019-04-10
2AI133EL07100-08090 | EOF: Cable Glanding for LV cables | [29 empty] | 2018-01-22: 2019-04-10
2AI133EL07100-08089 | EOF: Cable Laying - LV | [29 empty] | 2018-01-22: 2019-03-08; 2018-01-22: 2019-03-08; 2018-01-22: 2019-03-08
2AI133EL07100-08006 | EOF: Install cable trays | [29 empty] | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03
2AI133EL07100-08005 | 621-SUBST-0303 : Cable glanding, termination & continuity check | [29 empty] | 2018-01-03: 2019-04-10
2AI133EL07100-08003 | EOF: Install Tray support and Hangers | [29 empty] | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03
2AI133EL07100-08001 | EOF:Fabricate Tray Supports | [29 empty] | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03
2AI133EL07100-08000 | 621-SUBST-0303 : Cable laying | [29 empty] | 2018-01-03: 2019-03-08; 2018-01-03: 2019-03-08; 2018-01-03: 2019-03-08
2AI133EL07100 | EOF SS 52-SUBST-303 : Cable laying, glanding, termination & continuity check | [29 empty] | 2018-01-03: 2019-04-10
2AI133EL07000-08010 | EOF:Allignment | [27 empty] | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12
2AI133EL07000-08005 | EOF:Installation of Transformer | [27 empty] | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12
2AI133EL07000-08001 | EOF:Installation of Supports | [27 empty] | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12
2AI133EL07000-08000 | EOF SS 52-SUBST-303 : Install Transformers | [27 empty] | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12
2AI133EL07000 | EOF SS 52-SUBST-303 : Install Transformers | [27 empty] | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12
2AI133EL05700-08000 | EOF SS 52-SUBST-302 : Install E-SCADA | [33 empty] | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04
2AI133EL05700 | EOF SS 52-SUBST-302 : Install E-SCADA | [33 empty] | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04
2AI133EL05600-08015 | EOF:Installation of Batteries | [33 empty] | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06
2AI133EL05600-08010 | EOF:Installation of Isolator Switch | [33 empty] | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05
2AI133EL05600-08006 | EOF:Installation of battery Charger | [33 empty] | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06
2AI133EL05600-08005 | EOF:Installation of UPS | [33 empty] | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05
2AI133EL05600-08001 | EOF:Installation of Supports | [33 empty] | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04
2AI133EL05600-08000 | 621-SUBST-0302 : Install UPS with Battery bank and Isolator Switch | [33 empty] | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06
2AI133EL05600 | EOF SS 52-SUBST-302 : Install UPS, Battery Charger with Battery bank and Isolator Switch | [33 empty] | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06
2AI133EL05500-08015 | EOF:Allignment | [33 empty] | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24
2AI133EL05500-08010 | EOF:Installation of Annunciator Panels | [29 empty] | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03
2AI133EL05500-08005 | EOF:Installation of Distribution Board | [33 empty] | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24
2AI133EL05500-08001 | EOF:Installation of Supports | [33 empty] | 2018-04-23 | 2018-04-23 | 2018-04-23 | 2018-04-23 | 2018-04-23 | 2018-04-23 | 2018-04-23 | 2018-04-23 | 2018-04-23 | 2018-04-23 | 2018-04-23 | 2018-04-23 | 2018-04-23
2AI133EL05500-08000 | 621-SUBST-0302 : Install Distribution boards and Annunciator Panels | [33 empty] | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24
2AI133EL05500 | EOF SS 52-SUBST-302 : Install Distribution boards and Annunciator Panels | [33 empty] | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24
2AI133EL05400-08020 | EOF:Allignment of Bus duct | [35 empty] | 2018-07-27 | 2018-07-27 | 2018-07-27 | 2018-07-27 | 2018-07-27 | 2018-07-27 | 2018-07-27 | 2018-07-27 | 2018-07-27 | 2018-07-27 | 2018-07-27
2AI133EL05400-08015 | EOF:Allignment of LV Switchgear, RCP & MCC | [31 empty] | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18
2AI133EL05400-08010 | EOF:Installation of Bus duct | [35 empty] | 2018-07-13 | 2018-07-13 | 2018-07-13 | 2018-07-13 | 2018-07-13 | 2018-07-13 | 2018-07-13 | 2018-07-13 | 2018-07-13 | 2018-07-13 | 2018-07-13
2AI133EL05400-08005 | EOF:Installation of LV Switchgear, RCP & MCC | [31 empty] | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18
2AI133EL05400-08001 | EOF:Installation of Supports | [31 empty] | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18
2AI133EL05400-08000 | 621-SUBST-0302 : Install LV Switchboards with RCP, MCC & Bus Ducts(incl. Lighting/small power) | [35 empty] | 2018-07-27 | 2018-07-27 | 2018-07-27 | 2018-07-27 | 2018-07-27 | 2018-07-27 | 2018-07-27 | 2018-07-27 | 2018-07-27 | 2018-07-27 | 2018-07-27
2AI133EL05400 | EOF SS 52-SUBST-302 : Install LV Switchboards with RCP, MCC & Bus Ducts(incl. Lighting/small power) | [35 empty] | 2018-07-27 | 2018-07-27 | 2018-07-27 | 2018-07-27 | 2018-07-27 | 2018-07-27 | 2018-07-27 | 2018-07-27 | 2018-07-27 | 2018-07-27 | 2018-07-27
2AI133EL05300-08020 | EOF:Allignment of Bus duct | [33 empty] | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04
2AI133EL05300-08015 | EOF:Allignment of HV Switchgear, RCP | [29 empty] | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06
2AI133EL05300-08010 | EOF:Installation of Bus duct | [29 empty] | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05
2AI133EL05300-08005 | EOF:Installation of HV Switchgear, RCP | [29 empty] | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06
2AI133EL05300-08001 | EOF:Installation of Supports | [29 empty] | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06
2AI133EL05300-08000 | 621-SUBST-0302 : Install HV Switchboard with RCP, Power Factor & Bus Ducts | [33 empty] | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04
2AI133EL05300 | EOF SS 52-SUBST-302 : Install HV Switchboard with RCP, Capacitor & Bus Ducts | [33 empty] | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04
2AI133EL05200-08045 | COCC: Earth Pit Installation | [33 empty] | 2018-04-04: 2019-04-10
2AI133EL05200-08025 | COCC: Earth cable Termination | [37 empty] | 2018-08-08 | 2018-08-08 | 2018-08-08 | 2018-08-08 | 2018-08-08 | 2018-08-08 | 2018-08-08 | 2018-08-08 | 2018-08-08
2AI133EL05200-08020 | COCC: Earth Boss Installation | [37 empty] | 2018-08-08: 2019-04-10
2AI133EL05200-08015 | COCC: Earth Bus Installation | [37 empty] | 2018-08-08: 2019-01-18; 2018-08-08: 2019-01-18; 2018-08-08: 2019-01-18; 2018-08-08: 2019-01-18; 2018-08-08: 2019-01-18
2AI133EL05200-08010 | COCC: Cad welding | [39 empty] | 2018-10-19 | 2018-10-19 | 2018-10-19 | 2018-10-19 | 2018-10-19 | 2018-10-19 | 2018-10-19
2AI133EL05200-08005 | COCC: Earth Cable Laying | [33 empty] | 2018-05-25 | 2018-05-25 | 2018-05-25 | 2018-05-25 | 2018-05-25 | 2018-05-25 | 2018-05-25 | 2018-05-25 | 2018-05-25 | 2018-05-25 | 2018-05-25 | 2018-05-25 | 2018-05-25
2AI133EL05200-08001 | COCC: Earth rod Installation | [33 empty] | 2018-05-25: 2019-04-10
2AI133EL05200-08000 | EOF:Earthing Work | [33 empty] | 2018-05-25: 2019-04-10
2AI133EL05200 | EOF SS 52-SUBST-302 : Earthing Lightning Protection Works | [33 empty] | 2018-05-25: 2019-04-10
2AI133EL05100-08060 | EOF: Tagging for HV cables | [33 empty] | 2018-05-25: 2018-10-10; 2018-05-25: 2018-10-10; 2018-05-25: 2018-10-10; 2018-05-25: 2018-10-10; 2018-05-25: 2018-10-10; 2018-05-25: 2018-10-10; 2018-05-25: 2018-10-10
2AI133EL05100-08055 | EOF: Continuity Checks & Terminations for HV cables | [33 empty] | 2018-05-25: 2018-10-10; 2018-05-25: 2018-10-10; 2018-05-25: 2018-10-10; 2018-05-25: 2018-10-10; 2018-05-25: 2018-10-10; 2018-05-25: 2018-10-10; 2018-05-25: 2018-10-10
2AI133EL05100-08050 | EOF: Cable Glanding for HV cables | [33 empty] | 2018-05-25: 2018-10-10; 2018-05-25: 2018-10-10; 2018-05-25: 2018-10-10; 2018-05-25: 2018-10-10; 2018-05-25: 2018-10-10; 2018-05-25: 2018-10-10; 2018-05-25: 2018-10-10
2AI133EL05100-08045 | EOF: Cable Laying - HV | [33 empty] | 2018-05-25: 2019-04-10
2AI133EL05100-08040 | EOF: Tagging for LV cables | [33 empty] | 2018-05-25: 2018-10-10; 2018-05-25: 2018-10-10; 2018-05-25: 2018-10-10; 2018-05-25: 2018-10-10; 2018-05-25: 2018-10-10; 2018-05-25: 2018-10-10; 2018-05-25: 2018-10-10
2AI133EL05100-08035 | EOF: Continuity Checks & Terminations for LV cables | [33 empty] | 2018-05-25: 2018-10-10; 2018-05-25: 2018-10-10; 2018-05-25: 2018-10-10; 2018-05-25: 2018-10-10; 2018-05-25: 2018-10-10; 2018-05-25: 2018-10-10; 2018-05-25: 2018-10-10
2AI133EL05100-08030 | EOF: Cable Glanding for LV cables | [33 empty] | 2018-05-25: 2018-10-10; 2018-05-25: 2018-10-10; 2018-05-25: 2018-10-10; 2018-05-25: 2018-10-10; 2018-05-25: 2018-10-10; 2018-05-25: 2018-10-10; 2018-05-25: 2018-10-10
2AI133EL05100-08029 | EOF: Cable Laying - LV | [37 empty] | 2018-09-10 | 2018-09-10 | 2018-09-10 | 2018-09-10 | 2018-09-10 | 2018-09-10 | 2018-09-10 | 2018-09-10 | 2018-09-10
2AI133EL05100-08025 | EOF: Installcable trays covers | [39 empty] | 2018-10-15 | 2018-10-15 | 2018-10-15 | 2018-10-15 | 2018-10-15 | 2018-10-15 | 2018-10-15
2AI133EL05100-08020 | EOF: Install cable trays | [39 empty] | 2018-10-08 | 2018-10-08 | 2018-10-08 | 2018-10-08 | 2018-10-08 | 2018-10-08 | 2018-10-08
2AI133EL05100-08015 | EOF: Install Tray support and Hangers | [31 empty] | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07
2AI133EL05100-08005 | 621-SUBST-0302 : Cable glanding, termination & continuity check | [31 empty] | 2018-02-07: 2018-10-10; 2018-02-07: 2018-10-10; 2018-02-07: 2018-10-10; 2018-02-07: 2018-10-10; 2018-02-07: 2018-10-10; 2018-02-07: 2018-10-10; 2018-02-07: 2018-10-10
2AI133EL05100-08000 | 621-SUBST-0302 : Cable laying | [31 empty] | 2018-02-07: 2019-04-10
2AI133EL05100 | EOF SS 52-SUBST-302 : Cable laying, glanding, termination & continuity check | [31 empty] | 2018-02-07: 2019-04-10
2AI133EL05000-08010 | EOF:Allignment | [31 empty] | 2018-02-08 | 2018-02-08 | 2018-02-08 | 2018-02-08 | 2018-02-08 | 2018-02-08 | 2018-02-08 | 2018-02-08 | 2018-02-08 | 2018-02-08 | 2018-02-08 | 2018-02-08 | 2018-02-08 | 2018-02-08 | 2018-02-08
2AI133EL05000-08005 | EOF:Installation of Transformer | [31 empty] | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07
2AI133EL05000-08001 | EOF:Installation of Supports | [31 empty] | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27
2AI133EL05000-08000 | 621-SUBST-0302 : Install Transformers | [31 empty] | 2018-02-08 | 2018-02-08 | 2018-02-08 | 2018-02-08 | 2018-02-08 | 2018-02-08 | 2018-02-08 | 2018-02-08 | 2018-02-08 | 2018-02-08 | 2018-02-08 | 2018-02-08 | 2018-02-08 | 2018-02-08 | 2018-02-08
2AI133EL05000 | EOF SS 52-SUBST-302 : Install Transformers | [31 empty] | 2018-02-08 | 2018-02-08 | 2018-02-08 | 2018-02-08 | 2018-02-08 | 2018-02-08 | 2018-02-08 | 2018-02-08 | 2018-02-08 | 2018-02-08 | 2018-02-08 | 2018-02-08 | 2018-02-08 | 2018-02-08 | 2018-02-08
2AI133EL03700-08000 | EOF SS 52-SUBST-301 : Install E-SCADA | [33 empty] | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18
2AI133EL03700 | EOF SS 52-SUBST-301 : Install E-SCADA | [33 empty] | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18
2AI133EL03600-08020 | EOF:Installation of Batteries | [33 empty] | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04
2AI133EL03600-08015 | EOF:Installation of Isolator Switch | [33 empty] | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05
2AI133EL03600-08010 | EOF:Installation of battery Charger | [33 empty] | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04
2AI133EL03600-08005 | EOF:Installation of UPS | [33 empty] | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04
2AI133EL03600-08001 | EOF:Installation of Supports | [33 empty] | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04
2AI133EL03600-08000 | EOF SS 52-SUBST-301 : Install UPS with Battery bank and Isolator Switch | [33 empty] | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05
2AI133EL03600 | EOF SS 52-SUBST-301 : Install UPS with Battery bank and Isolator Switch | [33 empty] | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05
2AI133EL03500-08015 | EOF:Allignment | [31 empty] | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07
2AI133EL03500-08010 | EOF:Installation of Annunciator Panels | [29 empty] | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03
2AI133EL03500-08005 | EOF:Installation of Distribution Board | [31 empty] | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05
2AI133EL03500-08001 | EOF:Installation of Supports | [31 empty] | 2018-02-04 | 2018-02-04 | 2018-02-04 | 2018-02-04 | 2018-02-04 | 2018-02-04 | 2018-02-04 | 2018-02-04 | 2018-02-04 | 2018-02-04 | 2018-02-04 | 2018-02-04 | 2018-02-04 | 2018-02-04 | 2018-02-04
2AI133EL03500-08000 | EOF SS 52-SUBST-301 : Install Distribution boards and Annunciator Panels | [31 empty] | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07
2AI133EL03500 | EOF SS 52-SUBST-301 : Install Distribution boards and Annunciator Panels | [31 empty] | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07
2AI133EL03400-08030 | EOF:Installation of Lighting & Small Power Panels | [29 empty] | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03
2AI133EL03400-08020 | EOF:Allignment of Bus duct | [33 empty] | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27
2AI133EL03400-08015 | EOF:Allignment of LV Switchgear, RCP & MCC | [29 empty] | 2018-01-19 | 2018-01-19 | 2018-01-19 | 2018-01-19 | 2018-01-19 | 2018-01-19 | 2018-01-19 | 2018-01-19 | 2018-01-19 | 2018-01-19 | 2018-01-19 | 2018-01-19 | 2018-01-19 | 2018-01-19 | 2018-01-19 | 2018-01-19 | 2018-01-19
2AI133EL03400-08010 | EOF:Installation of Bus duct | [33 empty] | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27
2AI133EL03400-08005 | EOF:Installation of LV Switchgear, RCP & MCC | [29 empty] | 2018-01-19 | 2018-01-19 | 2018-01-19 | 2018-01-19 | 2018-01-19 | 2018-01-19 | 2018-01-19 | 2018-01-19 | 2018-01-19 | 2018-01-19 | 2018-01-19 | 2018-01-19 | 2018-01-19 | 2018-01-19 | 2018-01-19 | 2018-01-19 | 2018-01-19
2AI133EL03400-08001 | EOF:Installation of Supports | [29 empty] | 2018-01-19 | 2018-01-19 | 2018-01-19 | 2018-01-19 | 2018-01-19 | 2018-01-19 | 2018-01-19 | 2018-01-19 | 2018-01-19 | 2018-01-19 | 2018-01-19 | 2018-01-19 | 2018-01-19 | 2018-01-19 | 2018-01-19 | 2018-01-19 | 2018-01-19
2AI133EL03400-08000 | EOF SS 52-SUBST-301 : Install LV Switchboards with RCP, MCC & Bus Ducts(incl. Lighting/small power,Modification work) | [33 empty] | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27
2AI133EL03400 | EOF SS 52-SUBST-301 : Install LV Switchboards with RCP, MCC & Bus Ducts(incl. Lighting/small power,Modification work) | [33 empty] | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27
2AI133EL03300-08100 | MODIFICATION WORK IN EXISTING 11kV SWITCHGEAR AND IT'S ASSOCIATED WORKS IN MG-1 SUBSTATION | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AI133EL03300-08020 | EOF:Allignment of Bus duct | [31 empty] | 2018-02-27: 2018-12-18; 2018-02-27: 2018-12-18; 2018-02-27: 2018-12-18; 2018-02-27: 2018-12-18; 2018-02-27: 2018-12-18
2AI133EL03300-08015 | EOF:Allignment of HV Switchgear, RCP | [29 empty] | 2018-01-14 | 2018-01-14 | 2018-01-14 | 2018-01-14 | 2018-01-14 | 2018-01-14 | 2018-01-14 | 2018-01-14 | 2018-01-14 | 2018-01-14 | 2018-01-14 | 2018-01-14 | 2018-01-14 | 2018-01-14 | 2018-01-14 | 2018-01-14 | 2018-01-14
2AI133EL03300-08010 | EOF:Installation of Bus duct | [29 empty] | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03
2AI133EL03300-08005 | EOF:Installation of HV Switchgear, RCP | [29 empty] | 2018-01-12 | 2018-01-12 | 2018-01-12 | 2018-01-12 | 2018-01-12 | 2018-01-12 | 2018-01-12 | 2018-01-12 | 2018-01-12 | 2018-01-12 | 2018-01-12 | 2018-01-12 | 2018-01-12 | 2018-01-12 | 2018-01-12 | 2018-01-12 | 2018-01-12
2AI133EL03300-08001 | EOF:Installation of Supports | [29 empty] | 2018-01-12 | 2018-01-12 | 2018-01-12 | 2018-01-12 | 2018-01-12 | 2018-01-12 | 2018-01-12 | 2018-01-12 | 2018-01-12 | 2018-01-12 | 2018-01-12 | 2018-01-12 | 2018-01-12 | 2018-01-12 | 2018-01-12 | 2018-01-12 | 2018-01-12
2AI133EL03300-08000 | EOF SS 52-SUBST-301 : Install HV Switchboard with RCP, Power Factor & Bus Ducts (Including Modification work) | [29 empty] | 2018-01-12: 2018-12-18; 2018-01-12: 2018-12-18; 2018-01-12: 2018-12-18; 2018-01-12: 2018-12-18; 2018-01-12: 2018-12-18
2AI133EL03300 | EOF SS 52-SUBST-301 : Install HV Switchboard with RCP, Power Factor & Bus Ducts (Including Modification work) | [29 empty] | 2018-01-12: 2018-12-18; 2018-01-12: 2018-12-18; 2018-01-12: 2018-12-18; 2018-01-12: 2018-12-18; 2018-01-12: 2018-12-18
2AI133EL03200-08045 | EOF SS 52-SUBST-301 : Earth Pit Installation | [33 empty] | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06
2AI133EL03200-08025 | EOF SS 52-SUBST-301 : Earth cable Termination | [31 empty] | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18
2AI133EL03200-08020 | EOF SS 52-SUBST-301 : Earth Boss Installation | [33 empty] | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05
2AI133EL03200-08015 | EOF SS 52-SUBST-301 : Earth Bus Installation | [33 empty] | 2018-04-20 | 2018-04-20 | 2018-04-20 | 2018-04-20 | 2018-04-20 | 2018-04-20 | 2018-04-20 | 2018-04-20 | 2018-04-20 | 2018-04-20 | 2018-04-20 | 2018-04-20 | 2018-04-20
2AI133EL03200-08010 | EOF SS 52-SUBST-301 : Cad welding | [35 empty] | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04
2AI133EL03200-08005 | EOF SS 52-SUBST-301 : Earth Cable Laying | [31 empty] | 2018-02-12 | 2018-02-12 | 2018-02-12 | 2018-02-12 | 2018-02-12 | 2018-02-12 | 2018-02-12 | 2018-02-12 | 2018-02-12 | 2018-02-12 | 2018-02-12 | 2018-02-12 | 2018-02-12 | 2018-02-12 | 2018-02-12
2AI133EL03200-08001 | EOF SS 52-SUBST-301 : Earth rod Installation | [35 empty] | 2018-07-13 | 2018-07-13 | 2018-07-13 | 2018-07-13 | 2018-07-13 | 2018-07-13 | 2018-07-13 | 2018-07-13 | 2018-07-13 | 2018-07-13 | 2018-07-13
2AI133EL03200-08000 | EOF SS 52-SUBST-301 : Earthing Work | [35 empty] | 2018-07-13 | 2018-07-13 | 2018-07-13 | 2018-07-13 | 2018-07-13 | 2018-07-13 | 2018-07-13 | 2018-07-13 | 2018-07-13 | 2018-07-13 | 2018-07-13
2AI133EL03200 | EOF SS 52-SUBST-301 : Earthing Lightning Protection Works | [35 empty] | 2018-07-13 | 2018-07-13 | 2018-07-13 | 2018-07-13 | 2018-07-13 | 2018-07-13 | 2018-07-13 | 2018-07-13 | 2018-07-13 | 2018-07-13 | 2018-07-13
2AI133EL03100-08050 | EOF: Tagging for HV cables | [31 empty] | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07
2AI133EL03100-08045 | EOF: Continuity Checks & Terminations for HV cables | [31 empty] | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07
2AI133EL03100-08040 | EOF: Cable Glanding for HV cables | [31 empty] | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07
2AI133EL03100-08030 | EOF: Tagging for LV cables | [37 empty] | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28
2AI133EL03100-08025 | EOF: Continuity Checks & Terminations for LV cables | [31 empty] | 2018-03-16 | 2018-03-16 | 2018-03-16 | 2018-03-16 | 2018-03-16 | 2018-03-16 | 2018-03-16 | 2018-03-16 | 2018-03-16 | 2018-03-16 | 2018-03-16 | 2018-03-16 | 2018-03-16 | 2018-03-16 | 2018-03-16
2AI133EL03100-08020 | EOF: Cable Glanding for LV cables | [37 empty] | 2018-09-27 | 2018-09-27 | 2018-09-27 | 2018-09-27 | 2018-09-27 | 2018-09-27 | 2018-09-27 | 2018-09-27 | 2018-09-27
2AI133EL03100-08015 | EOF: Installcable trays covers | [29 empty] | 2018-01-13 | 2018-01-13 | 2018-01-13 | 2018-01-13 | 2018-01-13 | 2018-01-13 | 2018-01-13 | 2018-01-13 | 2018-01-13 | 2018-01-13 | 2018-01-13 | 2018-01-13 | 2018-01-13 | 2018-01-13 | 2018-01-13 | 2018-01-13 | 2018-01-13
2AI133EL03100-08014 | EOF: Cable Laying - HV | [29 empty] | 2018-01-13 | 2018-01-13 | 2018-01-13 | 2018-01-13 | 2018-01-13 | 2018-01-13 | 2018-01-13 | 2018-01-13 | 2018-01-13 | 2018-01-13 | 2018-01-13 | 2018-01-13 | 2018-01-13 | 2018-01-13 | 2018-01-13 | 2018-01-13 | 2018-01-13
2AI133EL03100-08013 | EOF: Cable Laying - LV | [35 empty] | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04
2AI133EL03100-08010 | EOF: Install cable trays | [29 empty] | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24
2AI133EL03100-08006 | EOF: Install Tray support and Hangers | [29 empty] | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24
2AI133EL03100-08005 | 621-SUBST-0301 : Cable glanding/termination,checks | [37 empty] | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28
2AI133EL03100-08000 | 621-SUBST-0301 : Cable laying | [35 empty] | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04
2AI133EL03100 | EOF SS 52-SUBST-301 : Cable laying, glanding/termination,checks (incl UG cable laying to Existing SS for Tie-in) | [37 empty] | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28
2AI133EL03000-08010 | EOF:Allignment | [29 empty] | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24
2AI133EL03000-08005 | EOF:Installation of Transformer | [29 empty] | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24
2AI133EL03000-08001 | EOF:Installation of Supports | [29 empty] | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23
2AI133EL03000-08000 | 621-SUBST-0301 : Install Transformers | [29 empty] | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24
2AI133EL03000 | EOF SS 52-SUBST-301 : Install Transformers | [29 empty] | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24
2AI133EL01700-08000 | EOF SS 52-SUBST-302 : Install E-SCADA | [33 empty] | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06
2AI133EL01700 | EOF SS 52-SUBST-302 : Install E-SCADA | [33 empty] | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06
2AI133EL01600-08020 | EOF:Installation of Batteries | [33 empty] | 2018-05-17 | 2018-05-17 | 2018-05-17 | 2018-05-17 | 2018-05-17 | 2018-05-17 | 2018-05-17 | 2018-05-17 | 2018-05-17 | 2018-05-17 | 2018-05-17 | 2018-05-17 | 2018-05-17
2AI133EL01600-08015 | EOF:Installation of Isolator Switch | [33 empty] | 2018-05-16 | 2018-05-16 | 2018-05-16 | 2018-05-16 | 2018-05-16 | 2018-05-16 | 2018-05-16 | 2018-05-16 | 2018-05-16 | 2018-05-16 | 2018-05-16 | 2018-05-16 | 2018-05-16
2AI133EL01600-08010 | EOF:Installation of battery Charger | [33 empty] | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15
2AI133EL01600-08005 | EOF:Installation of UPS | [33 empty] | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04
2AI133EL01600-08001 | EOF:Installation of Supports | [33 empty] | 2018-04-04: 2019-04-10
2AI133EL01600-08000 | EOF SS 50-SUBST-001 : Install UPS with Battery bank and Isolator Switch | [33 empty] | 2018-04-04: 2019-04-10
2AI133EL01600 | EOF SS 50-SUBST-001 : Install UPS with Battery bank and Isolator Switch | [33 empty] | 2018-04-04: 2019-04-10
2AI133EL01500-08015 | EOF:Allignment | [33 empty] | 2018-04-04: 2019-04-10
2AI133EL01500-08010 | EOF:Installation of Annunciator Panels | [33 empty] | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04
2AI133EL01500-08005 | EOF:Installation of Distribution Board | [33 empty] | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06
2AI133EL01500-08001 | EOF:Installation of Supports | [33 empty] | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05
2AI133EL01500-08000 | EOF SS 50-SUBST-001 : Install Distribution boards and Annunciator Panels | [33 empty] | 2018-04-05: 2019-04-10
2AI133EL01500 | EOF SS 50-SUBST-001 : Install Distribution boards and Annunciator Panels | [33 empty] | 2018-04-05: 2019-04-10
2AI133EL01400-08045 | EOF:Allignment of Bus duct | [33 empty] | 2018-04-05: 2019-02-08; 2018-04-05: 2019-02-08; 2018-04-05: 2019-02-08
2AI133EL01400-08040 | EOF:Allignment of LV Switchgear, RCP & MCC | [35 empty] | 2018-07-27 | 2018-07-27 | 2018-07-27 | 2018-07-27 | 2018-07-27 | 2018-07-27 | 2018-07-27 | 2018-07-27 | 2018-07-27 | 2018-07-27 | 2018-07-27
2AI133EL01400-08035 | EOF:Installation of Bus duct | [35 empty] | 2018-07-27: 2019-01-25; 2018-07-27: 2019-01-25; 2018-07-27: 2019-01-25; 2018-07-27: 2019-01-25; 2018-07-27: 2019-01-25
2AI133EL01400-08030 | EOF:Installation of LV Switchgear, RCP & MCC | [35 empty] | 2018-07-26 | 2018-07-26 | 2018-07-26 | 2018-07-26 | 2018-07-26 | 2018-07-26 | 2018-07-26 | 2018-07-26 | 2018-07-26 | 2018-07-26 | 2018-07-26
2AI133EL01400-08025 | EOF:Installation of Supports | [33 empty] | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04
2AI133EL01400-08000 | EOF SS 50-SUBST-001 : Install LV Switchboards with RCP, MCC & Bus Ducts(incl. Lighting/small power) | [33 empty] | 2018-04-04: 2019-02-08; 2018-04-04: 2019-02-08; 2018-04-04: 2019-02-08
2AI133EL01400 | EOF SS 50-SUBST-001 : Install LV Switchboards with RCP, MCC & Bus Ducts(incl. Lighting/small power) | [33 empty] | 2018-04-04: 2019-02-08; 2018-04-04: 2019-02-08; 2018-04-04: 2019-02-08
2AI133EL01300-08015 | Final Alignment | [29 empty] | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03
2AI133EL01300-08010 | Preliminary Alignment & Grouting | [29 empty] | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06
2AI133EL01300-08005 | Installation on Foundation | [29 empty] | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06
2AI133EL01300-08001 | Foundation Checks/Preparation | [29 empty] | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06
2AI133EL01300-08000 | EOF SS 50-SUBST-001 : Install HV Switchboard with RCP, Power Factor & Bus Ducts | [29 empty] | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03
2AI133EL01300 | EOF SS 50-SUBST-001 : Install HV Switchboard with RCP, Power Factor & Bus Ducts | [29 empty] | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03
2AI133EL01200-08030 | COCC: Earth Pit Installation | [29 empty] | 2018-01-03: 2019-04-10
2AI133EL01200-08025 | COCC: Earth cable Termination | [29 empty] | 2018-01-03: 2019-03-01; 2018-01-03: 2019-03-01; 2018-01-03: 2019-03-01
2AI133EL01200-08020 | COCC: Earth Boss Installation | [35 empty] | 2018-07-27 | 2018-07-27 | 2018-07-27 | 2018-07-27 | 2018-07-27 | 2018-07-27 | 2018-07-27 | 2018-07-27 | 2018-07-27 | 2018-07-27 | 2018-07-27
2AI133EL01200-08015 | COCC: Earth Bus Installation | [37 empty] | 2018-08-03 | 2018-08-03 | 2018-08-03 | 2018-08-03 | 2018-08-03 | 2018-08-03 | 2018-08-03 | 2018-08-03 | 2018-08-03
2AI133EL01200-08010 | COCC: Cad welding | [37 empty] | 2018-08-03: 2019-04-10
2AI133EL01200-08005 | COCC: Earth Cable Laying | [37 empty] | 2018-08-03: 2019-04-10
2AI133EL01200-08001 | COCC: Earth rod Installation | [39 empty] | 2018-10-19 | 2018-10-19 | 2018-10-19 | 2018-10-19 | 2018-10-19 | 2018-10-19 | 2018-10-19
2AI133EL01200-08000 | EOF:Earthing Work | [37 empty] | 2018-08-03: 2019-04-10
2AI133EL01200 | EOF:Earthing Work | [37 empty] | 2018-08-03: 2019-04-10
2AI133EL01100-08050 | EOF: Tagging for HV cables | [37 empty] | 2018-08-03: 2019-04-10
2AI133EL01100-08045 | EOF: Continuity Checks & Terminations for HV cables | [37 empty] | 2018-08-03: 2019-04-10
2AI133EL01100-08040 | EOF: Cable Glanding for HV cables | [37 empty] | 2018-08-03: 2019-04-10
2AI133EL01100-08035 | EOF: Cable Laying - HV | [31 empty] | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07
2AI133EL01100-08030 | EOF: Tagging for LV cables | [35 empty] | 2018-06-25 | 2018-06-25 | 2018-06-25 | 2018-06-25 | 2018-06-25 | 2018-06-25 | 2018-06-25 | 2018-06-25 | 2018-06-25 | 2018-06-25 | 2018-06-25
2AI133EL01100-08025 | EOF: Continuity Checks & Terminations for LV cables | [35 empty] | 2018-06-24 | 2018-06-24 | 2018-06-24 | 2018-06-24 | 2018-06-24 | 2018-06-24 | 2018-06-24 | 2018-06-24 | 2018-06-24 | 2018-06-24 | 2018-06-24
2AI133EL01100-08020 | EOF: Cable Glanding for LV cables | [35 empty] | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23
2AI133EL01100-08015 | EOF: Cable Laying - LV | [37 empty] | 2018-09-05 | 2018-09-05 | 2018-09-05 | 2018-09-05 | 2018-09-05 | 2018-09-05 | 2018-09-05 | 2018-09-05 | 2018-09-05
2AI133EL01100-08011 | EOF: Installcable trays covers | [37 empty] | 2018-09-05: 2019-03-06; 2018-09-05: 2019-03-06; 2018-09-05: 2019-03-06
2AI133EL01100-08006 | EOF: Install cable trays | [37 empty] | 2018-09-05: 2019-03-06; 2018-09-05: 2019-03-06; 2018-09-05: 2019-03-06
2AI133EL01100-08005 | 621-SUBST-0001 : Cable glanding, termination & continuity check | [37 empty] | 2018-09-05: 2019-04-10
2AI133EL01100-08001 | EOF:Fabricate Tray Supports | [37 empty] | 2018-09-05: 2019-04-10
2AI133EL01100-08000 | 621-SUBST-0001 : Cable laying | [37 empty] | 2018-09-05: 2019-04-10
2AI133EL01100 | EOF SS 50-SUBST-001 : Cable laying, glanding, termination & continuity check | [37 empty] | 2018-09-05: 2019-04-10
2AI133EL01000-08010 | EOF:Allignment | [33 empty] | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27
2AI133EL01000-08005 | EOF:Installation of Transformer | [33 empty] | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27
2AI133EL01000-08001 | EOF:Installation of Supports | [33 empty] | 2018-03-26 | 2018-03-26 | 2018-03-26 | 2018-03-26 | 2018-03-26 | 2018-03-26 | 2018-03-26 | 2018-03-26 | 2018-03-26 | 2018-03-26 | 2018-03-26 | 2018-03-26 | 2018-03-26
2AI133EL01000-08000 | EOF SS 50-SUBST-001 :Install Transformers | [33 empty] | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27
2AI133EL01000 | EOF SS 50-SUBST-001 :Install Transformers | [33 empty] | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27 | 2018-03-27
2AI133CV99500-08141 | COCC : Shelter Erection for Car park | [33 empty] | 2018-03-27: 2019-02-10; 2018-03-27: 2019-02-10; 2018-03-27: 2019-02-10
2AI133CV99500-08012 | COCC:Wall & Roof Cladding | [33 empty] | 2018-03-27: 2019-02-10; 2018-03-27: 2019-02-10; 2018-03-27: 2019-02-10
2AI133CV99500-08011 | COCC:Installation of gratings/handrail/stair/ladder | [33 empty] | 2018-03-27: 2019-02-05; 2018-03-27: 2019-02-05; 2018-03-27: 2019-02-05
2AI133CV99500-08010 | COCC: Grouting of Shelter | [33 empty] | 2018-03-27: 2019-01-28; 2018-03-27: 2019-01-28; 2018-03-27: 2019-01-28
2AI133CV99500-08006 | COCC:Torque Bolts | [33 empty] | 2018-03-27: 2019-01-17; 2018-03-27: 2019-01-17; 2018-03-27: 2019-01-17; 2018-03-27: 2019-01-17; 2018-03-27: 2019-01-17
2AI133CV99500-08005 | COCC: Alignment/Welding/Bolting for Shelter | [33 empty] | 2018-03-27: 2019-01-15; 2018-03-27: 2019-01-15; 2018-03-27: 2019-01-15; 2018-03-27: 2019-01-15; 2018-03-27: 2019-01-15
2AI133CV99500-08000 | COCC: Installation of Main steel structure | [33 empty] | 2018-03-27: 2019-01-14; 2018-03-27: 2019-01-14; 2018-03-27: 2019-01-14; 2018-03-27: 2019-01-14; 2018-03-27: 2019-01-14
2AI133CV99500 | COCC : Car Shelter Erection & Miscellanious Shelter | [33 empty] | 2018-03-27: 2019-02-10; 2018-03-27: 2019-02-10; 2018-03-27: 2019-02-10
2AI133CV99400-08141 | COCC : Shelter Foundation for Car Park | [37 empty] | 2018-08-18 | 2018-08-18 | 2018-08-18 | 2018-08-18 | 2018-08-18 | 2018-08-18 | 2018-08-18 | 2018-08-18 | 2018-08-18
2AI133CV99400-08025 | COCC: Backfilling & Compaction for Fnd | [37 empty] | 2018-08-18 | 2018-08-18 | 2018-08-18 | 2018-08-18 | 2018-08-18 | 2018-08-18 | 2018-08-18 | 2018-08-18 | 2018-08-18
2AI133CV99400-08020 | COCC: Concrete Potection for Fnd | [35 empty] | 2018-06-20 | 2018-06-20 | 2018-06-20 | 2018-06-20 | 2018-06-20 | 2018-06-20 | 2018-06-20 | 2018-06-20 | 2018-06-20 | 2018-06-20 | 2018-06-20
2AI133CV99400-08016 | COCC:Concrete Pouring for Pedestal | [35 empty] | 2018-06-25 | 2018-06-25 | 2018-06-25 | 2018-06-25 | 2018-06-25 | 2018-06-25 | 2018-06-25 | 2018-06-25 | 2018-06-25 | 2018-06-25 | 2018-06-25
2AI133CV99400-08015 | COCC: Rebar, Formwork & Install Embedments for Pedestal | [35 empty] | 2018-06-22 | 2018-06-22 | 2018-06-22 | 2018-06-22 | 2018-06-22 | 2018-06-22 | 2018-06-22 | 2018-06-22 | 2018-06-22 | 2018-06-22 | 2018-06-22
2AI133CV99400-08011 | COCC:Concrete Pouring for Footing | [35 empty] | 2018-06-20 | 2018-06-20 | 2018-06-20 | 2018-06-20 | 2018-06-20 | 2018-06-20 | 2018-06-20 | 2018-06-20 | 2018-06-20 | 2018-06-20 | 2018-06-20
2AI133CV99400-08010 | COCC: Rebar, Formwork for Footing | [35 empty] | 2018-06-20 | 2018-06-20 | 2018-06-20 | 2018-06-20 | 2018-06-20 | 2018-06-20 | 2018-06-20 | 2018-06-20 | 2018-06-20 | 2018-06-20 | 2018-06-20
2AI133CV99400-08005 | COCC: Blinding/PCC for Fnd | [35 empty] | 2018-06-18 | 2018-06-18 | 2018-06-18 | 2018-06-18 | 2018-06-18 | 2018-06-18 | 2018-06-18 | 2018-06-18 | 2018-06-18 | 2018-06-18 | 2018-06-18
2AI133CV99400-08000 | COCC: Excavation & Subgrade | [35 empty] | 2018-06-12 | 2018-06-12 | 2018-06-12 | 2018-06-12 | 2018-06-12 | 2018-06-12 | 2018-06-12 | 2018-06-12 | 2018-06-12 | 2018-06-12 | 2018-06-12
2AI133CV99400 | COCC : Construct Car Shelter Foundation & Miscellanious Shelter Foundation | [37 empty] | 2018-08-18 | 2018-08-18 | 2018-08-18 | 2018-08-18 | 2018-08-18 | 2018-08-18 | 2018-08-18 | 2018-08-18 | 2018-08-18
2AI133CV99300-08095 | EOF:Wall & Roof Cladding | [39 empty] | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05
2AI133CV99300-08085 | EOF:Wall & Roof Cladding | [39 empty] | 2018-10-23 | 2018-10-23 | 2018-10-23 | 2018-10-23 | 2018-10-23 | 2018-10-23 | 2018-10-23
2AI133CV99300-08075 | EOF:Installation of gratings/handrail/stair/ladder (wherever applicable) | [39 empty] | 2018-10-26 | 2018-10-26 | 2018-10-26 | 2018-10-26 | 2018-10-26 | 2018-10-26 | 2018-10-26
2AI133CV99300-08070 | EOF:Wall & Roof Cladding | [37 empty] | 2018-08-18: 2018-12-18; 2018-08-18: 2018-12-18; 2018-08-18: 2018-12-18; 2018-08-18: 2018-12-18; 2018-08-18: 2018-12-18
2AI133CV99300-08065 | EOF:Installation of gratings/handrail/stair/ladder (wherever applicable) | [35 empty] | 2018-06-10 | 2018-06-10 | 2018-06-10 | 2018-06-10 | 2018-06-10 | 2018-06-10 | 2018-06-10 | 2018-06-10 | 2018-06-10 | 2018-06-10 | 2018-06-10
2AI133CV99300-08060 | EOF:Installation of gratings/handrail/stair/ladder (wherever applicable) | [35 empty] | 2018-06-10: 2018-12-18; 2018-06-10: 2018-12-18; 2018-06-10: 2018-12-18; 2018-06-10: 2018-12-18; 2018-06-10: 2018-12-18
2AI133CV99300-08055 | EOF:Grouting | [39 empty] | 2018-10-26 | 2018-10-26 | 2018-10-26 | 2018-10-26 | 2018-10-26 | 2018-10-26 | 2018-10-26
2AI133CV99300-08050 | EOF:Alignment & Bolting/Torqueing | [39 empty] | 2018-10-15 | 2018-10-15 | 2018-10-15 | 2018-10-15 | 2018-10-15 | 2018-10-15 | 2018-10-15
2AI133CV99300-08045 | EOF:Installation of Str. Steel | [39 empty] | 2018-10-10 | 2018-10-10 | 2018-10-10 | 2018-10-10 | 2018-10-10 | 2018-10-10 | 2018-10-10
2AI133CV99300-08040 | EOF:Grouting | [35 empty] | 2018-06-10: 2018-12-23; 2018-06-10: 2018-12-23; 2018-06-10: 2018-12-23; 2018-06-10: 2018-12-23; 2018-06-10: 2018-12-23
2AI133CV99300-08036 | EOF:Wall & Roof Cladding | [37 empty] | 2018-08-08 | 2018-08-08 | 2018-08-08 | 2018-08-08 | 2018-08-08 | 2018-08-08 | 2018-08-08 | 2018-08-08 | 2018-08-08
2AI133CV99300-08035 | EOF:Alignment & Bolting/Torqueing | [39 empty] | 2018-10-15 | 2018-10-15 | 2018-10-15 | 2018-10-15 | 2018-10-15 | 2018-10-15 | 2018-10-15
2AI133CV99300-08030 | EOF:Installation of Str. Steel | [39 empty] | 2018-10-08 | 2018-10-08 | 2018-10-08 | 2018-10-08 | 2018-10-08 | 2018-10-08 | 2018-10-08
2AI133CV99300-08026 | EOF:Installation of gratings/handrail/stair/ladder (wherever applicable) | [37 empty] | 2018-08-08 | 2018-08-08 | 2018-08-08 | 2018-08-08 | 2018-08-08 | 2018-08-08 | 2018-08-08 | 2018-08-08 | 2018-08-08
2AI133CV99300-08025 | EOF:Grouting | [35 empty] | 2018-06-10 | 2018-06-10 | 2018-06-10 | 2018-06-10 | 2018-06-10 | 2018-06-10 | 2018-06-10 | 2018-06-10 | 2018-06-10 | 2018-06-10 | 2018-06-10
2AI133CV99300-08022 | EOF:Alignment & Bolting/Torqueing | [31 empty] | 2018-03-12 | 2018-03-12 | 2018-03-12 | 2018-03-12 | 2018-03-12 | 2018-03-12 | 2018-03-12 | 2018-03-12 | 2018-03-12 | 2018-03-12 | 2018-03-12 | 2018-03-12 | 2018-03-12 | 2018-03-12 | 2018-03-12
2AI133CV99300-08021 | EOF:Installation of Str. Steel | [31 empty] | 2018-02-06 | 2018-02-06 | 2018-02-06 | 2018-02-06 | 2018-02-06 | 2018-02-06 | 2018-02-06 | 2018-02-06 | 2018-02-06 | 2018-02-06 | 2018-02-06 | 2018-02-06 | 2018-02-06 | 2018-02-06 | 2018-02-06
2AI133CV99300-08016 | EOF:Grouting | [37 empty] | 2018-08-08 | 2018-08-08 | 2018-08-08 | 2018-08-08 | 2018-08-08 | 2018-08-08 | 2018-08-08 | 2018-08-08 | 2018-08-08
2AI133CV99300-08015 | Shelter Erection for Diesel Tank & Inert Agent of 52-SUBST-303 - SUBSTATION - LMM | [39 empty] | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05
2AI133CV99300-08011 | EOF:Alignment & Bolting/Torqueing | [35 empty] | 2018-06-21 | 2018-06-21 | 2018-06-21 | 2018-06-21 | 2018-06-21 | 2018-06-21 | 2018-06-21 | 2018-06-21 | 2018-06-21 | 2018-06-21 | 2018-06-21
2AI133CV99300-08010 | Shelter Erection for Diesel Tank & Inert Agent of 50-SUBST-001 - SUBSTATION - COCC | [35 empty] | 2018-06-21: 2018-12-23; 2018-06-21: 2018-12-23; 2018-06-21: 2018-12-23; 2018-06-21: 2018-12-23; 2018-06-21: 2018-12-23
2AI133CV99300-08006 | EOF:Installation of Str. Steel | [35 empty] | 2018-06-18 | 2018-06-18 | 2018-06-18 | 2018-06-18 | 2018-06-18 | 2018-06-18 | 2018-06-18 | 2018-06-18 | 2018-06-18 | 2018-06-18 | 2018-06-18
2AI133CV99300-08005 | Shelter Erection for Diesel Tank & Inert Agent of 52-SUBST-302 - SUBSTATION - STF | [39 empty] | 2018-10-23 | 2018-10-23 | 2018-10-23 | 2018-10-23 | 2018-10-23 | 2018-10-23 | 2018-10-23
2AI133CV99300-08000 | Shelter Erection for Diesel Tank & Inert Agent of 52-SUBST-301 - SUBSTATION - FMM | [37 empty] | 2018-08-08 | 2018-08-08 | 2018-08-08 | 2018-08-08 | 2018-08-08 | 2018-08-08 | 2018-08-08 | 2018-08-08 | 2018-08-08
2AI133CV99300 | EOF SS : Shelter Erection for Diesel Tank & Inert Agent | [37 empty] | 2018-08-08: 2018-12-23; 2018-08-08: 2018-12-23; 2018-08-08: 2018-12-23; 2018-08-08: 2018-12-23; 2018-08-08: 2018-12-23
2AI133CV99200-08115 | EOF:Backfilling & Compaction for Fnd | [29 empty] | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21
2AI133CV99200-08110 | EOF:Concrete Potection for Fnd | [27 empty] | 2017-11-23 | 2017-11-23 | 2017-11-23 | 2017-11-23 | 2017-11-23 | 2017-11-23 | 2017-11-23 | 2017-11-23 | 2017-11-23 | 2017-11-23 | 2017-11-23 | 2017-11-23 | 2017-11-23 | 2017-11-23 | 2017-11-23 | 2017-11-23 | 2017-11-23 | 2017-11-23 | 2017-11-23
2AI133CV99200-08106 | EOF:Concrete Pouring - for Pedestal | [27 empty] | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08
2AI133CV99200-08105 | EOF:Rebar, Formwork, Install Embedments for Pedestal | [27 empty] | 2017-11-07 | 2017-11-07 | 2017-11-07 | 2017-11-07 | 2017-11-07 | 2017-11-07 | 2017-11-07 | 2017-11-07 | 2017-11-07 | 2017-11-07 | 2017-11-07 | 2017-11-07 | 2017-11-07 | 2017-11-07 | 2017-11-07 | 2017-11-07 | 2017-11-07 | 2017-11-07 | 2017-11-07
2AI133CV99200-08101 | EOF:Concrete Pouring - for Footing | [27 empty] | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08
2AI133CV99200-08100 | EOF:Rebar, Formwork for Footing | [27 empty] | 2017-11-07 | 2017-11-07 | 2017-11-07 | 2017-11-07 | 2017-11-07 | 2017-11-07 | 2017-11-07 | 2017-11-07 | 2017-11-07 | 2017-11-07 | 2017-11-07 | 2017-11-07 | 2017-11-07 | 2017-11-07 | 2017-11-07 | 2017-11-07 | 2017-11-07 | 2017-11-07 | 2017-11-07
2AI133CV99200-08095 | EOF:Blinding/PCC for Fnd | [27 empty] | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02
2AI133CV99200-08090 | EOF:Survey Marking, Excavation & Subgrade | [27 empty] | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01
2AI133CV99200-08085 | EOF:Backfilling & Compaction for Fnd | [29 empty] | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26
2AI133CV99200-08080 | EOF:Concrete Potection for Fnd | [29 empty] | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22
2AI133CV99200-08076 | EOF:Concrete Pouring - for Pedestal | [29 empty] | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11
2AI133CV99200-08075 | EOF:Rebar, Formwork, Install Embedments for Pedestal | [29 empty] | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11
2AI133CV99200-08071 | EOF:Concrete Pouring - for Footing | [29 empty] | 2017-12-31 | 2017-12-31 | 2017-12-31 | 2017-12-31 | 2017-12-31 | 2017-12-31 | 2017-12-31 | 2017-12-31 | 2017-12-31 | 2017-12-31 | 2017-12-31 | 2017-12-31 | 2017-12-31 | 2017-12-31 | 2017-12-31 | 2017-12-31 | 2017-12-31
2AI133CV99200-08070 | EOF:Rebar, Formwork for Footing | [29 empty] | 2017-12-30 | 2017-12-30 | 2017-12-30 | 2017-12-30 | 2017-12-30 | 2017-12-30 | 2017-12-30 | 2017-12-30 | 2017-12-30 | 2017-12-30 | 2017-12-30 | 2017-12-30 | 2017-12-30 | 2017-12-30 | 2017-12-30 | 2017-12-30 | 2017-12-30
2AI133CV99200-08065 | EOF:Blinding/PCC for Fnd | [29 empty] | 2017-12-21 | 2017-12-21 | 2017-12-21 | 2017-12-21 | 2017-12-21 | 2017-12-21 | 2017-12-21 | 2017-12-21 | 2017-12-21 | 2017-12-21 | 2017-12-21 | 2017-12-21 | 2017-12-21 | 2017-12-21 | 2017-12-21 | 2017-12-21 | 2017-12-21
2AI133CV99200-08060 | EOF:Survey Marking, Excavation & Subgrade | [29 empty] | 2017-12-20 | 2017-12-20 | 2017-12-20 | 2017-12-20 | 2017-12-20 | 2017-12-20 | 2017-12-20 | 2017-12-20 | 2017-12-20 | 2017-12-20 | 2017-12-20 | 2017-12-20 | 2017-12-20 | 2017-12-20 | 2017-12-20 | 2017-12-20 | 2017-12-20
2AI133CV99200-08055 | EOF:Backfilling & Compaction for Fnd | [31 empty] | 2018-01-28 | 2018-01-28 | 2018-01-28 | 2018-01-28 | 2018-01-28 | 2018-01-28 | 2018-01-28 | 2018-01-28 | 2018-01-28 | 2018-01-28 | 2018-01-28 | 2018-01-28 | 2018-01-28 | 2018-01-28 | 2018-01-28
2AI133CV99200-08050 | EOF:Concrete Potection for Fnd | [29 empty] | 2018-01-09 | 2018-01-09 | 2018-01-09 | 2018-01-09 | 2018-01-09 | 2018-01-09 | 2018-01-09 | 2018-01-09 | 2018-01-09 | 2018-01-09 | 2018-01-09 | 2018-01-09 | 2018-01-09 | 2018-01-09 | 2018-01-09 | 2018-01-09 | 2018-01-09
2AI133CV99200-08046 | EOF:Concrete Pouring - for Pedestal | [29 empty] | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03
2AI133CV99200-08045 | EOF:Rebar, Formwork, Install Embedments for Pedestal | [29 empty] | 2018-01-02 | 2018-01-02 | 2018-01-02 | 2018-01-02 | 2018-01-02 | 2018-01-02 | 2018-01-02 | 2018-01-02 | 2018-01-02 | 2018-01-02 | 2018-01-02 | 2018-01-02 | 2018-01-02 | 2018-01-02 | 2018-01-02 | 2018-01-02 | 2018-01-02
2AI133CV99200-08041 | EOF:Concrete Pouring - for Footing | [29 empty] | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03
2AI133CV99200-08040 | EOF:Rebar, Formwork for Footing | [29 empty] | 2018-01-02 | 2018-01-02 | 2018-01-02 | 2018-01-02 | 2018-01-02 | 2018-01-02 | 2018-01-02 | 2018-01-02 | 2018-01-02 | 2018-01-02 | 2018-01-02 | 2018-01-02 | 2018-01-02 | 2018-01-02 | 2018-01-02 | 2018-01-02 | 2018-01-02
2AI133CV99200-08036 | EOF:Backfilling & Compaction for Fnd | [31 empty] | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07
2AI133CV99200-08035 | EOF:Blinding/PCC for Fnd | [27 empty] | 2017-10-25 | 2017-10-25 | 2017-10-25 | 2017-10-25 | 2017-10-25 | 2017-10-25 | 2017-10-25 | 2017-10-25 | 2017-10-25 | 2017-10-25 | 2017-10-25 | 2017-10-25 | 2017-10-25 | 2017-10-25 | 2017-10-25 | 2017-10-25 | 2017-10-25 | 2017-10-25 | 2017-10-25
2AI133CV99200-08031 | EOF:Concrete Potection for Fnd | [27 empty] | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22
2AI133CV99200-08030 | EOF:Survey Marking, Excavation & Subgrade | [27 empty] | 2017-10-24 | 2017-10-24 | 2017-10-24 | 2017-10-24 | 2017-10-24 | 2017-10-24 | 2017-10-24 | 2017-10-24 | 2017-10-24 | 2017-10-24 | 2017-10-24 | 2017-10-24 | 2017-10-24 | 2017-10-24 | 2017-10-24 | 2017-10-24 | 2017-10-24 | 2017-10-24 | 2017-10-24
2AI133CV99200-08026 | EOF:Concrete Pouring - for Pedestal | [27 empty] | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02
2AI133CV99200-08021 | EOF:Rebar, Formwork, Install Embedments for Pedestal | [27 empty] | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01
2AI133CV99200-08016 | EOF:Concrete Pouring - for Footing | [27 empty] | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02
2AI133CV99200-08015 | EOF SS : Shelter Foundation for Diesel Tank & Inert Agent of 52-SUBST-303 - SUBSTATION - LMM | [29 empty] | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21
2AI133CV99200-08011 | EOF:Rebar, Formwork for Footing | [27 empty] | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01
2AI133CV99200-08010 | EOF SS : Shelter Foundation for Diesel Tank & Inert Agent of 50-SUBST-001 - SUBSTATION - COCC | [29 empty] | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26
2AI133CV99200-08006 | EOF:Blinding/PCC for Fnd | [23 empty] | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23
2AI133CV99200-08005 | EOF SS : Shelter Foundation for Diesel Tank & Inert Agent of 52-SUBST-302 - SUBSTATION - STF | [31 empty] | 2018-01-28 | 2018-01-28 | 2018-01-28 | 2018-01-28 | 2018-01-28 | 2018-01-28 | 2018-01-28 | 2018-01-28 | 2018-01-28 | 2018-01-28 | 2018-01-28 | 2018-01-28 | 2018-01-28 | 2018-01-28 | 2018-01-28
2AI133CV99200-08001 | EOF:Survey Marking, Excavation & Subgrade | [23 empty] | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05
2AI133CV99200-08000 | EOF SS : Shelter Foundation for Diesel Tank & Inert Agent of 52-SUBST-301 - SUBSTATION - FMM | [31 empty] | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07
2AI133CV99200 | EOF SS : Shelter Foundation for Diesel Tank & Inert Agent | [31 empty] | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07
2AI133CV99100-08095 | Wall & Roof Cladding | [37 empty] | 2018-08-18 | 2018-08-18 | 2018-08-18 | 2018-08-18 | 2018-08-18 | 2018-08-18 | 2018-08-18 | 2018-08-18 | 2018-08-18
2AI133CV99100-08085 | Installation of gratings/handrail/stair/ladder (wherever applicable) | [37 empty] | 2018-08-18: 2018-12-14; 2018-08-18: 2018-12-14; 2018-08-18: 2018-12-14; 2018-08-18: 2018-12-14; 2018-08-18: 2018-12-14
2AI133CV99100-08075 | Wall & Roof Cladding | [33 empty] | 2018-05-12 | 2018-05-12 | 2018-05-12 | 2018-05-12 | 2018-05-12 | 2018-05-12 | 2018-05-12 | 2018-05-12 | 2018-05-12 | 2018-05-12 | 2018-05-12 | 2018-05-12 | 2018-05-12
2AI133CV99100-08070 | Wall & Roof Cladding | [33 empty] | 2018-05-12: 2018-10-09; 2018-05-12: 2018-10-09; 2018-05-12: 2018-10-09; 2018-05-12: 2018-10-09; 2018-05-12: 2018-10-09; 2018-05-12: 2018-10-09; 2018-05-12: 2018-10-09
2AI133CV99100-08065 | Installation of gratings/handrail/stair/ladder (wherever applicable) | [33 empty] | 2018-05-12 | 2018-05-12 | 2018-05-12 | 2018-05-12 | 2018-05-12 | 2018-05-12 | 2018-05-12 | 2018-05-12 | 2018-05-12 | 2018-05-12 | 2018-05-12 | 2018-05-12 | 2018-05-12
2AI133CV99100-08060 | Installation of gratings/handrail/stair/ladder (wherever applicable) | [37 empty] | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28
2AI133CV99100-08055 | EOF:Grouting | [37 empty] | 2018-09-01 | 2018-09-01 | 2018-09-01 | 2018-09-01 | 2018-09-01 | 2018-09-01 | 2018-09-01 | 2018-09-01 | 2018-09-01
2AI133CV99100-08050 | EOF:Alignment & Bolting/Torqueing | [29 empty] | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22
2AI133CV99100-08045 | EOF:Installation of Str. Steel | [29 empty] | 2017-12-27 | 2017-12-27 | 2017-12-27 | 2017-12-27 | 2017-12-27 | 2017-12-27 | 2017-12-27 | 2017-12-27 | 2017-12-27 | 2017-12-27 | 2017-12-27 | 2017-12-27 | 2017-12-27 | 2017-12-27 | 2017-12-27 | 2017-12-27 | 2017-12-27
2AI133CV99100-08040 | EOF:Grouting | [37 empty] | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28
2AI133CV99100-08035 | EOF:Alignment & Bolting/Torqueing | [37 empty] | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28
2AI133CV99100-08031 | Wall & Roof Cladding | [33 empty] | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15
2AI133CV99100-08030 | EOF:Installation of Str. Steel | [37 empty] | 2018-09-27 | 2018-09-27 | 2018-09-27 | 2018-09-27 | 2018-09-27 | 2018-09-27 | 2018-09-27 | 2018-09-27 | 2018-09-27
2AI133CV99100-08025 | EOF:Grouting | [37 empty] | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23
2AI133CV99100-08021 | Installation of gratings/handrail/stair/ladder (wherever applicable) | [33 empty] | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15
2AI133CV99100-08020 | EOF:Alignment & Bolting/Torqueing | [33 empty] | 2018-05-09 | 2018-05-09 | 2018-05-09 | 2018-05-09 | 2018-05-09 | 2018-05-09 | 2018-05-09 | 2018-05-09 | 2018-05-09 | 2018-05-09 | 2018-05-09 | 2018-05-09 | 2018-05-09
2AI133CV99100-08016 | EOF:Installation of Str. Steel | [33 empty] | 2018-05-08 | 2018-05-08 | 2018-05-08 | 2018-05-08 | 2018-05-08 | 2018-05-08 | 2018-05-08 | 2018-05-08 | 2018-05-08 | 2018-05-08 | 2018-05-08 | 2018-05-08 | 2018-05-08
2AI133CV99100-08015 | EOF SS : Shelter Erection for Transformer, Capacitor of 52-SUBST-303 - SUBSTATION - LMM | [33 empty] | 2018-05-08: 2018-12-14; 2018-05-08: 2018-12-14; 2018-05-08: 2018-12-14; 2018-05-08: 2018-12-14; 2018-05-08: 2018-12-14
2AI133CV99100-08011 | EOF:Grouting | [33 empty] | 2018-05-09 | 2018-05-09 | 2018-05-09 | 2018-05-09 | 2018-05-09 | 2018-05-09 | 2018-05-09 | 2018-05-09 | 2018-05-09 | 2018-05-09 | 2018-05-09 | 2018-05-09 | 2018-05-09
2AI133CV99100-08010 | EOF SS : Shelter Erection for Transformer, Capacitor of 50-SUBST-001 - SUBSTATION - COCC | [33 empty] | 2018-05-09: 2018-10-09; 2018-05-09: 2018-10-09; 2018-05-09: 2018-10-09; 2018-05-09: 2018-10-09; 2018-05-09: 2018-10-09; 2018-05-09: 2018-10-09; 2018-05-09: 2018-10-09
2AI133CV99100-08006 | EOF:Alignment & Bolting/Torqueing | [33 empty] | 2018-05-09 | 2018-05-09 | 2018-05-09 | 2018-05-09 | 2018-05-09 | 2018-05-09 | 2018-05-09 | 2018-05-09 | 2018-05-09 | 2018-05-09 | 2018-05-09 | 2018-05-09 | 2018-05-09
2AI133CV99100-08005 | EOF SS : Shelter Erection for Transformer, Capacitor of 52-SUBST-302 - SUBSTATION - STF | [37 empty] | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23
2AI133CV99100-08001 | EOF:Installation of Str. Steel | [33 empty] | 2018-05-08 | 2018-05-08 | 2018-05-08 | 2018-05-08 | 2018-05-08 | 2018-05-08 | 2018-05-08 | 2018-05-08 | 2018-05-08 | 2018-05-08 | 2018-05-08 | 2018-05-08 | 2018-05-08
2AI133CV99100-08000 | EOF SS : Shelter Erection for Transformer, Capacitor of 52-SUBST-301 - SUBSTATION - FMM | [33 empty] | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15
2AI133CV99100 | EOF SS : Shelter Erection for Transformer, Capacitor | [33 empty] | 2018-05-15: 2018-12-14; 2018-05-15: 2018-12-14; 2018-05-15: 2018-12-14; 2018-05-15: 2018-12-14; 2018-05-15: 2018-12-14
2AI133CV99000-08420 | EOF:Backfilling & Compaction for Fnd | [25 empty] | 2017-08-31 | 2017-08-31 | 2017-08-31 | 2017-08-31 | 2017-08-31 | 2017-08-31 | 2017-08-31 | 2017-08-31 | 2017-08-31 | 2017-08-31 | 2017-08-31 | 2017-08-31 | 2017-08-31 | 2017-08-31 | 2017-08-31 | 2017-08-31 | 2017-08-31 | 2017-08-31 | 2017-08-31 | 2017-08-31 | 2017-08-31
2AI133CV99000-08415 | EOF:Concrete Potection for Fnd | [25 empty] | 2017-08-16 | 2017-08-16 | 2017-08-16 | 2017-08-16 | 2017-08-16 | 2017-08-16 | 2017-08-16 | 2017-08-16 | 2017-08-16 | 2017-08-16 | 2017-08-16 | 2017-08-16 | 2017-08-16 | 2017-08-16 | 2017-08-16 | 2017-08-16 | 2017-08-16 | 2017-08-16 | 2017-08-16 | 2017-08-16 | 2017-08-16
2AI133CV99000-08411 | EOF:Concrete Pouring - for Pedestal | [23 empty] | 2017-07-27 | 2017-07-27 | 2017-07-27 | 2017-07-27 | 2017-07-27 | 2017-07-27 | 2017-07-27 | 2017-07-27 | 2017-07-27 | 2017-07-27 | 2017-07-27 | 2017-07-27 | 2017-07-27 | 2017-07-27 | 2017-07-27 | 2017-07-27 | 2017-07-27 | 2017-07-27 | 2017-07-27 | 2017-07-27 | 2017-07-27 | 2017-07-27 | 2017-07-27
2AI133CV99000-08410 | EOF:Rebar, Formwork & Install Embedments for Pedestal | [23 empty] | 2017-07-26 | 2017-07-26 | 2017-07-26 | 2017-07-26 | 2017-07-26 | 2017-07-26 | 2017-07-26 | 2017-07-26 | 2017-07-26 | 2017-07-26 | 2017-07-26 | 2017-07-26 | 2017-07-26 | 2017-07-26 | 2017-07-26 | 2017-07-26 | 2017-07-26 | 2017-07-26 | 2017-07-26 | 2017-07-26 | 2017-07-26 | 2017-07-26 | 2017-07-26
2AI133CV99000-08406 | EOF:Concrete Pouring - for Footing | [23 empty] | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17
2AI133CV99000-08405 | EOF:Rebar, Formwork for Footing | [23 empty] | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17
2AI133CV99000-08400 | EOF:Blinding/PCC for Fnd | [23 empty] | 2017-06-08 | 2017-06-08 | 2017-06-08 | 2017-06-08 | 2017-06-08 | 2017-06-08 | 2017-06-08 | 2017-06-08 | 2017-06-08 | 2017-06-08 | 2017-06-08 | 2017-06-08 | 2017-06-08 | 2017-06-08 | 2017-06-08 | 2017-06-08 | 2017-06-08 | 2017-06-08 | 2017-06-08 | 2017-06-08 | 2017-06-08 | 2017-06-08 | 2017-06-08
2AI133CV99000-08395 | EOF:Excavation & Subgrade | [23 empty] | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06
2AI133CV99000-08390 | EOF:Backfilling & Compaction for Fnd | [35 empty] | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04
2AI133CV99000-08385 | EOF:Concrete Potection for Fnd | [35 empty] | 2018-06-22 | 2018-06-22 | 2018-06-22 | 2018-06-22 | 2018-06-22 | 2018-06-22 | 2018-06-22 | 2018-06-22 | 2018-06-22 | 2018-06-22 | 2018-06-22
2AI133CV99000-08381 | EOF:Concrete Pouring - for Pedestal | [31 empty] | 2018-02-04 | 2018-02-04 | 2018-02-04 | 2018-02-04 | 2018-02-04 | 2018-02-04 | 2018-02-04 | 2018-02-04 | 2018-02-04 | 2018-02-04 | 2018-02-04 | 2018-02-04 | 2018-02-04 | 2018-02-04 | 2018-02-04
2AI133CV99000-08380 | EOF:Rebar, Formwork & Install Embedments for Pedestal | [31 empty] | 2018-02-01 | 2018-02-01 | 2018-02-01 | 2018-02-01 | 2018-02-01 | 2018-02-01 | 2018-02-01 | 2018-02-01 | 2018-02-01 | 2018-02-01 | 2018-02-01 | 2018-02-01 | 2018-02-01 | 2018-02-01 | 2018-02-01
2AI133CV99000-08376 | EOF:Concrete Pouring - for Footing | [29 empty] | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26
2AI133CV99000-08375 | EOF:Rebar, Formwork for Footing | [29 empty] | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06
2AI133CV99000-08370 | EOF:Blinding/PCC for Fnd | [29 empty] | 2018-01-05 | 2018-01-05 | 2018-01-05 | 2018-01-05 | 2018-01-05 | 2018-01-05 | 2018-01-05 | 2018-01-05 | 2018-01-05 | 2018-01-05 | 2018-01-05 | 2018-01-05 | 2018-01-05 | 2018-01-05 | 2018-01-05 | 2018-01-05 | 2018-01-05
2AI133CV99000-08365 | EOF:Survey Marking, Excavation & Subgrade | [29 empty] | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03
2AI133CV99000-08360 | EOF:Backfilling & Compaction for Fnd | [33 empty] | 2018-03-24 | 2018-03-24 | 2018-03-24 | 2018-03-24 | 2018-03-24 | 2018-03-24 | 2018-03-24 | 2018-03-24 | 2018-03-24 | 2018-03-24 | 2018-03-24 | 2018-03-24 | 2018-03-24
2AI133CV99000-08355 | EOF:Concrete Potection for Fnd | [31 empty] | 2018-01-30 | 2018-01-30 | 2018-01-30 | 2018-01-30 | 2018-01-30 | 2018-01-30 | 2018-01-30 | 2018-01-30 | 2018-01-30 | 2018-01-30 | 2018-01-30 | 2018-01-30 | 2018-01-30 | 2018-01-30 | 2018-01-30
2AI133CV99000-08351 | EOF:Concrete Pouring - for Pedestal | [29 empty] | 2018-01-18 | 2018-01-18 | 2018-01-18 | 2018-01-18 | 2018-01-18 | 2018-01-18 | 2018-01-18 | 2018-01-18 | 2018-01-18 | 2018-01-18 | 2018-01-18 | 2018-01-18 | 2018-01-18 | 2018-01-18 | 2018-01-18 | 2018-01-18 | 2018-01-18
2AI133CV99000-08350 | EOF:Rebar, Formwork & Install Embedments for Pedestal | [29 empty] | 2018-01-18 | 2018-01-18 | 2018-01-18 | 2018-01-18 | 2018-01-18 | 2018-01-18 | 2018-01-18 | 2018-01-18 | 2018-01-18 | 2018-01-18 | 2018-01-18 | 2018-01-18 | 2018-01-18 | 2018-01-18 | 2018-01-18 | 2018-01-18 | 2018-01-18
2AI133CV99000-08346 | EOF:Concrete Pouring - for Footing | [29 empty] | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16
2AI133CV99000-08345 | EOF:Rebar, Formwork for Footing | [29 empty] | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16
2AI133CV99000-08340 | EOF:Blinding/PCC for Fnd | [25 empty] | 2017-08-29 | 2017-08-29 | 2017-08-29 | 2017-08-29 | 2017-08-29 | 2017-08-29 | 2017-08-29 | 2017-08-29 | 2017-08-29 | 2017-08-29 | 2017-08-29 | 2017-08-29 | 2017-08-29 | 2017-08-29 | 2017-08-29 | 2017-08-29 | 2017-08-29 | 2017-08-29 | 2017-08-29 | 2017-08-29 | 2017-08-29
2AI133CV99000-08335 | EOF:Survey Marking, Excavation & Subgrade | [25 empty] | 2017-08-27 | 2017-08-27 | 2017-08-27 | 2017-08-27 | 2017-08-27 | 2017-08-27 | 2017-08-27 | 2017-08-27 | 2017-08-27 | 2017-08-27 | 2017-08-27 | 2017-08-27 | 2017-08-27 | 2017-08-27 | 2017-08-27 | 2017-08-27 | 2017-08-27 | 2017-08-27 | 2017-08-27 | 2017-08-27 | 2017-08-27
2AI133CV99000-08036 | EOF:Backfilling & Compaction for Fnd | [29 empty] | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16
2AI133CV99000-08031 | EOF:Concrete Potection for Fnd | [29 empty] | 2018-01-04 | 2018-01-04 | 2018-01-04 | 2018-01-04 | 2018-01-04 | 2018-01-04 | 2018-01-04 | 2018-01-04 | 2018-01-04 | 2018-01-04 | 2018-01-04 | 2018-01-04 | 2018-01-04 | 2018-01-04 | 2018-01-04 | 2018-01-04 | 2018-01-04
2AI133CV99000-08026 | EOF:Concrete Pouring - for Pedestal | [29 empty] | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17
2AI133CV99000-08021 | EOF:Rebar, Formwork, Install Embedments for Pedestal | [27 empty] | 2017-10-25 | 2017-10-25 | 2017-10-25 | 2017-10-25 | 2017-10-25 | 2017-10-25 | 2017-10-25 | 2017-10-25 | 2017-10-25 | 2017-10-25 | 2017-10-25 | 2017-10-25 | 2017-10-25 | 2017-10-25 | 2017-10-25 | 2017-10-25 | 2017-10-25 | 2017-10-25 | 2017-10-25
2AI133CV99000-08016 | EOF:Concrete Pouring - for Footing | [25 empty] | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03
2AI133CV99000-08015 | EOF SS : Shelter Foundation for Transformers of 52-SUBST-303 - SUBSTATION - LMM | [25 empty] | 2017-08-31 | 2017-08-31 | 2017-08-31 | 2017-08-31 | 2017-08-31 | 2017-08-31 | 2017-08-31 | 2017-08-31 | 2017-08-31 | 2017-08-31 | 2017-08-31 | 2017-08-31 | 2017-08-31 | 2017-08-31 | 2017-08-31 | 2017-08-31 | 2017-08-31 | 2017-08-31 | 2017-08-31 | 2017-08-31 | 2017-08-31
2AI133CV99000-08011 | EOF:Rebar, Formwork for Footing | [23 empty] | 2017-07-27 | 2017-07-27 | 2017-07-27 | 2017-07-27 | 2017-07-27 | 2017-07-27 | 2017-07-27 | 2017-07-27 | 2017-07-27 | 2017-07-27 | 2017-07-27 | 2017-07-27 | 2017-07-27 | 2017-07-27 | 2017-07-27 | 2017-07-27 | 2017-07-27 | 2017-07-27 | 2017-07-27 | 2017-07-27 | 2017-07-27 | 2017-07-27 | 2017-07-27
2AI133CV99000-08010 | EOF SS : Shelter Foundation for Transformers of 50-SUBST-001 - SUBSTATION - COCC | [35 empty] | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04
2AI133CV99000-08006 | EOF:Blinding/PCC for Fnd | [23 empty] | 2017-07-22 | 2017-07-22 | 2017-07-22 | 2017-07-22 | 2017-07-22 | 2017-07-22 | 2017-07-22 | 2017-07-22 | 2017-07-22 | 2017-07-22 | 2017-07-22 | 2017-07-22 | 2017-07-22 | 2017-07-22 | 2017-07-22 | 2017-07-22 | 2017-07-22 | 2017-07-22 | 2017-07-22 | 2017-07-22 | 2017-07-22 | 2017-07-22 | 2017-07-22
2AI133CV99000-08005 | EOF SS : Shelter Foundation for Transformers of 52-SUBST-302 - SUBSTATION - STF | [33 empty] | 2018-03-24 | 2018-03-24 | 2018-03-24 | 2018-03-24 | 2018-03-24 | 2018-03-24 | 2018-03-24 | 2018-03-24 | 2018-03-24 | 2018-03-24 | 2018-03-24 | 2018-03-24 | 2018-03-24
2AI133CV99000-08001 | EOF:Survey Marking, Excavation & Subgrade | [23 empty] | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17
2AI133CV99000-08000 | EOF SS : Shelter Foundation for Transformers of 52-SUBST-301 - SUBSTATION - FMM | [29 empty] | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16
2AI133CV99000 | EOF SS : Shelter Foundation for Transformer, Capacitor | [35 empty] | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04
2AI133CV41300-08030 | Backfill / Compaction | [27 empty] | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08
2AI133CV41300-08025 | Concrete Protection | [25 empty] | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26
2AI133CV41300-08022 | Concrete Pouring - for Pedestal | [25 empty] | 2017-08-08 | 2017-08-08 | 2017-08-08 | 2017-08-08 | 2017-08-08 | 2017-08-08 | 2017-08-08 | 2017-08-08 | 2017-08-08 | 2017-08-08 | 2017-08-08 | 2017-08-08 | 2017-08-08 | 2017-08-08 | 2017-08-08 | 2017-08-08 | 2017-08-08 | 2017-08-08 | 2017-08-08 | 2017-08-08 | 2017-08-08
2AI133CV41300-08021 | Rebar, Formwork & Install Embedments - for Pedestal | [25 empty] | 2017-08-07 | 2017-08-07 | 2017-08-07 | 2017-08-07 | 2017-08-07 | 2017-08-07 | 2017-08-07 | 2017-08-07 | 2017-08-07 | 2017-08-07 | 2017-08-07 | 2017-08-07 | 2017-08-07 | 2017-08-07 | 2017-08-07 | 2017-08-07 | 2017-08-07 | 2017-08-07 | 2017-08-07 | 2017-08-07 | 2017-08-07
2AI133CV41300-08020 | Concrete Pouring - for Footing | [23 empty] | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10
2AI133CV41300-08015 | Rebar & Formwork - for Footing | [23 empty] | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10
2AI133CV41300-08010 | Blinding/PCC | [23 empty] | 2017-07-06 | 2017-07-06 | 2017-07-06 | 2017-07-06 | 2017-07-06 | 2017-07-06 | 2017-07-06 | 2017-07-06 | 2017-07-06 | 2017-07-06 | 2017-07-06 | 2017-07-06 | 2017-07-06 | 2017-07-06 | 2017-07-06 | 2017-07-06 | 2017-07-06 | 2017-07-06 | 2017-07-06 | 2017-07-06 | 2017-07-06 | 2017-07-06 | 2017-07-06
2AI133CV41300-08006 | Survey Marking, Excavation & Subgrade preparation | [23 empty] | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03
2AI133CV41300-08005 | EOF EG Building 52-R-303 : Diesel Day Tank Foundation | [27 empty] | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08
2AI133CV41300 | EOF EG Building 52-R-303 : Construct Diesel Day Tank Foundation | [27 empty] | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08
2AI133CV31300-08035 | Backfill / Compaction | [29 empty] | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22
2AI133CV31300-08030 | Concrete Protection | [29 empty] | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20
2AI133CV31300-08025 | Concrete Pouring | [27 empty] | 2017-10-30 | 2017-10-30 | 2017-10-30 | 2017-10-30 | 2017-10-30 | 2017-10-30 | 2017-10-30 | 2017-10-30 | 2017-10-30 | 2017-10-30 | 2017-10-30 | 2017-10-30 | 2017-10-30 | 2017-10-30 | 2017-10-30 | 2017-10-30 | 2017-10-30 | 2017-10-30 | 2017-10-30
2AI133CV31300-08020 | Rebar & Formwork | [27 empty] | 2017-10-28 | 2017-10-28 | 2017-10-28 | 2017-10-28 | 2017-10-28 | 2017-10-28 | 2017-10-28 | 2017-10-28 | 2017-10-28 | 2017-10-28 | 2017-10-28 | 2017-10-28 | 2017-10-28 | 2017-10-28 | 2017-10-28 | 2017-10-28 | 2017-10-28 | 2017-10-28 | 2017-10-28
2AI133CV31300-08015 | Blinding/PCC | [27 empty] | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22
2AI133CV31300-08006 | Survey Marking, Excavation & Subgrade preparation | [27 empty] | 2017-10-21 | 2017-10-21 | 2017-10-21 | 2017-10-21 | 2017-10-21 | 2017-10-21 | 2017-10-21 | 2017-10-21 | 2017-10-21 | 2017-10-21 | 2017-10-21 | 2017-10-21 | 2017-10-21 | 2017-10-21 | 2017-10-21 | 2017-10-21 | 2017-10-21 | 2017-10-21 | 2017-10-21
2AI133CV31300-08005 | EOF EG Building 52-R-302 : Diesel Day Tank Foundation | [29 empty] | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22
2AI133CV31300 | EOF EG Building 52-R-302 : Diesel Day Tank Foundation | [29 empty] | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22
2AI133CV21300-08055 | Backfill / Compaction | [21 empty] | 2017-04-05 | 2017-04-05 | 2017-04-05 | 2017-04-05 | 2017-04-05 | 2017-04-05 | 2017-04-05 | 2017-04-05 | 2017-04-05 | 2017-04-05 | 2017-04-05 | 2017-04-05 | 2017-04-05 | 2017-04-05 | 2017-04-05 | 2017-04-05 | 2017-04-05 | 2017-04-05 | 2017-04-05 | 2017-04-05 | 2017-04-05 | 2017-04-05 | 2017-04-05 | 2017-04-05 | 2017-04-05
2AI133CV21300-08045 | Concrete Protection | [21 empty] | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30
2AI133CV21300-08037 | Concrete Pouring - for Pedestal | [19 empty] | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08
2AI133CV21300-08036 | Rebar, Formwork & Install Embedments - for Pedestal | [19 empty] | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08
2AI133CV21300-08035 | Concrete Pouring - for Footing | [19 empty] | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08
2AI133CV21300-08025 | Rebar & Formwork - for Footing | [17 empty] | 2017-01-21 | 2017-01-21 | 2017-01-21 | 2017-01-21 | 2017-01-21 | 2017-01-21 | 2017-01-21 | 2017-01-21 | 2017-01-21 | 2017-01-21 | 2017-01-21 | 2017-01-21 | 2017-01-21 | 2017-01-21 | 2017-01-21 | 2017-01-21 | 2017-01-21 | 2017-01-21 | 2017-01-21 | 2017-01-21 | 2017-01-21 | 2017-01-21 | 2017-01-21 | 2017-01-21 | 2017-01-21 | 2017-01-21 | 2017-01-21 | 2017-01-21 | 2017-01-21
2AI133CV21300-08015 | Blinding/PCC | [17 empty] | 2017-01-18 | 2017-01-18 | 2017-01-18 | 2017-01-18 | 2017-01-18 | 2017-01-18 | 2017-01-18 | 2017-01-18 | 2017-01-18 | 2017-01-18 | 2017-01-18 | 2017-01-18 | 2017-01-18 | 2017-01-18 | 2017-01-18 | 2017-01-18 | 2017-01-18 | 2017-01-18 | 2017-01-18 | 2017-01-18 | 2017-01-18 | 2017-01-18 | 2017-01-18 | 2017-01-18 | 2017-01-18 | 2017-01-18 | 2017-01-18 | 2017-01-18 | 2017-01-18
2AI133CV21300-08006 | Survey Marking, Excavation & Subgrade preparation | [17 empty] | 2017-01-15 | 2017-01-15 | 2017-01-15 | 2017-01-15 | 2017-01-15 | 2017-01-15 | 2017-01-15 | 2017-01-15 | 2017-01-15 | 2017-01-15 | 2017-01-15 | 2017-01-15 | 2017-01-15 | 2017-01-15 | 2017-01-15 | 2017-01-15 | 2017-01-15 | 2017-01-15 | 2017-01-15 | 2017-01-15 | 2017-01-15 | 2017-01-15 | 2017-01-15 | 2017-01-15 | 2017-01-15 | 2017-01-15 | 2017-01-15 | 2017-01-15 | 2017-01-15
2AI133CV21300-08005 | EOF EG Building 52-R-301 : Diesel Day Tank Foundation | [21 empty] | 2017-04-05 | 2017-04-05 | 2017-04-05 | 2017-04-05 | 2017-04-05 | 2017-04-05 | 2017-04-05 | 2017-04-05 | 2017-04-05 | 2017-04-05 | 2017-04-05 | 2017-04-05 | 2017-04-05 | 2017-04-05 | 2017-04-05 | 2017-04-05 | 2017-04-05 | 2017-04-05 | 2017-04-05 | 2017-04-05 | 2017-04-05 | 2017-04-05 | 2017-04-05 | 2017-04-05 | 2017-04-05
2AI133CV21300 | EOF EG Building 52-R-301 : Construct Diesel Day Tank Foundation | [21 empty] | 2017-04-05 | 2017-04-05 | 2017-04-05 | 2017-04-05 | 2017-04-05 | 2017-04-05 | 2017-04-05 | 2017-04-05 | 2017-04-05 | 2017-04-05 | 2017-04-05 | 2017-04-05 | 2017-04-05 | 2017-04-05 | 2017-04-05 | 2017-04-05 | 2017-04-05 | 2017-04-05 | 2017-04-05 | 2017-04-05 | 2017-04-05 | 2017-04-05 | 2017-04-05 | 2017-04-05 | 2017-04-05
2AI133CV11300-08050 | Backfill / Compaction | [29 empty] | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26
2AI133CV11300-08040 | Concrete Protection | [29 empty] | 2018-01-23 | 2018-01-23 | 2018-01-23 | 2018-01-23 | 2018-01-23 | 2018-01-23 | 2018-01-23 | 2018-01-23 | 2018-01-23 | 2018-01-23 | 2018-01-23 | 2018-01-23 | 2018-01-23 | 2018-01-23 | 2018-01-23 | 2018-01-23 | 2018-01-23
2AI133CV11300-08032 | Concrete Pouring - for Pedestal | [29 empty] | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11
2AI133CV11300-08031 | Rebar, Formwork & Install Embedments - for Pedestal | [29 empty] | 2018-01-10 | 2018-01-10 | 2018-01-10 | 2018-01-10 | 2018-01-10 | 2018-01-10 | 2018-01-10 | 2018-01-10 | 2018-01-10 | 2018-01-10 | 2018-01-10 | 2018-01-10 | 2018-01-10 | 2018-01-10 | 2018-01-10 | 2018-01-10 | 2018-01-10
2AI133CV11300-08030 | Concrete Pouring - for Footing | [29 empty] | 2018-01-02 | 2018-01-02 | 2018-01-02 | 2018-01-02 | 2018-01-02 | 2018-01-02 | 2018-01-02 | 2018-01-02 | 2018-01-02 | 2018-01-02 | 2018-01-02 | 2018-01-02 | 2018-01-02 | 2018-01-02 | 2018-01-02 | 2018-01-02 | 2018-01-02
2AI133CV11300-08020 | Rebar & Formwork - for Footing | [29 empty] | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01
2AI133CV11300-08010 | Blinding/PCC | [29 empty] | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23
2AI133CV11300-08006 | Survey Marking, Excavation & Subgrade preparation | [29 empty] | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23
2AI133CV11300-08005 | EOF EG Building 50-R-002 : Diesel Day Tank Foundation | [29 empty] | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26
2AI133CV11300 | EOF EG Building 50-R-002 : Diesel Day Tank Foundation | [29 empty] | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26
2AI133CV07500-08035 | EOF SS 52-SUBST-303 : Construction of Pit | [23 empty] | 2017-06-22 | 2017-06-22 | 2017-06-22 | 2017-06-22 | 2017-06-22 | 2017-06-22 | 2017-06-22 | 2017-06-22 | 2017-06-22 | 2017-06-22 | 2017-06-22 | 2017-06-22 | 2017-06-22 | 2017-06-22 | 2017-06-22 | 2017-06-22 | 2017-06-22 | 2017-06-22 | 2017-06-22 | 2017-06-22 | 2017-06-22 | 2017-06-22 | 2017-06-22
2AI133CV07500-08030 | EOF SS 52-SUBST-303 : Backfill / Compaction | [25 empty] | 2017-08-28 | 2017-08-28 | 2017-08-28 | 2017-08-28 | 2017-08-28 | 2017-08-28 | 2017-08-28 | 2017-08-28 | 2017-08-28 | 2017-08-28 | 2017-08-28 | 2017-08-28 | 2017-08-28 | 2017-08-28 | 2017-08-28 | 2017-08-28 | 2017-08-28 | 2017-08-28 | 2017-08-28 | 2017-08-28 | 2017-08-28
2AI133CV07500-08025 | EOF SS 52-SUBST-303 : Concrete Protection | [23 empty] | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17
2AI133CV07500-08020 | EOF SS 52-SUBST-303 : Concrete Pouring | [23 empty] | 2017-06-22 | 2017-06-22 | 2017-06-22 | 2017-06-22 | 2017-06-22 | 2017-06-22 | 2017-06-22 | 2017-06-22 | 2017-06-22 | 2017-06-22 | 2017-06-22 | 2017-06-22 | 2017-06-22 | 2017-06-22 | 2017-06-22 | 2017-06-22 | 2017-06-22 | 2017-06-22 | 2017-06-22 | 2017-06-22 | 2017-06-22 | 2017-06-22 | 2017-06-22
2AI133CV07500-08015 | EOF SS 52-SUBST-303 : Rebar & Formwork | [23 empty] | 2017-06-22 | 2017-06-22 | 2017-06-22 | 2017-06-22 | 2017-06-22 | 2017-06-22 | 2017-06-22 | 2017-06-22 | 2017-06-22 | 2017-06-22 | 2017-06-22 | 2017-06-22 | 2017-06-22 | 2017-06-22 | 2017-06-22 | 2017-06-22 | 2017-06-22 | 2017-06-22 | 2017-06-22 | 2017-06-22 | 2017-06-22 | 2017-06-22 | 2017-06-22
2AI133CV07500-08010 | EOF SS 52-SUBST-303 : Blinding/PCC | [23 empty] | 2017-06-08 | 2017-06-08 | 2017-06-08 | 2017-06-08 | 2017-06-08 | 2017-06-08 | 2017-06-08 | 2017-06-08 | 2017-06-08 | 2017-06-08 | 2017-06-08 | 2017-06-08 | 2017-06-08 | 2017-06-08 | 2017-06-08 | 2017-06-08 | 2017-06-08 | 2017-06-08 | 2017-06-08 | 2017-06-08 | 2017-06-08 | 2017-06-08 | 2017-06-08
2AI133CV07500-08005 | EOF SS 52-SUBST-303 : Survey Marking, Excavation & Subgrade preparation | [23 empty] | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07
2AI133CV07500-08000 | EOF SS 52-SUBST-303 : Foundation works for Transformer & Pit | [25 empty] | 2017-08-28 | 2017-08-28 | 2017-08-28 | 2017-08-28 | 2017-08-28 | 2017-08-28 | 2017-08-28 | 2017-08-28 | 2017-08-28 | 2017-08-28 | 2017-08-28 | 2017-08-28 | 2017-08-28 | 2017-08-28 | 2017-08-28 | 2017-08-28 | 2017-08-28 | 2017-08-28 | 2017-08-28 | 2017-08-28 | 2017-08-28
2AI133CV07500 | EOF SS 52-SUBST-303 : Construct Foundation (Transformer) & Pit | [25 empty] | 2017-08-28 | 2017-08-28 | 2017-08-28 | 2017-08-28 | 2017-08-28 | 2017-08-28 | 2017-08-28 | 2017-08-28 | 2017-08-28 | 2017-08-28 | 2017-08-28 | 2017-08-28 | 2017-08-28 | 2017-08-28 | 2017-08-28 | 2017-08-28 | 2017-08-28 | 2017-08-28 | 2017-08-28 | 2017-08-28 | 2017-08-28
2AI133CV05500-08070 | EOF SS 52-SUBST-302 :Construction of Pit | [27 empty] | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2017-11-24
2AI133CV05500-08060 | EOF SS 52-SUBST-302 :Backfill / Compaction | [29 empty] | 2018-01-24 | 2018-01-24 | 2018-01-24 | 2018-01-24 | 2018-01-24 | 2018-01-24 | 2018-01-24 | 2018-01-24 | 2018-01-24 | 2018-01-24 | 2018-01-24 | 2018-01-24 | 2018-01-24 | 2018-01-24 | 2018-01-24 | 2018-01-24 | 2018-01-24
2AI133CV05500-08050 | EOF SS 52-SUBST-302 :Concrete Protection | [29 empty] | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21
2AI133CV05500-08040 | EOF SS 52-SUBST-302 :Concrete Pouring | [27 empty] | 2017-10-23 | 2017-10-23 | 2017-10-23 | 2017-10-23 | 2017-10-23 | 2017-10-23 | 2017-10-23 | 2017-10-23 | 2017-10-23 | 2017-10-23 | 2017-10-23 | 2017-10-23 | 2017-10-23 | 2017-10-23 | 2017-10-23 | 2017-10-23 | 2017-10-23 | 2017-10-23 | 2017-10-23
2AI133CV05500-08030 | EOF SS 52-SUBST-302 : Rebar & Formwork | [27 empty] | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22
2AI133CV05500-08020 | EOF SS 52-SUBST-302 : Blinding/PCC | [25 empty] | 2017-08-29 | 2017-08-29 | 2017-08-29 | 2017-08-29 | 2017-08-29 | 2017-08-29 | 2017-08-29 | 2017-08-29 | 2017-08-29 | 2017-08-29 | 2017-08-29 | 2017-08-29 | 2017-08-29 | 2017-08-29 | 2017-08-29 | 2017-08-29 | 2017-08-29 | 2017-08-29 | 2017-08-29 | 2017-08-29 | 2017-08-29
2AI133CV05500-08010 | EOF SS 52-SUBST-302 : Survey Marking, Excavation & Subgrade preparation | [25 empty] | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26
2AI133CV05500-08000 | EOF SS 52-SUBST-302 : Foundation works for Transformer & Pit | [29 empty] | 2018-01-24 | 2018-01-24 | 2018-01-24 | 2018-01-24 | 2018-01-24 | 2018-01-24 | 2018-01-24 | 2018-01-24 | 2018-01-24 | 2018-01-24 | 2018-01-24 | 2018-01-24 | 2018-01-24 | 2018-01-24 | 2018-01-24 | 2018-01-24 | 2018-01-24
2AI133CV05500 | EOF SS 52-SUBST-302 : Construct Foundation (Transformer) & Pit | [29 empty] | 2018-01-24 | 2018-01-24 | 2018-01-24 | 2018-01-24 | 2018-01-24 | 2018-01-24 | 2018-01-24 | 2018-01-24 | 2018-01-24 | 2018-01-24 | 2018-01-24 | 2018-01-24 | 2018-01-24 | 2018-01-24 | 2018-01-24 | 2018-01-24 | 2018-01-24
2AI133CV03500-08040 | EOF SS 52-SUBST-301 : Construction of Pit | [29 empty] | 2018-01-17 | 2018-01-17 | 2018-01-17 | 2018-01-17 | 2018-01-17 | 2018-01-17 | 2018-01-17 | 2018-01-17 | 2018-01-17 | 2018-01-17 | 2018-01-17 | 2018-01-17 | 2018-01-17 | 2018-01-17 | 2018-01-17 | 2018-01-17 | 2018-01-17
2AI133CV03500-08030 | EOF SS 52-SUBST-301 : Backfill / Compaction | [29 empty] | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22
2AI133CV03500-08025 | EOF SS 52-SUBST-301 : Concrete Protection | [29 empty] | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21
2AI133CV03500-08020 | EOF SS 52-SUBST-301 : Concrete Pouring | [25 empty] | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03
2AI133CV03500-08015 | EOF SS 52-SUBST-301 : Rebar & Formwork | [23 empty] | 2017-07-27 | 2017-07-27 | 2017-07-27 | 2017-07-27 | 2017-07-27 | 2017-07-27 | 2017-07-27 | 2017-07-27 | 2017-07-27 | 2017-07-27 | 2017-07-27 | 2017-07-27 | 2017-07-27 | 2017-07-27 | 2017-07-27 | 2017-07-27 | 2017-07-27 | 2017-07-27 | 2017-07-27 | 2017-07-27 | 2017-07-27 | 2017-07-27 | 2017-07-27
2AI133CV03500-08010 | EOF SS 52-SUBST-301 : Blinding/PCC | [23 empty] | 2017-07-22 | 2017-07-22 | 2017-07-22 | 2017-07-22 | 2017-07-22 | 2017-07-22 | 2017-07-22 | 2017-07-22 | 2017-07-22 | 2017-07-22 | 2017-07-22 | 2017-07-22 | 2017-07-22 | 2017-07-22 | 2017-07-22 | 2017-07-22 | 2017-07-22 | 2017-07-22 | 2017-07-22 | 2017-07-22 | 2017-07-22 | 2017-07-22 | 2017-07-22
2AI133CV03500-08005 | EOF SS 52-SUBST-301 : Survey Marking, Excavation & Subgrade preparation | [23 empty] | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14
2AI133CV03500-08000 | EOF SS 52-SUBST-301 : Foundation works for Transformer & Pit | [29 empty] | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22
2AI133CV03500 | EOF SS 52-SUBST-301 : Construct Foundation (Transformer) & Pit | [29 empty] | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22
2AI133CV01500-08035 | EOF SS 50-SUBST-001 : Construction of Pit | [29 empty] | 2018-01-24 | 2018-01-24 | 2018-01-24 | 2018-01-24 | 2018-01-24 | 2018-01-24 | 2018-01-24 | 2018-01-24 | 2018-01-24 | 2018-01-24 | 2018-01-24 | 2018-01-24 | 2018-01-24 | 2018-01-24 | 2018-01-24 | 2018-01-24 | 2018-01-24
2AI133CV01500-08030 | EOF SS 50-SUBST-001 : Backfill / Compaction | [29 empty] | 2018-01-25 | 2018-01-25 | 2018-01-25 | 2018-01-25 | 2018-01-25 | 2018-01-25 | 2018-01-25 | 2018-01-25 | 2018-01-25 | 2018-01-25 | 2018-01-25 | 2018-01-25 | 2018-01-25 | 2018-01-25 | 2018-01-25 | 2018-01-25 | 2018-01-25
2AI133CV01500-08025 | EOF SS 50-SUBST-001 : Concrete Protection | [31 empty] | 2018-03-12 | 2018-03-12 | 2018-03-12 | 2018-03-12 | 2018-03-12 | 2018-03-12 | 2018-03-12 | 2018-03-12 | 2018-03-12 | 2018-03-12 | 2018-03-12 | 2018-03-12 | 2018-03-12 | 2018-03-12 | 2018-03-12
2AI133CV01500-08020 | EOF SS 50-SUBST-001 : Concrete Pouring | [29 empty] | 2017-12-30 | 2017-12-30 | 2017-12-30 | 2017-12-30 | 2017-12-30 | 2017-12-30 | 2017-12-30 | 2017-12-30 | 2017-12-30 | 2017-12-30 | 2017-12-30 | 2017-12-30 | 2017-12-30 | 2017-12-30 | 2017-12-30 | 2017-12-30 | 2017-12-30
2AI133CV01500-08015 | EOF SS 50-SUBST-001 : Rebar & Formwork | [29 empty] | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06
2AI133CV01500-08010 | EOF SS 50-SUBST-001 : Blinding/PCC | [29 empty] | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17
2AI133CV01500-08005 | EOF SS 50-SUBST-001 : Survey Marking, Excavation & Subgrade preparation | [29 empty] | 2017-12-15 | 2017-12-15 | 2017-12-15 | 2017-12-15 | 2017-12-15 | 2017-12-15 | 2017-12-15 | 2017-12-15 | 2017-12-15 | 2017-12-15 | 2017-12-15 | 2017-12-15 | 2017-12-15 | 2017-12-15 | 2017-12-15 | 2017-12-15 | 2017-12-15
2AI133CV01500-08000 | EOF SS 50-SUBST-001 : Foundation works for Transformer & Pit | [31 empty] | 2018-03-12 | 2018-03-12 | 2018-03-12 | 2018-03-12 | 2018-03-12 | 2018-03-12 | 2018-03-12 | 2018-03-12 | 2018-03-12 | 2018-03-12 | 2018-03-12 | 2018-03-12 | 2018-03-12 | 2018-03-12 | 2018-03-12
2AI133CV01500 | EOF SS 50-SUBST-001 : Construct Foundation (Transformer) & Pit | [31 empty] | 2018-03-12 | 2018-03-12 | 2018-03-12 | 2018-03-12 | 2018-03-12 | 2018-03-12 | 2018-03-12 | 2018-03-12 | 2018-03-12 | 2018-03-12 | 2018-03-12 | 2018-03-12 | 2018-03-12 | 2018-03-12 | 2018-03-12
2AI104PI20100-08005 | EOF:Piping Tie-Ins works Oily Water line | [31 empty] | 2018-03-12: 2019-02-04; 2018-03-12: 2019-02-04; 2018-03-12: 2019-02-04
2AI104PI20100-08000 | EOF:Piping Tie-Ins works Fire Water line | [31 empty] | 2018-03-12: 2019-01-24; 2018-03-12: 2019-01-24; 2018-03-12: 2019-01-24; 2018-03-12: 2019-01-24; 2018-03-12: 2019-01-24
2AI104PI20100 | EOF: Piping Tie-Ins works (Fire Water line & Oily Water line) | [31 empty] | 2018-03-12: 2019-02-04; 2018-03-12: 2019-02-04; 2018-03-12: 2019-02-04
2AI104EL20100-08100 | EOF: Issue AFC Drawings MG-1 SUBSTATION TIE-INS | [23 empty] | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07
2AI104EL20100-08000 | EOF : Tie-Ins works associated with 11KV Power Cable from MG-1 Substation to 52-SUBST-301 | [23 empty] | 2017-06-07: 2018-11-25; 2017-06-07: 2018-11-25; 2017-06-07: 2018-11-25; 2017-06-07: 2018-11-25; 2017-06-07: 2018-11-25
2AI104EL20100 | EOF: E,I&T Tie-Ins works associated with 52-SUBST-301& MG-1 Substation and Other EIT Tie-in scope in EOF Area | [23 empty] | 2017-06-07: 2018-11-25; 2017-06-07: 2018-11-25; 2017-06-07: 2018-11-25; 2017-06-07: 2018-11-25; 2017-06-07: 2018-11-25
2AI103MS20000-08030 | EOF:QC checks & clearance for Equipment | [21 empty] | 2017-05-10 | 2017-05-10 | 2017-05-10 | 2017-05-10 | 2017-05-10 | 2017-05-10 | 2017-05-10 | 2017-05-10 | 2017-05-10 | 2017-05-10 | 2017-05-10 | 2017-05-10 | 2017-05-10 | 2017-05-10 | 2017-05-10 | 2017-05-10 | 2017-05-10 | 2017-05-10 | 2017-05-10 | 2017-05-10 | 2017-05-10 | 2017-05-10 | 2017-05-10 | 2017-05-10 | 2017-05-10
2AI103MS20000-08025 | EOF:Install internals of Equipment | [21 empty] | 2017-05-10: 2018-11-07; 2017-05-10: 2018-11-07; 2017-05-10: 2018-11-07; 2017-05-10: 2018-11-07; 2017-05-10: 2018-11-07; 2017-05-10: 2018-11-07; 2017-05-10: 2018-11-07
2AI103MS20000-08020 | EOF:Install Platforms & ladders of Equipment | [35 empty] | 2018-06-20 | 2018-06-20 | 2018-06-20 | 2018-06-20 | 2018-06-20 | 2018-06-20 | 2018-06-20 | 2018-06-20 | 2018-06-20 | 2018-06-20 | 2018-06-20
2AI103MS20000-08015 | EOF:Final Allignment & Grouting of Equipment | [21 empty] | 2017-05-03 | 2017-05-03 | 2017-05-03 | 2017-05-03 | 2017-05-03 | 2017-05-03 | 2017-05-03 | 2017-05-03 | 2017-05-03 | 2017-05-03 | 2017-05-03 | 2017-05-03 | 2017-05-03 | 2017-05-03 | 2017-05-03 | 2017-05-03 | 2017-05-03 | 2017-05-03 | 2017-05-03 | 2017-05-03 | 2017-05-03 | 2017-05-03 | 2017-05-03 | 2017-05-03 | 2017-05-03
2AI103MS20000-08010 | EOF:Preliminary Allignment & Grouting of Equipment | [21 empty] | 2017-04-26 | 2017-04-26 | 2017-04-26 | 2017-04-26 | 2017-04-26 | 2017-04-26 | 2017-04-26 | 2017-04-26 | 2017-04-26 | 2017-04-26 | 2017-04-26 | 2017-04-26 | 2017-04-26 | 2017-04-26 | 2017-04-26 | 2017-04-26 | 2017-04-26 | 2017-04-26 | 2017-04-26 | 2017-04-26 | 2017-04-26 | 2017-04-26 | 2017-04-26 | 2017-04-26 | 2017-04-26
2AI103MS20000-08005 | EOF:Installation of 621-V-301 Oily Water Collection Vessel | [21 empty] | 2017-04-26 | 2017-04-26 | 2017-04-26 | 2017-04-26 | 2017-04-26 | 2017-04-26 | 2017-04-26 | 2017-04-26 | 2017-04-26 | 2017-04-26 | 2017-04-26 | 2017-04-26 | 2017-04-26 | 2017-04-26 | 2017-04-26 | 2017-04-26 | 2017-04-26 | 2017-04-26 | 2017-04-26 | 2017-04-26 | 2017-04-26 | 2017-04-26 | 2017-04-26 | 2017-04-26 | 2017-04-26
2AI103MS20000-08001 | EOF:Foundation checks/Preparation for Equipment | [19 empty] | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08
2AI103MS20000-08000 | EOF: Oily Water Transfer Vessel 621-V-301Erection | [19 empty] | 2017-02-08: 2018-11-07; 2017-02-08: 2018-11-07; 2017-02-08: 2018-11-07; 2017-02-08: 2018-11-07; 2017-02-08: 2018-11-07; 2017-02-08: 2018-11-07; 2017-02-08: 2018-11-07
2AI103MS20000 | EOF: Other Equipments (H2S Scrubber, PIG Receiver, Vessel etc) | [19 empty] | 2017-02-08: 2018-11-07; 2017-02-08: 2018-11-07; 2017-02-08: 2018-11-07; 2017-02-08: 2018-11-07; 2017-02-08: 2018-11-07; 2017-02-08: 2018-11-07; 2017-02-08: 2018-11-07
2AI103MS19900-08065 | EOF:QC checks & clearance for Equipment | [19 empty] | 2017-02-08: 2019-04-13
2AI103MS19900-08060 | EOF:Install internals of Equipment | [19 empty] | 2017-02-08: 2019-04-12
2AI103MS19900-08055 | EOF:Final Allignment & Grouting of Equipment | [19 empty] | 2017-02-08: 2019-04-11
2AI103MS19900-08050 | EOF:Preliminary Allignment & Grouting of Equipment | [19 empty] | 2017-02-08: 2018-11-12; 2017-02-08: 2018-11-12; 2017-02-08: 2018-11-12; 2017-02-08: 2018-11-12; 2017-02-08: 2018-11-12; 2017-02-08: 2018-11-12; 2017-02-08: 2018-11-12
2AI103MS19900-08045 | EOF:Installation of Diesel Fuel Tank 621-D307 C/D | [19 empty] | 2017-02-08: 2018-11-04; 2017-02-08: 2018-11-04; 2017-02-08: 2018-11-04; 2017-02-08: 2018-11-04; 2017-02-08: 2018-11-04; 2017-02-08: 2018-11-04; 2017-02-08: 2018-11-04
2AI103MS19900-08040 | EOF:Installation of Structural Support, Platforms & ladders of Equipment | [19 empty] | 2017-02-08: 2018-11-04; 2017-02-08: 2018-11-04; 2017-02-08: 2018-11-04; 2017-02-08: 2018-11-04; 2017-02-08: 2018-11-04; 2017-02-08: 2018-11-04; 2017-02-08: 2018-11-04
2AI103MS19900-08035 | EOF:Foundation checks/Preparation for Equipment | [19 empty] | 2017-02-08: 2018-11-04; 2017-02-08: 2018-11-04; 2017-02-08: 2018-11-04; 2017-02-08: 2018-11-04; 2017-02-08: 2018-11-04; 2017-02-08: 2018-11-04; 2017-02-08: 2018-11-04
2AI103MS19900-08030 | EOF:QC checks & clearance for Equipment | [19 empty] | 2017-02-08: 2019-04-13
2AI103MS19900-08025 | EOF:Install internals of Equipment | [19 empty] | 2017-02-08: 2019-04-12
2AI103MS19900-08020 | EOF:Final Allignment & Grouting of Equipment | [19 empty] | 2017-02-08: 2019-04-11
2AI103MS19900-08015 | EOF:Preliminary Allignment & Grouting of Equipment | [19 empty] | 2017-02-08: 2018-12-01; 2017-02-08: 2018-12-01; 2017-02-08: 2018-12-01; 2017-02-08: 2018-12-01; 2017-02-08: 2018-12-01
2AI103MS19900-08010 | EOF:Installation of Diesel Fuel Tank 621-D307 A/B | [19 empty] | 2017-02-08: 2018-10-30; 2017-02-08: 2018-10-30; 2017-02-08: 2018-10-30; 2017-02-08: 2018-10-30; 2017-02-08: 2018-10-30; 2017-02-08: 2018-10-30; 2017-02-08: 2018-10-30
2AI103MS19900-08006 | EOF:Installation of Structural Support, Platforms & ladders of Equipment | [19 empty] | 2017-02-08: 2018-10-30; 2017-02-08: 2018-10-30; 2017-02-08: 2018-10-30; 2017-02-08: 2018-10-30; 2017-02-08: 2018-10-30; 2017-02-08: 2018-10-30; 2017-02-08: 2018-10-30
2AI103MS19900-08005 | EOF: Erection of Diesel Fuel Tank (52-D-307 C/D) | [19 empty] | 2017-02-08: 2019-04-13
2AI103MS19900-08001 | EOF:Foundation checks/Preparation for Equipment | [19 empty] | 2017-02-08: 2018-10-30; 2017-02-08: 2018-10-30; 2017-02-08: 2018-10-30; 2017-02-08: 2018-10-30; 2017-02-08: 2018-10-30; 2017-02-08: 2018-10-30; 2017-02-08: 2018-10-30
2AI103MS19900-08000 | EOF: Erection of Diesel Fuel Tank (52-D-307 A/B) | [19 empty] | 2017-02-08: 2019-04-13
2AI103MS19900 | EOF: Tank Erection | [19 empty] | 2017-02-08: 2019-04-13
2AI103MR19300-08045 | EOF:QC checks & clearance for Equipment | [19 empty] | 2017-02-08: 2018-11-07; 2017-02-08: 2018-11-07; 2017-02-08: 2018-11-07; 2017-02-08: 2018-11-07; 2017-02-08: 2018-11-07; 2017-02-08: 2018-11-07; 2017-02-08: 2018-11-07
2AI103MR19300-08040 | EOF:Final Allignment & Grouting of Equipment | [37 empty] | 2018-08-28 | 2018-08-28 | 2018-08-28 | 2018-08-28 | 2018-08-28 | 2018-08-28 | 2018-08-28 | 2018-08-28 | 2018-08-28
2AI103MR19300-08035 | EOF:Preliminary Allignment & Grouting of Equipment | [33 empty] | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18
2AI103MR19300-08030 | EOF:Installation of Foam System Package (52-Z-301 A/B) Erection | [33 empty] | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08
2AI103MR19300-08025 | EOF:Foundation checks/Preparation for Equipment | [33 empty] | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04
2AI103MR19300-08020 | EOF:QC checks & clearance for Equipment | [33 empty] | 2018-04-04: 2018-11-07; 2018-04-04: 2018-11-07; 2018-04-04: 2018-11-07; 2018-04-04: 2018-11-07; 2018-04-04: 2018-11-07; 2018-04-04: 2018-11-07; 2018-04-04: 2018-11-07
2AI103MR19300-08015 | EOF:Final Allignment & Grouting of Equipment | [37 empty] | 2018-08-07 | 2018-08-07 | 2018-08-07 | 2018-08-07 | 2018-08-07 | 2018-08-07 | 2018-08-07 | 2018-08-07 | 2018-08-07
2AI103MR19300-08010 | EOF:Preliminary Allignment & Grouting of Equipment | [33 empty] | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18
2AI103MR19300-08006 | EOF:Installation of Foam System Package (52-Z-301 A/B) Erection | [33 empty] | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08
2AI103MR19300-08005 | EOF: Foam System Package (52-Z-301 B) Erection | [33 empty] | 2018-04-08: 2018-11-07; 2018-04-08: 2018-11-07; 2018-04-08: 2018-11-07; 2018-04-08: 2018-11-07; 2018-04-08: 2018-11-07; 2018-04-08: 2018-11-07; 2018-04-08: 2018-11-07
2AI103MR19300-08001 | EOF:Foundation checks/Preparation for Equipment | [33 empty] | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04
2AI103MR19300-08000 | EOF: Foam System Package (52-Z-301 A) Erection | [33 empty] | 2018-04-04: 2018-11-07; 2018-04-04: 2018-11-07; 2018-04-04: 2018-11-07; 2018-04-04: 2018-11-07; 2018-04-04: 2018-11-07; 2018-04-04: 2018-11-07; 2018-04-04: 2018-11-07
2AI103MR19300 | EOF: Foam System Package (52-Z-301 A/B) Erection | [33 empty] | 2018-04-04: 2018-11-07; 2018-04-04: 2018-11-07; 2018-04-04: 2018-11-07; 2018-04-04: 2018-11-07; 2018-04-04: 2018-11-07; 2018-04-04: 2018-11-07; 2018-04-04: 2018-11-07
2AI103MR18900-08095 | EOF:QC checks & clearance for Equipment 621-G-302 D Foam Pump Erection | [37 empty] | 2018-09-05 | 2018-09-05 | 2018-09-05 | 2018-09-05 | 2018-09-05 | 2018-09-05 | 2018-09-05 | 2018-09-05 | 2018-09-05
2AI103MR18900-08090 | EOF:Final Allignment & Grouting of Equipment 621-G-302 D Foam Pump Erection | [33 empty] | 2018-04-11 | 2018-04-11 | 2018-04-11 | 2018-04-11 | 2018-04-11 | 2018-04-11 | 2018-04-11 | 2018-04-11 | 2018-04-11 | 2018-04-11 | 2018-04-11 | 2018-04-11 | 2018-04-11
2AI103MR18900-08085 | EOF:Preliminary Allignment & Grouting of Equipment 621-G-302 D Foam Pump Erection | [33 empty] | 2018-04-09 | 2018-04-09 | 2018-04-09 | 2018-04-09 | 2018-04-09 | 2018-04-09 | 2018-04-09 | 2018-04-09 | 2018-04-09 | 2018-04-09 | 2018-04-09 | 2018-04-09 | 2018-04-09
2AI103MR18900-08080 | EOF:Installation of Equipment 621-G-302 D Foam Pump Erection | [33 empty] | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08
2AI103MR18900-08075 | EOF:Foundation checks/Preparation for Equipment 621-G-302 D Foam Pump Erection | [33 empty] | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05
2AI103MR18900-08070 | EOF:QC checks & clearance for Equipment 621-G-302 C Foam Pump Erection | [37 empty] | 2018-09-16 | 2018-09-16 | 2018-09-16 | 2018-09-16 | 2018-09-16 | 2018-09-16 | 2018-09-16 | 2018-09-16 | 2018-09-16
2AI103MR18900-08065 | EOF:Final Allignment & Grouting of Equipment 621-G-302 C Foam Pump Erection | [33 empty] | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04
2AI103MR18900-08060 | EOF:Preliminary Allignment & Grouting of Equipment 621-G-302 C Foam Pump Erection | [33 empty] | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04
2AI103MR18900-08055 | EOF:Installation of Equipment 621-G-302 C Foam Pump Erection | [33 empty] | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08
2AI103MR18900-08050 | EOF:Foundation checks/Preparation for Equipment 621-G-302 C Foam Pump Erection | [33 empty] | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05
2AI103MR18900-08045 | EOF:QC checks & clearance for Equipment 621-G-302 B Foam Pump Erection | [33 empty] | 2018-04-05: 2018-11-07; 2018-04-05: 2018-11-07; 2018-04-05: 2018-11-07; 2018-04-05: 2018-11-07; 2018-04-05: 2018-11-07; 2018-04-05: 2018-11-07; 2018-04-05: 2018-11-07
2AI103MR18900-08040 | EOF:Final Allignment & Grouting of Equipment 621-G-302 B Foam Pump Erection | [33 empty] | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04
2AI103MR18900-08035 | EOF:Preliminary Allignment & Grouting of Equipment 621-G-302 B Foam Pump Erection | [33 empty] | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04
2AI103MR18900-08030 | EOF:Installation of Equipment 621-G-302 B Foam Pump Erection | [33 empty] | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08
2AI103MR18900-08025 | EOF:Foundation checks/Preparation for Equipment 621-G-302 B Foam Pump Erection | [33 empty] | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05
2AI103MR18900-08016 | EOF:QC checks & clearance for Equipment 621-G-302 A Foam Pump Erection | [33 empty] | 2018-04-05: 2018-11-07; 2018-04-05: 2018-11-07; 2018-04-05: 2018-11-07; 2018-04-05: 2018-11-07; 2018-04-05: 2018-11-07; 2018-04-05: 2018-11-07; 2018-04-05: 2018-11-07
2AI103MR18900-08015 | EOF: 621-G-302 D Foam Pump Erection | [37 empty] | 2018-09-05 | 2018-09-05 | 2018-09-05 | 2018-09-05 | 2018-09-05 | 2018-09-05 | 2018-09-05 | 2018-09-05 | 2018-09-05
2AI103MR18900-08011 | EOF:Final Allignment & Grouting of Equipment 621-G-302 A Foam Pump Erection | [33 empty] | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04
2AI103MR18900-08010 | EOF: 621-G-302 C Foam Pump Erection | [37 empty] | 2018-09-16 | 2018-09-16 | 2018-09-16 | 2018-09-16 | 2018-09-16 | 2018-09-16 | 2018-09-16 | 2018-09-16 | 2018-09-16
2AI103MR18900-08006 | EOF:Preliminary Allignment & Grouting of Equipment 621-G-302 A Foam Pump Erection | [33 empty] | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04
2AI103MR18900-08005 | EOF: 621-G-302 B Foam Pump Erection | [33 empty] | 2018-04-04: 2018-11-07; 2018-04-04: 2018-11-07; 2018-04-04: 2018-11-07; 2018-04-04: 2018-11-07; 2018-04-04: 2018-11-07; 2018-04-04: 2018-11-07; 2018-04-04: 2018-11-07
2AI103MR18900-08002 | EOF:Installation of Equipment 621-G-302 A Foam Pump Erection | [33 empty] | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08
2AI103MR18900-08001 | EOF:Foundation checks/Preparation for Equipment 621-G-302 A Foam Pump Erection | [33 empty] | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05
2AI103MR18900-08000 | EOF: 621-G-302 A Foam Pump Erection | [33 empty] | 2018-04-05: 2018-11-07; 2018-04-05: 2018-11-07; 2018-04-05: 2018-11-07; 2018-04-05: 2018-11-07; 2018-04-05: 2018-11-07; 2018-04-05: 2018-11-07; 2018-04-05: 2018-11-07
2AI103MR18900 | EOF: Pump Erection | [33 empty] | 2018-04-05: 2018-11-07; 2018-04-05: 2018-11-07; 2018-04-05: 2018-11-07; 2018-04-05: 2018-11-07; 2018-04-05: 2018-11-07; 2018-04-05: 2018-11-07; 2018-04-05: 2018-11-07
2AI103HS01120-08005 | EOF:Installation - Outdoor Safety Signs
2AI103HS01120-08001 | EOF:Installation - Indoor Safety Signs
2AI103HS01120-08000 | EOF: Installation of Safety Sign Boards
2AI103HS01120 | EOF: Installation of Safety Sign Boards
2AI103HS01110-08001 | EOF: Installation of Fire fighting & Safety Equipments
2AI103HS01110-08000 | EOF: Installation of Fire fighting & Safety Equipments
2AI103HS01110 | EOF: Installation of Fire fighting & Safety Equipments
2AI103CV28220-08026 | EOF:Gate Installation & Speed bumbs
2AI103CV28220-08025 | EOF:Fence Mesh Installation
2AI103CV28220-08020 | EOF:Fence Post installation
2AI103CV28220-08017 | EOF:Install/Cast insitu fencing fnds
2AI103CV28220-08016 | EOF:Sub grade & Blinding
2AI103CV28220-08015 | EOF:Survey marking & Excavation for Fence Post
2AI103CV28220-08006 | EOF:Demolition Works - Existing Fence
2AI103CV28220-08005 | EOF:New Fencing Work - New Tank Area - 621
2AI103CV28220-08001 | EOF:Demolition Works - Existing Road | [13 empty] | 2016-09-14 | 2016-09-14 | 2016-09-14 | 2016-09-14 | 2016-09-14 | 2016-09-14 | 2016-09-14 | 2016-09-14 | 2016-09-14 | 2016-09-14 | 2016-09-14 | 2016-09-14 | 2016-09-14 | 2016-09-14 | 2016-09-14 | 2016-09-14 | 2016-09-14 | 2016-09-14 | 2016-09-14 | 2016-09-14 | 2016-09-14 | 2016-09-14 | 2016-09-14 | 2016-09-14 | 2016-09-14 | 2016-09-14 | 2016-09-14 | 2016-09-14 | 2016-09-14 | 2016-09-14 | 2016-09-14 | 2016-09-14 | 2016-09-14
2AI103CV28220-08000 | EOF:Demolition Work Existing Road & Existing Fence- New Tank Area - 621
2AI103CV28220 | EOF: Existing Road & Fence Demolition Works
2AI103CV20220-08355 | EOF:Backfilling & Compaction for Fnd | [21 empty] | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19
2AI103CV20220-08350 | EOF:Concrete Potection for Fnd | [21 empty] | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12
2AI103CV20220-08346 | Concrete Pouring - for Pedestal | [21 empty] | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01
2AI103CV20220-08345 | EOF:Rebar, Formwork, Install Embedments for Pedestal | [21 empty] | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29
2AI103CV20220-08341 | Concrete Pouring - for Footing | [19 empty] | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14
2AI103CV20220-08340 | EOF:Rebar, Formwork for Footing | [19 empty] | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08
2AI103CV20220-08335 | EOF:Blinding/PCC for Fnd | [17 empty] | 2016-12-25 | 2016-12-25 | 2016-12-25 | 2016-12-25 | 2016-12-25 | 2016-12-25 | 2016-12-25 | 2016-12-25 | 2016-12-25 | 2016-12-25 | 2016-12-25 | 2016-12-25 | 2016-12-25 | 2016-12-25 | 2016-12-25 | 2016-12-25 | 2016-12-25 | 2016-12-25 | 2016-12-25 | 2016-12-25 | 2016-12-25 | 2016-12-25 | 2016-12-25 | 2016-12-25 | 2016-12-25 | 2016-12-25 | 2016-12-25 | 2016-12-25 | 2016-12-25
2AI103CV20220-08030 | EOF:Survey Marking, Excavation & Subgrade | [17 empty] | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24
2AI103CV20220-08025 | EOF:Backfilling & Compaction for Fnd | [21 empty] | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19
2AI103CV20220-08021 | Concrete Pouring - for Pedestal | [21 empty] | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12
2AI103CV20220-08020 | EOF:Concrete Potection for Fnd | [21 empty] | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01
2AI103CV20220-08015 | EOF:Rebar, Formwork, Install Embedments for Pedestal | [21 empty] | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29
2AI103CV20220-08011 | Concrete Pouring - for Footing | [19 empty] | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14
2AI103CV20220-08010 | EOF:Rebar, Formwork for Footing | [19 empty] | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08
2AI103CV20220-08006 | EOF:Blinding/PCC for Fnd | [17 empty] | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26
2AI103CV20220-08005 | EOF: Foundation for Diesel Fuel Tank(52-D-307 C/D) | [21 empty] | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19
2AI103CV20220-08001 | EOF:Survey Marking, Excavation & Subgrade | [17 empty] | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24
2AI103CV20220-08000 | EOF: Foundation for Diesel Fuel Tank(52-D-307 A/B) | [21 empty] | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19
2AI103CV20220 | EOF: Tank Foundation | [21 empty] | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19
2AI103CV20120-08330 | EOF:Backfilling & Compaction | [15 empty] | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09
2AI103CV20120-08325 | EOF:Concrete Potection | [15 empty] | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03
2AI103CV20120-08321 | Concrete Pouring - for wall - 2nd pouring | [15 empty] | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18
2AI103CV20120-08320 | EOF:Rebar, Formwork for Wall for 2nd Pour | [15 empty] | 2016-10-17 | 2016-10-17 | 2016-10-17 | 2016-10-17 | 2016-10-17 | 2016-10-17 | 2016-10-17 | 2016-10-17 | 2016-10-17 | 2016-10-17 | 2016-10-17 | 2016-10-17 | 2016-10-17 | 2016-10-17 | 2016-10-17 | 2016-10-17 | 2016-10-17 | 2016-10-17 | 2016-10-17 | 2016-10-17 | 2016-10-17 | 2016-10-17 | 2016-10-17 | 2016-10-17 | 2016-10-17 | 2016-10-17 | 2016-10-17 | 2016-10-17 | 2016-10-17 | 2016-10-17 | 2016-10-17
2AI103CV20120-08316 | Concrete Pouring - for wall - 1st pouring | [13 empty] | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27
2AI103CV20120-08315 | EOF:Rebar, Formwork for Wall for 1st Pour | [13 empty] | 2016-08-26 | 2016-08-26 | 2016-08-26 | 2016-08-26 | 2016-08-26 | 2016-08-26 | 2016-08-26 | 2016-08-26 | 2016-08-26 | 2016-08-26 | 2016-08-26 | 2016-08-26 | 2016-08-26 | 2016-08-26 | 2016-08-26 | 2016-08-26 | 2016-08-26 | 2016-08-26 | 2016-08-26 | 2016-08-26 | 2016-08-26 | 2016-08-26 | 2016-08-26 | 2016-08-26 | 2016-08-26 | 2016-08-26 | 2016-08-26 | 2016-08-26 | 2016-08-26 | 2016-08-26 | 2016-08-26 | 2016-08-26 | 2016-08-26
2AI103CV20120-08311 | Concrete Pouring - for base | [15 empty] | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01
2AI103CV20120-08310 | EOF:Rebar, Formwork for base | [13 empty] | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27
2AI103CV20120-08305 | EOF:Blinding/PCC for Fnd | [11 empty] | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21
2AI103CV20120-08301 | EOF:Excavation & Subgrade | [11 empty] | 2016-07-16 | 2016-07-16 | 2016-07-16 | 2016-07-16 | 2016-07-16 | 2016-07-16 | 2016-07-16 | 2016-07-16 | 2016-07-16 | 2016-07-16 | 2016-07-16 | 2016-07-16 | 2016-07-16 | 2016-07-16 | 2016-07-16 | 2016-07-16 | 2016-07-16 | 2016-07-16 | 2016-07-16 | 2016-07-16 | 2016-07-16 | 2016-07-16 | 2016-07-16 | 2016-07-16 | 2016-07-16 | 2016-07-16 | 2016-07-16 | 2016-07-16 | 2016-07-16 | 2016-07-16 | 2016-07-16 | 2016-07-16 | 2016-07-16 | 2016-07-16 | 2016-07-16
2AI103CV20120-08000 | EOF: Oily Water Transfer Vessel 621-V-301( having Pump - 52-G-303 A/B ) Foundation | [15 empty] | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09
2AI103CV20120 | EOF: Foundation of Other Equipments (H2S Scrubber, PIG Receiver etc) | [15 empty] | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09
2AI103CV19820-08030 | EOF:Cable Jointing to Existing Cable | [11 empty] | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01
2AI103CV19820-08020 | EOF:Cable termination to RMU | [11 empty] | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02
2AI103CV19820-08019 | EOF:Relocation of RMU | [11 empty] | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02
2AI103CV19820-08018 | EOF:Disconnection/isolation of Existing cable | [11 empty] | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01
2AI103CV19820-08016 | EOF:Cable Jointing | [9 empty] | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28
2AI103CV19820-08015 | EOF: Shutdown for Reroting of UG Cable & Existing RMU | [11 empty] | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02
2AI103CV19820-08010 | EOF:Laying of UG Cable | [9 empty] | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26
2AI103CV19820-08006 | EOF: Demolition Works of Exisitng UG Cable & Existing RMU | [11 empty] | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02
2AI103CV19820-08005 | EOF: Rerouting of Exisitng UG Cable & Existing RMU | [9 empty] | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28
2AI103CV19820-08000 | EOF: Demolition Works of Exisitng UG Cable & Existing RMU | [11 empty] | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02
2AI103CV19820 | EOF: Demolition, Rerouting of Exisitng UG Cable & Existing RMU | [11 empty] | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02
2AI103CV19800-08030 | EOF:Backfilling & Compaction
2AI103CV19800-08025 | EOF:Installation of Manhole/Pit Cover
2AI103CV19800-08020 | EOF:Concrete Potection
2AI103CV19800-08016 | EOF:Concrete Pouring for cover slab | [11 empty] | 2016-07-02: 2019-04-13
2AI103CV19800-08015 | EOF:Rebar, Formwork for Cover slab | [11 empty] | 2016-07-02: 2019-04-12
2AI103CV19800-08011 | EOF:Concrete Pouring for base & Wall | [11 empty] | 2016-07-02: 2019-04-12
2AI103CV19800-08010 | EOF:Rebar, Formwork for base & Wall | [11 empty] | 2016-07-02: 2019-04-12
2AI103CV19800-08005 | EOF:Blinding/PCC for Sanitary/Sewer drain, Pits & manholes | [11 empty] | 2016-07-02: 2019-04-11
2AI103CV19800-08001 | EOF:Excavation & Subgrade | [11 empty] | 2016-07-02: 2019-04-10
2AI103CV19800-08000 | EOF: Sanitary / Sewer Drains
2AI103CV19800 | EOF: Sanitary / Sewer Drains / Valve Pit & Manholes
2AI103CV19700-08030 | EOF:Backfilling & Compaction
2AI103CV19700-08025 | EOF:Coverslab
2AI103CV19700-08020 | EOF:Concrete Potection
2AI103CV19700-08016 | EOF:Concrete Pouring for wall | [11 empty] | 2016-07-02: 2019-04-10
2AI103CV19700-08015 | EOF:Rebar, Formwork for wall | [11 empty] | 2016-07-02: 2019-01-05; 2016-07-02: 2019-01-05; 2016-07-02: 2019-01-05; 2016-07-02: 2019-01-05; 2016-07-02: 2019-01-05
2AI103CV19700-08011 | EOF:Concrete Pouring for base | [11 empty] | 2016-07-02: 2018-12-28; 2016-07-02: 2018-12-28; 2016-07-02: 2018-12-28; 2016-07-02: 2018-12-28; 2016-07-02: 2018-12-28
2AI103CV19700-08010 | EOF:Rebar, Formwork for base | [11 empty] | 2016-07-02: 2018-12-26; 2016-07-02: 2018-12-26; 2016-07-02: 2018-12-26; 2016-07-02: 2018-12-26; 2016-07-02: 2018-12-26
2AI103CV19700-08006 | EOF:Blinding/PCC for Sump | [11 empty] | 2016-07-02: 2018-12-24; 2016-07-02: 2018-12-24; 2016-07-02: 2018-12-24; 2016-07-02: 2018-12-24; 2016-07-02: 2018-12-24
2AI103CV19700-08005 | EOF: Miscellaneous Drain Pits
2AI103CV19700-08001 | EOF:Excavation & Subgrade | [11 empty] | 2016-07-02: 2018-12-20; 2016-07-02: 2018-12-20; 2016-07-02: 2018-12-20; 2016-07-02: 2018-12-20; 2016-07-02: 2018-12-20
2AI103CV19700 | EOF: Miscellaneous Drain Pits
2AI103CV19600-08025 | EOF:Backfilling & Compaction for Fnd | [11 empty] | 2016-07-02: 2019-02-02; 2016-07-02: 2019-02-02; 2016-07-02: 2019-02-02
2AI103CV19600-08020 | EOF:Concrete Potection for Fnd | [11 empty] | 2016-07-02: 2019-01-18; 2016-07-02: 2019-01-18; 2016-07-02: 2019-01-18; 2016-07-02: 2019-01-18; 2016-07-02: 2019-01-18
2AI103CV19600-08016 | Concrete Pouring - for Pedestal | [11 empty] | 2016-07-02: 2019-01-17; 2016-07-02: 2019-01-17; 2016-07-02: 2019-01-17; 2016-07-02: 2019-01-17; 2016-07-02: 2019-01-17
2AI103CV19600-08015 | EOF:Rebar, Formwork, Install Embedments for Pedestal | [11 empty] | 2016-07-02: 2019-01-14; 2016-07-02: 2019-01-14; 2016-07-02: 2019-01-14; 2016-07-02: 2019-01-14; 2016-07-02: 2019-01-14
2AI103CV19600-08011 | Concrete Pouring - for Footing | [11 empty] | 2016-07-02: 2019-01-10; 2016-07-02: 2019-01-10; 2016-07-02: 2019-01-10; 2016-07-02: 2019-01-10; 2016-07-02: 2019-01-10
2AI103CV19600-08010 | EOF:Rebar, Formwork for Footing | [11 empty] | 2016-07-02: 2019-01-07; 2016-07-02: 2019-01-07; 2016-07-02: 2019-01-07; 2016-07-02: 2019-01-07; 2016-07-02: 2019-01-07
2AI103CV19600-08005 | EOF:Blinding/PCC for Fnd | [11 empty] | 2016-07-02: 2019-01-03; 2016-07-02: 2019-01-03; 2016-07-02: 2019-01-03; 2016-07-02: 2019-01-03; 2016-07-02: 2019-01-03
2AI103CV19600-08001 | EOF:Survey Marking, Excavation & Subgrade | [11 empty] | 2016-07-02: 2019-01-02; 2016-07-02: 2019-01-02; 2016-07-02: 2019-01-02; 2016-07-02: 2019-01-02; 2016-07-02: 2019-01-02
2AI103CV19600-08000 | EOF: Ground Supported Platforms Foundation | [11 empty] | 2016-07-02: 2019-02-02; 2016-07-02: 2019-02-02; 2016-07-02: 2019-02-02
2AI103CV19600 | EOF: Ground Supported Platforms Foundation | [11 empty] | 2016-07-02: 2019-02-02; 2016-07-02: 2019-02-02; 2016-07-02: 2019-02-02
2AI103CV19400-08055 | EOF:Backfilling & Compaction for Fnd | [19 empty] | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08
2AI103CV19400-08050 | EOF:Concrete Potection for Fnd | [19 empty] | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07
2AI103CV19400-08046 | Concrete Pouring - for Pedestal | [19 empty] | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27
2AI103CV19400-08045 | EOF:Rebar, Formwork, Install Embedments for Pedestal | [19 empty] | 2017-02-20 | 2017-02-20 | 2017-02-20 | 2017-02-20 | 2017-02-20 | 2017-02-20 | 2017-02-20 | 2017-02-20 | 2017-02-20 | 2017-02-20 | 2017-02-20 | 2017-02-20 | 2017-02-20 | 2017-02-20 | 2017-02-20 | 2017-02-20 | 2017-02-20 | 2017-02-20 | 2017-02-20 | 2017-02-20 | 2017-02-20 | 2017-02-20 | 2017-02-20 | 2017-02-20 | 2017-02-20 | 2017-02-20 | 2017-02-20
2AI103CV19400-08041 | Concrete Pouring - for Footing | [19 empty] | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16
2AI103CV19400-08040 | EOF:Rebar, Formwork for Footing | [19 empty] | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15
2AI103CV19400-08035 | EOF:Blinding/PCC for Fnd | [19 empty] | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11
2AI103CV19400-08030 | EOF:Survey Marking, Excavation & Subgrade | [17 empty] | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30
2AI103CV19400-08025 | EOF:Backfilling & Compaction for Fnd | [19 empty] | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10
2AI103CV19400-08020 | EOF:Concrete Potection for Fnd | [19 empty] | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07
2AI103CV19400-08016 | Concrete Pouring - for Pedestal | [19 empty] | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27
2AI103CV19400-08015 | EOF:Rebar, Formwork, Install Embedments for Pedestal | [19 empty] | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23
2AI103CV19400-08011 | Concrete Pouring - for Footing | [19 empty] | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16
2AI103CV19400-08010 | EOF:Rebar, Formwork for Footing | [19 empty] | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15
2AI103CV19400-08006 | EOF:Blinding/PCC for Fnd | [19 empty] | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11
2AI103CV19400-08005 | EOF: Foam System Package (52-Z-301 B) Shelter Foundation | [19 empty] | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08
2AI103CV19400-08002 | EOF:Survey Marking, Excavation & Subgrade | [17 empty] | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30
2AI103CV19400-08000 | EOF: Foam System Package (52-Z-301 A) Shelter Foundation | [19 empty] | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10
2AI103CV19400 | EOF: Foam System Package (52-Z-301 A/B) Shelter Foundation | [19 empty] | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10
2AI103CV19200-08055 | EOF:Backfilling & Compaction for Fnd | [17 empty] | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07
2AI103CV19200-08050 | EOF:Concrete Potection for Fnd | [17 empty] | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26
2AI103CV19200-08046 | Concrete Pouring - for Pedestal | [17 empty] | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15
2AI103CV19200-08045 | EOF:Rebar, Formwork, Install Embedments for Pedestal | [17 empty] | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13
2AI103CV19200-08041 | Concrete Pouring - for Footing | [17 empty] | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15
2AI103CV19200-08040 | EOF:Rebar, Formwork for Footing | [17 empty] | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13
2AI103CV19200-08035 | EOF:Blinding/PCC for Fnd | [17 empty] | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08
2AI103CV19200-08030 | EOF:Survey Marking, Excavation & Subgrade | [17 empty] | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06
2AI103CV19200-08025 | EOF:Backfilling & Compaction for Fnd | [17 empty] | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02
2AI103CV19200-08020 | EOF:Concrete Potection for Fnd | [17 empty] | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26
2AI103CV19200-08016 | Concrete Pouring - for Pedestal | [17 empty] | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13
2AI103CV19200-08015 | EOF:Rebar, Formwork, Install Embedments for Pedestal | [17 empty] | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10
2AI103CV19200-08011 | Concrete Pouring - for Footing | [17 empty] | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13
2AI103CV19200-08010 | EOF:Rebar, Formwork for Footing | [17 empty] | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10
2AI103CV19200-08006 | EOF:Blinding/PCC for Fnd | [17 empty] | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04
2AI103CV19200-08005 | EOF: Foam System Package (52-Z-301 B) Foundation | [17 empty] | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07
2AI103CV19200-08001 | EOF:Survey Marking, Excavation & Subgrade | [17 empty] | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30
2AI103CV19200-08000 | EOF: Foam System Package (52-Z-301 A) Foundation | [17 empty] | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02
2AI103CV19200 | EOF: Foam System Package (52-Z-301 A/B) Foundation | [17 empty] | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07
2AI103CV19100-08080 | EOF:Asphalt Work
2AI103CV19100-08075 | EOF:Preparation of sub grade
2AI103CV19100-08070 | EOF:Grading & leveling
2AI103CV19100-08065 | EOF:Excavation
2AI103CV19100-08060 | EOF:Concrete Work
2AI103CV19100-08055 | EOF:Preparation of sub grade
2AI103CV19100-08050 | EOF:Grading & leveling
2AI103CV19100-08045 | EOF:Excavation
2AI103CV19100-08040 | EOF:Compaction
2AI103CV19100-08035 | EOF:Gatch Filling
2AI103CV19100-08030 | EOF:Grading & leveling
2AI103CV19100-08025 | EOF:Excavation
2AI103CV19100-08020 | EOF:Bollards & Crash barrier installation
2AI103CV19100-08016 | EOF:Kerb-stone installation
2AI103CV19100-08015 | EOF:Asphalt Paving
2AI103CV19100-08011 | EOF:Asphalt Work
2AI103CV19100-08010 | EOF:Reinforced Concrete Paving
2AI103CV19100-08006 | EOF:Preparation of sub grade | [17 empty] | 2017-01-07: 2019-04-10
2AI103CV19100-08005 | EOF:Asphalt Road Work
2AI103CV19100-08001 | EOF:Grading & leveling | [17 empty] | 2017-01-07: 2019-04-10
2AI103CV19100-08000 | EOF:Gutch Road Work
2AI103CV19100 | EOF: Roads, Crossing & Paving Works
2AI103CV19000-08020 | EOF:Backfilling & Compaction | [37 empty] | 2018-09-26 | 2018-09-26 | 2018-09-26 | 2018-09-26 | 2018-09-26 | 2018-09-26 | 2018-09-26 | 2018-09-26 | 2018-09-26
2AI103CV19000-08015 | EOF:Concrete Potection | [33 empty] | 2018-05-08 | 2018-05-08 | 2018-05-08 | 2018-05-08 | 2018-05-08 | 2018-05-08 | 2018-05-08 | 2018-05-08 | 2018-05-08 | 2018-05-08 | 2018-05-08 | 2018-05-08 | 2018-05-08
2AI103CV19000-08011 | EOF:Concrete Pouring | [23 empty] | 2017-07-22 | 2017-07-22 | 2017-07-22 | 2017-07-22 | 2017-07-22 | 2017-07-22 | 2017-07-22 | 2017-07-22 | 2017-07-22 | 2017-07-22 | 2017-07-22 | 2017-07-22 | 2017-07-22 | 2017-07-22 | 2017-07-22 | 2017-07-22 | 2017-07-22 | 2017-07-22 | 2017-07-22 | 2017-07-22 | 2017-07-22 | 2017-07-22 | 2017-07-22
2AI103CV19000-08010 | EOF:Rebar, Formwork & PVC conduits installation for Duct Bank | [23 empty] | 2017-07-21 | 2017-07-21 | 2017-07-21 | 2017-07-21 | 2017-07-21 | 2017-07-21 | 2017-07-21 | 2017-07-21 | 2017-07-21 | 2017-07-21 | 2017-07-21 | 2017-07-21 | 2017-07-21 | 2017-07-21 | 2017-07-21 | 2017-07-21 | 2017-07-21 | 2017-07-21 | 2017-07-21 | 2017-07-21 | 2017-07-21 | 2017-07-21 | 2017-07-21
2AI103CV19000-08005 | EOF:Blinding/PCC for Ductbank | [37 empty] | 2018-08-16 | 2018-08-16 | 2018-08-16 | 2018-08-16 | 2018-08-16 | 2018-08-16 | 2018-08-16 | 2018-08-16 | 2018-08-16
2AI103CV19000-08001 | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material | [37 empty] | 2018-08-07 | 2018-08-07 | 2018-08-07 | 2018-08-07 | 2018-08-07 | 2018-08-07 | 2018-08-07 | 2018-08-07 | 2018-08-07
2AI103CV19000-08000 | EOF: EIT Duct banks | [37 empty] | 2018-09-26 | 2018-09-26 | 2018-09-26 | 2018-09-26 | 2018-09-26 | 2018-09-26 | 2018-09-26 | 2018-09-26 | 2018-09-26
2AI103CV19000 | EOF: Road crossings & EIT Duct banks | [37 empty] | 2018-09-26 | 2018-09-26 | 2018-09-26 | 2018-09-26 | 2018-09-26 | 2018-09-26 | 2018-09-26 | 2018-09-26 | 2018-09-26
2AI103CV18800-08055 | EOF:Backfilling & Compaction for Fnd | [17 empty] | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07
2AI103CV18800-08050 | EOF:Concrete Potection for Fnd | [17 empty] | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26
2AI103CV18800-08046 | Concrete Pouring - for Pedestal | [17 empty] | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15
2AI103CV18800-08045 | EOF:Rebar, Formwork, Install Embedments for Pedestal | [17 empty] | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13
2AI103CV18800-08041 | Concrete Pouring - for Footing | [17 empty] | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15
2AI103CV18800-08040 | EOF:Rebar, Formwork for Footing | [17 empty] | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13
2AI103CV18800-08035 | EOF:Blinding/PCC for Fnd | [17 empty] | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08
2AI103CV18800-08030 | EOF:Survey Marking, Excavation & Subgrade | [17 empty] | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06
2AI103CV18800-08025 | EOF:Backfilling & Compaction for Fnd | [17 empty] | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02
2AI103CV18800-08020 | EOF:Concrete Potection for Fnd | [17 empty] | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26
2AI103CV18800-08018 | Concrete Pouring - for Footing | [17 empty] | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13
2AI103CV18800-08016 | Concrete Pouring - for Pedestal | [17 empty] | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13
2AI103CV18800-08015 | EOF:Rebar, Formwork, Install Embedments for Pedestal | [17 empty] | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10
2AI103CV18800-08011 | EOF:Rebar, Formwork for Footing | [17 empty] | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10
2AI103CV18800-08010 | EOF: 621-G-302 C/D Foam Pump Foundation | [17 empty] | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07
2AI103CV18800-08006 | EOF:Blinding/PCC for Fnd | [17 empty] | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04
2AI103CV18800-08005 | EOF: 621-G-302 A/B Foam Pump Foundation | [17 empty] | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02
2AI103CV18800-08000 | EOF:Survey Marking, Excavation & Subgrade | [17 empty] | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30
2AI103CV18800 | EOF: Pump Foundation | [17 empty] | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07
2AI103CV18700-08095 | Installation of gratings/handrail/ladder | [17 empty] | 2017-01-07: 2018-11-22; 2017-01-07: 2018-11-22; 2017-01-07: 2018-11-22; 2017-01-07: 2018-11-22; 2017-01-07: 2018-11-22; 2017-01-07: 2018-11-22; 2017-01-07: 2018-11-22
2AI103CV18700-08090 | Grouting (wherever applicable) | [17 empty] | 2017-01-07: 2018-10-01; 2017-01-07: 2018-10-01; 2017-01-07: 2018-10-01; 2017-01-07: 2018-10-01; 2017-01-07: 2018-10-01; 2017-01-07: 2018-10-01; 2017-01-07: 2018-10-01
2AI103CV18700-08085 | Torque Bolts (wherever applicable) | [37 empty] | 2018-09-04 | 2018-09-04 | 2018-09-04 | 2018-09-04 | 2018-09-04 | 2018-09-04 | 2018-09-04 | 2018-09-04 | 2018-09-04
2AI103CV18700-08080 | Alignment/Welding/Bolting | [37 empty] | 2018-09-04 | 2018-09-04 | 2018-09-04 | 2018-09-04 | 2018-09-04 | 2018-09-04 | 2018-09-04 | 2018-09-04 | 2018-09-04
2AI103CV18700-08075 | Installation of Main steel structure | [37 empty] | 2018-08-07 | 2018-08-07 | 2018-08-07 | 2018-08-07 | 2018-08-07 | 2018-08-07 | 2018-08-07 | 2018-08-07 | 2018-08-07
2AI103CV18700-08070 | Installation of gratings/handrail/ladder | [39 empty] | 2018-11-21 | 2018-11-21 | 2018-11-21 | 2018-11-21 | 2018-11-21 | 2018-11-21 | 2018-11-21
2AI103CV18700-08065 | Grouting (wherever applicable) | [37 empty] | 2018-08-27 | 2018-08-27 | 2018-08-27 | 2018-08-27 | 2018-08-27 | 2018-08-27 | 2018-08-27 | 2018-08-27 | 2018-08-27
2AI103CV18700-08060 | Torque Bolts (wherever applicable) | [37 empty] | 2018-08-22 | 2018-08-22 | 2018-08-22 | 2018-08-22 | 2018-08-22 | 2018-08-22 | 2018-08-22 | 2018-08-22 | 2018-08-22
2AI103CV18700-08055 | Alignment/Welding/Bolting | [35 empty] | 2018-07-25 | 2018-07-25 | 2018-07-25 | 2018-07-25 | 2018-07-25 | 2018-07-25 | 2018-07-25 | 2018-07-25 | 2018-07-25 | 2018-07-25 | 2018-07-25
2AI103CV18700-08050 | Installation of Main steel structure | [35 empty] | 2018-07-25 | 2018-07-25 | 2018-07-25 | 2018-07-25 | 2018-07-25 | 2018-07-25 | 2018-07-25 | 2018-07-25 | 2018-07-25 | 2018-07-25 | 2018-07-25
2AI103CV18700-08045 | Installation of gratings/handrail/ladder | [39 empty] | 2018-11-20 | 2018-11-20 | 2018-11-20 | 2018-11-20 | 2018-11-20 | 2018-11-20 | 2018-11-20
2AI103CV18700-08040 | Grouting (wherever applicable) | [35 empty] | 2018-07-05 | 2018-07-05 | 2018-07-05 | 2018-07-05 | 2018-07-05 | 2018-07-05 | 2018-07-05 | 2018-07-05 | 2018-07-05 | 2018-07-05 | 2018-07-05
2AI103CV18700-08035 | Torque Bolts (wherever applicable) | [35 empty] | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02
2AI103CV18700-08030 | Alignment/Welding/Bolting | [35 empty] | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02
2AI103CV18700-08025 | Installation of gratings/handrail/ladder | [39 empty] | 2018-11-20 | 2018-11-20 | 2018-11-20 | 2018-11-20 | 2018-11-20 | 2018-11-20 | 2018-11-20
2AI103CV18700-08020 | Grouting (wherever applicable) | [35 empty] | 2018-06-12 | 2018-06-12 | 2018-06-12 | 2018-06-12 | 2018-06-12 | 2018-06-12 | 2018-06-12 | 2018-06-12 | 2018-06-12 | 2018-06-12 | 2018-06-12
2AI103CV18700-08015 | Torque Bolts (wherever applicable) | [35 empty] | 2018-06-10 | 2018-06-10 | 2018-06-10 | 2018-06-10 | 2018-06-10 | 2018-06-10 | 2018-06-10 | 2018-06-10 | 2018-06-10 | 2018-06-10 | 2018-06-10
2AI103CV18700-08010 | Alignment/Welding/Bolting | [35 empty] | 2018-06-07 | 2018-06-07 | 2018-06-07 | 2018-06-07 | 2018-06-07 | 2018-06-07 | 2018-06-07 | 2018-06-07 | 2018-06-07 | 2018-06-07 | 2018-06-07
2AI103CV18700-08005 | Installation of Main steel structure | [35 empty] | 2018-06-05 | 2018-06-05 | 2018-06-05 | 2018-06-05 | 2018-06-05 | 2018-06-05 | 2018-06-05 | 2018-06-05 | 2018-06-05 | 2018-06-05 | 2018-06-05
2AI103CV18700-08001 | Installation of Main steel structure | [35 empty] | 2018-06-14 | 2018-06-14 | 2018-06-14 | 2018-06-14 | 2018-06-14 | 2018-06-14 | 2018-06-14 | 2018-06-14 | 2018-06-14 | 2018-06-14 | 2018-06-14
2AI103CV18700-08000 | EOF: Tank Stairways - Structural Steel Erection | [39 empty] | 2018-11-22 | 2018-11-22 | 2018-11-22 | 2018-11-22 | 2018-11-22 | 2018-11-22 | 2018-11-22
2AI103CV18700 | EOF: Structural Steel Erection | [39 empty] | 2018-11-22 | 2018-11-22 | 2018-11-22 | 2018-11-22 | 2018-11-22 | 2018-11-22 | 2018-11-22
2AI103CV18600-08130 | EOF:Backfilling & Compaction for Fnd | [19 empty] | 2017-02-26 | 2017-02-26 | 2017-02-26 | 2017-02-26 | 2017-02-26 | 2017-02-26 | 2017-02-26 | 2017-02-26 | 2017-02-26 | 2017-02-26 | 2017-02-26 | 2017-02-26 | 2017-02-26 | 2017-02-26 | 2017-02-26 | 2017-02-26 | 2017-02-26 | 2017-02-26 | 2017-02-26 | 2017-02-26 | 2017-02-26 | 2017-02-26 | 2017-02-26 | 2017-02-26 | 2017-02-26 | 2017-02-26 | 2017-02-26
2AI103CV18600-08125 | EOF:Concrete Potection for Fnd | [19 empty] | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07
2AI103CV18600-08121 | EOF:Concrete Pouring - for Pedestal | [17 empty] | 2017-01-25 | 2017-01-25 | 2017-01-25 | 2017-01-25 | 2017-01-25 | 2017-01-25 | 2017-01-25 | 2017-01-25 | 2017-01-25 | 2017-01-25 | 2017-01-25 | 2017-01-25 | 2017-01-25 | 2017-01-25 | 2017-01-25 | 2017-01-25 | 2017-01-25 | 2017-01-25 | 2017-01-25 | 2017-01-25 | 2017-01-25 | 2017-01-25 | 2017-01-25 | 2017-01-25 | 2017-01-25 | 2017-01-25 | 2017-01-25 | 2017-01-25 | 2017-01-25
2AI103CV18600-08120 | EOF:Rebar, Formwork, Install Embedments for Pedestal | [17 empty] | 2017-01-23 | 2017-01-23 | 2017-01-23 | 2017-01-23 | 2017-01-23 | 2017-01-23 | 2017-01-23 | 2017-01-23 | 2017-01-23 | 2017-01-23 | 2017-01-23 | 2017-01-23 | 2017-01-23 | 2017-01-23 | 2017-01-23 | 2017-01-23 | 2017-01-23 | 2017-01-23 | 2017-01-23 | 2017-01-23 | 2017-01-23 | 2017-01-23 | 2017-01-23 | 2017-01-23 | 2017-01-23 | 2017-01-23 | 2017-01-23 | 2017-01-23 | 2017-01-23
2AI103CV18600-08116 | EOF:Concrete Pouring - for Footing | [19 empty] | 2017-02-25 | 2017-02-25 | 2017-02-25 | 2017-02-25 | 2017-02-25 | 2017-02-25 | 2017-02-25 | 2017-02-25 | 2017-02-25 | 2017-02-25 | 2017-02-25 | 2017-02-25 | 2017-02-25 | 2017-02-25 | 2017-02-25 | 2017-02-25 | 2017-02-25 | 2017-02-25 | 2017-02-25 | 2017-02-25 | 2017-02-25 | 2017-02-25 | 2017-02-25 | 2017-02-25 | 2017-02-25 | 2017-02-25 | 2017-02-25
2AI103CV18600-08115 | EOF:Rebar, Formwork for Footing | [19 empty] | 2017-02-25 | 2017-02-25 | 2017-02-25 | 2017-02-25 | 2017-02-25 | 2017-02-25 | 2017-02-25 | 2017-02-25 | 2017-02-25 | 2017-02-25 | 2017-02-25 | 2017-02-25 | 2017-02-25 | 2017-02-25 | 2017-02-25 | 2017-02-25 | 2017-02-25 | 2017-02-25 | 2017-02-25 | 2017-02-25 | 2017-02-25 | 2017-02-25 | 2017-02-25 | 2017-02-25 | 2017-02-25 | 2017-02-25 | 2017-02-25
2AI103CV18600-08110 | EOF:Blinding/PCC for Fnd | [17 empty] | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08
2AI103CV18600-08105 | EOF:Survey Marking, Excavation & Subgrade | [17 empty] | 2016-11-27 | 2016-11-27 | 2016-11-27 | 2016-11-27 | 2016-11-27 | 2016-11-27 | 2016-11-27 | 2016-11-27 | 2016-11-27 | 2016-11-27 | 2016-11-27 | 2016-11-27 | 2016-11-27 | 2016-11-27 | 2016-11-27 | 2016-11-27 | 2016-11-27 | 2016-11-27 | 2016-11-27 | 2016-11-27 | 2016-11-27 | 2016-11-27 | 2016-11-27 | 2016-11-27 | 2016-11-27 | 2016-11-27 | 2016-11-27 | 2016-11-27 | 2016-11-27
2AI103CV18600-08090 | EOF:Backfilling & Compaction for Fnd | [21 empty] | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30
2AI103CV18600-08085 | EOF:Concrete Potection for Fnd | [21 empty] | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25
2AI103CV18600-08081 | EOF:Concrete Pouring - for Pedestal | [19 empty] | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09
2AI103CV18600-08080 | EOF:Rebar, Formwork, Install Embedments for Pedestal | [19 empty] | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08
2AI103CV18600-08076 | EOF:Concrete Pouring - for Footing | [19 empty] | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02
2AI103CV18600-08075 | EOF:Rebar, Formwork for Footing | [19 empty] | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02
2AI103CV18600-08070 | EOF:Blinding/PCC for Fnd | [19 empty] | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28
2AI103CV18600-08065 | EOF:Survey Marking, Excavation & Subgrade | [17 empty] | 2016-12-01 | 2016-12-01 | 2016-12-01 | 2016-12-01 | 2016-12-01 | 2016-12-01 | 2016-12-01 | 2016-12-01 | 2016-12-01 | 2016-12-01 | 2016-12-01 | 2016-12-01 | 2016-12-01 | 2016-12-01 | 2016-12-01 | 2016-12-01 | 2016-12-01 | 2016-12-01 | 2016-12-01 | 2016-12-01 | 2016-12-01 | 2016-12-01 | 2016-12-01 | 2016-12-01 | 2016-12-01 | 2016-12-01 | 2016-12-01 | 2016-12-01 | 2016-12-01
2AI103CV18600-08050 | EOF:Backfilling & Compaction for Fnd | [21 empty] | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30
2AI103CV18600-08045 | EOF:Concrete Potection for Fnd | [21 empty] | 2017-03-26 | 2017-03-26 | 2017-03-26 | 2017-03-26 | 2017-03-26 | 2017-03-26 | 2017-03-26 | 2017-03-26 | 2017-03-26 | 2017-03-26 | 2017-03-26 | 2017-03-26 | 2017-03-26 | 2017-03-26 | 2017-03-26 | 2017-03-26 | 2017-03-26 | 2017-03-26 | 2017-03-26 | 2017-03-26 | 2017-03-26 | 2017-03-26 | 2017-03-26 | 2017-03-26 | 2017-03-26
2AI103CV18600-08041 | EOF:Concrete Pouring - for Pedestal | [19 empty] | 2017-03-11 | 2017-03-11 | 2017-03-11 | 2017-03-11 | 2017-03-11 | 2017-03-11 | 2017-03-11 | 2017-03-11 | 2017-03-11 | 2017-03-11 | 2017-03-11 | 2017-03-11 | 2017-03-11 | 2017-03-11 | 2017-03-11 | 2017-03-11 | 2017-03-11 | 2017-03-11 | 2017-03-11 | 2017-03-11 | 2017-03-11 | 2017-03-11 | 2017-03-11 | 2017-03-11 | 2017-03-11 | 2017-03-11 | 2017-03-11
2AI103CV18600-08040 | EOF:Rebar, Formwork, Install Embedments for Pedestal | [19 empty] | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08
2AI103CV18600-08036 | EOF:Concrete Pouring - for Footing | [19 empty] | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05
2AI103CV18600-08035 | EOF:Rebar, Formwork for Footing | [19 empty] | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04
2AI103CV18600-08030 | EOF:Blinding/PCC for Fnd | [19 empty] | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02
2AI103CV18600-08025 | EOF:Backfilling & Compaction for Fnd | [21 empty] | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30
2AI103CV18600-08020 | EOF:Concrete Potection for Fnd | [21 empty] | 2017-03-26 | 2017-03-26 | 2017-03-26 | 2017-03-26 | 2017-03-26 | 2017-03-26 | 2017-03-26 | 2017-03-26 | 2017-03-26 | 2017-03-26 | 2017-03-26 | 2017-03-26 | 2017-03-26 | 2017-03-26 | 2017-03-26 | 2017-03-26 | 2017-03-26 | 2017-03-26 | 2017-03-26 | 2017-03-26 | 2017-03-26 | 2017-03-26 | 2017-03-26 | 2017-03-26 | 2017-03-26
2AI103CV18600-08016 | EOF:Concrete Pouring - for Pedestal | [19 empty] | 2017-03-11 | 2017-03-11 | 2017-03-11 | 2017-03-11 | 2017-03-11 | 2017-03-11 | 2017-03-11 | 2017-03-11 | 2017-03-11 | 2017-03-11 | 2017-03-11 | 2017-03-11 | 2017-03-11 | 2017-03-11 | 2017-03-11 | 2017-03-11 | 2017-03-11 | 2017-03-11 | 2017-03-11 | 2017-03-11 | 2017-03-11 | 2017-03-11 | 2017-03-11 | 2017-03-11 | 2017-03-11 | 2017-03-11 | 2017-03-11
2AI103CV18600-08015 | EOF:Rebar, Formwork, Install Embedments for Pedestal | [19 empty] | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08
2AI103CV18600-08011 | EOF:Concrete Pouring - for Footing | [19 empty] | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05
2AI103CV18600-08010 | EOF:Rebar, Formwork for Footing | [19 empty] | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04
2AI103CV18600-08005 | EOF:Blinding/PCC for Fnd | [19 empty] | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02
2AI103CV18600-08002 | EOF:Survey Marking, Excavation & Subgrade | [19 empty] | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01
2AI103CV18600-08001 | EOF:Survey Marking, Excavation & Subgrade | [19 empty] | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01
2AI103CV18600-08000 | EOF: Foundation for Tank Stairways Structural Steel | [21 empty] | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30
2AI103CV18600 | EOF: Foundation for Steel Structure | [21 empty] | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30
2AI103CV18500-08010 | EOF:Grouting Mobile Foam Cannon and Mobile Monitor Shelter | [37 empty] | 2018-08-12 | 2018-08-12 | 2018-08-12 | 2018-08-12 | 2018-08-12 | 2018-08-12 | 2018-08-12 | 2018-08-12 | 2018-08-12
2AI103CV18500-08005 | EOF:Alignment & Bolting/Torqueing Mobile Foam Cannon and Mobile Monitor Shelter | [35 empty] | 2018-07-26 | 2018-07-26 | 2018-07-26 | 2018-07-26 | 2018-07-26 | 2018-07-26 | 2018-07-26 | 2018-07-26 | 2018-07-26 | 2018-07-26 | 2018-07-26
2AI103CV18500-08001 | EOF:Installation of Str. Steel Mobile Foam Cannon and Mobile Monitor Shelter | [33 empty] | 2018-04-26 | 2018-04-26 | 2018-04-26 | 2018-04-26 | 2018-04-26 | 2018-04-26 | 2018-04-26 | 2018-04-26 | 2018-04-26 | 2018-04-26 | 2018-04-26 | 2018-04-26 | 2018-04-26
2AI103CV18500-08000 | EOF: Mobile Foam Cannon and Mobile Monitor Shelter Erection | [37 empty] | 2018-08-12 | 2018-08-12 | 2018-08-12 | 2018-08-12 | 2018-08-12 | 2018-08-12 | 2018-08-12 | 2018-08-12 | 2018-08-12
2AI103CV18500 | EOF: Mobile Foam Cannon and Mobile Monitor Shelter Erection | [37 empty] | 2018-08-12 | 2018-08-12 | 2018-08-12 | 2018-08-12 | 2018-08-12 | 2018-08-12 | 2018-08-12 | 2018-08-12 | 2018-08-12
2AI103CV18400-08025 | EOF:Backfilling & Compaction for Fnd | [15 empty] | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21
2AI103CV18400-08020 | EOF:Concrete Potection for Fnd | [15 empty] | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20
2AI103CV18400-08016 | EOF:Concrete Pouring - for Pedestal | [15 empty] | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06
2AI103CV18400-08015 | EOF:Rebar, Formwork, Install Embedments for Pedestal | [15 empty] | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03
2AI103CV18400-08011 | EOF:Concrete Pouring - for Footing | [15 empty] | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06
2AI103CV18400-08010 | EOF:Rebar, Formwork for Footing | [15 empty] | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03
2AI103CV18400-08005 | EOF:Blinding/PCC for Fnd | [15 empty] | 2016-09-30 | 2016-09-30 | 2016-09-30 | 2016-09-30 | 2016-09-30 | 2016-09-30 | 2016-09-30 | 2016-09-30 | 2016-09-30 | 2016-09-30 | 2016-09-30 | 2016-09-30 | 2016-09-30 | 2016-09-30 | 2016-09-30 | 2016-09-30 | 2016-09-30 | 2016-09-30 | 2016-09-30 | 2016-09-30 | 2016-09-30 | 2016-09-30 | 2016-09-30 | 2016-09-30 | 2016-09-30 | 2016-09-30 | 2016-09-30 | 2016-09-30 | 2016-09-30 | 2016-09-30 | 2016-09-30
2AI103CV18400-08001 | EOF:Survey Marking, Excavation & Subgrade | [13 empty] | 2016-09-16 | 2016-09-16 | 2016-09-16 | 2016-09-16 | 2016-09-16 | 2016-09-16 | 2016-09-16 | 2016-09-16 | 2016-09-16 | 2016-09-16 | 2016-09-16 | 2016-09-16 | 2016-09-16 | 2016-09-16 | 2016-09-16 | 2016-09-16 | 2016-09-16 | 2016-09-16 | 2016-09-16 | 2016-09-16 | 2016-09-16 | 2016-09-16 | 2016-09-16 | 2016-09-16 | 2016-09-16 | 2016-09-16 | 2016-09-16 | 2016-09-16 | 2016-09-16 | 2016-09-16 | 2016-09-16 | 2016-09-16 | 2016-09-16
2AI103CV18400-08000 | EOF: Mobile Foam Cannon and Mobile Monitor Shelter Foundation | [15 empty] | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21
2AI103CV18400 | EOF: Mobile Foam Cannon and Mobile Monitor Shelter Foundation | [15 empty] | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21
2AI103CV18300-08455 | EOF:Install Route/saftey Markers | [35 empty] | 2018-06-21 | 2018-06-21 | 2018-06-21 | 2018-06-21 | 2018-06-21 | 2018-06-21 | 2018-06-21 | 2018-06-21 | 2018-06-21 | 2018-06-21 | 2018-06-21
2AI103CV18300-08450 | EOF:Backfilling & Compaction | [35 empty] | 2018-06-20 | 2018-06-20 | 2018-06-20 | 2018-06-20 | 2018-06-20 | 2018-06-20 | 2018-06-20 | 2018-06-20 | 2018-06-20 | 2018-06-20 | 2018-06-20
2AI103CV18300-08445 | EOF:Install Cable Tile Laying & warning Tapes | [35 empty] | 2018-06-18 | 2018-06-18 | 2018-06-18 | 2018-06-18 | 2018-06-18 | 2018-06-18 | 2018-06-18 | 2018-06-18 | 2018-06-18 | 2018-06-18 | 2018-06-18
2AI103CV18300-08441 | EOF:Sand Padding | [35 empty] | 2018-06-16 | 2018-06-16 | 2018-06-16 | 2018-06-16 | 2018-06-16 | 2018-06-16 | 2018-06-16 | 2018-06-16 | 2018-06-16 | 2018-06-16 | 2018-06-16
2AI103CV18300-08440 | EOF:Sand bedding | [35 empty] | 2018-06-14 | 2018-06-14 | 2018-06-14 | 2018-06-14 | 2018-06-14 | 2018-06-14 | 2018-06-14 | 2018-06-14 | 2018-06-14 | 2018-06-14 | 2018-06-14
2AI103CV18300-08435 | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material | [35 empty] | 2018-06-12 | 2018-06-12 | 2018-06-12 | 2018-06-12 | 2018-06-12 | 2018-06-12 | 2018-06-12 | 2018-06-12 | 2018-06-12 | 2018-06-12 | 2018-06-12
2AI103CV18300-08380 | EOF:Install Route/saftey Markers
2AI103CV18300-08375 | EOF:Backfilling & Compaction | [35 empty] | 2018-06-12: 2019-01-31; 2018-06-12: 2019-01-31; 2018-06-12: 2019-01-31
2AI103CV18300-08370 | EOF:Install Cable Tile Laying & warning Tapes | [35 empty] | 2018-06-12: 2019-01-30; 2018-06-12: 2019-01-30; 2018-06-12: 2019-01-30
2AI103CV18300-08366 | EOF:Sand Padding | [35 empty] | 2018-06-12: 2019-01-31; 2018-06-12: 2019-01-31; 2018-06-12: 2019-01-31
2AI103CV18300-08365 | EOF:Sand bedding | [35 empty] | 2018-06-12: 2018-12-24; 2018-06-12: 2018-12-24; 2018-06-12: 2018-12-24; 2018-06-12: 2018-12-24; 2018-06-12: 2018-12-24
2AI103CV18300-08360 | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material | [35 empty] | 2018-06-12: 2018-12-23; 2018-06-12: 2018-12-23; 2018-06-12: 2018-12-23; 2018-06-12: 2018-12-23; 2018-06-12: 2018-12-23
2AI103CV18300-08355 | EOF:Install Route/saftey Markers
2AI103CV18300-08350 | EOF:Backfilling & Compaction | [35 empty] | 2018-07-27 | 2018-07-27 | 2018-07-27 | 2018-07-27 | 2018-07-27 | 2018-07-27 | 2018-07-27 | 2018-07-27 | 2018-07-27 | 2018-07-27 | 2018-07-27
2AI103CV18300-08345 | EOF:Install Cable Tile Laying & warning Tapes | [35 empty] | 2018-07-18 | 2018-07-18 | 2018-07-18 | 2018-07-18 | 2018-07-18 | 2018-07-18 | 2018-07-18 | 2018-07-18 | 2018-07-18 | 2018-07-18 | 2018-07-18
2AI103CV18300-08341 | EOF:Sand Padding | [35 empty] | 2018-07-06 | 2018-07-06 | 2018-07-06 | 2018-07-06 | 2018-07-06 | 2018-07-06 | 2018-07-06 | 2018-07-06 | 2018-07-06 | 2018-07-06 | 2018-07-06
2AI103CV18300-08340 | EOF:Sand bedding | [35 empty] | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02
2AI103CV18300-08335 | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material | [35 empty] | 2018-06-18 | 2018-06-18 | 2018-06-18 | 2018-06-18 | 2018-06-18 | 2018-06-18 | 2018-06-18 | 2018-06-18 | 2018-06-18 | 2018-06-18 | 2018-06-18
2AI103CV18300-08305 | EOF:Install Route/saftey Markers
2AI103CV18300-08300 | EOF:Backfilling & Compaction
2AI103CV18300-08295 | EOF:Install Cable Tile Laying & warning Tapes
2AI103CV18300-08291 | EOF:Sand Padding
2AI103CV18300-08290 | EOF:Sand bedding
2AI103CV18300-08285 | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material
2AI103CV18300-08180 | EOF:Install Route/saftey Markers
2AI103CV18300-08175 | EOF:Backfilling & Compaction
2AI103CV18300-08170 | EOF:Install Cable Tile Laying & warning Tapes
2AI103CV18300-08166 | EOF:Sand Padding
2AI103CV18300-08165 | EOF:Sand bedding
2AI103CV18300-08160 | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material
2AI103CV18300-08155 | EOF:Install Route/saftey Markers | [35 empty] | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07
2AI103CV18300-08150 | EOF:Backfilling & Compaction | [35 empty] | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07
2AI103CV18300-08145 | EOF:Install Cable Tile Laying & warning Tapes | [35 empty] | 2018-07-06 | 2018-07-06 | 2018-07-06 | 2018-07-06 | 2018-07-06 | 2018-07-06 | 2018-07-06 | 2018-07-06 | 2018-07-06 | 2018-07-06 | 2018-07-06
2AI103CV18300-08136 | EOF:Sand Padding | [35 empty] | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07
2AI103CV18300-08135 | EOF:Sand bedding | [35 empty] | 2018-07-03 | 2018-07-03 | 2018-07-03 | 2018-07-03 | 2018-07-03 | 2018-07-03 | 2018-07-03 | 2018-07-03 | 2018-07-03 | 2018-07-03 | 2018-07-03
2AI103CV18300-08125 | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material | [35 empty] | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02
2AI103CV18300-08055 | EOF:Install Route/saftey Markers | [39 empty] | 2018-11-23 | 2018-11-23 | 2018-11-23 | 2018-11-23 | 2018-11-23 | 2018-11-23 | 2018-11-23
2AI103CV18300-08050 | EOF:Backfilling & Compaction | [29 empty] | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06
2AI103CV18300-08045 | EOF:Install Cable Tile Laying & warning Tapes | [29 empty] | 2018-01-04 | 2018-01-04 | 2018-01-04 | 2018-01-04 | 2018-01-04 | 2018-01-04 | 2018-01-04 | 2018-01-04 | 2018-01-04 | 2018-01-04 | 2018-01-04 | 2018-01-04 | 2018-01-04 | 2018-01-04 | 2018-01-04 | 2018-01-04 | 2018-01-04
2AI103CV18300-08041 | EOF:Sand Padding | [29 empty] | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03
2AI103CV18300-08040 | EOF:Sand bedding | [27 empty] | 2017-11-11 | 2017-11-11 | 2017-11-11 | 2017-11-11 | 2017-11-11 | 2017-11-11 | 2017-11-11 | 2017-11-11 | 2017-11-11 | 2017-11-11 | 2017-11-11 | 2017-11-11 | 2017-11-11 | 2017-11-11 | 2017-11-11 | 2017-11-11 | 2017-11-11 | 2017-11-11 | 2017-11-11
2AI103CV18300-08035 | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material | [27 empty] | 2017-11-09 | 2017-11-09 | 2017-11-09 | 2017-11-09 | 2017-11-09 | 2017-11-09 | 2017-11-09 | 2017-11-09 | 2017-11-09 | 2017-11-09 | 2017-11-09 | 2017-11-09 | 2017-11-09 | 2017-11-09 | 2017-11-09 | 2017-11-09 | 2017-11-09 | 2017-11-09 | 2017-11-09
2AI103CV18300-08000 | EOF: Cable trench
2AI103CV18300 | EOF: RCC Cable trench
2AI103CV01200-08025 | EOF:Grouting of Ground Supported Platforms
2AI103CV01200-08020 | EOF:Alignment & Bolting/Torqueing of Ground Supported Platforms
2AI103CV01200-08015 | EOF:Installation of Str. Steel of Ground Supported Platforms
2AI103CV01200-08010 | EOF:Grouting of Ground Supported Platforms | [27 empty] | 2017-11-09: 2019-04-09
2AI103CV01200-08006 | EOF:Alignment & Bolting/Torqueing of Ground Supported Platforms | [27 empty] | 2017-11-09: 2019-03-19; 2017-11-09: 2019-03-19; 2017-11-09: 2019-03-19
2AI103CV01200-08005 | EOF: Pipe Support & EIT Supports Erection
2AI103CV01200-08001 | EOF:Installation of Str. Steel of Ground Supported Platforms | [27 empty] | 2017-11-09: 2019-03-11; 2017-11-09: 2019-03-11; 2017-11-09: 2019-03-11
2AI103CV01200-08000 | EOF: Structural Steel of Ground Supported /Equipment Mounted Platforms | [27 empty] | 2017-11-09: 2019-04-09
2AI103CV01200 | EOF: Structural Steel of Ground Supported Platforms
2AI102TE01100-08141 | Fiber Optic Cable Laying from Boundery Limit to 52-SUBST-302 | [27 empty] | 2017-11-09: 2019-04-10
2AI102TE01100-08100 | EOF: Issue AFC DrawingsTELECOM CABLE LAYING FROM COCC TO SUBSTATION | [29 empty] | 2017-12-14 | 2017-12-14 | 2017-12-14 | 2017-12-14 | 2017-12-14 | 2017-12-14 | 2017-12-14 | 2017-12-14 | 2017-12-14 | 2017-12-14 | 2017-12-14 | 2017-12-14 | 2017-12-14 | 2017-12-14 | 2017-12-14 | 2017-12-14 | 2017-12-14
2AI102TE01100 | EOF: Telecom Cable Laying from COCC to Substation | [29 empty] | 2017-12-14: 2019-04-10
2AI102TE01000-08141 | Fiber Optic Cable Laying in boudery Limit of COCC Area | [29 empty] | 2017-12-14: 2019-01-29; 2017-12-14: 2019-01-29; 2017-12-14: 2019-01-29
2AI102TE01000-08100 | EOF: Issue AFC Drawings TELECOM CABLE LAYING TO COCC | [29 empty] | 2017-12-14 | 2017-12-14 | 2017-12-14 | 2017-12-14 | 2017-12-14 | 2017-12-14 | 2017-12-14 | 2017-12-14 | 2017-12-14 | 2017-12-14 | 2017-12-14 | 2017-12-14 | 2017-12-14 | 2017-12-14 | 2017-12-14 | 2017-12-14 | 2017-12-14
2AI102TE01000 | EOF: Telecom Cable Laying to COCC | [29 empty] | 2017-12-14: 2019-01-29; 2017-12-14: 2019-01-29; 2017-12-14: 2019-01-29
2AI102PI01400-08141 | COCC: Touch-up painting of Piping | [29 empty] | 2017-12-14: 2019-01-17; 2017-12-14: 2019-01-17; 2017-12-14: 2019-01-17; 2017-12-14: 2019-01-17; 2017-12-14: 2019-01-17
2AI102PI01400-08010 | COCC: Touch-up painting of SS Pipe | [29 empty] | 2017-12-14: 2019-01-17; 2017-12-14: 2019-01-17; 2017-12-14: 2019-01-17; 2017-12-14: 2019-01-17; 2017-12-14: 2019-01-17
2AI102PI01400-08000 | COCC:Touch-up painting of CS Pipe | [29 empty] | 2017-12-14: 2019-01-17; 2017-12-14: 2019-01-17; 2017-12-14: 2019-01-17; 2017-12-14: 2019-01-17; 2017-12-14: 2019-01-17
2AI102PI01400 | EOF: Touch-up painting of Piping | [29 empty] | 2017-12-14: 2019-01-17; 2017-12-14: 2019-01-17; 2017-12-14: 2019-01-17; 2017-12-14: 2019-01-17; 2017-12-14: 2019-01-17
2AI102PI01300-08142 | Metallic (SS/SDSS) Piping Works | [29 empty] | 2017-12-14: 2018-12-12; 2017-12-14: 2018-12-12; 2017-12-14: 2018-12-12; 2017-12-14: 2018-12-12; 2017-12-14: 2018-12-12
2AI102PI01300-08141 | Metallic (CS/LTCS) Piping Works | [29 empty] | 2017-12-14: 2018-12-30; 2017-12-14: 2018-12-30; 2017-12-14: 2018-12-30; 2017-12-14: 2018-12-30; 2017-12-14: 2018-12-30
2AI102PI01300-08040 | COCC: Flange Management | [29 empty] | 2017-12-14: 2018-12-12; 2017-12-14: 2018-12-12; 2017-12-14: 2018-12-12; 2017-12-14: 2018-12-12; 2017-12-14: 2018-12-12
2AI102PI01300-08035 | EOF:Flange Management | [29 empty] | 2017-12-14: 2018-12-30; 2017-12-14: 2018-12-30; 2017-12-14: 2018-12-30; 2017-12-14: 2018-12-30; 2017-12-14: 2018-12-30
2AI102PI01300-08030 | COCC: Reinstatement | [29 empty] | 2017-12-14: 2018-12-12; 2017-12-14: 2018-12-12; 2017-12-14: 2018-12-12; 2017-12-14: 2018-12-12; 2017-12-14: 2018-12-12
2AI102PI01300-08015 | COCC: Pressure Testing & Approval | [29 empty] | 2017-12-14: 2018-12-12; 2017-12-14: 2018-12-12; 2017-12-14: 2018-12-12; 2017-12-14: 2018-12-12; 2017-12-14: 2018-12-12
2AI102PI01300-08010 | COCC: Test pack preparation & Ready for Test | [29 empty] | 2017-12-14: 2018-12-11; 2017-12-14: 2018-12-11; 2017-12-14: 2018-12-11; 2017-12-14: 2018-12-11; 2017-12-14: 2018-12-11
2AI102PI01300-08005 | EOF:Reinstatement | [29 empty] | 2017-12-14: 2018-12-30; 2017-12-14: 2018-12-30; 2017-12-14: 2018-12-30; 2017-12-14: 2018-12-30; 2017-12-14: 2018-12-30
2AI102PI01300-08002 | EOF:Pressure Testing & Approval | [29 empty] | 2017-12-14: 2018-12-28; 2017-12-14: 2018-12-28; 2017-12-14: 2018-12-28; 2017-12-14: 2018-12-28; 2017-12-14: 2018-12-28
2AI102PI01300-08000 | EOF:Test pack preparation & Ready for Test | [29 empty] | 2017-12-14: 2018-12-28; 2017-12-14: 2018-12-28; 2017-12-14: 2018-12-28; 2017-12-14: 2018-12-28; 2017-12-14: 2018-12-28
2AI102PI01300 | EOF: Hydrotesting | [29 empty] | 2017-12-14: 2018-12-30; 2017-12-14: 2018-12-30; 2017-12-14: 2018-12-30; 2017-12-14: 2018-12-30; 2017-12-14: 2018-12-30
2AI102PI01200-08141 | COCC: Insulation of Piping | [27 empty] | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09
2AI102PI01200-08020 | COCC: Cladding/Fastening/Sealing | [27 empty] | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09
2AI102PI01200-08015 | COCC: Lagging | [27 empty] | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09
2AI102PI01200-08010 | COCC: Cladding Fabrication | [27 empty] | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09
2AI102PI01200-08005 | COCC: Surface Preparation | [27 empty] | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09
2AI102PI01200 | COCC: Insulation of Piping | [27 empty] | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09
2AI102PI01100-08200 | COCC: Install piping valves | [27 empty] | 2017-10-09: 2018-12-12; 2017-10-09: 2018-12-12; 2017-10-09: 2018-12-12; 2017-10-09: 2018-12-12; 2017-10-09: 2018-12-12
2AI102PI01100-08195 | COCC: Install Permanent Supporting for Pipes | [27 empty] | 2017-10-09: 2018-12-14; 2017-10-09: 2018-12-14; 2017-10-09: 2018-12-14; 2017-10-09: 2018-12-14; 2017-10-09: 2018-12-14
2AI102PI01100-08190 | EOF:NDE/PWHT/QC Checks of Pipes | [27 empty] | 2017-10-09: 2018-12-12; 2017-10-09: 2018-12-12; 2017-10-09: 2018-12-12; 2017-10-09: 2018-12-12; 2017-10-09: 2018-12-12
2AI102PI01100-08185 | COCC:Welding/Bolting | [27 empty] | 2017-10-09: 2018-12-12; 2017-10-09: 2018-12-12; 2017-10-09: 2018-12-12; 2017-10-09: 2018-12-12; 2017-10-09: 2018-12-12
2AI102PI01100-08180 | COCC:Alignment/Fit-up | [27 empty] | 2017-10-09: 2018-12-12; 2017-10-09: 2018-12-12; 2017-10-09: 2018-12-12; 2017-10-09: 2018-12-12; 2017-10-09: 2018-12-12
2AI102PI01100-08175 | EOF:Installation of pipes | [27 empty] | 2017-10-09: 2018-12-12; 2017-10-09: 2018-12-12; 2017-10-09: 2018-12-12; 2017-10-09: 2018-12-12; 2017-10-09: 2018-12-12
2AI102PI01100-08170 | COCC:Install piping valves | [27 empty] | 2017-10-09: 2018-12-31; 2017-10-09: 2018-12-31; 2017-10-09: 2018-12-31; 2017-10-09: 2018-12-31; 2017-10-09: 2018-12-31
2AI102PI01100-08165 | EOF:Install Permanent Supporting for Pipes | [27 empty] | 2017-10-09: 2018-12-31; 2017-10-09: 2018-12-31; 2017-10-09: 2018-12-31; 2017-10-09: 2018-12-31; 2017-10-09: 2018-12-31
2AI102PI01100-08160 | EOF:NDE/PWHT/QC Checks of Pipes | [27 empty] | 2017-10-09: 2018-12-30; 2017-10-09: 2018-12-30; 2017-10-09: 2018-12-30; 2017-10-09: 2018-12-30; 2017-10-09: 2018-12-30
2AI102PI01100-08155 | COCC:Welding/Bolting | [27 empty] | 2017-10-09: 2018-12-29; 2017-10-09: 2018-12-29; 2017-10-09: 2018-12-29; 2017-10-09: 2018-12-29; 2017-10-09: 2018-12-29
2AI102PI01100-08150 | COCC:Alignment/Fit-up | [27 empty] | 2017-10-09: 2018-12-29; 2017-10-09: 2018-12-29; 2017-10-09: 2018-12-29; 2017-10-09: 2018-12-29; 2017-10-09: 2018-12-29
2AI102PI01100-08145 | EOF:Installation of pipes | [27 empty] | 2017-10-09: 2018-12-29; 2017-10-09: 2018-12-29; 2017-10-09: 2018-12-29; 2017-10-09: 2018-12-29; 2017-10-09: 2018-12-29
2AI102PI01100-08142 | Metallic (SS/SDSS) Piping Works | [27 empty] | 2017-10-09: 2018-12-14; 2017-10-09: 2018-12-14; 2017-10-09: 2018-12-14; 2017-10-09: 2018-12-14; 2017-10-09: 2018-12-14
2AI102PI01100-08141 | Metallic (CS/LTCS) Piping Works | [27 empty] | 2017-10-09: 2018-12-31; 2017-10-09: 2018-12-31; 2017-10-09: 2018-12-31; 2017-10-09: 2018-12-31; 2017-10-09: 2018-12-31
2AI102PI01100 | AG Piping works | [27 empty] | 2017-10-09: 2018-12-31; 2017-10-09: 2018-12-31; 2017-10-09: 2018-12-31; 2017-10-09: 2018-12-31; 2017-10-09: 2018-12-31
2AI102PI01000-08165 | COCC:Coating/Wrapping | [27 empty] | 2017-10-09: 2019-01-12; 2017-10-09: 2019-01-12; 2017-10-09: 2019-01-12; 2017-10-09: 2019-01-12; 2017-10-09: 2019-01-12
2AI102PI01000-08160 | COCC:NDE/PWHT/QC Checks of Pipes | [27 empty] | 2017-10-09: 2018-12-30; 2017-10-09: 2018-12-30; 2017-10-09: 2018-12-30; 2017-10-09: 2018-12-30; 2017-10-09: 2018-12-30
2AI102PI01000-08155 | COCC:Welding/Bolting | [27 empty] | 2017-10-09: 2018-12-29; 2017-10-09: 2018-12-29; 2017-10-09: 2018-12-29; 2017-10-09: 2018-12-29; 2017-10-09: 2018-12-29
2AI102PI01000-08150 | COCC:Alignment/Fit-up | [27 empty] | 2017-10-09: 2018-12-28; 2017-10-09: 2018-12-28; 2017-10-09: 2018-12-28; 2017-10-09: 2018-12-28; 2017-10-09: 2018-12-28
2AI102PI01000-08145 | COCC: Installation of pipes | [27 empty] | 2017-10-09: 2018-12-29; 2017-10-09: 2018-12-29; 2017-10-09: 2018-12-29; 2017-10-09: 2018-12-29; 2017-10-09: 2018-12-29
2AI102PI01000-08141 | COCC: Metallic (CS/LTCS) Piping Works | [27 empty] | 2017-10-09: 2019-01-12; 2017-10-09: 2019-01-12; 2017-10-09: 2019-01-12; 2017-10-09: 2019-01-12; 2017-10-09: 2019-01-12
2AI102PI01000 | UG Piping works | [27 empty] | 2017-10-09: 2019-01-12; 2017-10-09: 2019-01-12; 2017-10-09: 2019-01-12; 2017-10-09: 2019-01-12; 2017-10-09: 2019-01-12
2AI102PC04100-08005 | EOF:Lux testing | [29 empty] | 2018-01-04 | 2018-01-04 | 2018-01-04 | 2018-01-04 | 2018-01-04 | 2018-01-04 | 2018-01-04 | 2018-01-04 | 2018-01-04 | 2018-01-04 | 2018-01-04 | 2018-01-04 | 2018-01-04 | 2018-01-04 | 2018-01-04 | 2018-01-04 | 2018-01-04
2AI102PC04100-08001 | EOF:Continuity & IR testing | [25 empty] | 2017-09-12 | 2017-09-12 | 2017-09-12 | 2017-09-12 | 2017-09-12 | 2017-09-12 | 2017-09-12 | 2017-09-12 | 2017-09-12 | 2017-09-12 | 2017-09-12 | 2017-09-12 | 2017-09-12 | 2017-09-12 | 2017-09-12 | 2017-09-12 | 2017-09-12 | 2017-09-12 | 2017-09-12 | 2017-09-12 | 2017-09-12
2AI102PC04100-08000 | EOF SS 52-SUBST-303 : Lighting & Small Power | [29 empty] | 2018-01-04 | 2018-01-04 | 2018-01-04 | 2018-01-04 | 2018-01-04 | 2018-01-04 | 2018-01-04 | 2018-01-04 | 2018-01-04 | 2018-01-04 | 2018-01-04 | 2018-01-04 | 2018-01-04 | 2018-01-04 | 2018-01-04 | 2018-01-04 | 2018-01-04
2AI102PC04100 | EOF SS 52-SUBST-303 : Lighting & Small Power | [29 empty] | 2018-01-04 | 2018-01-04 | 2018-01-04 | 2018-01-04 | 2018-01-04 | 2018-01-04 | 2018-01-04 | 2018-01-04 | 2018-01-04 | 2018-01-04 | 2018-01-04 | 2018-01-04 | 2018-01-04 | 2018-01-04 | 2018-01-04 | 2018-01-04 | 2018-01-04
2AI102PC04000-08010 | EOF SS 52-SUBST-303 : Energize EDG 52-R-303
2AI102PC04000-08001 | EOF: GCP Testing, Switch Gear Testing
2AI102PC04000-08000 | EOF SS 52-SUBST-303 : Energize EDG 52-R-303
2AI102PC04000 | EOF SS 52-SUBST-303 : Energize EDG 52-R-303
2AI102PC03900-08030 | EOF: Energisation of Substation 52-SUBST-303
2AI102PC03900-08020 | EOF: Energisation of Substation 52-SUBST-302
2AI102PC03900-08015 | EOF: Cable Termination
2AI102PC03900-08010 | EOF: Cable Termination
2AI102PC03900-08005 | EOF:Incoming HV cables hipot testing
2AI102PC03900-08001 | EOF:Incoming cables IR and continuity test
2AI102PC03900-08000 | EOF SS 52-SUBST-303 : Electrical Tie-ins for Permanent Power & Energize
2AI102PC03900 | EOF SS 52-SUBST-303 : Electrical Tie-ins for Permanent Power & Energize
2AI102PC03700-08010 | EOF:BDV Testing
2AI102PC03700-08005 | EOF:Functional Test
2AI102PC03700-08001 | EOF:IR testing/WR testing/Turns ratio testing
2AI102PC03700-08000 | EOF SS 52-SUBST-303 : Transformer Testing
2AI102PC03700 | EOF SS 52-SUBST-303 : Transformer Testing
2AI102PC03600-08010 | EOF:Discharging test
2AI102PC03600-08005 | EOF:Charging test
2AI102PC03600-08001 | EOF:Polarity check
2AI102PC03600-08000 | EOF SS 52-SUBST-303 : 110V AC UPS
2AI102PC03600 | EOF SS 52-SUBST-303 : 110V AC UPS
2AI102PC03400-08025 | EOF: Stability Testing
2AI102PC03400-08020 | EOF: Hi-pot Test
2AI102PC03400-08015 | EOF Primary Injection Testing
2AI102PC03400-08010 | EOF: Relay & Functional Testing
2AI102PC03400-08005 | EOF: IR, Ductor testing
2AI102PC03400-08001 | EOF: CT,PT Testing
2AI102PC03400-08000 | EOF SS 52-SUBST-303 : LV Switchgear testing
2AI102PC03400 | EOF SS 52-SUBST-303 : LV Switchgear testing
2AI102PC03300-08010 | EOF:Discharging test
2AI102PC03300-08005 | EOF:Charging test
2AI102PC03300-08001 | EOF:Polarity check
2AI102PC03300-08000 | EOF SS 52-SUBST-303 : 24V DC Battery Charger
2AI102PC03300 | EOF SS 52-SUBST-303 : 24V DC Battery Charger
2AI102PC03200-08025 | EOF: Stability Testing
2AI102PC03200-08020 | EOF: Hi-pot Test
2AI102PC03200-08015 | EOF Primary Injection Testing
2AI102PC03200-08010 | EOF: Relay & Functional Testing
2AI102PC03200-08005 | EOF: IR, Ductor testing
2AI102PC03200-08001 | EOF: CT,PT,Breaker Testing
2AI102PC03200-08000 | EOF SS 52-SUBST-303 : HV Switchgear testing
2AI102PC03200 | EOF SS 52-SUBST-303 : HV Switchgear testing
2AI102PC03100-08005 | EOF:Earth resistance measurement
2AI102PC03100-08001 | EOF:Continuity testing
2AI102PC03100-08000 | EOF SS 52-SUBST-303 : SS Earthing & Lightning
2AI102PC03100 | EOF SS 52-SUBST-303 : SS Earthing & Lightning
2AI102PC03000-08010 | EOF:Discharging test
2AI102PC03000-08005 | EOF:Charging test
2AI102PC03000-08001 | EOF:Polarity check
2AI102PC03000-08000 | EOF SS 52-SUBST-303 : 110V DC Battery Charger
2AI102PC03000 | EOF SS 52-SUBST-303 : 110V DC Battery Charger
2AI102PC02100-08010 | EOF SS 52-SUBST-301 : Energize EDG 50-R-301 | [29 empty] | 2018-01-04: 2019-03-28; 2018-01-04: 2019-03-28; 2018-01-04: 2019-03-28
2AI102PC02100-08001 | GCP Testing, Switch Gear Testing | [29 empty] | 2018-01-04: 2019-03-15; 2018-01-04: 2019-03-15; 2018-01-04: 2019-03-15
2AI102PC02100-08000 | EOF SS 52-SUBST-301 : Energize EDG 50-R-301 | [29 empty] | 2018-01-04: 2019-03-28; 2018-01-04: 2019-03-28; 2018-01-04: 2019-03-28
2AI102PC02100 | EOF SS 52-SUBST-301 : Energize EDG 50-R-301 | [29 empty] | 2018-01-04: 2019-03-28; 2018-01-04: 2019-03-28; 2018-01-04: 2019-03-28
2AI102PC02000-08005 | EOF:Lux testing | [29 empty] | 2017-12-21 | 2017-12-21 | 2017-12-21 | 2017-12-21 | 2017-12-21 | 2017-12-21 | 2017-12-21 | 2017-12-21 | 2017-12-21 | 2017-12-21 | 2017-12-21 | 2017-12-21 | 2017-12-21 | 2017-12-21 | 2017-12-21 | 2017-12-21 | 2017-12-21
2AI102PC02000-08001 | EOF:Continuity & IR testing | [29 empty] | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03
2AI102PC02000-08000 | EOF SS 52-SUBST-301 : Lighting & Small Power | [29 empty] | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03
2AI102PC02000 | EOF SS 52-SUBST-301 : Lighting & Small Power | [29 empty] | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03
2AI102PC01900-08045 | EOF: Ready for Energisation of Substation 52-SUBST-301 | [29 empty] | 2018-01-03: 2019-01-13; 2018-01-03: 2019-01-13; 2018-01-03: 2019-01-13; 2018-01-03: 2019-01-13; 2018-01-03: 2019-01-13
2AI102PC01900-08010 | Cable Termination | [29 empty] | 2018-01-03: 2018-09-29; 2018-01-03: 2018-09-29; 2018-01-03: 2018-09-29; 2018-01-03: 2018-09-29; 2018-01-03: 2018-09-29; 2018-01-03: 2018-09-29; 2018-01-03: 2018-09-29
2AI102PC01900-08005 | EOF:Incoming HV cables hipot testing | [37 empty] | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28
2AI102PC01900-08001 | EOF:Incoming cables IR and continuity test | [37 empty] | 2018-09-27 | 2018-09-27 | 2018-09-27 | 2018-09-27 | 2018-09-27 | 2018-09-27 | 2018-09-27 | 2018-09-27 | 2018-09-27
2AI102PC01900-08000 | EOF SS 52-SUBST-301 : Electrical Tie-ins for Permanent Power & Energize | [37 empty] | 2018-09-27: 2019-01-13; 2018-09-27: 2019-01-13; 2018-09-27: 2019-01-13; 2018-09-27: 2019-01-13; 2018-09-27: 2019-01-13
2AI102PC01900 | EOF SS 52-SUBST-301 : Electrical Tie-ins for Permanent Power & Energize | [37 empty] | 2018-09-27: 2019-01-13; 2018-09-27: 2019-01-13; 2018-09-27: 2019-01-13; 2018-09-27: 2019-01-13; 2018-09-27: 2019-01-13
2AI102PC01700-08010 | EOF:BDV Testing | [39 empty] | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30
2AI102PC01700-08005 | EOF:Functional Test | [37 empty] | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28
2AI102PC01700-08001 | EOF:IR testing/WR testing/Turns ratio testing | [37 empty] | 2018-09-27 | 2018-09-27 | 2018-09-27 | 2018-09-27 | 2018-09-27 | 2018-09-27 | 2018-09-27 | 2018-09-27 | 2018-09-27
2AI102PC01700-08000 | EOF SS 52-SUBST-301 : Transformer Testing | [39 empty] | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30
2AI102PC01700 | EOF SS 52-SUBST-301 : Transformer Testing | [39 empty] | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30
2AI102PC01600-08010 | EOF:Discharging test | [39 empty] | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30
2AI102PC01600-08005 | EOF:Charging test | [37 empty] | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28
2AI102PC01600-08001 | EOF:Polarity check | [37 empty] | 2018-09-27 | 2018-09-27 | 2018-09-27 | 2018-09-27 | 2018-09-27 | 2018-09-27 | 2018-09-27 | 2018-09-27 | 2018-09-27
2AI102PC01600-08000 | EOF SS 52-SUBST-301 : 110V AC UPS | [39 empty] | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30
2AI102PC01600 | EOF SS 52-SUBST-301 : 110V AC UPS | [39 empty] | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30
2AI102PC01400-08025 | EOF: Stability Testing | [39 empty] | 2018-10-01 | 2018-10-01 | 2018-10-01 | 2018-10-01 | 2018-10-01 | 2018-10-01 | 2018-10-01
2AI102PC01400-08020 | EOF: Hi-pot Test | [39 empty] | 2018-11-07 | 2018-11-07 | 2018-11-07 | 2018-11-07 | 2018-11-07 | 2018-11-07 | 2018-11-07
2AI102PC01400-08015 | EOF Primary Injection Testing | [39 empty] | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30
2AI102PC01400-08010 | EOF: Relay & Functional Testing | [39 empty] | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30
2AI102PC01400-08005 | EOF: IR, Ductor testing | [39 empty] | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28
2AI102PC01400-08001 | EOF: CT,PT Testing | [37 empty] | 2018-09-26 | 2018-09-26 | 2018-09-26 | 2018-09-26 | 2018-09-26 | 2018-09-26 | 2018-09-26 | 2018-09-26 | 2018-09-26
2AI102PC01400-08000 | EOF SS 52-SUBST-301 : LV Switchgear testing | [39 empty] | 2018-11-07 | 2018-11-07 | 2018-11-07 | 2018-11-07 | 2018-11-07 | 2018-11-07 | 2018-11-07
2AI102PC01400 | EOF SS 52-SUBST-301 : LV Switchgear testing | [39 empty] | 2018-11-07 | 2018-11-07 | 2018-11-07 | 2018-11-07 | 2018-11-07 | 2018-11-07 | 2018-11-07
2AI102PC01300-08010 | EOF:Discharging test | [39 empty] | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30
2AI102PC01300-08005 | EOF:Charging test | [39 empty] | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28
2AI102PC01300-08001 | EOF:Polarity check | [37 empty] | 2018-09-27 | 2018-09-27 | 2018-09-27 | 2018-09-27 | 2018-09-27 | 2018-09-27 | 2018-09-27 | 2018-09-27 | 2018-09-27
2AI102PC01300-08000 | EOF SS 52-SUBST-301 : 24V DC Battery Charger | [39 empty] | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30
2AI102PC01300 | EOF SS 52-SUBST-301 : 24V DC Battery Charger | [39 empty] | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30
2AI102PC01200-08035 | EOF: Stability Testing | [39 empty] | 2018-10-01 | 2018-10-01 | 2018-10-01 | 2018-10-01 | 2018-10-01 | 2018-10-01 | 2018-10-01
2AI102PC01200-08034 | EOF: Hi-pot Test | [39 empty] | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30
2AI102PC01200-08025 | EOF Primary Injection Testing | [39 empty] | 2018-09-29 | 2018-09-29 | 2018-09-29 | 2018-09-29 | 2018-09-29 | 2018-09-29 | 2018-09-29
2AI102PC01200-08015 | EOF: Relay & Functional Testing | [39 empty] | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28
2AI102PC01200-08010 | EOF: IR, Ductor testing | [37 empty] | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28
2AI102PC01200-08005 | EOF: CT,PT,Breaker Testing | [37 empty] | 2018-09-26 | 2018-09-26 | 2018-09-26 | 2018-09-26 | 2018-09-26 | 2018-09-26 | 2018-09-26 | 2018-09-26 | 2018-09-26
2AI102PC01200-08000 | EOF SS 52-SUBST-301 : HV Switchgear testing | [39 empty] | 2018-10-01 | 2018-10-01 | 2018-10-01 | 2018-10-01 | 2018-10-01 | 2018-10-01 | 2018-10-01
2AI102PC01200 | EOF SS 52-SUBST-301 : HV Switchgear testing | [39 empty] | 2018-10-01 | 2018-10-01 | 2018-10-01 | 2018-10-01 | 2018-10-01 | 2018-10-01 | 2018-10-01
2AI102PC01100-08005 | EOF:Earth resistance measurement | [39 empty] | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30
2AI102PC01100-08001 | EOF:Continuity testing | [37 empty] | 2018-09-26 | 2018-09-26 | 2018-09-26 | 2018-09-26 | 2018-09-26 | 2018-09-26 | 2018-09-26 | 2018-09-26 | 2018-09-26
2AI102PC01100-08000 | EOF SS 52-SUBST-301 : SS Earthing & Lightning | [39 empty] | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30
2AI102PC01100 | EOF SS 52-SUBST-301 : SS Earthing & Lightning | [39 empty] | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30
2AI102PC01000-08010 | EOF:Discharging test | [39 empty] | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30
2AI102PC01000-08005 | EOF:Charging test | [37 empty] | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28
2AI102PC01000-08001 | EOF:Polarity check | [37 empty] | 2018-09-27 | 2018-09-27 | 2018-09-27 | 2018-09-27 | 2018-09-27 | 2018-09-27 | 2018-09-27 | 2018-09-27 | 2018-09-27
2AI102PC01000-08000 | EOF SS 52-SUBST-301 : 110V DC Battery Charger | [39 empty] | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30
2AI102PC01000 | EOF SS 52-SUBST-301 : 110V DC Battery Charger | [39 empty] | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30
2AI102IC01100-08141 | Fire Alarm Cable Laying from 52-SUBST-301 | [39 empty] | 2018-10-05 | 2018-10-05 | 2018-10-05 | 2018-10-05 | 2018-10-05 | 2018-10-05 | 2018-10-05
2AI102IC01100-08100 | EOF: Issue AFC Drawings FIRE ALARM CABLE WORKS | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AI102IC01100 | EOF: AG cable laying, Tubing, Field, Inline Instrument Installation, Cable Glading & Termination Instrument Works | [31 empty] | 2018-02-27: 2018-10-05; 2018-02-27: 2018-10-05; 2018-02-27: 2018-10-05; 2018-02-27: 2018-10-05; 2018-02-27: 2018-10-05; 2018-02-27: 2018-10-05; 2018-02-27: 2018-10-05
2AI102IC01000-08141 | Instrument Cable laying from 52-SUBST-302 to Storage Tank Junction Boxes | [31 empty] | 2018-02-27: 2019-04-10
2AI102IC01000-08100 | EOF: Issue AFC Drawings INSTRUMENTATION CABLE FROM SUBSTATION | [23 empty] | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01
2AI102IC01000 | EOF: Instrument Cable from Substation | [23 empty] | 2017-06-01: 2019-04-10
2AI102EL01100-08142 | LV Power Cable laying from 50-SUBST-001 | [23 empty] | 2017-06-01: 2019-03-06; 2017-06-01: 2019-03-06; 2017-06-01: 2019-03-06
2AI102EL01100-08141 | LV Power Cable laying from 52-SUBST-302 | [23 empty] | 2017-06-01: 2019-04-10
2AI102EL01100-08100 | EOF: Issue AFC Drawings POWER CABLE FROM SUBSTATION | [27 empty] | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18
2AI102EL01100 | EOF: AG Cable laying, CP, DB'S/JB, Panels, Lighting Pole, Fixtures, Cable Glaning & Termination Electrical Works | [27 empty] | 2017-10-18: 2019-04-10
2AI102EL01000-08141 | EOF: Power Cable Laying from from MG-1 Substation to 52-SUBST-301 | [29 empty] | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06
2AI102EL01000-08100 | EOF: Issue AFC Drawings POWER CABLE BETWEEN SUBSTATION | [23 empty] | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07
2AI102EL01000 | EOF: Power Cable Between Substation | [29 empty] | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06
2AI102CV28200-08141 | COCC: Touch-up painting of Structures / Shelters
2AI102CV28200-08000 | COCC: Touch-up painting of Structures / Shelters
2AI102CV28200 | EOF: Touch-up painting of Structures
2AI102CV01600-08150 | COCC: Backfill / Compaction | [31 empty] | 2018-01-28 | 2018-01-28 | 2018-01-28 | 2018-01-28 | 2018-01-28 | 2018-01-28 | 2018-01-28 | 2018-01-28 | 2018-01-28 | 2018-01-28 | 2018-01-28 | 2018-01-28 | 2018-01-28 | 2018-01-28 | 2018-01-28
2AI102CV01600-08142 | COCC: Paving Work
2AI102CV01600-08141 | COCC: Roads including Crossing Works
2AI102CV01600-08140 | COCC: Coating | [31 empty] | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27
2AI102CV01600-08130 | COCC: Concrete Pouring | [29 empty] | 2018-01-13 | 2018-01-13 | 2018-01-13 | 2018-01-13 | 2018-01-13 | 2018-01-13 | 2018-01-13 | 2018-01-13 | 2018-01-13 | 2018-01-13 | 2018-01-13 | 2018-01-13 | 2018-01-13 | 2018-01-13 | 2018-01-13 | 2018-01-13 | 2018-01-13
2AI102CV01600-08120 | COCC: Rebar, Formwork & Install Pipe sleeves | [29 empty] | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20
2AI102CV01600-08115 | COCC: Laying of Interlock Paving blocks
2AI102CV01600-08110 | COCC: Subgrade and Blinding | [29 empty] | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22
2AI102CV01600-08105 | COCC: Sand/gatch layer
2AI102CV01600-08100 | COCC: Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material | [29 empty] | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22
2AI102CV01600-08095 | COCC: Install Kerb stone
2AI102CV01600-08090 | COCC: Final Coat (incl. Road marking)
2AI102CV01600-08085 | COCC: Compacted Sub base preparation
2AI102CV01600-08080 | COCC: Asphalt Wearing course
2AI102CV01600-08075 | COCC: Excavation/trimming
2AI102CV01600-08070 | COCC: Asphalt binding course
2AI102CV01600-08065 | COCC: Finishing | [29 empty] | 2018-01-22: 2019-03-18; 2018-01-22: 2019-03-18; 2018-01-22: 2019-03-18
2AI102CV01600-08060 | COCC: Asphalt base course
2AI102CV01600-08055 | COCC: Concrete Pouring | [29 empty] | 2018-01-22: 2019-03-18; 2018-01-22: 2019-03-18; 2018-01-22: 2019-03-18
2AI102CV01600-08050 | COCC: Base Preparation & Kerbing (incl. Filling/Comp with Gatch & Crushed gravel layer)
2AI102CV01600-08045 | COCC: Reinforcement | [29 empty] | 2018-01-22: 2019-03-16; 2018-01-22: 2019-03-16; 2018-01-22: 2019-03-16
2AI102CV01600-08040 | COCC: Re-combaction of sub-grade
2AI102CV01600-08035 | COCC: Formwork | [29 empty] | 2018-01-22: 2019-03-13; 2018-01-22: 2019-03-13; 2018-01-22: 2019-03-13
2AI102CV01600-08030 | COCC: Finish Grading (Crushed gravel layer & Grading Top soil)
2AI102CV01600-08025 | COCC: Sub base & Base preparation | [29 empty] | 2018-01-22: 2019-03-10; 2018-01-22: 2019-03-10; 2018-01-22: 2019-03-10
2AI102CV01600-08020 | COCC: Fine Grading (Gatch Subgrade)
2AI102CV01600-08010 | COCC: Rough Grading for Road Works
2AI102CV01600 | COCC :Roads, Crossing & Paving Works
2AI102CV01500-08123 | EOF: EIT items Misc. Foundation
2AI102CV01500-08122 | EOF: Pipe Supports & Pipe Sleepers | [29 empty] | 2018-01-22: 2018-10-30; 2018-01-22: 2018-10-30; 2018-01-22: 2018-10-30; 2018-01-22: 2018-10-30; 2018-01-22: 2018-10-30; 2018-01-22: 2018-10-30; 2018-01-22: 2018-10-30
2AI102CV01500-08121 | EOF: HSE Safety Equipments & Safety Misc. Foundation
2AI102CV01500-08020 | EOF: EIT items Misc. Foundation
2AI102CV01500-08015 | EOF: Pipe Supports / Pipe Sleepers | [29 empty] | 2018-01-22: 2018-10-30; 2018-01-22: 2018-10-30; 2018-01-22: 2018-10-30; 2018-01-22: 2018-10-30; 2018-01-22: 2018-10-30; 2018-01-22: 2018-10-30; 2018-01-22: 2018-10-30
2AI102CV01500-08000 | EOF: HSE Safety Equipments & Safety Misc. Foundation
2AI102CV01500 | EOF: UG, Trenches & other Civil Works
2AI102CV01400-08045 | Wall & Roof Cladding | [19 empty] | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12
2AI102CV01400-08040 | Wall & Roof Cladding | [19 empty] | 2017-02-24 | 2017-02-24 | 2017-02-24 | 2017-02-24 | 2017-02-24 | 2017-02-24 | 2017-02-24 | 2017-02-24 | 2017-02-24 | 2017-02-24 | 2017-02-24 | 2017-02-24 | 2017-02-24 | 2017-02-24 | 2017-02-24 | 2017-02-24 | 2017-02-24 | 2017-02-24 | 2017-02-24 | 2017-02-24 | 2017-02-24 | 2017-02-24 | 2017-02-24 | 2017-02-24 | 2017-02-24 | 2017-02-24 | 2017-02-24
2AI102CV01400-08035 | Installation of gratings/handrail/stair/ladder | [19 empty] | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08
2AI102CV01400-08030 | Installation of gratings/handrail/stair/ladder | [19 empty] | 2017-02-24 | 2017-02-24 | 2017-02-24 | 2017-02-24 | 2017-02-24 | 2017-02-24 | 2017-02-24 | 2017-02-24 | 2017-02-24 | 2017-02-24 | 2017-02-24 | 2017-02-24 | 2017-02-24 | 2017-02-24 | 2017-02-24 | 2017-02-24 | 2017-02-24 | 2017-02-24 | 2017-02-24 | 2017-02-24 | 2017-02-24 | 2017-02-24 | 2017-02-24 | 2017-02-24 | 2017-02-24 | 2017-02-24 | 2017-02-24
2AI102CV01400-08025 | EOF:Grouting of Filling Manifold Auto Sampling Package (52-Z-306) Shelter | [19 empty] | 2017-02-24 | 2017-02-24 | 2017-02-24 | 2017-02-24 | 2017-02-24 | 2017-02-24 | 2017-02-24 | 2017-02-24 | 2017-02-24 | 2017-02-24 | 2017-02-24 | 2017-02-24 | 2017-02-24 | 2017-02-24 | 2017-02-24 | 2017-02-24 | 2017-02-24 | 2017-02-24 | 2017-02-24 | 2017-02-24 | 2017-02-24 | 2017-02-24 | 2017-02-24 | 2017-02-24 | 2017-02-24 | 2017-02-24 | 2017-02-24
2AI102CV01400-08020 | EOF:Alignment & Bolting/Torqueing for Filling Manifold Auto Sampling Package (52-Z-306) Shelter | [19 empty] | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15
2AI102CV01400-08015 | EOF:Installation of Str. Steel for Filling Manifold Auto Sampling Package (52-Z-306) Shelter | [19 empty] | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13
2AI102CV01400-08011 | EOF:Grouting of Filling Manifold Auto Sampling Package (52-Z-305) Shelter | [19 empty] | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15
2AI102CV01400-08010 | EOF: Filling Manifold Auto Sampling Package (52-Z-306) Shelter Erection | [19 empty] | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12
2AI102CV01400-08006 | EOF:Alignment & Bolting/Torqueing for Filling Manifold Auto Sampling Package (52-Z-305) Shelter | [19 empty] | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13
2AI102CV01400-08005 | EOF: Filling Manifold Auto Sampling Package (52-Z-305) Shelter Erection | [19 empty] | 2017-02-24 | 2017-02-24 | 2017-02-24 | 2017-02-24 | 2017-02-24 | 2017-02-24 | 2017-02-24 | 2017-02-24 | 2017-02-24 | 2017-02-24 | 2017-02-24 | 2017-02-24 | 2017-02-24 | 2017-02-24 | 2017-02-24 | 2017-02-24 | 2017-02-24 | 2017-02-24 | 2017-02-24 | 2017-02-24 | 2017-02-24 | 2017-02-24 | 2017-02-24 | 2017-02-24 | 2017-02-24 | 2017-02-24 | 2017-02-24
2AI102CV01400-08001 | EOF:Installation of Str. Steel for Filling Manifold Auto Sampling Package (52-Z-305) Shelter | [17 empty] | 2017-01-26 | 2017-01-26 | 2017-01-26 | 2017-01-26 | 2017-01-26 | 2017-01-26 | 2017-01-26 | 2017-01-26 | 2017-01-26 | 2017-01-26 | 2017-01-26 | 2017-01-26 | 2017-01-26 | 2017-01-26 | 2017-01-26 | 2017-01-26 | 2017-01-26 | 2017-01-26 | 2017-01-26 | 2017-01-26 | 2017-01-26 | 2017-01-26 | 2017-01-26 | 2017-01-26 | 2017-01-26 | 2017-01-26 | 2017-01-26 | 2017-01-26 | 2017-01-26
2AI102CV01400 | EOF: Filling Manifold Auto Sampling Package (52-Z-305 & 306) Shelter Erection | [19 empty] | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12
2AI102CV01100-08055 | EOF:Backfilling & Compaction for Fnd | [17 empty] | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13
2AI102CV01100-08050 | EOF:Concrete Potection for Fnd | [17 empty] | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13
2AI102CV01100-08046 | EOF:Concrete Pouring - for Pedestal | [17 empty] | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13
2AI102CV01100-08045 | EOF:Rebar, Formwork, Install Embedments for Pedestal | [17 empty] | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13
2AI102CV01100-08041 | EOF:Concrete Pouring - for Footing | [17 empty] | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13
2AI102CV01100-08040 | EOF:Rebar, Formwork for Footing | [17 empty] | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13
2AI102CV01100-08035 | EOF:Blinding/PCC for Fnd | [17 empty] | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13
2AI102CV01100-08030 | EOF:Survey Marking, Excavation & Subgrade | [17 empty] | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13
2AI102CV01100-08025 | EOF:Backfilling & Compaction for Fnd | [17 empty] | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13
2AI102CV01100-08020 | EOF:Concrete Potection for Fnd | [17 empty] | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13
2AI102CV01100-08016 | EOF:Concrete Pouring - for Pedestal | [17 empty] | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13
2AI102CV01100-08015 | EOF:Rebar, Formwork, Install Embedments for Pedestal | [17 empty] | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13
2AI102CV01100-08011 | EOF:Concrete Pouring - for Footing | [17 empty] | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13
2AI102CV01100-08010 | EOF:Rebar, Formwork for Footing | [17 empty] | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13
2AI102CV01100-08006 | EOF:Blinding/PCC for Fnd | [17 empty] | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13
2AI102CV01100-08005 | EOF: Filling Manifold Auto Sampling Package (52-Z-306) Shelter Foundation | [17 empty] | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13
2AI102CV01100-08001 | EOF:Survey Marking, Excavation & Subgrade | [17 empty] | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13
2AI102CV01100-08000 | EOF: Filling Manifold Auto Sampling Package (52-Z-305) Shelter Foundation | [17 empty] | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13
2AI102CV01100 | EOF: Filling Manifold Auto Sampling Package (52-Z-305 & 306) Shelter Foundation | [17 empty] | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13
2AI101TE01100-08016 | EOF:Cable Termination | [33 empty] | 2018-04-25 | 2018-04-25 | 2018-04-25 | 2018-04-25 | 2018-04-25 | 2018-04-25 | 2018-04-25 | 2018-04-25 | 2018-04-25 | 2018-04-25 | 2018-04-25 | 2018-04-25 | 2018-04-25
2AI101TE01100-08015 | EOF: Cable Termination | [33 empty] | 2018-04-25 | 2018-04-25 | 2018-04-25 | 2018-04-25 | 2018-04-25 | 2018-04-25 | 2018-04-25 | 2018-04-25 | 2018-04-25 | 2018-04-25 | 2018-04-25 | 2018-04-25 | 2018-04-25
2AI101TE01100-08010 | EOF:CCTV & Security System Installation | [31 empty] | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07
2AI101TE01100-08006 | EOF:Telecom Equipments Installation | [31 empty] | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07
2AI101TE01100-08005 | EOF: Telecom Equipments / CCTV & Security System Installation | [31 empty] | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07
2AI101TE01100-08001 | EOF:AG Cable laying | [33 empty] | 2018-05-09 | 2018-05-09 | 2018-05-09 | 2018-05-09 | 2018-05-09 | 2018-05-09 | 2018-05-09 | 2018-05-09 | 2018-05-09 | 2018-05-09 | 2018-05-09 | 2018-05-09 | 2018-05-09
2AI101TE01100-08000 | EOF: AG Cable laying | [33 empty] | 2018-05-09 | 2018-05-09 | 2018-05-09 | 2018-05-09 | 2018-05-09 | 2018-05-09 | 2018-05-09 | 2018-05-09 | 2018-05-09 | 2018-05-09 | 2018-05-09 | 2018-05-09 | 2018-05-09
2AI101TE01100 | EOF: AG Cable laying, Telecom Equipments / CCTV & Security System Installation & Cable Termination | [33 empty] | 2018-05-09 | 2018-05-09 | 2018-05-09 | 2018-05-09 | 2018-05-09 | 2018-05-09 | 2018-05-09 | 2018-05-09 | 2018-05-09 | 2018-05-09 | 2018-05-09 | 2018-05-09 | 2018-05-09
2AI101TE01000-08015 | EOF: Splicing of telecom cable | [35 empty] | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02
2AI101TE01000-08005 | EOF: Cable laying | [35 empty] | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02
2AI101TE01000-08001 | EOF: Laying Cable Duct | [35 empty] | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02
2AI101TE01000-08000 | EOF:Cable Glading & Termination | [35 empty] | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02
2AI101TE01000 | EOF:UG Telecom cable works | [35 empty] | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02
2AI101PI18100-08005 | EOF: Touch-Up Painting for Metallic (SS/SDSS)
2AI101PI18100-08001 | EOF: Touch-Up Painting for Metallic (CS/LTCS)
2AI101PI18100-08000 | EOF: Touch-up painting of Piping
2AI101PI18100 | EOF: Touch-up painting of Piping
2AI101PI01300-08515 | EOF:Flange management | [35 empty] | 2018-07-02: 2019-04-10
2AI101PI01300-08510 | EOF:Reinstatement
2AI101PI01300-08505 | EOF:Pressure testing & Approval | [35 empty] | 2018-07-02: 2019-03-22; 2018-07-02: 2019-03-22; 2018-07-02: 2019-03-22
2AI101PI01300-08500 | EOF:Test pack preparation & Ready for Test | [35 empty] | 2018-07-02: 2019-03-21; 2018-07-02: 2019-03-21; 2018-07-02: 2019-03-21
2AI101PI01300-08495 | EOF:Flange management | [35 empty] | 2018-07-02: 2019-04-06
2AI101PI01300-08490 | EOF:Reinstatement
2AI101PI01300-08485 | EOF:Pressure testing & Approval | [35 empty] | 2018-07-02: 2019-04-02
2AI101PI01300-08480 | EOF:Test pack preparation & Ready for Test | [35 empty] | 2018-07-02: 2019-03-28; 2018-07-02: 2019-03-28; 2018-07-02: 2019-03-28
2AI101PI01300-08475 | EOF:Flange management | [35 empty] | 2018-07-02: 2019-04-11
2AI101PI01300-08470 | EOF:Reinstatement
2AI101PI01300-08465 | EOF:Pressure testing & Approval | [35 empty] | 2018-07-02: 2019-04-07
2AI101PI01300-08460 | EOF:Test pack preparation & Ready for Test | [35 empty] | 2018-07-02: 2019-04-06
2AI101PI01300-08455 | EOF:Flange management | [35 empty] | 2018-07-02: 2019-03-08; 2018-07-02: 2019-03-08; 2018-07-02: 2019-03-08
2AI101PI01300-08450 | EOF:Reinstatement
2AI101PI01300-08445 | EOF:Pressure testing & Approval | [35 empty] | 2018-07-02: 2019-03-05; 2018-07-02: 2019-03-05; 2018-07-02: 2019-03-05
2AI101PI01300-08440 | EOF:Test pack preparation & Ready for Test | [35 empty] | 2018-07-02: 2019-03-05; 2018-07-02: 2019-03-05; 2018-07-02: 2019-03-05
2AI101PI01300-08435 | EOF:Flange management | [35 empty] | 2018-07-02: 2019-03-06; 2018-07-02: 2019-03-06; 2018-07-02: 2019-03-06
2AI101PI01300-08430 | EOF:Reinstatement
2AI101PI01300-08425 | EOF:Pressure testing & Approval | [35 empty] | 2018-07-02: 2019-03-05; 2018-07-02: 2019-03-05; 2018-07-02: 2019-03-05
2AI101PI01300-08420 | EOF:Test pack preparation & Ready for Test | [35 empty] | 2018-07-02: 2019-03-02; 2018-07-02: 2019-03-02; 2018-07-02: 2019-03-02
2AI101PI01300-08415 | EOF:Flange management | [35 empty] | 2018-07-02: 2019-04-10
2AI101PI01300-08410 | EOF:Reinstatement
2AI101PI01300-08405 | EOF:Pressure testing & Approval | [35 empty] | 2018-07-02: 2019-03-20; 2018-07-02: 2019-03-20; 2018-07-02: 2019-03-20
2AI101PI01300-08400 | EOF:Test pack preparation & Ready for Test | [35 empty] | 2018-07-02: 2019-03-19; 2018-07-02: 2019-03-19; 2018-07-02: 2019-03-19
2AI101PI01300-08106 | EOF:Flange management | [35 empty] | 2018-07-02: 2019-02-06; 2018-07-02: 2019-02-06; 2018-07-02: 2019-02-06
2AI101PI01300-08105 | EOF:Reinstatement | [35 empty] | 2018-07-02: 2019-02-06; 2018-07-02: 2019-02-06; 2018-07-02: 2019-02-06
2AI101PI01300-08101 | EOF:Pressure testing & Approval | [35 empty] | 2018-07-02: 2019-02-06; 2018-07-02: 2019-02-06; 2018-07-02: 2019-02-06
2AI101PI01300-08100 | EOF:Test pack preparation & Ready for Test | [35 empty] | 2018-07-02: 2019-02-06; 2018-07-02: 2019-02-06; 2018-07-02: 2019-02-06
2AI101PI01300-08096 | EOF:Flange management | [35 empty] | 2018-07-02: 2019-01-10; 2018-07-02: 2019-01-10; 2018-07-02: 2019-01-10; 2018-07-02: 2019-01-10; 2018-07-02: 2019-01-10
2AI101PI01300-08095 | EOF:Reinstatement
2AI101PI01300-08091 | EOF:Pressure testing & Approval | [35 empty] | 2018-07-02: 2019-01-07; 2018-07-02: 2019-01-07; 2018-07-02: 2019-01-07; 2018-07-02: 2019-01-07; 2018-07-02: 2019-01-07
2AI101PI01300-08090 | EOF:Test pack preparation & Ready for Test | [35 empty] | 2018-07-02: 2019-01-07; 2018-07-02: 2019-01-07; 2018-07-02: 2019-01-07; 2018-07-02: 2019-01-07; 2018-07-02: 2019-01-07
2AI101PI01300-08086 | EOF:Flange management | [35 empty] | 2018-07-02: 2019-04-09
2AI101PI01300-08085 | EOF:Reinstatement | [35 empty] | 2018-07-02: 2019-04-09
2AI101PI01300-08081 | EOF:Pressure testing & Approval | [35 empty] | 2018-07-02: 2019-04-07
2AI101PI01300-08080 | EOF:Test pack preparation & Ready for Test | [35 empty] | 2018-07-02: 2019-04-07
2AI101PI01300-08076 | EOF:Flange management | [35 empty] | 2018-07-02: 2019-01-19; 2018-07-02: 2019-01-19; 2018-07-02: 2019-01-19; 2018-07-02: 2019-01-19; 2018-07-02: 2019-01-19
2AI101PI01300-08075 | EOF:Reinstatement
2AI101PI01300-08071 | EOF:Pressure testing & Approval | [35 empty] | 2018-07-02: 2019-01-16; 2018-07-02: 2019-01-16; 2018-07-02: 2019-01-16; 2018-07-02: 2019-01-16; 2018-07-02: 2019-01-16
2AI101PI01300-08070 | EOF:Test pack preparation & Ready for Test | [35 empty] | 2018-07-02: 2019-01-15; 2018-07-02: 2019-01-15; 2018-07-02: 2019-01-15; 2018-07-02: 2019-01-15; 2018-07-02: 2019-01-15
2AI101PI01300-08066 | EOF:Flange management | [35 empty] | 2018-07-02: 2019-03-25; 2018-07-02: 2019-03-25; 2018-07-02: 2019-03-25
2AI101PI01300-08065 | EOF:Reinstatement
2AI101PI01300-08061 | EOF:Pressure testing & Approval | [35 empty] | 2018-07-02: 2019-03-22; 2018-07-02: 2019-03-22; 2018-07-02: 2019-03-22
2AI101PI01300-08060 | EOF:Test pack preparation & Ready for Test | [35 empty] | 2018-07-02: 2019-03-21; 2018-07-02: 2019-03-21; 2018-07-02: 2019-03-21
2AI101PI01300-08056 | EOF:Flange management | [35 empty] | 2018-07-02: 2019-03-20; 2018-07-02: 2019-03-20; 2018-07-02: 2019-03-20
2AI101PI01300-08055 | EOF:Reinstatement
2AI101PI01300-08051 | EOF:Pressure testing & Approval | [35 empty] | 2018-07-02: 2019-03-17; 2018-07-02: 2019-03-17; 2018-07-02: 2019-03-17
2AI101PI01300-08050 | EOF:Test pack preparation & Ready for Test | [35 empty] | 2018-07-02: 2019-03-06; 2018-07-02: 2019-03-06; 2018-07-02: 2019-03-06
2AI101PI01300-08046 | EOF:Flange management | [35 empty] | 2018-07-02: 2019-04-01
2AI101PI01300-08045 | EOF:Reinstatement
2AI101PI01300-08041 | EOF:Pressure testing & Approval | [35 empty] | 2018-07-02: 2019-03-29; 2018-07-02: 2019-03-29; 2018-07-02: 2019-03-29
2AI101PI01300-08040 | EOF:Test pack preparation & Ready for Test | [35 empty] | 2018-07-02: 2019-03-27; 2018-07-02: 2019-03-27; 2018-07-02: 2019-03-27
2AI101PI01300-08026 | EOF:Flange management | [35 empty] | 2018-07-02: 2019-03-16; 2018-07-02: 2019-03-16; 2018-07-02: 2019-03-16
2AI101PI01300-08025 | EOF:Reinstatement | [35 empty] | 2018-07-02: 2019-03-14; 2018-07-02: 2019-03-14; 2018-07-02: 2019-03-14
2AI101PI01300-08021 | EOF:Pressure testing & Approval | [35 empty] | 2018-07-02: 2019-03-12; 2018-07-02: 2019-03-12; 2018-07-02: 2019-03-12
2AI101PI01300-08020 | EOF:Test pack preparation & Ready for Test | [35 empty] | 2018-07-02: 2019-03-12; 2018-07-02: 2019-03-12; 2018-07-02: 2019-03-12
2AI101PI01300-08017 | EOF:Flange management | [35 empty] | 2018-07-02: 2019-03-30
2AI101PI01300-08016 | EOF:Reinstatement | [35 empty] | 2018-07-02: 2019-03-29
2AI101PI01300-08012 | EOF:Pressure testing & Approval | [35 empty] | 2018-07-02: 2019-04-10
2AI101PI01300-08011 | EOF:Test pack preparation & Ready for Test | [35 empty] | 2018-07-02: 2019-04-10
2AI101PI01300-08010 | EOF: Pressure testing for Metallic (SS/SDSS) | [35 empty] | 2018-07-02: 2019-03-16; 2018-07-02: 2019-03-16; 2018-07-02: 2019-03-16
2AI101PI01300-08007 | EOF:Flange management | [35 empty] | 2018-07-02: 2019-04-16
2AI101PI01300-08006 | EOF:Reinstatement | [35 empty] | 2018-07-02: 2019-04-16
2AI101PI01300-08005 | EOF: Pressure testing for Metallic (CS/LTCS)
2AI101PI01300-08002 | EOF:Pressure testing & Approval | [35 empty] | 2018-07-02: 2019-04-16
2AI101PI01300-08001 | EOF:Test pack preparation & Ready for Test | [35 empty] | 2018-07-02: 2019-04-16
2AI101PI01300-08000 | EOF: Pressure testing for Non Metallic | [35 empty] | 2018-07-02: 2019-04-16
2AI101PI01300 | EOF: Hydrotesting
2AI101PI01100-08545 | EOF:Install piping valves | [35 empty] | 2018-07-02: 2019-01-24; 2018-07-02: 2019-01-24; 2018-07-02: 2019-01-24; 2018-07-02: 2019-01-24; 2018-07-02: 2019-01-24
2AI101PI01100-08540 | EOF:Install Permanent Supporting for Pipes | [35 empty] | 2018-07-02: 2019-01-25; 2018-07-02: 2019-01-25; 2018-07-02: 2019-01-25; 2018-07-02: 2019-01-25; 2018-07-02: 2019-01-25
2AI101PI01100-08535 | EOF:NDE/PWHT/QC Checks of Pipes | [35 empty] | 2018-07-02: 2019-01-24; 2018-07-02: 2019-01-24; 2018-07-02: 2019-01-24; 2018-07-02: 2019-01-24; 2018-07-02: 2019-01-24
2AI101PI01100-08531 | EOF:Welding/Bolting of Pipes | [35 empty] | 2018-07-02: 2019-01-22; 2018-07-02: 2019-01-22; 2018-07-02: 2019-01-22; 2018-07-02: 2019-01-22; 2018-07-02: 2019-01-22
2AI101PI01100-08530 | EOF:Alignment/Fit-up | [35 empty] | 2018-07-02: 2019-01-20; 2018-07-02: 2019-01-20; 2018-07-02: 2019-01-20; 2018-07-02: 2019-01-20; 2018-07-02: 2019-01-20
2AI101PI01100-08525 | EOF:Installation of pipes | [35 empty] | 2018-07-02: 2019-01-15; 2018-07-02: 2019-01-15; 2018-07-02: 2019-01-15; 2018-07-02: 2019-01-15; 2018-07-02: 2019-01-15
2AI101PI01100-08520 | EOF:Install piping valves | [35 empty] | 2018-07-02: 2019-04-02
2AI101PI01100-08515 | EOF:Install Permanent Supporting for Pipes | [35 empty] | 2018-07-02: 2019-03-30
2AI101PI01100-08510 | EOF:NDE/PWHT/QC Checks of Pipes | [35 empty] | 2018-07-02: 2019-03-30
2AI101PI01100-08506 | EOF:Welding/Bolting of Pipes | [35 empty] | 2018-07-02: 2019-04-10
2AI101PI01100-08505 | EOF:Alignment/Fit-up | [35 empty] | 2018-07-02: 2019-04-10
2AI101PI01100-08500 | EOF:Installation of pipes | [35 empty] | 2018-07-02: 2019-04-10
2AI101PI01100-08495 | EOF:Install piping valves | [35 empty] | 2018-07-02: 2019-01-06; 2018-07-02: 2019-01-06; 2018-07-02: 2019-01-06; 2018-07-02: 2019-01-06; 2018-07-02: 2019-01-06
2AI101PI01100-08490 | EOF:Install Permanent Supporting for Pipes | [35 empty] | 2018-07-02: 2019-01-05; 2018-07-02: 2019-01-05; 2018-07-02: 2019-01-05; 2018-07-02: 2019-01-05; 2018-07-02: 2019-01-05
2AI101PI01100-08485 | EOF:NDE/PWHT/QC Checks of Pipes | [35 empty] | 2018-07-02: 2019-01-04; 2018-07-02: 2019-01-04; 2018-07-02: 2019-01-04; 2018-07-02: 2019-01-04; 2018-07-02: 2019-01-04
2AI101PI01100-08481 | EOF:Welding/Bolting of Pipes | [35 empty] | 2018-07-02: 2018-12-05; 2018-07-02: 2018-12-05; 2018-07-02: 2018-12-05; 2018-07-02: 2018-12-05; 2018-07-02: 2018-12-05
2AI101PI01100-08480 | EOF:Alignment/Fit-up | [35 empty] | 2018-07-02: 2018-12-05; 2018-07-02: 2018-12-05; 2018-07-02: 2018-12-05; 2018-07-02: 2018-12-05; 2018-07-02: 2018-12-05
2AI101PI01100-08475 | EOF:Installation of pipes | [39 empty] | 2018-11-07 | 2018-11-07 | 2018-11-07 | 2018-11-07 | 2018-11-07 | 2018-11-07 | 2018-11-07
2AI101PI01100-08470 | EOF:Install piping valves | [35 empty] | 2018-07-02: 2019-01-27; 2018-07-02: 2019-01-27; 2018-07-02: 2019-01-27
2AI101PI01100-08465 | EOF:Install Permanent Supporting for Pipes | [35 empty] | 2018-07-02: 2019-01-09; 2018-07-02: 2019-01-09; 2018-07-02: 2019-01-09; 2018-07-02: 2019-01-09; 2018-07-02: 2019-01-09
2AI101PI01100-08460 | EOF:NDE/PWHT/QC Checks of Pipes | [35 empty] | 2018-07-02: 2019-01-27; 2018-07-02: 2019-01-27; 2018-07-02: 2019-01-27
2AI101PI01100-08456 | EOF:Welding/Bolting of Pipes | [35 empty] | 2018-07-02: 2019-01-16; 2018-07-02: 2019-01-16; 2018-07-02: 2019-01-16; 2018-07-02: 2019-01-16; 2018-07-02: 2019-01-16
2AI101PI01100-08455 | EOF:Alignment/Fit-up | [35 empty] | 2018-07-02: 2019-01-14; 2018-07-02: 2019-01-14; 2018-07-02: 2019-01-14; 2018-07-02: 2019-01-14; 2018-07-02: 2019-01-14
2AI101PI01100-08450 | EOF:Installation of pipes | [35 empty] | 2018-07-02: 2019-01-10; 2018-07-02: 2019-01-10; 2018-07-02: 2019-01-10; 2018-07-02: 2019-01-10; 2018-07-02: 2019-01-10
2AI101PI01100-08445 | EOF:Install piping valves | [35 empty] | 2018-07-02: 2019-01-15; 2018-07-02: 2019-01-15; 2018-07-02: 2019-01-15; 2018-07-02: 2019-01-15; 2018-07-02: 2019-01-15
2AI101PI01100-08440 | EOF:Install Permanent Supporting for Pipes | [35 empty] | 2018-07-02: 2019-01-14; 2018-07-02: 2019-01-14; 2018-07-02: 2019-01-14; 2018-07-02: 2019-01-14; 2018-07-02: 2019-01-14
2AI101PI01100-08435 | EOF:NDE/PWHT/QC Checks of Pipes | [35 empty] | 2018-07-02: 2019-01-17; 2018-07-02: 2019-01-17; 2018-07-02: 2019-01-17; 2018-07-02: 2019-01-17; 2018-07-02: 2019-01-17
2AI101PI01100-08431 | EOF:Welding/Bolting of Pipes | [35 empty] | 2018-07-02: 2019-01-14; 2018-07-02: 2019-01-14; 2018-07-02: 2019-01-14; 2018-07-02: 2019-01-14; 2018-07-02: 2019-01-14
2AI101PI01100-08430 | EOF:Alignment/Fit-up | [35 empty] | 2018-07-02: 2019-01-13; 2018-07-02: 2019-01-13; 2018-07-02: 2019-01-13; 2018-07-02: 2019-01-13; 2018-07-02: 2019-01-13
2AI101PI01100-08425 | EOF:Installation of pipes | [35 empty] | 2018-07-02: 2019-01-12; 2018-07-02: 2019-01-12; 2018-07-02: 2019-01-12; 2018-07-02: 2019-01-12; 2018-07-02: 2019-01-12
2AI101PI01100-08420 | EOF:Install piping valves | [35 empty] | 2018-07-02: 2019-01-04; 2018-07-02: 2019-01-04; 2018-07-02: 2019-01-04; 2018-07-02: 2019-01-04; 2018-07-02: 2019-01-04
2AI101PI01100-08415 | EOF:Install Permanent Supporting for Pipes | [35 empty] | 2018-07-02: 2019-01-01; 2018-07-02: 2019-01-01; 2018-07-02: 2019-01-01; 2018-07-02: 2019-01-01; 2018-07-02: 2019-01-01
2AI101PI01100-08410 | EOF:NDE/PWHT/QC Checks of Pipes | [35 empty] | 2018-07-02: 2018-12-29; 2018-07-02: 2018-12-29; 2018-07-02: 2018-12-29; 2018-07-02: 2018-12-29; 2018-07-02: 2018-12-29
2AI101PI01100-08406 | EOF:Welding/Bolting of Pipes | [35 empty] | 2018-07-02: 2019-01-09; 2018-07-02: 2019-01-09; 2018-07-02: 2019-01-09; 2018-07-02: 2019-01-09; 2018-07-02: 2019-01-09
2AI101PI01100-08405 | EOF:Alignment/Fit-up | [35 empty] | 2018-07-02: 2019-01-09; 2018-07-02: 2019-01-09; 2018-07-02: 2019-01-09; 2018-07-02: 2019-01-09; 2018-07-02: 2019-01-09
2AI101PI01100-08400 | EOF:Installation of pipes | [35 empty] | 2018-07-02: 2019-01-09; 2018-07-02: 2019-01-09; 2018-07-02: 2019-01-09; 2018-07-02: 2019-01-09; 2018-07-02: 2019-01-09
2AI101PI01100-08395 | EOF:Install piping valves | [37 empty] | 2018-09-05 | 2018-09-05 | 2018-09-05 | 2018-09-05 | 2018-09-05 | 2018-09-05 | 2018-09-05 | 2018-09-05 | 2018-09-05
2AI101PI01100-08390 | EOF:Install Permanent Supporting for Pipes | [37 empty] | 2018-09-05 | 2018-09-05 | 2018-09-05 | 2018-09-05 | 2018-09-05 | 2018-09-05 | 2018-09-05 | 2018-09-05 | 2018-09-05
2AI101PI01100-08385 | EOF:NDE/PWHT/QC Checks of Pipes | [37 empty] | 2018-09-05 | 2018-09-05 | 2018-09-05 | 2018-09-05 | 2018-09-05 | 2018-09-05 | 2018-09-05 | 2018-09-05 | 2018-09-05
2AI101PI01100-08381 | EOF:Welding/Bolting of Pipes | [37 empty] | 2018-09-05: 2019-01-09; 2018-09-05: 2019-01-09; 2018-09-05: 2019-01-09; 2018-09-05: 2019-01-09; 2018-09-05: 2019-01-09
2AI101PI01100-08380 | EOF:Alignment/Fit-up | [37 empty] | 2018-09-05: 2019-01-09; 2018-09-05: 2019-01-09; 2018-09-05: 2019-01-09; 2018-09-05: 2019-01-09; 2018-09-05: 2019-01-09
2AI101PI01100-08375 | EOF:Installation of pipes | [37 empty] | 2018-09-05: 2019-01-09; 2018-09-05: 2019-01-09; 2018-09-05: 2019-01-09; 2018-09-05: 2019-01-09; 2018-09-05: 2019-01-09
2AI101PI01100-08370 | EOF:Install piping valves | [37 empty] | 2018-09-05: 2019-02-06; 2018-09-05: 2019-02-06; 2018-09-05: 2019-02-06
2AI101PI01100-08365 | EOF:Install Permanent Supporting for Pipes | [37 empty] | 2018-09-05: 2019-02-06; 2018-09-05: 2019-02-06; 2018-09-05: 2019-02-06
2AI101PI01100-08360 | EOF:NDE/PWHT/QC Checks of Pipes | [37 empty] | 2018-09-05: 2019-02-06; 2018-09-05: 2019-02-06; 2018-09-05: 2019-02-06
2AI101PI01100-08356 | EOF:Welding/Bolting of Pipes | [37 empty] | 2018-09-05: 2019-01-10; 2018-09-05: 2019-01-10; 2018-09-05: 2019-01-10; 2018-09-05: 2019-01-10; 2018-09-05: 2019-01-10
2AI101PI01100-08355 | EOF:Alignment/Fit-up | [37 empty] | 2018-09-05: 2019-01-10; 2018-09-05: 2019-01-10; 2018-09-05: 2019-01-10; 2018-09-05: 2019-01-10; 2018-09-05: 2019-01-10
2AI101PI01100-08350 | EOF:Installation of pipes | [37 empty] | 2018-09-05: 2019-01-09; 2018-09-05: 2019-01-09; 2018-09-05: 2019-01-09; 2018-09-05: 2019-01-09; 2018-09-05: 2019-01-09
2AI101PI01100-08345 | EOF:Install piping valves | [37 empty] | 2018-09-05: 2019-04-16
2AI101PI01100-08340 | EOF:Install Permanent Supporting for Pipes | [37 empty] | 2018-09-05: 2019-02-06; 2018-09-05: 2019-02-06; 2018-09-05: 2019-02-06
2AI101PI01100-08335 | EOF:NDE/PWHT/QC Checks of Pipes | [37 empty] | 2018-09-05: 2019-02-06; 2018-09-05: 2019-02-06; 2018-09-05: 2019-02-06
2AI101PI01100-08331 | EOF:Welding/Bolting of Pipes | [39 empty] | 2018-10-10 | 2018-10-10 | 2018-10-10 | 2018-10-10 | 2018-10-10 | 2018-10-10 | 2018-10-10
2AI101PI01100-08330 | EOF:Alignment/Fit-up | [39 empty] | 2018-10-10 | 2018-10-10 | 2018-10-10 | 2018-10-10 | 2018-10-10 | 2018-10-10 | 2018-10-10
2AI101PI01100-08325 | EOF:Installation of pipes | [39 empty] | 2018-10-15 | 2018-10-15 | 2018-10-15 | 2018-10-15 | 2018-10-15 | 2018-10-15 | 2018-10-15
2AI101PI01100-08320 | EOF:Install piping valves | [37 empty] | 2018-09-05: 2019-03-20; 2018-09-05: 2019-03-20; 2018-09-05: 2019-03-20
2AI101PI01100-08315 | EOF:Install Permanent Supporting for Pipes | [37 empty] | 2018-09-05: 2018-12-05; 2018-09-05: 2018-12-05; 2018-09-05: 2018-12-05; 2018-09-05: 2018-12-05; 2018-09-05: 2018-12-05
2AI101PI01100-08310 | EOF:NDE/PWHT/QC Checks of Pipes | [37 empty] | 2018-09-05: 2019-03-15; 2018-09-05: 2019-03-15; 2018-09-05: 2019-03-15
2AI101PI01100-08306 | EOF:Welding/Bolting of Pipes | [37 empty] | 2018-08-24 | 2018-08-24 | 2018-08-24 | 2018-08-24 | 2018-08-24 | 2018-08-24 | 2018-08-24 | 2018-08-24 | 2018-08-24
2AI101PI01100-08305 | EOF:Alignment/Fit-up | [37 empty] | 2018-08-24 | 2018-08-24 | 2018-08-24 | 2018-08-24 | 2018-08-24 | 2018-08-24 | 2018-08-24 | 2018-08-24 | 2018-08-24
2AI101PI01100-08300 | EOF:Installation of pipes | [37 empty] | 2018-08-24: 2019-03-13; 2018-08-24: 2019-03-13; 2018-08-24: 2019-03-13
2AI101PI01100-08295 | EOF:Install piping valves | [37 empty] | 2018-08-24: 2019-03-15; 2018-08-24: 2019-03-15; 2018-08-24: 2019-03-15
2AI101PI01100-08290 | EOF:Install Permanent Supporting for Pipes | [37 empty] | 2018-08-24: 2019-03-14; 2018-08-24: 2019-03-14; 2018-08-24: 2019-03-14
2AI101PI01100-08285 | EOF:NDE/PWHT/QC Checks of Pipes | [37 empty] | 2018-08-24: 2019-03-14; 2018-08-24: 2019-03-14; 2018-08-24: 2019-03-14
2AI101PI01100-08281 | EOF:Welding/Bolting of Pipes | [37 empty] | 2018-08-24: 2019-03-12; 2018-08-24: 2019-03-12; 2018-08-24: 2019-03-12
2AI101PI01100-08280 | EOF:Alignment/Fit-up | [37 empty] | 2018-08-24: 2019-03-12; 2018-08-24: 2019-03-12; 2018-08-24: 2019-03-12
2AI101PI01100-08275 | EOF:Installation of pipes | [37 empty] | 2018-08-24: 2019-03-11; 2018-08-24: 2019-03-11; 2018-08-24: 2019-03-11
2AI101PI01100-08270 | EOF:Install piping valves | [37 empty] | 2018-08-24: 2019-03-16; 2018-08-24: 2019-03-16; 2018-08-24: 2019-03-16
2AI101PI01100-08265 | EOF:Install Permanent Supporting for Pipes | [37 empty] | 2018-08-24: 2019-01-09; 2018-08-24: 2019-01-09; 2018-08-24: 2019-01-09; 2018-08-24: 2019-01-09; 2018-08-24: 2019-01-09
2AI101PI01100-08260 | EOF:NDE/PWHT/QC Checks of Pipes | [37 empty] | 2018-08-24: 2019-03-15; 2018-08-24: 2019-03-15; 2018-08-24: 2019-03-15
2AI101PI01100-08256 | EOF:Welding/Bolting of Pipes | [37 empty] | 2018-08-24: 2019-03-15; 2018-08-24: 2019-03-15; 2018-08-24: 2019-03-15
2AI101PI01100-08255 | EOF:Alignment/Fit-up | [37 empty] | 2018-08-24: 2019-03-14; 2018-08-24: 2019-03-14; 2018-08-24: 2019-03-14
2AI101PI01100-08250 | EOF:Installation of pipes | [37 empty] | 2018-08-24: 2019-03-12; 2018-08-24: 2019-03-12; 2018-08-24: 2019-03-12
2AI101PI01100-08245 | EOF:Install piping valves | [37 empty] | 2018-08-24: 2018-11-30; 2018-08-24: 2018-11-30; 2018-08-24: 2018-11-30; 2018-08-24: 2018-11-30; 2018-08-24: 2018-11-30
2AI101PI01100-08240 | EOF:Install Permanent Supporting for Pipes | [37 empty] | 2018-08-24: 2018-12-05; 2018-08-24: 2018-12-05; 2018-08-24: 2018-12-05; 2018-08-24: 2018-12-05; 2018-08-24: 2018-12-05
2AI101PI01100-08235 | EOF:NDE/PWHT/QC Checks of Pipes | [37 empty] | 2018-08-24: 2018-11-30; 2018-08-24: 2018-11-30; 2018-08-24: 2018-11-30; 2018-08-24: 2018-11-30; 2018-08-24: 2018-11-30
2AI101PI01100-08231 | EOF:Welding/Bolting of Pipes | [37 empty] | 2018-08-24: 2018-12-10; 2018-08-24: 2018-12-10; 2018-08-24: 2018-12-10; 2018-08-24: 2018-12-10; 2018-08-24: 2018-12-10
2AI101PI01100-08230 | EOF:Alignment/Fit-up | [37 empty] | 2018-08-24: 2018-12-08; 2018-08-24: 2018-12-08; 2018-08-24: 2018-12-08; 2018-08-24: 2018-12-08; 2018-08-24: 2018-12-08
2AI101PI01100-08225 | EOF:Installation of pipes | [37 empty] | 2018-08-24: 2018-12-05; 2018-08-24: 2018-12-05; 2018-08-24: 2018-12-05; 2018-08-24: 2018-12-05; 2018-08-24: 2018-12-05
2AI101PI01100-08220 | EOF:Install piping valves | [37 empty] | 2018-08-24: 2019-01-19; 2018-08-24: 2019-01-19; 2018-08-24: 2019-01-19; 2018-08-24: 2019-01-19; 2018-08-24: 2019-01-19
2AI101PI01100-08215 | EOF:Install Permanent Supporting for Pipes | [37 empty] | 2018-08-24: 2019-01-09; 2018-08-24: 2019-01-09; 2018-08-24: 2019-01-09; 2018-08-24: 2019-01-09; 2018-08-24: 2019-01-09
2AI101PI01100-08210 | EOF:NDE/PWHT/QC Checks of Pipes | [37 empty] | 2018-08-24: 2019-01-17; 2018-08-24: 2019-01-17; 2018-08-24: 2019-01-17; 2018-08-24: 2019-01-17; 2018-08-24: 2019-01-17
2AI101PI01100-08206 | EOF:Welding/Bolting of Pipes | [37 empty] | 2018-08-24: 2019-01-14; 2018-08-24: 2019-01-14; 2018-08-24: 2019-01-14; 2018-08-24: 2019-01-14; 2018-08-24: 2019-01-14
2AI101PI01100-08205 | EOF:Alignment/Fit-up | [37 empty] | 2018-08-24: 2019-01-13; 2018-08-24: 2019-01-13; 2018-08-24: 2019-01-13; 2018-08-24: 2019-01-13; 2018-08-24: 2019-01-13
2AI101PI01100-08200 | EOF:Installation of pipes | [37 empty] | 2018-08-24: 2019-01-12; 2018-08-24: 2019-01-12; 2018-08-24: 2019-01-12; 2018-08-24: 2019-01-12; 2018-08-24: 2019-01-12
2AI101PI01100-08195 | EOF:Install piping valves | [37 empty] | 2018-08-24: 2019-04-10
2AI101PI01100-08190 | EOF:Install Permanent Supporting for Pipes | [37 empty] | 2018-08-24: 2019-01-09; 2018-08-24: 2019-01-09; 2018-08-24: 2019-01-09; 2018-08-24: 2019-01-09; 2018-08-24: 2019-01-09
2AI101PI01100-08185 | EOF:NDE/PWHT/QC Checks of Pipes | [37 empty] | 2018-08-24: 2019-03-29; 2018-08-24: 2019-03-29; 2018-08-24: 2019-03-29
2AI101PI01100-08181 | EOF:Welding/Bolting of Pipes | [37 empty] | 2018-08-24: 2019-03-29; 2018-08-24: 2019-03-29; 2018-08-24: 2019-03-29
2AI101PI01100-08180 | EOF:Alignment/Fit-up | [37 empty] | 2018-08-24: 2019-03-28; 2018-08-24: 2019-03-28; 2018-08-24: 2019-03-28
2AI101PI01100-08175 | EOF:Installation of pipes | [37 empty] | 2018-08-24: 2019-03-26; 2018-08-24: 2019-03-26; 2018-08-24: 2019-03-26
2AI101PI01100-08170 | EOF:Install piping valves | [37 empty] | 2018-08-24: 2019-03-13; 2018-08-24: 2019-03-13; 2018-08-24: 2019-03-13
2AI101PI01100-08165 | EOF:Install Permanent Supporting for Pipes | [37 empty] | 2018-08-24: 2018-12-05; 2018-08-24: 2018-12-05; 2018-08-24: 2018-12-05; 2018-08-24: 2018-12-05; 2018-08-24: 2018-12-05
2AI101PI01100-08160 | EOF:NDE/PWHT/QC Checks of Pipes | [37 empty] | 2018-08-24: 2019-01-31; 2018-08-24: 2019-01-31; 2018-08-24: 2019-01-31
2AI101PI01100-08156 | EOF:Welding/Bolting of Pipes | [37 empty] | 2018-08-24: 2019-01-30; 2018-08-24: 2019-01-30; 2018-08-24: 2019-01-30
2AI101PI01100-08155 | EOF:Alignment/Fit-up | [37 empty] | 2018-08-24: 2019-01-28; 2018-08-24: 2019-01-28; 2018-08-24: 2019-01-28
2AI101PI01100-08150 | EOF:Installation of pipes | [37 empty] | 2018-08-24: 2019-01-26; 2018-08-24: 2019-01-26; 2018-08-24: 2019-01-26
2AI101PI01100-08145 | EOF:Install piping valves | [37 empty] | 2018-08-24: 2018-12-12; 2018-08-24: 2018-12-12; 2018-08-24: 2018-12-12; 2018-08-24: 2018-12-12; 2018-08-24: 2018-12-12
2AI101PI01100-08140 | EOF:Install Permanent Supporting for Pipes | [37 empty] | 2018-08-24: 2018-12-07; 2018-08-24: 2018-12-07; 2018-08-24: 2018-12-07; 2018-08-24: 2018-12-07; 2018-08-24: 2018-12-07
2AI101PI01100-08135 | EOF:NDE/PWHT/QC Checks of Pipes | [37 empty] | 2018-08-24: 2018-12-13; 2018-08-24: 2018-12-13; 2018-08-24: 2018-12-13; 2018-08-24: 2018-12-13; 2018-08-24: 2018-12-13
2AI101PI01100-08131 | EOF:Welding/Bolting of Pipes | [37 empty] | 2018-08-24: 2018-11-30; 2018-08-24: 2018-11-30; 2018-08-24: 2018-11-30; 2018-08-24: 2018-11-30; 2018-08-24: 2018-11-30
2AI101PI01100-08130 | EOF:Alignment/Fit-up | [37 empty] | 2018-08-24: 2018-11-25; 2018-08-24: 2018-11-25; 2018-08-24: 2018-11-25; 2018-08-24: 2018-11-25; 2018-08-24: 2018-11-25
2AI101PI01100-08125 | EOF:Installation of pipes | [37 empty] | 2018-08-24: 2018-12-05; 2018-08-24: 2018-12-05; 2018-08-24: 2018-12-05; 2018-08-24: 2018-12-05; 2018-08-24: 2018-12-05
2AI101PI01100-08120 | EOF:Install piping valves | [37 empty] | 2018-08-24: 2018-12-15; 2018-08-24: 2018-12-15; 2018-08-24: 2018-12-15; 2018-08-24: 2018-12-15; 2018-08-24: 2018-12-15
2AI101PI01100-08115 | EOF:Install Permanent Supporting for Pipes | [37 empty] | 2018-08-24: 2018-12-09; 2018-08-24: 2018-12-09; 2018-08-24: 2018-12-09; 2018-08-24: 2018-12-09; 2018-08-24: 2018-12-09
2AI101PI01100-08110 | EOF:NDE/PWHT/QC Checks of Pipes | [37 empty] | 2018-08-24: 2018-12-09; 2018-08-24: 2018-12-09; 2018-08-24: 2018-12-09; 2018-08-24: 2018-12-09; 2018-08-24: 2018-12-09
2AI101PI01100-08106 | EOF:Welding/Bolting of Pipes | [37 empty] | 2018-08-24: 2018-12-04; 2018-08-24: 2018-12-04; 2018-08-24: 2018-12-04; 2018-08-24: 2018-12-04; 2018-08-24: 2018-12-04
2AI101PI01100-08105 | EOF:Alignment/Fit-up | [37 empty] | 2018-08-24: 2018-11-30; 2018-08-24: 2018-11-30; 2018-08-24: 2018-11-30; 2018-08-24: 2018-11-30; 2018-08-24: 2018-11-30
2AI101PI01100-08100 | EOF:Installation of pipes | [37 empty] | 2018-08-24: 2018-11-25; 2018-08-24: 2018-11-25; 2018-08-24: 2018-11-25; 2018-08-24: 2018-11-25; 2018-08-24: 2018-11-25
2AI101PI01100-08070 | EOF:Install piping valves | [37 empty] | 2018-08-24: 2019-03-29; 2018-08-24: 2019-03-29; 2018-08-24: 2019-03-29
2AI101PI01100-08065 | EOF:Install Permanent Supporting for Pipes | [37 empty] | 2018-08-24: 2019-03-28; 2018-08-24: 2019-03-28; 2018-08-24: 2019-03-28
2AI101PI01100-08060 | EOF:NDE/PWHT/QC Checks of Pipes | [37 empty] | 2018-08-24: 2019-03-26; 2018-08-24: 2019-03-26; 2018-08-24: 2019-03-26
2AI101PI01100-08056 | EOF:Welding/Bolting of Pipes | [37 empty] | 2018-08-24: 2019-03-24; 2018-08-24: 2019-03-24; 2018-08-24: 2019-03-24
2AI101PI01100-08055 | EOF:Alignment/Fit-up | [37 empty] | 2018-08-24: 2019-03-22; 2018-08-24: 2019-03-22; 2018-08-24: 2019-03-22
2AI101PI01100-08050 | EOF:Installation of pipes | [37 empty] | 2018-08-24: 2019-03-20; 2018-08-24: 2019-03-20; 2018-08-24: 2019-03-20
2AI101PI01100-08045 | EOF:Install piping valves | [37 empty] | 2018-08-24: 2019-02-06; 2018-08-24: 2019-02-06; 2018-08-24: 2019-02-06
2AI101PI01100-08040 | EOF:Install Permanent Supporting for Pipes | [37 empty] | 2018-08-24: 2019-02-06; 2018-08-24: 2019-02-06; 2018-08-24: 2019-02-06
2AI101PI01100-08035 | EOF:NDE/PWHT/QC Checks of Pipes | [37 empty] | 2018-08-24: 2019-02-06; 2018-08-24: 2019-02-06; 2018-08-24: 2019-02-06
2AI101PI01100-08031 | EOF:Welding/Bolting of Pipes | [37 empty] | 2018-08-24: 2019-02-06; 2018-08-24: 2019-02-06; 2018-08-24: 2019-02-06
2AI101PI01100-08030 | EOF:Alignment/Fit-up | [37 empty] | 2018-08-24: 2019-02-06; 2018-08-24: 2019-02-06; 2018-08-24: 2019-02-06
2AI101PI01100-08025 | EOF:Installation of pipes | [37 empty] | 2018-08-24: 2019-02-06; 2018-08-24: 2019-02-06; 2018-08-24: 2019-02-06
2AI101PI01100-08020 | EOF:Install piping valves | [37 empty] | 2018-08-24: 2019-03-18; 2018-08-24: 2019-03-18; 2018-08-24: 2019-03-18
2AI101PI01100-08016 | EOF:Install Permanent Supporting for Pipes | [37 empty] | 2018-08-24: 2019-02-26; 2018-08-24: 2019-02-26; 2018-08-24: 2019-02-26
2AI101PI01100-08011 | EOF:NDE/PWHT/QC Checks of Pipes | [37 empty] | 2018-08-24: 2019-02-26; 2018-08-24: 2019-02-26; 2018-08-24: 2019-02-26
2AI101PI01100-08010 | EOF: AG Piping works for Metallic (SS/SDSS) | [37 empty] | 2018-08-24: 2019-03-29; 2018-08-24: 2019-03-29; 2018-08-24: 2019-03-29
2AI101PI01100-08006 | EOF: Jointing/Fusion welding | [37 empty] | 2018-08-24: 2019-02-26; 2018-08-24: 2019-02-26; 2018-08-24: 2019-02-26
2AI101PI01100-08005 | EOF: AG Piping works Metallic (CS/LTCS) | [37 empty] | 2018-08-24: 2019-04-16
2AI101PI01100-08001 | EOF:Installation of pipes | [37 empty] | 2018-08-24: 2019-02-25; 2018-08-24: 2019-02-25; 2018-08-24: 2019-02-25
2AI101PI01100-08000 | EOF: AG Piping works for Non Metallic | [37 empty] | 2018-08-24: 2019-03-18; 2018-08-24: 2019-03-18; 2018-08-24: 2019-03-18
2AI101PI01100 | EOF: AG Piping works | [37 empty] | 2018-08-24: 2019-04-16
2AI101PI01000-08936 | EOF:Coating/Wrapping | [35 empty] | 2018-07-26 | 2018-07-26 | 2018-07-26 | 2018-07-26 | 2018-07-26 | 2018-07-26 | 2018-07-26 | 2018-07-26 | 2018-07-26 | 2018-07-26 | 2018-07-26
2AI101PI01000-08935 | EOF:NDE/PWHT/QC Checks of Pipes | [35 empty] | 2018-06-03 | 2018-06-03 | 2018-06-03 | 2018-06-03 | 2018-06-03 | 2018-06-03 | 2018-06-03 | 2018-06-03 | 2018-06-03 | 2018-06-03 | 2018-06-03
2AI101PI01000-08931 | EOF:Welding/Bolting of Pipes | [35 empty] | 2018-06-02 | 2018-06-02 | 2018-06-02 | 2018-06-02 | 2018-06-02 | 2018-06-02 | 2018-06-02 | 2018-06-02 | 2018-06-02 | 2018-06-02 | 2018-06-02
2AI101PI01000-08930 | EOF:Alignment/Fit-up | [35 empty] | 2018-05-29 | 2018-05-29 | 2018-05-29 | 2018-05-29 | 2018-05-29 | 2018-05-29 | 2018-05-29 | 2018-05-29 | 2018-05-29 | 2018-05-29 | 2018-05-29
2AI101PI01000-08925 | EOF:Installation of pipes | [35 empty] | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26
2AI101PI01000-08326 | EOF:Coating/Wrapping | [35 empty] | 2018-05-26: 2019-02-21; 2018-05-26: 2019-02-21; 2018-05-26: 2019-02-21
2AI101PI01000-08325 | EOF:NDE/PWHT/QC Checks of Pipes | [35 empty] | 2018-05-26: 2019-01-08; 2018-05-26: 2019-01-08; 2018-05-26: 2019-01-08; 2018-05-26: 2019-01-08; 2018-05-26: 2019-01-08
2AI101PI01000-08321 | EOF:Welding/Bolting of Pipes | [35 empty] | 2018-05-26: 2019-01-05; 2018-05-26: 2019-01-05; 2018-05-26: 2019-01-05; 2018-05-26: 2019-01-05; 2018-05-26: 2019-01-05
2AI101PI01000-08320 | EOF:Alignment/Fit-up | [35 empty] | 2018-05-26: 2019-01-04; 2018-05-26: 2019-01-04; 2018-05-26: 2019-01-04; 2018-05-26: 2019-01-04; 2018-05-26: 2019-01-04
2AI101PI01000-08315 | EOF:Installation of pipes | [35 empty] | 2018-05-26: 2019-01-03; 2018-05-26: 2019-01-03; 2018-05-26: 2019-01-03; 2018-05-26: 2019-01-03; 2018-05-26: 2019-01-03
2AI101PI01000-08311 | EOF:Coating/Wrapping | [35 empty] | 2018-05-26: 2018-12-05; 2018-05-26: 2018-12-05; 2018-05-26: 2018-12-05; 2018-05-26: 2018-12-05; 2018-05-26: 2018-12-05
2AI101PI01000-08310 | EOF:NDE/PWHT/QC Checks of Pipes | [39 empty] | 2018-11-01 | 2018-11-01 | 2018-11-01 | 2018-11-01 | 2018-11-01 | 2018-11-01 | 2018-11-01
2AI101PI01000-08306 | EOF:Welding/Bolting of Pipes | [39 empty] | 2018-10-28 | 2018-10-28 | 2018-10-28 | 2018-10-28 | 2018-10-28 | 2018-10-28 | 2018-10-28
2AI101PI01000-08305 | EOF:Alignment/Fit-up | [39 empty] | 2018-10-19 | 2018-10-19 | 2018-10-19 | 2018-10-19 | 2018-10-19 | 2018-10-19 | 2018-10-19
2AI101PI01000-08300 | EOF:Installation of pipes | [39 empty] | 2018-10-19 | 2018-10-19 | 2018-10-19 | 2018-10-19 | 2018-10-19 | 2018-10-19 | 2018-10-19
2AI101PI01000-08296 | EOF:Coating/Wrapping | [35 empty] | 2018-05-26: 2018-12-28; 2018-05-26: 2018-12-28; 2018-05-26: 2018-12-28; 2018-05-26: 2018-12-28; 2018-05-26: 2018-12-28
2AI101PI01000-08295 | EOF:NDE/PWHT/QC Checks of Pipes | [39 empty] | 2018-11-01 | 2018-11-01 | 2018-11-01 | 2018-11-01 | 2018-11-01 | 2018-11-01 | 2018-11-01
2AI101PI01000-08291 | EOF:Welding/Bolting of Pipes | [39 empty] | 2018-10-30 | 2018-10-30 | 2018-10-30 | 2018-10-30 | 2018-10-30 | 2018-10-30 | 2018-10-30
2AI101PI01000-08290 | EOF:Alignment/Fit-up | [39 empty] | 2018-10-28 | 2018-10-28 | 2018-10-28 | 2018-10-28 | 2018-10-28 | 2018-10-28 | 2018-10-28
2AI101PI01000-08285 | EOF:Installation of pipes | [39 empty] | 2018-10-26 | 2018-10-26 | 2018-10-26 | 2018-10-26 | 2018-10-26 | 2018-10-26 | 2018-10-26
2AI101PI01000-08281 | EOF:Coating/Wrapping | [39 empty] | 2018-10-20 | 2018-10-20 | 2018-10-20 | 2018-10-20 | 2018-10-20 | 2018-10-20 | 2018-10-20
2AI101PI01000-08280 | EOF:NDE/PWHT/QC Checks of Pipes | [37 empty] | 2018-08-28 | 2018-08-28 | 2018-08-28 | 2018-08-28 | 2018-08-28 | 2018-08-28 | 2018-08-28 | 2018-08-28 | 2018-08-28
2AI101PI01000-08276 | EOF:Welding/Bolting of Pipes | [37 empty] | 2018-08-09 | 2018-08-09 | 2018-08-09 | 2018-08-09 | 2018-08-09 | 2018-08-09 | 2018-08-09 | 2018-08-09 | 2018-08-09
2AI101PI01000-08275 | EOF:Alignment/Fit-up | [37 empty] | 2018-08-09 | 2018-08-09 | 2018-08-09 | 2018-08-09 | 2018-08-09 | 2018-08-09 | 2018-08-09 | 2018-08-09 | 2018-08-09
2AI101PI01000-08270 | EOF:Installation of pipes | [35 empty] | 2018-07-20 | 2018-07-20 | 2018-07-20 | 2018-07-20 | 2018-07-20 | 2018-07-20 | 2018-07-20 | 2018-07-20 | 2018-07-20 | 2018-07-20 | 2018-07-20
2AI101PI01000-08266 | EOF:Coating/Wrapping | [35 empty] | 2018-07-08 | 2018-07-08 | 2018-07-08 | 2018-07-08 | 2018-07-08 | 2018-07-08 | 2018-07-08 | 2018-07-08 | 2018-07-08 | 2018-07-08 | 2018-07-08
2AI101PI01000-08265 | EOF:NDE/PWHT/QC Checks of Pipes | [33 empty] | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06
2AI101PI01000-08261 | EOF:Welding/Bolting of Pipes | [33 empty] | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05
2AI101PI01000-08260 | EOF:Alignment/Fit-up | [33 empty] | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04
2AI101PI01000-08255 | EOF:Installation of pipes | [31 empty] | 2018-03-07 | 2018-03-07 | 2018-03-07 | 2018-03-07 | 2018-03-07 | 2018-03-07 | 2018-03-07 | 2018-03-07 | 2018-03-07 | 2018-03-07 | 2018-03-07 | 2018-03-07 | 2018-03-07 | 2018-03-07 | 2018-03-07
2AI101PI01000-08251 | EOF:Coating/Wrapping | [35 empty] | 2018-07-08 | 2018-07-08 | 2018-07-08 | 2018-07-08 | 2018-07-08 | 2018-07-08 | 2018-07-08 | 2018-07-08 | 2018-07-08 | 2018-07-08 | 2018-07-08
2AI101PI01000-08250 | EOF:NDE/PWHT/QC Checks of Pipes | [33 empty] | 2018-04-26 | 2018-04-26 | 2018-04-26 | 2018-04-26 | 2018-04-26 | 2018-04-26 | 2018-04-26 | 2018-04-26 | 2018-04-26 | 2018-04-26 | 2018-04-26 | 2018-04-26 | 2018-04-26
2AI101PI01000-08246 | EOF:Welding/Bolting of Pipes | [33 empty] | 2018-04-26 | 2018-04-26 | 2018-04-26 | 2018-04-26 | 2018-04-26 | 2018-04-26 | 2018-04-26 | 2018-04-26 | 2018-04-26 | 2018-04-26 | 2018-04-26 | 2018-04-26 | 2018-04-26
2AI101PI01000-08245 | EOF:Alignment/Fit-up | [33 empty] | 2018-04-26 | 2018-04-26 | 2018-04-26 | 2018-04-26 | 2018-04-26 | 2018-04-26 | 2018-04-26 | 2018-04-26 | 2018-04-26 | 2018-04-26 | 2018-04-26 | 2018-04-26 | 2018-04-26
2AI101PI01000-08240 | EOF:Installation of pipes | [31 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
2AI101PI01000-08236 | EOF:Coating/Wrapping | [35 empty] | 2018-06-01 | 2018-06-01 | 2018-06-01 | 2018-06-01 | 2018-06-01 | 2018-06-01 | 2018-06-01 | 2018-06-01 | 2018-06-01 | 2018-06-01 | 2018-06-01
2AI101PI01000-08235 | EOF:NDE/PWHT/QC Checks of Pipes | [29 empty] | 2017-12-18 | 2017-12-18 | 2017-12-18 | 2017-12-18 | 2017-12-18 | 2017-12-18 | 2017-12-18 | 2017-12-18 | 2017-12-18 | 2017-12-18 | 2017-12-18 | 2017-12-18 | 2017-12-18 | 2017-12-18 | 2017-12-18 | 2017-12-18 | 2017-12-18
2AI101PI01000-08231 | EOF:Welding/Bolting of Pipes | [29 empty] | 2017-12-18 | 2017-12-18 | 2017-12-18 | 2017-12-18 | 2017-12-18 | 2017-12-18 | 2017-12-18 | 2017-12-18 | 2017-12-18 | 2017-12-18 | 2017-12-18 | 2017-12-18 | 2017-12-18 | 2017-12-18 | 2017-12-18 | 2017-12-18 | 2017-12-18
2AI101PI01000-08230 | EOF:Alignment/Fit-up | [29 empty] | 2017-12-18 | 2017-12-18 | 2017-12-18 | 2017-12-18 | 2017-12-18 | 2017-12-18 | 2017-12-18 | 2017-12-18 | 2017-12-18 | 2017-12-18 | 2017-12-18 | 2017-12-18 | 2017-12-18 | 2017-12-18 | 2017-12-18 | 2017-12-18 | 2017-12-18
2AI101PI01000-08225 | EOF:Installation of pipes | [29 empty] | 2017-11-28 | 2017-11-28 | 2017-11-28 | 2017-11-28 | 2017-11-28 | 2017-11-28 | 2017-11-28 | 2017-11-28 | 2017-11-28 | 2017-11-28 | 2017-11-28 | 2017-11-28 | 2017-11-28 | 2017-11-28 | 2017-11-28 | 2017-11-28 | 2017-11-28
2AI101PI01000-08221 | EOF:Coating/Wrapping | [35 empty] | 2018-07-27 | 2018-07-27 | 2018-07-27 | 2018-07-27 | 2018-07-27 | 2018-07-27 | 2018-07-27 | 2018-07-27 | 2018-07-27 | 2018-07-27 | 2018-07-27
2AI101PI01000-08220 | EOF:NDE/PWHT/QC Checks of Pipes | [33 empty] | 2018-04-23 | 2018-04-23 | 2018-04-23 | 2018-04-23 | 2018-04-23 | 2018-04-23 | 2018-04-23 | 2018-04-23 | 2018-04-23 | 2018-04-23 | 2018-04-23 | 2018-04-23 | 2018-04-23
2AI101PI01000-08216 | EOF:Welding/Bolting of Pipes | [33 empty] | 2018-04-20 | 2018-04-20 | 2018-04-20 | 2018-04-20 | 2018-04-20 | 2018-04-20 | 2018-04-20 | 2018-04-20 | 2018-04-20 | 2018-04-20 | 2018-04-20 | 2018-04-20 | 2018-04-20
2AI101PI01000-08215 | EOF:Alignment/Fit-up | [33 empty] | 2018-04-20 | 2018-04-20 | 2018-04-20 | 2018-04-20 | 2018-04-20 | 2018-04-20 | 2018-04-20 | 2018-04-20 | 2018-04-20 | 2018-04-20 | 2018-04-20 | 2018-04-20 | 2018-04-20
2AI101PI01000-08210 | EOF:Installation of pipes | [33 empty] | 2018-04-19 | 2018-04-19 | 2018-04-19 | 2018-04-19 | 2018-04-19 | 2018-04-19 | 2018-04-19 | 2018-04-19 | 2018-04-19 | 2018-04-19 | 2018-04-19 | 2018-04-19 | 2018-04-19
2AI101PI01000-08206 | EOF:Coating/Wrapping | [35 empty] | 2018-07-20 | 2018-07-20 | 2018-07-20 | 2018-07-20 | 2018-07-20 | 2018-07-20 | 2018-07-20 | 2018-07-20 | 2018-07-20 | 2018-07-20 | 2018-07-20
2AI101PI01000-08205 | EOF:NDE/PWHT/QC Checks of Pipes | [35 empty] | 2018-05-28 | 2018-05-28 | 2018-05-28 | 2018-05-28 | 2018-05-28 | 2018-05-28 | 2018-05-28 | 2018-05-28 | 2018-05-28 | 2018-05-28 | 2018-05-28
2AI101PI01000-08201 | EOF:Welding/Bolting of Pipes | [35 empty] | 2018-05-27 | 2018-05-27 | 2018-05-27 | 2018-05-27 | 2018-05-27 | 2018-05-27 | 2018-05-27 | 2018-05-27 | 2018-05-27 | 2018-05-27 | 2018-05-27
2AI101PI01000-08200 | EOF:Alignment/Fit-up | [35 empty] | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26
2AI101PI01000-08195 | EOF:Installation of pipes | [31 empty] | 2018-03-07 | 2018-03-07 | 2018-03-07 | 2018-03-07 | 2018-03-07 | 2018-03-07 | 2018-03-07 | 2018-03-07 | 2018-03-07 | 2018-03-07 | 2018-03-07 | 2018-03-07 | 2018-03-07 | 2018-03-07 | 2018-03-07
2AI101PI01000-08191 | EOF:Coating/Wrapping | [35 empty] | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02
2AI101PI01000-08190 | EOF:NDE/PWHT/QC Checks of Pipes | [35 empty] | 2018-05-27 | 2018-05-27 | 2018-05-27 | 2018-05-27 | 2018-05-27 | 2018-05-27 | 2018-05-27 | 2018-05-27 | 2018-05-27 | 2018-05-27 | 2018-05-27
2AI101PI01000-08186 | EOF:Welding/Bolting of Pipes | [35 empty] | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26
2AI101PI01000-08185 | EOF:Alignment/Fit-up | [33 empty] | 2018-04-23 | 2018-04-23 | 2018-04-23 | 2018-04-23 | 2018-04-23 | 2018-04-23 | 2018-04-23 | 2018-04-23 | 2018-04-23 | 2018-04-23 | 2018-04-23 | 2018-04-23 | 2018-04-23
2AI101PI01000-08180 | EOF:Installation of pipes | [31 empty] | 2018-03-07 | 2018-03-07 | 2018-03-07 | 2018-03-07 | 2018-03-07 | 2018-03-07 | 2018-03-07 | 2018-03-07 | 2018-03-07 | 2018-03-07 | 2018-03-07 | 2018-03-07 | 2018-03-07 | 2018-03-07 | 2018-03-07
2AI101PI01000-08176 | EOF:Coating/Wrapping | [35 empty] | 2018-05-30 | 2018-05-30 | 2018-05-30 | 2018-05-30 | 2018-05-30 | 2018-05-30 | 2018-05-30 | 2018-05-30 | 2018-05-30 | 2018-05-30 | 2018-05-30
2AI101PI01000-08175 | EOF:NDE/PWHT/QC Checks of Pipes | [29 empty] | 2017-12-16 | 2017-12-16 | 2017-12-16 | 2017-12-16 | 2017-12-16 | 2017-12-16 | 2017-12-16 | 2017-12-16 | 2017-12-16 | 2017-12-16 | 2017-12-16 | 2017-12-16 | 2017-12-16 | 2017-12-16 | 2017-12-16 | 2017-12-16 | 2017-12-16
2AI101PI01000-08171 | EOF:Welding/Bolting of Pipes | [29 empty] | 2017-12-16 | 2017-12-16 | 2017-12-16 | 2017-12-16 | 2017-12-16 | 2017-12-16 | 2017-12-16 | 2017-12-16 | 2017-12-16 | 2017-12-16 | 2017-12-16 | 2017-12-16 | 2017-12-16 | 2017-12-16 | 2017-12-16 | 2017-12-16 | 2017-12-16
2AI101PI01000-08170 | EOF:Alignment/Fit-up | [29 empty] | 2017-12-16 | 2017-12-16 | 2017-12-16 | 2017-12-16 | 2017-12-16 | 2017-12-16 | 2017-12-16 | 2017-12-16 | 2017-12-16 | 2017-12-16 | 2017-12-16 | 2017-12-16 | 2017-12-16 | 2017-12-16 | 2017-12-16 | 2017-12-16 | 2017-12-16
2AI101PI01000-08165 | EOF:Installation of pipes | [29 empty] | 2018-01-02 | 2018-01-02 | 2018-01-02 | 2018-01-02 | 2018-01-02 | 2018-01-02 | 2018-01-02 | 2018-01-02 | 2018-01-02 | 2018-01-02 | 2018-01-02 | 2018-01-02 | 2018-01-02 | 2018-01-02 | 2018-01-02 | 2018-01-02 | 2018-01-02
2AI101PI01000-08161 | EOF:Coating/Wrapping | [35 empty] | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26
2AI101PI01000-08160 | EOF:NDE/PWHT/QC Checks of Pipes | [35 empty] | 2018-05-25 | 2018-05-25 | 2018-05-25 | 2018-05-25 | 2018-05-25 | 2018-05-25 | 2018-05-25 | 2018-05-25 | 2018-05-25 | 2018-05-25 | 2018-05-25
2AI101PI01000-08156 | EOF:Welding/Bolting of Pipes | [35 empty] | 2018-05-29 | 2018-05-29 | 2018-05-29 | 2018-05-29 | 2018-05-29 | 2018-05-29 | 2018-05-29 | 2018-05-29 | 2018-05-29 | 2018-05-29 | 2018-05-29
2AI101PI01000-08155 | EOF:Alignment/Fit-up | [35 empty] | 2018-05-27 | 2018-05-27 | 2018-05-27 | 2018-05-27 | 2018-05-27 | 2018-05-27 | 2018-05-27 | 2018-05-27 | 2018-05-27 | 2018-05-27 | 2018-05-27
2AI101PI01000-08150 | EOF:Installation of pipes | [35 empty] | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26
2AI101PI01000-08145 | EOF:NDE/QC Checks of Pipes | [29 empty] | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03
2AI101PI01000-08140 | EOF:Jointing/Fusion Welding | [29 empty] | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03
2AI101PI01000-08135 | EOF:Laying of Piping Spools | [29 empty] | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03
2AI101PI01000-08131 | EOF:Coating/Wrapping | [29 empty] | 2018-01-03: 2018-10-09; 2018-01-03: 2018-10-09; 2018-01-03: 2018-10-09; 2018-01-03: 2018-10-09; 2018-01-03: 2018-10-09; 2018-01-03: 2018-10-09; 2018-01-03: 2018-10-09
2AI101PI01000-08130 | EOF:NDE/PWHT/QC Checks of Pipes | [37 empty] | 2018-08-12 | 2018-08-12 | 2018-08-12 | 2018-08-12 | 2018-08-12 | 2018-08-12 | 2018-08-12 | 2018-08-12 | 2018-08-12
2AI101PI01000-08126 | EOF:Welding/Bolting of Pipes | [37 empty] | 2018-08-15 | 2018-08-15 | 2018-08-15 | 2018-08-15 | 2018-08-15 | 2018-08-15 | 2018-08-15 | 2018-08-15 | 2018-08-15
2AI101PI01000-08125 | EOF:Alignment/Fit-up | [37 empty] | 2018-08-09 | 2018-08-09 | 2018-08-09 | 2018-08-09 | 2018-08-09 | 2018-08-09 | 2018-08-09 | 2018-08-09 | 2018-08-09
2AI101PI01000-08120 | EOF:Installation of pipes | [37 empty] | 2018-08-03 | 2018-08-03 | 2018-08-03 | 2018-08-03 | 2018-08-03 | 2018-08-03 | 2018-08-03 | 2018-08-03 | 2018-08-03
2AI101PI01000-08116 | EOF:Coating/Wrapping | [37 empty] | 2018-08-03: 2018-12-20; 2018-08-03: 2018-12-20; 2018-08-03: 2018-12-20; 2018-08-03: 2018-12-20; 2018-08-03: 2018-12-20
2AI101PI01000-08115 | EOF:NDE/PWHT/QC Checks of Pipes | [37 empty] | 2018-08-03: 2018-12-18; 2018-08-03: 2018-12-18; 2018-08-03: 2018-12-18; 2018-08-03: 2018-12-18; 2018-08-03: 2018-12-18
2AI101PI01000-08111 | EOF:Welding/Bolting of Pipes | [37 empty] | 2018-08-03: 2018-12-15; 2018-08-03: 2018-12-15; 2018-08-03: 2018-12-15; 2018-08-03: 2018-12-15; 2018-08-03: 2018-12-15
2AI101PI01000-08110 | EOF:Alignment/Fit-up | [37 empty] | 2018-08-03: 2018-12-12; 2018-08-03: 2018-12-12; 2018-08-03: 2018-12-12; 2018-08-03: 2018-12-12; 2018-08-03: 2018-12-12
2AI101PI01000-08105 | EOF:Installation of pipes | [37 empty] | 2018-08-03: 2018-12-10; 2018-08-03: 2018-12-10; 2018-08-03: 2018-12-10; 2018-08-03: 2018-12-10; 2018-08-03: 2018-12-10
2AI101PI01000-08100 | EOF:NDE/QC Checks of Pipes | [37 empty] | 2018-08-03: 2019-02-15; 2018-08-03: 2019-02-15; 2018-08-03: 2019-02-15
2AI101PI01000-08095 | EOF:Jointing/Fusion Welding | [37 empty] | 2018-08-03: 2019-02-12; 2018-08-03: 2019-02-12; 2018-08-03: 2019-02-12
2AI101PI01000-08090 | EOF:Laying of Piping Spools | [37 empty] | 2018-08-03: 2019-02-06; 2018-08-03: 2019-02-06; 2018-08-03: 2019-02-06
2AI101PI01000-08086 | EOF:Coating/Wrapping | [35 empty] | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26
2AI101PI01000-08085 | EOF:NDE/PWHT/QC Checks of Pipes | [29 empty] | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17
2AI101PI01000-08081 | EOF:Welding/Bolting of Pipes | [29 empty] | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17
2AI101PI01000-08080 | EOF:Alignment/Fit-up | [29 empty] | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17
2AI101PI01000-08079 | EOF:Coating/Wrapping | [29 empty] | 2017-12-17: 2018-11-24; 2017-12-17: 2018-11-24; 2017-12-17: 2018-11-24; 2017-12-17: 2018-11-24; 2017-12-17: 2018-11-24
2AI101PI01000-08077 | EOF:NDE/PWHT/QC Checks of Pipes | [29 empty] | 2017-12-17: 2018-09-30; 2017-12-17: 2018-09-30; 2017-12-17: 2018-09-30; 2017-12-17: 2018-09-30; 2017-12-17: 2018-09-30; 2017-12-17: 2018-09-30; 2017-12-17: 2018-09-30
2AI101PI01000-08075 | EOF:Installation of pipes | [29 empty] | 2017-12-07 | 2017-12-07 | 2017-12-07 | 2017-12-07 | 2017-12-07 | 2017-12-07 | 2017-12-07 | 2017-12-07 | 2017-12-07 | 2017-12-07 | 2017-12-07 | 2017-12-07 | 2017-12-07 | 2017-12-07 | 2017-12-07 | 2017-12-07 | 2017-12-07
2AI101PI01000-08073 | EOF:Welding/Bolting of Pipes | [37 empty] | 2018-09-27 | 2018-09-27 | 2018-09-27 | 2018-09-27 | 2018-09-27 | 2018-09-27 | 2018-09-27 | 2018-09-27 | 2018-09-27
2AI101PI01000-08072 | EOF:Alignment/Fit-up | [37 empty] | 2018-09-27 | 2018-09-27 | 2018-09-27 | 2018-09-27 | 2018-09-27 | 2018-09-27 | 2018-09-27 | 2018-09-27 | 2018-09-27
2AI101PI01000-08071 | EOF:Installation of pipes | [37 empty] | 2018-08-25 | 2018-08-25 | 2018-08-25 | 2018-08-25 | 2018-08-25 | 2018-08-25 | 2018-08-25 | 2018-08-25 | 2018-08-25
2AI101PI01000-08069 | EOF:Coating/Wrapping | [37 empty] | 2018-08-25: 2018-11-24; 2018-08-25: 2018-11-24; 2018-08-25: 2018-11-24; 2018-08-25: 2018-11-24; 2018-08-25: 2018-11-24
2AI101PI01000-08067 | EOF:NDE/PWHT/QC Checks of Pipes | [37 empty] | 2018-09-25 | 2018-09-25 | 2018-09-25 | 2018-09-25 | 2018-09-25 | 2018-09-25 | 2018-09-25 | 2018-09-25 | 2018-09-25
2AI101PI01000-08063 | EOF:Welding/Bolting of Pipes | [37 empty] | 2018-09-06 | 2018-09-06 | 2018-09-06 | 2018-09-06 | 2018-09-06 | 2018-09-06 | 2018-09-06 | 2018-09-06 | 2018-09-06
2AI101PI01000-08062 | EOF:Alignment/Fit-up | [37 empty] | 2018-09-01 | 2018-09-01 | 2018-09-01 | 2018-09-01 | 2018-09-01 | 2018-09-01 | 2018-09-01 | 2018-09-01 | 2018-09-01
2AI101PI01000-08061 | EOF:Installation of pipes | [37 empty] | 2018-08-27 | 2018-08-27 | 2018-08-27 | 2018-08-27 | 2018-08-27 | 2018-08-27 | 2018-08-27 | 2018-08-27 | 2018-08-27
2AI101PI01000-08056 | EOF:Coating/Wrapping | [33 empty] | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18
2AI101PI01000-08055 | EOF:NDE/PWHT/QC Checks of Pipes | [29 empty] | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17
2AI101PI01000-08053 | EOF:Coating/Wrapping | [29 empty] | 2017-12-17: 2018-12-30; 2017-12-17: 2018-12-30; 2017-12-17: 2018-12-30; 2017-12-17: 2018-12-30; 2017-12-17: 2018-12-30
2AI101PI01000-08051 | EOF:NDE/PWHT/QC Checks of Pipes | [29 empty] | 2017-12-17: 2018-10-15; 2017-12-17: 2018-10-15; 2017-12-17: 2018-10-15; 2017-12-17: 2018-10-15; 2017-12-17: 2018-10-15; 2017-12-17: 2018-10-15; 2017-12-17: 2018-10-15
2AI101PI01000-08050 | EOF:NDE/PWHT/QC Checks of Pipes | [29 empty] | 2017-12-17: 2019-01-18; 2017-12-17: 2019-01-18; 2017-12-17: 2019-01-18; 2017-12-17: 2019-01-18; 2017-12-17: 2019-01-18
2AI101PI01000-08049 | EOF:Welding/Bolting of Pipes | [29 empty] | 2017-12-17: 2018-10-15; 2017-12-17: 2018-10-15; 2017-12-17: 2018-10-15; 2017-12-17: 2018-10-15; 2017-12-17: 2018-10-15; 2017-12-17: 2018-10-15; 2017-12-17: 2018-10-15
2AI101PI01000-08047 | EOF:Alignment/Fit-up | [29 empty] | 2017-12-17: 2018-10-13; 2017-12-17: 2018-10-13; 2017-12-17: 2018-10-13; 2017-12-17: 2018-10-13; 2017-12-17: 2018-10-13; 2017-12-17: 2018-10-13; 2017-12-17: 2018-10-13
2AI101PI01000-08046 | EOF:Welding/Bolting of Pipes | [29 empty] | 2017-12-17: 2019-01-18; 2017-12-17: 2019-01-18; 2017-12-17: 2019-01-18; 2017-12-17: 2019-01-18; 2017-12-17: 2019-01-18
2AI101PI01000-08045 | EOF:Alignment/Fit-up | [29 empty] | 2017-12-17: 2019-01-17; 2017-12-17: 2019-01-17; 2017-12-17: 2019-01-17; 2017-12-17: 2019-01-17; 2017-12-17: 2019-01-17
2AI101PI01000-08043 | EOF:Installation of pipes | [29 empty] | 2017-12-17: 2018-10-08; 2017-12-17: 2018-10-08; 2017-12-17: 2018-10-08; 2017-12-17: 2018-10-08; 2017-12-17: 2018-10-08; 2017-12-17: 2018-10-08; 2017-12-17: 2018-10-08
2AI101PI01000-08041 | EOF:Coating/Wrapping | [29 empty] | 2017-12-17: 2018-12-30; 2017-12-17: 2018-12-30; 2017-12-17: 2018-12-30; 2017-12-17: 2018-12-30; 2017-12-17: 2018-12-30
2AI101PI01000-08040 | EOF:Installation of pipes | [29 empty] | 2017-12-17: 2019-01-16; 2017-12-17: 2019-01-16; 2017-12-17: 2019-01-16; 2017-12-17: 2019-01-16; 2017-12-17: 2019-01-16
2AI101PI01000-08039 | EOF:NDE/PWHT/QC Checks of Pipes | [29 empty] | 2017-12-17: 2018-10-15; 2017-12-17: 2018-10-15; 2017-12-17: 2018-10-15; 2017-12-17: 2018-10-15; 2017-12-17: 2018-10-15; 2017-12-17: 2018-10-15; 2017-12-17: 2018-10-15
2AI101PI01000-08037 | EOF:Welding/Bolting of Pipes | [29 empty] | 2017-12-17: 2018-10-13; 2017-12-17: 2018-10-13; 2017-12-17: 2018-10-13; 2017-12-17: 2018-10-13; 2017-12-17: 2018-10-13; 2017-12-17: 2018-10-13; 2017-12-17: 2018-10-13
2AI101PI01000-08036 | EOF:Welding/Bolting of Pipes | [29 empty] | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17
2AI101PI01000-08035 | EOF:Alignment/Fit-up | [29 empty] | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17
2AI101PI01000-08033 | EOF:Alignment/Fit-up | [29 empty] | 2017-12-17: 2018-10-11; 2017-12-17: 2018-10-11; 2017-12-17: 2018-10-11; 2017-12-17: 2018-10-11; 2017-12-17: 2018-10-11; 2017-12-17: 2018-10-11; 2017-12-17: 2018-10-11
2AI101PI01000-08032 | EOF:Installation of pipes | [29 empty] | 2017-12-17: 2018-10-10; 2017-12-17: 2018-10-10; 2017-12-17: 2018-10-10; 2017-12-17: 2018-10-10; 2017-12-17: 2018-10-10; 2017-12-17: 2018-10-10; 2017-12-17: 2018-10-10
2AI101PI01000-08031 | EOF:Coating/Wrapping | [37 empty] | 2018-08-08 | 2018-08-08 | 2018-08-08 | 2018-08-08 | 2018-08-08 | 2018-08-08 | 2018-08-08 | 2018-08-08 | 2018-08-08
2AI101PI01000-08030 | EOF:NDE/PWHT/QC Checks of Pipes | [35 empty] | 2018-05-30 | 2018-05-30 | 2018-05-30 | 2018-05-30 | 2018-05-30 | 2018-05-30 | 2018-05-30 | 2018-05-30 | 2018-05-30 | 2018-05-30 | 2018-05-30
2AI101PI01000-08026 | EOF:Welding/Bolting of Pipes | [35 empty] | 2018-05-30 | 2018-05-30 | 2018-05-30 | 2018-05-30 | 2018-05-30 | 2018-05-30 | 2018-05-30 | 2018-05-30 | 2018-05-30 | 2018-05-30 | 2018-05-30
2AI101PI01000-08025 | EOF:Alignment/Fit-up | [35 empty] | 2018-05-30 | 2018-05-30 | 2018-05-30 | 2018-05-30 | 2018-05-30 | 2018-05-30 | 2018-05-30 | 2018-05-30 | 2018-05-30 | 2018-05-30 | 2018-05-30
2AI101PI01000-08020 | EOF:Installation of pipes | [33 empty] | 2018-05-21 | 2018-05-21 | 2018-05-21 | 2018-05-21 | 2018-05-21 | 2018-05-21 | 2018-05-21 | 2018-05-21 | 2018-05-21 | 2018-05-21 | 2018-05-21 | 2018-05-21 | 2018-05-21
2AI101PI01000-08016 | EOF:Installation of pipes | [29 empty] | 2018-01-05 | 2018-01-05 | 2018-01-05 | 2018-01-05 | 2018-01-05 | 2018-01-05 | 2018-01-05 | 2018-01-05 | 2018-01-05 | 2018-01-05 | 2018-01-05 | 2018-01-05 | 2018-01-05 | 2018-01-05 | 2018-01-05 | 2018-01-05 | 2018-01-05
2AI101PI01000-08011 | EOF:NDE/QC Checks of Pipes | [29 empty] | 2018-01-05: 2019-02-20; 2018-01-05: 2019-02-20; 2018-01-05: 2019-02-20
2AI101PI01000-08010 | EOF: UG Piping works for Metallic (SS/SDSS) | [29 empty] | 2018-01-05: 2019-01-18; 2018-01-05: 2019-01-18; 2018-01-05: 2019-01-18; 2018-01-05: 2019-01-18; 2018-01-05: 2019-01-18
2AI101PI01000-08006 | EOF:Jointing/Fusion Welding | [29 empty] | 2018-01-05: 2019-02-17; 2018-01-05: 2019-02-17; 2018-01-05: 2019-02-17
2AI101PI01000-08005 | EOF: UG Piping works for Metallic (CS/LTCS) | [29 empty] | 2018-01-05: 2019-02-21; 2018-01-05: 2019-02-21; 2018-01-05: 2019-02-21
2AI101PI01000-08001 | EOF:Laying of Piping Spools | [29 empty] | 2018-01-05: 2019-02-15; 2018-01-05: 2019-02-15; 2018-01-05: 2019-02-15
2AI101PI01000-08000 | EOF: UG Piping works for Non Metallic | [29 empty] | 2018-01-05: 2019-02-20; 2018-01-05: 2019-02-20; 2018-01-05: 2019-02-20
2AI101PI01000 | EOF: UG Piping works | [29 empty] | 2018-01-05: 2019-02-21; 2018-01-05: 2019-02-21; 2018-01-05: 2019-02-21
2AI101PC02100-08010 | EOF SS 52-SUBST-302 : Energize EDG 60-R-706
2AI101PC02100-08001 | EOF: GCP Testing, Switch Gear Testing
2AI101PC02100-08000 | EOF SS 52-SUBST-302 : Energize EDG 60-R-706
2AI101PC02100 | EOF SS 52-SUBST-302 : Energize EDG 60-R-706
2AI101PC02000-08005 | EOF:Lux testing | [29 empty] | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24
2AI101PC02000-08001 | EOF:Continuity & IR testing | [25 empty] | 2017-08-12 | 2017-08-12 | 2017-08-12 | 2017-08-12 | 2017-08-12 | 2017-08-12 | 2017-08-12 | 2017-08-12 | 2017-08-12 | 2017-08-12 | 2017-08-12 | 2017-08-12 | 2017-08-12 | 2017-08-12 | 2017-08-12 | 2017-08-12 | 2017-08-12 | 2017-08-12 | 2017-08-12 | 2017-08-12 | 2017-08-12
2AI101PC02000-08000 | EOF SS 52-SUBST-302 : Lighting & Small Power | [29 empty] | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24
2AI101PC02000 | EOF SS 52-SUBST-302 : Lighting & Small Power | [29 empty] | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24
2AI101PC01900-08005 | EOF:Incoming HV cables hipot testing
2AI101PC01900-08001 | EOF:Incoming cables IR and continuity test
2AI101PC01900-08000 | EOF SS 52-SUBST-302 : Electrical Tie-ins for Permanent Power & Energize
2AI101PC01900 | EOF SS 52-SUBST-302 : Electrical Tie-ins for Permanent Power & Energize
2AI101PC01700-08010 | EOF:BDV Testing | [29 empty] | 2017-12-24: 2019-03-15; 2017-12-24: 2019-03-15; 2017-12-24: 2019-03-15
2AI101PC01700-08005 | EOF:Functional Test | [29 empty] | 2017-12-24: 2019-03-15; 2017-12-24: 2019-03-15; 2017-12-24: 2019-03-15
2AI101PC01700-08001 | EOF:IR testing/WR testing/Turns ratio testing | [29 empty] | 2017-12-24: 2019-03-14; 2017-12-24: 2019-03-14; 2017-12-24: 2019-03-14
2AI101PC01700-08000 | EOF SS 52-SUBST-302 : Transformer Testing | [29 empty] | 2017-12-24: 2019-03-15; 2017-12-24: 2019-03-15; 2017-12-24: 2019-03-15
2AI101PC01700 | EOF SS 52-SUBST-302 : Transformer Testing | [29 empty] | 2017-12-24: 2019-03-15; 2017-12-24: 2019-03-15; 2017-12-24: 2019-03-15
2AI101PC01600-08010 | EOF:Discharging test
2AI101PC01600-08005 | EOF:Charging test
2AI101PC01600-08001 | EOF:Polarity check
2AI101PC01600-08000 | EOF SS 52-SUBST-302 : 110V AC UPS
2AI101PC01600 | EOF SS 52-SUBST-302 : 110V AC UPS
2AI101PC01400-08025 | EOF: Stability Testing | [29 empty] | 2017-12-24: 2019-04-25
2AI101PC01400-08020 | EOF: Hi-pot Test | [29 empty] | 2017-12-24: 2019-04-17
2AI101PC01400-08015 | EOF Primary Injection Testing | [29 empty] | 2017-12-24: 2019-04-01; 2017-12-24: 2019-04-01; 2017-12-24: 2019-04-01
2AI101PC01400-08010 | EOF: Relay & Functional Testing | [29 empty] | 2017-12-24: 2019-03-30
2AI101PC01400-08005 | EOF: IR, Ductor testing | [29 empty] | 2017-12-24: 2019-03-28; 2017-12-24: 2019-03-28; 2017-12-24: 2019-03-28
2AI101PC01400-08001 | EOF: CT,PT Testing | [29 empty] | 2017-12-24: 2019-03-26; 2017-12-24: 2019-03-26; 2017-12-24: 2019-03-26
2AI101PC01400-08000 | EOF SS 52-SUBST-302 : LV Switchgear testing | [29 empty] | 2017-12-24: 2019-04-25
2AI101PC01400 | EOF SS 52-SUBST-302 : LV Switchgear testing | [29 empty] | 2017-12-24: 2019-04-25
2AI101PC01300-08010 | EOF:Discharging test
2AI101PC01300-08005 | EOF:Charging test
2AI101PC01300-08001 | EOF:Polarity check
2AI101PC01300-08000 | EOF SS 52-SUBST-302 : 24V DC Battery Charger
2AI101PC01300 | EOF SS 52-SUBST-302 : 24V DC Battery Charger
2AI101PC01200-08025 | EOF: Stability Testing
2AI101PC01200-08020 | EOF: Hi-pot Test
2AI101PC01200-08015 | EOF Primary Injection Testing | [29 empty] | 2017-12-24: 2019-03-26; 2017-12-24: 2019-03-26; 2017-12-24: 2019-03-26
2AI101PC01200-08010 | EOF: Relay & Functional Testing
2AI101PC01200-08005 | EOF: IR, Ductor testing | [29 empty] | 2017-12-24: 2019-03-25; 2017-12-24: 2019-03-25; 2017-12-24: 2019-03-25
2AI101PC01200-08001 | EOF: CT,PT,Breaker Testing | [29 empty] | 2017-12-24: 2019-03-24; 2017-12-24: 2019-03-24; 2017-12-24: 2019-03-24
2AI101PC01200-08000 | EOF SS 52-SUBST-302 : HV Switchgear testing
2AI101PC01200 | EOF SS 52-SUBST-302 : HV Switchgear testing
2AI101PC01100-08005 | EOF:Earth resistance measurement | [29 empty] | 2017-12-24: 2019-03-15; 2017-12-24: 2019-03-15; 2017-12-24: 2019-03-15
2AI101PC01100-08001 | EOF:Continuity testing | [29 empty] | 2017-12-24: 2019-03-26; 2017-12-24: 2019-03-26; 2017-12-24: 2019-03-26
2AI101PC01100-08000 | EOF SS 52-SUBST-302 : SS Earthing & Lightning | [29 empty] | 2017-12-24: 2019-03-26; 2017-12-24: 2019-03-26; 2017-12-24: 2019-03-26
2AI101PC01100 | EOF SS 52-SUBST-302 : SS Earthing & Lightning | [29 empty] | 2017-12-24: 2019-03-26; 2017-12-24: 2019-03-26; 2017-12-24: 2019-03-26
2AI101PC01000-08010 | EOF:Discharging test
2AI101PC01000-08005 | EOF:Charging test
2AI101PC01000-08001 | EOF:Polarity check
2AI101PC01000-08000 | EOF SS 52-SUBST-302 : 110V DC Battery Charger
2AI101PC01000 | EOF SS 52-SUBST-302 : 110V DC Battery Charger
2AI101MS03000-08095 | EOF:QC checks & clearance for Equipment 621-G-303 B Oily Water Transfer Pump
2AI101MS03000-08090 | EOF:Final Allignment & Grouting of Equipment 621-G-303 B Oily Water Transfer Pump
2AI101MS03000-08085 | EOF:Preliminary Allignment & Grouting of Equipment 621-G-303 B Oily Water Transfer Pump | [35 empty] | 2018-05-28 | 2018-05-28 | 2018-05-28 | 2018-05-28 | 2018-05-28 | 2018-05-28 | 2018-05-28 | 2018-05-28 | 2018-05-28 | 2018-05-28 | 2018-05-28
2AI101MS03000-08080 | EOF:Installation of Equipment 621-G-303 B Oily Water Transfer Pump | [35 empty] | 2018-05-27 | 2018-05-27 | 2018-05-27 | 2018-05-27 | 2018-05-27 | 2018-05-27 | 2018-05-27 | 2018-05-27 | 2018-05-27 | 2018-05-27 | 2018-05-27
2AI101MS03000-08075 | EOF:Foundation checks/Preparation for Equipment 621-G-303 B Oily Water Transfer Pump | [35 empty] | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26
2AI101MS03000-08070 | EOF:QC checks & clearance for Equipment 621-G-303 A Oily Water Transfer Pump
2AI101MS03000-08065 | EOF:Final Allignment & Grouting of Equipment 621-G-303 A Oily Water Transfer Pump
2AI101MS03000-08060 | EOF:Preliminary Allignment & Grouting of Equipment 621-G-303 A Oily Water Transfer Pump | [35 empty] | 2018-05-28 | 2018-05-28 | 2018-05-28 | 2018-05-28 | 2018-05-28 | 2018-05-28 | 2018-05-28 | 2018-05-28 | 2018-05-28 | 2018-05-28 | 2018-05-28
2AI101MS03000-08055 | EOF:Installation of Equipment 621-G-303 A Oily Water Transfer Pump | [35 empty] | 2018-05-27 | 2018-05-27 | 2018-05-27 | 2018-05-27 | 2018-05-27 | 2018-05-27 | 2018-05-27 | 2018-05-27 | 2018-05-27 | 2018-05-27 | 2018-05-27
2AI101MS03000-08050 | EOF:Foundation checks/Preparation for Equipment 621-G-303 A Oily Water Transfer Pump | [35 empty] | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26
2AI101MS03000-08045 | EOF:QC checks & clearance for Equipment 621-G-301 B Trim Pump Erection | [37 empty] | 2018-08-24 | 2018-08-24 | 2018-08-24 | 2018-08-24 | 2018-08-24 | 2018-08-24 | 2018-08-24 | 2018-08-24 | 2018-08-24
2AI101MS03000-08040 | EOF:Final Allignment & Grouting of Equipment 621-G-301 B Trim Pump Erection | [37 empty] | 2018-08-23 | 2018-08-23 | 2018-08-23 | 2018-08-23 | 2018-08-23 | 2018-08-23 | 2018-08-23 | 2018-08-23 | 2018-08-23
2AI101MS03000-08035 | EOF:Preliminary Allignment & Grouting of Equipment 621-G-301 B Trim Pump Erection | [35 empty] | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04
2AI101MS03000-08030 | EOF:Installation of Equipment 621-G-301 B Trim Pump Erection | [31 empty] | 2018-03-04 | 2018-03-04 | 2018-03-04 | 2018-03-04 | 2018-03-04 | 2018-03-04 | 2018-03-04 | 2018-03-04 | 2018-03-04 | 2018-03-04 | 2018-03-04 | 2018-03-04 | 2018-03-04 | 2018-03-04 | 2018-03-04
2AI101MS03000-08025 | EOF:Foundation checks/Preparation for Equipment 621-G-301 B Trim Pump Erection | [31 empty] | 2018-03-03 | 2018-03-03 | 2018-03-03 | 2018-03-03 | 2018-03-03 | 2018-03-03 | 2018-03-03 | 2018-03-03 | 2018-03-03 | 2018-03-03 | 2018-03-03 | 2018-03-03 | 2018-03-03 | 2018-03-03 | 2018-03-03
2AI101MS03000-08020 | EOF:QC checks & clearance for Equipment 621-G-301 A Trim Pump Erection | [37 empty] | 2018-08-23 | 2018-08-23 | 2018-08-23 | 2018-08-23 | 2018-08-23 | 2018-08-23 | 2018-08-23 | 2018-08-23 | 2018-08-23
2AI101MS03000-08016 | EOF:Final Allignment & Grouting of Equipment 621-G-301 A Trim Pump Erection | [37 empty] | 2018-08-22 | 2018-08-22 | 2018-08-22 | 2018-08-22 | 2018-08-22 | 2018-08-22 | 2018-08-22 | 2018-08-22 | 2018-08-22
2AI101MS03000-08015 | EOF: 621-G-303 B Oily Water Transfer Pump Erection
2AI101MS03000-08011 | EOF:Preliminary Allignment & Grouting of Equipment 621-G-301 A Trim Pump Erection | [35 empty] | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04
2AI101MS03000-08010 | EOF: 621-G-303 A Oily Water Transfer Pump Erection
2AI101MS03000-08006 | EOF:Installation of Equipment 621-G-301 A Trim Pump Erection | [31 empty] | 2018-03-03 | 2018-03-03 | 2018-03-03 | 2018-03-03 | 2018-03-03 | 2018-03-03 | 2018-03-03 | 2018-03-03 | 2018-03-03 | 2018-03-03 | 2018-03-03 | 2018-03-03 | 2018-03-03 | 2018-03-03 | 2018-03-03
2AI101MS03000-08005 | EOF: 621-G-301 B Trim Pump Erection | [37 empty] | 2018-08-24 | 2018-08-24 | 2018-08-24 | 2018-08-24 | 2018-08-24 | 2018-08-24 | 2018-08-24 | 2018-08-24 | 2018-08-24
2AI101MS03000-08001 | EOF:Foundation checks/Preparation for Equipment 621-G-301 A Trim Pump Erection | [31 empty] | 2018-03-02 | 2018-03-02 | 2018-03-02 | 2018-03-02 | 2018-03-02 | 2018-03-02 | 2018-03-02 | 2018-03-02 | 2018-03-02 | 2018-03-02 | 2018-03-02 | 2018-03-02 | 2018-03-02 | 2018-03-02 | 2018-03-02
2AI101MS03000-08000 | EOF: 621-G-301 A Trim Pump Erection | [37 empty] | 2018-08-23 | 2018-08-23 | 2018-08-23 | 2018-08-23 | 2018-08-23 | 2018-08-23 | 2018-08-23 | 2018-08-23 | 2018-08-23
2AI101MS03000 | EOF: Pump Erection
2AI101MS02600-08040 | EOF: PIG Release Release After completion of Erection by other sub contractor
2AI101MS02600-08035 | EOF: Sorage Tank tank 52-D-96: Release After completion of Erection by other sub contractor | [39 empty] | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30
2AI101MS02600-08030 | EOF: Sorage Tank tank 52-D-95: Release After completion of Erection by other sub contractor | [37 empty] | 2018-09-15 | 2018-09-15 | 2018-09-15 | 2018-09-15 | 2018-09-15 | 2018-09-15 | 2018-09-15 | 2018-09-15 | 2018-09-15
2AI101MS02600-08025 | EOF: Sorage Tank tank 52-D-94: Release After completion of Erection by other sub contractor | [37 empty] | 2018-08-24 | 2018-08-24 | 2018-08-24 | 2018-08-24 | 2018-08-24 | 2018-08-24 | 2018-08-24 | 2018-08-24 | 2018-08-24
2AI101MS02600-08020 | EOF: Sorage Tank tank 52-D-93: Release After completion of Erection by other sub contract | [35 empty] | 2018-07-25 | 2018-07-25 | 2018-07-25 | 2018-07-25 | 2018-07-25 | 2018-07-25 | 2018-07-25 | 2018-07-25 | 2018-07-25 | 2018-07-25 | 2018-07-25
2AI101MS02600-08010 | EOF: LFHO Storage Tank 52-D-96 - Last Piping Tie-In Works (Piping Installation ) | [39 empty] | 2018-10-20 | 2018-10-20 | 2018-10-20 | 2018-10-20 | 2018-10-20 | 2018-10-20 | 2018-10-20
2AI101MS02600-08005 | EOF: LFHO Storage Tank 52-D-95 - Last Piping Tie-In Works (Piping Installation ) | [39 empty] | 2018-10-17 | 2018-10-17 | 2018-10-17 | 2018-10-17 | 2018-10-17 | 2018-10-17 | 2018-10-17
2AI101MS01900-08150 | EOF: Water drain tank-52-D-308B Erection | [21 empty] | 2017-05-21 | 2017-05-21 | 2017-05-21 | 2017-05-21 | 2017-05-21 | 2017-05-21 | 2017-05-21 | 2017-05-21 | 2017-05-21 | 2017-05-21 | 2017-05-21 | 2017-05-21 | 2017-05-21 | 2017-05-21 | 2017-05-21 | 2017-05-21 | 2017-05-21 | 2017-05-21 | 2017-05-21 | 2017-05-21 | 2017-05-21 | 2017-05-21 | 2017-05-21 | 2017-05-21 | 2017-05-21
2AI101MS01900-08145 | EOF: Water drain tank-52-D-308A Erection | [21 empty] | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16
2AI101MS01900-08140 | EOF: Flushing water drain tank-52-D-306B Erection | [23 empty] | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19
2AI101MS01900-08135 | EOF: Flushing water drain tank-52-D-306A Erection | [23 empty] | 2017-06-14 | 2017-06-14 | 2017-06-14 | 2017-06-14 | 2017-06-14 | 2017-06-14 | 2017-06-14 | 2017-06-14 | 2017-06-14 | 2017-06-14 | 2017-06-14 | 2017-06-14 | 2017-06-14 | 2017-06-14 | 2017-06-14 | 2017-06-14 | 2017-06-14 | 2017-06-14 | 2017-06-14 | 2017-06-14 | 2017-06-14 | 2017-06-14 | 2017-06-14
2AI101MS01900-08130 | EOF: Foam drain tank-52-D-305B Erection | [25 empty] | 2017-08-09 | 2017-08-09 | 2017-08-09 | 2017-08-09 | 2017-08-09 | 2017-08-09 | 2017-08-09 | 2017-08-09 | 2017-08-09 | 2017-08-09 | 2017-08-09 | 2017-08-09 | 2017-08-09 | 2017-08-09 | 2017-08-09 | 2017-08-09 | 2017-08-09 | 2017-08-09 | 2017-08-09 | 2017-08-09 | 2017-08-09
2AI101MS01900-08125 | EOF: Foam drain tank-52-D-305A Erection | [23 empty] | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23
2AI101MS01900-08120 | EOF: Diesel Engine drain tank-52-D-304B Erection | [23 empty] | 2017-06-18 | 2017-06-18 | 2017-06-18 | 2017-06-18 | 2017-06-18 | 2017-06-18 | 2017-06-18 | 2017-06-18 | 2017-06-18 | 2017-06-18 | 2017-06-18 | 2017-06-18 | 2017-06-18 | 2017-06-18 | 2017-06-18 | 2017-06-18 | 2017-06-18 | 2017-06-18 | 2017-06-18 | 2017-06-18 | 2017-06-18 | 2017-06-18 | 2017-06-18
2AI101MS01900-08115 | EOF: Diesel Engine drain tank-52-D-304A Erection | [21 empty] | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14
2AI101MS01900-08075 | EOF:QC checks & clearance for Equipment | [21 empty] | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10
2AI101MS01900-08070 | EOF:Install internals of Equipment | [21 empty] | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10
2AI101MS01900-08065 | EOF:Install Platforms & ladders of Equipment | [21 empty] | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01
2AI101MS01900-08060 | EOF:Final Allignment & Grouting of Equipment | [21 empty] | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29
2AI101MS01900-08055 | EOF:Preliminary Allignment & Grouting of Equipment | [21 empty] | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29
2AI101MS01900-08050 | EOF:Installation of Equipment | [21 empty] | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29
2AI101MS01900-08046 | EOF:Installation of Structural Support | [21 empty] | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15
2AI101MS01900-08045 | EOF: Water drain tank-52-D-308BErection | [21 empty] | 2017-05-21 | 2017-05-21 | 2017-05-21 | 2017-05-21 | 2017-05-21 | 2017-05-21 | 2017-05-21 | 2017-05-21 | 2017-05-21 | 2017-05-21 | 2017-05-21 | 2017-05-21 | 2017-05-21 | 2017-05-21 | 2017-05-21 | 2017-05-21 | 2017-05-21 | 2017-05-21 | 2017-05-21 | 2017-05-21 | 2017-05-21 | 2017-05-21 | 2017-05-21 | 2017-05-21 | 2017-05-21
2AI101MS01900-08041 | EOF:Foundation checks/Preparation for Equipment | [21 empty] | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10
2AI101MS01900-08040 | EOF: Water drain tank-52-D-308AErection | [21 empty] | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16
2AI101MS01900-08036 | EOF:QC checks & clearance for Equipment | [21 empty] | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10
2AI101MS01900-08035 | EOF: Flushing water drain tank-52-D-306B Erection | [23 empty] | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19
2AI101MS01900-08031 | EOF:Install internals of Equipment | [21 empty] | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10
2AI101MS01900-08030 | EOF: Flushing water drain tank-52-D-306AErection | [23 empty] | 2017-06-14 | 2017-06-14 | 2017-06-14 | 2017-06-14 | 2017-06-14 | 2017-06-14 | 2017-06-14 | 2017-06-14 | 2017-06-14 | 2017-06-14 | 2017-06-14 | 2017-06-14 | 2017-06-14 | 2017-06-14 | 2017-06-14 | 2017-06-14 | 2017-06-14 | 2017-06-14 | 2017-06-14 | 2017-06-14 | 2017-06-14 | 2017-06-14 | 2017-06-14
2AI101MS01900-08026 | EOF:Install Platforms & ladders of Equipment | [21 empty] | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03
2AI101MS01900-08025 | EOF: Foam drain tank-52-D-305B Erection | [25 empty] | 2017-08-09 | 2017-08-09 | 2017-08-09 | 2017-08-09 | 2017-08-09 | 2017-08-09 | 2017-08-09 | 2017-08-09 | 2017-08-09 | 2017-08-09 | 2017-08-09 | 2017-08-09 | 2017-08-09 | 2017-08-09 | 2017-08-09 | 2017-08-09 | 2017-08-09 | 2017-08-09 | 2017-08-09 | 2017-08-09 | 2017-08-09
2AI101MS01900-08021 | EOF:Final Allignment & Grouting of Equipment | [21 empty] | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29
2AI101MS01900-08020 | EOF: Foam drain tank-52-D-305AErection | [23 empty] | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23
2AI101MS01900-08016 | EOF:Preliminary Allignment & Grouting of Equipment | [21 empty] | 2017-03-27 | 2017-03-27 | 2017-03-27 | 2017-03-27 | 2017-03-27 | 2017-03-27 | 2017-03-27 | 2017-03-27 | 2017-03-27 | 2017-03-27 | 2017-03-27 | 2017-03-27 | 2017-03-27 | 2017-03-27 | 2017-03-27 | 2017-03-27 | 2017-03-27 | 2017-03-27 | 2017-03-27 | 2017-03-27 | 2017-03-27 | 2017-03-27 | 2017-03-27 | 2017-03-27 | 2017-03-27
2AI101MS01900-08015 | EOF: Diesel Engine drain tank-52-D-304BErection | [23 empty] | 2017-06-18 | 2017-06-18 | 2017-06-18 | 2017-06-18 | 2017-06-18 | 2017-06-18 | 2017-06-18 | 2017-06-18 | 2017-06-18 | 2017-06-18 | 2017-06-18 | 2017-06-18 | 2017-06-18 | 2017-06-18 | 2017-06-18 | 2017-06-18 | 2017-06-18 | 2017-06-18 | 2017-06-18 | 2017-06-18 | 2017-06-18 | 2017-06-18 | 2017-06-18
2AI101MS01900-08011 | EOF:Installation of Equipment | [21 empty] | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25
2AI101MS01900-08010 | EOF: Diesel Engine drain tank-52-D-304AErection | [21 empty] | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14
2AI101MS01900-08006 | EOF:Installation of Structural Support | [19 empty] | 2017-03-18 | 2017-03-18 | 2017-03-18 | 2017-03-18 | 2017-03-18 | 2017-03-18 | 2017-03-18 | 2017-03-18 | 2017-03-18 | 2017-03-18 | 2017-03-18 | 2017-03-18 | 2017-03-18 | 2017-03-18 | 2017-03-18 | 2017-03-18 | 2017-03-18 | 2017-03-18 | 2017-03-18 | 2017-03-18 | 2017-03-18 | 2017-03-18 | 2017-03-18 | 2017-03-18 | 2017-03-18 | 2017-03-18 | 2017-03-18
2AI101MS01900-08005 | EOF: OverheadWater Tank (52-D-309 B) Erection | [21 empty] | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01
2AI101MS01900-08001 | EOF:Foundation checks/Preparation for Equipment | [19 empty] | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13
2AI101MS01900-08000 | EOF: OverheadWater Tank (52-D-309 A) Erection | [21 empty] | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10
2AI101MS01900 | EOF: Balance Tanks Erection | [25 empty] | 2017-08-09 | 2017-08-09 | 2017-08-09 | 2017-08-09 | 2017-08-09 | 2017-08-09 | 2017-08-09 | 2017-08-09 | 2017-08-09 | 2017-08-09 | 2017-08-09 | 2017-08-09 | 2017-08-09 | 2017-08-09 | 2017-08-09 | 2017-08-09 | 2017-08-09 | 2017-08-09 | 2017-08-09 | 2017-08-09 | 2017-08-09
2AI101MS01400-08010 | EOF: LFHO Storage Tank 52-D-94 - Last Piping Tie-In Works (Piping Installation ) | [25 empty] | 2017-08-09: 2018-10-21; 2017-08-09: 2018-10-21; 2017-08-09: 2018-10-21; 2017-08-09: 2018-10-21; 2017-08-09: 2018-10-21; 2017-08-09: 2018-10-21; 2017-08-09: 2018-10-21
2AI101MS01400-08005 | EOF: LFHO Storage Tank 52-D-93 - Last Piping Tie-In Works (Piping Installation ) | [25 empty] | 2017-08-09: 2018-10-01; 2017-08-09: 2018-10-01; 2017-08-09: 2018-10-01; 2017-08-09: 2018-10-01; 2017-08-09: 2018-10-01; 2017-08-09: 2018-10-01; 2017-08-09: 2018-10-01
2AI101IC01100-08140 | EOF: Leveling & Grouting | [25 empty] | 2017-08-09: 2019-04-12
2AI101IC01100-08130 | EOF: Mounting JB's | [25 empty] | 2017-08-09: 2019-04-11
2AI101IC01100-08120 | EOF: Supports Installation | [25 empty] | 2017-08-09: 2019-04-10
2AI101IC01100-08110 | EOF:Install Cable Tray Covers | [25 empty] | 2017-08-09: 2019-03-06; 2017-08-09: 2019-03-06; 2017-08-09: 2019-03-06
2AI101IC01100-08100 | EOF:Install Cable Trays | [35 empty] | 2018-07-26 | 2018-07-26 | 2018-07-26 | 2018-07-26 | 2018-07-26 | 2018-07-26 | 2018-07-26 | 2018-07-26 | 2018-07-26 | 2018-07-26 | 2018-07-26
2AI101IC01100-08090 | EOF: Alignment/Levelling and grouting
2AI101IC01100-08080 | EOF: Installation of Instruments on Support Structures
2AI101IC01100-08070 | EOF: Fabrication & Installation of Support Structures | [33 empty] | 2018-04-25 | 2018-04-25 | 2018-04-25 | 2018-04-25 | 2018-04-25 | 2018-04-25 | 2018-04-25 | 2018-04-25 | 2018-04-25 | 2018-04-25 | 2018-04-25 | 2018-04-25 | 2018-04-25
2AI101IC01100-08060 | EOF: Installation of Valves/Inline Instruments
2AI101IC01100-08050 | EOF: Mechanical/Piping Clearence and preparatory works
2AI101IC01100-08045 | EOF:Cable Marking | [33 empty] | 2018-05-09 | 2018-05-09 | 2018-05-09 | 2018-05-09 | 2018-05-09 | 2018-05-09 | 2018-05-09 | 2018-05-09 | 2018-05-09 | 2018-05-09 | 2018-05-09 | 2018-05-09 | 2018-05-09
2AI101IC01100-08040 | QC checks & clearance for installation | [33 empty] | 2018-05-09: 2019-04-16
2AI101IC01100-08035 | EOF:Cable Dressing & Fastening
2AI101IC01100-08031 | Testing of Valves/Instruments at Calibration shop | [33 empty] | 2018-05-09: 2019-04-15
2AI101IC01100-08030 | EOF:Cable Glading & Termination | [33 empty] | 2018-05-09: 2019-04-17
2AI101IC01100-08025 | EOF: Fabricate/Install Inst. tubing & Instrument Hookup
2AI101IC01100-08021 | Receipt of Valves/Instruments at Calibration shop | [33 empty] | 2018-05-09: 2019-04-10
2AI101IC01100-08020 | EOF: Install Inst. Valves/Inline mounted Instruments
2AI101IC01100-08016 | EOF:Cable Glading & Termination | [33 empty] | 2018-05-09: 2019-04-17
2AI101IC01100-08015 | EOF: Calibration of Valves/Instruments | [33 empty] | 2018-05-09: 2019-04-16
2AI101IC01100-08011 | EOF:Install Tray Supports | [33 empty] | 2018-05-09: 2019-03-06; 2018-05-09: 2019-03-06; 2018-05-09: 2019-03-06
2AI101IC01100-08010 | EOF: AG cable laying
2AI101IC01100-08006 | EOF:AG Cable laying
2AI101IC01100-08005 | EOF:Install Instrument JBs | [33 empty] | 2018-05-09: 2019-04-12
2AI101IC01100-08004 | EOF:Cable Drum Checks & Transport to Site | [33 empty] | 2018-05-09: 2019-04-10
2AI101IC01100-08001 | EOF:Fabricate Tray Supports | [33 empty] | 2018-05-09: 2019-03-06; 2018-05-09: 2019-03-06; 2018-05-09: 2019-03-06
2AI101IC01100-08000 | EOF:Install Instrument Cable trays & Supports | [33 empty] | 2018-05-09: 2019-03-06; 2018-05-09: 2019-03-06; 2018-05-09: 2019-03-06
2AI101IC01100 | EOF: AG cable laying,Tubing, Field&Inline Inst. Installation, Cable Glading & Termination (incl. F&G System)
2AI101IC01000-08030 | Cable Marking | [33 empty] | 2018-05-09: 2019-04-25
2AI101IC01000-08020 | Cable Dressing & Fastening | [33 empty] | 2018-05-09: 2019-04-10
2AI101IC01000-08010 | Cable Pulling | [33 empty] | 2018-05-09: 2019-04-10
2AI101IC01000-08001 | Cable Drum Checks & Transport to Site | [33 empty] | 2018-05-09: 2019-04-10
2AI101IC01000-08000 | EOF: UG Instrumentation cable works | [33 empty] | 2018-05-09: 2019-04-25
2AI101IC01000 | EOF: UG Instrumentation cable works | [33 empty] | 2018-05-09: 2019-04-25
2AI101EL01100-08150 | EOF:Leveling & Grouting | [33 empty] | 2018-05-09: 2018-10-10; 2018-05-09: 2018-10-10; 2018-05-09: 2018-10-10; 2018-05-09: 2018-10-10; 2018-05-09: 2018-10-10; 2018-05-09: 2018-10-10; 2018-05-09: 2018-10-10
2AI101EL01100-08140 | EOF:Install JB's/DB's | [33 empty] | 2018-05-09: 2018-10-09; 2018-05-09: 2018-10-09; 2018-05-09: 2018-10-09; 2018-05-09: 2018-10-09; 2018-05-09: 2018-10-09; 2018-05-09: 2018-10-09; 2018-05-09: 2018-10-09
2AI101EL01100-08138 | EOF:Installation of supports | [33 empty] | 2018-05-09: 2018-10-08; 2018-05-09: 2018-10-08; 2018-05-09: 2018-10-08; 2018-05-09: 2018-10-08; 2018-05-09: 2018-10-08; 2018-05-09: 2018-10-08; 2018-05-09: 2018-10-08
2AI101EL01100-08130 | EOF:Tagging
2AI101EL01100-08120 | EOF:Hi-Po test & Terminations
2AI101EL01100-08115 | EOF:Cable Glanding
2AI101EL01100-08113 | EOF: Cable Laying | [33 empty] | 2018-05-09: 2019-01-09; 2018-05-09: 2019-01-09; 2018-05-09: 2019-01-09; 2018-05-09: 2019-01-09; 2018-05-09: 2019-01-09
2AI101EL01100-08110 | EOF:Cable laying & Termination | [33 empty] | 2018-05-09: 2019-03-15; 2018-05-09: 2019-03-15; 2018-05-09: 2019-03-15
2AI101EL01100-08105 | EOF:Installation of Transformer/JBs | [33 empty] | 2018-05-09: 2019-02-06; 2018-05-09: 2019-02-06; 2018-05-09: 2019-02-06
2AI101EL01100-08100 | EOF:Installation of CP Anodes (incl. civil works) | [15 empty] | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31
2AI101EL01100-08095 | EOF:Cable laying & Termination | [15 empty] | 2016-10-31: 2019-03-15; 2016-10-31: 2019-03-15; 2016-10-31: 2019-03-15
2AI101EL01100-08090 | EOF:Installation of Transformer/JBs | [15 empty] | 2016-10-31: 2019-02-06; 2016-10-31: 2019-02-06; 2016-10-31: 2019-02-06
2AI101EL01100-08085 | EOF:Installation of CP Anodes (incl. civil works) | [15 empty] | 2016-09-29 | 2016-09-29 | 2016-09-29 | 2016-09-29 | 2016-09-29 | 2016-09-29 | 2016-09-29 | 2016-09-29 | 2016-09-29 | 2016-09-29 | 2016-09-29 | 2016-09-29 | 2016-09-29 | 2016-09-29 | 2016-09-29 | 2016-09-29 | 2016-09-29 | 2016-09-29 | 2016-09-29 | 2016-09-29 | 2016-09-29 | 2016-09-29 | 2016-09-29 | 2016-09-29 | 2016-09-29 | 2016-09-29 | 2016-09-29 | 2016-09-29 | 2016-09-29 | 2016-09-29 | 2016-09-29
2AI101EL01100-08080 | EOF:Cable laying & Termination | [15 empty] | 2016-09-29: 2019-03-15; 2016-09-29: 2019-03-15; 2016-09-29: 2019-03-15
2AI101EL01100-08075 | EOF:Installation of Transformer/JBs | [37 empty] | 2018-09-27 | 2018-09-27 | 2018-09-27 | 2018-09-27 | 2018-09-27 | 2018-09-27 | 2018-09-27 | 2018-09-27 | 2018-09-27
2AI101EL01100-08070 | EOF:Installation of CP Anodes (incl. civil works) | [13 empty] | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14
2AI101EL01100-08065 | EOF:Cable laying & Termination | [13 empty] | 2016-08-14: 2019-03-14; 2016-08-14: 2019-03-14; 2016-08-14: 2019-03-14
2AI101EL01100-08060 | EOF:Installation of Transformer/JBs | [13 empty] | 2016-08-14: 2019-03-14; 2016-08-14: 2019-03-14; 2016-08-14: 2019-03-14
2AI101EL01100-08055 | EOF:Installation of CP Anodes (incl. civil works) | [13 empty] | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24
2AI101EL01100-08050 | EOF:Install Lighting fixtures
2AI101EL01100-08045 | EOF:Install light pole
2AI101EL01100-08040 | EOF:Installation of supports
2AI101EL01100-08025 | EOF:Cable Glanding & Terminations
2AI101EL01100-08020 | EOF: CP Works | [13 empty] | 2016-08-24: 2019-03-15; 2016-08-24: 2019-03-15; 2016-08-24: 2019-03-15
2AI101EL01100-08015 | EOF:Installation of Lighting Poles & Fixtures
2AI101EL01100-08005 | EOF:Installation of DB'S / JB & Panels | [13 empty] | 2016-08-24: 2018-10-10; 2016-08-24: 2018-10-10; 2016-08-24: 2018-10-10; 2016-08-24: 2018-10-10; 2016-08-24: 2018-10-10; 2016-08-24: 2018-10-10; 2016-08-24: 2018-10-10
2AI101EL01100 | EOF:AG Cable laying, CP, DB'S/JB, Panels, Lighting Pole, Fixtures, Cable Glaning & Termination Electrical Works
2AI101EL01000-08070 | EOF: Earth Pit and Earth Bar Installation | [13 empty] | 2016-08-24: 2019-02-15; 2016-08-24: 2019-02-15; 2016-08-24: 2019-02-15
2AI101EL01000-08060 | EOF: Cable Marking | [27 empty] | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01
2AI101EL01000-08055 | EOF: Cable Dressing & Fastening - HV Cables | [27 empty] | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30
2AI101EL01000-08051 | EOF: Cable Spicing - HV | [27 empty] | 2017-09-28 | 2017-09-28 | 2017-09-28 | 2017-09-28 | 2017-09-28 | 2017-09-28 | 2017-09-28 | 2017-09-28 | 2017-09-28 | 2017-09-28 | 2017-09-28 | 2017-09-28 | 2017-09-28 | 2017-09-28 | 2017-09-28 | 2017-09-28 | 2017-09-28 | 2017-09-28 | 2017-09-28
2AI101EL01000-08050 | EOF: Cable Pulling - HV Cables | [27 empty] | 2017-09-26 | 2017-09-26 | 2017-09-26 | 2017-09-26 | 2017-09-26 | 2017-09-26 | 2017-09-26 | 2017-09-26 | 2017-09-26 | 2017-09-26 | 2017-09-26 | 2017-09-26 | 2017-09-26 | 2017-09-26 | 2017-09-26 | 2017-09-26 | 2017-09-26 | 2017-09-26 | 2017-09-26
2AI101EL01000-08045 | EOF: Cable Drum Checks & Transport to Site- HV Cables | [27 empty] | 2017-09-26 | 2017-09-26 | 2017-09-26 | 2017-09-26 | 2017-09-26 | 2017-09-26 | 2017-09-26 | 2017-09-26 | 2017-09-26 | 2017-09-26 | 2017-09-26 | 2017-09-26 | 2017-09-26 | 2017-09-26 | 2017-09-26 | 2017-09-26 | 2017-09-26 | 2017-09-26 | 2017-09-26
2AI101EL01000-08040 | EOF: Cable Marking | [27 empty] | 2017-09-26: 2019-02-03; 2017-09-26: 2019-02-03; 2017-09-26: 2019-02-03
2AI101EL01000-08030 | EOF: Base/Insulated earthing cable thermoweld jointing/connections | [33 empty] | 2018-05-16 | 2018-05-16 | 2018-05-16 | 2018-05-16 | 2018-05-16 | 2018-05-16 | 2018-05-16 | 2018-05-16 | 2018-05-16 | 2018-05-16 | 2018-05-16 | 2018-05-16 | 2018-05-16
2AI101EL01000-08025 | EOF: Cable Pulling - Base/Insulated earthing | [33 empty] | 2018-05-16: 2019-03-07; 2018-05-16: 2019-03-07; 2018-05-16: 2019-03-07
2AI101EL01000-08024 | EOF: Cable Drum Checks & Transport to Site- earthing Cables | [33 empty] | 2018-05-16: 2019-04-10
2AI101EL01000-08010 | EOF: Cable Dressing & Fastening - LV Cables | [33 empty] | 2018-05-16: 2019-02-02; 2018-05-16: 2019-02-02; 2018-05-16: 2019-02-02
2AI101EL01000-08005 | EOF: Cable Pulling - LV Cables | [33 empty] | 2018-05-16: 2019-02-02; 2018-05-16: 2019-02-02; 2018-05-16: 2019-02-02
2AI101EL01000-08001 | EOF: Cable Drum Checks & Transport to Site- LV Cables | [33 empty] | 2018-05-16: 2018-10-20; 2018-05-16: 2018-10-20; 2018-05-16: 2018-10-20; 2018-05-16: 2018-10-20; 2018-05-16: 2018-10-20; 2018-05-16: 2018-10-20; 2018-05-16: 2018-10-20
2AI101EL01000-08000 | EOF: UG Electrical cable Works | [33 empty] | 2018-05-16: 2019-04-10
2AI101EL01000 | EOF: UG Electrical cable Works | [33 empty] | 2018-05-16: 2019-04-10
2AI101CV22300-08055 | EOF:Backfilling & Compaction for Fnd | [19 empty] | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10
2AI101CV22300-08050 | EOF:Concrete Potection for Fnd | [19 empty] | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07
2AI101CV22300-08046 | EOF:Concrete Pouring - for Pedestal | [19 empty] | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27
2AI101CV22300-08045 | EOF:Rebar, Formwork, Install Embedments for Pedestal | [19 empty] | 2017-02-20 | 2017-02-20 | 2017-02-20 | 2017-02-20 | 2017-02-20 | 2017-02-20 | 2017-02-20 | 2017-02-20 | 2017-02-20 | 2017-02-20 | 2017-02-20 | 2017-02-20 | 2017-02-20 | 2017-02-20 | 2017-02-20 | 2017-02-20 | 2017-02-20 | 2017-02-20 | 2017-02-20 | 2017-02-20 | 2017-02-20 | 2017-02-20 | 2017-02-20 | 2017-02-20 | 2017-02-20 | 2017-02-20 | 2017-02-20
2AI101CV22300-08041 | EOF:Concrete Pouring - for Footing | [19 empty] | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16
2AI101CV22300-08040 | EOF:Rebar, Formwork for Footing | [19 empty] | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15
2AI101CV22300-08035 | EOF:Blinding/PCC for Fnd | [19 empty] | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11
2AI101CV22300-08030 | EOF:Survey Marking, Excavation & Subgrade | [17 empty] | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06
2AI101CV22300-08025 | EOF:Backfilling & Compaction for Fnd | [19 empty] | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10
2AI101CV22300-08020 | EOF:Concrete Potection for Fnd | [19 empty] | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07
2AI101CV22300-08016 | EOF:Concrete Pouring - for Pedestal | [19 empty] | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27
2AI101CV22300-08015 | EOF:Rebar, Formwork, Install Embedments for Pedestal | [19 empty] | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23
2AI101CV22300-08011 | EOF:Concrete Pouring - for Footing | [19 empty] | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16
2AI101CV22300-08010 | EOF:Rebar, Formwork for Footing | [19 empty] | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15
2AI101CV22300-08006 | EOF:Blinding/PCC for Fnd | [19 empty] | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11
2AI101CV22300-08005 | EOF: 621-G-302 C/D Foam Pump House Steel Building Foundation | [19 empty] | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10
2AI101CV22300-08001 | EOF:Survey Marking, Excavation & Subgrade | [17 empty] | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30
2AI101CV22300-08000 | EOF: 621-G-302 A/B Foam Pump House Steel Building Foundation | [19 empty] | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10
2AI101CV22300 | EOF: Foam Pump House Building Foundation | [19 empty] | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10
2AI101CV22200-08055 | EOF:Backfilling & Compaction for Fnd | [19 empty] | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07
2AI101CV22200-08050 | EOF:Concrete Potection for Fnd | [19 empty] | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06
2AI101CV22200-08046 | EOF:Concrete Pouring - for Pedestal | [19 empty] | 2017-02-14 | 2017-02-14 | 2017-02-14 | 2017-02-14 | 2017-02-14 | 2017-02-14 | 2017-02-14 | 2017-02-14 | 2017-02-14 | 2017-02-14 | 2017-02-14 | 2017-02-14 | 2017-02-14 | 2017-02-14 | 2017-02-14 | 2017-02-14 | 2017-02-14 | 2017-02-14 | 2017-02-14 | 2017-02-14 | 2017-02-14 | 2017-02-14 | 2017-02-14 | 2017-02-14 | 2017-02-14 | 2017-02-14 | 2017-02-14
2AI101CV22200-08045 | EOF:Rebar, Formwork, Install Embedments for Pedestal | [19 empty] | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13
2AI101CV22200-08041 | EOF:Concrete Pouring - for Footing | [19 empty] | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08
2AI101CV22200-08040 | EOF:Rebar, Formwork for Footing | [19 empty] | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07
2AI101CV22200-08035 | EOF:Blinding/PCC for Fnd | [19 empty] | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05
2AI101CV22200-08030 | EOF:Survey Marking, Excavation & Subgrade | [19 empty] | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04
2AI101CV22200-08025 | EOF:Backfilling & Compaction for Fnd | [19 empty] | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07
2AI101CV22200-08020 | EOF:Concrete Potection for Fnd | [19 empty] | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06
2AI101CV22200-08016 | EOF:Concrete Pouring - for Pedestal | [19 empty] | 2017-02-14 | 2017-02-14 | 2017-02-14 | 2017-02-14 | 2017-02-14 | 2017-02-14 | 2017-02-14 | 2017-02-14 | 2017-02-14 | 2017-02-14 | 2017-02-14 | 2017-02-14 | 2017-02-14 | 2017-02-14 | 2017-02-14 | 2017-02-14 | 2017-02-14 | 2017-02-14 | 2017-02-14 | 2017-02-14 | 2017-02-14 | 2017-02-14 | 2017-02-14 | 2017-02-14 | 2017-02-14 | 2017-02-14 | 2017-02-14
2AI101CV22200-08015 | EOF:Rebar, Formwork, Install Embedments for Pedestal | [19 empty] | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13
2AI101CV22200-08011 | EOF:Concrete Pouring - for Footing | [19 empty] | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08
2AI101CV22200-08010 | EOF:Rebar, Formwork for Footing | [19 empty] | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07
2AI101CV22200-08006 | EOF:Blinding/PCC for Fnd | [19 empty] | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05
2AI101CV22200-08005 | EOF: Trim Pump - 52-G-301B Shelter Foundation | [19 empty] | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07
2AI101CV22200-08001 | EOF:Survey Marking, Excavation & Subgrade | [19 empty] | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04
2AI101CV22200-08000 | EOF: Trim Pump - 52-G-301A Shelter Foundation | [19 empty] | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07
2AI101CV22200 | EOF: Pump Shelter Foundation | [19 empty] | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07
2AI101CV22100-08025 | EOF:Grouting of 621-G-302 B Trim Pump Shelter | [19 empty] | 2017-03-07: 2018-10-10; 2017-03-07: 2018-10-10; 2017-03-07: 2018-10-10; 2017-03-07: 2018-10-10; 2017-03-07: 2018-10-10; 2017-03-07: 2018-10-10; 2017-03-07: 2018-10-10
2AI101CV22100-08020 | EOF:Alignment & Bolting/Torqueing for 621-G-302 B Trim Pump Shelter | [35 empty] | 2018-06-30 | 2018-06-30 | 2018-06-30 | 2018-06-30 | 2018-06-30 | 2018-06-30 | 2018-06-30 | 2018-06-30 | 2018-06-30 | 2018-06-30 | 2018-06-30
2AI101CV22100-08015 | EOF:Installation of Str. Steel for 621-G-302 B Trim Pump Shelter | [33 empty] | 2018-04-26 | 2018-04-26 | 2018-04-26 | 2018-04-26 | 2018-04-26 | 2018-04-26 | 2018-04-26 | 2018-04-26 | 2018-04-26 | 2018-04-26 | 2018-04-26 | 2018-04-26 | 2018-04-26
2AI101CV22100-08010 | EOF:Grouting of 621-G-302 A Trim Pump Shelter | [33 empty] | 2018-04-26: 2018-10-10; 2018-04-26: 2018-10-10; 2018-04-26: 2018-10-10; 2018-04-26: 2018-10-10; 2018-04-26: 2018-10-10; 2018-04-26: 2018-10-10; 2018-04-26: 2018-10-10
2AI101CV22100-08006 | EOF:Alignment & Bolting/Torqueing for 621-G-302 A Trim Pump Shelter | [33 empty] | 2018-04-12 | 2018-04-12 | 2018-04-12 | 2018-04-12 | 2018-04-12 | 2018-04-12 | 2018-04-12 | 2018-04-12 | 2018-04-12 | 2018-04-12 | 2018-04-12 | 2018-04-12 | 2018-04-12
2AI101CV22100-08005 | EOF: 621-G-302 B Trim Pump Shelter | [33 empty] | 2018-04-12: 2018-10-10; 2018-04-12: 2018-10-10; 2018-04-12: 2018-10-10; 2018-04-12: 2018-10-10; 2018-04-12: 2018-10-10; 2018-04-12: 2018-10-10; 2018-04-12: 2018-10-10
2AI101CV22100-08001 | EOF:Installation of Str. Steel for 621-G-302 A Trim Pump Shelter | [33 empty] | 2018-04-09 | 2018-04-09 | 2018-04-09 | 2018-04-09 | 2018-04-09 | 2018-04-09 | 2018-04-09 | 2018-04-09 | 2018-04-09 | 2018-04-09 | 2018-04-09 | 2018-04-09 | 2018-04-09
2AI101CV22100-08000 | EOF: 621-G-302 A Trim Pump Shelter | [33 empty] | 2018-04-09: 2018-10-10; 2018-04-09: 2018-10-10; 2018-04-09: 2018-10-10; 2018-04-09: 2018-10-10; 2018-04-09: 2018-10-10; 2018-04-09: 2018-10-10; 2018-04-09: 2018-10-10
2AI101CV22100 | EOF: Pump Shelter | [33 empty] | 2018-04-09: 2018-10-10; 2018-04-09: 2018-10-10; 2018-04-09: 2018-10-10; 2018-04-09: 2018-10-10; 2018-04-09: 2018-10-10; 2018-04-09: 2018-10-10; 2018-04-09: 2018-10-10
2AI101CV22000-08055 | EOF:Backfilling & Compaction for Fnd | [19 empty] | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07
2AI101CV22000-08050 | EOF:Concrete Potection for Fnd | [19 empty] | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23
2AI101CV22000-08046 | EOF:Concrete Pouring - for Pedestal | [19 empty] | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02
2AI101CV22000-08045 | EOF:Rebar, Formwork, Install Embedments for Pedestal | [19 empty] | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01
2AI101CV22000-08041 | EOF:Concrete Pouring - for Footing | [19 empty] | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02
2AI101CV22000-08040 | EOF:Rebar, Formwork for Footing | [19 empty] | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01
2AI101CV22000-08035 | EOF:Blinding/PCC for Fnd | [17 empty] | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17
2AI101CV22000-08030 | EOF:Survey Marking, Excavation & Subgrade | [17 empty] | 2016-12-14 | 2016-12-14 | 2016-12-14 | 2016-12-14 | 2016-12-14 | 2016-12-14 | 2016-12-14 | 2016-12-14 | 2016-12-14 | 2016-12-14 | 2016-12-14 | 2016-12-14 | 2016-12-14 | 2016-12-14 | 2016-12-14 | 2016-12-14 | 2016-12-14 | 2016-12-14 | 2016-12-14 | 2016-12-14 | 2016-12-14 | 2016-12-14 | 2016-12-14 | 2016-12-14 | 2016-12-14 | 2016-12-14 | 2016-12-14 | 2016-12-14 | 2016-12-14
2AI101CV22000-08025 | EOF:Backfilling & Compaction for Fnd | [19 empty] | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07
2AI101CV22000-08020 | EOF:Concrete Potection for Fnd | [19 empty] | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23
2AI101CV22000-08016 | EOF:Concrete Pouring - for Pedestal | [19 empty] | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02
2AI101CV22000-08015 | EOF:Rebar, Formwork, Install Embedments for Pedestal | [19 empty] | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01
2AI101CV22000-08011 | EOF:Concrete Pouring - for Footing | [19 empty] | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02
2AI101CV22000-08010 | EOF:Rebar, Formwork for Footing | [19 empty] | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01
2AI101CV22000-08006 | EOF:Blinding/PCC for Fnd | [17 empty] | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17
2AI101CV22000-08005 | EOF: Foundation for Trim Pump - 52-G-301 B | [19 empty] | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07
2AI101CV22000-08001 | EOF:Survey Marking, Excavation & Subgrade | [17 empty] | 2016-12-14 | 2016-12-14 | 2016-12-14 | 2016-12-14 | 2016-12-14 | 2016-12-14 | 2016-12-14 | 2016-12-14 | 2016-12-14 | 2016-12-14 | 2016-12-14 | 2016-12-14 | 2016-12-14 | 2016-12-14 | 2016-12-14 | 2016-12-14 | 2016-12-14 | 2016-12-14 | 2016-12-14 | 2016-12-14 | 2016-12-14 | 2016-12-14 | 2016-12-14 | 2016-12-14 | 2016-12-14 | 2016-12-14 | 2016-12-14 | 2016-12-14 | 2016-12-14
2AI101CV22000-08000 | EOF: Foundation for Trim Pump - 52-G-301A | [19 empty] | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07
2AI101CV22000 | EOF: Pump Foundation | [19 empty] | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07
2AI101CV21000-08295 | EOF:Backfilling & Compaction for Fnd | [17 empty] | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02
2AI101CV21000-08290 | EOF:Concrete Potection for Fnd | [17 empty] | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04
2AI101CV21000-08286 | EOF:Concrete Pouring - for Pedestal | [17 empty] | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04
2AI101CV21000-08285 | EOF:Rebar, Formwork, Install Embedments for Pedestal | [17 empty] | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04
2AI101CV21000-08281 | EOF:Concrete Pouring - for Footing | [17 empty] | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04
2AI101CV21000-08280 | EOF:Rebar, Formwork for Footing | [17 empty] | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04
2AI101CV21000-08275 | EOF:Blinding/PCC for Fnd | [17 empty] | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04
2AI101CV21000-08270 | EOF:Survey Marking, Excavation & Subgrade | [17 empty] | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04
2AI101CV21000-08265 | EOF:Backfilling & Compaction for Fnd | [17 empty] | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04
2AI101CV21000-08260 | EOF:Concrete Potection for Fnd | [17 empty] | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04
2AI101CV21000-08256 | EOF:Concrete Pouring - for Pedestal | [17 empty] | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04
2AI101CV21000-08255 | EOF:Rebar, Formwork, Install Embedments for Pedestal | [17 empty] | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04
2AI101CV21000-08251 | EOF:Concrete Pouring - for Footing | [17 empty] | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04
2AI101CV21000-08250 | EOF:Rebar, Formwork for Footing | [17 empty] | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04
2AI101CV21000-08245 | EOF:Blinding/PCC for Fnd | [17 empty] | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04
2AI101CV21000-08240 | EOF:Survey Marking, Excavation & Subgrade | [17 empty] | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04
2AI101CV21000-08235 | EOF:Backfilling & Compaction for Fnd | [15 empty] | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09
2AI101CV21000-08230 | EOF:Concrete Potection for Fnd | [15 empty] | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21
2AI101CV21000-08226 | EOF:Concrete Pouring - for Pedestal | [15 empty] | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09
2AI101CV21000-08225 | EOF:Rebar, Formwork, Install Embedments for Pedestal | [15 empty] | 2016-11-08 | 2016-11-08 | 2016-11-08 | 2016-11-08 | 2016-11-08 | 2016-11-08 | 2016-11-08 | 2016-11-08 | 2016-11-08 | 2016-11-08 | 2016-11-08 | 2016-11-08 | 2016-11-08 | 2016-11-08 | 2016-11-08 | 2016-11-08 | 2016-11-08 | 2016-11-08 | 2016-11-08 | 2016-11-08 | 2016-11-08 | 2016-11-08 | 2016-11-08 | 2016-11-08 | 2016-11-08 | 2016-11-08 | 2016-11-08 | 2016-11-08 | 2016-11-08 | 2016-11-08 | 2016-11-08
2AI101CV21000-08221 | EOF:Concrete Pouring - for Footing | [15 empty] | 2016-11-01 | 2016-11-01 | 2016-11-01 | 2016-11-01 | 2016-11-01 | 2016-11-01 | 2016-11-01 | 2016-11-01 | 2016-11-01 | 2016-11-01 | 2016-11-01 | 2016-11-01 | 2016-11-01 | 2016-11-01 | 2016-11-01 | 2016-11-01 | 2016-11-01 | 2016-11-01 | 2016-11-01 | 2016-11-01 | 2016-11-01 | 2016-11-01 | 2016-11-01 | 2016-11-01 | 2016-11-01 | 2016-11-01 | 2016-11-01 | 2016-11-01 | 2016-11-01 | 2016-11-01 | 2016-11-01
2AI101CV21000-08220 | EOF:Rebar, Formwork for Footing | [15 empty] | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09
2AI101CV21000-08215 | EOF:Blinding/PCC for Fnd | [15 empty] | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09
2AI101CV21000-08210 | EOF:Survey Marking, Excavation & Subgrade | [15 empty] | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09
2AI101CV21000-08205 | EOF:Backfilling & Compaction for Fnd | [15 empty] | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09
2AI101CV21000-08200 | EOF:Concrete Potection for Fnd | [15 empty] | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09
2AI101CV21000-08196 | EOF:Concrete Pouring - for Pedestal | [15 empty] | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09
2AI101CV21000-08195 | EOF:Rebar, Formwork, Install Embedments for Pedestal | [15 empty] | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09
2AI101CV21000-08191 | EOF:Concrete Pouring - for Footing | [15 empty] | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09
2AI101CV21000-08190 | EOF:Rebar, Formwork for Footing | [15 empty] | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09
2AI101CV21000-08185 | EOF:Blinding/PCC for Fnd | [15 empty] | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09
2AI101CV21000-08180 | EOF:Survey Marking, Excavation & Subgrade | [15 empty] | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09
2AI101CV21000-08175 | EOF:Backfilling & Compaction for Foundation | [15 empty] | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09
2AI101CV21000-08170 | EOF:Concrete Potection for Foundation | [15 empty] | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09
2AI101CV21000-08166 | EOF:Concrete Pouring - for Pedestal | [15 empty] | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09
2AI101CV21000-08165 | EOF:Rebar, Formwork, Install Embedments for Pedestal | [15 empty] | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09
2AI101CV21000-08161 | EOF:Concrete Pouring - for Footing | [15 empty] | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09
2AI101CV21000-08160 | EOF:Rebar, Formwork for Footing | [15 empty] | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09
2AI101CV21000-08155 | EOF:Blinding/PCC for Foundation | [15 empty] | 2016-11-22 | 2016-11-22 | 2016-11-22 | 2016-11-22 | 2016-11-22 | 2016-11-22 | 2016-11-22 | 2016-11-22 | 2016-11-22 | 2016-11-22 | 2016-11-22 | 2016-11-22 | 2016-11-22 | 2016-11-22 | 2016-11-22 | 2016-11-22 | 2016-11-22 | 2016-11-22 | 2016-11-22 | 2016-11-22 | 2016-11-22 | 2016-11-22 | 2016-11-22 | 2016-11-22 | 2016-11-22 | 2016-11-22 | 2016-11-22 | 2016-11-22 | 2016-11-22 | 2016-11-22 | 2016-11-22
2AI101CV21000-08150 | EOF:Survey Marking, Excavation & Subgrade | [15 empty] | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20
2AI101CV21000-08145 | EOF:Backfilling & Compaction for Foundation | [15 empty] | 2016-11-19 | 2016-11-19 | 2016-11-19 | 2016-11-19 | 2016-11-19 | 2016-11-19 | 2016-11-19 | 2016-11-19 | 2016-11-19 | 2016-11-19 | 2016-11-19 | 2016-11-19 | 2016-11-19 | 2016-11-19 | 2016-11-19 | 2016-11-19 | 2016-11-19 | 2016-11-19 | 2016-11-19 | 2016-11-19 | 2016-11-19 | 2016-11-19 | 2016-11-19 | 2016-11-19 | 2016-11-19 | 2016-11-19 | 2016-11-19 | 2016-11-19 | 2016-11-19 | 2016-11-19 | 2016-11-19
2AI101CV21000-08140 | EOF:Concrete Potection for Foundation | [15 empty] | 2016-11-12 | 2016-11-12 | 2016-11-12 | 2016-11-12 | 2016-11-12 | 2016-11-12 | 2016-11-12 | 2016-11-12 | 2016-11-12 | 2016-11-12 | 2016-11-12 | 2016-11-12 | 2016-11-12 | 2016-11-12 | 2016-11-12 | 2016-11-12 | 2016-11-12 | 2016-11-12 | 2016-11-12 | 2016-11-12 | 2016-11-12 | 2016-11-12 | 2016-11-12 | 2016-11-12 | 2016-11-12 | 2016-11-12 | 2016-11-12 | 2016-11-12 | 2016-11-12 | 2016-11-12 | 2016-11-12
2AI101CV21000-08136 | EOF:Concrete Pouring - for Pedestal | [15 empty] | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31
2AI101CV21000-08132 | EOF:Rebar, Formwork, Install Embedments for Pedestal | [15 empty] | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09
2AI101CV21000-08131 | EOF:Concrete Pouring - for Footing | [15 empty] | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09
2AI101CV21000-08130 | EOF:Rebar, Formwork for Footing | [15 empty] | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09
2AI101CV21000-08125 | EOF:Blinding/PCC for Foundation | [15 empty] | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09
2AI101CV21000-08120 | EOF:Survey Marking, Excavation & Subgrade | [15 empty] | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09
2AI101CV21000-08115 | EOF:Backfilling & Compaction for Foundation | [15 empty] | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09
2AI101CV21000-08110 | EOF:Concrete Potection for Foundation | [15 empty] | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09
2AI101CV21000-08106 | EOF:Concrete Pouring - for Pedestal | [15 empty] | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09
2AI101CV21000-08105 | EOF:Rebar, Formwork, Install Embedments for Pedestal | [15 empty] | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09
2AI101CV21000-08101 | EOF:Concrete Pouring - for Footing | [15 empty] | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09
2AI101CV21000-08100 | EOF:Rebar, Formwork for Footing | [15 empty] | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09
2AI101CV21000-08095 | EOF:Blinding/PCC for Foundation | [15 empty] | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09
2AI101CV21000-08090 | EOF:Survey Marking, Excavation & Subgrade | [15 empty] | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09
2AI101CV21000-08085 | EOF:Backfilling & Compaction for Foundation | [15 empty] | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09
2AI101CV21000-08080 | EOF:Concrete Potection for Foundation | [15 empty] | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09
2AI101CV21000-08076 | EOF:Concrete Pouring - for Pedestal | [15 empty] | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09
2AI101CV21000-08075 | EOF:Rebar, Formwork, Install Embedments for Pedestal | [15 empty] | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09
2AI101CV21000-08071 | EOF:Concrete Pouring - for Footing | [15 empty] | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09
2AI101CV21000-08070 | EOF:Rebar, Formwork for Footing | [15 empty] | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09
2AI101CV21000-08065 | EOF:Blinding/PCC for Foundation | [15 empty] | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09
2AI101CV21000-08060 | EOF:Survey Marking, Excavation & Subgrade | [15 empty] | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09
2AI101CV21000-08055 | EOF:Backfilling & Compaction for Foundation | [19 empty] | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08
2AI101CV21000-08050 | EOF:Concrete Potection for Foundation | [19 empty] | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08
2AI101CV21000-08047 | EOF:Concrete Pouring - for Pedestal | [19 empty] | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08
2AI101CV21000-08046 | EOF:Rebar, Formwork, Install Embedments for Pedestal | [19 empty] | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08
2AI101CV21000-08045 | EOF: Foundation for Water drain tank-52-D-308B | [17 empty] | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04
2AI101CV21000-08042 | EOF:Concrete Pouring - for Footing | [19 empty] | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08
2AI101CV21000-08041 | EOF:Rebar, Formwork for Footing | [19 empty] | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08
2AI101CV21000-08040 | EOF: Foundation for Water drain tank-52-D-308A | [17 empty] | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04 | 2017-01-04
2AI101CV21000-08037 | EOF:Blinding/PCC for Foundation | [19 empty] | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08
2AI101CV21000-08036 | EOF:Backfilling & Compaction for Foundation | [19 empty] | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08
2AI101CV21000-08035 | EOF: Foundation for Flushing water drain tank-52-D-306B | [15 empty] | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21
2AI101CV21000-08032 | EOF:Survey Marking, Excavation & Subgrade | [19 empty] | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08
2AI101CV21000-08031 | EOF:Concrete Potection for Foundation | [19 empty] | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08
2AI101CV21000-08030 | EOF: Foundation for Flushing water drain tank-52-D-306A | [15 empty] | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09
2AI101CV21000-08026 | EOF:Concrete Pouring - for Pedestal | [19 empty] | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08
2AI101CV21000-08025 | EOF: Foundation for Foam drain tank-52-D-305B | [15 empty] | 2016-11-22 | 2016-11-22 | 2016-11-22 | 2016-11-22 | 2016-11-22 | 2016-11-22 | 2016-11-22 | 2016-11-22 | 2016-11-22 | 2016-11-22 | 2016-11-22 | 2016-11-22 | 2016-11-22 | 2016-11-22 | 2016-11-22 | 2016-11-22 | 2016-11-22 | 2016-11-22 | 2016-11-22 | 2016-11-22 | 2016-11-22 | 2016-11-22 | 2016-11-22 | 2016-11-22 | 2016-11-22 | 2016-11-22 | 2016-11-22 | 2016-11-22 | 2016-11-22 | 2016-11-22 | 2016-11-22
2AI101CV21000-08021 | EOF:Rebar, Formwork, Install Embedments for Pedestal | [19 empty] | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08
2AI101CV21000-08020 | EOF: Foundation for Foam drain tank-52-D-305A | [15 empty] | 2016-11-19 | 2016-11-19 | 2016-11-19 | 2016-11-19 | 2016-11-19 | 2016-11-19 | 2016-11-19 | 2016-11-19 | 2016-11-19 | 2016-11-19 | 2016-11-19 | 2016-11-19 | 2016-11-19 | 2016-11-19 | 2016-11-19 | 2016-11-19 | 2016-11-19 | 2016-11-19 | 2016-11-19 | 2016-11-19 | 2016-11-19 | 2016-11-19 | 2016-11-19 | 2016-11-19 | 2016-11-19 | 2016-11-19 | 2016-11-19 | 2016-11-19 | 2016-11-19 | 2016-11-19 | 2016-11-19
2AI101CV21000-08019 | EOF:Concrete Pouring - for Footing | [19 empty] | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08
2AI101CV21000-08018 | EOF:Rebar, Formwork for Footing | [19 empty] | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08
2AI101CV21000-08015 | EOF: Foundation for Diesel Engine drain tank-52-D-304B | [15 empty] | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09
2AI101CV21000-08010 | EOF: Foundation for Diesel Engine drain tank-52-D-304A | [15 empty] | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09
2AI101CV21000-08006 | EOF:Blinding/PCC for Foundation | [19 empty] | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08
2AI101CV21000-08005 | EOF: Foundation for OverheadWater Tank Structural (52-D-309 B) | [19 empty] | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08
2AI101CV21000-08001 | EOF:Survey Marking, Excavation & Subgrade | [19 empty] | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08
2AI101CV21000-08000 | EOF: Foundation for OverheadWater Tank Structural (52-D-309 A) | [19 empty] | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08
2AI101CV21000 | EOF: Balance Tank Foundation | [19 empty] | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08
2AI101CV18400-08511 | EOF:Install Route/saftey Markers
2AI101CV18400-08510 | EOF: Backfilling and Compaction | [19 empty] | 2017-02-08: 2018-12-08; 2017-02-08: 2018-12-08; 2017-02-08: 2018-12-08; 2017-02-08: 2018-12-08
2AI101CV18400-08505 | EOF: Bedding (incl. clean sand layer) | [19 empty] | 2017-02-08: 2018-12-05; 2017-02-08: 2018-12-05; 2017-02-08: 2018-12-05; 2017-02-08: 2018-12-05; 2017-02-08: 2018-12-05
2AI101CV18400-08500 | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material | [19 empty] | 2017-02-08: 2018-12-05; 2017-02-08: 2018-12-05; 2017-02-08: 2018-12-05; 2017-02-08: 2018-12-05; 2017-02-08: 2018-12-05
2AI101CV18400-08496 | EOF:Install Route/saftey Markers
2AI101CV18400-08495 | EOF: Backfilling and Compaction | [19 empty] | 2017-02-08: 2019-04-10
2AI101CV18400-08490 | EOF: Bedding (incl. clean sand layer) | [19 empty] | 2017-02-08: 2018-12-05; 2017-02-08: 2018-12-05; 2017-02-08: 2018-12-05; 2017-02-08: 2018-12-05; 2017-02-08: 2018-12-05
2AI101CV18400-08485 | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material | [19 empty] | 2017-02-08: 2018-12-05; 2017-02-08: 2018-12-05; 2017-02-08: 2018-12-05; 2017-02-08: 2018-12-05; 2017-02-08: 2018-12-05
2AI101CV18400-08481 | EOF:Install Route/saftey Markers
2AI101CV18400-08480 | EOF: Backfilling and Compaction | [19 empty] | 2017-02-08: 2019-04-10
2AI101CV18400-08475 | EOF: Bedding (incl. clean sand layer) | [19 empty] | 2017-02-08: 2018-12-05; 2017-02-08: 2018-12-05; 2017-02-08: 2018-12-05; 2017-02-08: 2018-12-05; 2017-02-08: 2018-12-05
2AI101CV18400-08470 | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material | [19 empty] | 2017-02-08: 2018-12-05; 2017-02-08: 2018-12-05; 2017-02-08: 2018-12-05; 2017-02-08: 2018-12-05; 2017-02-08: 2018-12-05
2AI101CV18400-08466 | EOF:Install Route/saftey Markers
2AI101CV18400-08465 | EOF: Backfilling and Compaction | [19 empty] | 2017-02-08: 2019-04-10
2AI101CV18400-08460 | EOF: Bedding (incl. clean sand layer) | [19 empty] | 2017-02-08: 2018-12-05; 2017-02-08: 2018-12-05; 2017-02-08: 2018-12-05; 2017-02-08: 2018-12-05; 2017-02-08: 2018-12-05
2AI101CV18400-08455 | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material | [19 empty] | 2017-02-08: 2018-12-05; 2017-02-08: 2018-12-05; 2017-02-08: 2018-12-05; 2017-02-08: 2018-12-05; 2017-02-08: 2018-12-05
2AI101CV18400-08451 | EOF:Install Route/saftey Markers
2AI101CV18400-08450 | EOF: Backfilling and Compaction | [35 empty] | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04
2AI101CV18400-08445 | EOF: Bedding (incl. clean sand layer) | [35 empty] | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04
2AI101CV18400-08440 | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material | [33 empty] | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07
2AI101CV18400-08436 | EOF:Install Route/saftey Markers
2AI101CV18400-08431 | EOF: Backfilling and Compaction | [35 empty] | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04 | 2018-07-04
2AI101CV18400-08430 | EOF: Bedding (incl. clean sand layer) | [33 empty] | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08
2AI101CV18400-08425 | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material | [33 empty] | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06
2AI101CV18400-08365 | EOF:Backfilling & Compaction for Foundation | [11 empty] | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03
2AI101CV18400-08360 | EOF:Concrete Potection for Foundation | [9 empty] | 2016-04-01 | 2016-04-01 | 2016-04-01 | 2016-04-01 | 2016-04-01 | 2016-04-01 | 2016-04-01 | 2016-04-01 | 2016-04-01 | 2016-04-01 | 2016-04-01 | 2016-04-01 | 2016-04-01 | 2016-04-01 | 2016-04-01 | 2016-04-01 | 2016-04-01 | 2016-04-01 | 2016-04-01 | 2016-04-01 | 2016-04-01 | 2016-04-01 | 2016-04-01 | 2016-04-01 | 2016-04-01 | 2016-04-01 | 2016-04-01 | 2016-04-01 | 2016-04-01 | 2016-04-01 | 2016-04-01 | 2016-04-01 | 2016-04-01 | 2016-04-01 | 2016-04-01 | 2016-04-01 | 2016-04-01
2AI101CV18400-08355 | EOF:Concrete Pouring - for Footing | [9 empty] | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27
2AI101CV18400-08350 | EOF:Rebar & Formwork - for Footing | [9 empty] | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27
2AI101CV18400-08346 | EOF:Blinding/PCC for Foundation | [9 empty] | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26
2AI101CV18400-08345 | EOF:Survey Marking, Excavation & Subgrade | [7 empty] | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24
2AI101CV18400-08331 | EOF:Install Route/saftey Markers
2AI101CV18400-08326 | EOF: Backfilling and Compaction | [7 empty] | 2016-03-24: 2019-02-06; 2016-03-24: 2019-02-06; 2016-03-24: 2019-02-06
2AI101CV18400-08325 | EOF: Bedding (incl. clean sand layer) | [31 empty] | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07
2AI101CV18400-08320 | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material | [31 empty] | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07
2AI101CV18400-08316 | EOF:Install Route/saftey Markers
2AI101CV18400-08311 | EOF: Backfilling and Compaction | [31 empty] | 2018-02-07: 2019-01-26; 2018-02-07: 2019-01-26; 2018-02-07: 2019-01-26
2AI101CV18400-08310 | EOF: Bedding (incl. clean sand layer) | [31 empty] | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07
2AI101CV18400-08305 | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material | [31 empty] | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07
2AI101CV18400-08301 | EOF:Install Route/saftey Markers
2AI101CV18400-08296 | EOF: Backfilling and Compaction | [31 empty] | 2018-02-07: 2019-04-10
2AI101CV18400-08295 | EOF: Bedding (incl. clean sand layer) | [29 empty] | 2017-11-30 | 2017-11-30 | 2017-11-30 | 2017-11-30 | 2017-11-30 | 2017-11-30 | 2017-11-30 | 2017-11-30 | 2017-11-30 | 2017-11-30 | 2017-11-30 | 2017-11-30 | 2017-11-30 | 2017-11-30 | 2017-11-30 | 2017-11-30 | 2017-11-30
2AI101CV18400-08290 | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material | [29 empty] | 2017-11-28 | 2017-11-28 | 2017-11-28 | 2017-11-28 | 2017-11-28 | 2017-11-28 | 2017-11-28 | 2017-11-28 | 2017-11-28 | 2017-11-28 | 2017-11-28 | 2017-11-28 | 2017-11-28 | 2017-11-28 | 2017-11-28 | 2017-11-28 | 2017-11-28
2AI101CV18400-08286 | EOF:Install Route/saftey Markers
2AI101CV18400-08281 | EOF: Backfilling and Compaction | [29 empty] | 2017-11-28: 2019-02-06; 2017-11-28: 2019-02-06; 2017-11-28: 2019-02-06
2AI101CV18400-08280 | EOF: Bedding (incl. clean sand layer) | [29 empty] | 2017-12-07 | 2017-12-07 | 2017-12-07 | 2017-12-07 | 2017-12-07 | 2017-12-07 | 2017-12-07 | 2017-12-07 | 2017-12-07 | 2017-12-07 | 2017-12-07 | 2017-12-07 | 2017-12-07 | 2017-12-07 | 2017-12-07 | 2017-12-07 | 2017-12-07
2AI101CV18400-08275 | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material | [29 empty] | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06
2AI101CV18400-08270 | EOF:Install Route/saftey Markers | [27 empty] | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08
2AI101CV18400-08265 | EOF:Backfilling & Compaction | [27 empty] | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08
2AI101CV18400-08260 | EOF:Install Cable Tile Laying & warning Tapes | [27 empty] | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08
2AI101CV18400-08256 | EOF:Sand Padding | [27 empty] | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08
2AI101CV18400-08255 | EOF:Sand bedding | [27 empty] | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08
2AI101CV18400-08250 | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material | [27 empty] | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08
2AI101CV18400-08245 | EOF:Install Route/saftey Markers | [27 empty] | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08
2AI101CV18400-08240 | EOF:Backfilling & Compaction | [27 empty] | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08
2AI101CV18400-08235 | EOF:Install Cable Tile Laying & warning Tapes | [27 empty] | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08
2AI101CV18400-08231 | EOF:Sand Padding | [27 empty] | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08
2AI101CV18400-08230 | EOF:Sand bedding | [27 empty] | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08
2AI101CV18400-08225 | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material | [27 empty] | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08
2AI101CV18400-08220 | EOF:Install Route/saftey Markers | [27 empty] | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08
2AI101CV18400-08215 | EOF:Backfilling & Compaction | [27 empty] | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08
2AI101CV18400-08210 | EOF:Install Cable Tile Laying & warning Tapes | [27 empty] | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08
2AI101CV18400-08206 | EOF:Sand Padding | [27 empty] | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08
2AI101CV18400-08205 | EOF:Sand bedding | [27 empty] | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08
2AI101CV18400-08200 | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material | [27 empty] | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08
2AI101CV18400-08195 | EOF:Install Route/saftey Markers | [27 empty] | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08
2AI101CV18400-08190 | EOF:Backfilling & Compaction | [27 empty] | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08
2AI101CV18400-08185 | EOF:Install Cable Tile Laying & warning Tapes | [27 empty] | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08
2AI101CV18400-08181 | EOF:Sand Padding | [27 empty] | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08
2AI101CV18400-08180 | EOF:Sand bedding | [27 empty] | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08
2AI101CV18400-08175 | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material | [27 empty] | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08
2AI101CV18400-08170 | EOF:Install Route/saftey Markers
2AI101CV18400-08165 | EOF:Backfilling & Compaction
2AI101CV18400-08160 | EOF:Install Cable Tile Laying & warning Tapes
2AI101CV18400-08156 | EOF:Sand Padding
2AI101CV18400-08155 | EOF:Sand bedding
2AI101CV18400-08150 | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material
2AI101CV18400-08145 | EOF:Install Route/saftey Markers
2AI101CV18400-08140 | EOF:Backfilling & Compaction
2AI101CV18400-08135 | EOF:Install Cable Tile Laying & warning Tapes
2AI101CV18400-08131 | EOF:Sand Padding
2AI101CV18400-08130 | EOF:Sand bedding
2AI101CV18400-08125 | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material
2AI101CV18400-08120 | EOF:Install Route/saftey Markers | [35 empty] | 2018-07-01 | 2018-07-01 | 2018-07-01 | 2018-07-01 | 2018-07-01 | 2018-07-01 | 2018-07-01 | 2018-07-01 | 2018-07-01 | 2018-07-01 | 2018-07-01
2AI101CV18400-08115 | EOF:Backfilling & Compaction | [35 empty] | 2018-07-01 | 2018-07-01 | 2018-07-01 | 2018-07-01 | 2018-07-01 | 2018-07-01 | 2018-07-01 | 2018-07-01 | 2018-07-01 | 2018-07-01 | 2018-07-01
2AI101CV18400-08110 | EOF:Install Cable Tile Laying & warning Tapes | [35 empty] | 2018-07-01 | 2018-07-01 | 2018-07-01 | 2018-07-01 | 2018-07-01 | 2018-07-01 | 2018-07-01 | 2018-07-01 | 2018-07-01 | 2018-07-01 | 2018-07-01
2AI101CV18400-08106 | EOF:Sand Padding | [35 empty] | 2018-07-01 | 2018-07-01 | 2018-07-01 | 2018-07-01 | 2018-07-01 | 2018-07-01 | 2018-07-01 | 2018-07-01 | 2018-07-01 | 2018-07-01 | 2018-07-01
2AI101CV18400-08105 | EOF:Sand bedding | [35 empty] | 2018-07-01 | 2018-07-01 | 2018-07-01 | 2018-07-01 | 2018-07-01 | 2018-07-01 | 2018-07-01 | 2018-07-01 | 2018-07-01 | 2018-07-01 | 2018-07-01
2AI101CV18400-08100 | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material | [35 empty] | 2018-06-14 | 2018-06-14 | 2018-06-14 | 2018-06-14 | 2018-06-14 | 2018-06-14 | 2018-06-14 | 2018-06-14 | 2018-06-14 | 2018-06-14 | 2018-06-14
2AI101CV18400-08095 | EOF:Install Route/saftey Markers | [15 empty] | 2016-10-13 | 2016-10-13 | 2016-10-13 | 2016-10-13 | 2016-10-13 | 2016-10-13 | 2016-10-13 | 2016-10-13 | 2016-10-13 | 2016-10-13 | 2016-10-13 | 2016-10-13 | 2016-10-13 | 2016-10-13 | 2016-10-13 | 2016-10-13 | 2016-10-13 | 2016-10-13 | 2016-10-13 | 2016-10-13 | 2016-10-13 | 2016-10-13 | 2016-10-13 | 2016-10-13 | 2016-10-13 | 2016-10-13 | 2016-10-13 | 2016-10-13 | 2016-10-13 | 2016-10-13 | 2016-10-13
2AI101CV18400-08090 | EOF:Backfilling & Compaction | [11 empty] | 2016-07-05 | 2016-07-05 | 2016-07-05 | 2016-07-05 | 2016-07-05 | 2016-07-05 | 2016-07-05 | 2016-07-05 | 2016-07-05 | 2016-07-05 | 2016-07-05 | 2016-07-05 | 2016-07-05 | 2016-07-05 | 2016-07-05 | 2016-07-05 | 2016-07-05 | 2016-07-05 | 2016-07-05 | 2016-07-05 | 2016-07-05 | 2016-07-05 | 2016-07-05 | 2016-07-05 | 2016-07-05 | 2016-07-05 | 2016-07-05 | 2016-07-05 | 2016-07-05 | 2016-07-05 | 2016-07-05 | 2016-07-05 | 2016-07-05 | 2016-07-05 | 2016-07-05
2AI101CV18400-08085 | EOF:Install Cable Tile Laying & warning Tapes | [11 empty] | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04
2AI101CV18400-08081 | EOF:Sand Padding | [9 empty] | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26
2AI101CV18400-08080 | EOF:Sand bedding | [9 empty] | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26
2AI101CV18400-08075 | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material | [7 empty] | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23
2AI101CV18400-08071 | EOF:Install Route/saftey Markers
2AI101CV18400-08070 | EOF: Backfilling and Compaction
2AI101CV18400-08065 | EOF: Bedding (incl. clean sand layer) | [33 empty] | 2018-05-03 | 2018-05-03 | 2018-05-03 | 2018-05-03 | 2018-05-03 | 2018-05-03 | 2018-05-03 | 2018-05-03 | 2018-05-03 | 2018-05-03 | 2018-05-03 | 2018-05-03 | 2018-05-03
2AI101CV18400-08060 | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material | [33 empty] | 2018-05-03 | 2018-05-03 | 2018-05-03 | 2018-05-03 | 2018-05-03 | 2018-05-03 | 2018-05-03 | 2018-05-03 | 2018-05-03 | 2018-05-03 | 2018-05-03 | 2018-05-03 | 2018-05-03
2AI101CV18400-08056 | EOF:Install Route/saftey Markers
2AI101CV18400-08055 | EOF: Backfilling and Compaction
2AI101CV18400-08050 | EOF: Bedding (incl. clean sand layer) | [33 empty] | 2018-05-03: 2018-11-25; 2018-05-03: 2018-11-25; 2018-05-03: 2018-11-25; 2018-05-03: 2018-11-25; 2018-05-03: 2018-11-25
2AI101CV18400-08045 | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material | [33 empty] | 2018-05-03: 2018-11-24; 2018-05-03: 2018-11-24; 2018-05-03: 2018-11-24; 2018-05-03: 2018-11-24; 2018-05-03: 2018-11-24
2AI101CV18400-08041 | EOF:Install Route/saftey Markers
2AI101CV18400-08036 | EOF: Backfilling and Compaction | [33 empty] | 2018-05-03: 2019-03-06; 2018-05-03: 2019-03-06; 2018-05-03: 2019-03-06
2AI101CV18400-08035 | EOF: Bedding (incl. clean sand layer) | [33 empty] | 2018-05-03: 2018-11-07; 2018-05-03: 2018-11-07; 2018-05-03: 2018-11-07; 2018-05-03: 2018-11-07; 2018-05-03: 2018-11-07; 2018-05-03: 2018-11-07; 2018-05-03: 2018-11-07
2AI101CV18400-08030 | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material | [33 empty] | 2018-05-03: 2018-11-07; 2018-05-03: 2018-11-07; 2018-05-03: 2018-11-07; 2018-05-03: 2018-11-07; 2018-05-03: 2018-11-07; 2018-05-03: 2018-11-07; 2018-05-03: 2018-11-07
2AI101CV18400-08026 | EOF:Install Route/saftey Markers
2AI101CV18400-08021 | EOF: Backfilling and Compaction | [33 empty] | 2018-05-03: 2019-02-06; 2018-05-03: 2019-02-06; 2018-05-03: 2019-02-06
2AI101CV18400-08020 | EOF: Bedding (incl. clean sand layer) | [33 empty] | 2018-05-03: 2018-12-05; 2018-05-03: 2018-12-05; 2018-05-03: 2018-12-05; 2018-05-03: 2018-12-05; 2018-05-03: 2018-12-05
2AI101CV18400-08015 | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material | [33 empty] | 2018-05-03: 2018-11-07; 2018-05-03: 2018-11-07; 2018-05-03: 2018-11-07; 2018-05-03: 2018-11-07; 2018-05-03: 2018-11-07; 2018-05-03: 2018-11-07; 2018-05-03: 2018-11-07
2AI101CV18400-08013 | EOF:Install Route/saftey Markers
2AI101CV18400-08010 | EOF: Foundation for Relocation of existing RMU | [11 empty] | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03
2AI101CV18400-08007 | EOF: Backfilling and Compaction
2AI101CV18400-08006 | EOF: Bedding (incl. clean sand layer) | [11 empty] | 2016-07-03: 2018-11-09; 2016-07-03: 2018-11-09; 2016-07-03: 2018-11-09; 2016-07-03: 2018-11-09; 2016-07-03: 2018-11-09; 2016-07-03: 2018-11-09; 2016-07-03: 2018-11-09
2AI101CV18400-08005 | EOF: EIT Cable Trench
2AI101CV18400-08001 | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material | [11 empty] | 2016-07-03: 2018-11-07; 2016-07-03: 2018-11-07; 2016-07-03: 2018-11-07; 2016-07-03: 2018-11-07; 2016-07-03: 2018-11-07; 2016-07-03: 2018-11-07; 2016-07-03: 2018-11-07
2AI101CV18400-08000 | EOF: Pipe Trench
2AI101CV18400 | EOF: UG Trench and Other Civl Worrks
2AI101CV18200-08000 | EOF: Touch-up painting of Structures
2AI101CV18200 | EOF: Touch-up painting of Structures
2AI101CV11000-08030 | EOF:Backfilling & Compaction Around Sump | [15 empty] | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09
2AI101CV11000-08025 | EOF:Cover slab for Sump | [15 empty] | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03
2AI101CV11000-08020 | EOF:Concrete Protection for Sump | [15 empty] | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03
2AI101CV11000-08016 | EOF:Concrete Pouring for Wall of Sump | [15 empty] | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18
2AI101CV11000-08015 | EOF:Rebar, Formwork for wall of Sump | [15 empty] | 2016-10-17 | 2016-10-17 | 2016-10-17 | 2016-10-17 | 2016-10-17 | 2016-10-17 | 2016-10-17 | 2016-10-17 | 2016-10-17 | 2016-10-17 | 2016-10-17 | 2016-10-17 | 2016-10-17 | 2016-10-17 | 2016-10-17 | 2016-10-17 | 2016-10-17 | 2016-10-17 | 2016-10-17 | 2016-10-17 | 2016-10-17 | 2016-10-17 | 2016-10-17 | 2016-10-17 | 2016-10-17 | 2016-10-17 | 2016-10-17 | 2016-10-17 | 2016-10-17 | 2016-10-17 | 2016-10-17
2AI101CV11000-08011 | EOF:Concrete Pouring for base of Sump | [15 empty] | 2016-09-30 | 2016-09-30 | 2016-09-30 | 2016-09-30 | 2016-09-30 | 2016-09-30 | 2016-09-30 | 2016-09-30 | 2016-09-30 | 2016-09-30 | 2016-09-30 | 2016-09-30 | 2016-09-30 | 2016-09-30 | 2016-09-30 | 2016-09-30 | 2016-09-30 | 2016-09-30 | 2016-09-30 | 2016-09-30 | 2016-09-30 | 2016-09-30 | 2016-09-30 | 2016-09-30 | 2016-09-30 | 2016-09-30 | 2016-09-30 | 2016-09-30 | 2016-09-30 | 2016-09-30 | 2016-09-30
2AI101CV11000-08010 | EOF:Rebar, Formwork for base of Sump | [13 empty] | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27
2AI101CV11000-08005 | EOF:Blinding/PCC for Sump Fnd | [11 empty] | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21
2AI101CV11000-08001 | EOF:Excavation & Subgrade for Sump | [11 empty] | 2016-07-16 | 2016-07-16 | 2016-07-16 | 2016-07-16 | 2016-07-16 | 2016-07-16 | 2016-07-16 | 2016-07-16 | 2016-07-16 | 2016-07-16 | 2016-07-16 | 2016-07-16 | 2016-07-16 | 2016-07-16 | 2016-07-16 | 2016-07-16 | 2016-07-16 | 2016-07-16 | 2016-07-16 | 2016-07-16 | 2016-07-16 | 2016-07-16 | 2016-07-16 | 2016-07-16 | 2016-07-16 | 2016-07-16 | 2016-07-16 | 2016-07-16 | 2016-07-16 | 2016-07-16 | 2016-07-16 | 2016-07-16 | 2016-07-16 | 2016-07-16 | 2016-07-16
2AI101CV11000-08000 | EOF: Oily Water Collection Vessel Sump (52-SU-301) Construction | [15 empty] | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09
2AI101CV11000 | EOF: Construction of Sump | [15 empty] | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09
2AI101CV03100-08040 | EOF: Fire Proofing of Diesel Generator Day Tank - 52-R-303
2AI101CV03100-08035 | EOF: Fire Proofing of Diesel Generator Day Tank - 52-R-301
2AI101CV03100-08030 | EOF: Fire Proofing of Trimp Pump - 621-G-301
2AI101CV03100-08025 | EOF: Fire Proofing of Diesel Generator Day Tank - 52-R-302
2AI101CV03100-08020 | EOF: Fire Proofing of Diesel Generator Day Tank - 50-R-002
2AI101CV03100-08015 | EOF: Fire Proofing of LFHO at Storage Tank - 52-D-96 Area
2AI101CV03100-08010 | EOF: Fire Proofing of LFHO at Storage Tank - 52-D-95 Area
2AI101CV03100-08005 | EOF: Fire Proofing of LFHO at Storage Tank - 52-D-94 Area
2AI101CV03100-08000 | EOF: Fire Proofing of LFHO at Storage Tank - 52-D-93 Area
2AI101CV03100 | EOF: Fire Proofing of Structures/equipments
2AI101CV02100-08065 | EOF:Asphalt Lining for Inside slope for Bund Wall 52-D-96 & 52-D-95
2AI101CV02100-08060 | EOF:Rebar, Form work & Concreting for Stair cases for Bund Wall around Storage tank 52-D-96 & 52-D-95
2AI101CV02100-08055 | EOF:Prepare Access ramp (with Compact fill & Gatch layer) for Bund Wall around Storage tank 52-D-96 & 52-D-95 | [15 empty] | 2016-11-09: 2019-01-20; 2016-11-09: 2019-01-20; 2016-11-09: 2019-01-20; 2016-11-09: 2019-01-20; 2016-11-09: 2019-01-20
2AI101CV02100-08050 | EOF:Gatch Filling & Compaction for Bund Wall around Storage tank 52-D-96 & 52-D-95
2AI101CV02100-08045 | EOF:Install Linar Membrane (incl. base & inside slope) for Bund Wall around Storage tank 52-D-96 & 52-D-95
2AI101CV02100-08040 | EOF:Sand layer (Inside) upto Linear Menbrane Lvl for Bund Wall around Storage tank 52-D-96 & 52-D-95
2AI101CV02100-08035 | EOF:Lay Drain Pipe (CB to Valve pit) for Bund Wall around Storage tank 52-D-96 & 52-D-95 | [15 empty] | 2016-11-09: 2018-10-10; 2016-11-09: 2018-10-10; 2016-11-09: 2018-10-10; 2016-11-09: 2018-10-10; 2016-11-09: 2018-10-10; 2016-11-09: 2018-10-10; 2016-11-09: 2018-10-10
2AI101CV02100-08030 | EOF:Install/Cast Catch basin (inside) & Valve pit (outside) for Bund Wall around Storage tank 52-D-96 & 52-D-95 | [15 empty] | 2016-11-09: 2018-12-19; 2016-11-09: 2018-12-19; 2016-11-09: 2018-12-19; 2016-11-09: 2018-12-19; 2016-11-09: 2018-12-19
2AI101CV02100-08025 | EOF:Slope Preparation for Bund Wall around Storage tank 52-D-96 & 52-D-95 | [15 empty] | 2016-11-09: 2019-04-10
2AI101CV02100-08020 | EOF: Prepare Subgrade lvl for Bund Wall around Storage tank 52-D-96 & 52-D-95 | [15 empty] | 2016-11-09: 2019-02-06; 2016-11-09: 2019-02-06; 2016-11-09: 2019-02-06
2AI101CV02100-08015 | EOF: Survey Marking, Excavation & Disposal of unsutiable Material for Bund Wall around Storage tank 52-D-96 & 52-D-95 | [15 empty] | 2016-11-09: 2019-04-10
2AI101CV02100-08005 | LFHO Storage Tank (52-D-95) & (52-D-96) : Construct Bund Wall
2AI101CV02100 | EOF:Lot-1-J : LFHO Storage Tank (52-D-95 & 52-D-96) : Construct Bund Wall
2AI101CV02000 | EOF:Lot-1-J : LFHO Storage Tank (52-D-95 & 52-D-96) : CP works | [15 empty] | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31
2AI101CV01900-08125 | Install PVC leak detection pipes & HDPE drain canister (External)
2AI101CV01900-08120 | Asphaltic Concrete layer (External)
2AI101CV01900-08115 | Concreting for Access staircases & Service platforms (External) | [15 empty] | 2016-10-31: 2018-12-10; 2016-10-31: 2018-12-10; 2016-10-31: 2018-12-10; 2016-10-31: 2018-12-10; 2016-10-31: 2018-12-10
2AI101CV01900-08112 | Rebar & Formwork for Access staircases & Service platforms (External) | [15 empty] | 2016-10-31: 2018-12-05; 2016-10-31: 2018-12-05; 2016-10-31: 2018-12-05; 2016-10-31: 2018-12-05; 2016-10-31: 2018-12-05
2AI101CV01900-08110 | Crushed Gravel w/ Gatch Mix Layer (External) | [15 empty] | 2016-10-31: 2019-02-07; 2016-10-31: 2019-02-07; 2016-10-31: 2019-02-07
2AI101CV01900-08105 | Compacted Gatch fill & Blinding for HDPE drain canister (External) | [15 empty] | 2016-10-31: 2018-12-16; 2016-10-31: 2018-12-16; 2016-10-31: 2018-12-16; 2016-10-31: 2018-12-16; 2016-10-31: 2018-12-16
2AI101CV01900-08100 | EOF:Clean Sand filling after CP installation (Internal) for 52-D-96 Fnd | [15 empty] | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03
2AI101CV01900-08095 | EOF:Permeable Sand-gravel filling (Internal) for 52-D-96 Fnd | [15 empty] | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20
2AI101CV01900-08090 | EOF:Install Embedments (Internal) for 52-D-96 Fnd | [15 empty] | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18
2AI101CV01900-08085 | EOF:Sand filling (Internal) for 52-D-96 Fnd | [15 empty] | 2016-10-15 | 2016-10-15 | 2016-10-15 | 2016-10-15 | 2016-10-15 | 2016-10-15 | 2016-10-15 | 2016-10-15 | 2016-10-15 | 2016-10-15 | 2016-10-15 | 2016-10-15 | 2016-10-15 | 2016-10-15 | 2016-10-15 | 2016-10-15 | 2016-10-15 | 2016-10-15 | 2016-10-15 | 2016-10-15 | 2016-10-15 | 2016-10-15 | 2016-10-15 | 2016-10-15 | 2016-10-15 | 2016-10-15 | 2016-10-15 | 2016-10-15 | 2016-10-15 | 2016-10-15 | 2016-10-15
2AI101CV01900-08080 | EOF:Geo Membrane laying (Internal) for 52-D-96 Fnd | [15 empty] | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09
2AI101CV01900-08075 | EOF:Sand layer & Compaction (Internal) for 52-D-96 Fnd | [15 empty] | 2016-10-10 | 2016-10-10 | 2016-10-10 | 2016-10-10 | 2016-10-10 | 2016-10-10 | 2016-10-10 | 2016-10-10 | 2016-10-10 | 2016-10-10 | 2016-10-10 | 2016-10-10 | 2016-10-10 | 2016-10-10 | 2016-10-10 | 2016-10-10 | 2016-10-10 | 2016-10-10 | 2016-10-10 | 2016-10-10 | 2016-10-10 | 2016-10-10 | 2016-10-10 | 2016-10-10 | 2016-10-10 | 2016-10-10 | 2016-10-10 | 2016-10-10 | 2016-10-10 | 2016-10-10 | 2016-10-10
2AI101CV01900-08070 | EOF:Gatch Filling & Compaction (Internal) for Tank Fnd | [15 empty] | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09
2AI101CV01900-08055 | Install PVC leak detection pipes & HDPE drain canister (External)
2AI101CV01900-08050 | Asphaltic Concrete layer (External)
2AI101CV01900-08045 | Concreting for Access staircases & Service platforms (External) | [15 empty] | 2016-10-09: 2018-12-10; 2016-10-09: 2018-12-10; 2016-10-09: 2018-12-10; 2016-10-09: 2018-12-10; 2016-10-09: 2018-12-10
2AI101CV01900-08042 | Rebar & Formwork for Access staircases & Service platforms (External) | [15 empty] | 2016-10-09: 2018-12-05; 2016-10-09: 2018-12-05; 2016-10-09: 2018-12-05; 2016-10-09: 2018-12-05; 2016-10-09: 2018-12-05
2AI101CV01900-08040 | Crushed Gravel w/ Gatch Mix Layer (External) | [15 empty] | 2016-10-09: 2019-01-29; 2016-10-09: 2019-01-29; 2016-10-09: 2019-01-29
2AI101CV01900-08035 | Compacted Gatch fill & Blinding for HDPE drain canister (External) | [15 empty] | 2016-10-09: 2018-12-26; 2016-10-09: 2018-12-26; 2016-10-09: 2018-12-26; 2016-10-09: 2018-12-26; 2016-10-09: 2018-12-26
2AI101CV01900-08030 | EOF:Clean Sand filling after CP installation (Internal) for 52-D-95 Fnd | [15 empty] | 2016-10-07 | 2016-10-07 | 2016-10-07 | 2016-10-07 | 2016-10-07 | 2016-10-07 | 2016-10-07 | 2016-10-07 | 2016-10-07 | 2016-10-07 | 2016-10-07 | 2016-10-07 | 2016-10-07 | 2016-10-07 | 2016-10-07 | 2016-10-07 | 2016-10-07 | 2016-10-07 | 2016-10-07 | 2016-10-07 | 2016-10-07 | 2016-10-07 | 2016-10-07 | 2016-10-07 | 2016-10-07 | 2016-10-07 | 2016-10-07 | 2016-10-07 | 2016-10-07 | 2016-10-07 | 2016-10-07
2AI101CV01900-08025 | EOF:Permeable Sand-gravel filling (Internal) for 52-D-95 Fnd | [13 empty] | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23
2AI101CV01900-08020 | EOF:Install Embedments (Internal) for 52-D-95 Fnd | [15 empty] | 2016-09-29 | 2016-09-29 | 2016-09-29 | 2016-09-29 | 2016-09-29 | 2016-09-29 | 2016-09-29 | 2016-09-29 | 2016-09-29 | 2016-09-29 | 2016-09-29 | 2016-09-29 | 2016-09-29 | 2016-09-29 | 2016-09-29 | 2016-09-29 | 2016-09-29 | 2016-09-29 | 2016-09-29 | 2016-09-29 | 2016-09-29 | 2016-09-29 | 2016-09-29 | 2016-09-29 | 2016-09-29 | 2016-09-29 | 2016-09-29 | 2016-09-29 | 2016-09-29 | 2016-09-29 | 2016-09-29
2AI101CV01900-08015 | EOF:Sand filling (Internal) for 52-D-95 Fnd | [13 empty] | 2016-09-21 | 2016-09-21 | 2016-09-21 | 2016-09-21 | 2016-09-21 | 2016-09-21 | 2016-09-21 | 2016-09-21 | 2016-09-21 | 2016-09-21 | 2016-09-21 | 2016-09-21 | 2016-09-21 | 2016-09-21 | 2016-09-21 | 2016-09-21 | 2016-09-21 | 2016-09-21 | 2016-09-21 | 2016-09-21 | 2016-09-21 | 2016-09-21 | 2016-09-21 | 2016-09-21 | 2016-09-21 | 2016-09-21 | 2016-09-21 | 2016-09-21 | 2016-09-21 | 2016-09-21 | 2016-09-21 | 2016-09-21 | 2016-09-21
2AI101CV01900-08011 | EOF:Geo Membrane laying (Internal) for 52-D-95 Fnd | [13 empty] | 2016-09-17 | 2016-09-17 | 2016-09-17 | 2016-09-17 | 2016-09-17 | 2016-09-17 | 2016-09-17 | 2016-09-17 | 2016-09-17 | 2016-09-17 | 2016-09-17 | 2016-09-17 | 2016-09-17 | 2016-09-17 | 2016-09-17 | 2016-09-17 | 2016-09-17 | 2016-09-17 | 2016-09-17 | 2016-09-17 | 2016-09-17 | 2016-09-17 | 2016-09-17 | 2016-09-17 | 2016-09-17 | 2016-09-17 | 2016-09-17 | 2016-09-17 | 2016-09-17 | 2016-09-17 | 2016-09-17 | 2016-09-17 | 2016-09-17
2AI101CV01900-08010 | LFHO Storage Tank (52-D-96) : Backfilling
2AI101CV01900-08006 | EOF:Sand layer & Compaction (Internal) for 52-D-95 Fnd | [13 empty] | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27
2AI101CV01900-08005 | LFHO Storage Tank (52-D-95) : Backfilling
2AI101CV01900-08000 | EOF:Gatch Filling & Compaction (Internal) for Tank Fnd | [13 empty] | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27
2AI101CV01900 | EOF:Lot-1-J : LFHO Storage Tank (52-D-95 & 52-D-96) : Backfilling
2AI101CV01800-08035 | EOF:Concrete protection for Ring wall fnd of Storage Tank 52-D-96 | [13 empty] | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23
2AI101CV01800-08033 | EOF:Concrete Pouring for Ring beam wall | [13 empty] | 2016-08-08 | 2016-08-08 | 2016-08-08 | 2016-08-08 | 2016-08-08 | 2016-08-08 | 2016-08-08 | 2016-08-08 | 2016-08-08 | 2016-08-08 | 2016-08-08 | 2016-08-08 | 2016-08-08 | 2016-08-08 | 2016-08-08 | 2016-08-08 | 2016-08-08 | 2016-08-08 | 2016-08-08 | 2016-08-08 | 2016-08-08 | 2016-08-08 | 2016-08-08 | 2016-08-08 | 2016-08-08 | 2016-08-08 | 2016-08-08 | 2016-08-08 | 2016-08-08 | 2016-08-08 | 2016-08-08 | 2016-08-08 | 2016-08-08
2AI101CV01800-08032 | EOF:Rebar, Formwork & Install Embedments (Ring beam wall) | [13 empty] | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07
2AI101CV01800-08031 | EOF:Concrete Pouring - for Footing | [11 empty] | 2016-07-14 | 2016-07-14 | 2016-07-14 | 2016-07-14 | 2016-07-14 | 2016-07-14 | 2016-07-14 | 2016-07-14 | 2016-07-14 | 2016-07-14 | 2016-07-14 | 2016-07-14 | 2016-07-14 | 2016-07-14 | 2016-07-14 | 2016-07-14 | 2016-07-14 | 2016-07-14 | 2016-07-14 | 2016-07-14 | 2016-07-14 | 2016-07-14 | 2016-07-14 | 2016-07-14 | 2016-07-14 | 2016-07-14 | 2016-07-14 | 2016-07-14 | 2016-07-14 | 2016-07-14 | 2016-07-14 | 2016-07-14 | 2016-07-14 | 2016-07-14 | 2016-07-14
2AI101CV01800-08030 | EOF:Rebar, Formwork & Construction joint of Storage Tank 52-D-96 | [11 empty] | 2016-07-12 | 2016-07-12 | 2016-07-12 | 2016-07-12 | 2016-07-12 | 2016-07-12 | 2016-07-12 | 2016-07-12 | 2016-07-12 | 2016-07-12 | 2016-07-12 | 2016-07-12 | 2016-07-12 | 2016-07-12 | 2016-07-12 | 2016-07-12 | 2016-07-12 | 2016-07-12 | 2016-07-12 | 2016-07-12 | 2016-07-12 | 2016-07-12 | 2016-07-12 | 2016-07-12 | 2016-07-12 | 2016-07-12 | 2016-07-12 | 2016-07-12 | 2016-07-12 | 2016-07-12 | 2016-07-12 | 2016-07-12 | 2016-07-12 | 2016-07-12 | 2016-07-12
2AI101CV01800-08025 | EOF:Blinding/PCC for Fnd of Infield Pop Tank 52-D-96 | [11 empty] | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04
2AI101CV01800-08020 | EOF:Survey Marking, Excavation & Subgrade | [11 empty] | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03
2AI101CV01800-08015 | EOF:Concrete protection for Ring wall fnd of Storage Tank 52-D-95 | [13 empty] | 2016-08-29 | 2016-08-29 | 2016-08-29 | 2016-08-29 | 2016-08-29 | 2016-08-29 | 2016-08-29 | 2016-08-29 | 2016-08-29 | 2016-08-29 | 2016-08-29 | 2016-08-29 | 2016-08-29 | 2016-08-29 | 2016-08-29 | 2016-08-29 | 2016-08-29 | 2016-08-29 | 2016-08-29 | 2016-08-29 | 2016-08-29 | 2016-08-29 | 2016-08-29 | 2016-08-29 | 2016-08-29 | 2016-08-29 | 2016-08-29 | 2016-08-29 | 2016-08-29 | 2016-08-29 | 2016-08-29 | 2016-08-29 | 2016-08-29
2AI101CV01800-08014 | EOF:Concrete Pouring for Ring beam wall | [11 empty] | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04
2AI101CV01800-08013 | EOF:Rebar, Formwork & Install Embedments (Ring beam wall) | [11 empty] | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02
2AI101CV01800-08012 | EOF:Concrete Pouring - for Footing | [11 empty] | 2016-06-08 | 2016-06-08 | 2016-06-08 | 2016-06-08 | 2016-06-08 | 2016-06-08 | 2016-06-08 | 2016-06-08 | 2016-06-08 | 2016-06-08 | 2016-06-08 | 2016-06-08 | 2016-06-08 | 2016-06-08 | 2016-06-08 | 2016-06-08 | 2016-06-08 | 2016-06-08 | 2016-06-08 | 2016-06-08 | 2016-06-08 | 2016-06-08 | 2016-06-08 | 2016-06-08 | 2016-06-08 | 2016-06-08 | 2016-06-08 | 2016-06-08 | 2016-06-08 | 2016-06-08 | 2016-06-08 | 2016-06-08 | 2016-06-08 | 2016-06-08 | 2016-06-08
2AI101CV01800-08011 | EOF:Rebar, Formwork & Construction joint of Storage Tank 52-D-95 | [11 empty] | 2016-06-07 | 2016-06-07 | 2016-06-07 | 2016-06-07 | 2016-06-07 | 2016-06-07 | 2016-06-07 | 2016-06-07 | 2016-06-07 | 2016-06-07 | 2016-06-07 | 2016-06-07 | 2016-06-07 | 2016-06-07 | 2016-06-07 | 2016-06-07 | 2016-06-07 | 2016-06-07 | 2016-06-07 | 2016-06-07 | 2016-06-07 | 2016-06-07 | 2016-06-07 | 2016-06-07 | 2016-06-07 | 2016-06-07 | 2016-06-07 | 2016-06-07 | 2016-06-07 | 2016-06-07 | 2016-06-07 | 2016-06-07 | 2016-06-07 | 2016-06-07 | 2016-06-07
2AI101CV01800-08010 | LFHO Storage Tank (52-D-96) : Ring wall type Foundation | [13 empty] | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23
2AI101CV01800-08006 | EOF:Blinding/PCC for Fnd of Infield Pop Tank 52-D-95 | [9 empty] | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20
2AI101CV01800-08005 | LFHO Storage Tank (52-D-95) : Ring wall type Foundation | [13 empty] | 2016-08-29 | 2016-08-29 | 2016-08-29 | 2016-08-29 | 2016-08-29 | 2016-08-29 | 2016-08-29 | 2016-08-29 | 2016-08-29 | 2016-08-29 | 2016-08-29 | 2016-08-29 | 2016-08-29 | 2016-08-29 | 2016-08-29 | 2016-08-29 | 2016-08-29 | 2016-08-29 | 2016-08-29 | 2016-08-29 | 2016-08-29 | 2016-08-29 | 2016-08-29 | 2016-08-29 | 2016-08-29 | 2016-08-29 | 2016-08-29 | 2016-08-29 | 2016-08-29 | 2016-08-29 | 2016-08-29 | 2016-08-29 | 2016-08-29
2AI101CV01800-08000 | EOF:Survey Marking, Excavation & Subgrade | [9 empty] | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11
2AI101CV01800 | EOF:Lot-1-J : LFHO Storage Tank (52-D-95 & 52-D-96) : Ring wall type Foundation | [13 empty] | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23
2AI101CV01700-08060 | EOF:Asphalt Lining for Inside slope for Bund Wall (52-D-93 & 52-D-94)
2AI101CV01700-08055 | EOF:Rebar, Form work & Concreting for Stair cases for Bund Wall around Storage tank (52-D-93 & 52-D-94)
2AI101CV01700-08050 | EOF:Prepare Access ramp (with Compact fill & Gatch layer) for Bund Wall around Storage tank(52-D-93 & 52-D-94) | [13 empty] | 2016-09-23: 2018-10-29; 2016-09-23: 2018-10-29; 2016-09-23: 2018-10-29; 2016-09-23: 2018-10-29; 2016-09-23: 2018-10-29; 2016-09-23: 2018-10-29; 2016-09-23: 2018-10-29
2AI101CV01700-08045 | EOF:Gatch Filling & Compaction for Bund Wall around Storage tank (52-D-93 & 52-D-94)
2AI101CV01700-08040 | EOF:Install Linar Membrane (incl. base & inside slope) for Bund Wall around Storage tank (52-D-93 & 52-D-94) | [13 empty] | 2016-09-23: 2019-04-26
2AI101CV01700-08035 | EOF:Sand layer (Inside) upto Linear Menbrane Lvl for Bund Wall around Storage tank (52-D-93 & 52-D-94) | [13 empty] | 2016-09-23: 2019-04-10
2AI101CV01700-08030 | EOF:Lay Drain Pipe (CB to Valve pit) for Bund Wall around Storage tank (52-D-93 & 52-D-94) | [13 empty] | 2016-09-23: 2018-10-10; 2016-09-23: 2018-10-10; 2016-09-23: 2018-10-10; 2016-09-23: 2018-10-10; 2016-09-23: 2018-10-10; 2016-09-23: 2018-10-10; 2016-09-23: 2018-10-10
2AI101CV01700-08025 | EOF:Install/Cast Catch basin (inside) & Valve pit (outside) for Bund Wall around Storage tank (52-D-93 & 52-D-94) | [13 empty] | 2016-09-23: 2018-10-22; 2016-09-23: 2018-10-22; 2016-09-23: 2018-10-22; 2016-09-23: 2018-10-22; 2016-09-23: 2018-10-22; 2016-09-23: 2018-10-22; 2016-09-23: 2018-10-22
2AI101CV01700-08020 | EOF:Slope Preparation for Bund Wall around Storage tank (52-D-93 & 52-D-94) | [13 empty] | 2016-09-23: 2019-01-29; 2016-09-23: 2019-01-29; 2016-09-23: 2019-01-29
2AI101CV01700-08015 | EOF: Prepare Subgrade lvl for Bund Wall around Storage tank (52-D-93 & 52-D-94) | [13 empty] | 2016-09-23: 2019-01-27; 2016-09-23: 2019-01-27; 2016-09-23: 2019-01-27
2AI101CV01700-08010 | EOF:Survey Marking, Excavation & Disposal of unsutiable Material for Bund Wall around Storage tank (52-D-93 & 52-D-94) | [13 empty] | 2016-09-23: 2019-02-06; 2016-09-23: 2019-02-06; 2016-09-23: 2019-02-06
2AI101CV01700-08005 | LFHO Storage Tank (52-D-93) & (52-D-94): Construct Bund Wall
2AI101CV01700 | EOF:Lot-1-J : LFHO Storage Tank (52-D-93 & 52-D-94) : Construct Bund Wall
2AI101CV01600-08010 | LFHO Storage Tank (52-D-94) : CP works | [13 empty] | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14
2AI101CV01600-08005 | LFHO Storage Tank (52-D-93) : CP works | [13 empty] | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24
2AI101CV01600 | EOF:Lot-1-J : LFHO Storage Tank (52-D-93 & 52-D-94) : CP works | [13 empty] | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24
2AI101CV01500-08125 | Install PVC leak detection pipes & HDPE drain canister (External) | [13 empty] | 2016-08-24: 2019-04-20
2AI101CV01500-08120 | Asphaltic Concrete layer (External)
2AI101CV01500-08115 | Concreting for Access staircases & Service platforms (External) | [13 empty] | 2016-08-24: 2018-12-10; 2016-08-24: 2018-12-10; 2016-08-24: 2018-12-10; 2016-08-24: 2018-12-10; 2016-08-24: 2018-12-10
2AI101CV01500-08112 | Rebar & Formwork for Access staircases & Service platforms (External) | [13 empty] | 2016-08-24: 2018-12-05; 2016-08-24: 2018-12-05; 2016-08-24: 2018-12-05; 2016-08-24: 2018-12-05; 2016-08-24: 2018-12-05
2AI101CV01500-08110 | Crushed Gravel w/ Gatch Mix Layer (External) | [13 empty] | 2016-08-24: 2018-12-19; 2016-08-24: 2018-12-19; 2016-08-24: 2018-12-19; 2016-08-24: 2018-12-19; 2016-08-24: 2018-12-19
2AI101CV01500-08105 | Compacted Gatch fill & Blinding for HDPE drain canister (External) | [13 empty] | 2016-08-24: 2018-12-26; 2016-08-24: 2018-12-26; 2016-08-24: 2018-12-26; 2016-08-24: 2018-12-26; 2016-08-24: 2018-12-26
2AI101CV01500-08100 | EOF:Clean Sand filling after CP installation (Internal) for 52-D-94 Fnd | [13 empty] | 2016-08-20 | 2016-08-20 | 2016-08-20 | 2016-08-20 | 2016-08-20 | 2016-08-20 | 2016-08-20 | 2016-08-20 | 2016-08-20 | 2016-08-20 | 2016-08-20 | 2016-08-20 | 2016-08-20 | 2016-08-20 | 2016-08-20 | 2016-08-20 | 2016-08-20 | 2016-08-20 | 2016-08-20 | 2016-08-20 | 2016-08-20 | 2016-08-20 | 2016-08-20 | 2016-08-20 | 2016-08-20 | 2016-08-20 | 2016-08-20 | 2016-08-20 | 2016-08-20 | 2016-08-20 | 2016-08-20 | 2016-08-20 | 2016-08-20
2AI101CV01500-08095 | EOF:Permeable Sand-gravel filling (Internal) for 52-D-94 Fnd | [13 empty] | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01
2AI101CV01500-08090 | EOF:Install Embedments (Internal) for 52-D-94 Fnd | [13 empty] | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27
2AI101CV01500-08085 | EOF:Sand filling (Internal) for 52-D-94 Fnd | [13 empty] | 2016-07-26 | 2016-07-26 | 2016-07-26 | 2016-07-26 | 2016-07-26 | 2016-07-26 | 2016-07-26 | 2016-07-26 | 2016-07-26 | 2016-07-26 | 2016-07-26 | 2016-07-26 | 2016-07-26 | 2016-07-26 | 2016-07-26 | 2016-07-26 | 2016-07-26 | 2016-07-26 | 2016-07-26 | 2016-07-26 | 2016-07-26 | 2016-07-26 | 2016-07-26 | 2016-07-26 | 2016-07-26 | 2016-07-26 | 2016-07-26 | 2016-07-26 | 2016-07-26 | 2016-07-26 | 2016-07-26 | 2016-07-26 | 2016-07-26
2AI101CV01500-08080 | EOF:Geo Membrane laying (Internal) for 52-D-94 Fnd | [13 empty] | 2016-07-24 | 2016-07-24 | 2016-07-24 | 2016-07-24 | 2016-07-24 | 2016-07-24 | 2016-07-24 | 2016-07-24 | 2016-07-24 | 2016-07-24 | 2016-07-24 | 2016-07-24 | 2016-07-24 | 2016-07-24 | 2016-07-24 | 2016-07-24 | 2016-07-24 | 2016-07-24 | 2016-07-24 | 2016-07-24 | 2016-07-24 | 2016-07-24 | 2016-07-24 | 2016-07-24 | 2016-07-24 | 2016-07-24 | 2016-07-24 | 2016-07-24 | 2016-07-24 | 2016-07-24 | 2016-07-24 | 2016-07-24 | 2016-07-24
2AI101CV01500-08075 | EOF:Sand layer & Compaction (Internal) for 52-D-94 Fnd | [13 empty] | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23
2AI101CV01500-08070 | EOF:Gatch Filling & Compaction (Internal) for Tank Fnd | [11 empty] | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30
2AI101CV01500-08055 | Install PVC leak detection pipes & HDPE drain canister (External) | [11 empty] | 2016-06-30: 2019-03-06; 2016-06-30: 2019-03-06; 2016-06-30: 2019-03-06
2AI101CV01500-08050 | Asphaltic Concrete layer (External)
2AI101CV01500-08045 | Concreting for Access staircases & Service platforms (External) | [11 empty] | 2016-06-30: 2018-12-15; 2016-06-30: 2018-12-15; 2016-06-30: 2018-12-15; 2016-06-30: 2018-12-15; 2016-06-30: 2018-12-15
2AI101CV01500-08042 | Rebar & Formwork for Access staircases & Service platforms (External) | [11 empty] | 2016-06-30: 2018-12-05; 2016-06-30: 2018-12-05; 2016-06-30: 2018-12-05; 2016-06-30: 2018-12-05; 2016-06-30: 2018-12-05
2AI101CV01500-08040 | Crushed Gravel w/ Gatch Mix Layer (External) | [11 empty] | 2016-06-30: 2018-11-04; 2016-06-30: 2018-11-04; 2016-06-30: 2018-11-04; 2016-06-30: 2018-11-04; 2016-06-30: 2018-11-04; 2016-06-30: 2018-11-04; 2016-06-30: 2018-11-04
2AI101CV01500-08035 | Compacted Gatch fill & Blinding for HDPE drain canister (External) | [11 empty] | 2016-06-30: 2018-12-26; 2016-06-30: 2018-12-26; 2016-06-30: 2018-12-26; 2016-06-30: 2018-12-26; 2016-06-30: 2018-12-26
2AI101CV01500-08030 | EOF:Clean Sand filling after CP installation (Internal) for 52-D-93 Fnd | [13 empty] | 2016-09-01 | 2016-09-01 | 2016-09-01 | 2016-09-01 | 2016-09-01 | 2016-09-01 | 2016-09-01 | 2016-09-01 | 2016-09-01 | 2016-09-01 | 2016-09-01 | 2016-09-01 | 2016-09-01 | 2016-09-01 | 2016-09-01 | 2016-09-01 | 2016-09-01 | 2016-09-01 | 2016-09-01 | 2016-09-01 | 2016-09-01 | 2016-09-01 | 2016-09-01 | 2016-09-01 | 2016-09-01 | 2016-09-01 | 2016-09-01 | 2016-09-01 | 2016-09-01 | 2016-09-01 | 2016-09-01 | 2016-09-01 | 2016-09-01
2AI101CV01500-08025 | EOF:Permeable Sand-gravel filling (Internal) for 52-D-93 Fnd | [13 empty] | 2016-08-09 | 2016-08-09 | 2016-08-09 | 2016-08-09 | 2016-08-09 | 2016-08-09 | 2016-08-09 | 2016-08-09 | 2016-08-09 | 2016-08-09 | 2016-08-09 | 2016-08-09 | 2016-08-09 | 2016-08-09 | 2016-08-09 | 2016-08-09 | 2016-08-09 | 2016-08-09 | 2016-08-09 | 2016-08-09 | 2016-08-09 | 2016-08-09 | 2016-08-09 | 2016-08-09 | 2016-08-09 | 2016-08-09 | 2016-08-09 | 2016-08-09 | 2016-08-09 | 2016-08-09 | 2016-08-09 | 2016-08-09 | 2016-08-09
2AI101CV01500-08020 | EOF:Install Embedments (Internal) for 52-D-93 Fnd | [13 empty] | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07
2AI101CV01500-08015 | EOF:Sand filling (Internal) for 52-D-93 Fnd | [13 empty] | 2016-08-06 | 2016-08-06 | 2016-08-06 | 2016-08-06 | 2016-08-06 | 2016-08-06 | 2016-08-06 | 2016-08-06 | 2016-08-06 | 2016-08-06 | 2016-08-06 | 2016-08-06 | 2016-08-06 | 2016-08-06 | 2016-08-06 | 2016-08-06 | 2016-08-06 | 2016-08-06 | 2016-08-06 | 2016-08-06 | 2016-08-06 | 2016-08-06 | 2016-08-06 | 2016-08-06 | 2016-08-06 | 2016-08-06 | 2016-08-06 | 2016-08-06 | 2016-08-06 | 2016-08-06 | 2016-08-06 | 2016-08-06 | 2016-08-06
2AI101CV01500-08011 | EOF:Geo Membrane laying (Internal) for 52-D-93 Fnd | [13 empty] | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04
2AI101CV01500-08010 | LFHO Storage Tank (52-D-94) : Backfilling
2AI101CV01500-08005 | LFHO Storage Tank (52-D-93) : Backfilling
2AI101CV01500-08000 | EOF:Gatch Filling & Compaction (Internal) for Tank Fnd | [13 empty] | 2016-07-26 | 2016-07-26 | 2016-07-26 | 2016-07-26 | 2016-07-26 | 2016-07-26 | 2016-07-26 | 2016-07-26 | 2016-07-26 | 2016-07-26 | 2016-07-26 | 2016-07-26 | 2016-07-26 | 2016-07-26 | 2016-07-26 | 2016-07-26 | 2016-07-26 | 2016-07-26 | 2016-07-26 | 2016-07-26 | 2016-07-26 | 2016-07-26 | 2016-07-26 | 2016-07-26 | 2016-07-26 | 2016-07-26 | 2016-07-26 | 2016-07-26 | 2016-07-26 | 2016-07-26 | 2016-07-26 | 2016-07-26 | 2016-07-26
2AI101CV01500 | EOF:Lot-1-J : LFHO Storage Tank (52-D-93 & 52-D-94) : Backfilling
2AI101CV01400-08035 | EOF:Concrete protection for Ring wall fnd of Storage Tank 52-D-94 | [11 empty] | 2016-07-20 | 2016-07-20 | 2016-07-20 | 2016-07-20 | 2016-07-20 | 2016-07-20 | 2016-07-20 | 2016-07-20 | 2016-07-20 | 2016-07-20 | 2016-07-20 | 2016-07-20 | 2016-07-20 | 2016-07-20 | 2016-07-20 | 2016-07-20 | 2016-07-20 | 2016-07-20 | 2016-07-20 | 2016-07-20 | 2016-07-20 | 2016-07-20 | 2016-07-20 | 2016-07-20 | 2016-07-20 | 2016-07-20 | 2016-07-20 | 2016-07-20 | 2016-07-20 | 2016-07-20 | 2016-07-20 | 2016-07-20 | 2016-07-20 | 2016-07-20 | 2016-07-20
2AI101CV01400-08033 | EOF:Concrete Pouring for Ring beam wall | [9 empty] | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25
2AI101CV01400-08032 | EOF:Rebar, Formwork & Install Embedments (Ring beam wall) | [9 empty] | 2016-05-24 | 2016-05-24 | 2016-05-24 | 2016-05-24 | 2016-05-24 | 2016-05-24 | 2016-05-24 | 2016-05-24 | 2016-05-24 | 2016-05-24 | 2016-05-24 | 2016-05-24 | 2016-05-24 | 2016-05-24 | 2016-05-24 | 2016-05-24 | 2016-05-24 | 2016-05-24 | 2016-05-24 | 2016-05-24 | 2016-05-24 | 2016-05-24 | 2016-05-24 | 2016-05-24 | 2016-05-24 | 2016-05-24 | 2016-05-24 | 2016-05-24 | 2016-05-24 | 2016-05-24 | 2016-05-24 | 2016-05-24 | 2016-05-24 | 2016-05-24 | 2016-05-24 | 2016-05-24 | 2016-05-24
2AI101CV01400-08031 | EOF:Concrete Pouring - for Footing | [9 empty] | 2016-05-03 | 2016-05-03 | 2016-05-03 | 2016-05-03 | 2016-05-03 | 2016-05-03 | 2016-05-03 | 2016-05-03 | 2016-05-03 | 2016-05-03 | 2016-05-03 | 2016-05-03 | 2016-05-03 | 2016-05-03 | 2016-05-03 | 2016-05-03 | 2016-05-03 | 2016-05-03 | 2016-05-03 | 2016-05-03 | 2016-05-03 | 2016-05-03 | 2016-05-03 | 2016-05-03 | 2016-05-03 | 2016-05-03 | 2016-05-03 | 2016-05-03 | 2016-05-03 | 2016-05-03 | 2016-05-03 | 2016-05-03 | 2016-05-03 | 2016-05-03 | 2016-05-03 | 2016-05-03 | 2016-05-03
2AI101CV01400-08030 | EOF:Rebar, Formwork & Construction joint of Storage Tank 52-D-94 | [9 empty] | 2016-05-01 | 2016-05-01 | 2016-05-01 | 2016-05-01 | 2016-05-01 | 2016-05-01 | 2016-05-01 | 2016-05-01 | 2016-05-01 | 2016-05-01 | 2016-05-01 | 2016-05-01 | 2016-05-01 | 2016-05-01 | 2016-05-01 | 2016-05-01 | 2016-05-01 | 2016-05-01 | 2016-05-01 | 2016-05-01 | 2016-05-01 | 2016-05-01 | 2016-05-01 | 2016-05-01 | 2016-05-01 | 2016-05-01 | 2016-05-01 | 2016-05-01 | 2016-05-01 | 2016-05-01 | 2016-05-01 | 2016-05-01 | 2016-05-01 | 2016-05-01 | 2016-05-01 | 2016-05-01 | 2016-05-01
2AI101CV01400-08025 | EOF:Blinding/PCC for Fnd of Infield Storage Tank 52-D-94 | [9 empty] | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14
2AI101CV01400-08020 | EOF:Survey Marking, Excavation & Subgrade | [9 empty] | 2016-04-04 | 2016-04-04 | 2016-04-04 | 2016-04-04 | 2016-04-04 | 2016-04-04 | 2016-04-04 | 2016-04-04 | 2016-04-04 | 2016-04-04 | 2016-04-04 | 2016-04-04 | 2016-04-04 | 2016-04-04 | 2016-04-04 | 2016-04-04 | 2016-04-04 | 2016-04-04 | 2016-04-04 | 2016-04-04 | 2016-04-04 | 2016-04-04 | 2016-04-04 | 2016-04-04 | 2016-04-04 | 2016-04-04 | 2016-04-04 | 2016-04-04 | 2016-04-04 | 2016-04-04 | 2016-04-04 | 2016-04-04 | 2016-04-04 | 2016-04-04 | 2016-04-04 | 2016-04-04 | 2016-04-04
2AI101CV01400-08015 | EOF:Concrete protection for Ring wall fnd of Storage Tank 52-D-93 | [13 empty] | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01
2AI101CV01400-08013 | EOF:Concrete Pouring for Ring beam wall | [11 empty] | 2016-06-13 | 2016-06-13 | 2016-06-13 | 2016-06-13 | 2016-06-13 | 2016-06-13 | 2016-06-13 | 2016-06-13 | 2016-06-13 | 2016-06-13 | 2016-06-13 | 2016-06-13 | 2016-06-13 | 2016-06-13 | 2016-06-13 | 2016-06-13 | 2016-06-13 | 2016-06-13 | 2016-06-13 | 2016-06-13 | 2016-06-13 | 2016-06-13 | 2016-06-13 | 2016-06-13 | 2016-06-13 | 2016-06-13 | 2016-06-13 | 2016-06-13 | 2016-06-13 | 2016-06-13 | 2016-06-13 | 2016-06-13 | 2016-06-13 | 2016-06-13 | 2016-06-13
2AI101CV01400-08012 | EOF:Rebar, Formwork & Install Embedments (Ring beam wall) | [11 empty] | 2016-06-11 | 2016-06-11 | 2016-06-11 | 2016-06-11 | 2016-06-11 | 2016-06-11 | 2016-06-11 | 2016-06-11 | 2016-06-11 | 2016-06-11 | 2016-06-11 | 2016-06-11 | 2016-06-11 | 2016-06-11 | 2016-06-11 | 2016-06-11 | 2016-06-11 | 2016-06-11 | 2016-06-11 | 2016-06-11 | 2016-06-11 | 2016-06-11 | 2016-06-11 | 2016-06-11 | 2016-06-11 | 2016-06-11 | 2016-06-11 | 2016-06-11 | 2016-06-11 | 2016-06-11 | 2016-06-11 | 2016-06-11 | 2016-06-11 | 2016-06-11 | 2016-06-11
2AI101CV01400-08011 | EOF:Concrete Pouring - for Footing | [9 empty] | 2016-05-08 | 2016-05-08 | 2016-05-08 | 2016-05-08 | 2016-05-08 | 2016-05-08 | 2016-05-08 | 2016-05-08 | 2016-05-08 | 2016-05-08 | 2016-05-08 | 2016-05-08 | 2016-05-08 | 2016-05-08 | 2016-05-08 | 2016-05-08 | 2016-05-08 | 2016-05-08 | 2016-05-08 | 2016-05-08 | 2016-05-08 | 2016-05-08 | 2016-05-08 | 2016-05-08 | 2016-05-08 | 2016-05-08 | 2016-05-08 | 2016-05-08 | 2016-05-08 | 2016-05-08 | 2016-05-08 | 2016-05-08 | 2016-05-08 | 2016-05-08 | 2016-05-08 | 2016-05-08 | 2016-05-08
2AI101CV01400-08010 | EOF:LFHO Storage Tank 52-D-94 : Ring wall type Foundation | [11 empty] | 2016-07-20 | 2016-07-20 | 2016-07-20 | 2016-07-20 | 2016-07-20 | 2016-07-20 | 2016-07-20 | 2016-07-20 | 2016-07-20 | 2016-07-20 | 2016-07-20 | 2016-07-20 | 2016-07-20 | 2016-07-20 | 2016-07-20 | 2016-07-20 | 2016-07-20 | 2016-07-20 | 2016-07-20 | 2016-07-20 | 2016-07-20 | 2016-07-20 | 2016-07-20 | 2016-07-20 | 2016-07-20 | 2016-07-20 | 2016-07-20 | 2016-07-20 | 2016-07-20 | 2016-07-20 | 2016-07-20 | 2016-07-20 | 2016-07-20 | 2016-07-20 | 2016-07-20
2AI101CV01400-08009 | EOF:Rebar, Formwork & Construction joint of Storage Tank 52-D-93 | [9 empty] | 2016-05-07 | 2016-05-07 | 2016-05-07 | 2016-05-07 | 2016-05-07 | 2016-05-07 | 2016-05-07 | 2016-05-07 | 2016-05-07 | 2016-05-07 | 2016-05-07 | 2016-05-07 | 2016-05-07 | 2016-05-07 | 2016-05-07 | 2016-05-07 | 2016-05-07 | 2016-05-07 | 2016-05-07 | 2016-05-07 | 2016-05-07 | 2016-05-07 | 2016-05-07 | 2016-05-07 | 2016-05-07 | 2016-05-07 | 2016-05-07 | 2016-05-07 | 2016-05-07 | 2016-05-07 | 2016-05-07 | 2016-05-07 | 2016-05-07 | 2016-05-07 | 2016-05-07 | 2016-05-07 | 2016-05-07
2AI101CV01400-08006 | EOF:Blinding/PCC for Fnd of Infield Storage Tank 52-D-93 | [9 empty] | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19
2AI101CV01400-08005 | EOF:LFHO Storage Tank 52-D-93 : Ring wall type Foundation | [13 empty] | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01
2AI101CV01400-08001 | EOF:Survey Marking, Excavation & Subgrade | [9 empty] | 2016-04-16 | 2016-04-16 | 2016-04-16 | 2016-04-16 | 2016-04-16 | 2016-04-16 | 2016-04-16 | 2016-04-16 | 2016-04-16 | 2016-04-16 | 2016-04-16 | 2016-04-16 | 2016-04-16 | 2016-04-16 | 2016-04-16 | 2016-04-16 | 2016-04-16 | 2016-04-16 | 2016-04-16 | 2016-04-16 | 2016-04-16 | 2016-04-16 | 2016-04-16 | 2016-04-16 | 2016-04-16 | 2016-04-16 | 2016-04-16 | 2016-04-16 | 2016-04-16 | 2016-04-16 | 2016-04-16 | 2016-04-16 | 2016-04-16 | 2016-04-16 | 2016-04-16 | 2016-04-16 | 2016-04-16
2AI101CV01400 | EOF:Lot-1-J : LFHO Storage Tank (52-D-93 & 52-D-94) : Ring wall type Foundation | [13 empty] | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01 | 2016-08-01
2AI101CV01200-08025 | EOF:Grouting of 621-G-302 C/D Foam Pump House Building | [13 empty] | 2016-08-01: 2018-10-05; 2016-08-01: 2018-10-05; 2016-08-01: 2018-10-05; 2016-08-01: 2018-10-05; 2016-08-01: 2018-10-05; 2016-08-01: 2018-10-05; 2016-08-01: 2018-10-05
2AI101CV01200-08020 | EOF:Alignment & Bolting/Torqueing for 621-G-302 C/D Foam Pump House Building
2AI101CV01200-08015 | EOF:Installation of Str. Steel for 621-G-302 C/D Foam Pump House Building
2AI101CV01200-08010 | EOF:Grouting of 621-G-302 A/B Foam Pump House Building | [37 empty] | 2018-08-08 | 2018-08-08 | 2018-08-08 | 2018-08-08 | 2018-08-08 | 2018-08-08 | 2018-08-08 | 2018-08-08 | 2018-08-08
2AI101CV01200-08006 | EOF:Alignment & Bolting/Torqueing for621-G-302 A/B Foam Pump House Building | [35 empty] | 2018-07-03 | 2018-07-03 | 2018-07-03 | 2018-07-03 | 2018-07-03 | 2018-07-03 | 2018-07-03 | 2018-07-03 | 2018-07-03 | 2018-07-03 | 2018-07-03
2AI101CV01200-08005 | EOF: 621-G-302 C/D Foam Pump House Building structural works
2AI101CV01200-08001 | EOF:Installation of Str. Steel for 621-G-302 A/B Foam Pump House Building | [33 empty] | 2018-05-25 | 2018-05-25 | 2018-05-25 | 2018-05-25 | 2018-05-25 | 2018-05-25 | 2018-05-25 | 2018-05-25 | 2018-05-25 | 2018-05-25 | 2018-05-25 | 2018-05-25 | 2018-05-25
2AI101CV01200-08000 | EOF: 621-G-302 A/B Foam Pump House Building structural works | [37 empty] | 2018-08-08 | 2018-08-08 | 2018-08-08 | 2018-08-08 | 2018-08-08 | 2018-08-08 | 2018-08-08 | 2018-08-08 | 2018-08-08
2AI101CV01200 | EOF: Foam Pump House Building structural works
2AI101CV01100-08140 | EOF:Embankment for Road crossing | [17 empty] | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28
2AI101CV01100-08130 | EOF:Backfilling duct bank | [17 empty] | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28
2AI101CV01100-08120 | EOF:Concrete Protection duct bank | [15 empty] | 2016-11-25 | 2016-11-25 | 2016-11-25 | 2016-11-25 | 2016-11-25 | 2016-11-25 | 2016-11-25 | 2016-11-25 | 2016-11-25 | 2016-11-25 | 2016-11-25 | 2016-11-25 | 2016-11-25 | 2016-11-25 | 2016-11-25 | 2016-11-25 | 2016-11-25 | 2016-11-25 | 2016-11-25 | 2016-11-25 | 2016-11-25 | 2016-11-25 | 2016-11-25 | 2016-11-25 | 2016-11-25 | 2016-11-25 | 2016-11-25 | 2016-11-25 | 2016-11-25 | 2016-11-25 | 2016-11-25
2AI101CV01100-08110 | EOF:Rebar, Formwork, embadents fixing and Concreting for duct bank | [15 empty] | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21
2AI101CV01100-08100 | EOF:Blinding/PCC for duct bank | [15 empty] | 2016-11-14 | 2016-11-14 | 2016-11-14 | 2016-11-14 | 2016-11-14 | 2016-11-14 | 2016-11-14 | 2016-11-14 | 2016-11-14 | 2016-11-14 | 2016-11-14 | 2016-11-14 | 2016-11-14 | 2016-11-14 | 2016-11-14 | 2016-11-14 | 2016-11-14 | 2016-11-14 | 2016-11-14 | 2016-11-14 | 2016-11-14 | 2016-11-14 | 2016-11-14 | 2016-11-14 | 2016-11-14 | 2016-11-14 | 2016-11-14 | 2016-11-14 | 2016-11-14 | 2016-11-14 | 2016-11-14
2AI101CV01100-08090 | EOF:Excavation & Subgrade for duct bank | [15 empty] | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30
2AI101CV01100-08075 | EOF:Asphalt Work
2AI101CV01100-08070 | EOF:Preparation of sub grade
2AI101CV01100-08065 | EOF:Grading & leveling
2AI101CV01100-08060 | EOF:Excavation
2AI101CV01100-08055 | EOF:Concrete Work
2AI101CV01100-08050 | EOF:Preparation of sub grade
2AI101CV01100-08045 | EOF:Grading & leveling
2AI101CV01100-08040 | EOF:Excavation
2AI101CV01100-08035 | EOF:Compaction
2AI101CV01100-08033 | EOF: Finishing
2AI101CV01100-08032 | EOF: Concrete Pouring
2AI101CV01100-08030 | EOF:Gutch Filling
2AI101CV01100-08029 | EOF: Reinforcement
2AI101CV01100-08028 | EOF: Formwork
2AI101CV01100-08027 | EOF: Sub base & Base preparation
2AI101CV01100-08026 | EOF:Grading & leveling
2AI101CV01100-08025 | EOF: Grade slab for Pump shelters/Mobile shelters
2AI101CV01100-08021 | EOF:Excavation
2AI101CV01100-08020 | EOF: Road Crossing and Concrete cable duct banks | [17 empty] | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28
2AI101CV01100-08016 | EOF:Bollards & Crash barrier installation
2AI101CV01100-08015 | EOF: Asphalt Paving
2AI101CV01100-08011 | EOF:Asphalt Work
2AI101CV01100-08010 | EOF: Reinforced Concrete Paving
2AI101CV01100-08006 | EOF:Preparation of sub grade
2AI101CV01100-08005 | EOF: Asphalt Road Work
2AI101CV01100-08001 | EOF:Grading & leveling
2AI101CV01100-08000 | EOF: Gutch Road Work
2AI101CV01100 | EOF: Roads, Crossing & Paving Works
2AI101CV01000-08100 | EOF: Site preparation (New storage Tank Area) including substation | [15 empty] | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24
2AI101CV01000-08025 | EOF:Disposal of Surplus Material | [15 empty] | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09
2AI101CV01000-08020 | EOF:Grading, Filling & Compaction | [15 empty] | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24
2AI101CV01000-08015 | EOF:Grading, Cutting & Stockpiling | [15 empty] | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24
2AI101CV01000-08010 | EOF:Site clearance & Stripping & disposal of Contaminated material(If any) | [11 empty] | 2016-07-15 | 2016-07-15 | 2016-07-15 | 2016-07-15 | 2016-07-15 | 2016-07-15 | 2016-07-15 | 2016-07-15 | 2016-07-15 | 2016-07-15 | 2016-07-15 | 2016-07-15 | 2016-07-15 | 2016-07-15 | 2016-07-15 | 2016-07-15 | 2016-07-15 | 2016-07-15 | 2016-07-15 | 2016-07-15 | 2016-07-15 | 2016-07-15 | 2016-07-15 | 2016-07-15 | 2016-07-15 | 2016-07-15 | 2016-07-15 | 2016-07-15 | 2016-07-15 | 2016-07-15 | 2016-07-15 | 2016-07-15 | 2016-07-15 | 2016-07-15 | 2016-07-15
2AI101CV01000-08005 | EOF: Excavation Notification | [5 empty] | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10
2AI101CV01000-08000 | EOF:Verification of Survey for existing grade Level | [5 empty] | 2016-01-02 | 2016-01-02 | 2016-01-02 | 2016-01-02 | 2016-01-02 | 2016-01-02 | 2016-01-02 | 2016-01-02 | 2016-01-02 | 2016-01-02 | 2016-01-02 | 2016-01-02 | 2016-01-02 | 2016-01-02 | 2016-01-02 | 2016-01-02 | 2016-01-02 | 2016-01-02 | 2016-01-02 | 2016-01-02 | 2016-01-02 | 2016-01-02 | 2016-01-02 | 2016-01-02 | 2016-01-02 | 2016-01-02 | 2016-01-02 | 2016-01-02 | 2016-01-02 | 2016-01-02 | 2016-01-02 | 2016-01-02 | 2016-01-02 | 2016-01-02 | 2016-01-02 | 2016-01-02 | 2016-01-02 | 2016-01-02 | 2016-01-02 | 2016-01-02 | 2016-01-02
2AI101CV01000 | EOF: Site preparation (New storage Tank Area) | [15 empty] | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24 | 2016-11-24
2AI000PC00300-08000 | Portion2 : EOF Construction Completion Certificate - Submission to Company & Approval by Company
2AI000PC00300 | Portion2 : EOF Construction Completion Certificate - Submission to Company & Approval by Company
2AI000ME00320-08255 | Milled asphalt Work | [5 empty] | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29
2AI000ME00320-08250 | Grading Work | [5 empty] | 2015-12-24 | 2015-12-24 | 2015-12-24 | 2015-12-24 | 2015-12-24 | 2015-12-24 | 2015-12-24 | 2015-12-24 | 2015-12-24 | 2015-12-24 | 2015-12-24 | 2015-12-24 | 2015-12-24 | 2015-12-24 | 2015-12-24 | 2015-12-24 | 2015-12-24 | 2015-12-24 | 2015-12-24 | 2015-12-24 | 2015-12-24 | 2015-12-24 | 2015-12-24 | 2015-12-24 | 2015-12-24 | 2015-12-24 | 2015-12-24 | 2015-12-24 | 2015-12-24 | 2015-12-24 | 2015-12-24 | 2015-12-24 | 2015-12-24 | 2015-12-24 | 2015-12-24 | 2015-12-24 | 2015-12-24 | 2015-12-24 | 2015-12-24 | 2015-12-24 | 2015-12-24
2AI000ME00320-08245 | Mechanical Fabrication Yard | [5 empty] | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27
2AI000ME00320-08240 | Installation of Water Tank | [5 empty] | 2015-12-30 | 2015-12-30 | 2015-12-30 | 2015-12-30 | 2015-12-30 | 2015-12-30 | 2015-12-30 | 2015-12-30 | 2015-12-30 | 2015-12-30 | 2015-12-30 | 2015-12-30 | 2015-12-30 | 2015-12-30 | 2015-12-30 | 2015-12-30 | 2015-12-30 | 2015-12-30 | 2015-12-30 | 2015-12-30 | 2015-12-30 | 2015-12-30 | 2015-12-30 | 2015-12-30 | 2015-12-30 | 2015-12-30 | 2015-12-30 | 2015-12-30 | 2015-12-30 | 2015-12-30 | 2015-12-30 | 2015-12-30 | 2015-12-30 | 2015-12-30 | 2015-12-30 | 2015-12-30 | 2015-12-30 | 2015-12-30 | 2015-12-30 | 2015-12-30 | 2015-12-30
2AI000ME00320-08235 | Fabrication & Installation - Garage Shed | [5 empty] | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28
2AI000ME00320-08230 | Vehicle/Equipment Maintenance Area | [5 empty] | 2015-12-20 | 2015-12-20 | 2015-12-20 | 2015-12-20 | 2015-12-20 | 2015-12-20 | 2015-12-20 | 2015-12-20 | 2015-12-20 | 2015-12-20 | 2015-12-20 | 2015-12-20 | 2015-12-20 | 2015-12-20 | 2015-12-20 | 2015-12-20 | 2015-12-20 | 2015-12-20 | 2015-12-20 | 2015-12-20 | 2015-12-20 | 2015-12-20 | 2015-12-20 | 2015-12-20 | 2015-12-20 | 2015-12-20 | 2015-12-20 | 2015-12-20 | 2015-12-20 | 2015-12-20 | 2015-12-20 | 2015-12-20 | 2015-12-20 | 2015-12-20 | 2015-12-20 | 2015-12-20 | 2015-12-20 | 2015-12-20 | 2015-12-20 | 2015-12-20 | 2015-12-20
2AI000ME00320-08225 | Paving Works for Rebar/Precast Area | [5 empty] | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16
2AI000ME00320-08220 | Commissioning & Ready to Use | [5 empty] | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23
2AI000ME00320-08215 | Electrical Works | [5 empty] | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22
2AI000ME00320-08210 | Completion of Shelter | [5 empty] | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17
2AI000ME00320-08205 | Installation of Generator | [5 empty] | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15
2AI000ME00320-08200 | Completion of Plumbing Works | [5 empty] | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10
2AI000ME00320-08195 | Installation | [5 empty] | 2015-12-03 | 2015-12-03 | 2015-12-03 | 2015-12-03 | 2015-12-03 | 2015-12-03 | 2015-12-03 | 2015-12-03 | 2015-12-03 | 2015-12-03 | 2015-12-03 | 2015-12-03 | 2015-12-03 | 2015-12-03 | 2015-12-03 | 2015-12-03 | 2015-12-03 | 2015-12-03 | 2015-12-03 | 2015-12-03 | 2015-12-03 | 2015-12-03 | 2015-12-03 | 2015-12-03 | 2015-12-03 | 2015-12-03 | 2015-12-03 | 2015-12-03 | 2015-12-03 | 2015-12-03 | 2015-12-03 | 2015-12-03 | 2015-12-03 | 2015-12-03 | 2015-12-03 | 2015-12-03 | 2015-12-03 | 2015-12-03 | 2015-12-03 | 2015-12-03 | 2015-12-03
2AI000ME00320-08190 | Foundation | time axis 2015-11-29 to 2015-11-29
2AI000ME00320-08185 | Completion of Plumbing Works | [5 empty] | 2015-12-01 | 2015-12-01 | 2015-12-01 | 2015-12-01 | 2015-12-01 | 2015-12-01 | 2015-12-01 | 2015-12-01 | 2015-12-01 | 2015-12-01 | 2015-12-01 | 2015-12-01 | 2015-12-01 | 2015-12-01 | 2015-12-01 | 2015-12-01 | 2015-12-01 | 2015-12-01 | 2015-12-01 | 2015-12-01 | 2015-12-01 | 2015-12-01 | 2015-12-01 | 2015-12-01 | 2015-12-01 | 2015-12-01 | 2015-12-01 | 2015-12-01 | 2015-12-01 | 2015-12-01 | 2015-12-01 | 2015-12-01 | 2015-12-01 | 2015-12-01 | 2015-12-01 | 2015-12-01 | 2015-12-01 | 2015-12-01 | 2015-12-01 | 2015-12-01 | 2015-12-01
2AI000ME00320-08180 | Foundation Works | time axis 2015-11-28 to 2015-11-28
2AI000ME00320-08175 | Pit Excavation | time axis 2015-11-25 to 2015-11-25
2AI000ME00320-08170 | MEP Works Completion | [5 empty] | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15
2AI000ME00320-08165 | Installation & Assembling of Portable cabins | [5 empty] | 2015-12-12 | 2015-12-12 | 2015-12-12 | 2015-12-12 | 2015-12-12 | 2015-12-12 | 2015-12-12 | 2015-12-12 | 2015-12-12 | 2015-12-12 | 2015-12-12 | 2015-12-12 | 2015-12-12 | 2015-12-12 | 2015-12-12 | 2015-12-12 | 2015-12-12 | 2015-12-12 | 2015-12-12 | 2015-12-12 | 2015-12-12 | 2015-12-12 | 2015-12-12 | 2015-12-12 | 2015-12-12 | 2015-12-12 | 2015-12-12 | 2015-12-12 | 2015-12-12 | 2015-12-12 | 2015-12-12 | 2015-12-12 | 2015-12-12 | 2015-12-12 | 2015-12-12 | 2015-12-12 | 2015-12-12 | 2015-12-12 | 2015-12-12 | 2015-12-12 | 2015-12-12
2AI000ME00320-08160 | Foundation Block Fixing | [5 empty] | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08
2AI000ME00320-08155 | MEP Works Completion | [5 empty] | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17
2AI000ME00320-08150 | Inside Furnishing | [5 empty] | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14
2AI000ME00320-08145 | Installation & Assembling of Mess Hall Portable cabins | [5 empty] | 2015-12-12 | 2015-12-12 | 2015-12-12 | 2015-12-12 | 2015-12-12 | 2015-12-12 | 2015-12-12 | 2015-12-12 | 2015-12-12 | 2015-12-12 | 2015-12-12 | 2015-12-12 | 2015-12-12 | 2015-12-12 | 2015-12-12 | 2015-12-12 | 2015-12-12 | 2015-12-12 | 2015-12-12 | 2015-12-12 | 2015-12-12 | 2015-12-12 | 2015-12-12 | 2015-12-12 | 2015-12-12 | 2015-12-12 | 2015-12-12 | 2015-12-12 | 2015-12-12 | 2015-12-12 | 2015-12-12 | 2015-12-12 | 2015-12-12 | 2015-12-12 | 2015-12-12 | 2015-12-12 | 2015-12-12 | 2015-12-12 | 2015-12-12 | 2015-12-12 | 2015-12-12
2AI000ME00320-08140 | Foundation Block Fixing for Portable cabins | [5 empty] | 2015-12-07 | 2015-12-07 | 2015-12-07 | 2015-12-07 | 2015-12-07 | 2015-12-07 | 2015-12-07 | 2015-12-07 | 2015-12-07 | 2015-12-07 | 2015-12-07 | 2015-12-07 | 2015-12-07 | 2015-12-07 | 2015-12-07 | 2015-12-07 | 2015-12-07 | 2015-12-07 | 2015-12-07 | 2015-12-07 | 2015-12-07 | 2015-12-07 | 2015-12-07 | 2015-12-07 | 2015-12-07 | 2015-12-07 | 2015-12-07 | 2015-12-07 | 2015-12-07 | 2015-12-07 | 2015-12-07 | 2015-12-07 | 2015-12-07 | 2015-12-07 | 2015-12-07 | 2015-12-07 | 2015-12-07 | 2015-12-07 | 2015-12-07 | 2015-12-07 | 2015-12-07
2AI000ME00320-08135 | Installation of Portable cabins for store | [5 empty] | 2015-12-19 | 2015-12-19 | 2015-12-19 | 2015-12-19 | 2015-12-19 | 2015-12-19 | 2015-12-19 | 2015-12-19 | 2015-12-19 | 2015-12-19 | 2015-12-19 | 2015-12-19 | 2015-12-19 | 2015-12-19 | 2015-12-19 | 2015-12-19 | 2015-12-19 | 2015-12-19 | 2015-12-19 | 2015-12-19 | 2015-12-19 | 2015-12-19 | 2015-12-19 | 2015-12-19 | 2015-12-19 | 2015-12-19 | 2015-12-19 | 2015-12-19 | 2015-12-19 | 2015-12-19 | 2015-12-19 | 2015-12-19 | 2015-12-19 | 2015-12-19 | 2015-12-19 | 2015-12-19 | 2015-12-19 | 2015-12-19 | 2015-12-19 | 2015-12-19 | 2015-12-19
2AI000ME00320-08130 | Installation of Storage Containers | [5 empty] | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15
2AI000ME00320-08125 | Foundation Block Fixing for Portable cabins | [5 empty] | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08
2AI000ME00320-08120 | Fabrication of Store Portable Cabin | [5 empty] | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06
2AI000ME00320-08115 | Parking Area | [5 empty] | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31
2AI000ME00320-08110 | Furnishing & Networking | [5 empty] | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29
2AI000ME00320-08105 | Electrical & Plumbing Works | [5 empty] | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22
2AI000ME00320-08100 | Installation & Assembling of Portable cabins | [5 empty] | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27
2AI000ME00320-08095 | Shipment & Delivery to site | [5 empty] | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09
2AI000ME00320-08090 | Foundation Block Fixing - Site office | [5 empty] | 2015-12-05 | 2015-12-05 | 2015-12-05 | 2015-12-05 | 2015-12-05 | 2015-12-05 | 2015-12-05 | 2015-12-05 | 2015-12-05 | 2015-12-05 | 2015-12-05 | 2015-12-05 | 2015-12-05 | 2015-12-05 | 2015-12-05 | 2015-12-05 | 2015-12-05 | 2015-12-05 | 2015-12-05 | 2015-12-05 | 2015-12-05 | 2015-12-05 | 2015-12-05 | 2015-12-05 | 2015-12-05 | 2015-12-05 | 2015-12-05 | 2015-12-05 | 2015-12-05 | 2015-12-05 | 2015-12-05 | 2015-12-05 | 2015-12-05 | 2015-12-05 | 2015-12-05 | 2015-12-05 | 2015-12-05 | 2015-12-05 | 2015-12-05 | 2015-12-05 | 2015-12-05
2AI000ME00320-08085 | Manufacturing Site office Cabins | [5 empty] | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06
2AI000ME00320-08080 | Project Sign Board Fixing | [5 empty] | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15
2AI000ME00320-08075 | Internal Fencing & Gate Installation-Yard | [5 empty] | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23
2AI000ME00320-08070 | External Fencing & Gate Installation | [5 empty] | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14
2AI000ME00320-08065 | Procurement of fencing material | [5 empty] | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10
2AI000ME00320-08060 | Scrubbing & Grading | time axis 2015-11-30 to 2015-11-30
2AI000ME00320-08055 | Slit Trench Excavation Work | [5 empty] | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08
2AI000ME00320-08050 | Excavation Notification | time axis 2015-11-04 to 2015-11-04
2AI000ME00320-08045 | Survey & Setting Layout | [5 empty] | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08
2AI000GE01300-08000 | Portion2 : EOF Mechanical Completion Certificate - Submission to Company & Approval by Company
2AI000GE01300 | Portion2 : EOF Mechanical Completion Certificate - Submission to Company & Approval by Company
2AI000GE00300-08005 | EOF - Liquidation of construction punch points ('A' items)
2AI000GE00300 | EOF - Liquidation of construction punch points ('A' items)
2AG000M505200-08045 | Issue First Equipment/Material by PIL | [7 empty] | 2016-03-12 | 2016-03-12 | 2016-03-12 | 2016-03-12 | 2016-03-12 | 2016-03-12 | 2016-03-12 | 2016-03-12 | 2016-03-12 | 2016-03-12 | 2016-03-12 | 2016-03-12 | 2016-03-12 | 2016-03-12 | 2016-03-12 | 2016-03-12 | 2016-03-12 | 2016-03-12 | 2016-03-12 | 2016-03-12 | 2016-03-12 | 2016-03-12 | 2016-03-12 | 2016-03-12 | 2016-03-12 | 2016-03-12 | 2016-03-12 | 2016-03-12 | 2016-03-12 | 2016-03-12 | 2016-03-12 | 2016-03-12 | 2016-03-12 | 2016-03-12 | 2016-03-12 | 2016-03-12 | 2016-03-12 | 2016-03-12 | 2016-03-12
2AG000M505200-08035 | Issue First AFC Drawing by PIL | [7 empty] | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24
2AG000M505200-08030 | Construction Completion of temp. facility | [5 empty] | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31
2AG000M505200-08025 | Area Clearance from client for TFC | time axis 2015-10-20 to 2015-10-20
2AG000M505200-08020 | Kickoff Meeting | time axis 2015-10-20 to 2015-10-20
2AG000M505200-08015 | Sub-contractor Approval By KOC | time axis 2015-10-20 to 2015-10-20
2AG000M505200-08000 | Subcontract Effective Date | time axis 2015-08-06 to 2015-08-06
2AG000M100100-08085 | 52-R-303 - EMERGENCY GENERATOR BUILDING (LMM) Readyness for EIT Works inside the Building | [31 empty] | 2018-03-06 | 2018-03-06 | 2018-03-06 | 2018-03-06 | 2018-03-06 | 2018-03-06 | 2018-03-06 | 2018-03-06 | 2018-03-06 | 2018-03-06 | 2018-03-06 | 2018-03-06 | 2018-03-06 | 2018-03-06 | 2018-03-06
2AG000M100100-08080 | 52-R-302 - EMERGENCY GENERATOR BUILDING (STF) Readyness for EIT Works inside the Building | [35 empty] | 2018-07-12 | 2018-07-12 | 2018-07-12 | 2018-07-12 | 2018-07-12 | 2018-07-12 | 2018-07-12 | 2018-07-12 | 2018-07-12 | 2018-07-12 | 2018-07-12
2AG000M100100-08075 | 50-R-002 - EMERGENCY GENERATOR BUILDING (COCC) Readyness for EIT Works inside the Building | [35 empty] | 2018-07-23 | 2018-07-23 | 2018-07-23 | 2018-07-23 | 2018-07-23 | 2018-07-23 | 2018-07-23 | 2018-07-23 | 2018-07-23 | 2018-07-23 | 2018-07-23
2AG000M100100-08070 | 52-R-301 - EMERGENCY GENERATOR BUILDING (FMM) Readyness for EIT Works inside the Building | [35 empty] | 2018-06-25 | 2018-06-25 | 2018-06-25 | 2018-06-25 | 2018-06-25 | 2018-06-25 | 2018-06-25 | 2018-06-25 | 2018-06-25 | 2018-06-25 | 2018-06-25
2AG000M100100-08065 | EOF SS: 52-SUBST-303 - SUBSTATION - LMM Readyness for EIT Works inside the Building | [27 empty] | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15
2AG000M100100-08060 | EOF SS: 50-SUBST-001 - SUBSTATION - COCC Readyness for EIT Works inside the Building | [29 empty] | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20
2AG000M100100-08055 | EOF SS: 52-SUBST-302 - SUBSTATION - STF Readyness for EIT Works inside the Building | [29 empty] | 2018-01-08 | 2018-01-08 | 2018-01-08 | 2018-01-08 | 2018-01-08 | 2018-01-08 | 2018-01-08 | 2018-01-08 | 2018-01-08 | 2018-01-08 | 2018-01-08 | 2018-01-08 | 2018-01-08 | 2018-01-08 | 2018-01-08 | 2018-01-08 | 2018-01-08
2AG000M100100-08050 | EOF SS: 52-SUBST-301 - SUBSTATION - FMM Readyness for EIT Works inside the Building | [29 empty] | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01
2AG000M100100-08045 | COCC Building : Clearance for EIT Works inside the Building | [31 empty] | 2018-03-06 | 2018-03-06 | 2018-03-06 | 2018-03-06 | 2018-03-06 | 2018-03-06 | 2018-03-06 | 2018-03-06 | 2018-03-06 | 2018-03-06 | 2018-03-06 | 2018-03-06 | 2018-03-06 | 2018-03-06 | 2018-03-06
2AG000M100100-08040 | LFHO Tank Foundation Completion 52-D-96 | [15 empty] | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05
2AG000M100100-08035 | LFHO Tank Foundation Completion 52-D-95 | [15 empty] | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09
2AG000M100100-08030 | LFHO Tank Foundation Completion 52-D-94 | [13 empty] | 2016-08-22 | 2016-08-22 | 2016-08-22 | 2016-08-22 | 2016-08-22 | 2016-08-22 | 2016-08-22 | 2016-08-22 | 2016-08-22 | 2016-08-22 | 2016-08-22 | 2016-08-22 | 2016-08-22 | 2016-08-22 | 2016-08-22 | 2016-08-22 | 2016-08-22 | 2016-08-22 | 2016-08-22 | 2016-08-22 | 2016-08-22 | 2016-08-22 | 2016-08-22 | 2016-08-22 | 2016-08-22 | 2016-08-22 | 2016-08-22 | 2016-08-22 | 2016-08-22 | 2016-08-22 | 2016-08-22 | 2016-08-22 | 2016-08-22
2AG000M100100-08025 | LFHO Tank Foundation Completion 52-D-93 | [13 empty] | 2016-09-05 | 2016-09-05 | 2016-09-05 | 2016-09-05 | 2016-09-05 | 2016-09-05 | 2016-09-05 | 2016-09-05 | 2016-09-05 | 2016-09-05 | 2016-09-05 | 2016-09-05 | 2016-09-05 | 2016-09-05 | 2016-09-05 | 2016-09-05 | 2016-09-05 | 2016-09-05 | 2016-09-05 | 2016-09-05 | 2016-09-05 | 2016-09-05 | 2016-09-05 | 2016-09-05 | 2016-09-05 | 2016-09-05 | 2016-09-05 | 2016-09-05 | 2016-09-05 | 2016-09-05 | 2016-09-05 | 2016-09-05 | 2016-09-05
2AG000M100100-08020 | Construction Completion / Subcontract Mechancial Completion for MEI Works
2AG000M100100-08015 | Mechanical Completion Certificate (MCC) for MEI Works
2AG000M100100-08010 | Construction Completion / Subcontract Mechancial Completion for Civil Works
2AG000M100100-08005 | Mechanical Completion Certificate (MCC) for Civil Works
2AG000M100100-08000 | Contract Commencement | time axis 2015-10-01 to 2015-10-01
2AG000D101401-08045 | Report formats | time axis 2015-10-31 to 2015-10-31
2AG000D101401-08040 | Project Quality Plan | [7 empty] | 2016-02-04 | 2016-02-04 | 2016-02-04 | 2016-02-04 | 2016-02-04 | 2016-02-04 | 2016-02-04 | 2016-02-04 | 2016-02-04 | 2016-02-04 | 2016-02-04 | 2016-02-04 | 2016-02-04 | 2016-02-04 | 2016-02-04 | 2016-02-04 | 2016-02-04 | 2016-02-04 | 2016-02-04 | 2016-02-04 | 2016-02-04 | 2016-02-04 | 2016-02-04 | 2016-02-04 | 2016-02-04 | 2016-02-04 | 2016-02-04 | 2016-02-04 | 2016-02-04 | 2016-02-04 | 2016-02-04 | 2016-02-04 | 2016-02-04 | 2016-02-04 | 2016-02-04 | 2016-02-04 | 2016-02-04 | 2016-02-04 | 2016-02-04
2AG000D101401-08030 | Construction Execution Plan | [7 empty] | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01
2AG000D101401-08025 | Site HSE Plan | [7 empty] | 2016-02-20 | 2016-02-20 | 2016-02-20 | 2016-02-20 | 2016-02-20 | 2016-02-20 | 2016-02-20 | 2016-02-20 | 2016-02-20 | 2016-02-20 | 2016-02-20 | 2016-02-20 | 2016-02-20 | 2016-02-20 | 2016-02-20 | 2016-02-20 | 2016-02-20 | 2016-02-20 | 2016-02-20 | 2016-02-20 | 2016-02-20 | 2016-02-20 | 2016-02-20 | 2016-02-20 | 2016-02-20 | 2016-02-20 | 2016-02-20 | 2016-02-20 | 2016-02-20 | 2016-02-20 | 2016-02-20 | 2016-02-20 | 2016-02-20 | 2016-02-20 | 2016-02-20 | 2016-02-20 | 2016-02-20 | 2016-02-20 | 2016-02-20
2AG000D101401-08020 | Bank Guaranty Submital | time axis 2015-09-26 to 2015-09-26
2AG000D101401-08015 | Deliverable List | [7 empty] | 2016-02-24 | 2016-02-24 | 2016-02-24 | 2016-02-24 | 2016-02-24 | 2016-02-24 | 2016-02-24 | 2016-02-24 | 2016-02-24 | 2016-02-24 | 2016-02-24 | 2016-02-24 | 2016-02-24 | 2016-02-24 | 2016-02-24 | 2016-02-24 | 2016-02-24 | 2016-02-24 | 2016-02-24 | 2016-02-24 | 2016-02-24 | 2016-02-24 | 2016-02-24 | 2016-02-24 | 2016-02-24 | 2016-02-24 | 2016-02-24 | 2016-02-24 | 2016-02-24 | 2016-02-24 | 2016-02-24 | 2016-02-24 | 2016-02-24 | 2016-02-24 | 2016-02-24 | 2016-02-24 | 2016-02-24 | 2016-02-24 | 2016-02-24
2AG000D101401-08010 | CV's of Key Personnel | [5 empty] | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16
2AG000D101401-08005 | Organization Chart | [11 empty] | 2016-07-13 | 2016-07-13 | 2016-07-13 | 2016-07-13 | 2016-07-13 | 2016-07-13 | 2016-07-13 | 2016-07-13 | 2016-07-13 | 2016-07-13 | 2016-07-13 | 2016-07-13 | 2016-07-13 | 2016-07-13 | 2016-07-13 | 2016-07-13 | 2016-07-13 | 2016-07-13 | 2016-07-13 | 2016-07-13 | 2016-07-13 | 2016-07-13 | 2016-07-13 | 2016-07-13 | 2016-07-13 | 2016-07-13 | 2016-07-13 | 2016-07-13 | 2016-07-13 | 2016-07-13 | 2016-07-13 | 2016-07-13 | 2016-07-13 | 2016-07-13 | 2016-07-13
2AG000D101401-08000 | Insurance | time axis 2015-10-20 to 2015-10-20
2AE800MC02100-08005 | Delivery of Cathodic Protection System - First Lot | [31 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
2AE142CV01100-08105 | COCC: AFC drawings for EIT Duct Banks | [19 empty] | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21
2AE142CV01100-08100 | COCC: AFC drawings for EIT Cable Trench Routing Layout | [29 empty] | 2018-01-09 | 2018-01-09 | 2018-01-09 | 2018-01-09 | 2018-01-09 | 2018-01-09 | 2018-01-09 | 2018-01-09 | 2018-01-09 | 2018-01-09 | 2018-01-09 | 2018-01-09 | 2018-01-09 | 2018-01-09 | 2018-01-09 | 2018-01-09 | 2018-01-09
2AE142CV01000-08105 | EOF: AFC drawings for Existing U/G Cable Re-Routing & Relocation of RMU | [9 empty] | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11
2AE142CV01000-08100 | EOF: AFC drawings for Demolition of Existing Road and Exisitng Fence Relocation | [21 empty] | 2017-05-22 | 2017-05-22 | 2017-05-22 | 2017-05-22 | 2017-05-22 | 2017-05-22 | 2017-05-22 | 2017-05-22 | 2017-05-22 | 2017-05-22 | 2017-05-22 | 2017-05-22 | 2017-05-22 | 2017-05-22 | 2017-05-22 | 2017-05-22 | 2017-05-22 | 2017-05-22 | 2017-05-22 | 2017-05-22 | 2017-05-22 | 2017-05-22 | 2017-05-22 | 2017-05-22 | 2017-05-22
2AE141EL00100-08100 | EOF: COCC CCR Building 621-R-001: AFC Drawing for Single Line Diagram | [25 empty] | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19
2AE133EL05800-08400 | 52-R-303 - AFC Drawing for Equipment layout | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AE133EL05800-08300 | 52-R-302 - AFC Drawing for Equipment layout | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AE133EL05800-08200 | 52-R-002 - AFC Drawing for Equipment layout | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AE133EL05800-08100 | 52-R-301 - AFC Drawing for Equipment layout | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AE133EL03800-08100 | EOF: Substation 52-SUBT-303: AFC Drawing for Earthing & lightning Layout | [27 empty] | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30
2AE133EL03700-08100 | EOF: Substation 52-SUBT-302: AFC Drawing for Earthing & lightning Layout | [25 empty] | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20
2AE133EL03600-08200 | 52-R-301 - AFC Drawing for Earthing & lightning Layout | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AE133EL03600-08100 | EOF: Substation 52-SUBT-301: AFC Drawing for Earthing & lightning Layout | [25 empty] | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20
2AE133EL03500-08100 | COCC: Substation 52-SUBT-001: AFC Drawing for Earthing & lightning Layout | [23 empty] | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31
2AE133EL02500-08100 | EOF: Substation 52-SUBT-303: AFC Drawing for Equipment layout | [27 empty] | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17
2AE133EL02400-08100 | EOF: Substation 52-SUBT-302: AFC Drawing for Equipment layout | [27 empty] | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11
2AE133EL02300-08100 | EOF: Substation 52-SUBT-301: AFC Drawing for Equipment layout | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AE133EL02200-08100 | COCC: Substation 52-SUBT-001: AFC Drawing for Equipment layout | [27 empty] | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17
2AE133EL02100-08200 | 52-R-303 - AFC Drawing for Single Line Diagram | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AE133EL02100-08100 | EOF: Substation 52-SUBT-303: AFC Drawing for Single Line Diagram | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AE133EL01400-08200 | 52-R-302 - AFC Drawing for Single Line Diagram | [31 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
2AE133EL01400-08100 | EOF: Substation 52-SUBT-302: AFC Drawing for Single Line Diagram | [31 empty] | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05
2AE133EL01000-08200 | 52-R-301 - AFC Drawing for Single Line Diagram | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AE133EL01000-08100 | EOF: Substation 52-SUBT-301: AFC Drawing for Single Line Diagram | [31 empty] | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05
2AE133EL00600-08200 | 52-R-002 - AFC Drawing for Single Line Diagram | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AE133EL00600-08100 | COCC: Substation 52-SUBT-001: AFC Drawing for Single Line Diagram | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AE133CV05200-08100 | EOF: AFC drawings for Diesel Fuel Day Tanks of Substations | [17 empty] | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17
2AE133CV05100-08100 | EOF: AFC drawings for Transformers for 52-SUBST-303, 52-SUBST-001, 52-SUBST-301 & 52-SUBST-302 | [19 empty] | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21
2AE133CV04500-08100 | EOF: AFC drawings for Shelters of Diesel Fuel Day Tanks of Substations | [23 empty] | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01
2AE133CV04400-08100 | EOF: AFC drawings for Shelter of Transformers for 52-SUBST-303, 52-SUBST-001, 52-SUBST-301 & 52-SUBST-302 | [19 empty] | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21
2AE133CV04000-08120 | COCC: AFC drawings for Road and Paving | [23 empty] | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31
2AE133CV04000-08110 | COCC: AFC drawings for Fire Water Pump Shelters | [11 empty] | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17
2AE133CV04000-08105 | COCC: AFC drawings for Car Park Shelters & Other Misc. Shelters | [23 empty] | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31
2AE133CV04000-08100 | EOF: AFC drawings for Car Park Shelters & Other Misc. Shelters | [23 empty] | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31
2AE101CV01400-08100 | EOF: AFC drawings for Foam System Package (621-Z-301A/B) | [23 empty] | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27
2AE101CV01300-08100 | EOF: AFC drawings for Bund Wall of LFHO Storage Tank | [33 empty] | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06
2AE101CV01200-08100 | EOF: AFC drawings for Trim Pump (621-G-301A/B) | [19 empty] | 2017-01-30 | 2017-01-30 | 2017-01-30 | 2017-01-30 | 2017-01-30 | 2017-01-30 | 2017-01-30 | 2017-01-30 | 2017-01-30 | 2017-01-30 | 2017-01-30 | 2017-01-30 | 2017-01-30 | 2017-01-30 | 2017-01-30 | 2017-01-30 | 2017-01-30 | 2017-01-30 | 2017-01-30 | 2017-01-30 | 2017-01-30 | 2017-01-30 | 2017-01-30 | 2017-01-30 | 2017-01-30 | 2017-01-30 | 2017-01-30
2AE101CV01100-08125 | EOF: AFC drawings for Oily Water Transfer Vessel 621-V-301( having Pump - 52-G-303 A/B ) | [13 empty] | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25
2AE101CV01100-08115 | EOF: AFC drawings for Overhead Water Tank (621-D-309A/B) | [11 empty] | 2016-06-19 | 2016-06-19 | 2016-06-19 | 2016-06-19 | 2016-06-19 | 2016-06-19 | 2016-06-19 | 2016-06-19 | 2016-06-19 | 2016-06-19 | 2016-06-19 | 2016-06-19 | 2016-06-19 | 2016-06-19 | 2016-06-19 | 2016-06-19 | 2016-06-19 | 2016-06-19 | 2016-06-19 | 2016-06-19 | 2016-06-19 | 2016-06-19 | 2016-06-19 | 2016-06-19 | 2016-06-19 | 2016-06-19 | 2016-06-19 | 2016-06-19 | 2016-06-19 | 2016-06-19 | 2016-06-19 | 2016-06-19 | 2016-06-19 | 2016-06-19 | 2016-06-19
2AE101CV01100-08110 | EOF: AFC drawings for Drain Tank (621-D-308A/B) | [27 empty] | 2017-10-24 | 2017-10-24 | 2017-10-24 | 2017-10-24 | 2017-10-24 | 2017-10-24 | 2017-10-24 | 2017-10-24 | 2017-10-24 | 2017-10-24 | 2017-10-24 | 2017-10-24 | 2017-10-24 | 2017-10-24 | 2017-10-24 | 2017-10-24 | 2017-10-24 | 2017-10-24 | 2017-10-24
2AE101CV01100-08105 | EOF: AFC drawings for Flushing Water Drain Tank (621-D-306A/B) | [9 empty] | 2016-05-02 | 2016-05-02 | 2016-05-02 | 2016-05-02 | 2016-05-02 | 2016-05-02 | 2016-05-02 | 2016-05-02 | 2016-05-02 | 2016-05-02 | 2016-05-02 | 2016-05-02 | 2016-05-02 | 2016-05-02 | 2016-05-02 | 2016-05-02 | 2016-05-02 | 2016-05-02 | 2016-05-02 | 2016-05-02 | 2016-05-02 | 2016-05-02 | 2016-05-02 | 2016-05-02 | 2016-05-02 | 2016-05-02 | 2016-05-02 | 2016-05-02 | 2016-05-02 | 2016-05-02 | 2016-05-02 | 2016-05-02 | 2016-05-02 | 2016-05-02 | 2016-05-02 | 2016-05-02 | 2016-05-02
2AE101CV01100-08100 | EOF: AFC drawings for Foam Drain Tank (621-D-305A/B) | [9 empty] | 2016-04-26 | 2016-04-26 | 2016-04-26 | 2016-04-26 | 2016-04-26 | 2016-04-26 | 2016-04-26 | 2016-04-26 | 2016-04-26 | 2016-04-26 | 2016-04-26 | 2016-04-26 | 2016-04-26 | 2016-04-26 | 2016-04-26 | 2016-04-26 | 2016-04-26 | 2016-04-26 | 2016-04-26 | 2016-04-26 | 2016-04-26 | 2016-04-26 | 2016-04-26 | 2016-04-26 | 2016-04-26 | 2016-04-26 | 2016-04-26 | 2016-04-26 | 2016-04-26 | 2016-04-26 | 2016-04-26 | 2016-04-26 | 2016-04-26 | 2016-04-26 | 2016-04-26 | 2016-04-26 | 2016-04-26
2AE101CV01000-08105 | EOF: AFC drawings for Diesel Fuel Tank (621-D-307A-D) | [19 empty] | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21
2AE101CV01000-08100 | EOF: AFC drawings for Diesel Engine Drain Tank (621-D-304A/B) | [9 empty] | 2016-04-21 | 2016-04-21 | 2016-04-21 | 2016-04-21 | 2016-04-21 | 2016-04-21 | 2016-04-21 | 2016-04-21 | 2016-04-21 | 2016-04-21 | 2016-04-21 | 2016-04-21 | 2016-04-21 | 2016-04-21 | 2016-04-21 | 2016-04-21 | 2016-04-21 | 2016-04-21 | 2016-04-21 | 2016-04-21 | 2016-04-21 | 2016-04-21 | 2016-04-21 | 2016-04-21 | 2016-04-21 | 2016-04-21 | 2016-04-21 | 2016-04-21 | 2016-04-21 | 2016-04-21 | 2016-04-21 | 2016-04-21 | 2016-04-21 | 2016-04-21 | 2016-04-21 | 2016-04-21 | 2016-04-21
2AE101CV00800-08115 | EOF: AFC drawings for LFHO Storage Tank (621-D-96) | [9 empty] | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25
2AE101CV00800-08110 | EOF: AFC drawings for LFHO Storage Tank (621-D-95) | [9 empty] | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25
2AE101CV00800-08105 | EOF: AFC drawings for LFHO Storage Tank (621-D-94) | [9 empty] | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25
2AE101CV00800-08100 | EOF: AFC drawings for LFHO Storage Tank (621-D-93) | [9 empty] | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25
2AE100TE00200-08110 | EOF: AFC drawings for Cable Trench & Tray Routing Layout | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AE100TE00200-08100 | Interconnection & Termination Drawing | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AE100PI01400-08110 | EOF : Isometrics Book for COCC | [27 empty] | 2017-11-23 | 2017-11-23 | 2017-11-23 | 2017-11-23 | 2017-11-23 | 2017-11-23 | 2017-11-23 | 2017-11-23 | 2017-11-23 | 2017-11-23 | 2017-11-23 | 2017-11-23 | 2017-11-23 | 2017-11-23 | 2017-11-23 | 2017-11-23 | 2017-11-23 | 2017-11-23 | 2017-11-23
2AE100PI01400-08100 | EOF : Isometrics Book for South Tank Farm | [27 empty] | 2017-11-23: 2018-10-11; 2017-11-23: 2018-10-11; 2017-11-23: 2018-10-11; 2017-11-23: 2018-10-11; 2017-11-23: 2018-10-11; 2017-11-23: 2018-10-11; 2017-11-23: 2018-10-11
2AE100PI01300-08110 | EOF : Piping GAD for COCC | [27 empty] | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18
2AE100PI01300-08100 | EOF : Piping GAD for South Tank Farm | [33 empty] | 2018-04-11 | 2018-04-11 | 2018-04-11 | 2018-04-11 | 2018-04-11 | 2018-04-11 | 2018-04-11 | 2018-04-11 | 2018-04-11 | 2018-04-11 | 2018-04-11 | 2018-04-11 | 2018-04-11
2AE100MC00100-08110 | EOF:AFC Drawings for CP Works at Tanks 621-D-93/94/95/96 | [15 empty] | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16
2AE100MC00100-08100 | EOF: AFC drawings for CP Works Out side Tank | [29 empty] | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26
2AE100IC02900-08900 | 52-R-303 - AFC Drawing for Cable Termination Schedule | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AE100IC02900-08800 | 52-R-302 - AFC Drawing for Cable Termination Schedule | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AE100IC02900-08700 | 52-R-002 - AFC Drawing for Cable Termination Schedule | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AE100IC02900-08600 | 52-R-301 - AFC Drawing for Cable Termination Schedule | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AE100IC02900-08500 | COCC: Substation 52-SUBT-001: AFC Drawing for Cable Termination Schedule | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AE100IC02900-08400 | EOF: Substation 52-SUBT-303: AFC Drawing for Cable Termination Schedule | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AE100IC02900-08200 | EOF: Substation 52-SUBT-301: AFC Drawing for Cable Termination Schedule | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AE100IC02900-08190 | EOF: Substation 52-SUBT-301: AFC Drawing for Cable Schedule & Cable Cutting Schedule | [29 empty] | 2017-12-19 | 2017-12-19 | 2017-12-19 | 2017-12-19 | 2017-12-19 | 2017-12-19 | 2017-12-19 | 2017-12-19 | 2017-12-19 | 2017-12-19 | 2017-12-19 | 2017-12-19 | 2017-12-19 | 2017-12-19 | 2017-12-19 | 2017-12-19 | 2017-12-19
2AE100IC02900-08120 | EOF: COCC CCR Building 621-R-001: AFC Drawing for Equipment layout | [27 empty] | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17
2AE100IC02900-08111 | EOF: COCC CCR Building 621-R-001: AFC Drawing for Cable Termination Schedule | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AE100IC02900-08110 | EOF: COCC CCR Building 621-R-001: AFC Drawing for Cable Schedule & Cable Cutting Schedule | [31 empty] | 2018-03-02 | 2018-03-02 | 2018-03-02 | 2018-03-02 | 2018-03-02 | 2018-03-02 | 2018-03-02 | 2018-03-02 | 2018-03-02 | 2018-03-02 | 2018-03-02 | 2018-03-02 | 2018-03-02 | 2018-03-02 | 2018-03-02
2AE100IC02900-08101 | MAIN FUSE PANEL, POWER PANEL, SUB FEEDER POWER PANEL, CATHODIC PROTECTION DB & MOV DB | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AE100IC02900-08100 | EOF: AFC drawings for Instrument Termination Drawing | [33 empty] | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18
2AE100IC02400-08100 | EOF: AFC drawings for Instrument Location Layout | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AE100IC02200-08100 | EOF: AFC drawings for Cable Trench & Tray Routing Layout | [23 empty] | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01
2AE100EL03600-08100 | EOF: AFC drawings for Electrical Cable Trench & Tray Routing Layout | [29 empty] | 2018-01-09 | 2018-01-09 | 2018-01-09 | 2018-01-09 | 2018-01-09 | 2018-01-09 | 2018-01-09 | 2018-01-09 | 2018-01-09 | 2018-01-09 | 2018-01-09 | 2018-01-09 | 2018-01-09 | 2018-01-09 | 2018-01-09 | 2018-01-09 | 2018-01-09
2AE100EL00400-08200 | 52-R-303 - AFC Drawing for Cable Schedule & Cable Cutting Schedule | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AE100EL00400-08100 | EOF: Substation 52-SUBT-303: AFC Drawing for Cable Schedule & Cable Cutting Schedule | [29 empty] | 2018-01-09 | 2018-01-09 | 2018-01-09 | 2018-01-09 | 2018-01-09 | 2018-01-09 | 2018-01-09 | 2018-01-09 | 2018-01-09 | 2018-01-09 | 2018-01-09 | 2018-01-09 | 2018-01-09 | 2018-01-09 | 2018-01-09 | 2018-01-09 | 2018-01-09
2AE100EL00300-08200 | 52-R-302 - AFC Drawing for Cable Schedule & Cable Cutting Schedule | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AE100EL00300-08110 | EOF: Substation 52-SUBT-302: AFC Drawing for Cable Termination Schedule | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AE100EL00300-08100 | EOF: Substation 52-SUBT-302: AFC Drawing for Cable Schedule & Cable Cutting Schedule | [29 empty] | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27
2AE100EL00200-08300 | 52-R-002 - AFC Drawing for Cable Schedule & Cable Cutting Schedule | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AE100EL00200-08210 | COCC: Substation 52-SUBT-001: AFC Drawing for Cable Schedule & Cable Cutting Schedule | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AE100EL00200-08200 | 52-R-301 - AFC Drawing for Cable Schedule & Cable Cutting Schedule | [31 empty] | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27 | 2018-02-27
2AE100EL00200-08100 | EOF: COCC CCR Building 621-R-001: AFC Drawing for Earthing & lightning Layout | [23 empty] | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31
2AE100CV02900-08105 | EOF: AFC drawings for Pipe Sleepers | [23 empty] | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24
2AE100CV02900-08100 | EOF: AFC drawings for Pipe Supports | [19 empty] | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21
2AE100CV02800-08100 | EOF: AFC drawings for Oily Water Collection Vessel Sump (621-SU-301) | [13 empty] | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25
2AE100CV02700-08220 | EOF: AFC drawings for Filling Manifold Auto Sampling Package (52-Z-305)& (52-Z-306) Shelter Erection | [17 empty] | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28
2AE100CV02700-08125 | EOF AFC drawings for Miscellanious/ Pump Shelter Foundation | [23 empty] | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24
2AE100CV02700-08120 | EOF: AFC drawings for Filling Manifold Auto Sampling Package (52-Z-305) & (52-Z-306) Shelter Foundation | [15 empty] | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01
2AE100CV02700-08115 | EOF: AFC drawings for Sunshade for Mobile Fire Monitors | [15 empty] | 2016-09-28 | 2016-09-28 | 2016-09-28 | 2016-09-28 | 2016-09-28 | 2016-09-28 | 2016-09-28 | 2016-09-28 | 2016-09-28 | 2016-09-28 | 2016-09-28 | 2016-09-28 | 2016-09-28 | 2016-09-28 | 2016-09-28 | 2016-09-28 | 2016-09-28 | 2016-09-28 | 2016-09-28 | 2016-09-28 | 2016-09-28 | 2016-09-28 | 2016-09-28 | 2016-09-28 | 2016-09-28 | 2016-09-28 | 2016-09-28 | 2016-09-28 | 2016-09-28 | 2016-09-28 | 2016-09-28
2AE100CV02700-08110 | EOF: AFC drawings for Shelter for Foam System Package (621-Z-301A/B) | [23 empty] | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24
2AE100CV02700-08105 | EOF: AFC drawings for Shelter for Trim Pump (621-G-301A/B) | [23 empty] | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27
2AE100CV02700-08100 | EOF: AFC drawings for Shelter for Oily Water transfer Pump (621-G-303A/B) | [13 empty] | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25
2AE100CV02600-08100 | EOF: AFC drawings for Ground Supported Platforms | [27 empty] | 2017-10-23 | 2017-10-23 | 2017-10-23 | 2017-10-23 | 2017-10-23 | 2017-10-23 | 2017-10-23 | 2017-10-23 | 2017-10-23 | 2017-10-23 | 2017-10-23 | 2017-10-23 | 2017-10-23 | 2017-10-23 | 2017-10-23 | 2017-10-23 | 2017-10-23 | 2017-10-23 | 2017-10-23
2AE100CV02500-08100 | EOF: AFC drawings for Storm Water Drain Road Crossings | [27 empty] | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18
2AE100CV02400-08110 | EOF: AFC Drawing for Pipe & Cable trench at new Tank Area | [33 empty] | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06
2AE100CV02400-08100 | EOF: AFC drawings for EIT Duct Banks | [19 empty] | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21
2AE100CV02300-08100 | EOF: AFC drawings for EIT Supports | [23 empty] | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09
2AE100CV01200-08100 | EOF: AFC drawings for Sanitary / Sewer Drains, Manholes & Misc Drain Pits | [23 empty] | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31
2AE100CV00300-08100 | EOF: AFC drawings for Road & Fencing Layout and Cross Section Details | [23 empty] | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01
2AE100CV00100-08105 | EOF: Site Preparation AFC drawings - COCC | [7 empty] | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16
2AE100CV00100-08100 | EOF: Site Preparation AFC drawings - STF | [7 empty] | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30

## Actual Start
 | time axis 2015-08-06 to 2019-04-26
TASK CODE | TASK NAME | WA-01A | WA-01B | WA-02A | WA-02B | WA-03A | WA-03B | WA-04A | WA-04B | WA-05A | WA-05B | WA-06A | WA-06B | WA-07A | WA-07B | WA-08A | WA-08B | WA-09A | WA-09B | WA-10A | WA-10B | WA-11A | WA-11B | WA-12A | WA-12B | WA-13A | WA-13B | WA-14A | WA-14B | WA-15A | WA-15B | WA-16A | WA-16B | WA-17A | WA-17B | WA-18A | WA-18B | WA-19A | WA-19B | WA-20A | WA-20B | WA-21A | WA-21B | WA-22A | WA-22B | WA-23A | WA-23B | CHECK 1 | CHECK 2 | CHECK 3
2AE100CV00100-08100 | EOF: Site Preparation AFC drawings - STF | [7 empty] | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24
2AE100CV00100-08105 | EOF: Site Preparation AFC drawings - COCC | [7 empty] | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16
2AE100CV00300-08100 | EOF: AFC drawings for Road & Fencing Layout and Cross Section Details | [11 empty] | 2016-06-02 | 2016-06-02 | 2016-06-02 | 2016-06-02 | 2016-06-02 | 2016-06-02 | 2016-06-02 | 2016-06-02 | 2016-06-02 | 2016-06-02 | 2016-06-02 | 2016-06-02 | 2016-06-02 | 2016-06-02 | 2016-06-02 | 2016-06-02 | 2016-06-02 | 2016-06-02 | 2016-06-02 | 2016-06-02 | 2016-06-02 | 2016-06-02 | 2016-06-02 | 2016-06-02 | 2016-06-02 | 2016-06-02 | 2016-06-02 | 2016-06-02 | 2016-06-02 | 2016-06-02 | 2016-06-02 | 2016-06-02 | 2016-06-02 | 2016-06-02 | 2016-06-02
2AE100CV01200-08100 | EOF: AFC drawings for Sanitary / Sewer Drains, Manholes & Misc Drain Pits | [11 empty] | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03
2AE100CV02300-08100 | EOF: AFC drawings for EIT Supports | [23 empty] | 2017-06-17 | 2017-06-17 | 2017-06-17 | 2017-06-17 | 2017-06-17 | 2017-06-17 | 2017-06-17 | 2017-06-17 | 2017-06-17 | 2017-06-17 | 2017-06-17 | 2017-06-17 | 2017-06-17 | 2017-06-17 | 2017-06-17 | 2017-06-17 | 2017-06-17 | 2017-06-17 | 2017-06-17 | 2017-06-17 | 2017-06-17 | 2017-06-17 | 2017-06-17
2AE100CV02400-08100 | EOF: AFC drawings for EIT Duct Banks | [9 empty] | 2016-05-10 | 2016-05-10 | 2016-05-10 | 2016-05-10 | 2016-05-10 | 2016-05-10 | 2016-05-10 | 2016-05-10 | 2016-05-10 | 2016-05-10 | 2016-05-10 | 2016-05-10 | 2016-05-10 | 2016-05-10 | 2016-05-10 | 2016-05-10 | 2016-05-10 | 2016-05-10 | 2016-05-10 | 2016-05-10 | 2016-05-10 | 2016-05-10 | 2016-05-10 | 2016-05-10 | 2016-05-10 | 2016-05-10 | 2016-05-10 | 2016-05-10 | 2016-05-10 | 2016-05-10 | 2016-05-10 | 2016-05-10 | 2016-05-10 | 2016-05-10 | 2016-05-10 | 2016-05-10 | 2016-05-10
2AE100CV02400-08110 | EOF: AFC Drawing for Pipe & Cable trench at new Tank Area | [9 empty] | 2016-05-10 | 2016-05-10 | 2016-05-10 | 2016-05-10 | 2016-05-10 | 2016-05-10 | 2016-05-10 | 2016-05-10 | 2016-05-10 | 2016-05-10 | 2016-05-10 | 2016-05-10 | 2016-05-10 | 2016-05-10 | 2016-05-10 | 2016-05-10 | 2016-05-10 | 2016-05-10 | 2016-05-10 | 2016-05-10 | 2016-05-10 | 2016-05-10 | 2016-05-10 | 2016-05-10 | 2016-05-10 | 2016-05-10 | 2016-05-10 | 2016-05-10 | 2016-05-10 | 2016-05-10 | 2016-05-10 | 2016-05-10 | 2016-05-10 | 2016-05-10 | 2016-05-10 | 2016-05-10 | 2016-05-10
2AE100CV02500-08100 | EOF: AFC drawings for Storm Water Drain Road Crossings | [15 empty] | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18
2AE100CV02600-08100 | EOF: AFC drawings for Ground Supported Platforms | [15 empty] | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18
2AE100CV02700-08100 | EOF: AFC drawings for Shelter for Oily Water transfer Pump (621-G-303A/B) | [13 empty] | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25
2AE100CV02700-08105 | EOF: AFC drawings for Shelter for Trim Pump (621-G-301A/B) | [19 empty] | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07
2AE100CV02700-08110 | EOF: AFC drawings for Shelter for Foam System Package (621-Z-301A/B) | [19 empty] | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21
2AE100CV02700-08115 | EOF: AFC drawings for Sunshade for Mobile Fire Monitors | [15 empty] | 2016-09-24 | 2016-09-24 | 2016-09-24 | 2016-09-24 | 2016-09-24 | 2016-09-24 | 2016-09-24 | 2016-09-24 | 2016-09-24 | 2016-09-24 | 2016-09-24 | 2016-09-24 | 2016-09-24 | 2016-09-24 | 2016-09-24 | 2016-09-24 | 2016-09-24 | 2016-09-24 | 2016-09-24 | 2016-09-24 | 2016-09-24 | 2016-09-24 | 2016-09-24 | 2016-09-24 | 2016-09-24 | 2016-09-24 | 2016-09-24 | 2016-09-24 | 2016-09-24 | 2016-09-24 | 2016-09-24
2AE100CV02700-08120 | EOF: AFC drawings for Filling Manifold Auto Sampling Package (52-Z-305) & (52-Z-306) Shelter Foundation | [15 empty] | 2016-09-26 | 2016-09-26 | 2016-09-26 | 2016-09-26 | 2016-09-26 | 2016-09-26 | 2016-09-26 | 2016-09-26 | 2016-09-26 | 2016-09-26 | 2016-09-26 | 2016-09-26 | 2016-09-26 | 2016-09-26 | 2016-09-26 | 2016-09-26 | 2016-09-26 | 2016-09-26 | 2016-09-26 | 2016-09-26 | 2016-09-26 | 2016-09-26 | 2016-09-26 | 2016-09-26 | 2016-09-26 | 2016-09-26 | 2016-09-26 | 2016-09-26 | 2016-09-26 | 2016-09-26 | 2016-09-26
2AE100CV02700-08125 | EOF AFC drawings for Miscellanious/ Pump Shelter Foundation | [19 empty] | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07
2AE100CV02700-08220 | EOF: AFC drawings for Filling Manifold Auto Sampling Package (52-Z-305)& (52-Z-306) Shelter Erection | [17 empty] | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24
2AE100CV02800-08100 | EOF: AFC drawings for Oily Water Collection Vessel Sump (621-SU-301) | [13 empty] | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25
2AE100CV02900-08100 | EOF: AFC drawings for Pipe Supports | [13 empty] | 2016-08-11 | 2016-08-11 | 2016-08-11 | 2016-08-11 | 2016-08-11 | 2016-08-11 | 2016-08-11 | 2016-08-11 | 2016-08-11 | 2016-08-11 | 2016-08-11 | 2016-08-11 | 2016-08-11 | 2016-08-11 | 2016-08-11 | 2016-08-11 | 2016-08-11 | 2016-08-11 | 2016-08-11 | 2016-08-11 | 2016-08-11 | 2016-08-11 | 2016-08-11 | 2016-08-11 | 2016-08-11 | 2016-08-11 | 2016-08-11 | 2016-08-11 | 2016-08-11 | 2016-08-11 | 2016-08-11 | 2016-08-11 | 2016-08-11
2AE100CV02900-08105 | EOF: AFC drawings for Pipe Sleepers | [17 empty] | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05
2AE100EL00200-08100 | EOF: COCC CCR Building 621-R-001: AFC Drawing for Earthing & lightning Layout | [23 empty] | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31
2AE100EL00200-08200 | 52-R-301 - AFC Drawing for Cable Schedule & Cable Cutting Schedule | [31 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
2AE100EL00200-08210 | COCC: Substation 52-SUBT-001: AFC Drawing for Cable Schedule & Cable Cutting Schedule | [31 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
2AE100EL00200-08300 | 52-R-002 - AFC Drawing for Cable Schedule & Cable Cutting Schedule | [31 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
2AE100EL00300-08100 | EOF: Substation 52-SUBT-302: AFC Drawing for Cable Schedule & Cable Cutting Schedule | [21 empty] | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04
2AE100EL00300-08110 | EOF: Substation 52-SUBT-302: AFC Drawing for Cable Termination Schedule | [31 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
2AE100EL00300-08200 | 52-R-302 - AFC Drawing for Cable Schedule & Cable Cutting Schedule | [31 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
2AE100EL00400-08100 | EOF: Substation 52-SUBT-303: AFC Drawing for Cable Schedule & Cable Cutting Schedule | [25 empty] | 2017-09-14 | 2017-09-14 | 2017-09-14 | 2017-09-14 | 2017-09-14 | 2017-09-14 | 2017-09-14 | 2017-09-14 | 2017-09-14 | 2017-09-14 | 2017-09-14 | 2017-09-14 | 2017-09-14 | 2017-09-14 | 2017-09-14 | 2017-09-14 | 2017-09-14 | 2017-09-14 | 2017-09-14 | 2017-09-14 | 2017-09-14
2AE100EL00400-08200 | 52-R-303 - AFC Drawing for Cable Schedule & Cable Cutting Schedule | [31 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
2AE100EL03600-08100 | EOF: AFC drawings for Electrical Cable Trench & Tray Routing Layout | [17 empty] | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17
2AE100IC02200-08100 | EOF: AFC drawings for Cable Trench & Tray Routing Layout | [23 empty] | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01
2AE100IC02400-08100 | EOF: AFC drawings for Instrument Location Layout | [23 empty] | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01
2AE100IC02900-08100 | EOF: AFC drawings for Instrument Termination Drawing | [29 empty] | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23
2AE100IC02900-08101 | MAIN FUSE PANEL, POWER PANEL, SUB FEEDER POWER PANEL, CATHODIC PROTECTION DB & MOV DB | [29 empty] | 2017-12-20 | 2017-12-20 | 2017-12-20 | 2017-12-20 | 2017-12-20 | 2017-12-20 | 2017-12-20 | 2017-12-20 | 2017-12-20 | 2017-12-20 | 2017-12-20 | 2017-12-20 | 2017-12-20 | 2017-12-20 | 2017-12-20 | 2017-12-20 | 2017-12-20
2AE100IC02900-08110 | EOF: COCC CCR Building 621-R-001: AFC Drawing for Cable Schedule & Cable Cutting Schedule | [31 empty] | 2018-03-02 | 2018-03-02 | 2018-03-02 | 2018-03-02 | 2018-03-02 | 2018-03-02 | 2018-03-02 | 2018-03-02 | 2018-03-02 | 2018-03-02 | 2018-03-02 | 2018-03-02 | 2018-03-02 | 2018-03-02 | 2018-03-02
2AE100IC02900-08111 | EOF: COCC CCR Building 621-R-001: AFC Drawing for Cable Termination Schedule | [31 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
2AE100IC02900-08120 | EOF: COCC CCR Building 621-R-001: AFC Drawing for Equipment layout | [25 empty] | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19
2AE100IC02900-08190 | EOF: Substation 52-SUBT-301: AFC Drawing for Cable Schedule & Cable Cutting Schedule | [29 empty] | 2017-12-19 | 2017-12-19 | 2017-12-19 | 2017-12-19 | 2017-12-19 | 2017-12-19 | 2017-12-19 | 2017-12-19 | 2017-12-19 | 2017-12-19 | 2017-12-19 | 2017-12-19 | 2017-12-19 | 2017-12-19 | 2017-12-19 | 2017-12-19 | 2017-12-19
2AE100IC02900-08200 | EOF: Substation 52-SUBT-301: AFC Drawing for Cable Termination Schedule | [31 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
2AE100IC02900-08400 | EOF: Substation 52-SUBT-303: AFC Drawing for Cable Termination Schedule | [31 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
2AE100IC02900-08500 | COCC: Substation 52-SUBT-001: AFC Drawing for Cable Termination Schedule | [31 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
2AE100IC02900-08600 | 52-R-301 - AFC Drawing for Cable Termination Schedule | [31 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
2AE100IC02900-08700 | 52-R-002 - AFC Drawing for Cable Termination Schedule | [31 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
2AE100IC02900-08800 | 52-R-302 - AFC Drawing for Cable Termination Schedule | [31 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
2AE100IC02900-08900 | 52-R-303 - AFC Drawing for Cable Termination Schedule | [31 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
2AE100MC00100-08100 | EOF: AFC drawings for CP Works Out side Tank | [29 empty] | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23
2AE100MC00100-08110 | EOF:AFC Drawings for CP Works at Tanks 621-D-93/94/95/96 | [13 empty] | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31
2AE100PI01300-08100 | EOF : Piping GAD for South Tank Farm | [19 empty] | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02
2AE100PI01300-08110 | EOF : Piping GAD for COCC | [27 empty] | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18
2AE100PI01400-08100 | EOF : Isometrics Book for South Tank Farm | [27 empty] | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20
2AE100PI01400-08110 | EOF : Isometrics Book for COCC | [23 empty] | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01
2AE100TE00200-08100 | Interconnection & Termination Drawing | [23 empty] | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31
2AE100TE00200-08110 | EOF: AFC drawings for Cable Trench & Tray Routing Layout | [23 empty] | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31
2AE101CV00800-08100 | EOF: AFC drawings for LFHO Storage Tank (621-D-93) | [7 empty] | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01
2AE101CV00800-08105 | EOF: AFC drawings for LFHO Storage Tank (621-D-94) | [7 empty] | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01
2AE101CV00800-08110 | EOF: AFC drawings for LFHO Storage Tank (621-D-95) | [7 empty] | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01
2AE101CV00800-08115 | EOF: AFC drawings for LFHO Storage Tank (621-D-96) | [7 empty] | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01 | 2016-02-01
2AE101CV01000-08100 | EOF: AFC drawings for Diesel Engine Drain Tank (621-D-304A/B) | [9 empty] | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17
2AE101CV01000-08105 | EOF: AFC drawings for Diesel Fuel Tank (621-D-307A-D) | [19 empty] | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21
2AE101CV01100-08100 | EOF: AFC drawings for Foam Drain Tank (621-D-305A/B) | [9 empty] | 2016-04-22 | 2016-04-22 | 2016-04-22 | 2016-04-22 | 2016-04-22 | 2016-04-22 | 2016-04-22 | 2016-04-22 | 2016-04-22 | 2016-04-22 | 2016-04-22 | 2016-04-22 | 2016-04-22 | 2016-04-22 | 2016-04-22 | 2016-04-22 | 2016-04-22 | 2016-04-22 | 2016-04-22 | 2016-04-22 | 2016-04-22 | 2016-04-22 | 2016-04-22 | 2016-04-22 | 2016-04-22 | 2016-04-22 | 2016-04-22 | 2016-04-22 | 2016-04-22 | 2016-04-22 | 2016-04-22 | 2016-04-22 | 2016-04-22 | 2016-04-22 | 2016-04-22 | 2016-04-22 | 2016-04-22
2AE101CV01100-08105 | EOF: AFC drawings for Flushing Water Drain Tank (621-D-306A/B) | [9 empty] | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27
2AE101CV01100-08110 | EOF: AFC drawings for Drain Tank (621-D-308A/B) | [25 empty] | 2017-08-07 | 2017-08-07 | 2017-08-07 | 2017-08-07 | 2017-08-07 | 2017-08-07 | 2017-08-07 | 2017-08-07 | 2017-08-07 | 2017-08-07 | 2017-08-07 | 2017-08-07 | 2017-08-07 | 2017-08-07 | 2017-08-07 | 2017-08-07 | 2017-08-07 | 2017-08-07 | 2017-08-07 | 2017-08-07 | 2017-08-07
2AE101CV01100-08115 | EOF: AFC drawings for Overhead Water Tank (621-D-309A/B) | [11 empty] | 2016-06-16 | 2016-06-16 | 2016-06-16 | 2016-06-16 | 2016-06-16 | 2016-06-16 | 2016-06-16 | 2016-06-16 | 2016-06-16 | 2016-06-16 | 2016-06-16 | 2016-06-16 | 2016-06-16 | 2016-06-16 | 2016-06-16 | 2016-06-16 | 2016-06-16 | 2016-06-16 | 2016-06-16 | 2016-06-16 | 2016-06-16 | 2016-06-16 | 2016-06-16 | 2016-06-16 | 2016-06-16 | 2016-06-16 | 2016-06-16 | 2016-06-16 | 2016-06-16 | 2016-06-16 | 2016-06-16 | 2016-06-16 | 2016-06-16 | 2016-06-16 | 2016-06-16
2AE101CV01100-08125 | EOF: AFC drawings for Oily Water Transfer Vessel 621-V-301( having Pump - 52-G-303 A/B ) | [13 empty] | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25
2AE101CV01200-08100 | EOF: AFC drawings for Trim Pump (621-G-301A/B) | [19 empty] | 2017-01-30 | 2017-01-30 | 2017-01-30 | 2017-01-30 | 2017-01-30 | 2017-01-30 | 2017-01-30 | 2017-01-30 | 2017-01-30 | 2017-01-30 | 2017-01-30 | 2017-01-30 | 2017-01-30 | 2017-01-30 | 2017-01-30 | 2017-01-30 | 2017-01-30 | 2017-01-30 | 2017-01-30 | 2017-01-30 | 2017-01-30 | 2017-01-30 | 2017-01-30 | 2017-01-30 | 2017-01-30 | 2017-01-30 | 2017-01-30
2AE101CV01300-08100 | EOF: AFC drawings for Bund Wall of LFHO Storage Tank | [15 empty] | 2016-11-01 | 2016-11-01 | 2016-11-01 | 2016-11-01 | 2016-11-01 | 2016-11-01 | 2016-11-01 | 2016-11-01 | 2016-11-01 | 2016-11-01 | 2016-11-01 | 2016-11-01 | 2016-11-01 | 2016-11-01 | 2016-11-01 | 2016-11-01 | 2016-11-01 | 2016-11-01 | 2016-11-01 | 2016-11-01 | 2016-11-01 | 2016-11-01 | 2016-11-01 | 2016-11-01 | 2016-11-01 | 2016-11-01 | 2016-11-01 | 2016-11-01 | 2016-11-01 | 2016-11-01 | 2016-11-01
2AE101CV01400-08100 | EOF: AFC drawings for Foam System Package (621-Z-301A/B) | [17 empty] | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17
2AE133CV04000-08100 | EOF: AFC drawings for Car Park Shelters & Other Misc. Shelters | [11 empty] | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17
2AE133CV04000-08105 | COCC: AFC drawings for Car Park Shelters & Other Misc. Shelters | [17 empty] | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17
2AE133CV04000-08110 | COCC: AFC drawings for Fire Water Pump Shelters | [11 empty] | 2016-07-12 | 2016-07-12 | 2016-07-12 | 2016-07-12 | 2016-07-12 | 2016-07-12 | 2016-07-12 | 2016-07-12 | 2016-07-12 | 2016-07-12 | 2016-07-12 | 2016-07-12 | 2016-07-12 | 2016-07-12 | 2016-07-12 | 2016-07-12 | 2016-07-12 | 2016-07-12 | 2016-07-12 | 2016-07-12 | 2016-07-12 | 2016-07-12 | 2016-07-12 | 2016-07-12 | 2016-07-12 | 2016-07-12 | 2016-07-12 | 2016-07-12 | 2016-07-12 | 2016-07-12 | 2016-07-12 | 2016-07-12 | 2016-07-12 | 2016-07-12 | 2016-07-12
2AE133CV04000-08120 | COCC: AFC drawings for Road and Paving | [19 empty] | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21
2AE133CV04400-08100 | EOF: AFC drawings for Shelter of Transformers for 52-SUBST-303, 52-SUBST-001, 52-SUBST-301 & 52-SUBST-302 | [19 empty] | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21
2AE133CV04500-08100 | EOF: AFC drawings for Shelters of Diesel Fuel Day Tanks of Substations | [11 empty] | 2016-07-16 | 2016-07-16 | 2016-07-16 | 2016-07-16 | 2016-07-16 | 2016-07-16 | 2016-07-16 | 2016-07-16 | 2016-07-16 | 2016-07-16 | 2016-07-16 | 2016-07-16 | 2016-07-16 | 2016-07-16 | 2016-07-16 | 2016-07-16 | 2016-07-16 | 2016-07-16 | 2016-07-16 | 2016-07-16 | 2016-07-16 | 2016-07-16 | 2016-07-16 | 2016-07-16 | 2016-07-16 | 2016-07-16 | 2016-07-16 | 2016-07-16 | 2016-07-16 | 2016-07-16 | 2016-07-16 | 2016-07-16 | 2016-07-16 | 2016-07-16 | 2016-07-16
2AE133CV05100-08100 | EOF: AFC drawings for Transformers for 52-SUBST-303, 52-SUBST-001, 52-SUBST-301 & 52-SUBST-302 | [15 empty] | 2016-11-12 | 2016-11-12 | 2016-11-12 | 2016-11-12 | 2016-11-12 | 2016-11-12 | 2016-11-12 | 2016-11-12 | 2016-11-12 | 2016-11-12 | 2016-11-12 | 2016-11-12 | 2016-11-12 | 2016-11-12 | 2016-11-12 | 2016-11-12 | 2016-11-12 | 2016-11-12 | 2016-11-12 | 2016-11-12 | 2016-11-12 | 2016-11-12 | 2016-11-12 | 2016-11-12 | 2016-11-12 | 2016-11-12 | 2016-11-12 | 2016-11-12 | 2016-11-12 | 2016-11-12 | 2016-11-12
2AE133CV05200-08100 | EOF: AFC drawings for Diesel Fuel Day Tanks of Substations | [11 empty] | 2016-05-29 | 2016-05-29 | 2016-05-29 | 2016-05-29 | 2016-05-29 | 2016-05-29 | 2016-05-29 | 2016-05-29 | 2016-05-29 | 2016-05-29 | 2016-05-29 | 2016-05-29 | 2016-05-29 | 2016-05-29 | 2016-05-29 | 2016-05-29 | 2016-05-29 | 2016-05-29 | 2016-05-29 | 2016-05-29 | 2016-05-29 | 2016-05-29 | 2016-05-29 | 2016-05-29 | 2016-05-29 | 2016-05-29 | 2016-05-29 | 2016-05-29 | 2016-05-29 | 2016-05-29 | 2016-05-29 | 2016-05-29 | 2016-05-29 | 2016-05-29 | 2016-05-29
2AE133EL00600-08100 | COCC: Substation 52-SUBT-001: AFC Drawing for Single Line Diagram | [29 empty] | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23
2AE133EL00600-08200 | 52-R-002 - AFC Drawing for Single Line Diagram | [25 empty] | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19
2AE133EL01000-08100 | EOF: Substation 52-SUBT-301: AFC Drawing for Single Line Diagram | [31 empty] | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05
2AE133EL01000-08200 | 52-R-301 - AFC Drawing for Single Line Diagram | [25 empty] | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19
2AE133EL01400-08100 | EOF: Substation 52-SUBT-302: AFC Drawing for Single Line Diagram | [31 empty] | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05
2AE133EL01400-08200 | 52-R-302 - AFC Drawing for Single Line Diagram | [25 empty] | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19
2AE133EL02100-08100 | EOF: Substation 52-SUBT-303: AFC Drawing for Single Line Diagram | [31 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
2AE133EL02100-08200 | 52-R-303 - AFC Drawing for Single Line Diagram | [25 empty] | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19
2AE133EL02200-08100 | COCC: Substation 52-SUBT-001: AFC Drawing for Equipment layout | [27 empty] | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17
2AE133EL02300-08100 | EOF: Substation 52-SUBT-301: AFC Drawing for Equipment layout | [27 empty] | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11
2AE133EL02400-08100 | EOF: Substation 52-SUBT-302: AFC Drawing for Equipment layout | [27 empty] | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11
2AE133EL02500-08100 | EOF: Substation 52-SUBT-303: AFC Drawing for Equipment layout | [27 empty] | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17
2AE133EL03500-08100 | COCC: Substation 52-SUBT-001: AFC Drawing for Earthing & lightning Layout | [23 empty] | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31
2AE133EL03600-08100 | EOF: Substation 52-SUBT-301: AFC Drawing for Earthing & lightning Layout | [25 empty] | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20
2AE133EL03600-08200 | 52-R-301 - AFC Drawing for Earthing & lightning Layout | [31 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
2AE133EL03700-08100 | EOF: Substation 52-SUBT-302: AFC Drawing for Earthing & lightning Layout | [25 empty] | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20
2AE133EL03800-08100 | EOF: Substation 52-SUBT-303: AFC Drawing for Earthing & lightning Layout | [27 empty] | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30
2AE133EL05800-08100 | 52-R-301 - AFC Drawing for Equipment layout | [23 empty] | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24
2AE133EL05800-08200 | 52-R-002 - AFC Drawing for Equipment layout | [27 empty] | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17
2AE133EL05800-08300 | 52-R-302 - AFC Drawing for Equipment layout | [23 empty] | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24
2AE133EL05800-08400 | 52-R-303 - AFC Drawing for Equipment layout | [31 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
2AE141EL00100-08100 | EOF: COCC CCR Building 621-R-001: AFC Drawing for Single Line Diagram | [25 empty] | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19
2AE142CV01000-08100 | EOF: AFC drawings for Demolition of Existing Road and Exisitng Fence Relocation | [7 empty] | 2016-03-17 | 2016-03-17 | 2016-03-17 | 2016-03-17 | 2016-03-17 | 2016-03-17 | 2016-03-17 | 2016-03-17 | 2016-03-17 | 2016-03-17 | 2016-03-17 | 2016-03-17 | 2016-03-17 | 2016-03-17 | 2016-03-17 | 2016-03-17 | 2016-03-17 | 2016-03-17 | 2016-03-17 | 2016-03-17 | 2016-03-17 | 2016-03-17 | 2016-03-17 | 2016-03-17 | 2016-03-17 | 2016-03-17 | 2016-03-17 | 2016-03-17 | 2016-03-17 | 2016-03-17 | 2016-03-17 | 2016-03-17 | 2016-03-17 | 2016-03-17 | 2016-03-17 | 2016-03-17 | 2016-03-17 | 2016-03-17 | 2016-03-17
2AE142CV01000-08105 | EOF: AFC drawings for Existing U/G Cable Re-Routing & Relocation of RMU | [9 empty] | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11
2AE142CV01100-08100 | COCC: AFC drawings for EIT Cable Trench Routing Layout | [19 empty] | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21
2AE142CV01100-08105 | COCC: AFC drawings for EIT Duct Banks | [19 empty] | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21
2AE800MC02100-08005 | Delivery of Cathodic Protection System - First Lot | [13 empty] | 2016-08-12 | 2016-08-12 | 2016-08-12 | 2016-08-12 | 2016-08-12 | 2016-08-12 | 2016-08-12 | 2016-08-12 | 2016-08-12 | 2016-08-12 | 2016-08-12 | 2016-08-12 | 2016-08-12 | 2016-08-12 | 2016-08-12 | 2016-08-12 | 2016-08-12 | 2016-08-12 | 2016-08-12 | 2016-08-12 | 2016-08-12 | 2016-08-12 | 2016-08-12 | 2016-08-12 | 2016-08-12 | 2016-08-12 | 2016-08-12 | 2016-08-12 | 2016-08-12 | 2016-08-12 | 2016-08-12 | 2016-08-12 | 2016-08-12
2AG000D101401-08000 | Insurance | time axis 2015-10-01 to 2015-10-01
2AG000D101401-08005 | Organization Chart | time axis 2015-10-15 to 2015-10-15
2AG000D101401-08010 | CV's of Key Personnel | time axis 2015-10-15 to 2015-10-15
2AG000D101401-08015 | Deliverable List | [5 empty] | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10
2AG000D101401-08020 | Bank Guaranty Submital | time axis 2015-09-26 to 2015-09-26
2AG000D101401-08025 | Site HSE Plan | time axis 2015-11-23 to 2015-11-23
2AG000D101401-08030 | Construction Execution Plan | time axis 2015-11-22 to 2015-11-22
2AG000D101401-08040 | Project Quality Plan | time axis 2015-11-11 to 2015-11-11
2AG000D101401-08045 | Report formats | time axis 2015-10-31 to 2015-10-31
2AG000M100100-08000 | Contract Commencement | time axis 2015-10-01 to 2015-10-01
2AG000M100100-08005 | Mechanical Completion Certificate (MCC) for Civil Works
2AG000M100100-08010 | Construction Completion / Subcontract Mechancial Completion for Civil Works
2AG000M100100-08015 | Mechanical Completion Certificate (MCC) for MEI Works
2AG000M100100-08020 | Construction Completion / Subcontract Mechancial Completion for MEI Works
2AG000M100100-08025 | LFHO Tank Foundation Completion 52-D-93 | [13 empty] | 2016-09-05 | 2016-09-05 | 2016-09-05 | 2016-09-05 | 2016-09-05 | 2016-09-05 | 2016-09-05 | 2016-09-05 | 2016-09-05 | 2016-09-05 | 2016-09-05 | 2016-09-05 | 2016-09-05 | 2016-09-05 | 2016-09-05 | 2016-09-05 | 2016-09-05 | 2016-09-05 | 2016-09-05 | 2016-09-05 | 2016-09-05 | 2016-09-05 | 2016-09-05 | 2016-09-05 | 2016-09-05 | 2016-09-05 | 2016-09-05 | 2016-09-05 | 2016-09-05 | 2016-09-05 | 2016-09-05 | 2016-09-05 | 2016-09-05
2AG000M100100-08030 | LFHO Tank Foundation Completion 52-D-94 | [13 empty] | 2016-08-22 | 2016-08-22 | 2016-08-22 | 2016-08-22 | 2016-08-22 | 2016-08-22 | 2016-08-22 | 2016-08-22 | 2016-08-22 | 2016-08-22 | 2016-08-22 | 2016-08-22 | 2016-08-22 | 2016-08-22 | 2016-08-22 | 2016-08-22 | 2016-08-22 | 2016-08-22 | 2016-08-22 | 2016-08-22 | 2016-08-22 | 2016-08-22 | 2016-08-22 | 2016-08-22 | 2016-08-22 | 2016-08-22 | 2016-08-22 | 2016-08-22 | 2016-08-22 | 2016-08-22 | 2016-08-22 | 2016-08-22 | 2016-08-22
2AG000M100100-08035 | LFHO Tank Foundation Completion 52-D-95 | [15 empty] | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09 | 2016-10-09
2AG000M100100-08040 | LFHO Tank Foundation Completion 52-D-96 | [15 empty] | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05
2AG000M100100-08045 | COCC Building : Clearance for EIT Works inside the Building | [31 empty] | 2018-03-06 | 2018-03-06 | 2018-03-06 | 2018-03-06 | 2018-03-06 | 2018-03-06 | 2018-03-06 | 2018-03-06 | 2018-03-06 | 2018-03-06 | 2018-03-06 | 2018-03-06 | 2018-03-06 | 2018-03-06 | 2018-03-06
2AG000M100100-08050 | EOF SS: 52-SUBST-301 - SUBSTATION - FMM Readyness for EIT Works inside the Building | [29 empty] | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01
2AG000M100100-08055 | EOF SS: 52-SUBST-302 - SUBSTATION - STF Readyness for EIT Works inside the Building | [29 empty] | 2018-01-08 | 2018-01-08 | 2018-01-08 | 2018-01-08 | 2018-01-08 | 2018-01-08 | 2018-01-08 | 2018-01-08 | 2018-01-08 | 2018-01-08 | 2018-01-08 | 2018-01-08 | 2018-01-08 | 2018-01-08 | 2018-01-08 | 2018-01-08 | 2018-01-08
2AG000M100100-08060 | EOF SS: 50-SUBST-001 - SUBSTATION - COCC Readyness for EIT Works inside the Building | [29 empty] | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20
2AG000M100100-08065 | EOF SS: 52-SUBST-303 - SUBSTATION - LMM Readyness for EIT Works inside the Building | [27 empty] | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15
2AG000M100100-08070 | 52-R-301 - EMERGENCY GENERATOR BUILDING (FMM) Readyness for EIT Works inside the Building | [35 empty] | 2018-06-25 | 2018-06-25 | 2018-06-25 | 2018-06-25 | 2018-06-25 | 2018-06-25 | 2018-06-25 | 2018-06-25 | 2018-06-25 | 2018-06-25 | 2018-06-25
2AG000M100100-08075 | 50-R-002 - EMERGENCY GENERATOR BUILDING (COCC) Readyness for EIT Works inside the Building | [35 empty] | 2018-07-23 | 2018-07-23 | 2018-07-23 | 2018-07-23 | 2018-07-23 | 2018-07-23 | 2018-07-23 | 2018-07-23 | 2018-07-23 | 2018-07-23 | 2018-07-23
2AG000M100100-08080 | 52-R-302 - EMERGENCY GENERATOR BUILDING (STF) Readyness for EIT Works inside the Building | [35 empty] | 2018-07-12 | 2018-07-12 | 2018-07-12 | 2018-07-12 | 2018-07-12 | 2018-07-12 | 2018-07-12 | 2018-07-12 | 2018-07-12 | 2018-07-12 | 2018-07-12
2AG000M100100-08085 | 52-R-303 - EMERGENCY GENERATOR BUILDING (LMM) Readyness for EIT Works inside the Building | [31 empty] | 2018-03-06 | 2018-03-06 | 2018-03-06 | 2018-03-06 | 2018-03-06 | 2018-03-06 | 2018-03-06 | 2018-03-06 | 2018-03-06 | 2018-03-06 | 2018-03-06 | 2018-03-06 | 2018-03-06 | 2018-03-06 | 2018-03-06
2AG000M505200-08000 | Subcontract Effective Date | time axis 2015-08-06 to 2015-08-06
2AG000M505200-08015 | Sub-contractor Approval By KOC | time axis 2015-10-20 to 2015-10-20
2AG000M505200-08020 | Kickoff Meeting | time axis 2015-10-20 to 2015-10-20
2AG000M505200-08025 | Area Clearance from client for TFC | time axis 2015-10-20 to 2015-10-20
2AG000M505200-08030 | Construction Completion of temp. facility | [5 empty] | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31
2AG000M505200-08035 | Issue First AFC Drawing by PIL | [7 empty] | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24
2AG000M505200-08045 | Issue First Equipment/Material by PIL | [7 empty] | 2016-03-12 | 2016-03-12 | 2016-03-12 | 2016-03-12 | 2016-03-12 | 2016-03-12 | 2016-03-12 | 2016-03-12 | 2016-03-12 | 2016-03-12 | 2016-03-12 | 2016-03-12 | 2016-03-12 | 2016-03-12 | 2016-03-12 | 2016-03-12 | 2016-03-12 | 2016-03-12 | 2016-03-12 | 2016-03-12 | 2016-03-12 | 2016-03-12 | 2016-03-12 | 2016-03-12 | 2016-03-12 | 2016-03-12 | 2016-03-12 | 2016-03-12 | 2016-03-12 | 2016-03-12 | 2016-03-12 | 2016-03-12 | 2016-03-12 | 2016-03-12 | 2016-03-12 | 2016-03-12 | 2016-03-12 | 2016-03-12 | 2016-03-12
2AI000GE00300 | EOF - Liquidation of construction punch points ('A' items) | [33 empty] | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15
2AI000GE00300-08005 | EOF - Liquidation of construction punch points ('A' items) | [33 empty] | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15
2AI000GE01300 | Portion2 : EOF Mechanical Completion Certificate - Submission to Company & Approval by Company | [33 empty] | 2018-05-15: 2018-10-13; 2018-05-15: 2018-10-13; 2018-05-15: 2018-10-13; 2018-05-15: 2018-10-13; 2018-05-15: 2018-10-13; 2018-05-15: 2018-10-13; 2018-05-15: 2018-10-13
2AI000GE01300-08000 | Portion2 : EOF Mechanical Completion Certificate - Submission to Company & Approval by Company | [33 empty] | 2018-05-15: 2018-10-13; 2018-05-15: 2018-10-13; 2018-05-15: 2018-10-13; 2018-05-15: 2018-10-13; 2018-05-15: 2018-10-13; 2018-05-15: 2018-10-13; 2018-05-15: 2018-10-13
2AI000ME00320-08045 | Survey & Setting Layout | time axis 2015-10-31 to 2015-10-31
2AI000ME00320-08050 | Excavation Notification | time axis 2015-11-03 to 2015-11-03
2AI000ME00320-08055 | Slit Trench Excavation Work | time axis 2015-11-04 to 2015-11-04
2AI000ME00320-08060 | Scrubbing & Grading | time axis 2015-11-24 to 2015-11-24
2AI000ME00320-08065 | Procurement of fencing material | time axis 2015-11-01 to 2015-11-01
2AI000ME00320-08070 | External Fencing & Gate Installation | time axis 2015-11-26 to 2015-11-26
2AI000ME00320-08075 | Internal Fencing & Gate Installation-Yard | [5 empty] | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09
2AI000ME00320-08080 | Project Sign Board Fixing | [5 empty] | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14 | 2015-12-14
2AI000ME00320-08085 | Manufacturing Site office Cabins | time axis 2015-10-26 to 2015-10-26
2AI000ME00320-08090 | Foundation Block Fixing - Site office | time axis 2015-11-30 to 2015-11-30
2AI000ME00320-08095 | Shipment & Delivery to site | [5 empty] | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06
2AI000ME00320-08100 | Installation & Assembling of Portable cabins | [5 empty] | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09
2AI000ME00320-08105 | Electrical & Plumbing Works | [5 empty] | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15
2AI000ME00320-08110 | Furnishing & Networking | [5 empty] | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23
2AI000ME00320-08115 | Parking Area | [5 empty] | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22 | 2015-12-22
2AI000ME00320-08120 | Fabrication of Store Portable Cabin | time axis 2015-11-24 to 2015-11-24
2AI000ME00320-08125 | Foundation Block Fixing for Portable cabins | [5 empty] | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06 | 2015-12-06
2AI000ME00320-08130 | Installation of Storage Containers | [5 empty] | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08
2AI000ME00320-08135 | Installation of Portable cabins for store | [5 empty] | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08
2AI000ME00320-08140 | Foundation Block Fixing for Portable cabins | [5 empty] | 2015-12-07 | 2015-12-07 | 2015-12-07 | 2015-12-07 | 2015-12-07 | 2015-12-07 | 2015-12-07 | 2015-12-07 | 2015-12-07 | 2015-12-07 | 2015-12-07 | 2015-12-07 | 2015-12-07 | 2015-12-07 | 2015-12-07 | 2015-12-07 | 2015-12-07 | 2015-12-07 | 2015-12-07 | 2015-12-07 | 2015-12-07 | 2015-12-07 | 2015-12-07 | 2015-12-07 | 2015-12-07 | 2015-12-07 | 2015-12-07 | 2015-12-07 | 2015-12-07 | 2015-12-07 | 2015-12-07 | 2015-12-07 | 2015-12-07 | 2015-12-07 | 2015-12-07 | 2015-12-07 | 2015-12-07 | 2015-12-07 | 2015-12-07 | 2015-12-07 | 2015-12-07
2AI000ME00320-08145 | Installation & Assembling of Mess Hall Portable cabins | [5 empty] | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08
2AI000ME00320-08150 | Inside Furnishing | [5 empty] | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13
2AI000ME00320-08155 | MEP Works Completion | [5 empty] | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15
2AI000ME00320-08160 | Foundation Block Fixing | [5 empty] | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08
2AI000ME00320-08165 | Installation & Assembling of Portable cabins | [5 empty] | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09
2AI000ME00320-08170 | MEP Works Completion | [5 empty] | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13
2AI000ME00320-08175 | Pit Excavation | time axis 2015-11-24 to 2015-11-24
2AI000ME00320-08180 | Foundation Works | time axis 2015-11-25 to 2015-11-25
2AI000ME00320-08185 | Completion of Plumbing Works | time axis 2015-11-28 to 2015-11-28
2AI000ME00320-08190 | Foundation | time axis 2015-11-28 to 2015-11-28
2AI000ME00320-08195 | Installation | time axis 2015-11-29 to 2015-11-29
2AI000ME00320-08200 | Completion of Plumbing Works | [5 empty] | 2015-12-03 | 2015-12-03 | 2015-12-03 | 2015-12-03 | 2015-12-03 | 2015-12-03 | 2015-12-03 | 2015-12-03 | 2015-12-03 | 2015-12-03 | 2015-12-03 | 2015-12-03 | 2015-12-03 | 2015-12-03 | 2015-12-03 | 2015-12-03 | 2015-12-03 | 2015-12-03 | 2015-12-03 | 2015-12-03 | 2015-12-03 | 2015-12-03 | 2015-12-03 | 2015-12-03 | 2015-12-03 | 2015-12-03 | 2015-12-03 | 2015-12-03 | 2015-12-03 | 2015-12-03 | 2015-12-03 | 2015-12-03 | 2015-12-03 | 2015-12-03 | 2015-12-03 | 2015-12-03 | 2015-12-03 | 2015-12-03 | 2015-12-03 | 2015-12-03 | 2015-12-03
2AI000ME00320-08205 | Installation of Generator | [5 empty] | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15
2AI000ME00320-08210 | Completion of Shelter | [5 empty] | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16 | 2015-12-16
2AI000ME00320-08215 | Electrical Works | [5 empty] | 2015-12-19 | 2015-12-19 | 2015-12-19 | 2015-12-19 | 2015-12-19 | 2015-12-19 | 2015-12-19 | 2015-12-19 | 2015-12-19 | 2015-12-19 | 2015-12-19 | 2015-12-19 | 2015-12-19 | 2015-12-19 | 2015-12-19 | 2015-12-19 | 2015-12-19 | 2015-12-19 | 2015-12-19 | 2015-12-19 | 2015-12-19 | 2015-12-19 | 2015-12-19 | 2015-12-19 | 2015-12-19 | 2015-12-19 | 2015-12-19 | 2015-12-19 | 2015-12-19 | 2015-12-19 | 2015-12-19 | 2015-12-19 | 2015-12-19 | 2015-12-19 | 2015-12-19 | 2015-12-19 | 2015-12-19 | 2015-12-19 | 2015-12-19 | 2015-12-19 | 2015-12-19
2AI000ME00320-08220 | Commissioning & Ready to Use | [5 empty] | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23
2AI000ME00320-08225 | Paving Works for Rebar/Precast Area | [5 empty] | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09 | 2015-12-09
2AI000ME00320-08230 | Vehicle/Equipment Maintenance Area | [5 empty] | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13 | 2015-12-13
2AI000ME00320-08235 | Fabrication & Installation - Garage Shed | [5 empty] | 2015-12-21 | 2015-12-21 | 2015-12-21 | 2015-12-21 | 2015-12-21 | 2015-12-21 | 2015-12-21 | 2015-12-21 | 2015-12-21 | 2015-12-21 | 2015-12-21 | 2015-12-21 | 2015-12-21 | 2015-12-21 | 2015-12-21 | 2015-12-21 | 2015-12-21 | 2015-12-21 | 2015-12-21 | 2015-12-21 | 2015-12-21 | 2015-12-21 | 2015-12-21 | 2015-12-21 | 2015-12-21 | 2015-12-21 | 2015-12-21 | 2015-12-21 | 2015-12-21 | 2015-12-21 | 2015-12-21 | 2015-12-21 | 2015-12-21 | 2015-12-21 | 2015-12-21 | 2015-12-21 | 2015-12-21 | 2015-12-21 | 2015-12-21 | 2015-12-21 | 2015-12-21
2AI000ME00320-08240 | Installation of Water Tank | [5 empty] | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29 | 2015-12-29
2AI000ME00320-08245 | Mechanical Fabrication Yard | [5 empty] | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17 | 2015-12-17
2AI000ME00320-08250 | Grading Work | [5 empty] | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23
2AI000ME00320-08255 | Milled asphalt Work | [5 empty] | 2015-12-26 | 2015-12-26 | 2015-12-26 | 2015-12-26 | 2015-12-26 | 2015-12-26 | 2015-12-26 | 2015-12-26 | 2015-12-26 | 2015-12-26 | 2015-12-26 | 2015-12-26 | 2015-12-26 | 2015-12-26 | 2015-12-26 | 2015-12-26 | 2015-12-26 | 2015-12-26 | 2015-12-26 | 2015-12-26 | 2015-12-26 | 2015-12-26 | 2015-12-26 | 2015-12-26 | 2015-12-26 | 2015-12-26 | 2015-12-26 | 2015-12-26 | 2015-12-26 | 2015-12-26 | 2015-12-26 | 2015-12-26 | 2015-12-26 | 2015-12-26 | 2015-12-26 | 2015-12-26 | 2015-12-26 | 2015-12-26 | 2015-12-26 | 2015-12-26 | 2015-12-26
2AI000PC00300 | Portion2 : EOF Construction Completion Certificate - Submission to Company & Approval by Company
2AI000PC00300-08000 | Portion2 : EOF Construction Completion Certificate - Submission to Company & Approval by Company
2AI101CV01000 | EOF: Site preparation (New storage Tank Area) | [5 empty] | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08
2AI101CV01000-08000 | EOF:Verification of Survey for existing grade Level | [5 empty] | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08
2AI101CV01000-08005 | EOF: Excavation Notification | [5 empty] | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08
2AI101CV01000-08010 | EOF:Site clearance & Stripping & disposal of Contaminated material(If any) | [5 empty] | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27 | 2015-12-27
2AI101CV01000-08015 | EOF:Grading, Cutting & Stockpiling | [9 empty] | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25
2AI101CV01000-08020 | EOF:Grading, Filling & Compaction | [9 empty] | 2016-04-20 | 2016-04-20 | 2016-04-20 | 2016-04-20 | 2016-04-20 | 2016-04-20 | 2016-04-20 | 2016-04-20 | 2016-04-20 | 2016-04-20 | 2016-04-20 | 2016-04-20 | 2016-04-20 | 2016-04-20 | 2016-04-20 | 2016-04-20 | 2016-04-20 | 2016-04-20 | 2016-04-20 | 2016-04-20 | 2016-04-20 | 2016-04-20 | 2016-04-20 | 2016-04-20 | 2016-04-20 | 2016-04-20 | 2016-04-20 | 2016-04-20 | 2016-04-20 | 2016-04-20 | 2016-04-20 | 2016-04-20 | 2016-04-20 | 2016-04-20 | 2016-04-20 | 2016-04-20 | 2016-04-20
2AI101CV01000-08025 | EOF:Disposal of Surplus Material | [9 empty] | 2016-04-01 | 2016-04-01 | 2016-04-01 | 2016-04-01 | 2016-04-01 | 2016-04-01 | 2016-04-01 | 2016-04-01 | 2016-04-01 | 2016-04-01 | 2016-04-01 | 2016-04-01 | 2016-04-01 | 2016-04-01 | 2016-04-01 | 2016-04-01 | 2016-04-01 | 2016-04-01 | 2016-04-01 | 2016-04-01 | 2016-04-01 | 2016-04-01 | 2016-04-01 | 2016-04-01 | 2016-04-01 | 2016-04-01 | 2016-04-01 | 2016-04-01 | 2016-04-01 | 2016-04-01 | 2016-04-01 | 2016-04-01 | 2016-04-01 | 2016-04-01 | 2016-04-01 | 2016-04-01 | 2016-04-01
2AI101CV01000-08100 | EOF: Site preparation (New storage Tank Area) including substation | [5 empty] | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08
2AI101CV01100 | EOF: Roads, Crossing & Paving Works | [13 empty] | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30
2AI101CV01100-08000 | EOF: Gutch Road Work
2AI101CV01100-08001 | EOF:Grading & leveling | [33 empty] | 2018-05-03 | 2018-05-03 | 2018-05-03 | 2018-05-03 | 2018-05-03 | 2018-05-03 | 2018-05-03 | 2018-05-03 | 2018-05-03 | 2018-05-03 | 2018-05-03 | 2018-05-03 | 2018-05-03
2AI101CV01100-08005 | EOF: Asphalt Road Work | [33 empty] | 2018-05-03 | 2018-05-03 | 2018-05-03 | 2018-05-03 | 2018-05-03 | 2018-05-03 | 2018-05-03 | 2018-05-03 | 2018-05-03 | 2018-05-03 | 2018-05-03 | 2018-05-03 | 2018-05-03
2AI101CV01100-08006 | EOF:Preparation of sub grade | [33 empty] | 2018-05-04 | 2018-05-04 | 2018-05-04 | 2018-05-04 | 2018-05-04 | 2018-05-04 | 2018-05-04 | 2018-05-04 | 2018-05-04 | 2018-05-04 | 2018-05-04 | 2018-05-04 | 2018-05-04
2AI101CV01100-08010 | EOF: Reinforced Concrete Paving | [33 empty] | 2018-05-04: 2019-03-30
2AI101CV01100-08011 | EOF:Asphalt Work | [33 empty] | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05
2AI101CV01100-08015 | EOF: Asphalt Paving
2AI101CV01100-08016 | EOF:Bollards & Crash barrier installation | [33 empty] | 2018-05-05: 2019-03-15; 2018-05-05: 2019-03-15; 2018-05-05: 2019-03-15
2AI101CV01100-08020 | EOF: Road Crossing and Concrete cable duct banks | [15 empty] | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01
2AI101CV01100-08021 | EOF:Excavation
2AI101CV01100-08025 | EOF: Grade slab for Pump shelters/Mobile shelters | [13 empty] | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30
2AI101CV01100-08026 | EOF:Grading & leveling
2AI101CV01100-08027 | EOF: Sub base & Base preparation | [13 empty] | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30
2AI101CV01100-08028 | EOF: Formwork | [13 empty] | 2016-09-20 | 2016-09-20 | 2016-09-20 | 2016-09-20 | 2016-09-20 | 2016-09-20 | 2016-09-20 | 2016-09-20 | 2016-09-20 | 2016-09-20 | 2016-09-20 | 2016-09-20 | 2016-09-20 | 2016-09-20 | 2016-09-20 | 2016-09-20 | 2016-09-20 | 2016-09-20 | 2016-09-20 | 2016-09-20 | 2016-09-20 | 2016-09-20 | 2016-09-20 | 2016-09-20 | 2016-09-20 | 2016-09-20 | 2016-09-20 | 2016-09-20 | 2016-09-20 | 2016-09-20 | 2016-09-20 | 2016-09-20 | 2016-09-20
2AI101CV01100-08029 | EOF: Reinforcement | [13 empty] | 2016-09-20 | 2016-09-20 | 2016-09-20 | 2016-09-20 | 2016-09-20 | 2016-09-20 | 2016-09-20 | 2016-09-20 | 2016-09-20 | 2016-09-20 | 2016-09-20 | 2016-09-20 | 2016-09-20 | 2016-09-20 | 2016-09-20 | 2016-09-20 | 2016-09-20 | 2016-09-20 | 2016-09-20 | 2016-09-20 | 2016-09-20 | 2016-09-20 | 2016-09-20 | 2016-09-20 | 2016-09-20 | 2016-09-20 | 2016-09-20 | 2016-09-20 | 2016-09-20 | 2016-09-20 | 2016-09-20 | 2016-09-20 | 2016-09-20
2AI101CV01100-08030 | EOF:Gutch Filling
2AI101CV01100-08032 | EOF: Concrete Pouring | [15 empty] | 2016-09-24 | 2016-09-24 | 2016-09-24 | 2016-09-24 | 2016-09-24 | 2016-09-24 | 2016-09-24 | 2016-09-24 | 2016-09-24 | 2016-09-24 | 2016-09-24 | 2016-09-24 | 2016-09-24 | 2016-09-24 | 2016-09-24 | 2016-09-24 | 2016-09-24 | 2016-09-24 | 2016-09-24 | 2016-09-24 | 2016-09-24 | 2016-09-24 | 2016-09-24 | 2016-09-24 | 2016-09-24 | 2016-09-24 | 2016-09-24 | 2016-09-24 | 2016-09-24 | 2016-09-24 | 2016-09-24
2AI101CV01100-08033 | EOF: Finishing | [15 empty] | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21
2AI101CV01100-08035 | EOF:Compaction
2AI101CV01100-08040 | EOF:Excavation | [15 empty] | 2016-10-21: 2019-03-30
2AI101CV01100-08045 | EOF:Grading & leveling | [15 empty] | 2016-10-21: 2019-03-31
2AI101CV01100-08050 | EOF:Preparation of sub grade | [15 empty] | 2016-10-21: 2019-04-02
2AI101CV01100-08055 | EOF:Concrete Work
2AI101CV01100-08060 | EOF:Excavation
2AI101CV01100-08065 | EOF:Grading & leveling
2AI101CV01100-08070 | EOF:Preparation of sub grade
2AI101CV01100-08075 | EOF:Asphalt Work
2AI101CV01100-08090 | EOF:Excavation & Subgrade for duct bank | [15 empty] | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01 | 2016-10-01
2AI101CV01100-08100 | EOF:Blinding/PCC for duct bank | [15 empty] | 2016-10-22 | 2016-10-22 | 2016-10-22 | 2016-10-22 | 2016-10-22 | 2016-10-22 | 2016-10-22 | 2016-10-22 | 2016-10-22 | 2016-10-22 | 2016-10-22 | 2016-10-22 | 2016-10-22 | 2016-10-22 | 2016-10-22 | 2016-10-22 | 2016-10-22 | 2016-10-22 | 2016-10-22 | 2016-10-22 | 2016-10-22 | 2016-10-22 | 2016-10-22 | 2016-10-22 | 2016-10-22 | 2016-10-22 | 2016-10-22 | 2016-10-22 | 2016-10-22 | 2016-10-22 | 2016-10-22
2AI101CV01100-08110 | EOF:Rebar, Formwork, embadents fixing and Concreting for duct bank | [15 empty] | 2016-10-26 | 2016-10-26 | 2016-10-26 | 2016-10-26 | 2016-10-26 | 2016-10-26 | 2016-10-26 | 2016-10-26 | 2016-10-26 | 2016-10-26 | 2016-10-26 | 2016-10-26 | 2016-10-26 | 2016-10-26 | 2016-10-26 | 2016-10-26 | 2016-10-26 | 2016-10-26 | 2016-10-26 | 2016-10-26 | 2016-10-26 | 2016-10-26 | 2016-10-26 | 2016-10-26 | 2016-10-26 | 2016-10-26 | 2016-10-26 | 2016-10-26 | 2016-10-26 | 2016-10-26 | 2016-10-26
2AI101CV01100-08120 | EOF:Concrete Protection duct bank | [15 empty] | 2016-11-06 | 2016-11-06 | 2016-11-06 | 2016-11-06 | 2016-11-06 | 2016-11-06 | 2016-11-06 | 2016-11-06 | 2016-11-06 | 2016-11-06 | 2016-11-06 | 2016-11-06 | 2016-11-06 | 2016-11-06 | 2016-11-06 | 2016-11-06 | 2016-11-06 | 2016-11-06 | 2016-11-06 | 2016-11-06 | 2016-11-06 | 2016-11-06 | 2016-11-06 | 2016-11-06 | 2016-11-06 | 2016-11-06 | 2016-11-06 | 2016-11-06 | 2016-11-06 | 2016-11-06 | 2016-11-06
2AI101CV01100-08130 | EOF:Backfilling duct bank | [15 empty] | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21
2AI101CV01100-08140 | EOF:Embankment for Road crossing | [15 empty] | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21
2AI101CV01200 | EOF: Foam Pump House Building structural works | [27 empty] | 2017-11-04 | 2017-11-04 | 2017-11-04 | 2017-11-04 | 2017-11-04 | 2017-11-04 | 2017-11-04 | 2017-11-04 | 2017-11-04 | 2017-11-04 | 2017-11-04 | 2017-11-04 | 2017-11-04 | 2017-11-04 | 2017-11-04 | 2017-11-04 | 2017-11-04 | 2017-11-04 | 2017-11-04
2AI101CV01200-08000 | EOF: 621-G-302 A/B Foam Pump House Building structural works | [27 empty] | 2017-11-04 | 2017-11-04 | 2017-11-04 | 2017-11-04 | 2017-11-04 | 2017-11-04 | 2017-11-04 | 2017-11-04 | 2017-11-04 | 2017-11-04 | 2017-11-04 | 2017-11-04 | 2017-11-04 | 2017-11-04 | 2017-11-04 | 2017-11-04 | 2017-11-04 | 2017-11-04 | 2017-11-04
2AI101CV01200-08001 | EOF:Installation of Str. Steel for 621-G-302 A/B Foam Pump House Building | [27 empty] | 2017-11-04 | 2017-11-04 | 2017-11-04 | 2017-11-04 | 2017-11-04 | 2017-11-04 | 2017-11-04 | 2017-11-04 | 2017-11-04 | 2017-11-04 | 2017-11-04 | 2017-11-04 | 2017-11-04 | 2017-11-04 | 2017-11-04 | 2017-11-04 | 2017-11-04 | 2017-11-04 | 2017-11-04
2AI101CV01200-08005 | EOF: 621-G-302 C/D Foam Pump House Building structural works | [27 empty] | 2017-11-05 | 2017-11-05 | 2017-11-05 | 2017-11-05 | 2017-11-05 | 2017-11-05 | 2017-11-05 | 2017-11-05 | 2017-11-05 | 2017-11-05 | 2017-11-05 | 2017-11-05 | 2017-11-05 | 2017-11-05 | 2017-11-05 | 2017-11-05 | 2017-11-05 | 2017-11-05 | 2017-11-05
2AI101CV01200-08006 | EOF:Alignment & Bolting/Torqueing for621-G-302 A/B Foam Pump House Building | [27 empty] | 2017-11-10 | 2017-11-10 | 2017-11-10 | 2017-11-10 | 2017-11-10 | 2017-11-10 | 2017-11-10 | 2017-11-10 | 2017-11-10 | 2017-11-10 | 2017-11-10 | 2017-11-10 | 2017-11-10 | 2017-11-10 | 2017-11-10 | 2017-11-10 | 2017-11-10 | 2017-11-10 | 2017-11-10
2AI101CV01200-08010 | EOF:Grouting of 621-G-302 A/B Foam Pump House Building | [37 empty] | 2018-08-06 | 2018-08-06 | 2018-08-06 | 2018-08-06 | 2018-08-06 | 2018-08-06 | 2018-08-06 | 2018-08-06 | 2018-08-06
2AI101CV01200-08015 | EOF:Installation of Str. Steel for 621-G-302 C/D Foam Pump House Building | [27 empty] | 2017-11-05 | 2017-11-05 | 2017-11-05 | 2017-11-05 | 2017-11-05 | 2017-11-05 | 2017-11-05 | 2017-11-05 | 2017-11-05 | 2017-11-05 | 2017-11-05 | 2017-11-05 | 2017-11-05 | 2017-11-05 | 2017-11-05 | 2017-11-05 | 2017-11-05 | 2017-11-05 | 2017-11-05
2AI101CV01200-08020 | EOF:Alignment & Bolting/Torqueing for 621-G-302 C/D Foam Pump House Building | [27 empty] | 2017-11-10 | 2017-11-10 | 2017-11-10 | 2017-11-10 | 2017-11-10 | 2017-11-10 | 2017-11-10 | 2017-11-10 | 2017-11-10 | 2017-11-10 | 2017-11-10 | 2017-11-10 | 2017-11-10 | 2017-11-10 | 2017-11-10 | 2017-11-10 | 2017-11-10 | 2017-11-10 | 2017-11-10
2AI101CV01200-08025 | EOF:Grouting of 621-G-302 C/D Foam Pump House Building | [27 empty] | 2017-11-10: 2018-10-04; 2017-11-10: 2018-10-04; 2017-11-10: 2018-10-04; 2017-11-10: 2018-10-04; 2017-11-10: 2018-10-04; 2017-11-10: 2018-10-04; 2017-11-10: 2018-10-04
2AI101CV01400 | EOF:Lot-1-J : LFHO Storage Tank (52-D-93 & 52-D-94) : Ring wall type Foundation | [9 empty] | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29
2AI101CV01400-08001 | EOF:Survey Marking, Excavation & Subgrade | [9 empty] | 2016-04-05 | 2016-04-05 | 2016-04-05 | 2016-04-05 | 2016-04-05 | 2016-04-05 | 2016-04-05 | 2016-04-05 | 2016-04-05 | 2016-04-05 | 2016-04-05 | 2016-04-05 | 2016-04-05 | 2016-04-05 | 2016-04-05 | 2016-04-05 | 2016-04-05 | 2016-04-05 | 2016-04-05 | 2016-04-05 | 2016-04-05 | 2016-04-05 | 2016-04-05 | 2016-04-05 | 2016-04-05 | 2016-04-05 | 2016-04-05 | 2016-04-05 | 2016-04-05 | 2016-04-05 | 2016-04-05 | 2016-04-05 | 2016-04-05 | 2016-04-05 | 2016-04-05 | 2016-04-05 | 2016-04-05
2AI101CV01400-08005 | EOF:LFHO Storage Tank 52-D-93 : Ring wall type Foundation | [9 empty] | 2016-04-05 | 2016-04-05 | 2016-04-05 | 2016-04-05 | 2016-04-05 | 2016-04-05 | 2016-04-05 | 2016-04-05 | 2016-04-05 | 2016-04-05 | 2016-04-05 | 2016-04-05 | 2016-04-05 | 2016-04-05 | 2016-04-05 | 2016-04-05 | 2016-04-05 | 2016-04-05 | 2016-04-05 | 2016-04-05 | 2016-04-05 | 2016-04-05 | 2016-04-05 | 2016-04-05 | 2016-04-05 | 2016-04-05 | 2016-04-05 | 2016-04-05 | 2016-04-05 | 2016-04-05 | 2016-04-05 | 2016-04-05 | 2016-04-05 | 2016-04-05 | 2016-04-05 | 2016-04-05 | 2016-04-05
2AI101CV01400-08006 | EOF:Blinding/PCC for Fnd of Infield Storage Tank 52-D-93 | [9 empty] | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19
2AI101CV01400-08009 | EOF:Rebar, Formwork & Construction joint of Storage Tank 52-D-93 | [9 empty] | 2016-04-24 | 2016-04-24 | 2016-04-24 | 2016-04-24 | 2016-04-24 | 2016-04-24 | 2016-04-24 | 2016-04-24 | 2016-04-24 | 2016-04-24 | 2016-04-24 | 2016-04-24 | 2016-04-24 | 2016-04-24 | 2016-04-24 | 2016-04-24 | 2016-04-24 | 2016-04-24 | 2016-04-24 | 2016-04-24 | 2016-04-24 | 2016-04-24 | 2016-04-24 | 2016-04-24 | 2016-04-24 | 2016-04-24 | 2016-04-24 | 2016-04-24 | 2016-04-24 | 2016-04-24 | 2016-04-24 | 2016-04-24 | 2016-04-24 | 2016-04-24 | 2016-04-24 | 2016-04-24 | 2016-04-24
2AI101CV01400-08010 | EOF:LFHO Storage Tank 52-D-94 : Ring wall type Foundation | [9 empty] | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29
2AI101CV01400-08011 | EOF:Concrete Pouring - for Footing | [9 empty] | 2016-05-08 | 2016-05-08 | 2016-05-08 | 2016-05-08 | 2016-05-08 | 2016-05-08 | 2016-05-08 | 2016-05-08 | 2016-05-08 | 2016-05-08 | 2016-05-08 | 2016-05-08 | 2016-05-08 | 2016-05-08 | 2016-05-08 | 2016-05-08 | 2016-05-08 | 2016-05-08 | 2016-05-08 | 2016-05-08 | 2016-05-08 | 2016-05-08 | 2016-05-08 | 2016-05-08 | 2016-05-08 | 2016-05-08 | 2016-05-08 | 2016-05-08 | 2016-05-08 | 2016-05-08 | 2016-05-08 | 2016-05-08 | 2016-05-08 | 2016-05-08 | 2016-05-08 | 2016-05-08 | 2016-05-08
2AI101CV01400-08012 | EOF:Rebar, Formwork & Install Embedments (Ring beam wall) | [9 empty] | 2016-05-18 | 2016-05-18 | 2016-05-18 | 2016-05-18 | 2016-05-18 | 2016-05-18 | 2016-05-18 | 2016-05-18 | 2016-05-18 | 2016-05-18 | 2016-05-18 | 2016-05-18 | 2016-05-18 | 2016-05-18 | 2016-05-18 | 2016-05-18 | 2016-05-18 | 2016-05-18 | 2016-05-18 | 2016-05-18 | 2016-05-18 | 2016-05-18 | 2016-05-18 | 2016-05-18 | 2016-05-18 | 2016-05-18 | 2016-05-18 | 2016-05-18 | 2016-05-18 | 2016-05-18 | 2016-05-18 | 2016-05-18 | 2016-05-18 | 2016-05-18 | 2016-05-18 | 2016-05-18 | 2016-05-18
2AI101CV01400-08013 | EOF:Concrete Pouring for Ring beam wall | [11 empty] | 2016-06-13 | 2016-06-13 | 2016-06-13 | 2016-06-13 | 2016-06-13 | 2016-06-13 | 2016-06-13 | 2016-06-13 | 2016-06-13 | 2016-06-13 | 2016-06-13 | 2016-06-13 | 2016-06-13 | 2016-06-13 | 2016-06-13 | 2016-06-13 | 2016-06-13 | 2016-06-13 | 2016-06-13 | 2016-06-13 | 2016-06-13 | 2016-06-13 | 2016-06-13 | 2016-06-13 | 2016-06-13 | 2016-06-13 | 2016-06-13 | 2016-06-13 | 2016-06-13 | 2016-06-13 | 2016-06-13 | 2016-06-13 | 2016-06-13 | 2016-06-13 | 2016-06-13
2AI101CV01400-08015 | EOF:Concrete protection for Ring wall fnd of Storage Tank 52-D-93 | [11 empty] | 2016-06-21 | 2016-06-21 | 2016-06-21 | 2016-06-21 | 2016-06-21 | 2016-06-21 | 2016-06-21 | 2016-06-21 | 2016-06-21 | 2016-06-21 | 2016-06-21 | 2016-06-21 | 2016-06-21 | 2016-06-21 | 2016-06-21 | 2016-06-21 | 2016-06-21 | 2016-06-21 | 2016-06-21 | 2016-06-21 | 2016-06-21 | 2016-06-21 | 2016-06-21 | 2016-06-21 | 2016-06-21 | 2016-06-21 | 2016-06-21 | 2016-06-21 | 2016-06-21 | 2016-06-21 | 2016-06-21 | 2016-06-21 | 2016-06-21 | 2016-06-21 | 2016-06-21
2AI101CV01400-08020 | EOF:Survey Marking, Excavation & Subgrade | [9 empty] | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29
2AI101CV01400-08025 | EOF:Blinding/PCC for Fnd of Infield Storage Tank 52-D-94 | [9 empty] | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14
2AI101CV01400-08030 | EOF:Rebar, Formwork & Construction joint of Storage Tank 52-D-94 | [9 empty] | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19
2AI101CV01400-08031 | EOF:Concrete Pouring - for Footing | [9 empty] | 2016-05-03 | 2016-05-03 | 2016-05-03 | 2016-05-03 | 2016-05-03 | 2016-05-03 | 2016-05-03 | 2016-05-03 | 2016-05-03 | 2016-05-03 | 2016-05-03 | 2016-05-03 | 2016-05-03 | 2016-05-03 | 2016-05-03 | 2016-05-03 | 2016-05-03 | 2016-05-03 | 2016-05-03 | 2016-05-03 | 2016-05-03 | 2016-05-03 | 2016-05-03 | 2016-05-03 | 2016-05-03 | 2016-05-03 | 2016-05-03 | 2016-05-03 | 2016-05-03 | 2016-05-03 | 2016-05-03 | 2016-05-03 | 2016-05-03 | 2016-05-03 | 2016-05-03 | 2016-05-03 | 2016-05-03
2AI101CV01400-08032 | EOF:Rebar, Formwork & Install Embedments (Ring beam wall) | [9 empty] | 2016-05-05 | 2016-05-05 | 2016-05-05 | 2016-05-05 | 2016-05-05 | 2016-05-05 | 2016-05-05 | 2016-05-05 | 2016-05-05 | 2016-05-05 | 2016-05-05 | 2016-05-05 | 2016-05-05 | 2016-05-05 | 2016-05-05 | 2016-05-05 | 2016-05-05 | 2016-05-05 | 2016-05-05 | 2016-05-05 | 2016-05-05 | 2016-05-05 | 2016-05-05 | 2016-05-05 | 2016-05-05 | 2016-05-05 | 2016-05-05 | 2016-05-05 | 2016-05-05 | 2016-05-05 | 2016-05-05 | 2016-05-05 | 2016-05-05 | 2016-05-05 | 2016-05-05 | 2016-05-05 | 2016-05-05
2AI101CV01400-08033 | EOF:Concrete Pouring for Ring beam wall | [9 empty] | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25
2AI101CV01400-08035 | EOF:Concrete protection for Ring wall fnd of Storage Tank 52-D-94 | [11 empty] | 2016-06-11 | 2016-06-11 | 2016-06-11 | 2016-06-11 | 2016-06-11 | 2016-06-11 | 2016-06-11 | 2016-06-11 | 2016-06-11 | 2016-06-11 | 2016-06-11 | 2016-06-11 | 2016-06-11 | 2016-06-11 | 2016-06-11 | 2016-06-11 | 2016-06-11 | 2016-06-11 | 2016-06-11 | 2016-06-11 | 2016-06-11 | 2016-06-11 | 2016-06-11 | 2016-06-11 | 2016-06-11 | 2016-06-11 | 2016-06-11 | 2016-06-11 | 2016-06-11 | 2016-06-11 | 2016-06-11 | 2016-06-11 | 2016-06-11 | 2016-06-11 | 2016-06-11
2AI101CV01500 | EOF:Lot-1-J : LFHO Storage Tank (52-D-93 & 52-D-94) : Backfilling | [11 empty] | 2016-06-06 | 2016-06-06 | 2016-06-06 | 2016-06-06 | 2016-06-06 | 2016-06-06 | 2016-06-06 | 2016-06-06 | 2016-06-06 | 2016-06-06 | 2016-06-06 | 2016-06-06 | 2016-06-06 | 2016-06-06 | 2016-06-06 | 2016-06-06 | 2016-06-06 | 2016-06-06 | 2016-06-06 | 2016-06-06 | 2016-06-06 | 2016-06-06 | 2016-06-06 | 2016-06-06 | 2016-06-06 | 2016-06-06 | 2016-06-06 | 2016-06-06 | 2016-06-06 | 2016-06-06 | 2016-06-06 | 2016-06-06 | 2016-06-06 | 2016-06-06 | 2016-06-06
2AI101CV01500-08000 | EOF:Gatch Filling & Compaction (Internal) for Tank Fnd | [11 empty] | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26
2AI101CV01500-08005 | LFHO Storage Tank (52-D-93) : Backfilling | [11 empty] | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26
2AI101CV01500-08010 | LFHO Storage Tank (52-D-94) : Backfilling | [11 empty] | 2016-06-06 | 2016-06-06 | 2016-06-06 | 2016-06-06 | 2016-06-06 | 2016-06-06 | 2016-06-06 | 2016-06-06 | 2016-06-06 | 2016-06-06 | 2016-06-06 | 2016-06-06 | 2016-06-06 | 2016-06-06 | 2016-06-06 | 2016-06-06 | 2016-06-06 | 2016-06-06 | 2016-06-06 | 2016-06-06 | 2016-06-06 | 2016-06-06 | 2016-06-06 | 2016-06-06 | 2016-06-06 | 2016-06-06 | 2016-06-06 | 2016-06-06 | 2016-06-06 | 2016-06-06 | 2016-06-06 | 2016-06-06 | 2016-06-06 | 2016-06-06 | 2016-06-06
2AI101CV01500-08011 | EOF:Geo Membrane laying (Internal) for 52-D-93 Fnd | [13 empty] | 2016-07-29 | 2016-07-29 | 2016-07-29 | 2016-07-29 | 2016-07-29 | 2016-07-29 | 2016-07-29 | 2016-07-29 | 2016-07-29 | 2016-07-29 | 2016-07-29 | 2016-07-29 | 2016-07-29 | 2016-07-29 | 2016-07-29 | 2016-07-29 | 2016-07-29 | 2016-07-29 | 2016-07-29 | 2016-07-29 | 2016-07-29 | 2016-07-29 | 2016-07-29 | 2016-07-29 | 2016-07-29 | 2016-07-29 | 2016-07-29 | 2016-07-29 | 2016-07-29 | 2016-07-29 | 2016-07-29 | 2016-07-29 | 2016-07-29
2AI101CV01500-08015 | EOF:Sand filling (Internal) for 52-D-93 Fnd | [13 empty] | 2016-08-05 | 2016-08-05 | 2016-08-05 | 2016-08-05 | 2016-08-05 | 2016-08-05 | 2016-08-05 | 2016-08-05 | 2016-08-05 | 2016-08-05 | 2016-08-05 | 2016-08-05 | 2016-08-05 | 2016-08-05 | 2016-08-05 | 2016-08-05 | 2016-08-05 | 2016-08-05 | 2016-08-05 | 2016-08-05 | 2016-08-05 | 2016-08-05 | 2016-08-05 | 2016-08-05 | 2016-08-05 | 2016-08-05 | 2016-08-05 | 2016-08-05 | 2016-08-05 | 2016-08-05 | 2016-08-05 | 2016-08-05 | 2016-08-05
2AI101CV01500-08020 | EOF:Install Embedments (Internal) for 52-D-93 Fnd | [13 empty] | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07
2AI101CV01500-08025 | EOF:Permeable Sand-gravel filling (Internal) for 52-D-93 Fnd | [13 empty] | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07 | 2016-08-07
2AI101CV01500-08030 | EOF:Clean Sand filling after CP installation (Internal) for 52-D-93 Fnd | [13 empty] | 2016-08-10 | 2016-08-10 | 2016-08-10 | 2016-08-10 | 2016-08-10 | 2016-08-10 | 2016-08-10 | 2016-08-10 | 2016-08-10 | 2016-08-10 | 2016-08-10 | 2016-08-10 | 2016-08-10 | 2016-08-10 | 2016-08-10 | 2016-08-10 | 2016-08-10 | 2016-08-10 | 2016-08-10 | 2016-08-10 | 2016-08-10 | 2016-08-10 | 2016-08-10 | 2016-08-10 | 2016-08-10 | 2016-08-10 | 2016-08-10 | 2016-08-10 | 2016-08-10 | 2016-08-10 | 2016-08-10 | 2016-08-10 | 2016-08-10
2AI101CV01500-08035 | Compacted Gatch fill & Blinding for HDPE drain canister (External) | [11 empty] | 2016-06-27 | 2016-06-27 | 2016-06-27 | 2016-06-27 | 2016-06-27 | 2016-06-27 | 2016-06-27 | 2016-06-27 | 2016-06-27 | 2016-06-27 | 2016-06-27 | 2016-06-27 | 2016-06-27 | 2016-06-27 | 2016-06-27 | 2016-06-27 | 2016-06-27 | 2016-06-27 | 2016-06-27 | 2016-06-27 | 2016-06-27 | 2016-06-27 | 2016-06-27 | 2016-06-27 | 2016-06-27 | 2016-06-27 | 2016-06-27 | 2016-06-27 | 2016-06-27 | 2016-06-27 | 2016-06-27 | 2016-06-27 | 2016-06-27 | 2016-06-27 | 2016-06-27
2AI101CV01500-08040 | Crushed Gravel w/ Gatch Mix Layer (External) | [37 empty] | 2018-09-09 | 2018-09-09 | 2018-09-09 | 2018-09-09 | 2018-09-09 | 2018-09-09 | 2018-09-09 | 2018-09-09 | 2018-09-09
2AI101CV01500-08042 | Rebar & Formwork for Access staircases & Service platforms (External) | [21 empty] | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03
2AI101CV01500-08045 | Concreting for Access staircases & Service platforms (External) | [21 empty] | 2017-04-20 | 2017-04-20 | 2017-04-20 | 2017-04-20 | 2017-04-20 | 2017-04-20 | 2017-04-20 | 2017-04-20 | 2017-04-20 | 2017-04-20 | 2017-04-20 | 2017-04-20 | 2017-04-20 | 2017-04-20 | 2017-04-20 | 2017-04-20 | 2017-04-20 | 2017-04-20 | 2017-04-20 | 2017-04-20 | 2017-04-20 | 2017-04-20 | 2017-04-20 | 2017-04-20 | 2017-04-20
2AI101CV01500-08050 | Asphaltic Concrete layer (External) | [21 empty] | 2017-04-20: 2019-03-05; 2017-04-20: 2019-03-05; 2017-04-20: 2019-03-05
2AI101CV01500-08055 | Install PVC leak detection pipes & HDPE drain canister (External) | [21 empty] | 2017-04-20: 2018-12-03; 2017-04-20: 2018-12-03; 2017-04-20: 2018-12-03; 2017-04-20: 2018-12-03; 2017-04-20: 2018-12-03
2AI101CV01500-08070 | EOF:Gatch Filling & Compaction (Internal) for Tank Fnd | [11 empty] | 2016-06-14 | 2016-06-14 | 2016-06-14 | 2016-06-14 | 2016-06-14 | 2016-06-14 | 2016-06-14 | 2016-06-14 | 2016-06-14 | 2016-06-14 | 2016-06-14 | 2016-06-14 | 2016-06-14 | 2016-06-14 | 2016-06-14 | 2016-06-14 | 2016-06-14 | 2016-06-14 | 2016-06-14 | 2016-06-14 | 2016-06-14 | 2016-06-14 | 2016-06-14 | 2016-06-14 | 2016-06-14 | 2016-06-14 | 2016-06-14 | 2016-06-14 | 2016-06-14 | 2016-06-14 | 2016-06-14 | 2016-06-14 | 2016-06-14 | 2016-06-14 | 2016-06-14
2AI101CV01500-08075 | EOF:Sand layer & Compaction (Internal) for 52-D-94 Fnd | [11 empty] | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30 | 2016-06-30
2AI101CV01500-08080 | EOF:Geo Membrane laying (Internal) for 52-D-94 Fnd | [11 empty] | 2016-07-19 | 2016-07-19 | 2016-07-19 | 2016-07-19 | 2016-07-19 | 2016-07-19 | 2016-07-19 | 2016-07-19 | 2016-07-19 | 2016-07-19 | 2016-07-19 | 2016-07-19 | 2016-07-19 | 2016-07-19 | 2016-07-19 | 2016-07-19 | 2016-07-19 | 2016-07-19 | 2016-07-19 | 2016-07-19 | 2016-07-19 | 2016-07-19 | 2016-07-19 | 2016-07-19 | 2016-07-19 | 2016-07-19 | 2016-07-19 | 2016-07-19 | 2016-07-19 | 2016-07-19 | 2016-07-19 | 2016-07-19 | 2016-07-19 | 2016-07-19 | 2016-07-19
2AI101CV01500-08085 | EOF:Sand filling (Internal) for 52-D-94 Fnd | [13 empty] | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25
2AI101CV01500-08090 | EOF:Install Embedments (Internal) for 52-D-94 Fnd | [13 empty] | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27
2AI101CV01500-08095 | EOF:Permeable Sand-gravel filling (Internal) for 52-D-94 Fnd | [13 empty] | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27
2AI101CV01500-08100 | EOF:Clean Sand filling after CP installation (Internal) for 52-D-94 Fnd | [13 empty] | 2016-08-03 | 2016-08-03 | 2016-08-03 | 2016-08-03 | 2016-08-03 | 2016-08-03 | 2016-08-03 | 2016-08-03 | 2016-08-03 | 2016-08-03 | 2016-08-03 | 2016-08-03 | 2016-08-03 | 2016-08-03 | 2016-08-03 | 2016-08-03 | 2016-08-03 | 2016-08-03 | 2016-08-03 | 2016-08-03 | 2016-08-03 | 2016-08-03 | 2016-08-03 | 2016-08-03 | 2016-08-03 | 2016-08-03 | 2016-08-03 | 2016-08-03 | 2016-08-03 | 2016-08-03 | 2016-08-03 | 2016-08-03 | 2016-08-03
2AI101CV01500-08105 | Compacted Gatch fill & Blinding for HDPE drain canister (External) | [11 empty] | 2016-06-06 | 2016-06-06 | 2016-06-06 | 2016-06-06 | 2016-06-06 | 2016-06-06 | 2016-06-06 | 2016-06-06 | 2016-06-06 | 2016-06-06 | 2016-06-06 | 2016-06-06 | 2016-06-06 | 2016-06-06 | 2016-06-06 | 2016-06-06 | 2016-06-06 | 2016-06-06 | 2016-06-06 | 2016-06-06 | 2016-06-06 | 2016-06-06 | 2016-06-06 | 2016-06-06 | 2016-06-06 | 2016-06-06 | 2016-06-06 | 2016-06-06 | 2016-06-06 | 2016-06-06 | 2016-06-06 | 2016-06-06 | 2016-06-06 | 2016-06-06 | 2016-06-06
2AI101CV01500-08110 | Crushed Gravel w/ Gatch Mix Layer (External) | [11 empty] | 2016-06-06: 2018-10-07; 2016-06-06: 2018-10-07; 2016-06-06: 2018-10-07; 2016-06-06: 2018-10-07; 2016-06-06: 2018-10-07; 2016-06-06: 2018-10-07; 2016-06-06: 2018-10-07
2AI101CV01500-08112 | Rebar & Formwork for Access staircases & Service platforms (External) | [21 empty] | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03
2AI101CV01500-08115 | Concreting for Access staircases & Service platforms (External) | [21 empty] | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09
2AI101CV01500-08120 | Asphaltic Concrete layer (External) | [21 empty] | 2017-04-09: 2019-03-08; 2017-04-09: 2019-03-08; 2017-04-09: 2019-03-08
2AI101CV01500-08125 | Install PVC leak detection pipes & HDPE drain canister (External) | [21 empty] | 2017-04-09: 2018-11-08; 2017-04-09: 2018-11-08; 2017-04-09: 2018-11-08; 2017-04-09: 2018-11-08; 2017-04-09: 2018-11-08; 2017-04-09: 2018-11-08; 2017-04-09: 2018-11-08
2AI101CV01600 | EOF:Lot-1-J : LFHO Storage Tank (52-D-93 & 52-D-94) : CP works | [13 empty] | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14
2AI101CV01600-08005 | LFHO Storage Tank (52-D-93) : CP works | [13 empty] | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24
2AI101CV01600-08010 | LFHO Storage Tank (52-D-94) : CP works | [13 empty] | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14 | 2016-08-14
2AI101CV01700 | EOF:Lot-1-J : LFHO Storage Tank (52-D-93 & 52-D-94) : Construct Bund Wall | [13 empty] | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08
2AI101CV01700-08005 | LFHO Storage Tank (52-D-93) & (52-D-94): Construct Bund Wall | [13 empty] | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08
2AI101CV01700-08010 | EOF:Survey Marking, Excavation & Disposal of unsutiable Material for Bund Wall around Storage tank (52-D-93 & 52-D-94) | [13 empty] | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08
2AI101CV01700-08015 | EOF: Prepare Subgrade lvl for Bund Wall around Storage tank (52-D-93 & 52-D-94) | [17 empty] | 2016-12-25 | 2016-12-25 | 2016-12-25 | 2016-12-25 | 2016-12-25 | 2016-12-25 | 2016-12-25 | 2016-12-25 | 2016-12-25 | 2016-12-25 | 2016-12-25 | 2016-12-25 | 2016-12-25 | 2016-12-25 | 2016-12-25 | 2016-12-25 | 2016-12-25 | 2016-12-25 | 2016-12-25 | 2016-12-25 | 2016-12-25 | 2016-12-25 | 2016-12-25 | 2016-12-25 | 2016-12-25 | 2016-12-25 | 2016-12-25 | 2016-12-25 | 2016-12-25
2AI101CV01700-08020 | EOF:Slope Preparation for Bund Wall around Storage tank (52-D-93 & 52-D-94) | [17 empty] | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29
2AI101CV01700-08025 | EOF:Install/Cast Catch basin (inside) & Valve pit (outside) for Bund Wall around Storage tank (52-D-93 & 52-D-94) | [15 empty] | 2016-10-29 | 2016-10-29 | 2016-10-29 | 2016-10-29 | 2016-10-29 | 2016-10-29 | 2016-10-29 | 2016-10-29 | 2016-10-29 | 2016-10-29 | 2016-10-29 | 2016-10-29 | 2016-10-29 | 2016-10-29 | 2016-10-29 | 2016-10-29 | 2016-10-29 | 2016-10-29 | 2016-10-29 | 2016-10-29 | 2016-10-29 | 2016-10-29 | 2016-10-29 | 2016-10-29 | 2016-10-29 | 2016-10-29 | 2016-10-29 | 2016-10-29 | 2016-10-29 | 2016-10-29 | 2016-10-29
2AI101CV01700-08030 | EOF:Lay Drain Pipe (CB to Valve pit) for Bund Wall around Storage tank (52-D-93 & 52-D-94) | [25 empty] | 2017-08-24 | 2017-08-24 | 2017-08-24 | 2017-08-24 | 2017-08-24 | 2017-08-24 | 2017-08-24 | 2017-08-24 | 2017-08-24 | 2017-08-24 | 2017-08-24 | 2017-08-24 | 2017-08-24 | 2017-08-24 | 2017-08-24 | 2017-08-24 | 2017-08-24 | 2017-08-24 | 2017-08-24 | 2017-08-24 | 2017-08-24
2AI101CV01700-08035 | EOF:Sand layer (Inside) upto Linear Menbrane Lvl for Bund Wall around Storage tank (52-D-93 & 52-D-94) | [21 empty] | 2017-05-18 | 2017-05-18 | 2017-05-18 | 2017-05-18 | 2017-05-18 | 2017-05-18 | 2017-05-18 | 2017-05-18 | 2017-05-18 | 2017-05-18 | 2017-05-18 | 2017-05-18 | 2017-05-18 | 2017-05-18 | 2017-05-18 | 2017-05-18 | 2017-05-18 | 2017-05-18 | 2017-05-18 | 2017-05-18 | 2017-05-18 | 2017-05-18 | 2017-05-18 | 2017-05-18 | 2017-05-18
2AI101CV01700-08040 | EOF:Install Linar Membrane (incl. base & inside slope) for Bund Wall around Storage tank (52-D-93 & 52-D-94) | [21 empty] | 2017-05-23 | 2017-05-23 | 2017-05-23 | 2017-05-23 | 2017-05-23 | 2017-05-23 | 2017-05-23 | 2017-05-23 | 2017-05-23 | 2017-05-23 | 2017-05-23 | 2017-05-23 | 2017-05-23 | 2017-05-23 | 2017-05-23 | 2017-05-23 | 2017-05-23 | 2017-05-23 | 2017-05-23 | 2017-05-23 | 2017-05-23 | 2017-05-23 | 2017-05-23 | 2017-05-23 | 2017-05-23
2AI101CV01700-08045 | EOF:Gatch Filling & Compaction for Bund Wall around Storage tank (52-D-93 & 52-D-94) | [23 empty] | 2017-06-15 | 2017-06-15 | 2017-06-15 | 2017-06-15 | 2017-06-15 | 2017-06-15 | 2017-06-15 | 2017-06-15 | 2017-06-15 | 2017-06-15 | 2017-06-15 | 2017-06-15 | 2017-06-15 | 2017-06-15 | 2017-06-15 | 2017-06-15 | 2017-06-15 | 2017-06-15 | 2017-06-15 | 2017-06-15 | 2017-06-15 | 2017-06-15 | 2017-06-15
2AI101CV01700-08050 | EOF:Prepare Access ramp (with Compact fill & Gatch layer) for Bund Wall around Storage tank(52-D-93 & 52-D-94) | [37 empty] | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22
2AI101CV01700-08055 | EOF:Rebar, Form work & Concreting for Stair cases for Bund Wall around Storage tank (52-D-93 & 52-D-94) | [21 empty] | 2017-05-19 | 2017-05-19 | 2017-05-19 | 2017-05-19 | 2017-05-19 | 2017-05-19 | 2017-05-19 | 2017-05-19 | 2017-05-19 | 2017-05-19 | 2017-05-19 | 2017-05-19 | 2017-05-19 | 2017-05-19 | 2017-05-19 | 2017-05-19 | 2017-05-19 | 2017-05-19 | 2017-05-19 | 2017-05-19 | 2017-05-19 | 2017-05-19 | 2017-05-19 | 2017-05-19 | 2017-05-19
2AI101CV01700-08060 | EOF:Asphalt Lining for Inside slope for Bund Wall (52-D-93 & 52-D-94) | [33 empty] | 2018-03-26 | 2018-03-26 | 2018-03-26 | 2018-03-26 | 2018-03-26 | 2018-03-26 | 2018-03-26 | 2018-03-26 | 2018-03-26 | 2018-03-26 | 2018-03-26 | 2018-03-26 | 2018-03-26
2AI101CV01800 | EOF:Lot-1-J : LFHO Storage Tank (52-D-95 & 52-D-96) : Ring wall type Foundation | [9 empty] | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06
2AI101CV01800-08000 | EOF:Survey Marking, Excavation & Subgrade | [9 empty] | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06
2AI101CV01800-08005 | LFHO Storage Tank (52-D-95) : Ring wall type Foundation | [9 empty] | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06 | 2016-05-06
2AI101CV01800-08006 | EOF:Blinding/PCC for Fnd of Infield Pop Tank 52-D-95 | [9 empty] | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20 | 2016-05-20
2AI101CV01800-08010 | LFHO Storage Tank (52-D-96) : Ring wall type Foundation | [9 empty] | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17
2AI101CV01800-08011 | EOF:Rebar, Formwork & Construction joint of Storage Tank 52-D-95 | [9 empty] | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25 | 2016-05-25
2AI101CV01800-08012 | EOF:Concrete Pouring - for Footing | [11 empty] | 2016-06-08 | 2016-06-08 | 2016-06-08 | 2016-06-08 | 2016-06-08 | 2016-06-08 | 2016-06-08 | 2016-06-08 | 2016-06-08 | 2016-06-08 | 2016-06-08 | 2016-06-08 | 2016-06-08 | 2016-06-08 | 2016-06-08 | 2016-06-08 | 2016-06-08 | 2016-06-08 | 2016-06-08 | 2016-06-08 | 2016-06-08 | 2016-06-08 | 2016-06-08 | 2016-06-08 | 2016-06-08 | 2016-06-08 | 2016-06-08 | 2016-06-08 | 2016-06-08 | 2016-06-08 | 2016-06-08 | 2016-06-08 | 2016-06-08 | 2016-06-08 | 2016-06-08
2AI101CV01800-08013 | EOF:Rebar, Formwork & Install Embedments (Ring beam wall) | [11 empty] | 2016-06-07 | 2016-06-07 | 2016-06-07 | 2016-06-07 | 2016-06-07 | 2016-06-07 | 2016-06-07 | 2016-06-07 | 2016-06-07 | 2016-06-07 | 2016-06-07 | 2016-06-07 | 2016-06-07 | 2016-06-07 | 2016-06-07 | 2016-06-07 | 2016-06-07 | 2016-06-07 | 2016-06-07 | 2016-06-07 | 2016-06-07 | 2016-06-07 | 2016-06-07 | 2016-06-07 | 2016-06-07 | 2016-06-07 | 2016-06-07 | 2016-06-07 | 2016-06-07 | 2016-06-07 | 2016-06-07 | 2016-06-07 | 2016-06-07 | 2016-06-07 | 2016-06-07
2AI101CV01800-08014 | EOF:Concrete Pouring for Ring beam wall | [11 empty] | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04
2AI101CV01800-08015 | EOF:Concrete protection for Ring wall fnd of Storage Tank 52-D-95 | [11 empty] | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17
2AI101CV01800-08020 | EOF:Survey Marking, Excavation & Subgrade | [9 empty] | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17
2AI101CV01800-08025 | EOF:Blinding/PCC for Fnd of Infield Pop Tank 52-D-96 | [11 empty] | 2016-06-13 | 2016-06-13 | 2016-06-13 | 2016-06-13 | 2016-06-13 | 2016-06-13 | 2016-06-13 | 2016-06-13 | 2016-06-13 | 2016-06-13 | 2016-06-13 | 2016-06-13 | 2016-06-13 | 2016-06-13 | 2016-06-13 | 2016-06-13 | 2016-06-13 | 2016-06-13 | 2016-06-13 | 2016-06-13 | 2016-06-13 | 2016-06-13 | 2016-06-13 | 2016-06-13 | 2016-06-13 | 2016-06-13 | 2016-06-13 | 2016-06-13 | 2016-06-13 | 2016-06-13 | 2016-06-13 | 2016-06-13 | 2016-06-13 | 2016-06-13 | 2016-06-13
2AI101CV01800-08030 | EOF:Rebar, Formwork & Construction joint of Storage Tank 52-D-96 | [11 empty] | 2016-06-27 | 2016-06-27 | 2016-06-27 | 2016-06-27 | 2016-06-27 | 2016-06-27 | 2016-06-27 | 2016-06-27 | 2016-06-27 | 2016-06-27 | 2016-06-27 | 2016-06-27 | 2016-06-27 | 2016-06-27 | 2016-06-27 | 2016-06-27 | 2016-06-27 | 2016-06-27 | 2016-06-27 | 2016-06-27 | 2016-06-27 | 2016-06-27 | 2016-06-27 | 2016-06-27 | 2016-06-27 | 2016-06-27 | 2016-06-27 | 2016-06-27 | 2016-06-27 | 2016-06-27 | 2016-06-27 | 2016-06-27 | 2016-06-27 | 2016-06-27 | 2016-06-27
2AI101CV01800-08031 | EOF:Concrete Pouring - for Footing | [11 empty] | 2016-07-14 | 2016-07-14 | 2016-07-14 | 2016-07-14 | 2016-07-14 | 2016-07-14 | 2016-07-14 | 2016-07-14 | 2016-07-14 | 2016-07-14 | 2016-07-14 | 2016-07-14 | 2016-07-14 | 2016-07-14 | 2016-07-14 | 2016-07-14 | 2016-07-14 | 2016-07-14 | 2016-07-14 | 2016-07-14 | 2016-07-14 | 2016-07-14 | 2016-07-14 | 2016-07-14 | 2016-07-14 | 2016-07-14 | 2016-07-14 | 2016-07-14 | 2016-07-14 | 2016-07-14 | 2016-07-14 | 2016-07-14 | 2016-07-14 | 2016-07-14 | 2016-07-14
2AI101CV01800-08032 | EOF:Rebar, Formwork & Install Embedments (Ring beam wall) | [11 empty] | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17 | 2016-07-17
2AI101CV01800-08033 | EOF:Concrete Pouring for Ring beam wall | [13 empty] | 2016-08-08 | 2016-08-08 | 2016-08-08 | 2016-08-08 | 2016-08-08 | 2016-08-08 | 2016-08-08 | 2016-08-08 | 2016-08-08 | 2016-08-08 | 2016-08-08 | 2016-08-08 | 2016-08-08 | 2016-08-08 | 2016-08-08 | 2016-08-08 | 2016-08-08 | 2016-08-08 | 2016-08-08 | 2016-08-08 | 2016-08-08 | 2016-08-08 | 2016-08-08 | 2016-08-08 | 2016-08-08 | 2016-08-08 | 2016-08-08 | 2016-08-08 | 2016-08-08 | 2016-08-08 | 2016-08-08 | 2016-08-08 | 2016-08-08
2AI101CV01800-08035 | EOF:Concrete protection for Ring wall fnd of Storage Tank 52-D-96 | [13 empty] | 2016-08-28 | 2016-08-28 | 2016-08-28 | 2016-08-28 | 2016-08-28 | 2016-08-28 | 2016-08-28 | 2016-08-28 | 2016-08-28 | 2016-08-28 | 2016-08-28 | 2016-08-28 | 2016-08-28 | 2016-08-28 | 2016-08-28 | 2016-08-28 | 2016-08-28 | 2016-08-28 | 2016-08-28 | 2016-08-28 | 2016-08-28 | 2016-08-28 | 2016-08-28 | 2016-08-28 | 2016-08-28 | 2016-08-28 | 2016-08-28 | 2016-08-28 | 2016-08-28 | 2016-08-28 | 2016-08-28 | 2016-08-28 | 2016-08-28
2AI101CV01900 | EOF:Lot-1-J : LFHO Storage Tank (52-D-95 & 52-D-96) : Backfilling | [11 empty] | 2016-07-22 | 2016-07-22 | 2016-07-22 | 2016-07-22 | 2016-07-22 | 2016-07-22 | 2016-07-22 | 2016-07-22 | 2016-07-22 | 2016-07-22 | 2016-07-22 | 2016-07-22 | 2016-07-22 | 2016-07-22 | 2016-07-22 | 2016-07-22 | 2016-07-22 | 2016-07-22 | 2016-07-22 | 2016-07-22 | 2016-07-22 | 2016-07-22 | 2016-07-22 | 2016-07-22 | 2016-07-22 | 2016-07-22 | 2016-07-22 | 2016-07-22 | 2016-07-22 | 2016-07-22 | 2016-07-22 | 2016-07-22 | 2016-07-22 | 2016-07-22 | 2016-07-22
2AI101CV01900-08000 | EOF:Gatch Filling & Compaction (Internal) for Tank Fnd | [11 empty] | 2016-07-22 | 2016-07-22 | 2016-07-22 | 2016-07-22 | 2016-07-22 | 2016-07-22 | 2016-07-22 | 2016-07-22 | 2016-07-22 | 2016-07-22 | 2016-07-22 | 2016-07-22 | 2016-07-22 | 2016-07-22 | 2016-07-22 | 2016-07-22 | 2016-07-22 | 2016-07-22 | 2016-07-22 | 2016-07-22 | 2016-07-22 | 2016-07-22 | 2016-07-22 | 2016-07-22 | 2016-07-22 | 2016-07-22 | 2016-07-22 | 2016-07-22 | 2016-07-22 | 2016-07-22 | 2016-07-22 | 2016-07-22 | 2016-07-22 | 2016-07-22 | 2016-07-22
2AI101CV01900-08005 | LFHO Storage Tank (52-D-95) : Backfilling | [11 empty] | 2016-07-22 | 2016-07-22 | 2016-07-22 | 2016-07-22 | 2016-07-22 | 2016-07-22 | 2016-07-22 | 2016-07-22 | 2016-07-22 | 2016-07-22 | 2016-07-22 | 2016-07-22 | 2016-07-22 | 2016-07-22 | 2016-07-22 | 2016-07-22 | 2016-07-22 | 2016-07-22 | 2016-07-22 | 2016-07-22 | 2016-07-22 | 2016-07-22 | 2016-07-22 | 2016-07-22 | 2016-07-22 | 2016-07-22 | 2016-07-22 | 2016-07-22 | 2016-07-22 | 2016-07-22 | 2016-07-22 | 2016-07-22 | 2016-07-22 | 2016-07-22 | 2016-07-22
2AI101CV01900-08006 | EOF:Sand layer & Compaction (Internal) for 52-D-95 Fnd | [13 empty] | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27
2AI101CV01900-08010 | LFHO Storage Tank (52-D-96) : Backfilling | [13 empty] | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08
2AI101CV01900-08011 | EOF:Geo Membrane laying (Internal) for 52-D-95 Fnd | [13 empty] | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08
2AI101CV01900-08015 | EOF:Sand filling (Internal) for 52-D-95 Fnd | [13 empty] | 2016-09-19 | 2016-09-19 | 2016-09-19 | 2016-09-19 | 2016-09-19 | 2016-09-19 | 2016-09-19 | 2016-09-19 | 2016-09-19 | 2016-09-19 | 2016-09-19 | 2016-09-19 | 2016-09-19 | 2016-09-19 | 2016-09-19 | 2016-09-19 | 2016-09-19 | 2016-09-19 | 2016-09-19 | 2016-09-19 | 2016-09-19 | 2016-09-19 | 2016-09-19 | 2016-09-19 | 2016-09-19 | 2016-09-19 | 2016-09-19 | 2016-09-19 | 2016-09-19 | 2016-09-19 | 2016-09-19 | 2016-09-19 | 2016-09-19
2AI101CV01900-08020 | EOF:Install Embedments (Internal) for 52-D-95 Fnd | [15 empty] | 2016-09-29 | 2016-09-29 | 2016-09-29 | 2016-09-29 | 2016-09-29 | 2016-09-29 | 2016-09-29 | 2016-09-29 | 2016-09-29 | 2016-09-29 | 2016-09-29 | 2016-09-29 | 2016-09-29 | 2016-09-29 | 2016-09-29 | 2016-09-29 | 2016-09-29 | 2016-09-29 | 2016-09-29 | 2016-09-29 | 2016-09-29 | 2016-09-29 | 2016-09-29 | 2016-09-29 | 2016-09-29 | 2016-09-29 | 2016-09-29 | 2016-09-29 | 2016-09-29 | 2016-09-29 | 2016-09-29
2AI101CV01900-08025 | EOF:Permeable Sand-gravel filling (Internal) for 52-D-95 Fnd | [13 empty] | 2016-09-22 | 2016-09-22 | 2016-09-22 | 2016-09-22 | 2016-09-22 | 2016-09-22 | 2016-09-22 | 2016-09-22 | 2016-09-22 | 2016-09-22 | 2016-09-22 | 2016-09-22 | 2016-09-22 | 2016-09-22 | 2016-09-22 | 2016-09-22 | 2016-09-22 | 2016-09-22 | 2016-09-22 | 2016-09-22 | 2016-09-22 | 2016-09-22 | 2016-09-22 | 2016-09-22 | 2016-09-22 | 2016-09-22 | 2016-09-22 | 2016-09-22 | 2016-09-22 | 2016-09-22 | 2016-09-22 | 2016-09-22 | 2016-09-22
2AI101CV01900-08030 | EOF:Clean Sand filling after CP installation (Internal) for 52-D-95 Fnd | [15 empty] | 2016-09-25 | 2016-09-25 | 2016-09-25 | 2016-09-25 | 2016-09-25 | 2016-09-25 | 2016-09-25 | 2016-09-25 | 2016-09-25 | 2016-09-25 | 2016-09-25 | 2016-09-25 | 2016-09-25 | 2016-09-25 | 2016-09-25 | 2016-09-25 | 2016-09-25 | 2016-09-25 | 2016-09-25 | 2016-09-25 | 2016-09-25 | 2016-09-25 | 2016-09-25 | 2016-09-25 | 2016-09-25 | 2016-09-25 | 2016-09-25 | 2016-09-25 | 2016-09-25 | 2016-09-25 | 2016-09-25
2AI101CV01900-08035 | Compacted Gatch fill & Blinding for HDPE drain canister (External) | [13 empty] | 2016-08-08 | 2016-08-08 | 2016-08-08 | 2016-08-08 | 2016-08-08 | 2016-08-08 | 2016-08-08 | 2016-08-08 | 2016-08-08 | 2016-08-08 | 2016-08-08 | 2016-08-08 | 2016-08-08 | 2016-08-08 | 2016-08-08 | 2016-08-08 | 2016-08-08 | 2016-08-08 | 2016-08-08 | 2016-08-08 | 2016-08-08 | 2016-08-08 | 2016-08-08 | 2016-08-08 | 2016-08-08 | 2016-08-08 | 2016-08-08 | 2016-08-08 | 2016-08-08 | 2016-08-08 | 2016-08-08 | 2016-08-08 | 2016-08-08
2AI101CV01900-08040 | Crushed Gravel w/ Gatch Mix Layer (External) | [13 empty] | 2016-08-08: 2018-12-01; 2016-08-08: 2018-12-01; 2016-08-08: 2018-12-01; 2016-08-08: 2018-12-01; 2016-08-08: 2018-12-01
2AI101CV01900-08042 | Rebar & Formwork for Access staircases & Service platforms (External) | [21 empty] | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03
2AI101CV01900-08045 | Concreting for Access staircases & Service platforms (External) | [21 empty] | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09
2AI101CV01900-08050 | Asphaltic Concrete layer (External)
2AI101CV01900-08055 | Install PVC leak detection pipes & HDPE drain canister (External) | [21 empty] | 2017-04-09: 2019-01-12; 2017-04-09: 2019-01-12; 2017-04-09: 2019-01-12; 2017-04-09: 2019-01-12; 2017-04-09: 2019-01-12
2AI101CV01900-08070 | EOF:Gatch Filling & Compaction (Internal) for Tank Fnd | [13 empty] | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08
2AI101CV01900-08075 | EOF:Sand layer & Compaction (Internal) for 52-D-96 Fnd | [15 empty] | 2016-10-10 | 2016-10-10 | 2016-10-10 | 2016-10-10 | 2016-10-10 | 2016-10-10 | 2016-10-10 | 2016-10-10 | 2016-10-10 | 2016-10-10 | 2016-10-10 | 2016-10-10 | 2016-10-10 | 2016-10-10 | 2016-10-10 | 2016-10-10 | 2016-10-10 | 2016-10-10 | 2016-10-10 | 2016-10-10 | 2016-10-10 | 2016-10-10 | 2016-10-10 | 2016-10-10 | 2016-10-10 | 2016-10-10 | 2016-10-10 | 2016-10-10 | 2016-10-10 | 2016-10-10 | 2016-10-10
2AI101CV01900-08080 | EOF:Geo Membrane laying (Internal) for 52-D-96 Fnd | [15 empty] | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03
2AI101CV01900-08085 | EOF:Sand filling (Internal) for 52-D-96 Fnd | [15 empty] | 2016-10-10 | 2016-10-10 | 2016-10-10 | 2016-10-10 | 2016-10-10 | 2016-10-10 | 2016-10-10 | 2016-10-10 | 2016-10-10 | 2016-10-10 | 2016-10-10 | 2016-10-10 | 2016-10-10 | 2016-10-10 | 2016-10-10 | 2016-10-10 | 2016-10-10 | 2016-10-10 | 2016-10-10 | 2016-10-10 | 2016-10-10 | 2016-10-10 | 2016-10-10 | 2016-10-10 | 2016-10-10 | 2016-10-10 | 2016-10-10 | 2016-10-10 | 2016-10-10 | 2016-10-10 | 2016-10-10
2AI101CV01900-08090 | EOF:Install Embedments (Internal) for 52-D-96 Fnd | [15 empty] | 2016-10-17 | 2016-10-17 | 2016-10-17 | 2016-10-17 | 2016-10-17 | 2016-10-17 | 2016-10-17 | 2016-10-17 | 2016-10-17 | 2016-10-17 | 2016-10-17 | 2016-10-17 | 2016-10-17 | 2016-10-17 | 2016-10-17 | 2016-10-17 | 2016-10-17 | 2016-10-17 | 2016-10-17 | 2016-10-17 | 2016-10-17 | 2016-10-17 | 2016-10-17 | 2016-10-17 | 2016-10-17 | 2016-10-17 | 2016-10-17 | 2016-10-17 | 2016-10-17 | 2016-10-17 | 2016-10-17
2AI101CV01900-08095 | EOF:Permeable Sand-gravel filling (Internal) for 52-D-96 Fnd | [15 empty] | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18
2AI101CV01900-08100 | EOF:Clean Sand filling after CP installation (Internal) for 52-D-96 Fnd | [15 empty] | 2016-10-22 | 2016-10-22 | 2016-10-22 | 2016-10-22 | 2016-10-22 | 2016-10-22 | 2016-10-22 | 2016-10-22 | 2016-10-22 | 2016-10-22 | 2016-10-22 | 2016-10-22 | 2016-10-22 | 2016-10-22 | 2016-10-22 | 2016-10-22 | 2016-10-22 | 2016-10-22 | 2016-10-22 | 2016-10-22 | 2016-10-22 | 2016-10-22 | 2016-10-22 | 2016-10-22 | 2016-10-22 | 2016-10-22 | 2016-10-22 | 2016-10-22 | 2016-10-22 | 2016-10-22 | 2016-10-22
2AI101CV01900-08105 | Compacted Gatch fill & Blinding for HDPE drain canister (External) | [15 empty] | 2016-09-25 | 2016-09-25 | 2016-09-25 | 2016-09-25 | 2016-09-25 | 2016-09-25 | 2016-09-25 | 2016-09-25 | 2016-09-25 | 2016-09-25 | 2016-09-25 | 2016-09-25 | 2016-09-25 | 2016-09-25 | 2016-09-25 | 2016-09-25 | 2016-09-25 | 2016-09-25 | 2016-09-25 | 2016-09-25 | 2016-09-25 | 2016-09-25 | 2016-09-25 | 2016-09-25 | 2016-09-25 | 2016-09-25 | 2016-09-25 | 2016-09-25 | 2016-09-25 | 2016-09-25 | 2016-09-25
2AI101CV01900-08110 | Crushed Gravel w/ Gatch Mix Layer (External) | [15 empty] | 2016-09-25: 2018-12-22; 2016-09-25: 2018-12-22; 2016-09-25: 2018-12-22; 2016-09-25: 2018-12-22; 2016-09-25: 2018-12-22
2AI101CV01900-08112 | Rebar & Formwork for Access staircases & Service platforms (External) | [21 empty] | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03
2AI101CV01900-08115 | Concreting for Access staircases & Service platforms (External) | [21 empty] | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09
2AI101CV01900-08120 | Asphaltic Concrete layer (External)
2AI101CV01900-08125 | Install PVC leak detection pipes & HDPE drain canister (External) | [21 empty] | 2017-04-09: 2019-01-28; 2017-04-09: 2019-01-28; 2017-04-09: 2019-01-28
2AI101CV02000 | EOF:Lot-1-J : LFHO Storage Tank (52-D-95 & 52-D-96) : CP works | [15 empty] | 2016-09-26 | 2016-09-26 | 2016-09-26 | 2016-09-26 | 2016-09-26 | 2016-09-26 | 2016-09-26 | 2016-09-26 | 2016-09-26 | 2016-09-26 | 2016-09-26 | 2016-09-26 | 2016-09-26 | 2016-09-26 | 2016-09-26 | 2016-09-26 | 2016-09-26 | 2016-09-26 | 2016-09-26 | 2016-09-26 | 2016-09-26 | 2016-09-26 | 2016-09-26 | 2016-09-26 | 2016-09-26 | 2016-09-26 | 2016-09-26 | 2016-09-26 | 2016-09-26 | 2016-09-26 | 2016-09-26
2AI101CV02100 | EOF:Lot-1-J : LFHO Storage Tank (52-D-95 & 52-D-96) : Construct Bund Wall | [13 empty] | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08
2AI101CV02100-08005 | LFHO Storage Tank (52-D-95) & (52-D-96) : Construct Bund Wall | [13 empty] | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08
2AI101CV02100-08015 | EOF: Survey Marking, Excavation & Disposal of unsutiable Material for Bund Wall around Storage tank 52-D-96 & 52-D-95 | [13 empty] | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08
2AI101CV02100-08020 | EOF: Prepare Subgrade lvl for Bund Wall around Storage tank 52-D-96 & 52-D-95 | [15 empty] | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06
2AI101CV02100-08025 | EOF:Slope Preparation for Bund Wall around Storage tank 52-D-96 & 52-D-95 | [15 empty] | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06
2AI101CV02100-08030 | EOF:Install/Cast Catch basin (inside) & Valve pit (outside) for Bund Wall around Storage tank 52-D-96 & 52-D-95 | [15 empty] | 2016-10-15 | 2016-10-15 | 2016-10-15 | 2016-10-15 | 2016-10-15 | 2016-10-15 | 2016-10-15 | 2016-10-15 | 2016-10-15 | 2016-10-15 | 2016-10-15 | 2016-10-15 | 2016-10-15 | 2016-10-15 | 2016-10-15 | 2016-10-15 | 2016-10-15 | 2016-10-15 | 2016-10-15 | 2016-10-15 | 2016-10-15 | 2016-10-15 | 2016-10-15 | 2016-10-15 | 2016-10-15 | 2016-10-15 | 2016-10-15 | 2016-10-15 | 2016-10-15 | 2016-10-15 | 2016-10-15
2AI101CV02100-08035 | EOF:Lay Drain Pipe (CB to Valve pit) for Bund Wall around Storage tank 52-D-96 & 52-D-95 | [25 empty] | 2017-08-25 | 2017-08-25 | 2017-08-25 | 2017-08-25 | 2017-08-25 | 2017-08-25 | 2017-08-25 | 2017-08-25 | 2017-08-25 | 2017-08-25 | 2017-08-25 | 2017-08-25 | 2017-08-25 | 2017-08-25 | 2017-08-25 | 2017-08-25 | 2017-08-25 | 2017-08-25 | 2017-08-25 | 2017-08-25 | 2017-08-25
2AI101CV02100-08040 | EOF:Sand layer (Inside) upto Linear Menbrane Lvl for Bund Wall around Storage tank 52-D-96 & 52-D-95 | [23 empty] | 2017-05-29 | 2017-05-29 | 2017-05-29 | 2017-05-29 | 2017-05-29 | 2017-05-29 | 2017-05-29 | 2017-05-29 | 2017-05-29 | 2017-05-29 | 2017-05-29 | 2017-05-29 | 2017-05-29 | 2017-05-29 | 2017-05-29 | 2017-05-29 | 2017-05-29 | 2017-05-29 | 2017-05-29 | 2017-05-29 | 2017-05-29 | 2017-05-29 | 2017-05-29
2AI101CV02100-08045 | EOF:Install Linar Membrane (incl. base & inside slope) for Bund Wall around Storage tank 52-D-96 & 52-D-95 | [31 empty] | 2018-02-03 | 2018-02-03 | 2018-02-03 | 2018-02-03 | 2018-02-03 | 2018-02-03 | 2018-02-03 | 2018-02-03 | 2018-02-03 | 2018-02-03 | 2018-02-03 | 2018-02-03 | 2018-02-03 | 2018-02-03 | 2018-02-03
2AI101CV02100-08050 | EOF:Gatch Filling & Compaction for Bund Wall around Storage tank 52-D-96 & 52-D-95 | [31 empty] | 2018-02-12 | 2018-02-12 | 2018-02-12 | 2018-02-12 | 2018-02-12 | 2018-02-12 | 2018-02-12 | 2018-02-12 | 2018-02-12 | 2018-02-12 | 2018-02-12 | 2018-02-12 | 2018-02-12 | 2018-02-12 | 2018-02-12
2AI101CV02100-08055 | EOF:Prepare Access ramp (with Compact fill & Gatch layer) for Bund Wall around Storage tank 52-D-96 & 52-D-95 | [31 empty] | 2018-02-12: 2018-11-05; 2018-02-12: 2018-11-05; 2018-02-12: 2018-11-05; 2018-02-12: 2018-11-05; 2018-02-12: 2018-11-05; 2018-02-12: 2018-11-05; 2018-02-12: 2018-11-05
2AI101CV02100-08060 | EOF:Rebar, Form work & Concreting for Stair cases for Bund Wall around Storage tank 52-D-96 & 52-D-95 | [23 empty] | 2017-06-15 | 2017-06-15 | 2017-06-15 | 2017-06-15 | 2017-06-15 | 2017-06-15 | 2017-06-15 | 2017-06-15 | 2017-06-15 | 2017-06-15 | 2017-06-15 | 2017-06-15 | 2017-06-15 | 2017-06-15 | 2017-06-15 | 2017-06-15 | 2017-06-15 | 2017-06-15 | 2017-06-15 | 2017-06-15 | 2017-06-15 | 2017-06-15 | 2017-06-15
2AI101CV02100-08065 | EOF:Asphalt Lining for Inside slope for Bund Wall 52-D-96 & 52-D-95 | [33 empty] | 2018-03-24 | 2018-03-24 | 2018-03-24 | 2018-03-24 | 2018-03-24 | 2018-03-24 | 2018-03-24 | 2018-03-24 | 2018-03-24 | 2018-03-24 | 2018-03-24 | 2018-03-24 | 2018-03-24
2AI101CV03100 | EOF: Fire Proofing of Structures/equipments | [33 empty] | 2018-03-24: 2019-04-17
2AI101CV03100-08000 | EOF: Fire Proofing of LFHO at Storage Tank - 52-D-93 Area
2AI101CV03100-08005 | EOF: Fire Proofing of LFHO at Storage Tank - 52-D-94 Area
2AI101CV03100-08010 | EOF: Fire Proofing of LFHO at Storage Tank - 52-D-95 Area
2AI101CV03100-08015 | EOF: Fire Proofing of LFHO at Storage Tank - 52-D-96 Area
2AI101CV03100-08020 | EOF: Fire Proofing of Diesel Generator Day Tank - 50-R-002
2AI101CV03100-08025 | EOF: Fire Proofing of Diesel Generator Day Tank - 52-R-302
2AI101CV03100-08030 | EOF: Fire Proofing of Trimp Pump - 621-G-301 | [33 empty] | 2018-03-24: 2019-04-17
2AI101CV03100-08035 | EOF: Fire Proofing of Diesel Generator Day Tank - 52-R-301
2AI101CV03100-08040 | EOF: Fire Proofing of Diesel Generator Day Tank - 52-R-303
2AI101CV11000 | EOF: Construction of Sump | [11 empty] | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22
2AI101CV11000-08000 | EOF: Oily Water Collection Vessel Sump (52-SU-301) Construction | [11 empty] | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22
2AI101CV11000-08001 | EOF:Excavation & Subgrade for Sump | [11 empty] | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22
2AI101CV11000-08005 | EOF:Blinding/PCC for Sump Fnd | [11 empty] | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21
2AI101CV11000-08010 | EOF:Rebar, Formwork for base of Sump | [13 empty] | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23
2AI101CV11000-08011 | EOF:Concrete Pouring for base of Sump | [13 empty] | 2016-07-28 | 2016-07-28 | 2016-07-28 | 2016-07-28 | 2016-07-28 | 2016-07-28 | 2016-07-28 | 2016-07-28 | 2016-07-28 | 2016-07-28 | 2016-07-28 | 2016-07-28 | 2016-07-28 | 2016-07-28 | 2016-07-28 | 2016-07-28 | 2016-07-28 | 2016-07-28 | 2016-07-28 | 2016-07-28 | 2016-07-28 | 2016-07-28 | 2016-07-28 | 2016-07-28 | 2016-07-28 | 2016-07-28 | 2016-07-28 | 2016-07-28 | 2016-07-28 | 2016-07-28 | 2016-07-28 | 2016-07-28 | 2016-07-28
2AI101CV11000-08015 | EOF:Rebar, Formwork for wall of Sump | [13 empty] | 2016-08-09 | 2016-08-09 | 2016-08-09 | 2016-08-09 | 2016-08-09 | 2016-08-09 | 2016-08-09 | 2016-08-09 | 2016-08-09 | 2016-08-09 | 2016-08-09 | 2016-08-09 | 2016-08-09 | 2016-08-09 | 2016-08-09 | 2016-08-09 | 2016-08-09 | 2016-08-09 | 2016-08-09 | 2016-08-09 | 2016-08-09 | 2016-08-09 | 2016-08-09 | 2016-08-09 | 2016-08-09 | 2016-08-09 | 2016-08-09 | 2016-08-09 | 2016-08-09 | 2016-08-09 | 2016-08-09 | 2016-08-09 | 2016-08-09
2AI101CV11000-08016 | EOF:Concrete Pouring for Wall of Sump | [13 empty] | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27
2AI101CV11000-08020 | EOF:Concrete Protection for Sump | [13 empty] | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08
2AI101CV11000-08025 | EOF:Cover slab for Sump | [15 empty] | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03
2AI101CV11000-08030 | EOF:Backfilling & Compaction Around Sump | [13 empty] | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10
2AI101CV18200 | EOF: Touch-up painting of Structures | [31 empty] | 2018-03-21 | 2018-03-21 | 2018-03-21 | 2018-03-21 | 2018-03-21 | 2018-03-21 | 2018-03-21 | 2018-03-21 | 2018-03-21 | 2018-03-21 | 2018-03-21 | 2018-03-21 | 2018-03-21 | 2018-03-21 | 2018-03-21
2AI101CV18200-08000 | EOF: Touch-up painting of Structures | [31 empty] | 2018-03-21 | 2018-03-21 | 2018-03-21 | 2018-03-21 | 2018-03-21 | 2018-03-21 | 2018-03-21 | 2018-03-21 | 2018-03-21 | 2018-03-21 | 2018-03-21 | 2018-03-21 | 2018-03-21 | 2018-03-21 | 2018-03-21
2AI101CV18400 | EOF: UG Trench and Other Civl Worrks | [7 empty] | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16
2AI101CV18400-08000 | EOF: Pipe Trench | [15 empty] | 2016-11-17 | 2016-11-17 | 2016-11-17 | 2016-11-17 | 2016-11-17 | 2016-11-17 | 2016-11-17 | 2016-11-17 | 2016-11-17 | 2016-11-17 | 2016-11-17 | 2016-11-17 | 2016-11-17 | 2016-11-17 | 2016-11-17 | 2016-11-17 | 2016-11-17 | 2016-11-17 | 2016-11-17 | 2016-11-17 | 2016-11-17 | 2016-11-17 | 2016-11-17 | 2016-11-17 | 2016-11-17 | 2016-11-17 | 2016-11-17 | 2016-11-17 | 2016-11-17 | 2016-11-17 | 2016-11-17
2AI101CV18400-08001 | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material | [17 empty] | 2017-01-15 | 2017-01-15 | 2017-01-15 | 2017-01-15 | 2017-01-15 | 2017-01-15 | 2017-01-15 | 2017-01-15 | 2017-01-15 | 2017-01-15 | 2017-01-15 | 2017-01-15 | 2017-01-15 | 2017-01-15 | 2017-01-15 | 2017-01-15 | 2017-01-15 | 2017-01-15 | 2017-01-15 | 2017-01-15 | 2017-01-15 | 2017-01-15 | 2017-01-15 | 2017-01-15 | 2017-01-15 | 2017-01-15 | 2017-01-15 | 2017-01-15 | 2017-01-15
2AI101CV18400-08005 | EOF: EIT Cable Trench | [7 empty] | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16
2AI101CV18400-08006 | EOF: Bedding (incl. clean sand layer) | [19 empty] | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28
2AI101CV18400-08007 | EOF: Backfilling and Compaction | [23 empty] | 2017-07-13 | 2017-07-13 | 2017-07-13 | 2017-07-13 | 2017-07-13 | 2017-07-13 | 2017-07-13 | 2017-07-13 | 2017-07-13 | 2017-07-13 | 2017-07-13 | 2017-07-13 | 2017-07-13 | 2017-07-13 | 2017-07-13 | 2017-07-13 | 2017-07-13 | 2017-07-13 | 2017-07-13 | 2017-07-13 | 2017-07-13 | 2017-07-13 | 2017-07-13
2AI101CV18400-08010 | EOF: Foundation for Relocation of existing RMU | [7 empty] | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24
2AI101CV18400-08013 | EOF:Install Route/saftey Markers
2AI101CV18400-08015 | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material | [17 empty] | 2017-01-10 | 2017-01-10 | 2017-01-10 | 2017-01-10 | 2017-01-10 | 2017-01-10 | 2017-01-10 | 2017-01-10 | 2017-01-10 | 2017-01-10 | 2017-01-10 | 2017-01-10 | 2017-01-10 | 2017-01-10 | 2017-01-10 | 2017-01-10 | 2017-01-10 | 2017-01-10 | 2017-01-10 | 2017-01-10 | 2017-01-10 | 2017-01-10 | 2017-01-10 | 2017-01-10 | 2017-01-10 | 2017-01-10 | 2017-01-10 | 2017-01-10 | 2017-01-10
2AI101CV18400-08020 | EOF: Bedding (incl. clean sand layer) | [17 empty] | 2017-01-15 | 2017-01-15 | 2017-01-15 | 2017-01-15 | 2017-01-15 | 2017-01-15 | 2017-01-15 | 2017-01-15 | 2017-01-15 | 2017-01-15 | 2017-01-15 | 2017-01-15 | 2017-01-15 | 2017-01-15 | 2017-01-15 | 2017-01-15 | 2017-01-15 | 2017-01-15 | 2017-01-15 | 2017-01-15 | 2017-01-15 | 2017-01-15 | 2017-01-15 | 2017-01-15 | 2017-01-15 | 2017-01-15 | 2017-01-15 | 2017-01-15 | 2017-01-15
2AI101CV18400-08021 | EOF: Backfilling and Compaction | [21 empty] | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03
2AI101CV18400-08026 | EOF:Install Route/saftey Markers
2AI101CV18400-08030 | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material | [23 empty] | 2017-07-16 | 2017-07-16 | 2017-07-16 | 2017-07-16 | 2017-07-16 | 2017-07-16 | 2017-07-16 | 2017-07-16 | 2017-07-16 | 2017-07-16 | 2017-07-16 | 2017-07-16 | 2017-07-16 | 2017-07-16 | 2017-07-16 | 2017-07-16 | 2017-07-16 | 2017-07-16 | 2017-07-16 | 2017-07-16 | 2017-07-16 | 2017-07-16 | 2017-07-16
2AI101CV18400-08035 | EOF: Bedding (incl. clean sand layer) | [23 empty] | 2017-07-26 | 2017-07-26 | 2017-07-26 | 2017-07-26 | 2017-07-26 | 2017-07-26 | 2017-07-26 | 2017-07-26 | 2017-07-26 | 2017-07-26 | 2017-07-26 | 2017-07-26 | 2017-07-26 | 2017-07-26 | 2017-07-26 | 2017-07-26 | 2017-07-26 | 2017-07-26 | 2017-07-26 | 2017-07-26 | 2017-07-26 | 2017-07-26 | 2017-07-26
2AI101CV18400-08036 | EOF: Backfilling and Compaction | [31 empty] | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05
2AI101CV18400-08041 | EOF:Install Route/saftey Markers
2AI101CV18400-08045 | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material | [21 empty] | 2017-05-23 | 2017-05-23 | 2017-05-23 | 2017-05-23 | 2017-05-23 | 2017-05-23 | 2017-05-23 | 2017-05-23 | 2017-05-23 | 2017-05-23 | 2017-05-23 | 2017-05-23 | 2017-05-23 | 2017-05-23 | 2017-05-23 | 2017-05-23 | 2017-05-23 | 2017-05-23 | 2017-05-23 | 2017-05-23 | 2017-05-23 | 2017-05-23 | 2017-05-23 | 2017-05-23 | 2017-05-23
2AI101CV18400-08050 | EOF: Bedding (incl. clean sand layer) | [23 empty] | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01
2AI101CV18400-08055 | EOF: Backfilling and Compaction | [27 empty] | 2017-09-23 | 2017-09-23 | 2017-09-23 | 2017-09-23 | 2017-09-23 | 2017-09-23 | 2017-09-23 | 2017-09-23 | 2017-09-23 | 2017-09-23 | 2017-09-23 | 2017-09-23 | 2017-09-23 | 2017-09-23 | 2017-09-23 | 2017-09-23 | 2017-09-23 | 2017-09-23 | 2017-09-23
2AI101CV18400-08056 | EOF:Install Route/saftey Markers
2AI101CV18400-08060 | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material | [15 empty] | 2016-11-17 | 2016-11-17 | 2016-11-17 | 2016-11-17 | 2016-11-17 | 2016-11-17 | 2016-11-17 | 2016-11-17 | 2016-11-17 | 2016-11-17 | 2016-11-17 | 2016-11-17 | 2016-11-17 | 2016-11-17 | 2016-11-17 | 2016-11-17 | 2016-11-17 | 2016-11-17 | 2016-11-17 | 2016-11-17 | 2016-11-17 | 2016-11-17 | 2016-11-17 | 2016-11-17 | 2016-11-17 | 2016-11-17 | 2016-11-17 | 2016-11-17 | 2016-11-17 | 2016-11-17 | 2016-11-17
2AI101CV18400-08065 | EOF: Bedding (incl. clean sand layer) | [17 empty] | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06 | 2016-12-06
2AI101CV18400-08070 | EOF: Backfilling and Compaction | [19 empty] | 2017-01-31 | 2017-01-31 | 2017-01-31 | 2017-01-31 | 2017-01-31 | 2017-01-31 | 2017-01-31 | 2017-01-31 | 2017-01-31 | 2017-01-31 | 2017-01-31 | 2017-01-31 | 2017-01-31 | 2017-01-31 | 2017-01-31 | 2017-01-31 | 2017-01-31 | 2017-01-31 | 2017-01-31 | 2017-01-31 | 2017-01-31 | 2017-01-31 | 2017-01-31 | 2017-01-31 | 2017-01-31 | 2017-01-31 | 2017-01-31
2AI101CV18400-08071 | EOF:Install Route/saftey Markers
2AI101CV18400-08075 | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material | [7 empty] | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16
2AI101CV18400-08080 | EOF:Sand bedding | [7 empty] | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18
2AI101CV18400-08081 | EOF:Sand Padding | [9 empty] | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26
2AI101CV18400-08085 | EOF:Install Cable Tile Laying & warning Tapes | [9 empty] | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27
2AI101CV18400-08090 | EOF:Backfilling & Compaction | [9 empty] | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29
2AI101CV18400-08095 | EOF:Install Route/saftey Markers | [15 empty] | 2016-10-12 | 2016-10-12 | 2016-10-12 | 2016-10-12 | 2016-10-12 | 2016-10-12 | 2016-10-12 | 2016-10-12 | 2016-10-12 | 2016-10-12 | 2016-10-12 | 2016-10-12 | 2016-10-12 | 2016-10-12 | 2016-10-12 | 2016-10-12 | 2016-10-12 | 2016-10-12 | 2016-10-12 | 2016-10-12 | 2016-10-12 | 2016-10-12 | 2016-10-12 | 2016-10-12 | 2016-10-12 | 2016-10-12 | 2016-10-12 | 2016-10-12 | 2016-10-12 | 2016-10-12 | 2016-10-12
2AI101CV18400-08100 | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material | [21 empty] | 2017-05-05 | 2017-05-05 | 2017-05-05 | 2017-05-05 | 2017-05-05 | 2017-05-05 | 2017-05-05 | 2017-05-05 | 2017-05-05 | 2017-05-05 | 2017-05-05 | 2017-05-05 | 2017-05-05 | 2017-05-05 | 2017-05-05 | 2017-05-05 | 2017-05-05 | 2017-05-05 | 2017-05-05 | 2017-05-05 | 2017-05-05 | 2017-05-05 | 2017-05-05 | 2017-05-05 | 2017-05-05
2AI101CV18400-08105 | EOF:Sand bedding | [21 empty] | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06
2AI101CV18400-08106 | EOF:Sand Padding | [23 empty] | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03
2AI101CV18400-08110 | EOF:Install Cable Tile Laying & warning Tapes | [23 empty] | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03
2AI101CV18400-08115 | EOF:Backfilling & Compaction | [23 empty] | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03
2AI101CV18400-08120 | EOF:Install Route/saftey Markers | [35 empty] | 2018-07-01 | 2018-07-01 | 2018-07-01 | 2018-07-01 | 2018-07-01 | 2018-07-01 | 2018-07-01 | 2018-07-01 | 2018-07-01 | 2018-07-01 | 2018-07-01
2AI101CV18400-08125 | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material | [19 empty] | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04
2AI101CV18400-08130 | EOF:Sand bedding | [19 empty] | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05
2AI101CV18400-08131 | EOF:Sand Padding | [21 empty] | 2017-05-21 | 2017-05-21 | 2017-05-21 | 2017-05-21 | 2017-05-21 | 2017-05-21 | 2017-05-21 | 2017-05-21 | 2017-05-21 | 2017-05-21 | 2017-05-21 | 2017-05-21 | 2017-05-21 | 2017-05-21 | 2017-05-21 | 2017-05-21 | 2017-05-21 | 2017-05-21 | 2017-05-21 | 2017-05-21 | 2017-05-21 | 2017-05-21 | 2017-05-21 | 2017-05-21 | 2017-05-21
2AI101CV18400-08135 | EOF:Install Cable Tile Laying & warning Tapes | [27 empty] | 2017-11-07 | 2017-11-07 | 2017-11-07 | 2017-11-07 | 2017-11-07 | 2017-11-07 | 2017-11-07 | 2017-11-07 | 2017-11-07 | 2017-11-07 | 2017-11-07 | 2017-11-07 | 2017-11-07 | 2017-11-07 | 2017-11-07 | 2017-11-07 | 2017-11-07 | 2017-11-07 | 2017-11-07
2AI101CV18400-08140 | EOF:Backfilling & Compaction | [27 empty] | 2017-11-21 | 2017-11-21 | 2017-11-21 | 2017-11-21 | 2017-11-21 | 2017-11-21 | 2017-11-21 | 2017-11-21 | 2017-11-21 | 2017-11-21 | 2017-11-21 | 2017-11-21 | 2017-11-21 | 2017-11-21 | 2017-11-21 | 2017-11-21 | 2017-11-21 | 2017-11-21 | 2017-11-21
2AI101CV18400-08145 | EOF:Install Route/saftey Markers
2AI101CV18400-08150 | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material | [17 empty] | 2017-01-11 | 2017-01-11 | 2017-01-11 | 2017-01-11 | 2017-01-11 | 2017-01-11 | 2017-01-11 | 2017-01-11 | 2017-01-11 | 2017-01-11 | 2017-01-11 | 2017-01-11 | 2017-01-11 | 2017-01-11 | 2017-01-11 | 2017-01-11 | 2017-01-11 | 2017-01-11 | 2017-01-11 | 2017-01-11 | 2017-01-11 | 2017-01-11 | 2017-01-11 | 2017-01-11 | 2017-01-11 | 2017-01-11 | 2017-01-11 | 2017-01-11 | 2017-01-11
2AI101CV18400-08155 | EOF:Sand bedding | [19 empty] | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28
2AI101CV18400-08156 | EOF:Sand Padding | [21 empty] | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07
2AI101CV18400-08160 | EOF:Install Cable Tile Laying & warning Tapes | [25 empty] | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29
2AI101CV18400-08165 | EOF:Backfilling & Compaction | [25 empty] | 2017-07-31 | 2017-07-31 | 2017-07-31 | 2017-07-31 | 2017-07-31 | 2017-07-31 | 2017-07-31 | 2017-07-31 | 2017-07-31 | 2017-07-31 | 2017-07-31 | 2017-07-31 | 2017-07-31 | 2017-07-31 | 2017-07-31 | 2017-07-31 | 2017-07-31 | 2017-07-31 | 2017-07-31 | 2017-07-31 | 2017-07-31
2AI101CV18400-08170 | EOF:Install Route/saftey Markers
2AI101CV18400-08175 | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material | [27 empty] | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06
2AI101CV18400-08180 | EOF:Sand bedding | [27 empty] | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06
2AI101CV18400-08181 | EOF:Sand Padding | [27 empty] | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06
2AI101CV18400-08185 | EOF:Install Cable Tile Laying & warning Tapes | [27 empty] | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06
2AI101CV18400-08190 | EOF:Backfilling & Compaction | [27 empty] | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06
2AI101CV18400-08195 | EOF:Install Route/saftey Markers | [27 empty] | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06
2AI101CV18400-08200 | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material | [27 empty] | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06
2AI101CV18400-08205 | EOF:Sand bedding | [27 empty] | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06
2AI101CV18400-08206 | EOF:Sand Padding | [27 empty] | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06
2AI101CV18400-08210 | EOF:Install Cable Tile Laying & warning Tapes | [27 empty] | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06
2AI101CV18400-08215 | EOF:Backfilling & Compaction | [27 empty] | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06
2AI101CV18400-08220 | EOF:Install Route/saftey Markers | [27 empty] | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06
2AI101CV18400-08225 | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material | [27 empty] | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06
2AI101CV18400-08230 | EOF:Sand bedding | [27 empty] | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06
2AI101CV18400-08231 | EOF:Sand Padding | [27 empty] | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06
2AI101CV18400-08235 | EOF:Install Cable Tile Laying & warning Tapes | [27 empty] | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06
2AI101CV18400-08240 | EOF:Backfilling & Compaction | [27 empty] | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06
2AI101CV18400-08245 | EOF:Install Route/saftey Markers | [27 empty] | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06
2AI101CV18400-08250 | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material | [27 empty] | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06
2AI101CV18400-08255 | EOF:Sand bedding | [27 empty] | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06
2AI101CV18400-08256 | EOF:Sand Padding | [27 empty] | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06
2AI101CV18400-08260 | EOF:Install Cable Tile Laying & warning Tapes | [27 empty] | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06
2AI101CV18400-08265 | EOF:Backfilling & Compaction | [27 empty] | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06
2AI101CV18400-08270 | EOF:Install Route/saftey Markers | [27 empty] | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06
2AI101CV18400-08275 | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material | [23 empty] | 2017-07-18 | 2017-07-18 | 2017-07-18 | 2017-07-18 | 2017-07-18 | 2017-07-18 | 2017-07-18 | 2017-07-18 | 2017-07-18 | 2017-07-18 | 2017-07-18 | 2017-07-18 | 2017-07-18 | 2017-07-18 | 2017-07-18 | 2017-07-18 | 2017-07-18 | 2017-07-18 | 2017-07-18 | 2017-07-18 | 2017-07-18 | 2017-07-18 | 2017-07-18
2AI101CV18400-08280 | EOF: Bedding (incl. clean sand layer) | [23 empty] | 2017-07-27 | 2017-07-27 | 2017-07-27 | 2017-07-27 | 2017-07-27 | 2017-07-27 | 2017-07-27 | 2017-07-27 | 2017-07-27 | 2017-07-27 | 2017-07-27 | 2017-07-27 | 2017-07-27 | 2017-07-27 | 2017-07-27 | 2017-07-27 | 2017-07-27 | 2017-07-27 | 2017-07-27 | 2017-07-27 | 2017-07-27 | 2017-07-27 | 2017-07-27
2AI101CV18400-08281 | EOF: Backfilling and Compaction | [33 empty] | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02
2AI101CV18400-08286 | EOF:Install Route/saftey Markers
2AI101CV18400-08290 | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material | [23 empty] | 2017-07-18 | 2017-07-18 | 2017-07-18 | 2017-07-18 | 2017-07-18 | 2017-07-18 | 2017-07-18 | 2017-07-18 | 2017-07-18 | 2017-07-18 | 2017-07-18 | 2017-07-18 | 2017-07-18 | 2017-07-18 | 2017-07-18 | 2017-07-18 | 2017-07-18 | 2017-07-18 | 2017-07-18 | 2017-07-18 | 2017-07-18 | 2017-07-18 | 2017-07-18
2AI101CV18400-08295 | EOF: Bedding (incl. clean sand layer) | [23 empty] | 2017-07-27 | 2017-07-27 | 2017-07-27 | 2017-07-27 | 2017-07-27 | 2017-07-27 | 2017-07-27 | 2017-07-27 | 2017-07-27 | 2017-07-27 | 2017-07-27 | 2017-07-27 | 2017-07-27 | 2017-07-27 | 2017-07-27 | 2017-07-27 | 2017-07-27 | 2017-07-27 | 2017-07-27 | 2017-07-27 | 2017-07-27 | 2017-07-27 | 2017-07-27
2AI101CV18400-08296 | EOF: Backfilling and Compaction | [33 empty] | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02
2AI101CV18400-08301 | EOF:Install Route/saftey Markers
2AI101CV18400-08305 | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material | [25 empty] | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26
2AI101CV18400-08310 | EOF: Bedding (incl. clean sand layer) | [27 empty] | 2017-09-26 | 2017-09-26 | 2017-09-26 | 2017-09-26 | 2017-09-26 | 2017-09-26 | 2017-09-26 | 2017-09-26 | 2017-09-26 | 2017-09-26 | 2017-09-26 | 2017-09-26 | 2017-09-26 | 2017-09-26 | 2017-09-26 | 2017-09-26 | 2017-09-26 | 2017-09-26 | 2017-09-26
2AI101CV18400-08311 | EOF: Backfilling and Compaction | [33 empty] | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02
2AI101CV18400-08316 | EOF:Install Route/saftey Markers
2AI101CV18400-08320 | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material | [27 empty] | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02
2AI101CV18400-08325 | EOF: Bedding (incl. clean sand layer) | [27 empty] | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02
2AI101CV18400-08326 | EOF: Backfilling and Compaction | [33 empty] | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02
2AI101CV18400-08331 | EOF:Install Route/saftey Markers
2AI101CV18400-08345 | EOF:Survey Marking, Excavation & Subgrade | [7 empty] | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24 | 2016-03-24
2AI101CV18400-08346 | EOF:Blinding/PCC for Foundation | [9 empty] | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26 | 2016-03-26
2AI101CV18400-08350 | EOF:Rebar & Formwork - for Footing | [9 empty] | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27
2AI101CV18400-08355 | EOF:Concrete Pouring - for Footing | [9 empty] | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27
2AI101CV18400-08360 | EOF:Concrete Potection for Foundation | [9 empty] | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29
2AI101CV18400-08365 | EOF:Backfilling & Compaction for Foundation | [11 empty] | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03
2AI101CV18400-08425 | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material | [21 empty] | 2017-05-23 | 2017-05-23 | 2017-05-23 | 2017-05-23 | 2017-05-23 | 2017-05-23 | 2017-05-23 | 2017-05-23 | 2017-05-23 | 2017-05-23 | 2017-05-23 | 2017-05-23 | 2017-05-23 | 2017-05-23 | 2017-05-23 | 2017-05-23 | 2017-05-23 | 2017-05-23 | 2017-05-23 | 2017-05-23 | 2017-05-23 | 2017-05-23 | 2017-05-23 | 2017-05-23 | 2017-05-23
2AI101CV18400-08430 | EOF: Bedding (incl. clean sand layer) | [23 empty] | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01
2AI101CV18400-08431 | EOF: Backfilling and Compaction | [27 empty] | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02
2AI101CV18400-08436 | EOF:Install Route/saftey Markers
2AI101CV18400-08440 | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material | [21 empty] | 2017-05-11 | 2017-05-11 | 2017-05-11 | 2017-05-11 | 2017-05-11 | 2017-05-11 | 2017-05-11 | 2017-05-11 | 2017-05-11 | 2017-05-11 | 2017-05-11 | 2017-05-11 | 2017-05-11 | 2017-05-11 | 2017-05-11 | 2017-05-11 | 2017-05-11 | 2017-05-11 | 2017-05-11 | 2017-05-11 | 2017-05-11 | 2017-05-11 | 2017-05-11 | 2017-05-11 | 2017-05-11
2AI101CV18400-08445 | EOF: Bedding (incl. clean sand layer) | [23 empty] | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01
2AI101CV18400-08450 | EOF: Backfilling and Compaction | [27 empty] | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02
2AI101CV18400-08451 | EOF:Install Route/saftey Markers
2AI101CV18400-08455 | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material | [23 empty] | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14
2AI101CV18400-08460 | EOF: Bedding (incl. clean sand layer) | [23 empty] | 2017-07-18 | 2017-07-18 | 2017-07-18 | 2017-07-18 | 2017-07-18 | 2017-07-18 | 2017-07-18 | 2017-07-18 | 2017-07-18 | 2017-07-18 | 2017-07-18 | 2017-07-18 | 2017-07-18 | 2017-07-18 | 2017-07-18 | 2017-07-18 | 2017-07-18 | 2017-07-18 | 2017-07-18 | 2017-07-18 | 2017-07-18 | 2017-07-18 | 2017-07-18
2AI101CV18400-08465 | EOF: Backfilling and Compaction | [29 empty] | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01
2AI101CV18400-08466 | EOF:Install Route/saftey Markers
2AI101CV18400-08470 | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material | [23 empty] | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14
2AI101CV18400-08475 | EOF: Bedding (incl. clean sand layer) | [23 empty] | 2017-07-18 | 2017-07-18 | 2017-07-18 | 2017-07-18 | 2017-07-18 | 2017-07-18 | 2017-07-18 | 2017-07-18 | 2017-07-18 | 2017-07-18 | 2017-07-18 | 2017-07-18 | 2017-07-18 | 2017-07-18 | 2017-07-18 | 2017-07-18 | 2017-07-18 | 2017-07-18 | 2017-07-18 | 2017-07-18 | 2017-07-18 | 2017-07-18 | 2017-07-18
2AI101CV18400-08480 | EOF: Backfilling and Compaction | [29 empty] | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23
2AI101CV18400-08481 | EOF:Install Route/saftey Markers
2AI101CV18400-08485 | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material | [19 empty] | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06
2AI101CV18400-08490 | EOF: Bedding (incl. clean sand layer) | [19 empty] | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28
2AI101CV18400-08495 | EOF: Backfilling and Compaction | [23 empty] | 2017-06-24 | 2017-06-24 | 2017-06-24 | 2017-06-24 | 2017-06-24 | 2017-06-24 | 2017-06-24 | 2017-06-24 | 2017-06-24 | 2017-06-24 | 2017-06-24 | 2017-06-24 | 2017-06-24 | 2017-06-24 | 2017-06-24 | 2017-06-24 | 2017-06-24 | 2017-06-24 | 2017-06-24 | 2017-06-24 | 2017-06-24 | 2017-06-24 | 2017-06-24
2AI101CV18400-08496 | EOF:Install Route/saftey Markers
2AI101CV18400-08500 | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material | [29 empty] | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04
2AI101CV18400-08505 | EOF: Bedding (incl. clean sand layer) | [29 empty] | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04
2AI101CV18400-08510 | EOF: Backfilling and Compaction | [31 empty] | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05
2AI101CV18400-08511 | EOF:Install Route/saftey Markers
2AI101CV21000 | EOF: Balance Tank Foundation | [15 empty] | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30
2AI101CV21000-08000 | EOF: Foundation for OverheadWater Tank Structural (52-D-309 A) | [19 empty] | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06
2AI101CV21000-08001 | EOF:Survey Marking, Excavation & Subgrade | [19 empty] | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06
2AI101CV21000-08005 | EOF: Foundation for OverheadWater Tank Structural (52-D-309 B) | [19 empty] | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06
2AI101CV21000-08006 | EOF:Blinding/PCC for Foundation | [19 empty] | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06
2AI101CV21000-08010 | EOF: Foundation for Diesel Engine drain tank-52-D-304A | [15 empty] | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07
2AI101CV21000-08015 | EOF: Foundation for Diesel Engine drain tank-52-D-304B | [15 empty] | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07
2AI101CV21000-08018 | EOF:Rebar, Formwork for Footing | [19 empty] | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06
2AI101CV21000-08019 | EOF:Concrete Pouring - for Footing | [19 empty] | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06
2AI101CV21000-08020 | EOF: Foundation for Foam drain tank-52-D-305A | [15 empty] | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30
2AI101CV21000-08021 | EOF:Rebar, Formwork, Install Embedments for Pedestal | [19 empty] | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06
2AI101CV21000-08025 | EOF: Foundation for Foam drain tank-52-D-305B | [15 empty] | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07
2AI101CV21000-08026 | EOF:Concrete Pouring - for Pedestal | [19 empty] | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06
2AI101CV21000-08030 | EOF: Foundation for Flushing water drain tank-52-D-306A | [15 empty] | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07
2AI101CV21000-08031 | EOF:Concrete Potection for Foundation | [19 empty] | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06
2AI101CV21000-08032 | EOF:Survey Marking, Excavation & Subgrade | [19 empty] | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06
2AI101CV21000-08035 | EOF: Foundation for Flushing water drain tank-52-D-306B | [15 empty] | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31
2AI101CV21000-08036 | EOF:Backfilling & Compaction for Foundation | [19 empty] | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06
2AI101CV21000-08037 | EOF:Blinding/PCC for Foundation | [19 empty] | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06
2AI101CV21000-08040 | EOF: Foundation for Water drain tank-52-D-308A | [17 empty] | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02
2AI101CV21000-08041 | EOF:Rebar, Formwork for Footing | [19 empty] | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06
2AI101CV21000-08042 | EOF:Concrete Pouring - for Footing | [19 empty] | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06
2AI101CV21000-08045 | EOF: Foundation for Water drain tank-52-D-308B | [17 empty] | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28
2AI101CV21000-08046 | EOF:Rebar, Formwork, Install Embedments for Pedestal | [19 empty] | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06
2AI101CV21000-08047 | EOF:Concrete Pouring - for Pedestal | [19 empty] | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06
2AI101CV21000-08050 | EOF:Concrete Potection for Foundation | [19 empty] | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06
2AI101CV21000-08055 | EOF:Backfilling & Compaction for Foundation | [19 empty] | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06
2AI101CV21000-08060 | EOF:Survey Marking, Excavation & Subgrade | [15 empty] | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07
2AI101CV21000-08065 | EOF:Blinding/PCC for Foundation | [15 empty] | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07
2AI101CV21000-08070 | EOF:Rebar, Formwork for Footing | [15 empty] | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07
2AI101CV21000-08071 | EOF:Concrete Pouring - for Footing | [15 empty] | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07
2AI101CV21000-08075 | EOF:Rebar, Formwork, Install Embedments for Pedestal | [15 empty] | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07
2AI101CV21000-08076 | EOF:Concrete Pouring - for Pedestal | [15 empty] | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07
2AI101CV21000-08080 | EOF:Concrete Potection for Foundation | [15 empty] | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07
2AI101CV21000-08085 | EOF:Backfilling & Compaction for Foundation | [15 empty] | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07
2AI101CV21000-08090 | EOF:Survey Marking, Excavation & Subgrade | [15 empty] | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07
2AI101CV21000-08095 | EOF:Blinding/PCC for Foundation | [15 empty] | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07
2AI101CV21000-08100 | EOF:Rebar, Formwork for Footing | [15 empty] | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07
2AI101CV21000-08101 | EOF:Concrete Pouring - for Footing | [15 empty] | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07
2AI101CV21000-08105 | EOF:Rebar, Formwork, Install Embedments for Pedestal | [15 empty] | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07
2AI101CV21000-08106 | EOF:Concrete Pouring - for Pedestal | [15 empty] | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07
2AI101CV21000-08110 | EOF:Concrete Potection for Foundation | [15 empty] | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07
2AI101CV21000-08115 | EOF:Backfilling & Compaction for Foundation | [15 empty] | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07
2AI101CV21000-08120 | EOF:Survey Marking, Excavation & Subgrade | [15 empty] | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07
2AI101CV21000-08125 | EOF:Blinding/PCC for Foundation | [15 empty] | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07
2AI101CV21000-08130 | EOF:Rebar, Formwork for Footing | [15 empty] | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07
2AI101CV21000-08131 | EOF:Concrete Pouring - for Footing | [15 empty] | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07
2AI101CV21000-08132 | EOF:Rebar, Formwork, Install Embedments for Pedestal | [15 empty] | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07
2AI101CV21000-08136 | EOF:Concrete Pouring - for Pedestal | [15 empty] | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30 | 2016-10-30
2AI101CV21000-08140 | EOF:Concrete Potection for Foundation | [15 empty] | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07
2AI101CV21000-08145 | EOF:Backfilling & Compaction for Foundation | [15 empty] | 2016-11-13 | 2016-11-13 | 2016-11-13 | 2016-11-13 | 2016-11-13 | 2016-11-13 | 2016-11-13 | 2016-11-13 | 2016-11-13 | 2016-11-13 | 2016-11-13 | 2016-11-13 | 2016-11-13 | 2016-11-13 | 2016-11-13 | 2016-11-13 | 2016-11-13 | 2016-11-13 | 2016-11-13 | 2016-11-13 | 2016-11-13 | 2016-11-13 | 2016-11-13 | 2016-11-13 | 2016-11-13 | 2016-11-13 | 2016-11-13 | 2016-11-13 | 2016-11-13 | 2016-11-13 | 2016-11-13
2AI101CV21000-08150 | EOF:Survey Marking, Excavation & Subgrade | [15 empty] | 2016-11-19 | 2016-11-19 | 2016-11-19 | 2016-11-19 | 2016-11-19 | 2016-11-19 | 2016-11-19 | 2016-11-19 | 2016-11-19 | 2016-11-19 | 2016-11-19 | 2016-11-19 | 2016-11-19 | 2016-11-19 | 2016-11-19 | 2016-11-19 | 2016-11-19 | 2016-11-19 | 2016-11-19 | 2016-11-19 | 2016-11-19 | 2016-11-19 | 2016-11-19 | 2016-11-19 | 2016-11-19 | 2016-11-19 | 2016-11-19 | 2016-11-19 | 2016-11-19 | 2016-11-19 | 2016-11-19
2AI101CV21000-08155 | EOF:Blinding/PCC for Foundation | [15 empty] | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20
2AI101CV21000-08160 | EOF:Rebar, Formwork for Footing | [15 empty] | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07
2AI101CV21000-08161 | EOF:Concrete Pouring - for Footing | [15 empty] | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07
2AI101CV21000-08165 | EOF:Rebar, Formwork, Install Embedments for Pedestal | [15 empty] | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07
2AI101CV21000-08166 | EOF:Concrete Pouring - for Pedestal | [15 empty] | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07
2AI101CV21000-08170 | EOF:Concrete Potection for Foundation | [15 empty] | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07
2AI101CV21000-08175 | EOF:Backfilling & Compaction for Foundation | [15 empty] | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07
2AI101CV21000-08180 | EOF:Survey Marking, Excavation & Subgrade | [15 empty] | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07
2AI101CV21000-08185 | EOF:Blinding/PCC for Fnd | [15 empty] | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07
2AI101CV21000-08190 | EOF:Rebar, Formwork for Footing | [15 empty] | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07
2AI101CV21000-08191 | EOF:Concrete Pouring - for Footing | [15 empty] | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07
2AI101CV21000-08195 | EOF:Rebar, Formwork, Install Embedments for Pedestal | [15 empty] | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07
2AI101CV21000-08196 | EOF:Concrete Pouring - for Pedestal | [15 empty] | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07
2AI101CV21000-08200 | EOF:Concrete Potection for Fnd | [15 empty] | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07
2AI101CV21000-08205 | EOF:Backfilling & Compaction for Fnd | [15 empty] | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07
2AI101CV21000-08210 | EOF:Survey Marking, Excavation & Subgrade | [15 empty] | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07
2AI101CV21000-08215 | EOF:Blinding/PCC for Fnd | [15 empty] | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07
2AI101CV21000-08220 | EOF:Rebar, Formwork for Footing | [15 empty] | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07
2AI101CV21000-08221 | EOF:Concrete Pouring - for Footing | [15 empty] | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31
2AI101CV21000-08225 | EOF:Rebar, Formwork, Install Embedments for Pedestal | [15 empty] | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03
2AI101CV21000-08226 | EOF:Concrete Pouring - for Pedestal | [15 empty] | 2016-11-08 | 2016-11-08 | 2016-11-08 | 2016-11-08 | 2016-11-08 | 2016-11-08 | 2016-11-08 | 2016-11-08 | 2016-11-08 | 2016-11-08 | 2016-11-08 | 2016-11-08 | 2016-11-08 | 2016-11-08 | 2016-11-08 | 2016-11-08 | 2016-11-08 | 2016-11-08 | 2016-11-08 | 2016-11-08 | 2016-11-08 | 2016-11-08 | 2016-11-08 | 2016-11-08 | 2016-11-08 | 2016-11-08 | 2016-11-08 | 2016-11-08 | 2016-11-08 | 2016-11-08 | 2016-11-08
2AI101CV21000-08230 | EOF:Concrete Potection for Fnd | [15 empty] | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16
2AI101CV21000-08235 | EOF:Backfilling & Compaction for Fnd | [15 empty] | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07
2AI101CV21000-08240 | EOF:Survey Marking, Excavation & Subgrade | [17 empty] | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02
2AI101CV21000-08245 | EOF:Blinding/PCC for Fnd | [17 empty] | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02
2AI101CV21000-08250 | EOF:Rebar, Formwork for Footing | [17 empty] | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02
2AI101CV21000-08251 | EOF:Concrete Pouring - for Footing | [17 empty] | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02
2AI101CV21000-08255 | EOF:Rebar, Formwork, Install Embedments for Pedestal | [17 empty] | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02
2AI101CV21000-08256 | EOF:Concrete Pouring - for Pedestal | [17 empty] | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02
2AI101CV21000-08260 | EOF:Concrete Potection for Fnd | [17 empty] | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02
2AI101CV21000-08265 | EOF:Backfilling & Compaction for Fnd | [17 empty] | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02
2AI101CV21000-08270 | EOF:Survey Marking, Excavation & Subgrade | [17 empty] | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02
2AI101CV21000-08275 | EOF:Blinding/PCC for Fnd | [17 empty] | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02
2AI101CV21000-08280 | EOF:Rebar, Formwork for Footing | [17 empty] | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02
2AI101CV21000-08281 | EOF:Concrete Pouring - for Footing | [17 empty] | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02
2AI101CV21000-08285 | EOF:Rebar, Formwork, Install Embedments for Pedestal | [17 empty] | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02
2AI101CV21000-08286 | EOF:Concrete Pouring - for Pedestal | [17 empty] | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02
2AI101CV21000-08290 | EOF:Concrete Potection for Fnd | [17 empty] | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02
2AI101CV21000-08295 | EOF:Backfilling & Compaction for Fnd | [17 empty] | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28
2AI101CV22000 | EOF: Pump Foundation | [17 empty] | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12
2AI101CV22000-08000 | EOF: Foundation for Trim Pump - 52-G-301A | [17 empty] | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12
2AI101CV22000-08001 | EOF:Survey Marking, Excavation & Subgrade | [17 empty] | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12
2AI101CV22000-08005 | EOF: Foundation for Trim Pump - 52-G-301 B | [17 empty] | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12
2AI101CV22000-08006 | EOF:Blinding/PCC for Fnd | [17 empty] | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17
2AI101CV22000-08010 | EOF:Rebar, Formwork for Footing | [17 empty] | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07
2AI101CV22000-08011 | EOF:Concrete Pouring - for Footing | [19 empty] | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02
2AI101CV22000-08015 | EOF:Rebar, Formwork, Install Embedments for Pedestal | [19 empty] | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28
2AI101CV22000-08016 | EOF:Concrete Pouring - for Pedestal | [19 empty] | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02
2AI101CV22000-08020 | EOF:Concrete Potection for Fnd | [19 empty] | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16
2AI101CV22000-08025 | EOF:Backfilling & Compaction for Fnd | [19 empty] | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01
2AI101CV22000-08030 | EOF:Survey Marking, Excavation & Subgrade | [17 empty] | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12
2AI101CV22000-08035 | EOF:Blinding/PCC for Fnd | [17 empty] | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17
2AI101CV22000-08040 | EOF:Rebar, Formwork for Footing | [17 empty] | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07
2AI101CV22000-08041 | EOF:Concrete Pouring - for Footing | [19 empty] | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02
2AI101CV22000-08045 | EOF:Rebar, Formwork, Install Embedments for Pedestal | [19 empty] | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28
2AI101CV22000-08046 | EOF:Concrete Pouring - for Pedestal | [19 empty] | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02
2AI101CV22000-08050 | EOF:Concrete Potection for Fnd | [19 empty] | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16
2AI101CV22000-08055 | EOF:Backfilling & Compaction for Fnd | [19 empty] | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01
2AI101CV22100 | EOF: Pump Shelter | [29 empty] | 2017-11-25 | 2017-11-25 | 2017-11-25 | 2017-11-25 | 2017-11-25 | 2017-11-25 | 2017-11-25 | 2017-11-25 | 2017-11-25 | 2017-11-25 | 2017-11-25 | 2017-11-25 | 2017-11-25 | 2017-11-25 | 2017-11-25 | 2017-11-25 | 2017-11-25
2AI101CV22100-08000 | EOF: 621-G-302 A Trim Pump Shelter | [29 empty] | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27
2AI101CV22100-08001 | EOF:Installation of Str. Steel for 621-G-302 A Trim Pump Shelter | [29 empty] | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27
2AI101CV22100-08005 | EOF: 621-G-302 B Trim Pump Shelter | [29 empty] | 2017-11-25 | 2017-11-25 | 2017-11-25 | 2017-11-25 | 2017-11-25 | 2017-11-25 | 2017-11-25 | 2017-11-25 | 2017-11-25 | 2017-11-25 | 2017-11-25 | 2017-11-25 | 2017-11-25 | 2017-11-25 | 2017-11-25 | 2017-11-25 | 2017-11-25
2AI101CV22100-08006 | EOF:Alignment & Bolting/Torqueing for 621-G-302 A Trim Pump Shelter | [29 empty] | 2017-12-11 | 2017-12-11 | 2017-12-11 | 2017-12-11 | 2017-12-11 | 2017-12-11 | 2017-12-11 | 2017-12-11 | 2017-12-11 | 2017-12-11 | 2017-12-11 | 2017-12-11 | 2017-12-11 | 2017-12-11 | 2017-12-11 | 2017-12-11 | 2017-12-11
2AI101CV22100-08010 | EOF:Grouting of 621-G-302 A Trim Pump Shelter | [29 empty] | 2017-12-11: 2018-10-08; 2017-12-11: 2018-10-08; 2017-12-11: 2018-10-08; 2017-12-11: 2018-10-08; 2017-12-11: 2018-10-08; 2017-12-11: 2018-10-08; 2017-12-11: 2018-10-08
2AI101CV22100-08015 | EOF:Installation of Str. Steel for 621-G-302 B Trim Pump Shelter | [29 empty] | 2017-11-25 | 2017-11-25 | 2017-11-25 | 2017-11-25 | 2017-11-25 | 2017-11-25 | 2017-11-25 | 2017-11-25 | 2017-11-25 | 2017-11-25 | 2017-11-25 | 2017-11-25 | 2017-11-25 | 2017-11-25 | 2017-11-25 | 2017-11-25 | 2017-11-25
2AI101CV22100-08020 | EOF:Alignment & Bolting/Torqueing for 621-G-302 B Trim Pump Shelter | [29 empty] | 2017-12-11 | 2017-12-11 | 2017-12-11 | 2017-12-11 | 2017-12-11 | 2017-12-11 | 2017-12-11 | 2017-12-11 | 2017-12-11 | 2017-12-11 | 2017-12-11 | 2017-12-11 | 2017-12-11 | 2017-12-11 | 2017-12-11 | 2017-12-11 | 2017-12-11
2AI101CV22100-08025 | EOF:Grouting of 621-G-302 B Trim Pump Shelter | [29 empty] | 2017-12-11: 2018-10-08; 2017-12-11: 2018-10-08; 2017-12-11: 2018-10-08; 2017-12-11: 2018-10-08; 2017-12-11: 2018-10-08; 2017-12-11: 2018-10-08; 2017-12-11: 2018-10-08
2AI101CV22200 | EOF: Pump Shelter Foundation | [19 empty] | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04
2AI101CV22200-08000 | EOF: Trim Pump - 52-G-301A Shelter Foundation | [19 empty] | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04
2AI101CV22200-08001 | EOF:Survey Marking, Excavation & Subgrade | [19 empty] | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04
2AI101CV22200-08005 | EOF: Trim Pump - 52-G-301B Shelter Foundation | [19 empty] | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04
2AI101CV22200-08006 | EOF:Blinding/PCC for Fnd | [19 empty] | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05
2AI101CV22200-08010 | EOF:Rebar, Formwork for Footing | [19 empty] | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05
2AI101CV22200-08011 | EOF:Concrete Pouring - for Footing | [19 empty] | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08
2AI101CV22200-08015 | EOF:Rebar, Formwork, Install Embedments for Pedestal | [19 empty] | 2017-02-09 | 2017-02-09 | 2017-02-09 | 2017-02-09 | 2017-02-09 | 2017-02-09 | 2017-02-09 | 2017-02-09 | 2017-02-09 | 2017-02-09 | 2017-02-09 | 2017-02-09 | 2017-02-09 | 2017-02-09 | 2017-02-09 | 2017-02-09 | 2017-02-09 | 2017-02-09 | 2017-02-09 | 2017-02-09 | 2017-02-09 | 2017-02-09 | 2017-02-09 | 2017-02-09 | 2017-02-09 | 2017-02-09 | 2017-02-09
2AI101CV22200-08016 | EOF:Concrete Pouring - for Pedestal | [19 empty] | 2017-02-14 | 2017-02-14 | 2017-02-14 | 2017-02-14 | 2017-02-14 | 2017-02-14 | 2017-02-14 | 2017-02-14 | 2017-02-14 | 2017-02-14 | 2017-02-14 | 2017-02-14 | 2017-02-14 | 2017-02-14 | 2017-02-14 | 2017-02-14 | 2017-02-14 | 2017-02-14 | 2017-02-14 | 2017-02-14 | 2017-02-14 | 2017-02-14 | 2017-02-14 | 2017-02-14 | 2017-02-14 | 2017-02-14 | 2017-02-14
2AI101CV22200-08020 | EOF:Concrete Potection for Fnd | [19 empty] | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28
2AI101CV22200-08025 | EOF:Backfilling & Compaction for Fnd | [19 empty] | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01
2AI101CV22200-08030 | EOF:Survey Marking, Excavation & Subgrade | [19 empty] | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04 | 2017-02-04
2AI101CV22200-08035 | EOF:Blinding/PCC for Fnd | [19 empty] | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05
2AI101CV22200-08040 | EOF:Rebar, Formwork for Footing | [19 empty] | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06
2AI101CV22200-08041 | EOF:Concrete Pouring - for Footing | [19 empty] | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08
2AI101CV22200-08045 | EOF:Rebar, Formwork, Install Embedments for Pedestal | [19 empty] | 2017-02-09 | 2017-02-09 | 2017-02-09 | 2017-02-09 | 2017-02-09 | 2017-02-09 | 2017-02-09 | 2017-02-09 | 2017-02-09 | 2017-02-09 | 2017-02-09 | 2017-02-09 | 2017-02-09 | 2017-02-09 | 2017-02-09 | 2017-02-09 | 2017-02-09 | 2017-02-09 | 2017-02-09 | 2017-02-09 | 2017-02-09 | 2017-02-09 | 2017-02-09 | 2017-02-09 | 2017-02-09 | 2017-02-09 | 2017-02-09
2AI101CV22200-08046 | EOF:Concrete Pouring - for Pedestal | [19 empty] | 2017-02-14 | 2017-02-14 | 2017-02-14 | 2017-02-14 | 2017-02-14 | 2017-02-14 | 2017-02-14 | 2017-02-14 | 2017-02-14 | 2017-02-14 | 2017-02-14 | 2017-02-14 | 2017-02-14 | 2017-02-14 | 2017-02-14 | 2017-02-14 | 2017-02-14 | 2017-02-14 | 2017-02-14 | 2017-02-14 | 2017-02-14 | 2017-02-14 | 2017-02-14 | 2017-02-14 | 2017-02-14 | 2017-02-14 | 2017-02-14
2AI101CV22200-08050 | EOF:Concrete Potection for Fnd | [19 empty] | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28
2AI101CV22200-08055 | EOF:Backfilling & Compaction for Fnd | [19 empty] | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01
2AI101CV22300 | EOF: Foam Pump House Building Foundation | [17 empty] | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30
2AI101CV22300-08000 | EOF: 621-G-302 A/B Foam Pump House Steel Building Foundation | [17 empty] | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30
2AI101CV22300-08001 | EOF:Survey Marking, Excavation & Subgrade | [17 empty] | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30
2AI101CV22300-08005 | EOF: 621-G-302 C/D Foam Pump House Steel Building Foundation | [17 empty] | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05
2AI101CV22300-08006 | EOF:Blinding/PCC for Fnd | [19 empty] | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11
2AI101CV22300-08010 | EOF:Rebar, Formwork for Footing | [19 empty] | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13
2AI101CV22300-08011 | EOF:Concrete Pouring - for Footing | [19 empty] | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16
2AI101CV22300-08015 | EOF:Rebar, Formwork, Install Embedments for Pedestal | [19 empty] | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18
2AI101CV22300-08016 | EOF:Concrete Pouring - for Pedestal | [19 empty] | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27
2AI101CV22300-08020 | EOF:Concrete Potection for Fnd | [19 empty] | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02
2AI101CV22300-08025 | EOF:Backfilling & Compaction for Fnd | [19 empty] | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07
2AI101CV22300-08030 | EOF:Survey Marking, Excavation & Subgrade | [17 empty] | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05
2AI101CV22300-08035 | EOF:Blinding/PCC for Fnd | [19 empty] | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11
2AI101CV22300-08040 | EOF:Rebar, Formwork for Footing | [19 empty] | 2017-02-12 | 2017-02-12 | 2017-02-12 | 2017-02-12 | 2017-02-12 | 2017-02-12 | 2017-02-12 | 2017-02-12 | 2017-02-12 | 2017-02-12 | 2017-02-12 | 2017-02-12 | 2017-02-12 | 2017-02-12 | 2017-02-12 | 2017-02-12 | 2017-02-12 | 2017-02-12 | 2017-02-12 | 2017-02-12 | 2017-02-12 | 2017-02-12 | 2017-02-12 | 2017-02-12 | 2017-02-12 | 2017-02-12 | 2017-02-12
2AI101CV22300-08041 | EOF:Concrete Pouring - for Footing | [19 empty] | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16
2AI101CV22300-08045 | EOF:Rebar, Formwork, Install Embedments for Pedestal | [19 empty] | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18
2AI101CV22300-08046 | EOF:Concrete Pouring - for Pedestal | [19 empty] | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27
2AI101CV22300-08050 | EOF:Concrete Potection for Fnd | [19 empty] | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02
2AI101CV22300-08055 | EOF:Backfilling & Compaction for Fnd | [19 empty] | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07
2AI101EL01000 | EOF: UG Electrical cable Works | [19 empty] | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28
2AI101EL01000-08000 | EOF: UG Electrical cable Works | [19 empty] | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28
2AI101EL01000-08001 | EOF: Cable Drum Checks & Transport to Site- LV Cables | [19 empty] | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28
2AI101EL01000-08005 | EOF: Cable Pulling - LV Cables | [19 empty] | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28
2AI101EL01000-08010 | EOF: Cable Dressing & Fastening - LV Cables | [21 empty] | 2017-04-13 | 2017-04-13 | 2017-04-13 | 2017-04-13 | 2017-04-13 | 2017-04-13 | 2017-04-13 | 2017-04-13 | 2017-04-13 | 2017-04-13 | 2017-04-13 | 2017-04-13 | 2017-04-13 | 2017-04-13 | 2017-04-13 | 2017-04-13 | 2017-04-13 | 2017-04-13 | 2017-04-13 | 2017-04-13 | 2017-04-13 | 2017-04-13 | 2017-04-13 | 2017-04-13 | 2017-04-13
2AI101EL01000-08024 | EOF: Cable Drum Checks & Transport to Site- earthing Cables | [23 empty] | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03
2AI101EL01000-08025 | EOF: Cable Pulling - Base/Insulated earthing | [23 empty] | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03
2AI101EL01000-08030 | EOF: Base/Insulated earthing cable thermoweld jointing/connections | [23 empty] | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05
2AI101EL01000-08040 | EOF: Cable Marking | [21 empty] | 2017-05-13 | 2017-05-13 | 2017-05-13 | 2017-05-13 | 2017-05-13 | 2017-05-13 | 2017-05-13 | 2017-05-13 | 2017-05-13 | 2017-05-13 | 2017-05-13 | 2017-05-13 | 2017-05-13 | 2017-05-13 | 2017-05-13 | 2017-05-13 | 2017-05-13 | 2017-05-13 | 2017-05-13 | 2017-05-13 | 2017-05-13 | 2017-05-13 | 2017-05-13 | 2017-05-13 | 2017-05-13
2AI101EL01000-08045 | EOF: Cable Drum Checks & Transport to Site- HV Cables | [25 empty] | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04
2AI101EL01000-08050 | EOF: Cable Pulling - HV Cables | [25 empty] | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04
2AI101EL01000-08051 | EOF: Cable Spicing - HV | [25 empty] | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04
2AI101EL01000-08055 | EOF: Cable Dressing & Fastening - HV Cables | [25 empty] | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26
2AI101EL01000-08060 | EOF: Cable Marking | [25 empty] | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04
2AI101EL01000-08070 | EOF: Earth Pit and Earth Bar Installation | [35 empty] | 2018-05-29 | 2018-05-29 | 2018-05-29 | 2018-05-29 | 2018-05-29 | 2018-05-29 | 2018-05-29 | 2018-05-29 | 2018-05-29 | 2018-05-29 | 2018-05-29
2AI101EL01100 | EOF:AG Cable laying, CP, DB'S/JB, Panels, Lighting Pole, Fixtures, Cable Glaning & Termination Electrical Works | [13 empty] | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04
2AI101EL01100-08005 | EOF:Installation of DB'S / JB & Panels | [29 empty] | 2017-11-26 | 2017-11-26 | 2017-11-26 | 2017-11-26 | 2017-11-26 | 2017-11-26 | 2017-11-26 | 2017-11-26 | 2017-11-26 | 2017-11-26 | 2017-11-26 | 2017-11-26 | 2017-11-26 | 2017-11-26 | 2017-11-26 | 2017-11-26 | 2017-11-26
2AI101EL01100-08015 | EOF:Installation of Lighting Poles & Fixtures | [19 empty] | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06
2AI101EL01100-08020 | EOF: CP Works | [13 empty] | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04
2AI101EL01100-08025 | EOF:Cable Glanding & Terminations | [33 empty] | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02
2AI101EL01100-08040 | EOF:Installation of supports | [19 empty] | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06
2AI101EL01100-08045 | EOF:Install light pole | [27 empty] | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16
2AI101EL01100-08050 | EOF:Install Lighting fixtures | [27 empty] | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16
2AI101EL01100-08055 | EOF:Installation of CP Anodes (incl. civil works) | [13 empty] | 2016-08-12 | 2016-08-12 | 2016-08-12 | 2016-08-12 | 2016-08-12 | 2016-08-12 | 2016-08-12 | 2016-08-12 | 2016-08-12 | 2016-08-12 | 2016-08-12 | 2016-08-12 | 2016-08-12 | 2016-08-12 | 2016-08-12 | 2016-08-12 | 2016-08-12 | 2016-08-12 | 2016-08-12 | 2016-08-12 | 2016-08-12 | 2016-08-12 | 2016-08-12 | 2016-08-12 | 2016-08-12 | 2016-08-12 | 2016-08-12 | 2016-08-12 | 2016-08-12 | 2016-08-12 | 2016-08-12 | 2016-08-12 | 2016-08-12
2AI101EL01100-08060 | EOF:Installation of Transformer/JBs | [37 empty] | 2018-09-04 | 2018-09-04 | 2018-09-04 | 2018-09-04 | 2018-09-04 | 2018-09-04 | 2018-09-04 | 2018-09-04 | 2018-09-04
2AI101EL01100-08065 | EOF:Cable laying & Termination | [33 empty] | 2018-05-16 | 2018-05-16 | 2018-05-16 | 2018-05-16 | 2018-05-16 | 2018-05-16 | 2018-05-16 | 2018-05-16 | 2018-05-16 | 2018-05-16 | 2018-05-16 | 2018-05-16 | 2018-05-16
2AI101EL01100-08070 | EOF:Installation of CP Anodes (incl. civil works) | [13 empty] | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04
2AI101EL01100-08075 | EOF:Installation of Transformer/JBs | [37 empty] | 2018-09-04 | 2018-09-04 | 2018-09-04 | 2018-09-04 | 2018-09-04 | 2018-09-04 | 2018-09-04 | 2018-09-04 | 2018-09-04
2AI101EL01100-08080 | EOF:Cable laying & Termination | [33 empty] | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15
2AI101EL01100-08085 | EOF:Installation of CP Anodes (incl. civil works) | [15 empty] | 2016-09-26 | 2016-09-26 | 2016-09-26 | 2016-09-26 | 2016-09-26 | 2016-09-26 | 2016-09-26 | 2016-09-26 | 2016-09-26 | 2016-09-26 | 2016-09-26 | 2016-09-26 | 2016-09-26 | 2016-09-26 | 2016-09-26 | 2016-09-26 | 2016-09-26 | 2016-09-26 | 2016-09-26 | 2016-09-26 | 2016-09-26 | 2016-09-26 | 2016-09-26 | 2016-09-26 | 2016-09-26 | 2016-09-26 | 2016-09-26 | 2016-09-26 | 2016-09-26 | 2016-09-26 | 2016-09-26
2AI101EL01100-08090 | EOF:Installation of Transformer/JBs | [15 empty] | 2016-09-26: 2018-11-05; 2016-09-26: 2018-11-05; 2016-09-26: 2018-11-05; 2016-09-26: 2018-11-05; 2016-09-26: 2018-11-05; 2016-09-26: 2018-11-05; 2016-09-26: 2018-11-05
2AI101EL01100-08095 | EOF:Cable laying & Termination | [33 empty] | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15
2AI101EL01100-08100 | EOF:Installation of CP Anodes (incl. civil works) | [15 empty] | 2016-10-24 | 2016-10-24 | 2016-10-24 | 2016-10-24 | 2016-10-24 | 2016-10-24 | 2016-10-24 | 2016-10-24 | 2016-10-24 | 2016-10-24 | 2016-10-24 | 2016-10-24 | 2016-10-24 | 2016-10-24 | 2016-10-24 | 2016-10-24 | 2016-10-24 | 2016-10-24 | 2016-10-24 | 2016-10-24 | 2016-10-24 | 2016-10-24 | 2016-10-24 | 2016-10-24 | 2016-10-24 | 2016-10-24 | 2016-10-24 | 2016-10-24 | 2016-10-24 | 2016-10-24 | 2016-10-24
2AI101EL01100-08105 | EOF:Installation of Transformer/JBs | [15 empty] | 2016-10-24: 2018-11-05; 2016-10-24: 2018-11-05; 2016-10-24: 2018-11-05; 2016-10-24: 2018-11-05; 2016-10-24: 2018-11-05; 2016-10-24: 2018-11-05; 2016-10-24: 2018-11-05
2AI101EL01100-08110 | EOF:Cable laying & Termination | [33 empty] | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15
2AI101EL01100-08113 | EOF: Cable Laying | [33 empty] | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02
2AI101EL01100-08115 | EOF:Cable Glanding | [33 empty] | 2018-04-02: 2018-11-05; 2018-04-02: 2018-11-05; 2018-04-02: 2018-11-05; 2018-04-02: 2018-11-05; 2018-04-02: 2018-11-05; 2018-04-02: 2018-11-05; 2018-04-02: 2018-11-05
2AI101EL01100-08120 | EOF:Hi-Po test & Terminations | [33 empty] | 2018-04-02: 2018-11-05; 2018-04-02: 2018-11-05; 2018-04-02: 2018-11-05; 2018-04-02: 2018-11-05; 2018-04-02: 2018-11-05; 2018-04-02: 2018-11-05; 2018-04-02: 2018-11-05
2AI101EL01100-08130 | EOF:Tagging | [37 empty] | 2018-09-25 | 2018-09-25 | 2018-09-25 | 2018-09-25 | 2018-09-25 | 2018-09-25 | 2018-09-25 | 2018-09-25 | 2018-09-25
2AI101EL01100-08138 | EOF:Installation of supports | [29 empty] | 2017-11-26 | 2017-11-26 | 2017-11-26 | 2017-11-26 | 2017-11-26 | 2017-11-26 | 2017-11-26 | 2017-11-26 | 2017-11-26 | 2017-11-26 | 2017-11-26 | 2017-11-26 | 2017-11-26 | 2017-11-26 | 2017-11-26 | 2017-11-26 | 2017-11-26
2AI101EL01100-08140 | EOF:Install JB's/DB's | [29 empty] | 2017-12-02 | 2017-12-02 | 2017-12-02 | 2017-12-02 | 2017-12-02 | 2017-12-02 | 2017-12-02 | 2017-12-02 | 2017-12-02 | 2017-12-02 | 2017-12-02 | 2017-12-02 | 2017-12-02 | 2017-12-02 | 2017-12-02 | 2017-12-02 | 2017-12-02
2AI101EL01100-08150 | EOF:Leveling & Grouting | [33 empty] | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02
2AI101IC01000 | EOF: UG Instrumentation cable works | [21 empty] | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10
2AI101IC01000-08000 | EOF: UG Instrumentation cable works | [21 empty] | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10
2AI101IC01000-08001 | Cable Drum Checks & Transport to Site | [21 empty] | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10
2AI101IC01000-08010 | Cable Pulling | [21 empty] | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16
2AI101IC01000-08020 | Cable Dressing & Fastening | [21 empty] | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16
2AI101IC01000-08030 | Cable Marking | [21 empty] | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29
2AI101IC01100 | EOF: AG cable laying,Tubing, Field&Inline Inst. Installation, Cable Glading & Termination (incl. F&G System) | [23 empty] | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27
2AI101IC01100-08000 | EOF:Install Instrument Cable trays & Supports | [23 empty] | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27
2AI101IC01100-08001 | EOF:Fabricate Tray Supports | [23 empty] | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27
2AI101IC01100-08004 | EOF:Cable Drum Checks & Transport to Site | [37 empty] | 2018-08-29 | 2018-08-29 | 2018-08-29 | 2018-08-29 | 2018-08-29 | 2018-08-29 | 2018-08-29 | 2018-08-29 | 2018-08-29
2AI101IC01100-08005 | EOF:Install Instrument JBs | [29 empty] | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06
2AI101IC01100-08006 | EOF:AG Cable laying | [37 empty] | 2018-08-29 | 2018-08-29 | 2018-08-29 | 2018-08-29 | 2018-08-29 | 2018-08-29 | 2018-08-29 | 2018-08-29 | 2018-08-29
2AI101IC01100-08010 | EOF: AG cable laying | [33 empty] | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07
2AI101IC01100-08011 | EOF:Install Tray Supports | [23 empty] | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27
2AI101IC01100-08015 | EOF: Calibration of Valves/Instruments | [37 empty] | 2018-07-28 | 2018-07-28 | 2018-07-28 | 2018-07-28 | 2018-07-28 | 2018-07-28 | 2018-07-28 | 2018-07-28 | 2018-07-28
2AI101IC01100-08016 | EOF:Cable Glading & Termination | [31 empty] | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05
2AI101IC01100-08020 | EOF: Install Inst. Valves/Inline mounted Instruments | [37 empty] | 2018-08-06 | 2018-08-06 | 2018-08-06 | 2018-08-06 | 2018-08-06 | 2018-08-06 | 2018-08-06 | 2018-08-06 | 2018-08-06
2AI101IC01100-08021 | Receipt of Valves/Instruments at Calibration shop | [37 empty] | 2018-07-28 | 2018-07-28 | 2018-07-28 | 2018-07-28 | 2018-07-28 | 2018-07-28 | 2018-07-28 | 2018-07-28 | 2018-07-28
2AI101IC01100-08025 | EOF: Fabricate/Install Inst. tubing & Instrument Hookup | [33 empty] | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21
2AI101IC01100-08030 | EOF:Cable Glading & Termination | [31 empty] | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05
2AI101IC01100-08031 | Testing of Valves/Instruments at Calibration shop | [37 empty] | 2018-07-28 | 2018-07-28 | 2018-07-28 | 2018-07-28 | 2018-07-28 | 2018-07-28 | 2018-07-28 | 2018-07-28 | 2018-07-28
2AI101IC01100-08035 | EOF:Cable Dressing & Fastening | [37 empty] | 2018-08-29 | 2018-08-29 | 2018-08-29 | 2018-08-29 | 2018-08-29 | 2018-08-29 | 2018-08-29 | 2018-08-29 | 2018-08-29
2AI101IC01100-08040 | QC checks & clearance for installation | [37 empty] | 2018-07-29 | 2018-07-29 | 2018-07-29 | 2018-07-29 | 2018-07-29 | 2018-07-29 | 2018-07-29 | 2018-07-29 | 2018-07-29
2AI101IC01100-08045 | EOF:Cable Marking | [33 empty] | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07
2AI101IC01100-08050 | EOF: Mechanical/Piping Clearence and preparatory works | [37 empty] | 2018-08-06 | 2018-08-06 | 2018-08-06 | 2018-08-06 | 2018-08-06 | 2018-08-06 | 2018-08-06 | 2018-08-06 | 2018-08-06
2AI101IC01100-08060 | EOF: Installation of Valves/Inline Instruments | [37 empty] | 2018-08-06 | 2018-08-06 | 2018-08-06 | 2018-08-06 | 2018-08-06 | 2018-08-06 | 2018-08-06 | 2018-08-06 | 2018-08-06
2AI101IC01100-08070 | EOF: Fabrication & Installation of Support Structures | [33 empty] | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21
2AI101IC01100-08080 | EOF: Installation of Instruments on Support Structures | [33 empty] | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21
2AI101IC01100-08090 | EOF: Alignment/Levelling and grouting | [33 empty] | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21
2AI101IC01100-08100 | EOF:Install Cable Trays | [23 empty] | 2017-06-28 | 2017-06-28 | 2017-06-28 | 2017-06-28 | 2017-06-28 | 2017-06-28 | 2017-06-28 | 2017-06-28 | 2017-06-28 | 2017-06-28 | 2017-06-28 | 2017-06-28 | 2017-06-28 | 2017-06-28 | 2017-06-28 | 2017-06-28 | 2017-06-28 | 2017-06-28 | 2017-06-28 | 2017-06-28 | 2017-06-28 | 2017-06-28 | 2017-06-28
2AI101IC01100-08110 | EOF:Install Cable Tray Covers | [37 empty] | 2018-08-29 | 2018-08-29 | 2018-08-29 | 2018-08-29 | 2018-08-29 | 2018-08-29 | 2018-08-29 | 2018-08-29 | 2018-08-29
2AI101IC01100-08120 | EOF: Supports Installation | [29 empty] | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06
2AI101IC01100-08130 | EOF: Mounting JB's | [29 empty] | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06
2AI101IC01100-08140 | EOF: Leveling & Grouting | [29 empty] | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06
2AI101MS01400-08005 | EOF: LFHO Storage Tank 52-D-93 - Last Piping Tie-In Works (Piping Installation ) | [29 empty] | 2018-01-06: 2018-10-01; 2018-01-06: 2018-10-01; 2018-01-06: 2018-10-01; 2018-01-06: 2018-10-01; 2018-01-06: 2018-10-01; 2018-01-06: 2018-10-01; 2018-01-06: 2018-10-01
2AI101MS01400-08010 | EOF: LFHO Storage Tank 52-D-94 - Last Piping Tie-In Works (Piping Installation ) | [29 empty] | 2018-01-06: 2018-10-21; 2018-01-06: 2018-10-21; 2018-01-06: 2018-10-21; 2018-01-06: 2018-10-21; 2018-01-06: 2018-10-21; 2018-01-06: 2018-10-21; 2018-01-06: 2018-10-21
2AI101MS01900 | EOF: Balance Tanks Erection | [19 empty] | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12
2AI101MS01900-08000 | EOF: OverheadWater Tank (52-D-309 A) Erection | [19 empty] | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12
2AI101MS01900-08001 | EOF:Foundation checks/Preparation for Equipment | [19 empty] | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12
2AI101MS01900-08005 | EOF: OverheadWater Tank (52-D-309 B) Erection | [21 empty] | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03
2AI101MS01900-08006 | EOF:Installation of Structural Support | [19 empty] | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13
2AI101MS01900-08010 | EOF: Diesel Engine drain tank-52-D-304AErection | [21 empty] | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09
2AI101MS01900-08011 | EOF:Installation of Equipment | [19 empty] | 2017-03-18 | 2017-03-18 | 2017-03-18 | 2017-03-18 | 2017-03-18 | 2017-03-18 | 2017-03-18 | 2017-03-18 | 2017-03-18 | 2017-03-18 | 2017-03-18 | 2017-03-18 | 2017-03-18 | 2017-03-18 | 2017-03-18 | 2017-03-18 | 2017-03-18 | 2017-03-18 | 2017-03-18 | 2017-03-18 | 2017-03-18 | 2017-03-18 | 2017-03-18 | 2017-03-18 | 2017-03-18 | 2017-03-18 | 2017-03-18
2AI101MS01900-08015 | EOF: Diesel Engine drain tank-52-D-304BErection | [21 empty] | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14
2AI101MS01900-08016 | EOF:Preliminary Allignment & Grouting of Equipment | [21 empty] | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25
2AI101MS01900-08020 | EOF: Foam drain tank-52-D-305AErection | [23 empty] | 2017-06-18 | 2017-06-18 | 2017-06-18 | 2017-06-18 | 2017-06-18 | 2017-06-18 | 2017-06-18 | 2017-06-18 | 2017-06-18 | 2017-06-18 | 2017-06-18 | 2017-06-18 | 2017-06-18 | 2017-06-18 | 2017-06-18 | 2017-06-18 | 2017-06-18 | 2017-06-18 | 2017-06-18 | 2017-06-18 | 2017-06-18 | 2017-06-18 | 2017-06-18
2AI101MS01900-08021 | EOF:Final Allignment & Grouting of Equipment | [21 empty] | 2017-03-27 | 2017-03-27 | 2017-03-27 | 2017-03-27 | 2017-03-27 | 2017-03-27 | 2017-03-27 | 2017-03-27 | 2017-03-27 | 2017-03-27 | 2017-03-27 | 2017-03-27 | 2017-03-27 | 2017-03-27 | 2017-03-27 | 2017-03-27 | 2017-03-27 | 2017-03-27 | 2017-03-27 | 2017-03-27 | 2017-03-27 | 2017-03-27 | 2017-03-27 | 2017-03-27 | 2017-03-27
2AI101MS01900-08025 | EOF: Foam drain tank-52-D-305B Erection | [25 empty] | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29
2AI101MS01900-08026 | EOF:Install Platforms & ladders of Equipment | [21 empty] | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29
2AI101MS01900-08030 | EOF: Flushing water drain tank-52-D-306AErection | [21 empty] | 2017-05-10 | 2017-05-10 | 2017-05-10 | 2017-05-10 | 2017-05-10 | 2017-05-10 | 2017-05-10 | 2017-05-10 | 2017-05-10 | 2017-05-10 | 2017-05-10 | 2017-05-10 | 2017-05-10 | 2017-05-10 | 2017-05-10 | 2017-05-10 | 2017-05-10 | 2017-05-10 | 2017-05-10 | 2017-05-10 | 2017-05-10 | 2017-05-10 | 2017-05-10 | 2017-05-10 | 2017-05-10
2AI101MS01900-08031 | EOF:Install internals of Equipment | [21 empty] | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03
2AI101MS01900-08035 | EOF: Flushing water drain tank-52-D-306B Erection | [23 empty] | 2017-06-14 | 2017-06-14 | 2017-06-14 | 2017-06-14 | 2017-06-14 | 2017-06-14 | 2017-06-14 | 2017-06-14 | 2017-06-14 | 2017-06-14 | 2017-06-14 | 2017-06-14 | 2017-06-14 | 2017-06-14 | 2017-06-14 | 2017-06-14 | 2017-06-14 | 2017-06-14 | 2017-06-14 | 2017-06-14 | 2017-06-14 | 2017-06-14 | 2017-06-14
2AI101MS01900-08036 | EOF:QC checks & clearance for Equipment | [21 empty] | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03
2AI101MS01900-08040 | EOF: Water drain tank-52-D-308AErection | [19 empty] | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12
2AI101MS01900-08041 | EOF:Foundation checks/Preparation for Equipment | [21 empty] | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09
2AI101MS01900-08045 | EOF: Water drain tank-52-D-308BErection | [21 empty] | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16
2AI101MS01900-08046 | EOF:Installation of Structural Support | [21 empty] | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10
2AI101MS01900-08050 | EOF:Installation of Equipment | [21 empty] | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15
2AI101MS01900-08055 | EOF:Preliminary Allignment & Grouting of Equipment | [21 empty] | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29
2AI101MS01900-08060 | EOF:Final Allignment & Grouting of Equipment | [21 empty] | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29
2AI101MS01900-08065 | EOF:Install Platforms & ladders of Equipment | [21 empty] | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29
2AI101MS01900-08070 | EOF:Install internals of Equipment | [21 empty] | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03
2AI101MS01900-08075 | EOF:QC checks & clearance for Equipment | [21 empty] | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03 | 2017-04-03
2AI101MS01900-08115 | EOF: Diesel Engine drain tank-52-D-304A Erection | [21 empty] | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09 | 2017-04-09
2AI101MS01900-08120 | EOF: Diesel Engine drain tank-52-D-304B Erection | [21 empty] | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14
2AI101MS01900-08125 | EOF: Foam drain tank-52-D-305A Erection | [23 empty] | 2017-06-18 | 2017-06-18 | 2017-06-18 | 2017-06-18 | 2017-06-18 | 2017-06-18 | 2017-06-18 | 2017-06-18 | 2017-06-18 | 2017-06-18 | 2017-06-18 | 2017-06-18 | 2017-06-18 | 2017-06-18 | 2017-06-18 | 2017-06-18 | 2017-06-18 | 2017-06-18 | 2017-06-18 | 2017-06-18 | 2017-06-18 | 2017-06-18 | 2017-06-18
2AI101MS01900-08130 | EOF: Foam drain tank-52-D-305B Erection | [25 empty] | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29
2AI101MS01900-08135 | EOF: Flushing water drain tank-52-D-306A Erection | [21 empty] | 2017-05-10 | 2017-05-10 | 2017-05-10 | 2017-05-10 | 2017-05-10 | 2017-05-10 | 2017-05-10 | 2017-05-10 | 2017-05-10 | 2017-05-10 | 2017-05-10 | 2017-05-10 | 2017-05-10 | 2017-05-10 | 2017-05-10 | 2017-05-10 | 2017-05-10 | 2017-05-10 | 2017-05-10 | 2017-05-10 | 2017-05-10 | 2017-05-10 | 2017-05-10 | 2017-05-10 | 2017-05-10
2AI101MS01900-08140 | EOF: Flushing water drain tank-52-D-306B Erection | [23 empty] | 2017-06-14 | 2017-06-14 | 2017-06-14 | 2017-06-14 | 2017-06-14 | 2017-06-14 | 2017-06-14 | 2017-06-14 | 2017-06-14 | 2017-06-14 | 2017-06-14 | 2017-06-14 | 2017-06-14 | 2017-06-14 | 2017-06-14 | 2017-06-14 | 2017-06-14 | 2017-06-14 | 2017-06-14 | 2017-06-14 | 2017-06-14 | 2017-06-14 | 2017-06-14
2AI101MS01900-08145 | EOF: Water drain tank-52-D-308A Erection | [19 empty] | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12
2AI101MS01900-08150 | EOF: Water drain tank-52-D-308B Erection | [21 empty] | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16
2AI101MS02600-08005 | EOF: LFHO Storage Tank 52-D-95 - Last Piping Tie-In Works (Piping Installation ) | [21 empty] | 2017-04-16: 2018-10-17; 2017-04-16: 2018-10-17; 2017-04-16: 2018-10-17; 2017-04-16: 2018-10-17; 2017-04-16: 2018-10-17; 2017-04-16: 2018-10-17; 2017-04-16: 2018-10-17
2AI101MS02600-08010 | EOF: LFHO Storage Tank 52-D-96 - Last Piping Tie-In Works (Piping Installation ) | [21 empty] | 2017-04-16: 2018-10-20; 2017-04-16: 2018-10-20; 2017-04-16: 2018-10-20; 2017-04-16: 2018-10-20; 2017-04-16: 2018-10-20; 2017-04-16: 2018-10-20; 2017-04-16: 2018-10-20
2AI101MS02600-08020 | EOF: Sorage Tank tank 52-D-93: Release After completion of Erection by other sub contract | [35 empty] | 2018-07-25 | 2018-07-25 | 2018-07-25 | 2018-07-25 | 2018-07-25 | 2018-07-25 | 2018-07-25 | 2018-07-25 | 2018-07-25 | 2018-07-25 | 2018-07-25
2AI101MS02600-08025 | EOF: Sorage Tank tank 52-D-94: Release After completion of Erection by other sub contractor | [37 empty] | 2018-08-24 | 2018-08-24 | 2018-08-24 | 2018-08-24 | 2018-08-24 | 2018-08-24 | 2018-08-24 | 2018-08-24 | 2018-08-24
2AI101MS02600-08030 | EOF: Sorage Tank tank 52-D-95: Release After completion of Erection by other sub contractor | [37 empty] | 2018-09-15 | 2018-09-15 | 2018-09-15 | 2018-09-15 | 2018-09-15 | 2018-09-15 | 2018-09-15 | 2018-09-15 | 2018-09-15
2AI101MS02600-08035 | EOF: Sorage Tank tank 52-D-96: Release After completion of Erection by other sub contractor | [39 empty] | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30
2AI101MS02600-08040 | EOF: PIG Release Release After completion of Erection by other sub contractor
2AI101MS03000 | EOF: Pump Erection | [31 empty] | 2018-03-01 | 2018-03-01 | 2018-03-01 | 2018-03-01 | 2018-03-01 | 2018-03-01 | 2018-03-01 | 2018-03-01 | 2018-03-01 | 2018-03-01 | 2018-03-01 | 2018-03-01 | 2018-03-01 | 2018-03-01 | 2018-03-01
2AI101MS03000-08000 | EOF: 621-G-301 A Trim Pump Erection | [31 empty] | 2018-03-01 | 2018-03-01 | 2018-03-01 | 2018-03-01 | 2018-03-01 | 2018-03-01 | 2018-03-01 | 2018-03-01 | 2018-03-01 | 2018-03-01 | 2018-03-01 | 2018-03-01 | 2018-03-01 | 2018-03-01 | 2018-03-01
2AI101MS03000-08001 | EOF:Foundation checks/Preparation for Equipment 621-G-301 A Trim Pump Erection | [31 empty] | 2018-03-01 | 2018-03-01 | 2018-03-01 | 2018-03-01 | 2018-03-01 | 2018-03-01 | 2018-03-01 | 2018-03-01 | 2018-03-01 | 2018-03-01 | 2018-03-01 | 2018-03-01 | 2018-03-01 | 2018-03-01 | 2018-03-01
2AI101MS03000-08005 | EOF: 621-G-301 B Trim Pump Erection | [31 empty] | 2018-03-02 | 2018-03-02 | 2018-03-02 | 2018-03-02 | 2018-03-02 | 2018-03-02 | 2018-03-02 | 2018-03-02 | 2018-03-02 | 2018-03-02 | 2018-03-02 | 2018-03-02 | 2018-03-02 | 2018-03-02 | 2018-03-02
2AI101MS03000-08006 | EOF:Installation of Equipment 621-G-301 A Trim Pump Erection | [31 empty] | 2018-03-03 | 2018-03-03 | 2018-03-03 | 2018-03-03 | 2018-03-03 | 2018-03-03 | 2018-03-03 | 2018-03-03 | 2018-03-03 | 2018-03-03 | 2018-03-03 | 2018-03-03 | 2018-03-03 | 2018-03-03 | 2018-03-03
2AI101MS03000-08010 | EOF: 621-G-303 A Oily Water Transfer Pump Erection | [35 empty] | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26
2AI101MS03000-08011 | EOF:Preliminary Allignment & Grouting of Equipment 621-G-301 A Trim Pump Erection | [33 empty] | 2018-04-23 | 2018-04-23 | 2018-04-23 | 2018-04-23 | 2018-04-23 | 2018-04-23 | 2018-04-23 | 2018-04-23 | 2018-04-23 | 2018-04-23 | 2018-04-23 | 2018-04-23 | 2018-04-23
2AI101MS03000-08015 | EOF: 621-G-303 B Oily Water Transfer Pump Erection | [35 empty] | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26
2AI101MS03000-08016 | EOF:Final Allignment & Grouting of Equipment 621-G-301 A Trim Pump Erection | [37 empty] | 2018-08-03 | 2018-08-03 | 2018-08-03 | 2018-08-03 | 2018-08-03 | 2018-08-03 | 2018-08-03 | 2018-08-03 | 2018-08-03
2AI101MS03000-08020 | EOF:QC checks & clearance for Equipment 621-G-301 A Trim Pump Erection | [37 empty] | 2018-08-23 | 2018-08-23 | 2018-08-23 | 2018-08-23 | 2018-08-23 | 2018-08-23 | 2018-08-23 | 2018-08-23 | 2018-08-23
2AI101MS03000-08025 | EOF:Foundation checks/Preparation for Equipment 621-G-301 B Trim Pump Erection | [31 empty] | 2018-03-02 | 2018-03-02 | 2018-03-02 | 2018-03-02 | 2018-03-02 | 2018-03-02 | 2018-03-02 | 2018-03-02 | 2018-03-02 | 2018-03-02 | 2018-03-02 | 2018-03-02 | 2018-03-02 | 2018-03-02 | 2018-03-02
2AI101MS03000-08030 | EOF:Installation of Equipment 621-G-301 B Trim Pump Erection | [31 empty] | 2018-03-04 | 2018-03-04 | 2018-03-04 | 2018-03-04 | 2018-03-04 | 2018-03-04 | 2018-03-04 | 2018-03-04 | 2018-03-04 | 2018-03-04 | 2018-03-04 | 2018-03-04 | 2018-03-04 | 2018-03-04 | 2018-03-04
2AI101MS03000-08035 | EOF:Preliminary Allignment & Grouting of Equipment 621-G-301 B Trim Pump Erection | [33 empty] | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21
2AI101MS03000-08040 | EOF:Final Allignment & Grouting of Equipment 621-G-301 B Trim Pump Erection | [37 empty] | 2018-08-05 | 2018-08-05 | 2018-08-05 | 2018-08-05 | 2018-08-05 | 2018-08-05 | 2018-08-05 | 2018-08-05 | 2018-08-05
2AI101MS03000-08045 | EOF:QC checks & clearance for Equipment 621-G-301 B Trim Pump Erection | [37 empty] | 2018-08-24 | 2018-08-24 | 2018-08-24 | 2018-08-24 | 2018-08-24 | 2018-08-24 | 2018-08-24 | 2018-08-24 | 2018-08-24
2AI101MS03000-08050 | EOF:Foundation checks/Preparation for Equipment 621-G-303 A Oily Water Transfer Pump | [35 empty] | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26
2AI101MS03000-08055 | EOF:Installation of Equipment 621-G-303 A Oily Water Transfer Pump | [35 empty] | 2018-05-27 | 2018-05-27 | 2018-05-27 | 2018-05-27 | 2018-05-27 | 2018-05-27 | 2018-05-27 | 2018-05-27 | 2018-05-27 | 2018-05-27 | 2018-05-27
2AI101MS03000-08060 | EOF:Preliminary Allignment & Grouting of Equipment 621-G-303 A Oily Water Transfer Pump | [35 empty] | 2018-05-27 | 2018-05-27 | 2018-05-27 | 2018-05-27 | 2018-05-27 | 2018-05-27 | 2018-05-27 | 2018-05-27 | 2018-05-27 | 2018-05-27 | 2018-05-27
2AI101MS03000-08065 | EOF:Final Allignment & Grouting of Equipment 621-G-303 A Oily Water Transfer Pump
2AI101MS03000-08070 | EOF:QC checks & clearance for Equipment 621-G-303 A Oily Water Transfer Pump
2AI101MS03000-08075 | EOF:Foundation checks/Preparation for Equipment 621-G-303 B Oily Water Transfer Pump | [35 empty] | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26
2AI101MS03000-08080 | EOF:Installation of Equipment 621-G-303 B Oily Water Transfer Pump | [35 empty] | 2018-05-27 | 2018-05-27 | 2018-05-27 | 2018-05-27 | 2018-05-27 | 2018-05-27 | 2018-05-27 | 2018-05-27 | 2018-05-27 | 2018-05-27 | 2018-05-27
2AI101MS03000-08085 | EOF:Preliminary Allignment & Grouting of Equipment 621-G-303 B Oily Water Transfer Pump | [35 empty] | 2018-05-27 | 2018-05-27 | 2018-05-27 | 2018-05-27 | 2018-05-27 | 2018-05-27 | 2018-05-27 | 2018-05-27 | 2018-05-27 | 2018-05-27 | 2018-05-27
2AI101MS03000-08090 | EOF:Final Allignment & Grouting of Equipment 621-G-303 B Oily Water Transfer Pump
2AI101MS03000-08095 | EOF:QC checks & clearance for Equipment 621-G-303 B Oily Water Transfer Pump
2AI101PC01000 | EOF SS 52-SUBST-302 : 110V DC Battery Charger
2AI101PC01000-08000 | EOF SS 52-SUBST-302 : 110V DC Battery Charger
2AI101PC01000-08001 | EOF:Polarity check
2AI101PC01000-08005 | EOF:Charging test
2AI101PC01000-08010 | EOF:Discharging test
2AI101PC01100 | EOF SS 52-SUBST-302 : SS Earthing & Lightning | [35 empty] | 2018-05-27: 2019-03-09; 2018-05-27: 2019-03-09; 2018-05-27: 2019-03-09
2AI101PC01100-08000 | EOF SS 52-SUBST-302 : SS Earthing & Lightning | [35 empty] | 2018-05-27: 2019-03-09; 2018-05-27: 2019-03-09; 2018-05-27: 2019-03-09
2AI101PC01100-08001 | EOF:Continuity testing | [35 empty] | 2018-05-27: 2019-03-16; 2018-05-27: 2019-03-16; 2018-05-27: 2019-03-16
2AI101PC01100-08005 | EOF:Earth resistance measurement | [35 empty] | 2018-05-27: 2019-03-09; 2018-05-27: 2019-03-09; 2018-05-27: 2019-03-09
2AI101PC01200 | EOF SS 52-SUBST-302 : HV Switchgear testing | [35 empty] | 2018-05-27: 2019-03-23; 2018-05-27: 2019-03-23; 2018-05-27: 2019-03-23
2AI101PC01200-08000 | EOF SS 52-SUBST-302 : HV Switchgear testing | [35 empty] | 2018-05-27: 2019-03-23; 2018-05-27: 2019-03-23; 2018-05-27: 2019-03-23
2AI101PC01200-08001 | EOF: CT,PT,Breaker Testing | [35 empty] | 2018-05-27: 2019-03-23; 2018-05-27: 2019-03-23; 2018-05-27: 2019-03-23
2AI101PC01200-08005 | EOF: IR, Ductor testing | [35 empty] | 2018-05-27: 2019-03-23; 2018-05-27: 2019-03-23; 2018-05-27: 2019-03-23
2AI101PC01200-08010 | EOF: Relay & Functional Testing
2AI101PC01200-08015 | EOF Primary Injection Testing | [35 empty] | 2018-05-27: 2019-03-25; 2018-05-27: 2019-03-25; 2018-05-27: 2019-03-25
2AI101PC01200-08020 | EOF: Hi-pot Test
2AI101PC01200-08025 | EOF: Stability Testing
2AI101PC01300 | EOF SS 52-SUBST-302 : 24V DC Battery Charger
2AI101PC01300-08000 | EOF SS 52-SUBST-302 : 24V DC Battery Charger
2AI101PC01300-08001 | EOF:Polarity check
2AI101PC01300-08005 | EOF:Charging test
2AI101PC01300-08010 | EOF:Discharging test
2AI101PC01400 | EOF SS 52-SUBST-302 : LV Switchgear testing | [35 empty] | 2018-05-27: 2019-03-16; 2018-05-27: 2019-03-16; 2018-05-27: 2019-03-16
2AI101PC01400-08000 | EOF SS 52-SUBST-302 : LV Switchgear testing | [35 empty] | 2018-05-27: 2019-03-16; 2018-05-27: 2019-03-16; 2018-05-27: 2019-03-16
2AI101PC01400-08001 | EOF: CT,PT Testing | [35 empty] | 2018-05-27: 2019-03-16; 2018-05-27: 2019-03-16; 2018-05-27: 2019-03-16
2AI101PC01400-08005 | EOF: IR, Ductor testing | [35 empty] | 2018-05-27: 2019-03-16; 2018-05-27: 2019-03-16; 2018-05-27: 2019-03-16
2AI101PC01400-08010 | EOF: Relay & Functional Testing | [35 empty] | 2018-05-27: 2019-03-17; 2018-05-27: 2019-03-17; 2018-05-27: 2019-03-17
2AI101PC01400-08015 | EOF Primary Injection Testing | [35 empty] | 2018-05-27: 2019-03-17; 2018-05-27: 2019-03-17; 2018-05-27: 2019-03-17
2AI101PC01400-08020 | EOF: Hi-pot Test | [35 empty] | 2018-05-27: 2019-04-05
2AI101PC01400-08025 | EOF: Stability Testing | [35 empty] | 2018-05-27: 2019-04-21
2AI101PC01600 | EOF SS 52-SUBST-302 : 110V AC UPS
2AI101PC01600-08000 | EOF SS 52-SUBST-302 : 110V AC UPS
2AI101PC01600-08001 | EOF:Polarity check
2AI101PC01600-08005 | EOF:Charging test
2AI101PC01600-08010 | EOF:Discharging test
2AI101PC01700 | EOF SS 52-SUBST-302 : Transformer Testing | [35 empty] | 2018-05-27: 2019-03-09; 2018-05-27: 2019-03-09; 2018-05-27: 2019-03-09
2AI101PC01700-08000 | EOF SS 52-SUBST-302 : Transformer Testing | [35 empty] | 2018-05-27: 2019-03-09; 2018-05-27: 2019-03-09; 2018-05-27: 2019-03-09
2AI101PC01700-08001 | EOF:IR testing/WR testing/Turns ratio testing | [35 empty] | 2018-05-27: 2019-03-10; 2018-05-27: 2019-03-10; 2018-05-27: 2019-03-10
2AI101PC01700-08005 | EOF:Functional Test | [35 empty] | 2018-05-27: 2019-03-10; 2018-05-27: 2019-03-10; 2018-05-27: 2019-03-10
2AI101PC01700-08010 | EOF:BDV Testing | [35 empty] | 2018-05-27: 2019-03-09; 2018-05-27: 2019-03-09; 2018-05-27: 2019-03-09
2AI101PC01900 | EOF SS 52-SUBST-302 : Electrical Tie-ins for Permanent Power & Energize
2AI101PC01900-08000 | EOF SS 52-SUBST-302 : Electrical Tie-ins for Permanent Power & Energize
2AI101PC01900-08001 | EOF:Incoming cables IR and continuity test
2AI101PC01900-08005 | EOF:Incoming HV cables hipot testing
2AI101PC02000 | EOF SS 52-SUBST-302 : Lighting & Small Power | [25 empty] | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03
2AI101PC02000-08000 | EOF SS 52-SUBST-302 : Lighting & Small Power | [25 empty] | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03
2AI101PC02000-08001 | EOF:Continuity & IR testing | [25 empty] | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03
2AI101PC02000-08005 | EOF:Lux testing | [29 empty] | 2017-12-21 | 2017-12-21 | 2017-12-21 | 2017-12-21 | 2017-12-21 | 2017-12-21 | 2017-12-21 | 2017-12-21 | 2017-12-21 | 2017-12-21 | 2017-12-21 | 2017-12-21 | 2017-12-21 | 2017-12-21 | 2017-12-21 | 2017-12-21 | 2017-12-21
2AI101PC02100 | EOF SS 52-SUBST-302 : Energize EDG 60-R-706
2AI101PC02100-08000 | EOF SS 52-SUBST-302 : Energize EDG 60-R-706
2AI101PC02100-08001 | EOF: GCP Testing, Switch Gear Testing
2AI101PC02100-08010 | EOF SS 52-SUBST-302 : Energize EDG 60-R-706
2AI101PI01000 | EOF: UG Piping works | [17 empty] | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16
2AI101PI01000-08000 | EOF: UG Piping works for Non Metallic | [19 empty] | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06
2AI101PI01000-08001 | EOF:Laying of Piping Spools | [19 empty] | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06
2AI101PI01000-08005 | EOF: UG Piping works for Metallic (CS/LTCS) | [17 empty] | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16
2AI101PI01000-08006 | EOF:Jointing/Fusion Welding | [19 empty] | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06
2AI101PI01000-08010 | EOF: UG Piping works for Metallic (SS/SDSS) | [35 empty] | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26
2AI101PI01000-08011 | EOF:NDE/QC Checks of Pipes | [19 empty] | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06
2AI101PI01000-08016 | EOF:Installation of pipes | [27 empty] | 2017-10-28 | 2017-10-28 | 2017-10-28 | 2017-10-28 | 2017-10-28 | 2017-10-28 | 2017-10-28 | 2017-10-28 | 2017-10-28 | 2017-10-28 | 2017-10-28 | 2017-10-28 | 2017-10-28 | 2017-10-28 | 2017-10-28 | 2017-10-28 | 2017-10-28 | 2017-10-28 | 2017-10-28
2AI101PI01000-08020 | EOF:Installation of pipes | [17 empty] | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16
2AI101PI01000-08025 | EOF:Alignment/Fit-up | [17 empty] | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16
2AI101PI01000-08026 | EOF:Welding/Bolting of Pipes | [17 empty] | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17
2AI101PI01000-08030 | EOF:NDE/PWHT/QC Checks of Pipes | [19 empty] | 2017-01-30 | 2017-01-30 | 2017-01-30 | 2017-01-30 | 2017-01-30 | 2017-01-30 | 2017-01-30 | 2017-01-30 | 2017-01-30 | 2017-01-30 | 2017-01-30 | 2017-01-30 | 2017-01-30 | 2017-01-30 | 2017-01-30 | 2017-01-30 | 2017-01-30 | 2017-01-30 | 2017-01-30 | 2017-01-30 | 2017-01-30 | 2017-01-30 | 2017-01-30 | 2017-01-30 | 2017-01-30 | 2017-01-30 | 2017-01-30
2AI101PI01000-08031 | EOF:Coating/Wrapping | [35 empty] | 2018-06-22 | 2018-06-22 | 2018-06-22 | 2018-06-22 | 2018-06-22 | 2018-06-22 | 2018-06-22 | 2018-06-22 | 2018-06-22 | 2018-06-22 | 2018-06-22
2AI101PI01000-08032 | EOF:Installation of pipes | [23 empty] | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06
2AI101PI01000-08033 | EOF:Alignment/Fit-up | [23 empty] | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06
2AI101PI01000-08035 | EOF:Alignment/Fit-up | [23 empty] | 2017-07-04 | 2017-07-04 | 2017-07-04 | 2017-07-04 | 2017-07-04 | 2017-07-04 | 2017-07-04 | 2017-07-04 | 2017-07-04 | 2017-07-04 | 2017-07-04 | 2017-07-04 | 2017-07-04 | 2017-07-04 | 2017-07-04 | 2017-07-04 | 2017-07-04 | 2017-07-04 | 2017-07-04 | 2017-07-04 | 2017-07-04 | 2017-07-04 | 2017-07-04
2AI101PI01000-08036 | EOF:Welding/Bolting of Pipes | [23 empty] | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07
2AI101PI01000-08037 | EOF:Welding/Bolting of Pipes | [23 empty] | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07
2AI101PI01000-08039 | EOF:NDE/PWHT/QC Checks of Pipes | [23 empty] | 2017-06-08 | 2017-06-08 | 2017-06-08 | 2017-06-08 | 2017-06-08 | 2017-06-08 | 2017-06-08 | 2017-06-08 | 2017-06-08 | 2017-06-08 | 2017-06-08 | 2017-06-08 | 2017-06-08 | 2017-06-08 | 2017-06-08 | 2017-06-08 | 2017-06-08 | 2017-06-08 | 2017-06-08 | 2017-06-08 | 2017-06-08 | 2017-06-08 | 2017-06-08
2AI101PI01000-08040 | EOF:Installation of pipes | [35 empty] | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26
2AI101PI01000-08041 | EOF:Coating/Wrapping | [27 empty] | 2017-10-25 | 2017-10-25 | 2017-10-25 | 2017-10-25 | 2017-10-25 | 2017-10-25 | 2017-10-25 | 2017-10-25 | 2017-10-25 | 2017-10-25 | 2017-10-25 | 2017-10-25 | 2017-10-25 | 2017-10-25 | 2017-10-25 | 2017-10-25 | 2017-10-25 | 2017-10-25 | 2017-10-25
2AI101PI01000-08043 | EOF:Installation of pipes | [23 empty] | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19
2AI101PI01000-08045 | EOF:Alignment/Fit-up | [35 empty] | 2018-06-21 | 2018-06-21 | 2018-06-21 | 2018-06-21 | 2018-06-21 | 2018-06-21 | 2018-06-21 | 2018-06-21 | 2018-06-21 | 2018-06-21 | 2018-06-21
2AI101PI01000-08046 | EOF:Welding/Bolting of Pipes | [35 empty] | 2018-06-21 | 2018-06-21 | 2018-06-21 | 2018-06-21 | 2018-06-21 | 2018-06-21 | 2018-06-21 | 2018-06-21 | 2018-06-21 | 2018-06-21 | 2018-06-21
2AI101PI01000-08047 | EOF:Alignment/Fit-up | [23 empty] | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05
2AI101PI01000-08049 | EOF:Welding/Bolting of Pipes | [23 empty] | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05
2AI101PI01000-08050 | EOF:NDE/PWHT/QC Checks of Pipes | [23 empty] | 2017-06-05: 2018-10-11; 2017-06-05: 2018-10-11; 2017-06-05: 2018-10-11; 2017-06-05: 2018-10-11; 2017-06-05: 2018-10-11; 2017-06-05: 2018-10-11; 2017-06-05: 2018-10-11
2AI101PI01000-08051 | EOF:NDE/PWHT/QC Checks of Pipes | [23 empty] | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05
2AI101PI01000-08053 | EOF:Coating/Wrapping | [27 empty] | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06
2AI101PI01000-08055 | EOF:NDE/PWHT/QC Checks of Pipes | [23 empty] | 2017-07-12 | 2017-07-12 | 2017-07-12 | 2017-07-12 | 2017-07-12 | 2017-07-12 | 2017-07-12 | 2017-07-12 | 2017-07-12 | 2017-07-12 | 2017-07-12 | 2017-07-12 | 2017-07-12 | 2017-07-12 | 2017-07-12 | 2017-07-12 | 2017-07-12 | 2017-07-12 | 2017-07-12 | 2017-07-12 | 2017-07-12 | 2017-07-12 | 2017-07-12
2AI101PI01000-08056 | EOF:Coating/Wrapping | [33 empty] | 2018-04-17 | 2018-04-17 | 2018-04-17 | 2018-04-17 | 2018-04-17 | 2018-04-17 | 2018-04-17 | 2018-04-17 | 2018-04-17 | 2018-04-17 | 2018-04-17 | 2018-04-17 | 2018-04-17
2AI101PI01000-08061 | EOF:Installation of pipes | [27 empty] | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02
2AI101PI01000-08062 | EOF:Alignment/Fit-up | [23 empty] | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05
2AI101PI01000-08063 | EOF:Welding/Bolting of Pipes | [23 empty] | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05
2AI101PI01000-08067 | EOF:NDE/PWHT/QC Checks of Pipes | [23 empty] | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05
2AI101PI01000-08069 | EOF:Coating/Wrapping | [29 empty] | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01
2AI101PI01000-08071 | EOF:Installation of pipes | [27 empty] | 2017-09-23 | 2017-09-23 | 2017-09-23 | 2017-09-23 | 2017-09-23 | 2017-09-23 | 2017-09-23 | 2017-09-23 | 2017-09-23 | 2017-09-23 | 2017-09-23 | 2017-09-23 | 2017-09-23 | 2017-09-23 | 2017-09-23 | 2017-09-23 | 2017-09-23 | 2017-09-23 | 2017-09-23
2AI101PI01000-08072 | EOF:Alignment/Fit-up | [23 empty] | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05
2AI101PI01000-08073 | EOF:Welding/Bolting of Pipes | [23 empty] | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05
2AI101PI01000-08075 | EOF:Installation of pipes | [27 empty] | 2017-09-23 | 2017-09-23 | 2017-09-23 | 2017-09-23 | 2017-09-23 | 2017-09-23 | 2017-09-23 | 2017-09-23 | 2017-09-23 | 2017-09-23 | 2017-09-23 | 2017-09-23 | 2017-09-23 | 2017-09-23 | 2017-09-23 | 2017-09-23 | 2017-09-23 | 2017-09-23 | 2017-09-23
2AI101PI01000-08077 | EOF:NDE/PWHT/QC Checks of Pipes | [23 empty] | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05
2AI101PI01000-08079 | EOF:Coating/Wrapping | [29 empty] | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01
2AI101PI01000-08080 | EOF:Alignment/Fit-up | [19 empty] | 2017-03-17 | 2017-03-17 | 2017-03-17 | 2017-03-17 | 2017-03-17 | 2017-03-17 | 2017-03-17 | 2017-03-17 | 2017-03-17 | 2017-03-17 | 2017-03-17 | 2017-03-17 | 2017-03-17 | 2017-03-17 | 2017-03-17 | 2017-03-17 | 2017-03-17 | 2017-03-17 | 2017-03-17 | 2017-03-17 | 2017-03-17 | 2017-03-17 | 2017-03-17 | 2017-03-17 | 2017-03-17 | 2017-03-17 | 2017-03-17
2AI101PI01000-08081 | EOF:Welding/Bolting of Pipes | [19 empty] | 2017-03-17 | 2017-03-17 | 2017-03-17 | 2017-03-17 | 2017-03-17 | 2017-03-17 | 2017-03-17 | 2017-03-17 | 2017-03-17 | 2017-03-17 | 2017-03-17 | 2017-03-17 | 2017-03-17 | 2017-03-17 | 2017-03-17 | 2017-03-17 | 2017-03-17 | 2017-03-17 | 2017-03-17 | 2017-03-17 | 2017-03-17 | 2017-03-17 | 2017-03-17 | 2017-03-17 | 2017-03-17 | 2017-03-17 | 2017-03-17
2AI101PI01000-08085 | EOF:NDE/PWHT/QC Checks of Pipes | [19 empty] | 2017-03-20 | 2017-03-20 | 2017-03-20 | 2017-03-20 | 2017-03-20 | 2017-03-20 | 2017-03-20 | 2017-03-20 | 2017-03-20 | 2017-03-20 | 2017-03-20 | 2017-03-20 | 2017-03-20 | 2017-03-20 | 2017-03-20 | 2017-03-20 | 2017-03-20 | 2017-03-20 | 2017-03-20 | 2017-03-20 | 2017-03-20 | 2017-03-20 | 2017-03-20 | 2017-03-20 | 2017-03-20 | 2017-03-20 | 2017-03-20
2AI101PI01000-08086 | EOF:Coating/Wrapping | [33 empty] | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18
2AI101PI01000-08090 | EOF:Laying of Piping Spools | [29 empty] | 2017-12-21 | 2017-12-21 | 2017-12-21 | 2017-12-21 | 2017-12-21 | 2017-12-21 | 2017-12-21 | 2017-12-21 | 2017-12-21 | 2017-12-21 | 2017-12-21 | 2017-12-21 | 2017-12-21 | 2017-12-21 | 2017-12-21 | 2017-12-21 | 2017-12-21
2AI101PI01000-08095 | EOF:Jointing/Fusion Welding | [29 empty] | 2017-11-28 | 2017-11-28 | 2017-11-28 | 2017-11-28 | 2017-11-28 | 2017-11-28 | 2017-11-28 | 2017-11-28 | 2017-11-28 | 2017-11-28 | 2017-11-28 | 2017-11-28 | 2017-11-28 | 2017-11-28 | 2017-11-28 | 2017-11-28 | 2017-11-28
2AI101PI01000-08100 | EOF:NDE/QC Checks of Pipes | [33 empty] | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02
2AI101PI01000-08105 | EOF:Installation of pipes | [23 empty] | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27
2AI101PI01000-08110 | EOF:Alignment/Fit-up | [21 empty] | 2017-05-03 | 2017-05-03 | 2017-05-03 | 2017-05-03 | 2017-05-03 | 2017-05-03 | 2017-05-03 | 2017-05-03 | 2017-05-03 | 2017-05-03 | 2017-05-03 | 2017-05-03 | 2017-05-03 | 2017-05-03 | 2017-05-03 | 2017-05-03 | 2017-05-03 | 2017-05-03 | 2017-05-03 | 2017-05-03 | 2017-05-03 | 2017-05-03 | 2017-05-03 | 2017-05-03 | 2017-05-03
2AI101PI01000-08111 | EOF:Welding/Bolting of Pipes | [21 empty] | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04
2AI101PI01000-08115 | EOF:NDE/PWHT/QC Checks of Pipes | [23 empty] | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27
2AI101PI01000-08116 | EOF:Coating/Wrapping | [23 empty] | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17
2AI101PI01000-08120 | EOF:Installation of pipes | [23 empty] | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06
2AI101PI01000-08125 | EOF:Alignment/Fit-up | [21 empty] | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20
2AI101PI01000-08126 | EOF:Welding/Bolting of Pipes | [21 empty] | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20
2AI101PI01000-08130 | EOF:NDE/PWHT/QC Checks of Pipes | [23 empty] | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07
2AI101PI01000-08131 | EOF:Coating/Wrapping | [27 empty] | 2017-10-15 | 2017-10-15 | 2017-10-15 | 2017-10-15 | 2017-10-15 | 2017-10-15 | 2017-10-15 | 2017-10-15 | 2017-10-15 | 2017-10-15 | 2017-10-15 | 2017-10-15 | 2017-10-15 | 2017-10-15 | 2017-10-15 | 2017-10-15 | 2017-10-15 | 2017-10-15 | 2017-10-15
2AI101PI01000-08135 | EOF:Laying of Piping Spools | [29 empty] | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01
2AI101PI01000-08140 | EOF:Jointing/Fusion Welding | [29 empty] | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01
2AI101PI01000-08145 | EOF:NDE/QC Checks of Pipes | [29 empty] | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01
2AI101PI01000-08150 | EOF:Installation of pipes | [21 empty] | 2017-04-22 | 2017-04-22 | 2017-04-22 | 2017-04-22 | 2017-04-22 | 2017-04-22 | 2017-04-22 | 2017-04-22 | 2017-04-22 | 2017-04-22 | 2017-04-22 | 2017-04-22 | 2017-04-22 | 2017-04-22 | 2017-04-22 | 2017-04-22 | 2017-04-22 | 2017-04-22 | 2017-04-22 | 2017-04-22 | 2017-04-22 | 2017-04-22 | 2017-04-22 | 2017-04-22 | 2017-04-22
2AI101PI01000-08155 | EOF:Alignment/Fit-up | [21 empty] | 2017-04-25 | 2017-04-25 | 2017-04-25 | 2017-04-25 | 2017-04-25 | 2017-04-25 | 2017-04-25 | 2017-04-25 | 2017-04-25 | 2017-04-25 | 2017-04-25 | 2017-04-25 | 2017-04-25 | 2017-04-25 | 2017-04-25 | 2017-04-25 | 2017-04-25 | 2017-04-25 | 2017-04-25 | 2017-04-25 | 2017-04-25 | 2017-04-25 | 2017-04-25 | 2017-04-25 | 2017-04-25
2AI101PI01000-08156 | EOF:Welding/Bolting of Pipes | [21 empty] | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09
2AI101PI01000-08160 | EOF:NDE/PWHT/QC Checks of Pipes | [23 empty] | 2017-06-25 | 2017-06-25 | 2017-06-25 | 2017-06-25 | 2017-06-25 | 2017-06-25 | 2017-06-25 | 2017-06-25 | 2017-06-25 | 2017-06-25 | 2017-06-25 | 2017-06-25 | 2017-06-25 | 2017-06-25 | 2017-06-25 | 2017-06-25 | 2017-06-25 | 2017-06-25 | 2017-06-25 | 2017-06-25 | 2017-06-25 | 2017-06-25 | 2017-06-25
2AI101PI01000-08161 | EOF:Coating/Wrapping | [33 empty] | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15
2AI101PI01000-08165 | EOF:Installation of pipes | [27 empty] | 2017-11-04 | 2017-11-04 | 2017-11-04 | 2017-11-04 | 2017-11-04 | 2017-11-04 | 2017-11-04 | 2017-11-04 | 2017-11-04 | 2017-11-04 | 2017-11-04 | 2017-11-04 | 2017-11-04 | 2017-11-04 | 2017-11-04 | 2017-11-04 | 2017-11-04 | 2017-11-04 | 2017-11-04
2AI101PI01000-08170 | EOF:Alignment/Fit-up | [23 empty] | 2017-06-25 | 2017-06-25 | 2017-06-25 | 2017-06-25 | 2017-06-25 | 2017-06-25 | 2017-06-25 | 2017-06-25 | 2017-06-25 | 2017-06-25 | 2017-06-25 | 2017-06-25 | 2017-06-25 | 2017-06-25 | 2017-06-25 | 2017-06-25 | 2017-06-25 | 2017-06-25 | 2017-06-25 | 2017-06-25 | 2017-06-25 | 2017-06-25 | 2017-06-25
2AI101PI01000-08171 | EOF:Welding/Bolting of Pipes | [23 empty] | 2017-06-25 | 2017-06-25 | 2017-06-25 | 2017-06-25 | 2017-06-25 | 2017-06-25 | 2017-06-25 | 2017-06-25 | 2017-06-25 | 2017-06-25 | 2017-06-25 | 2017-06-25 | 2017-06-25 | 2017-06-25 | 2017-06-25 | 2017-06-25 | 2017-06-25 | 2017-06-25 | 2017-06-25 | 2017-06-25 | 2017-06-25 | 2017-06-25 | 2017-06-25
2AI101PI01000-08175 | EOF:NDE/PWHT/QC Checks of Pipes | [23 empty] | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07
2AI101PI01000-08176 | EOF:Coating/Wrapping | [35 empty] | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26
2AI101PI01000-08180 | EOF:Installation of pipes | [27 empty] | 2017-10-28 | 2017-10-28 | 2017-10-28 | 2017-10-28 | 2017-10-28 | 2017-10-28 | 2017-10-28 | 2017-10-28 | 2017-10-28 | 2017-10-28 | 2017-10-28 | 2017-10-28 | 2017-10-28 | 2017-10-28 | 2017-10-28 | 2017-10-28 | 2017-10-28 | 2017-10-28 | 2017-10-28
2AI101PI01000-08185 | EOF:Alignment/Fit-up | [23 empty] | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14
2AI101PI01000-08186 | EOF:Welding/Bolting of Pipes | [23 empty] | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14
2AI101PI01000-08190 | EOF:NDE/PWHT/QC Checks of Pipes | [25 empty] | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29
2AI101PI01000-08191 | EOF:Coating/Wrapping | [35 empty] | 2018-06-26 | 2018-06-26 | 2018-06-26 | 2018-06-26 | 2018-06-26 | 2018-06-26 | 2018-06-26 | 2018-06-26 | 2018-06-26 | 2018-06-26 | 2018-06-26
2AI101PI01000-08195 | EOF:Installation of pipes | [27 empty] | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02
2AI101PI01000-08200 | EOF:Alignment/Fit-up | [23 empty] | 2017-07-15 | 2017-07-15 | 2017-07-15 | 2017-07-15 | 2017-07-15 | 2017-07-15 | 2017-07-15 | 2017-07-15 | 2017-07-15 | 2017-07-15 | 2017-07-15 | 2017-07-15 | 2017-07-15 | 2017-07-15 | 2017-07-15 | 2017-07-15 | 2017-07-15 | 2017-07-15 | 2017-07-15 | 2017-07-15 | 2017-07-15 | 2017-07-15 | 2017-07-15
2AI101PI01000-08201 | EOF:Welding/Bolting of Pipes | [23 empty] | 2017-07-16 | 2017-07-16 | 2017-07-16 | 2017-07-16 | 2017-07-16 | 2017-07-16 | 2017-07-16 | 2017-07-16 | 2017-07-16 | 2017-07-16 | 2017-07-16 | 2017-07-16 | 2017-07-16 | 2017-07-16 | 2017-07-16 | 2017-07-16 | 2017-07-16 | 2017-07-16 | 2017-07-16 | 2017-07-16 | 2017-07-16 | 2017-07-16 | 2017-07-16
2AI101PI01000-08205 | EOF:NDE/PWHT/QC Checks of Pipes | [25 empty] | 2017-08-06 | 2017-08-06 | 2017-08-06 | 2017-08-06 | 2017-08-06 | 2017-08-06 | 2017-08-06 | 2017-08-06 | 2017-08-06 | 2017-08-06 | 2017-08-06 | 2017-08-06 | 2017-08-06 | 2017-08-06 | 2017-08-06 | 2017-08-06 | 2017-08-06 | 2017-08-06 | 2017-08-06 | 2017-08-06 | 2017-08-06
2AI101PI01000-08206 | EOF:Coating/Wrapping | [35 empty] | 2018-07-12 | 2018-07-12 | 2018-07-12 | 2018-07-12 | 2018-07-12 | 2018-07-12 | 2018-07-12 | 2018-07-12 | 2018-07-12 | 2018-07-12 | 2018-07-12
2AI101PI01000-08210 | EOF:Installation of pipes | [19 empty] | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08
2AI101PI01000-08215 | EOF:Alignment/Fit-up | [19 empty] | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09
2AI101PI01000-08216 | EOF:Welding/Bolting of Pipes | [19 empty] | 2017-03-11 | 2017-03-11 | 2017-03-11 | 2017-03-11 | 2017-03-11 | 2017-03-11 | 2017-03-11 | 2017-03-11 | 2017-03-11 | 2017-03-11 | 2017-03-11 | 2017-03-11 | 2017-03-11 | 2017-03-11 | 2017-03-11 | 2017-03-11 | 2017-03-11 | 2017-03-11 | 2017-03-11 | 2017-03-11 | 2017-03-11 | 2017-03-11 | 2017-03-11 | 2017-03-11 | 2017-03-11 | 2017-03-11 | 2017-03-11
2AI101PI01000-08220 | EOF:NDE/PWHT/QC Checks of Pipes | [21 empty] | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30
2AI101PI01000-08221 | EOF:Coating/Wrapping | [35 empty] | 2018-05-28 | 2018-05-28 | 2018-05-28 | 2018-05-28 | 2018-05-28 | 2018-05-28 | 2018-05-28 | 2018-05-28 | 2018-05-28 | 2018-05-28 | 2018-05-28
2AI101PI01000-08225 | EOF:Installation of pipes | [27 empty] | 2017-09-23 | 2017-09-23 | 2017-09-23 | 2017-09-23 | 2017-09-23 | 2017-09-23 | 2017-09-23 | 2017-09-23 | 2017-09-23 | 2017-09-23 | 2017-09-23 | 2017-09-23 | 2017-09-23 | 2017-09-23 | 2017-09-23 | 2017-09-23 | 2017-09-23 | 2017-09-23 | 2017-09-23
2AI101PI01000-08230 | EOF:Alignment/Fit-up | [21 empty] | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29
2AI101PI01000-08231 | EOF:Welding/Bolting of Pipes | [21 empty] | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29
2AI101PI01000-08235 | EOF:NDE/PWHT/QC Checks of Pipes | [21 empty] | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30
2AI101PI01000-08236 | EOF:Coating/Wrapping | [35 empty] | 2018-05-25 | 2018-05-25 | 2018-05-25 | 2018-05-25 | 2018-05-25 | 2018-05-25 | 2018-05-25 | 2018-05-25 | 2018-05-25 | 2018-05-25 | 2018-05-25
2AI101PI01000-08240 | EOF:Installation of pipes | [27 empty] | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01
2AI101PI01000-08245 | EOF:Alignment/Fit-up | [21 empty] | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25
2AI101PI01000-08246 | EOF:Welding/Bolting of Pipes | [21 empty] | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25
2AI101PI01000-08250 | EOF:NDE/PWHT/QC Checks of Pipes | [21 empty] | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29
2AI101PI01000-08251 | EOF:Coating/Wrapping | [35 empty] | 2018-06-29 | 2018-06-29 | 2018-06-29 | 2018-06-29 | 2018-06-29 | 2018-06-29 | 2018-06-29 | 2018-06-29 | 2018-06-29 | 2018-06-29 | 2018-06-29
2AI101PI01000-08255 | EOF:Installation of pipes | [25 empty] | 2017-08-29 | 2017-08-29 | 2017-08-29 | 2017-08-29 | 2017-08-29 | 2017-08-29 | 2017-08-29 | 2017-08-29 | 2017-08-29 | 2017-08-29 | 2017-08-29 | 2017-08-29 | 2017-08-29 | 2017-08-29 | 2017-08-29 | 2017-08-29 | 2017-08-29 | 2017-08-29 | 2017-08-29 | 2017-08-29 | 2017-08-29
2AI101PI01000-08260 | EOF:Alignment/Fit-up | [21 empty] | 2017-03-26 | 2017-03-26 | 2017-03-26 | 2017-03-26 | 2017-03-26 | 2017-03-26 | 2017-03-26 | 2017-03-26 | 2017-03-26 | 2017-03-26 | 2017-03-26 | 2017-03-26 | 2017-03-26 | 2017-03-26 | 2017-03-26 | 2017-03-26 | 2017-03-26 | 2017-03-26 | 2017-03-26 | 2017-03-26 | 2017-03-26 | 2017-03-26 | 2017-03-26 | 2017-03-26 | 2017-03-26
2AI101PI01000-08261 | EOF:Welding/Bolting of Pipes | [21 empty] | 2017-03-26 | 2017-03-26 | 2017-03-26 | 2017-03-26 | 2017-03-26 | 2017-03-26 | 2017-03-26 | 2017-03-26 | 2017-03-26 | 2017-03-26 | 2017-03-26 | 2017-03-26 | 2017-03-26 | 2017-03-26 | 2017-03-26 | 2017-03-26 | 2017-03-26 | 2017-03-26 | 2017-03-26 | 2017-03-26 | 2017-03-26 | 2017-03-26 | 2017-03-26 | 2017-03-26 | 2017-03-26
2AI101PI01000-08265 | EOF:NDE/PWHT/QC Checks of Pipes | [21 empty] | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29
2AI101PI01000-08266 | EOF:Coating/Wrapping | [35 empty] | 2018-06-29 | 2018-06-29 | 2018-06-29 | 2018-06-29 | 2018-06-29 | 2018-06-29 | 2018-06-29 | 2018-06-29 | 2018-06-29 | 2018-06-29 | 2018-06-29
2AI101PI01000-08270 | EOF:Installation of pipes | [23 empty] | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06
2AI101PI01000-08275 | EOF:Alignment/Fit-up | [21 empty] | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12
2AI101PI01000-08276 | EOF:Welding/Bolting of Pipes | [21 empty] | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12 | 2017-05-12
2AI101PI01000-08280 | EOF:NDE/PWHT/QC Checks of Pipes | [23 empty] | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07
2AI101PI01000-08281 | EOF:Coating/Wrapping | [27 empty] | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06
2AI101PI01000-08285 | EOF:Installation of pipes | [23 empty] | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24
2AI101PI01000-08290 | EOF:Alignment/Fit-up | [21 empty] | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08
2AI101PI01000-08291 | EOF:Welding/Bolting of Pipes | [21 empty] | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08
2AI101PI01000-08295 | EOF:NDE/PWHT/QC Checks of Pipes | [23 empty] | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05
2AI101PI01000-08296 | EOF:Coating/Wrapping | [29 empty] | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01
2AI101PI01000-08300 | EOF:Installation of pipes | [23 empty] | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25
2AI101PI01000-08305 | EOF:Alignment/Fit-up | [21 empty] | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08
2AI101PI01000-08306 | EOF:Welding/Bolting of Pipes | [21 empty] | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09
2AI101PI01000-08310 | EOF:NDE/PWHT/QC Checks of Pipes | [23 empty] | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05
2AI101PI01000-08311 | EOF:Coating/Wrapping | [29 empty] | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01
2AI101PI01000-08315 | EOF:Installation of pipes | [19 empty] | 2017-03-22 | 2017-03-22 | 2017-03-22 | 2017-03-22 | 2017-03-22 | 2017-03-22 | 2017-03-22 | 2017-03-22 | 2017-03-22 | 2017-03-22 | 2017-03-22 | 2017-03-22 | 2017-03-22 | 2017-03-22 | 2017-03-22 | 2017-03-22 | 2017-03-22 | 2017-03-22 | 2017-03-22 | 2017-03-22 | 2017-03-22 | 2017-03-22 | 2017-03-22 | 2017-03-22 | 2017-03-22 | 2017-03-22 | 2017-03-22
2AI101PI01000-08320 | EOF:Alignment/Fit-up | [21 empty] | 2017-04-04 | 2017-04-04 | 2017-04-04 | 2017-04-04 | 2017-04-04 | 2017-04-04 | 2017-04-04 | 2017-04-04 | 2017-04-04 | 2017-04-04 | 2017-04-04 | 2017-04-04 | 2017-04-04 | 2017-04-04 | 2017-04-04 | 2017-04-04 | 2017-04-04 | 2017-04-04 | 2017-04-04 | 2017-04-04 | 2017-04-04 | 2017-04-04 | 2017-04-04 | 2017-04-04 | 2017-04-04
2AI101PI01000-08321 | EOF:Welding/Bolting of Pipes | [21 empty] | 2017-04-04 | 2017-04-04 | 2017-04-04 | 2017-04-04 | 2017-04-04 | 2017-04-04 | 2017-04-04 | 2017-04-04 | 2017-04-04 | 2017-04-04 | 2017-04-04 | 2017-04-04 | 2017-04-04 | 2017-04-04 | 2017-04-04 | 2017-04-04 | 2017-04-04 | 2017-04-04 | 2017-04-04 | 2017-04-04 | 2017-04-04 | 2017-04-04 | 2017-04-04 | 2017-04-04 | 2017-04-04
2AI101PI01000-08325 | EOF:NDE/PWHT/QC Checks of Pipes | [21 empty] | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06
2AI101PI01000-08326 | EOF:Coating/Wrapping | [23 empty] | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06 | 2017-06-06
2AI101PI01000-08925 | EOF:Installation of pipes | [19 empty] | 2017-02-25 | 2017-02-25 | 2017-02-25 | 2017-02-25 | 2017-02-25 | 2017-02-25 | 2017-02-25 | 2017-02-25 | 2017-02-25 | 2017-02-25 | 2017-02-25 | 2017-02-25 | 2017-02-25 | 2017-02-25 | 2017-02-25 | 2017-02-25 | 2017-02-25 | 2017-02-25 | 2017-02-25 | 2017-02-25 | 2017-02-25 | 2017-02-25 | 2017-02-25 | 2017-02-25 | 2017-02-25 | 2017-02-25 | 2017-02-25
2AI101PI01000-08930 | EOF:Alignment/Fit-up | [19 empty] | 2017-02-26 | 2017-02-26 | 2017-02-26 | 2017-02-26 | 2017-02-26 | 2017-02-26 | 2017-02-26 | 2017-02-26 | 2017-02-26 | 2017-02-26 | 2017-02-26 | 2017-02-26 | 2017-02-26 | 2017-02-26 | 2017-02-26 | 2017-02-26 | 2017-02-26 | 2017-02-26 | 2017-02-26 | 2017-02-26 | 2017-02-26 | 2017-02-26 | 2017-02-26 | 2017-02-26 | 2017-02-26 | 2017-02-26 | 2017-02-26
2AI101PI01000-08931 | EOF:Welding/Bolting of Pipes | [19 empty] | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27
2AI101PI01000-08935 | EOF:NDE/PWHT/QC Checks of Pipes | [19 empty] | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28
2AI101PI01000-08936 | EOF:Coating/Wrapping | [35 empty] | 2018-06-25 | 2018-06-25 | 2018-06-25 | 2018-06-25 | 2018-06-25 | 2018-06-25 | 2018-06-25 | 2018-06-25 | 2018-06-25 | 2018-06-25 | 2018-06-25
2AI101PI01100 | EOF: AG Piping works | [29 empty] | 2017-12-11 | 2017-12-11 | 2017-12-11 | 2017-12-11 | 2017-12-11 | 2017-12-11 | 2017-12-11 | 2017-12-11 | 2017-12-11 | 2017-12-11 | 2017-12-11 | 2017-12-11 | 2017-12-11 | 2017-12-11 | 2017-12-11 | 2017-12-11 | 2017-12-11
2AI101PI01100-08000 | EOF: AG Piping works for Non Metallic | [33 empty] | 2018-04-17 | 2018-04-17 | 2018-04-17 | 2018-04-17 | 2018-04-17 | 2018-04-17 | 2018-04-17 | 2018-04-17 | 2018-04-17 | 2018-04-17 | 2018-04-17 | 2018-04-17 | 2018-04-17
2AI101PI01100-08001 | EOF:Installation of pipes | [35 empty] | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26
2AI101PI01100-08005 | EOF: AG Piping works Metallic (CS/LTCS) | [29 empty] | 2017-12-11 | 2017-12-11 | 2017-12-11 | 2017-12-11 | 2017-12-11 | 2017-12-11 | 2017-12-11 | 2017-12-11 | 2017-12-11 | 2017-12-11 | 2017-12-11 | 2017-12-11 | 2017-12-11 | 2017-12-11 | 2017-12-11 | 2017-12-11 | 2017-12-11
2AI101PI01100-08006 | EOF: Jointing/Fusion welding | [33 empty] | 2018-04-17 | 2018-04-17 | 2018-04-17 | 2018-04-17 | 2018-04-17 | 2018-04-17 | 2018-04-17 | 2018-04-17 | 2018-04-17 | 2018-04-17 | 2018-04-17 | 2018-04-17 | 2018-04-17
2AI101PI01100-08010 | EOF: AG Piping works for Metallic (SS/SDSS) | [35 empty] | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23
2AI101PI01100-08011 | EOF:NDE/PWHT/QC Checks of Pipes | [37 empty] | 2018-07-28 | 2018-07-28 | 2018-07-28 | 2018-07-28 | 2018-07-28 | 2018-07-28 | 2018-07-28 | 2018-07-28 | 2018-07-28
2AI101PI01100-08016 | EOF:Install Permanent Supporting for Pipes | [39 empty] | 2018-09-29 | 2018-09-29 | 2018-09-29 | 2018-09-29 | 2018-09-29 | 2018-09-29 | 2018-09-29
2AI101PI01100-08020 | EOF:Install piping valves | [39 empty] | 2018-09-29 | 2018-09-29 | 2018-09-29 | 2018-09-29 | 2018-09-29 | 2018-09-29 | 2018-09-29
2AI101PI01100-08025 | EOF:Installation of pipes | [37 empty] | 2018-07-28: 2019-02-04; 2018-07-28: 2019-02-04; 2018-07-28: 2019-02-04
2AI101PI01100-08030 | EOF:Alignment/Fit-up | [37 empty] | 2018-07-28: 2019-02-04; 2018-07-28: 2019-02-04; 2018-07-28: 2019-02-04
2AI101PI01100-08031 | EOF:Welding/Bolting of Pipes | [37 empty] | 2018-07-28: 2019-02-04; 2018-07-28: 2019-02-04; 2018-07-28: 2019-02-04
2AI101PI01100-08035 | EOF:NDE/PWHT/QC Checks of Pipes | [37 empty] | 2018-07-28: 2019-02-04; 2018-07-28: 2019-02-04; 2018-07-28: 2019-02-04
2AI101PI01100-08040 | EOF:Install Permanent Supporting for Pipes | [37 empty] | 2018-07-28: 2019-02-04; 2018-07-28: 2019-02-04; 2018-07-28: 2019-02-04
2AI101PI01100-08045 | EOF:Install piping valves | [37 empty] | 2018-07-28: 2019-02-04; 2018-07-28: 2019-02-04; 2018-07-28: 2019-02-04
2AI101PI01100-08050 | EOF:Installation of pipes | [39 empty] | 2018-10-02 | 2018-10-02 | 2018-10-02 | 2018-10-02 | 2018-10-02 | 2018-10-02 | 2018-10-02
2AI101PI01100-08055 | EOF:Alignment/Fit-up | [35 empty] | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23
2AI101PI01100-08056 | EOF:Welding/Bolting of Pipes | [35 empty] | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23
2AI101PI01100-08060 | EOF:NDE/PWHT/QC Checks of Pipes | [37 empty] | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03
2AI101PI01100-08065 | EOF:Install Permanent Supporting for Pipes | [39 empty] | 2018-10-08 | 2018-10-08 | 2018-10-08 | 2018-10-08 | 2018-10-08 | 2018-10-08 | 2018-10-08
2AI101PI01100-08070 | EOF:Install piping valves | [39 empty] | 2018-10-08 | 2018-10-08 | 2018-10-08 | 2018-10-08 | 2018-10-08 | 2018-10-08 | 2018-10-08
2AI101PI01100-08100 | EOF:Installation of pipes | [39 empty] | 2018-09-29 | 2018-09-29 | 2018-09-29 | 2018-09-29 | 2018-09-29 | 2018-09-29 | 2018-09-29
2AI101PI01100-08105 | EOF:Alignment/Fit-up | [39 empty] | 2018-10-04 | 2018-10-04 | 2018-10-04 | 2018-10-04 | 2018-10-04 | 2018-10-04 | 2018-10-04
2AI101PI01100-08106 | EOF:Welding/Bolting of Pipes | [39 empty] | 2018-10-05 | 2018-10-05 | 2018-10-05 | 2018-10-05 | 2018-10-05 | 2018-10-05 | 2018-10-05
2AI101PI01100-08110 | EOF:NDE/PWHT/QC Checks of Pipes | [37 empty] | 2018-09-03: 2018-12-08; 2018-09-03: 2018-12-08; 2018-09-03: 2018-12-08; 2018-09-03: 2018-12-08; 2018-09-03: 2018-12-08
2AI101PI01100-08115 | EOF:Install Permanent Supporting for Pipes | [39 empty] | 2018-09-29 | 2018-09-29 | 2018-09-29 | 2018-09-29 | 2018-09-29 | 2018-09-29 | 2018-09-29
2AI101PI01100-08120 | EOF:Install piping valves | [37 empty] | 2018-09-03: 2018-12-10; 2018-09-03: 2018-12-10; 2018-09-03: 2018-12-10; 2018-09-03: 2018-12-10; 2018-09-03: 2018-12-10
2AI101PI01100-08125 | EOF:Installation of pipes | [37 empty] | 2018-09-08 | 2018-09-08 | 2018-09-08 | 2018-09-08 | 2018-09-08 | 2018-09-08 | 2018-09-08 | 2018-09-08 | 2018-09-08
2AI101PI01100-08130 | EOF:Alignment/Fit-up | [37 empty] | 2018-09-08 | 2018-09-08 | 2018-09-08 | 2018-09-08 | 2018-09-08 | 2018-09-08 | 2018-09-08 | 2018-09-08 | 2018-09-08
2AI101PI01100-08131 | EOF:Welding/Bolting of Pipes | [37 empty] | 2018-09-09 | 2018-09-09 | 2018-09-09 | 2018-09-09 | 2018-09-09 | 2018-09-09 | 2018-09-09 | 2018-09-09 | 2018-09-09
2AI101PI01100-08135 | EOF:NDE/PWHT/QC Checks of Pipes | [37 empty] | 2018-09-09: 2018-12-10; 2018-09-09: 2018-12-10; 2018-09-09: 2018-12-10; 2018-09-09: 2018-12-10; 2018-09-09: 2018-12-10
2AI101PI01100-08140 | EOF:Install Permanent Supporting for Pipes | [37 empty] | 2018-09-10 | 2018-09-10 | 2018-09-10 | 2018-09-10 | 2018-09-10 | 2018-09-10 | 2018-09-10 | 2018-09-10 | 2018-09-10
2AI101PI01100-08145 | EOF:Install piping valves | [37 empty] | 2018-09-10: 2018-12-03; 2018-09-10: 2018-12-03; 2018-09-10: 2018-12-03; 2018-09-10: 2018-12-03; 2018-09-10: 2018-12-03
2AI101PI01100-08150 | EOF:Installation of pipes | [39 empty] | 2018-10-28 | 2018-10-28 | 2018-10-28 | 2018-10-28 | 2018-10-28 | 2018-10-28 | 2018-10-28
2AI101PI01100-08155 | EOF:Alignment/Fit-up | [39 empty] | 2018-11-04 | 2018-11-04 | 2018-11-04 | 2018-11-04 | 2018-11-04 | 2018-11-04 | 2018-11-04
2AI101PI01100-08156 | EOF:Welding/Bolting of Pipes | [39 empty] | 2018-11-10 | 2018-11-10 | 2018-11-10 | 2018-11-10 | 2018-11-10 | 2018-11-10 | 2018-11-10
2AI101PI01100-08160 | EOF:NDE/PWHT/QC Checks of Pipes | [39 empty] | 2018-11-12 | 2018-11-12 | 2018-11-12 | 2018-11-12 | 2018-11-12 | 2018-11-12 | 2018-11-12
2AI101PI01100-08165 | EOF:Install Permanent Supporting for Pipes | [39 empty] | 2018-10-28 | 2018-10-28 | 2018-10-28 | 2018-10-28 | 2018-10-28 | 2018-10-28 | 2018-10-28
2AI101PI01100-08170 | EOF:Install piping valves | [37 empty] | 2018-09-10: 2019-01-07; 2018-09-10: 2019-01-07; 2018-09-10: 2019-01-07; 2018-09-10: 2019-01-07; 2018-09-10: 2019-01-07
2AI101PI01100-08175 | EOF:Installation of pipes | [37 empty] | 2018-09-10: 2018-12-04; 2018-09-10: 2018-12-04; 2018-09-10: 2018-12-04; 2018-09-10: 2018-12-04; 2018-09-10: 2018-12-04
2AI101PI01100-08180 | EOF:Alignment/Fit-up | [37 empty] | 2018-09-10: 2018-12-06; 2018-09-10: 2018-12-06; 2018-09-10: 2018-12-06; 2018-09-10: 2018-12-06; 2018-09-10: 2018-12-06
2AI101PI01100-08181 | EOF:Welding/Bolting of Pipes | [37 empty] | 2018-09-10: 2018-12-06; 2018-09-10: 2018-12-06; 2018-09-10: 2018-12-06; 2018-09-10: 2018-12-06; 2018-09-10: 2018-12-06
2AI101PI01100-08185 | EOF:NDE/PWHT/QC Checks of Pipes | [37 empty] | 2018-09-10: 2018-12-09; 2018-09-10: 2018-12-09; 2018-09-10: 2018-12-09; 2018-09-10: 2018-12-09; 2018-09-10: 2018-12-09
2AI101PI01100-08190 | EOF:Install Permanent Supporting for Pipes | [37 empty] | 2018-09-10: 2018-12-01; 2018-09-10: 2018-12-01; 2018-09-10: 2018-12-01; 2018-09-10: 2018-12-01; 2018-09-10: 2018-12-01
2AI101PI01100-08195 | EOF:Install piping valves | [37 empty] | 2018-09-10: 2019-01-07; 2018-09-10: 2019-01-07; 2018-09-10: 2019-01-07; 2018-09-10: 2019-01-07; 2018-09-10: 2019-01-07
2AI101PI01100-08200 | EOF:Installation of pipes | [37 empty] | 2018-09-12 | 2018-09-12 | 2018-09-12 | 2018-09-12 | 2018-09-12 | 2018-09-12 | 2018-09-12 | 2018-09-12 | 2018-09-12
2AI101PI01100-08205 | EOF:Alignment/Fit-up | [37 empty] | 2018-09-12 | 2018-09-12 | 2018-09-12 | 2018-09-12 | 2018-09-12 | 2018-09-12 | 2018-09-12 | 2018-09-12 | 2018-09-12
2AI101PI01100-08206 | EOF:Welding/Bolting of Pipes | [37 empty] | 2018-09-14 | 2018-09-14 | 2018-09-14 | 2018-09-14 | 2018-09-14 | 2018-09-14 | 2018-09-14 | 2018-09-14 | 2018-09-14
2AI101PI01100-08210 | EOF:NDE/PWHT/QC Checks of Pipes | [37 empty] | 2018-09-14: 2018-12-13; 2018-09-14: 2018-12-13; 2018-09-14: 2018-12-13; 2018-09-14: 2018-12-13; 2018-09-14: 2018-12-13
2AI101PI01100-08215 | EOF:Install Permanent Supporting for Pipes | [37 empty] | 2018-09-12 | 2018-09-12 | 2018-09-12 | 2018-09-12 | 2018-09-12 | 2018-09-12 | 2018-09-12 | 2018-09-12 | 2018-09-12
2AI101PI01100-08220 | EOF:Install piping valves | [37 empty] | 2018-09-12: 2018-12-03; 2018-09-12: 2018-12-03; 2018-09-12: 2018-12-03; 2018-09-12: 2018-12-03; 2018-09-12: 2018-12-03
2AI101PI01100-08225 | EOF:Installation of pipes | [37 empty] | 2018-08-18 | 2018-08-18 | 2018-08-18 | 2018-08-18 | 2018-08-18 | 2018-08-18 | 2018-08-18 | 2018-08-18 | 2018-08-18
2AI101PI01100-08230 | EOF:Alignment/Fit-up | [37 empty] | 2018-08-19 | 2018-08-19 | 2018-08-19 | 2018-08-19 | 2018-08-19 | 2018-08-19 | 2018-08-19 | 2018-08-19 | 2018-08-19
2AI101PI01100-08231 | EOF:Welding/Bolting of Pipes | [37 empty] | 2018-08-19 | 2018-08-19 | 2018-08-19 | 2018-08-19 | 2018-08-19 | 2018-08-19 | 2018-08-19 | 2018-08-19 | 2018-08-19
2AI101PI01100-08235 | EOF:NDE/PWHT/QC Checks of Pipes | [37 empty] | 2018-09-05 | 2018-09-05 | 2018-09-05 | 2018-09-05 | 2018-09-05 | 2018-09-05 | 2018-09-05 | 2018-09-05 | 2018-09-05
2AI101PI01100-08240 | EOF:Install Permanent Supporting for Pipes | [37 empty] | 2018-08-18 | 2018-08-18 | 2018-08-18 | 2018-08-18 | 2018-08-18 | 2018-08-18 | 2018-08-18 | 2018-08-18 | 2018-08-18
2AI101PI01100-08245 | EOF:Install piping valves | [37 empty] | 2018-08-18: 2018-11-30; 2018-08-18: 2018-11-30; 2018-08-18: 2018-11-30; 2018-08-18: 2018-11-30; 2018-08-18: 2018-11-30
2AI101PI01100-08250 | EOF:Installation of pipes | [39 empty] | 2018-10-24 | 2018-10-24 | 2018-10-24 | 2018-10-24 | 2018-10-24 | 2018-10-24 | 2018-10-24
2AI101PI01100-08255 | EOF:Alignment/Fit-up | [39 empty] | 2018-10-24 | 2018-10-24 | 2018-10-24 | 2018-10-24 | 2018-10-24 | 2018-10-24 | 2018-10-24
2AI101PI01100-08256 | EOF:Welding/Bolting of Pipes | [39 empty] | 2018-10-24 | 2018-10-24 | 2018-10-24 | 2018-10-24 | 2018-10-24 | 2018-10-24 | 2018-10-24
2AI101PI01100-08260 | EOF:NDE/PWHT/QC Checks of Pipes | [37 empty] | 2018-08-18: 2018-11-25; 2018-08-18: 2018-11-25; 2018-08-18: 2018-11-25; 2018-08-18: 2018-11-25; 2018-08-18: 2018-11-25
2AI101PI01100-08265 | EOF:Install Permanent Supporting for Pipes | [39 empty] | 2018-10-10 | 2018-10-10 | 2018-10-10 | 2018-10-10 | 2018-10-10 | 2018-10-10 | 2018-10-10
2AI101PI01100-08270 | EOF:Install piping valves | [37 empty] | 2018-08-18: 2018-12-03; 2018-08-18: 2018-12-03; 2018-08-18: 2018-12-03; 2018-08-18: 2018-12-03; 2018-08-18: 2018-12-03
2AI101PI01100-08275 | EOF:Installation of pipes | [39 empty] | 2018-10-30 | 2018-10-30 | 2018-10-30 | 2018-10-30 | 2018-10-30 | 2018-10-30 | 2018-10-30
2AI101PI01100-08280 | EOF:Alignment/Fit-up | [39 empty] | 2018-10-30 | 2018-10-30 | 2018-10-30 | 2018-10-30 | 2018-10-30 | 2018-10-30 | 2018-10-30
2AI101PI01100-08281 | EOF:Welding/Bolting of Pipes | [39 empty] | 2018-10-30 | 2018-10-30 | 2018-10-30 | 2018-10-30 | 2018-10-30 | 2018-10-30 | 2018-10-30
2AI101PI01100-08285 | EOF:NDE/PWHT/QC Checks of Pipes | [37 empty] | 2018-08-18: 2018-11-24; 2018-08-18: 2018-11-24; 2018-08-18: 2018-11-24; 2018-08-18: 2018-11-24; 2018-08-18: 2018-11-24
2AI101PI01100-08290 | EOF:Install Permanent Supporting for Pipes | [39 empty] | 2018-10-25 | 2018-10-25 | 2018-10-25 | 2018-10-25 | 2018-10-25 | 2018-10-25 | 2018-10-25
2AI101PI01100-08295 | EOF:Install piping valves | [37 empty] | 2018-08-18: 2018-12-03; 2018-08-18: 2018-12-03; 2018-08-18: 2018-12-03; 2018-08-18: 2018-12-03; 2018-08-18: 2018-12-03
2AI101PI01100-08300 | EOF:Installation of pipes | [37 empty] | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03
2AI101PI01100-08305 | EOF:Alignment/Fit-up | [37 empty] | 2018-08-13 | 2018-08-13 | 2018-08-13 | 2018-08-13 | 2018-08-13 | 2018-08-13 | 2018-08-13 | 2018-08-13 | 2018-08-13
2AI101PI01100-08306 | EOF:Welding/Bolting of Pipes | [37 empty] | 2018-08-15 | 2018-08-15 | 2018-08-15 | 2018-08-15 | 2018-08-15 | 2018-08-15 | 2018-08-15 | 2018-08-15 | 2018-08-15
2AI101PI01100-08310 | EOF:NDE/PWHT/QC Checks of Pipes | [39 empty] | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05
2AI101PI01100-08315 | EOF:Install Permanent Supporting for Pipes | [39 empty] | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05
2AI101PI01100-08320 | EOF:Install piping valves | [39 empty] | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05
2AI101PI01100-08325 | EOF:Installation of pipes | [35 empty] | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04
2AI101PI01100-08330 | EOF:Alignment/Fit-up | [35 empty] | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04
2AI101PI01100-08331 | EOF:Welding/Bolting of Pipes | [35 empty] | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04
2AI101PI01100-08335 | EOF:NDE/PWHT/QC Checks of Pipes | [39 empty] | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05
2AI101PI01100-08340 | EOF:Install Permanent Supporting for Pipes | [37 empty] | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03
2AI101PI01100-08345 | EOF:Install piping valves | [37 empty] | 2018-09-01 | 2018-09-01 | 2018-09-01 | 2018-09-01 | 2018-09-01 | 2018-09-01 | 2018-09-01 | 2018-09-01 | 2018-09-01
2AI101PI01100-08350 | EOF:Installation of pipes | [35 empty] | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04
2AI101PI01100-08355 | EOF:Alignment/Fit-up | [35 empty] | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04
2AI101PI01100-08356 | EOF:Welding/Bolting of Pipes | [29 empty] | 2018-01-13 | 2018-01-13 | 2018-01-13 | 2018-01-13 | 2018-01-13 | 2018-01-13 | 2018-01-13 | 2018-01-13 | 2018-01-13 | 2018-01-13 | 2018-01-13 | 2018-01-13 | 2018-01-13 | 2018-01-13 | 2018-01-13 | 2018-01-13 | 2018-01-13
2AI101PI01100-08360 | EOF:NDE/PWHT/QC Checks of Pipes | [37 empty] | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03
2AI101PI01100-08365 | EOF:Install Permanent Supporting for Pipes | [37 empty] | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03
2AI101PI01100-08370 | EOF:Install piping valves | [37 empty] | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03
2AI101PI01100-08375 | EOF:Installation of pipes | [35 empty] | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04
2AI101PI01100-08380 | EOF:Alignment/Fit-up | [35 empty] | 2018-06-05 | 2018-06-05 | 2018-06-05 | 2018-06-05 | 2018-06-05 | 2018-06-05 | 2018-06-05 | 2018-06-05 | 2018-06-05 | 2018-06-05 | 2018-06-05
2AI101PI01100-08381 | EOF:Welding/Bolting of Pipes | [35 empty] | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04
2AI101PI01100-08385 | EOF:NDE/PWHT/QC Checks of Pipes | [35 empty] | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04
2AI101PI01100-08390 | EOF:Install Permanent Supporting for Pipes | [37 empty] | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03
2AI101PI01100-08395 | EOF:Install piping valves | [37 empty] | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03
2AI101PI01100-08400 | EOF:Installation of pipes | [35 empty] | 2018-07-05 | 2018-07-05 | 2018-07-05 | 2018-07-05 | 2018-07-05 | 2018-07-05 | 2018-07-05 | 2018-07-05 | 2018-07-05 | 2018-07-05 | 2018-07-05
2AI101PI01100-08405 | EOF:Alignment/Fit-up | [35 empty] | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07
2AI101PI01100-08406 | EOF:Welding/Bolting of Pipes | [35 empty] | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07
2AI101PI01100-08410 | EOF:NDE/PWHT/QC Checks of Pipes | [37 empty] | 2018-08-02 | 2018-08-02 | 2018-08-02 | 2018-08-02 | 2018-08-02 | 2018-08-02 | 2018-08-02 | 2018-08-02 | 2018-08-02
2AI101PI01100-08415 | EOF:Install Permanent Supporting for Pipes | [37 empty] | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03
2AI101PI01100-08420 | EOF:Install piping valves | [37 empty] | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03
2AI101PI01100-08425 | EOF:Installation of pipes | [35 empty] | 2018-07-05 | 2018-07-05 | 2018-07-05 | 2018-07-05 | 2018-07-05 | 2018-07-05 | 2018-07-05 | 2018-07-05 | 2018-07-05 | 2018-07-05 | 2018-07-05
2AI101PI01100-08430 | EOF:Alignment/Fit-up | [35 empty] | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07
2AI101PI01100-08431 | EOF:Welding/Bolting of Pipes | [35 empty] | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07
2AI101PI01100-08435 | EOF:NDE/PWHT/QC Checks of Pipes | [37 empty] | 2018-08-02 | 2018-08-02 | 2018-08-02 | 2018-08-02 | 2018-08-02 | 2018-08-02 | 2018-08-02 | 2018-08-02 | 2018-08-02
2AI101PI01100-08440 | EOF:Install Permanent Supporting for Pipes | [37 empty] | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03
2AI101PI01100-08445 | EOF:Install piping valves | [37 empty] | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03
2AI101PI01100-08450 | EOF:Installation of pipes | [29 empty] | 2017-12-11 | 2017-12-11 | 2017-12-11 | 2017-12-11 | 2017-12-11 | 2017-12-11 | 2017-12-11 | 2017-12-11 | 2017-12-11 | 2017-12-11 | 2017-12-11 | 2017-12-11 | 2017-12-11 | 2017-12-11 | 2017-12-11 | 2017-12-11 | 2017-12-11
2AI101PI01100-08455 | EOF:Alignment/Fit-up | [33 empty] | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07
2AI101PI01100-08456 | EOF:Welding/Bolting of Pipes | [35 empty] | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02
2AI101PI01100-08460 | EOF:NDE/PWHT/QC Checks of Pipes | [35 empty] | 2018-07-02: 2019-01-07; 2018-07-02: 2019-01-07; 2018-07-02: 2019-01-07; 2018-07-02: 2019-01-07; 2018-07-02: 2019-01-07
2AI101PI01100-08465 | EOF:Install Permanent Supporting for Pipes | [35 empty] | 2018-07-02: 2019-01-07; 2018-07-02: 2019-01-07; 2018-07-02: 2019-01-07; 2018-07-02: 2019-01-07; 2018-07-02: 2019-01-07
2AI101PI01100-08470 | EOF:Install piping valves | [35 empty] | 2018-07-02: 2019-01-07; 2018-07-02: 2019-01-07; 2018-07-02: 2019-01-07; 2018-07-02: 2019-01-07; 2018-07-02: 2019-01-07
2AI101PI01100-08475 | EOF:Installation of pipes | [35 empty] | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04
2AI101PI01100-08480 | EOF:Alignment/Fit-up | [35 empty] | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04
2AI101PI01100-08481 | EOF:Welding/Bolting of Pipes | [35 empty] | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04
2AI101PI01100-08485 | EOF:NDE/PWHT/QC Checks of Pipes | [35 empty] | 2018-06-10 | 2018-06-10 | 2018-06-10 | 2018-06-10 | 2018-06-10 | 2018-06-10 | 2018-06-10 | 2018-06-10 | 2018-06-10 | 2018-06-10 | 2018-06-10
2AI101PI01100-08490 | EOF:Install Permanent Supporting for Pipes | [39 empty] | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05
2AI101PI01100-08495 | EOF:Install piping valves | [39 empty] | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05
2AI101PI01100-08500 | EOF:Installation of pipes | [35 empty] | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23
2AI101PI01100-08505 | EOF:Alignment/Fit-up | [35 empty] | 2018-06-24 | 2018-06-24 | 2018-06-24 | 2018-06-24 | 2018-06-24 | 2018-06-24 | 2018-06-24 | 2018-06-24 | 2018-06-24 | 2018-06-24 | 2018-06-24
2AI101PI01100-08506 | EOF:Welding/Bolting of Pipes | [35 empty] | 2018-06-25 | 2018-06-25 | 2018-06-25 | 2018-06-25 | 2018-06-25 | 2018-06-25 | 2018-06-25 | 2018-06-25 | 2018-06-25 | 2018-06-25 | 2018-06-25
2AI101PI01100-08510 | EOF:NDE/PWHT/QC Checks of Pipes | [39 empty] | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05
2AI101PI01100-08515 | EOF:Install Permanent Supporting for Pipes | [39 empty] | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05
2AI101PI01100-08520 | EOF:Install piping valves | [39 empty] | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05
2AI101PI01100-08525 | EOF:Installation of pipes | [35 empty] | 2018-06-28 | 2018-06-28 | 2018-06-28 | 2018-06-28 | 2018-06-28 | 2018-06-28 | 2018-06-28 | 2018-06-28 | 2018-06-28 | 2018-06-28 | 2018-06-28
2AI101PI01100-08530 | EOF:Alignment/Fit-up | [35 empty] | 2018-06-28 | 2018-06-28 | 2018-06-28 | 2018-06-28 | 2018-06-28 | 2018-06-28 | 2018-06-28 | 2018-06-28 | 2018-06-28 | 2018-06-28 | 2018-06-28
2AI101PI01100-08531 | EOF:Welding/Bolting of Pipes | [35 empty] | 2018-06-28 | 2018-06-28 | 2018-06-28 | 2018-06-28 | 2018-06-28 | 2018-06-28 | 2018-06-28 | 2018-06-28 | 2018-06-28 | 2018-06-28 | 2018-06-28
2AI101PI01100-08535 | EOF:NDE/PWHT/QC Checks of Pipes | [39 empty] | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05
2AI101PI01100-08540 | EOF:Install Permanent Supporting for Pipes | [39 empty] | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05
2AI101PI01100-08545 | EOF:Install piping valves | [39 empty] | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05
2AI101PI01300 | EOF: Hydrotesting | [21 empty] | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01
2AI101PI01300-08000 | EOF: Pressure testing for Non Metallic | [21 empty] | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01
2AI101PI01300-08001 | EOF:Test pack preparation & Ready for Test | [21 empty] | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01
2AI101PI01300-08002 | EOF:Pressure testing & Approval | [21 empty] | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06
2AI101PI01300-08005 | EOF: Pressure testing for Metallic (CS/LTCS) | [21 empty] | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04
2AI101PI01300-08006 | EOF:Reinstatement | [21 empty] | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06
2AI101PI01300-08007 | EOF:Flange management | [21 empty] | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06
2AI101PI01300-08010 | EOF: Pressure testing for Metallic (SS/SDSS) | [37 empty] | 2018-08-06 | 2018-08-06 | 2018-08-06 | 2018-08-06 | 2018-08-06 | 2018-08-06 | 2018-08-06 | 2018-08-06 | 2018-08-06
2AI101PI01300-08011 | EOF:Test pack preparation & Ready for Test | [37 empty] | 2018-08-06: 2019-04-08
2AI101PI01300-08012 | EOF:Pressure testing & Approval | [37 empty] | 2018-08-06: 2019-04-08
2AI101PI01300-08016 | EOF:Reinstatement | [37 empty] | 2018-08-06: 2019-03-29
2AI101PI01300-08017 | EOF:Flange management | [37 empty] | 2018-08-06: 2019-03-30
2AI101PI01300-08020 | EOF:Test pack preparation & Ready for Test | [37 empty] | 2018-08-06 | 2018-08-06 | 2018-08-06 | 2018-08-06 | 2018-08-06 | 2018-08-06 | 2018-08-06 | 2018-08-06 | 2018-08-06
2AI101PI01300-08021 | EOF:Pressure testing & Approval | [37 empty] | 2018-09-12 | 2018-09-12 | 2018-09-12 | 2018-09-12 | 2018-09-12 | 2018-09-12 | 2018-09-12 | 2018-09-12 | 2018-09-12
2AI101PI01300-08025 | EOF:Reinstatement | [37 empty] | 2018-09-13 | 2018-09-13 | 2018-09-13 | 2018-09-13 | 2018-09-13 | 2018-09-13 | 2018-09-13 | 2018-09-13 | 2018-09-13
2AI101PI01300-08026 | EOF:Flange management | [37 empty] | 2018-09-13 | 2018-09-13 | 2018-09-13 | 2018-09-13 | 2018-09-13 | 2018-09-13 | 2018-09-13 | 2018-09-13 | 2018-09-13
2AI101PI01300-08040 | EOF:Test pack preparation & Ready for Test | [27 empty] | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17
2AI101PI01300-08041 | EOF:Pressure testing & Approval | [27 empty] | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18
2AI101PI01300-08045 | EOF:Reinstatement | [29 empty] | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04
2AI101PI01300-08046 | EOF:Flange management | [29 empty] | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04
2AI101PI01300-08050 | EOF:Test pack preparation & Ready for Test | [21 empty] | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04
2AI101PI01300-08051 | EOF:Pressure testing & Approval | [21 empty] | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07
2AI101PI01300-08055 | EOF:Reinstatement | [21 empty] | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07
2AI101PI01300-08056 | EOF:Flange management | [21 empty] | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07
2AI101PI01300-08060 | EOF:Test pack preparation & Ready for Test | [29 empty] | 2017-12-10 | 2017-12-10 | 2017-12-10 | 2017-12-10 | 2017-12-10 | 2017-12-10 | 2017-12-10 | 2017-12-10 | 2017-12-10 | 2017-12-10 | 2017-12-10 | 2017-12-10 | 2017-12-10 | 2017-12-10 | 2017-12-10 | 2017-12-10 | 2017-12-10
2AI101PI01300-08061 | EOF:Pressure testing & Approval | [29 empty] | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17
2AI101PI01300-08065 | EOF:Reinstatement | [29 empty] | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01
2AI101PI01300-08066 | EOF:Flange management | [29 empty] | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01
2AI101PI01300-08070 | EOF:Test pack preparation & Ready for Test | [33 empty] | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02
2AI101PI01300-08071 | EOF:Pressure testing & Approval | [33 empty] | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08
2AI101PI01300-08075 | EOF:Reinstatement | [33 empty] | 2018-04-13 | 2018-04-13 | 2018-04-13 | 2018-04-13 | 2018-04-13 | 2018-04-13 | 2018-04-13 | 2018-04-13 | 2018-04-13 | 2018-04-13 | 2018-04-13 | 2018-04-13 | 2018-04-13
2AI101PI01300-08076 | EOF:Flange management | [33 empty] | 2018-04-13 | 2018-04-13 | 2018-04-13 | 2018-04-13 | 2018-04-13 | 2018-04-13 | 2018-04-13 | 2018-04-13 | 2018-04-13 | 2018-04-13 | 2018-04-13 | 2018-04-13 | 2018-04-13
2AI101PI01300-08080 | EOF:Test pack preparation & Ready for Test | [31 empty] | 2018-03-10 | 2018-03-10 | 2018-03-10 | 2018-03-10 | 2018-03-10 | 2018-03-10 | 2018-03-10 | 2018-03-10 | 2018-03-10 | 2018-03-10 | 2018-03-10 | 2018-03-10 | 2018-03-10 | 2018-03-10 | 2018-03-10
2AI101PI01300-08081 | EOF:Pressure testing & Approval | [31 empty] | 2018-03-20 | 2018-03-20 | 2018-03-20 | 2018-03-20 | 2018-03-20 | 2018-03-20 | 2018-03-20 | 2018-03-20 | 2018-03-20 | 2018-03-20 | 2018-03-20 | 2018-03-20 | 2018-03-20 | 2018-03-20 | 2018-03-20
2AI101PI01300-08085 | EOF:Reinstatement | [31 empty] | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05
2AI101PI01300-08086 | EOF:Flange management | [31 empty] | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05
2AI101PI01300-08090 | EOF:Test pack preparation & Ready for Test | [31 empty] | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18
2AI101PI01300-08091 | EOF:Pressure testing & Approval | [31 empty] | 2018-03-20 | 2018-03-20 | 2018-03-20 | 2018-03-20 | 2018-03-20 | 2018-03-20 | 2018-03-20 | 2018-03-20 | 2018-03-20 | 2018-03-20 | 2018-03-20 | 2018-03-20 | 2018-03-20 | 2018-03-20 | 2018-03-20
2AI101PI01300-08095 | EOF:Reinstatement | [33 empty] | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02
2AI101PI01300-08096 | EOF:Flange management | [33 empty] | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02
2AI101PI01300-08100 | EOF:Test pack preparation & Ready for Test | [33 empty] | 2018-04-02: 2019-02-04; 2018-04-02: 2019-02-04; 2018-04-02: 2019-02-04
2AI101PI01300-08101 | EOF:Pressure testing & Approval | [33 empty] | 2018-04-02: 2019-02-04; 2018-04-02: 2019-02-04; 2018-04-02: 2019-02-04
2AI101PI01300-08105 | EOF:Reinstatement | [33 empty] | 2018-04-02: 2019-02-04; 2018-04-02: 2019-02-04; 2018-04-02: 2019-02-04
2AI101PI01300-08106 | EOF:Flange management | [33 empty] | 2018-04-02: 2019-02-04; 2018-04-02: 2019-02-04; 2018-04-02: 2019-02-04
2AI101PI01300-08400 | EOF:Test pack preparation & Ready for Test | [33 empty] | 2018-04-02: 2019-01-12; 2018-04-02: 2019-01-12; 2018-04-02: 2019-01-12; 2018-04-02: 2019-01-12; 2018-04-02: 2019-01-12
2AI101PI01300-08405 | EOF:Pressure testing & Approval | [33 empty] | 2018-04-02: 2019-01-14; 2018-04-02: 2019-01-14; 2018-04-02: 2019-01-14; 2018-04-02: 2019-01-14; 2018-04-02: 2019-01-14
2AI101PI01300-08410 | EOF:Reinstatement | [33 empty] | 2018-04-02: 2019-04-08
2AI101PI01300-08415 | EOF:Flange management | [33 empty] | 2018-04-02: 2019-04-08
2AI101PI01300-08420 | EOF:Test pack preparation & Ready for Test | [33 empty] | 2018-04-02: 2018-11-21; 2018-04-02: 2018-11-21; 2018-04-02: 2018-11-21; 2018-04-02: 2018-11-21; 2018-04-02: 2018-11-21; 2018-04-02: 2018-11-21; 2018-04-02: 2018-11-21
2AI101PI01300-08425 | EOF:Pressure testing & Approval | [33 empty] | 2018-04-02: 2018-11-21; 2018-04-02: 2018-11-21; 2018-04-02: 2018-11-21; 2018-04-02: 2018-11-21; 2018-04-02: 2018-11-21; 2018-04-02: 2018-11-21; 2018-04-02: 2018-11-21
2AI101PI01300-08430 | EOF:Reinstatement | [33 empty] | 2018-04-02: 2019-01-20; 2018-04-02: 2019-01-20; 2018-04-02: 2019-01-20; 2018-04-02: 2019-01-20; 2018-04-02: 2019-01-20
2AI101PI01300-08435 | EOF:Flange management | [33 empty] | 2018-04-02: 2018-11-25; 2018-04-02: 2018-11-25; 2018-04-02: 2018-11-25; 2018-04-02: 2018-11-25; 2018-04-02: 2018-11-25
2AI101PI01300-08440 | EOF:Test pack preparation & Ready for Test | [33 empty] | 2018-04-02: 2018-10-01; 2018-04-02: 2018-10-01; 2018-04-02: 2018-10-01; 2018-04-02: 2018-10-01; 2018-04-02: 2018-10-01; 2018-04-02: 2018-10-01; 2018-04-02: 2018-10-01
2AI101PI01300-08445 | EOF:Pressure testing & Approval | [33 empty] | 2018-04-02: 2018-10-09; 2018-04-02: 2018-10-09; 2018-04-02: 2018-10-09; 2018-04-02: 2018-10-09; 2018-04-02: 2018-10-09; 2018-04-02: 2018-10-09; 2018-04-02: 2018-10-09
2AI101PI01300-08450 | EOF:Reinstatement | [33 empty] | 2018-04-02: 2019-03-10; 2018-04-02: 2019-03-10; 2018-04-02: 2019-03-10
2AI101PI01300-08455 | EOF:Flange management | [33 empty] | 2018-04-02: 2018-10-12; 2018-04-02: 2018-10-12; 2018-04-02: 2018-10-12; 2018-04-02: 2018-10-12; 2018-04-02: 2018-10-12; 2018-04-02: 2018-10-12; 2018-04-02: 2018-10-12
2AI101PI01300-08460 | EOF:Test pack preparation & Ready for Test | [33 empty] | 2018-04-02: 2018-12-01; 2018-04-02: 2018-12-01; 2018-04-02: 2018-12-01; 2018-04-02: 2018-12-01; 2018-04-02: 2018-12-01
2AI101PI01300-08465 | EOF:Pressure testing & Approval | [33 empty] | 2018-04-02: 2018-12-02; 2018-04-02: 2018-12-02; 2018-04-02: 2018-12-02; 2018-04-02: 2018-12-02; 2018-04-02: 2018-12-02
2AI101PI01300-08470 | EOF:Reinstatement | [33 empty] | 2018-04-02: 2019-01-21; 2018-04-02: 2019-01-21; 2018-04-02: 2019-01-21; 2018-04-02: 2019-01-21; 2018-04-02: 2019-01-21
2AI101PI01300-08475 | EOF:Flange management | [33 empty] | 2018-04-02: 2019-01-21; 2018-04-02: 2019-01-21; 2018-04-02: 2019-01-21; 2018-04-02: 2019-01-21; 2018-04-02: 2019-01-21
2AI101PI01300-08480 | EOF:Test pack preparation & Ready for Test | [33 empty] | 2018-04-02: 2018-11-29; 2018-04-02: 2018-11-29; 2018-04-02: 2018-11-29; 2018-04-02: 2018-11-29; 2018-04-02: 2018-11-29
2AI101PI01300-08485 | EOF:Pressure testing & Approval | [33 empty] | 2018-04-02: 2018-12-01; 2018-04-02: 2018-12-01; 2018-04-02: 2018-12-01; 2018-04-02: 2018-12-01; 2018-04-02: 2018-12-01
2AI101PI01300-08490 | EOF:Reinstatement | [33 empty] | 2018-04-02: 2019-01-26; 2018-04-02: 2019-01-26; 2018-04-02: 2019-01-26
2AI101PI01300-08495 | EOF:Flange management | [33 empty] | 2018-04-02: 2019-01-26; 2018-04-02: 2019-01-26; 2018-04-02: 2019-01-26
2AI101PI01300-08500 | EOF:Test pack preparation & Ready for Test | [33 empty] | 2018-04-02: 2019-03-09; 2018-04-02: 2019-03-09; 2018-04-02: 2019-03-09
2AI101PI01300-08505 | EOF:Pressure testing & Approval | [33 empty] | 2018-04-02: 2019-03-09; 2018-04-02: 2019-03-09; 2018-04-02: 2019-03-09
2AI101PI01300-08510 | EOF:Reinstatement | [33 empty] | 2018-04-02: 2019-04-08
2AI101PI01300-08515 | EOF:Flange management | [33 empty] | 2018-04-02: 2019-04-08
2AI101PI18100 | EOF: Touch-up painting of Piping | [23 empty] | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05
2AI101PI18100-08000 | EOF: Touch-up painting of Piping | [23 empty] | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05
2AI101PI18100-08001 | EOF: Touch-Up Painting for Metallic (CS/LTCS) | [23 empty] | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05 | 2017-06-05
2AI101PI18100-08005 | EOF: Touch-Up Painting for Metallic (SS/SDSS) | [37 empty] | 2018-08-25 | 2018-08-25 | 2018-08-25 | 2018-08-25 | 2018-08-25 | 2018-08-25 | 2018-08-25 | 2018-08-25 | 2018-08-25
2AI101TE01000 | EOF:UG Telecom cable works | [21 empty] | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08
2AI101TE01000-08000 | EOF:Cable Glading & Termination | [21 empty] | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08
2AI101TE01000-08001 | EOF: Laying Cable Duct | [21 empty] | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08
2AI101TE01000-08005 | EOF: Cable laying | [29 empty] | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11
2AI101TE01000-08015 | EOF: Splicing of telecom cable | [35 empty] | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02
2AI101TE01100 | EOF: AG Cable laying, Telecom Equipments / CCTV & Security System Installation & Cable Termination | [31 empty] | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05
2AI101TE01100-08000 | EOF: AG Cable laying | [33 empty] | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07
2AI101TE01100-08001 | EOF:AG Cable laying | [33 empty] | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07
2AI101TE01100-08005 | EOF: Telecom Equipments / CCTV & Security System Installation | [31 empty] | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05
2AI101TE01100-08006 | EOF:Telecom Equipments Installation | [31 empty] | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05
2AI101TE01100-08010 | EOF:CCTV & Security System Installation | [31 empty] | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05
2AI101TE01100-08015 | EOF: Cable Termination | [33 empty] | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21
2AI101TE01100-08016 | EOF:Cable Termination | [33 empty] | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21
2AI102CV01100 | EOF: Filling Manifold Auto Sampling Package (52-Z-305 & 306) Shelter Foundation | [17 empty] | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13
2AI102CV01100-08000 | EOF: Filling Manifold Auto Sampling Package (52-Z-305) Shelter Foundation | [17 empty] | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13
2AI102CV01100-08001 | EOF:Survey Marking, Excavation & Subgrade | [17 empty] | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13
2AI102CV01100-08005 | EOF: Filling Manifold Auto Sampling Package (52-Z-306) Shelter Foundation | [17 empty] | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13
2AI102CV01100-08006 | EOF:Blinding/PCC for Fnd | [17 empty] | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13
2AI102CV01100-08010 | EOF:Rebar, Formwork for Footing | [17 empty] | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13
2AI102CV01100-08011 | EOF:Concrete Pouring - for Footing | [17 empty] | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13
2AI102CV01100-08015 | EOF:Rebar, Formwork, Install Embedments for Pedestal | [17 empty] | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13
2AI102CV01100-08016 | EOF:Concrete Pouring - for Pedestal | [17 empty] | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13
2AI102CV01100-08020 | EOF:Concrete Potection for Fnd | [17 empty] | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13
2AI102CV01100-08025 | EOF:Backfilling & Compaction for Fnd | [17 empty] | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13
2AI102CV01100-08030 | EOF:Survey Marking, Excavation & Subgrade | [17 empty] | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13
2AI102CV01100-08035 | EOF:Blinding/PCC for Fnd | [17 empty] | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13
2AI102CV01100-08040 | EOF:Rebar, Formwork for Footing | [17 empty] | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13
2AI102CV01100-08041 | EOF:Concrete Pouring - for Footing | [17 empty] | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13
2AI102CV01100-08045 | EOF:Rebar, Formwork, Install Embedments for Pedestal | [17 empty] | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13
2AI102CV01100-08046 | EOF:Concrete Pouring - for Pedestal | [17 empty] | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13
2AI102CV01100-08050 | EOF:Concrete Potection for Fnd | [17 empty] | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13
2AI102CV01100-08055 | EOF:Backfilling & Compaction for Fnd | [17 empty] | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13
2AI102CV01400 | EOF: Filling Manifold Auto Sampling Package (52-Z-305 & 306) Shelter Erection | [17 empty] | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09
2AI102CV01400-08001 | EOF:Installation of Str. Steel for Filling Manifold Auto Sampling Package (52-Z-305) Shelter | [17 empty] | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09
2AI102CV01400-08005 | EOF: Filling Manifold Auto Sampling Package (52-Z-305) Shelter Erection | [17 empty] | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09
2AI102CV01400-08006 | EOF:Alignment & Bolting/Torqueing for Filling Manifold Auto Sampling Package (52-Z-305) Shelter | [19 empty] | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28 | 2017-01-28
2AI102CV01400-08010 | EOF: Filling Manifold Auto Sampling Package (52-Z-306) Shelter Erection | [17 empty] | 2017-01-26 | 2017-01-26 | 2017-01-26 | 2017-01-26 | 2017-01-26 | 2017-01-26 | 2017-01-26 | 2017-01-26 | 2017-01-26 | 2017-01-26 | 2017-01-26 | 2017-01-26 | 2017-01-26 | 2017-01-26 | 2017-01-26 | 2017-01-26 | 2017-01-26 | 2017-01-26 | 2017-01-26 | 2017-01-26 | 2017-01-26 | 2017-01-26 | 2017-01-26 | 2017-01-26 | 2017-01-26 | 2017-01-26 | 2017-01-26 | 2017-01-26 | 2017-01-26
2AI102CV01400-08011 | EOF:Grouting of Filling Manifold Auto Sampling Package (52-Z-305) Shelter | [19 empty] | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05
2AI102CV01400-08015 | EOF:Installation of Str. Steel for Filling Manifold Auto Sampling Package (52-Z-306) Shelter | [17 empty] | 2017-01-26 | 2017-01-26 | 2017-01-26 | 2017-01-26 | 2017-01-26 | 2017-01-26 | 2017-01-26 | 2017-01-26 | 2017-01-26 | 2017-01-26 | 2017-01-26 | 2017-01-26 | 2017-01-26 | 2017-01-26 | 2017-01-26 | 2017-01-26 | 2017-01-26 | 2017-01-26 | 2017-01-26 | 2017-01-26 | 2017-01-26 | 2017-01-26 | 2017-01-26 | 2017-01-26 | 2017-01-26 | 2017-01-26 | 2017-01-26 | 2017-01-26 | 2017-01-26
2AI102CV01400-08020 | EOF:Alignment & Bolting/Torqueing for Filling Manifold Auto Sampling Package (52-Z-306) Shelter | [19 empty] | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29
2AI102CV01400-08025 | EOF:Grouting of Filling Manifold Auto Sampling Package (52-Z-306) Shelter | [19 empty] | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15
2AI102CV01400-08030 | Installation of gratings/handrail/stair/ladder | [19 empty] | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16
2AI102CV01400-08035 | Installation of gratings/handrail/stair/ladder | [19 empty] | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06
2AI102CV01400-08040 | Wall & Roof Cladding | [19 empty] | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15
2AI102CV01400-08045 | Wall & Roof Cladding | [19 empty] | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23
2AI102CV01500 | EOF: UG, Trenches & other Civil Works | [11 empty] | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21
2AI102CV01500-08000 | EOF: HSE Safety Equipments & Safety Misc. Foundation | [17 empty] | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29
2AI102CV01500-08015 | EOF: Pipe Supports / Pipe Sleepers | [11 empty] | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21
2AI102CV01500-08020 | EOF: EIT items Misc. Foundation | [15 empty] | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05
2AI102CV01500-08121 | EOF: HSE Safety Equipments & Safety Misc. Foundation | [17 empty] | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29
2AI102CV01500-08122 | EOF: Pipe Supports & Pipe Sleepers | [11 empty] | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21
2AI102CV01500-08123 | EOF: EIT items Misc. Foundation | [15 empty] | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05
2AI102CV01600 | COCC :Roads, Crossing & Paving Works | [21 empty] | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29
2AI102CV01600-08010 | COCC: Rough Grading for Road Works | [37 empty] | 2018-08-26 | 2018-08-26 | 2018-08-26 | 2018-08-26 | 2018-08-26 | 2018-08-26 | 2018-08-26 | 2018-08-26 | 2018-08-26
2AI102CV01600-08020 | COCC: Fine Grading (Gatch Subgrade) | [39 empty] | 2018-09-29 | 2018-09-29 | 2018-09-29 | 2018-09-29 | 2018-09-29 | 2018-09-29 | 2018-09-29
2AI102CV01600-08025 | COCC: Sub base & Base preparation | [33 empty] | 2018-03-24 | 2018-03-24 | 2018-03-24 | 2018-03-24 | 2018-03-24 | 2018-03-24 | 2018-03-24 | 2018-03-24 | 2018-03-24 | 2018-03-24 | 2018-03-24 | 2018-03-24 | 2018-03-24
2AI102CV01600-08030 | COCC: Finish Grading (Crushed gravel layer & Grading Top soil) | [33 empty] | 2018-03-24: 2018-10-04; 2018-03-24: 2018-10-04; 2018-03-24: 2018-10-04; 2018-03-24: 2018-10-04; 2018-03-24: 2018-10-04; 2018-03-24: 2018-10-04; 2018-03-24: 2018-10-04
2AI102CV01600-08035 | COCC: Formwork | [33 empty] | 2018-03-25 | 2018-03-25 | 2018-03-25 | 2018-03-25 | 2018-03-25 | 2018-03-25 | 2018-03-25 | 2018-03-25 | 2018-03-25 | 2018-03-25 | 2018-03-25 | 2018-03-25 | 2018-03-25
2AI102CV01600-08040 | COCC: Re-combaction of sub-grade | [33 empty] | 2018-03-25: 2018-10-02; 2018-03-25: 2018-10-02; 2018-03-25: 2018-10-02; 2018-03-25: 2018-10-02; 2018-03-25: 2018-10-02; 2018-03-25: 2018-10-02; 2018-03-25: 2018-10-02
2AI102CV01600-08045 | COCC: Reinforcement | [33 empty] | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23
2AI102CV01600-08050 | COCC: Base Preparation & Kerbing (incl. Filling/Comp with Gatch & Crushed gravel layer) | [33 empty] | 2018-03-23: 2018-10-03; 2018-03-23: 2018-10-03; 2018-03-23: 2018-10-03; 2018-03-23: 2018-10-03; 2018-03-23: 2018-10-03; 2018-03-23: 2018-10-03; 2018-03-23: 2018-10-03
2AI102CV01600-08055 | COCC: Concrete Pouring | [33 empty] | 2018-03-29 | 2018-03-29 | 2018-03-29 | 2018-03-29 | 2018-03-29 | 2018-03-29 | 2018-03-29 | 2018-03-29 | 2018-03-29 | 2018-03-29 | 2018-03-29 | 2018-03-29 | 2018-03-29
2AI102CV01600-08060 | COCC: Asphalt base course | [33 empty] | 2018-03-29: 2018-10-03; 2018-03-29: 2018-10-03; 2018-03-29: 2018-10-03; 2018-03-29: 2018-10-03; 2018-03-29: 2018-10-03; 2018-03-29: 2018-10-03; 2018-03-29: 2018-10-03
2AI102CV01600-08065 | COCC: Finishing | [33 empty] | 2018-04-03 | 2018-04-03 | 2018-04-03 | 2018-04-03 | 2018-04-03 | 2018-04-03 | 2018-04-03 | 2018-04-03 | 2018-04-03 | 2018-04-03 | 2018-04-03 | 2018-04-03 | 2018-04-03
2AI102CV01600-08070 | COCC: Asphalt binding course | [33 empty] | 2018-04-03: 2019-01-02; 2018-04-03: 2019-01-02; 2018-04-03: 2019-01-02; 2018-04-03: 2019-01-02; 2018-04-03: 2019-01-02
2AI102CV01600-08075 | COCC: Excavation/trimming | [33 empty] | 2018-03-24 | 2018-03-24 | 2018-03-24 | 2018-03-24 | 2018-03-24 | 2018-03-24 | 2018-03-24 | 2018-03-24 | 2018-03-24 | 2018-03-24 | 2018-03-24 | 2018-03-24 | 2018-03-24
2AI102CV01600-08080 | COCC: Asphalt Wearing course | [33 empty] | 2018-03-24: 2019-03-04; 2018-03-24: 2019-03-04; 2018-03-24: 2019-03-04
2AI102CV01600-08085 | COCC: Compacted Sub base preparation | [33 empty] | 2018-03-25 | 2018-03-25 | 2018-03-25 | 2018-03-25 | 2018-03-25 | 2018-03-25 | 2018-03-25 | 2018-03-25 | 2018-03-25 | 2018-03-25 | 2018-03-25 | 2018-03-25 | 2018-03-25
2AI102CV01600-08090 | COCC: Final Coat (incl. Road marking) | [33 empty] | 2018-03-25: 2019-04-08
2AI102CV01600-08095 | COCC: Install Kerb stone | [33 empty] | 2018-03-26 | 2018-03-26 | 2018-03-26 | 2018-03-26 | 2018-03-26 | 2018-03-26 | 2018-03-26 | 2018-03-26 | 2018-03-26 | 2018-03-26 | 2018-03-26 | 2018-03-26 | 2018-03-26
2AI102CV01600-08100 | COCC: Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material | [21 empty] | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29
2AI102CV01600-08105 | COCC: Sand/gatch layer | [33 empty] | 2018-04-01 | 2018-04-01 | 2018-04-01 | 2018-04-01 | 2018-04-01 | 2018-04-01 | 2018-04-01 | 2018-04-01 | 2018-04-01 | 2018-04-01 | 2018-04-01 | 2018-04-01 | 2018-04-01
2AI102CV01600-08110 | COCC: Subgrade and Blinding | [21 empty] | 2017-05-13 | 2017-05-13 | 2017-05-13 | 2017-05-13 | 2017-05-13 | 2017-05-13 | 2017-05-13 | 2017-05-13 | 2017-05-13 | 2017-05-13 | 2017-05-13 | 2017-05-13 | 2017-05-13 | 2017-05-13 | 2017-05-13 | 2017-05-13 | 2017-05-13 | 2017-05-13 | 2017-05-13 | 2017-05-13 | 2017-05-13 | 2017-05-13 | 2017-05-13 | 2017-05-13 | 2017-05-13
2AI102CV01600-08115 | COCC: Laying of Interlock Paving blocks | [33 empty] | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07
2AI102CV01600-08120 | COCC: Rebar, Formwork & Install Pipe sleeves | [21 empty] | 2017-05-15 | 2017-05-15 | 2017-05-15 | 2017-05-15 | 2017-05-15 | 2017-05-15 | 2017-05-15 | 2017-05-15 | 2017-05-15 | 2017-05-15 | 2017-05-15 | 2017-05-15 | 2017-05-15 | 2017-05-15 | 2017-05-15 | 2017-05-15 | 2017-05-15 | 2017-05-15 | 2017-05-15 | 2017-05-15 | 2017-05-15 | 2017-05-15 | 2017-05-15 | 2017-05-15 | 2017-05-15
2AI102CV01600-08130 | COCC: Concrete Pouring | [21 empty] | 2017-05-18 | 2017-05-18 | 2017-05-18 | 2017-05-18 | 2017-05-18 | 2017-05-18 | 2017-05-18 | 2017-05-18 | 2017-05-18 | 2017-05-18 | 2017-05-18 | 2017-05-18 | 2017-05-18 | 2017-05-18 | 2017-05-18 | 2017-05-18 | 2017-05-18 | 2017-05-18 | 2017-05-18 | 2017-05-18 | 2017-05-18 | 2017-05-18 | 2017-05-18 | 2017-05-18 | 2017-05-18
2AI102CV01600-08140 | COCC: Coating | [23 empty] | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30
2AI102CV01600-08141 | COCC: Roads including Crossing Works | [21 empty] | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29
2AI102CV01600-08142 | COCC: Paving Work | [33 empty] | 2018-03-24 | 2018-03-24 | 2018-03-24 | 2018-03-24 | 2018-03-24 | 2018-03-24 | 2018-03-24 | 2018-03-24 | 2018-03-24 | 2018-03-24 | 2018-03-24 | 2018-03-24 | 2018-03-24
2AI102CV01600-08150 | COCC: Backfill / Compaction | [23 empty] | 2017-06-11 | 2017-06-11 | 2017-06-11 | 2017-06-11 | 2017-06-11 | 2017-06-11 | 2017-06-11 | 2017-06-11 | 2017-06-11 | 2017-06-11 | 2017-06-11 | 2017-06-11 | 2017-06-11 | 2017-06-11 | 2017-06-11 | 2017-06-11 | 2017-06-11 | 2017-06-11 | 2017-06-11 | 2017-06-11 | 2017-06-11 | 2017-06-11 | 2017-06-11
2AI102CV28200 | EOF: Touch-up painting of Structures | [35 empty] | 2018-06-05 | 2018-06-05 | 2018-06-05 | 2018-06-05 | 2018-06-05 | 2018-06-05 | 2018-06-05 | 2018-06-05 | 2018-06-05 | 2018-06-05 | 2018-06-05
2AI102CV28200-08000 | COCC: Touch-up painting of Structures / Shelters | [35 empty] | 2018-06-05 | 2018-06-05 | 2018-06-05 | 2018-06-05 | 2018-06-05 | 2018-06-05 | 2018-06-05 | 2018-06-05 | 2018-06-05 | 2018-06-05 | 2018-06-05
2AI102CV28200-08141 | COCC: Touch-up painting of Structures / Shelters | [35 empty] | 2018-06-05 | 2018-06-05 | 2018-06-05 | 2018-06-05 | 2018-06-05 | 2018-06-05 | 2018-06-05 | 2018-06-05 | 2018-06-05 | 2018-06-05 | 2018-06-05
2AI102EL01000 | EOF: Power Cable Between Substation | [19 empty] | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06
2AI102EL01000-08100 | EOF: Issue AFC Drawings POWER CABLE BETWEEN SUBSTATION | [17 empty] | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17
2AI102EL01000-08141 | EOF: Power Cable Laying from from MG-1 Substation to 52-SUBST-301 | [19 empty] | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06
2AI102EL01100 | EOF: AG Cable laying, CP, DB'S/JB, Panels, Lighting Pole, Fixtures, Cable Glaning & Termination Electrical Works | [19 empty] | 2017-03-06: 2019-03-04; 2017-03-06: 2019-03-04; 2017-03-06: 2019-03-04
2AI102EL01100-08100 | EOF: Issue AFC Drawings POWER CABLE FROM SUBSTATION | [19 empty] | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02
2AI102EL01100-08141 | LV Power Cable laying from 52-SUBST-302 | [19 empty] | 2017-03-02: 2019-03-04; 2017-03-02: 2019-03-04; 2017-03-02: 2019-03-04
2AI102EL01100-08142 | LV Power Cable laying from 50-SUBST-001 | [19 empty] | 2017-03-02: 2019-03-04; 2017-03-02: 2019-03-04; 2017-03-02: 2019-03-04
2AI102IC01000 | EOF: Instrument Cable from Substation | [21 empty] | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01
2AI102IC01000-08100 | EOF: Issue AFC Drawings INSTRUMENTATION CABLE FROM SUBSTATION | [23 empty] | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01
2AI102IC01000-08141 | Instrument Cable laying from 52-SUBST-302 to Storage Tank Junction Boxes | [21 empty] | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01
2AI102IC01100 | EOF: AG cable laying, Tubing, Field, Inline Instrument Installation, Cable Glading & Termination Instrument Works | [21 empty] | 2017-05-01: 2018-10-03; 2017-05-01: 2018-10-03; 2017-05-01: 2018-10-03; 2017-05-01: 2018-10-03; 2017-05-01: 2018-10-03; 2017-05-01: 2018-10-03; 2017-05-01: 2018-10-03
2AI102IC01100-08100 | EOF: Issue AFC Drawings FIRE ALARM CABLE WORKS | [19 empty] | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02
2AI102IC01100-08141 | Fire Alarm Cable Laying from 52-SUBST-301 | [19 empty] | 2017-03-02: 2018-10-03; 2017-03-02: 2018-10-03; 2017-03-02: 2018-10-03; 2017-03-02: 2018-10-03; 2017-03-02: 2018-10-03; 2017-03-02: 2018-10-03; 2017-03-02: 2018-10-03
2AI102PC01000 | EOF SS 52-SUBST-301 : 110V DC Battery Charger | [37 empty] | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22
2AI102PC01000-08000 | EOF SS 52-SUBST-301 : 110V DC Battery Charger | [37 empty] | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22
2AI102PC01000-08001 | EOF:Polarity check | [37 empty] | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22
2AI102PC01000-08005 | EOF:Charging test | [37 empty] | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22
2AI102PC01000-08010 | EOF:Discharging test | [37 empty] | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22
2AI102PC01100 | EOF SS 52-SUBST-301 : SS Earthing & Lightning | [37 empty] | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22
2AI102PC01100-08000 | EOF SS 52-SUBST-301 : SS Earthing & Lightning | [37 empty] | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22
2AI102PC01100-08001 | EOF:Continuity testing | [37 empty] | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22
2AI102PC01100-08005 | EOF:Earth resistance measurement | [37 empty] | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22
2AI102PC01200 | EOF SS 52-SUBST-301 : HV Switchgear testing | [37 empty] | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22
2AI102PC01200-08000 | EOF SS 52-SUBST-301 : HV Switchgear testing | [37 empty] | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22
2AI102PC01200-08005 | EOF: CT,PT,Breaker Testing | [37 empty] | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22
2AI102PC01200-08010 | EOF: IR, Ductor testing | [37 empty] | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23
2AI102PC01200-08015 | EOF: Relay & Functional Testing | [37 empty] | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23
2AI102PC01200-08025 | EOF Primary Injection Testing | [37 empty] | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23
2AI102PC01200-08034 | EOF: Hi-pot Test | [37 empty] | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23
2AI102PC01200-08035 | EOF: Stability Testing | [37 empty] | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23
2AI102PC01300 | EOF SS 52-SUBST-301 : 24V DC Battery Charger | [37 empty] | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23
2AI102PC01300-08000 | EOF SS 52-SUBST-301 : 24V DC Battery Charger | [37 empty] | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23
2AI102PC01300-08001 | EOF:Polarity check | [37 empty] | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23
2AI102PC01300-08005 | EOF:Charging test | [37 empty] | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23
2AI102PC01300-08010 | EOF:Discharging test | [37 empty] | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23
2AI102PC01400 | EOF SS 52-SUBST-301 : LV Switchgear testing | [37 empty] | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23
2AI102PC01400-08000 | EOF SS 52-SUBST-301 : LV Switchgear testing | [37 empty] | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23
2AI102PC01400-08001 | EOF: CT,PT Testing | [37 empty] | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23
2AI102PC01400-08005 | EOF: IR, Ductor testing | [37 empty] | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23
2AI102PC01400-08010 | EOF: Relay & Functional Testing | [37 empty] | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23
2AI102PC01400-08015 | EOF Primary Injection Testing | [37 empty] | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24
2AI102PC01400-08020 | EOF: Hi-pot Test | [39 empty] | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05
2AI102PC01400-08025 | EOF: Stability Testing | [37 empty] | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24
2AI102PC01600 | EOF SS 52-SUBST-301 : 110V AC UPS | [37 empty] | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24
2AI102PC01600-08000 | EOF SS 52-SUBST-301 : 110V AC UPS | [37 empty] | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24
2AI102PC01600-08001 | EOF:Polarity check | [37 empty] | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24
2AI102PC01600-08005 | EOF:Charging test | [37 empty] | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24
2AI102PC01600-08010 | EOF:Discharging test | [37 empty] | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24
2AI102PC01700 | EOF SS 52-SUBST-301 : Transformer Testing | [37 empty] | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24
2AI102PC01700-08000 | EOF SS 52-SUBST-301 : Transformer Testing | [37 empty] | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24
2AI102PC01700-08001 | EOF:IR testing/WR testing/Turns ratio testing | [37 empty] | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24
2AI102PC01700-08005 | EOF:Functional Test | [37 empty] | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24
2AI102PC01700-08010 | EOF:BDV Testing | [37 empty] | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24
2AI102PC01900 | EOF SS 52-SUBST-301 : Electrical Tie-ins for Permanent Power & Energize | [37 empty] | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24
2AI102PC01900-08000 | EOF SS 52-SUBST-301 : Electrical Tie-ins for Permanent Power & Energize | [37 empty] | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24
2AI102PC01900-08001 | EOF:Incoming cables IR and continuity test | [37 empty] | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24
2AI102PC01900-08005 | EOF:Incoming HV cables hipot testing | [37 empty] | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24
2AI102PC01900-08010 | Cable Termination | [37 empty] | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24
2AI102PC01900-08045 | EOF: Ready for Energisation of Substation 52-SUBST-301 | [37 empty] | 2018-09-24: 2019-01-13; 2018-09-24: 2019-01-13; 2018-09-24: 2019-01-13; 2018-09-24: 2019-01-13; 2018-09-24: 2019-01-13
2AI102PC02000 | EOF SS 52-SUBST-301 : Lighting & Small Power | [29 empty] | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04
2AI102PC02000-08000 | EOF SS 52-SUBST-301 : Lighting & Small Power | [29 empty] | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04
2AI102PC02000-08001 | EOF:Continuity & IR testing | [29 empty] | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04
2AI102PC02000-08005 | EOF:Lux testing | [29 empty] | 2017-12-19 | 2017-12-19 | 2017-12-19 | 2017-12-19 | 2017-12-19 | 2017-12-19 | 2017-12-19 | 2017-12-19 | 2017-12-19 | 2017-12-19 | 2017-12-19 | 2017-12-19 | 2017-12-19 | 2017-12-19 | 2017-12-19 | 2017-12-19 | 2017-12-19
2AI102PC02100 | EOF SS 52-SUBST-301 : Energize EDG 50-R-301 | [29 empty] | 2017-12-19: 2019-03-09; 2017-12-19: 2019-03-09; 2017-12-19: 2019-03-09
2AI102PC02100-08000 | EOF SS 52-SUBST-301 : Energize EDG 50-R-301 | [29 empty] | 2017-12-19: 2019-03-09; 2017-12-19: 2019-03-09; 2017-12-19: 2019-03-09
2AI102PC02100-08001 | GCP Testing, Switch Gear Testing | [29 empty] | 2017-12-19: 2019-03-09; 2017-12-19: 2019-03-09; 2017-12-19: 2019-03-09
2AI102PC02100-08010 | EOF SS 52-SUBST-301 : Energize EDG 50-R-301 | [29 empty] | 2017-12-19: 2019-03-23; 2017-12-19: 2019-03-23; 2017-12-19: 2019-03-23
2AI102PC03000 | EOF SS 52-SUBST-303 : 110V DC Battery Charger
2AI102PC03000-08000 | EOF SS 52-SUBST-303 : 110V DC Battery Charger
2AI102PC03000-08001 | EOF:Polarity check
2AI102PC03000-08005 | EOF:Charging test
2AI102PC03000-08010 | EOF:Discharging test
2AI102PC03100 | EOF SS 52-SUBST-303 : SS Earthing & Lightning
2AI102PC03100-08000 | EOF SS 52-SUBST-303 : SS Earthing & Lightning
2AI102PC03100-08001 | EOF:Continuity testing
2AI102PC03100-08005 | EOF:Earth resistance measurement
2AI102PC03200 | EOF SS 52-SUBST-303 : HV Switchgear testing
2AI102PC03200-08000 | EOF SS 52-SUBST-303 : HV Switchgear testing
2AI102PC03200-08001 | EOF: CT,PT,Breaker Testing
2AI102PC03200-08005 | EOF: IR, Ductor testing
2AI102PC03200-08010 | EOF: Relay & Functional Testing
2AI102PC03200-08015 | EOF Primary Injection Testing
2AI102PC03200-08020 | EOF: Hi-pot Test
2AI102PC03200-08025 | EOF: Stability Testing
2AI102PC03300 | EOF SS 52-SUBST-303 : 24V DC Battery Charger
2AI102PC03300-08000 | EOF SS 52-SUBST-303 : 24V DC Battery Charger
2AI102PC03300-08001 | EOF:Polarity check
2AI102PC03300-08005 | EOF:Charging test
2AI102PC03300-08010 | EOF:Discharging test
2AI102PC03400 | EOF SS 52-SUBST-303 : LV Switchgear testing
2AI102PC03400-08000 | EOF SS 52-SUBST-303 : LV Switchgear testing
2AI102PC03400-08001 | EOF: CT,PT Testing
2AI102PC03400-08005 | EOF: IR, Ductor testing
2AI102PC03400-08010 | EOF: Relay & Functional Testing
2AI102PC03400-08015 | EOF Primary Injection Testing
2AI102PC03400-08020 | EOF: Hi-pot Test
2AI102PC03400-08025 | EOF: Stability Testing
2AI102PC03600 | EOF SS 52-SUBST-303 : 110V AC UPS
2AI102PC03600-08000 | EOF SS 52-SUBST-303 : 110V AC UPS
2AI102PC03600-08001 | EOF:Polarity check
2AI102PC03600-08005 | EOF:Charging test
2AI102PC03600-08010 | EOF:Discharging test
2AI102PC03700 | EOF SS 52-SUBST-303 : Transformer Testing
2AI102PC03700-08000 | EOF SS 52-SUBST-303 : Transformer Testing
2AI102PC03700-08001 | EOF:IR testing/WR testing/Turns ratio testing
2AI102PC03700-08005 | EOF:Functional Test
2AI102PC03700-08010 | EOF:BDV Testing
2AI102PC03900 | EOF SS 52-SUBST-303 : Electrical Tie-ins for Permanent Power & Energize
2AI102PC03900-08000 | EOF SS 52-SUBST-303 : Electrical Tie-ins for Permanent Power & Energize
2AI102PC03900-08001 | EOF:Incoming cables IR and continuity test
2AI102PC03900-08005 | EOF:Incoming HV cables hipot testing
2AI102PC03900-08010 | EOF: Cable Termination
2AI102PC03900-08015 | EOF: Cable Termination
2AI102PC03900-08020 | EOF: Energisation of Substation 52-SUBST-302
2AI102PC03900-08030 | EOF: Energisation of Substation 52-SUBST-303
2AI102PC04000 | EOF SS 52-SUBST-303 : Energize EDG 52-R-303
2AI102PC04000-08000 | EOF SS 52-SUBST-303 : Energize EDG 52-R-303
2AI102PC04000-08001 | EOF: GCP Testing, Switch Gear Testing
2AI102PC04000-08010 | EOF SS 52-SUBST-303 : Energize EDG 52-R-303
2AI102PC04100 | EOF SS 52-SUBST-303 : Lighting & Small Power | [25 empty] | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04
2AI102PC04100-08000 | EOF SS 52-SUBST-303 : Lighting & Small Power | [25 empty] | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04
2AI102PC04100-08001 | EOF:Continuity & IR testing | [25 empty] | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04 | 2017-09-04
2AI102PC04100-08005 | EOF:Lux testing | [29 empty] | 2018-01-02 | 2018-01-02 | 2018-01-02 | 2018-01-02 | 2018-01-02 | 2018-01-02 | 2018-01-02 | 2018-01-02 | 2018-01-02 | 2018-01-02 | 2018-01-02 | 2018-01-02 | 2018-01-02 | 2018-01-02 | 2018-01-02 | 2018-01-02 | 2018-01-02
2AI102PI01000 | UG Piping works | [29 empty] | 2018-01-10 | 2018-01-10 | 2018-01-10 | 2018-01-10 | 2018-01-10 | 2018-01-10 | 2018-01-10 | 2018-01-10 | 2018-01-10 | 2018-01-10 | 2018-01-10 | 2018-01-10 | 2018-01-10 | 2018-01-10 | 2018-01-10 | 2018-01-10 | 2018-01-10
2AI102PI01000-08141 | COCC: Metallic (CS/LTCS) Piping Works | [29 empty] | 2018-01-10 | 2018-01-10 | 2018-01-10 | 2018-01-10 | 2018-01-10 | 2018-01-10 | 2018-01-10 | 2018-01-10 | 2018-01-10 | 2018-01-10 | 2018-01-10 | 2018-01-10 | 2018-01-10 | 2018-01-10 | 2018-01-10 | 2018-01-10 | 2018-01-10
2AI102PI01000-08145 | COCC: Installation of pipes | [29 empty] | 2018-01-10 | 2018-01-10 | 2018-01-10 | 2018-01-10 | 2018-01-10 | 2018-01-10 | 2018-01-10 | 2018-01-10 | 2018-01-10 | 2018-01-10 | 2018-01-10 | 2018-01-10 | 2018-01-10 | 2018-01-10 | 2018-01-10 | 2018-01-10 | 2018-01-10
2AI102PI01000-08150 | COCC:Alignment/Fit-up | [29 empty] | 2018-01-15 | 2018-01-15 | 2018-01-15 | 2018-01-15 | 2018-01-15 | 2018-01-15 | 2018-01-15 | 2018-01-15 | 2018-01-15 | 2018-01-15 | 2018-01-15 | 2018-01-15 | 2018-01-15 | 2018-01-15 | 2018-01-15 | 2018-01-15 | 2018-01-15
2AI102PI01000-08155 | COCC:Welding/Bolting | [29 empty] | 2018-01-15 | 2018-01-15 | 2018-01-15 | 2018-01-15 | 2018-01-15 | 2018-01-15 | 2018-01-15 | 2018-01-15 | 2018-01-15 | 2018-01-15 | 2018-01-15 | 2018-01-15 | 2018-01-15 | 2018-01-15 | 2018-01-15 | 2018-01-15 | 2018-01-15
2AI102PI01000-08160 | COCC:NDE/PWHT/QC Checks of Pipes | [31 empty] | 2018-01-30 | 2018-01-30 | 2018-01-30 | 2018-01-30 | 2018-01-30 | 2018-01-30 | 2018-01-30 | 2018-01-30 | 2018-01-30 | 2018-01-30 | 2018-01-30 | 2018-01-30 | 2018-01-30 | 2018-01-30 | 2018-01-30
2AI102PI01000-08165 | COCC:Coating/Wrapping | [31 empty] | 2018-01-31 | 2018-01-31 | 2018-01-31 | 2018-01-31 | 2018-01-31 | 2018-01-31 | 2018-01-31 | 2018-01-31 | 2018-01-31 | 2018-01-31 | 2018-01-31 | 2018-01-31 | 2018-01-31 | 2018-01-31 | 2018-01-31
2AI102PI01100 | AG Piping works | [35 empty] | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02
2AI102PI01100-08141 | Metallic (CS/LTCS) Piping Works | [35 empty] | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02
2AI102PI01100-08142 | Metallic (SS/SDSS) Piping Works | [39 empty] | 2018-10-05 | 2018-10-05 | 2018-10-05 | 2018-10-05 | 2018-10-05 | 2018-10-05 | 2018-10-05
2AI102PI01100-08145 | EOF:Installation of pipes | [37 empty] | 2018-08-06 | 2018-08-06 | 2018-08-06 | 2018-08-06 | 2018-08-06 | 2018-08-06 | 2018-08-06 | 2018-08-06 | 2018-08-06
2AI102PI01100-08150 | COCC:Alignment/Fit-up | [35 empty] | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02
2AI102PI01100-08155 | COCC:Welding/Bolting | [37 empty] | 2018-08-07 | 2018-08-07 | 2018-08-07 | 2018-08-07 | 2018-08-07 | 2018-08-07 | 2018-08-07 | 2018-08-07 | 2018-08-07
2AI102PI01100-08160 | EOF:NDE/PWHT/QC Checks of Pipes | [37 empty] | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03
2AI102PI01100-08165 | EOF:Install Permanent Supporting for Pipes | [37 empty] | 2018-09-04 | 2018-09-04 | 2018-09-04 | 2018-09-04 | 2018-09-04 | 2018-09-04 | 2018-09-04 | 2018-09-04 | 2018-09-04
2AI102PI01100-08170 | COCC:Install piping valves | [37 empty] | 2018-09-04 | 2018-09-04 | 2018-09-04 | 2018-09-04 | 2018-09-04 | 2018-09-04 | 2018-09-04 | 2018-09-04 | 2018-09-04
2AI102PI01100-08175 | EOF:Installation of pipes | [39 empty] | 2018-10-05 | 2018-10-05 | 2018-10-05 | 2018-10-05 | 2018-10-05 | 2018-10-05 | 2018-10-05
2AI102PI01100-08180 | COCC:Alignment/Fit-up | [39 empty] | 2018-10-07 | 2018-10-07 | 2018-10-07 | 2018-10-07 | 2018-10-07 | 2018-10-07 | 2018-10-07
2AI102PI01100-08185 | COCC:Welding/Bolting | [39 empty] | 2018-10-08 | 2018-10-08 | 2018-10-08 | 2018-10-08 | 2018-10-08 | 2018-10-08 | 2018-10-08
2AI102PI01100-08190 | EOF:NDE/PWHT/QC Checks of Pipes | [37 empty] | 2018-09-04: 2018-12-03; 2018-09-04: 2018-12-03; 2018-09-04: 2018-12-03; 2018-09-04: 2018-12-03; 2018-09-04: 2018-12-03
2AI102PI01100-08195 | COCC: Install Permanent Supporting for Pipes | [37 empty] | 2018-09-04: 2018-12-04; 2018-09-04: 2018-12-04; 2018-09-04: 2018-12-04; 2018-09-04: 2018-12-04; 2018-09-04: 2018-12-04
2AI102PI01100-08200 | COCC: Install piping valves | [37 empty] | 2018-09-04: 2018-11-30; 2018-09-04: 2018-11-30; 2018-09-04: 2018-11-30; 2018-09-04: 2018-11-30; 2018-09-04: 2018-11-30
2AI102PI01200 | COCC: Insulation of Piping | [27 empty] | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09
2AI102PI01200-08005 | COCC: Surface Preparation | [27 empty] | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09
2AI102PI01200-08010 | COCC: Cladding Fabrication | [27 empty] | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09
2AI102PI01200-08015 | COCC: Lagging | [27 empty] | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09
2AI102PI01200-08020 | COCC: Cladding/Fastening/Sealing | [27 empty] | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09
2AI102PI01200-08141 | COCC: Insulation of Piping | [27 empty] | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09 | 2017-10-09
2AI102PI01300 | EOF: Hydrotesting | [29 empty] | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16
2AI102PI01300-08000 | EOF:Test pack preparation & Ready for Test | [29 empty] | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16
2AI102PI01300-08002 | EOF:Pressure Testing & Approval | [29 empty] | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16
2AI102PI01300-08005 | EOF:Reinstatement | [29 empty] | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16
2AI102PI01300-08010 | COCC: Test pack preparation & Ready for Test | [29 empty] | 2018-01-16: 2018-10-08; 2018-01-16: 2018-10-08; 2018-01-16: 2018-10-08; 2018-01-16: 2018-10-08; 2018-01-16: 2018-10-08; 2018-01-16: 2018-10-08; 2018-01-16: 2018-10-08
2AI102PI01300-08015 | COCC: Pressure Testing & Approval | [29 empty] | 2018-01-16: 2018-10-09; 2018-01-16: 2018-10-09; 2018-01-16: 2018-10-09; 2018-01-16: 2018-10-09; 2018-01-16: 2018-10-09; 2018-01-16: 2018-10-09; 2018-01-16: 2018-10-09
2AI102PI01300-08030 | COCC: Reinstatement | [29 empty] | 2018-01-16: 2018-10-09; 2018-01-16: 2018-10-09; 2018-01-16: 2018-10-09; 2018-01-16: 2018-10-09; 2018-01-16: 2018-10-09; 2018-01-16: 2018-10-09; 2018-01-16: 2018-10-09
2AI102PI01300-08035 | EOF:Flange Management | [29 empty] | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16
2AI102PI01300-08040 | COCC: Flange Management | [29 empty] | 2018-01-16: 2018-10-10; 2018-01-16: 2018-10-10; 2018-01-16: 2018-10-10; 2018-01-16: 2018-10-10; 2018-01-16: 2018-10-10; 2018-01-16: 2018-10-10; 2018-01-16: 2018-10-10
2AI102PI01300-08141 | Metallic (CS/LTCS) Piping Works | [29 empty] | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16
2AI102PI01300-08142 | Metallic (SS/SDSS) Piping Works | [29 empty] | 2018-01-16: 2018-10-08; 2018-01-16: 2018-10-08; 2018-01-16: 2018-10-08; 2018-01-16: 2018-10-08; 2018-01-16: 2018-10-08; 2018-01-16: 2018-10-08; 2018-01-16: 2018-10-08
2AI102PI01400 | EOF: Touch-up painting of Piping | [31 empty] | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05
2AI102PI01400-08000 | COCC:Touch-up painting of CS Pipe | [31 empty] | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05
2AI102PI01400-08010 | COCC: Touch-up painting of SS Pipe | [31 empty] | 2018-02-05: 2019-01-07; 2018-02-05: 2019-01-07; 2018-02-05: 2019-01-07; 2018-02-05: 2019-01-07; 2018-02-05: 2019-01-07
2AI102PI01400-08141 | COCC: Touch-up painting of Piping | [31 empty] | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05
2AI102TE01000 | EOF: Telecom Cable Laying to COCC | [35 empty] | 2018-06-17 | 2018-06-17 | 2018-06-17 | 2018-06-17 | 2018-06-17 | 2018-06-17 | 2018-06-17 | 2018-06-17 | 2018-06-17 | 2018-06-17 | 2018-06-17
2AI102TE01000-08100 | EOF: Issue AFC Drawings TELECOM CABLE LAYING TO COCC | [23 empty] | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24
2AI102TE01000-08141 | Fiber Optic Cable Laying in boudery Limit of COCC Area | [35 empty] | 2018-06-17 | 2018-06-17 | 2018-06-17 | 2018-06-17 | 2018-06-17 | 2018-06-17 | 2018-06-17 | 2018-06-17 | 2018-06-17 | 2018-06-17 | 2018-06-17
2AI102TE01100 | EOF: Telecom Cable Laying from COCC to Substation | [35 empty] | 2018-06-17: 2019-04-08
2AI102TE01100-08100 | EOF: Issue AFC DrawingsTELECOM CABLE LAYING FROM COCC TO SUBSTATION | [23 empty] | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24
2AI102TE01100-08141 | Fiber Optic Cable Laying from Boundery Limit to 52-SUBST-302 | [23 empty] | 2017-07-24: 2019-04-08
2AI103CV01200 | EOF: Structural Steel of Ground Supported Platforms | [21 empty] | 2017-04-22 | 2017-04-22 | 2017-04-22 | 2017-04-22 | 2017-04-22 | 2017-04-22 | 2017-04-22 | 2017-04-22 | 2017-04-22 | 2017-04-22 | 2017-04-22 | 2017-04-22 | 2017-04-22 | 2017-04-22 | 2017-04-22 | 2017-04-22 | 2017-04-22 | 2017-04-22 | 2017-04-22 | 2017-04-22 | 2017-04-22 | 2017-04-22 | 2017-04-22 | 2017-04-22 | 2017-04-22
2AI103CV01200-08000 | EOF: Structural Steel of Ground Supported /Equipment Mounted Platforms | [21 empty] | 2017-04-22 | 2017-04-22 | 2017-04-22 | 2017-04-22 | 2017-04-22 | 2017-04-22 | 2017-04-22 | 2017-04-22 | 2017-04-22 | 2017-04-22 | 2017-04-22 | 2017-04-22 | 2017-04-22 | 2017-04-22 | 2017-04-22 | 2017-04-22 | 2017-04-22 | 2017-04-22 | 2017-04-22 | 2017-04-22 | 2017-04-22 | 2017-04-22 | 2017-04-22 | 2017-04-22 | 2017-04-22
2AI103CV01200-08001 | EOF:Installation of Str. Steel of Ground Supported Platforms | [21 empty] | 2017-04-22 | 2017-04-22 | 2017-04-22 | 2017-04-22 | 2017-04-22 | 2017-04-22 | 2017-04-22 | 2017-04-22 | 2017-04-22 | 2017-04-22 | 2017-04-22 | 2017-04-22 | 2017-04-22 | 2017-04-22 | 2017-04-22 | 2017-04-22 | 2017-04-22 | 2017-04-22 | 2017-04-22 | 2017-04-22 | 2017-04-22 | 2017-04-22 | 2017-04-22 | 2017-04-22 | 2017-04-22
2AI103CV01200-08005 | EOF: Pipe Support & EIT Supports Erection | [23 empty] | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25
2AI103CV01200-08006 | EOF:Alignment & Bolting/Torqueing of Ground Supported Platforms | [21 empty] | 2017-05-10 | 2017-05-10 | 2017-05-10 | 2017-05-10 | 2017-05-10 | 2017-05-10 | 2017-05-10 | 2017-05-10 | 2017-05-10 | 2017-05-10 | 2017-05-10 | 2017-05-10 | 2017-05-10 | 2017-05-10 | 2017-05-10 | 2017-05-10 | 2017-05-10 | 2017-05-10 | 2017-05-10 | 2017-05-10 | 2017-05-10 | 2017-05-10 | 2017-05-10 | 2017-05-10 | 2017-05-10
2AI103CV01200-08010 | EOF:Grouting of Ground Supported Platforms | [27 empty] | 2017-11-14 | 2017-11-14 | 2017-11-14 | 2017-11-14 | 2017-11-14 | 2017-11-14 | 2017-11-14 | 2017-11-14 | 2017-11-14 | 2017-11-14 | 2017-11-14 | 2017-11-14 | 2017-11-14 | 2017-11-14 | 2017-11-14 | 2017-11-14 | 2017-11-14 | 2017-11-14 | 2017-11-14
2AI103CV01200-08015 | EOF:Installation of Str. Steel of Ground Supported Platforms | [23 empty] | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25
2AI103CV01200-08020 | EOF:Alignment & Bolting/Torqueing of Ground Supported Platforms | [23 empty] | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25
2AI103CV01200-08025 | EOF:Grouting of Ground Supported Platforms | [29 empty] | 2017-12-10 | 2017-12-10 | 2017-12-10 | 2017-12-10 | 2017-12-10 | 2017-12-10 | 2017-12-10 | 2017-12-10 | 2017-12-10 | 2017-12-10 | 2017-12-10 | 2017-12-10 | 2017-12-10 | 2017-12-10 | 2017-12-10 | 2017-12-10 | 2017-12-10
2AI103CV18300 | EOF: RCC Cable trench | [17 empty] | 2016-12-19 | 2016-12-19 | 2016-12-19 | 2016-12-19 | 2016-12-19 | 2016-12-19 | 2016-12-19 | 2016-12-19 | 2016-12-19 | 2016-12-19 | 2016-12-19 | 2016-12-19 | 2016-12-19 | 2016-12-19 | 2016-12-19 | 2016-12-19 | 2016-12-19 | 2016-12-19 | 2016-12-19 | 2016-12-19 | 2016-12-19 | 2016-12-19 | 2016-12-19 | 2016-12-19 | 2016-12-19 | 2016-12-19 | 2016-12-19 | 2016-12-19 | 2016-12-19
2AI103CV18300-08000 | EOF: Cable trench | [17 empty] | 2016-12-19 | 2016-12-19 | 2016-12-19 | 2016-12-19 | 2016-12-19 | 2016-12-19 | 2016-12-19 | 2016-12-19 | 2016-12-19 | 2016-12-19 | 2016-12-19 | 2016-12-19 | 2016-12-19 | 2016-12-19 | 2016-12-19 | 2016-12-19 | 2016-12-19 | 2016-12-19 | 2016-12-19 | 2016-12-19 | 2016-12-19 | 2016-12-19 | 2016-12-19 | 2016-12-19 | 2016-12-19 | 2016-12-19 | 2016-12-19 | 2016-12-19 | 2016-12-19
2AI103CV18300-08035 | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material | [17 empty] | 2016-12-19 | 2016-12-19 | 2016-12-19 | 2016-12-19 | 2016-12-19 | 2016-12-19 | 2016-12-19 | 2016-12-19 | 2016-12-19 | 2016-12-19 | 2016-12-19 | 2016-12-19 | 2016-12-19 | 2016-12-19 | 2016-12-19 | 2016-12-19 | 2016-12-19 | 2016-12-19 | 2016-12-19 | 2016-12-19 | 2016-12-19 | 2016-12-19 | 2016-12-19 | 2016-12-19 | 2016-12-19 | 2016-12-19 | 2016-12-19 | 2016-12-19 | 2016-12-19
2AI103CV18300-08040 | EOF:Sand bedding | [19 empty] | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28
2AI103CV18300-08041 | EOF:Sand Padding | [19 empty] | 2017-03-22 | 2017-03-22 | 2017-03-22 | 2017-03-22 | 2017-03-22 | 2017-03-22 | 2017-03-22 | 2017-03-22 | 2017-03-22 | 2017-03-22 | 2017-03-22 | 2017-03-22 | 2017-03-22 | 2017-03-22 | 2017-03-22 | 2017-03-22 | 2017-03-22 | 2017-03-22 | 2017-03-22 | 2017-03-22 | 2017-03-22 | 2017-03-22 | 2017-03-22 | 2017-03-22 | 2017-03-22 | 2017-03-22 | 2017-03-22
2AI103CV18300-08045 | EOF:Install Cable Tile Laying & warning Tapes | [19 empty] | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23
2AI103CV18300-08050 | EOF:Backfilling & Compaction | [21 empty] | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16
2AI103CV18300-08055 | EOF:Install Route/saftey Markers | [23 empty] | 2017-07-18 | 2017-07-18 | 2017-07-18 | 2017-07-18 | 2017-07-18 | 2017-07-18 | 2017-07-18 | 2017-07-18 | 2017-07-18 | 2017-07-18 | 2017-07-18 | 2017-07-18 | 2017-07-18 | 2017-07-18 | 2017-07-18 | 2017-07-18 | 2017-07-18 | 2017-07-18 | 2017-07-18 | 2017-07-18 | 2017-07-18 | 2017-07-18 | 2017-07-18
2AI103CV18300-08125 | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material | [35 empty] | 2018-07-01 | 2018-07-01 | 2018-07-01 | 2018-07-01 | 2018-07-01 | 2018-07-01 | 2018-07-01 | 2018-07-01 | 2018-07-01 | 2018-07-01 | 2018-07-01
2AI103CV18300-08135 | EOF:Sand bedding | [35 empty] | 2018-07-03 | 2018-07-03 | 2018-07-03 | 2018-07-03 | 2018-07-03 | 2018-07-03 | 2018-07-03 | 2018-07-03 | 2018-07-03 | 2018-07-03 | 2018-07-03
2AI103CV18300-08136 | EOF:Sand Padding | [35 empty] | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07
2AI103CV18300-08145 | EOF:Install Cable Tile Laying & warning Tapes | [35 empty] | 2018-07-06 | 2018-07-06 | 2018-07-06 | 2018-07-06 | 2018-07-06 | 2018-07-06 | 2018-07-06 | 2018-07-06 | 2018-07-06 | 2018-07-06 | 2018-07-06
2AI103CV18300-08150 | EOF:Backfilling & Compaction | [35 empty] | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07
2AI103CV18300-08155 | EOF:Install Route/saftey Markers | [35 empty] | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07
2AI103CV18300-08160 | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material | [21 empty] | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01
2AI103CV18300-08165 | EOF:Sand bedding | [21 empty] | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04
2AI103CV18300-08166 | EOF:Sand Padding | [23 empty] | 2017-06-24 | 2017-06-24 | 2017-06-24 | 2017-06-24 | 2017-06-24 | 2017-06-24 | 2017-06-24 | 2017-06-24 | 2017-06-24 | 2017-06-24 | 2017-06-24 | 2017-06-24 | 2017-06-24 | 2017-06-24 | 2017-06-24 | 2017-06-24 | 2017-06-24 | 2017-06-24 | 2017-06-24 | 2017-06-24 | 2017-06-24 | 2017-06-24 | 2017-06-24
2AI103CV18300-08170 | EOF:Install Cable Tile Laying & warning Tapes | [25 empty] | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29
2AI103CV18300-08175 | EOF:Backfilling & Compaction | [25 empty] | 2017-07-31 | 2017-07-31 | 2017-07-31 | 2017-07-31 | 2017-07-31 | 2017-07-31 | 2017-07-31 | 2017-07-31 | 2017-07-31 | 2017-07-31 | 2017-07-31 | 2017-07-31 | 2017-07-31 | 2017-07-31 | 2017-07-31 | 2017-07-31 | 2017-07-31 | 2017-07-31 | 2017-07-31 | 2017-07-31 | 2017-07-31
2AI103CV18300-08180 | EOF:Install Route/saftey Markers
2AI103CV18300-08285 | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material | [19 empty] | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04
2AI103CV18300-08290 | EOF:Sand bedding | [19 empty] | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05
2AI103CV18300-08291 | EOF:Sand Padding | [21 empty] | 2017-05-21 | 2017-05-21 | 2017-05-21 | 2017-05-21 | 2017-05-21 | 2017-05-21 | 2017-05-21 | 2017-05-21 | 2017-05-21 | 2017-05-21 | 2017-05-21 | 2017-05-21 | 2017-05-21 | 2017-05-21 | 2017-05-21 | 2017-05-21 | 2017-05-21 | 2017-05-21 | 2017-05-21 | 2017-05-21 | 2017-05-21 | 2017-05-21 | 2017-05-21 | 2017-05-21 | 2017-05-21
2AI103CV18300-08295 | EOF:Install Cable Tile Laying & warning Tapes | [27 empty] | 2017-11-07 | 2017-11-07 | 2017-11-07 | 2017-11-07 | 2017-11-07 | 2017-11-07 | 2017-11-07 | 2017-11-07 | 2017-11-07 | 2017-11-07 | 2017-11-07 | 2017-11-07 | 2017-11-07 | 2017-11-07 | 2017-11-07 | 2017-11-07 | 2017-11-07 | 2017-11-07 | 2017-11-07
2AI103CV18300-08300 | EOF:Backfilling & Compaction | [27 empty] | 2017-11-21 | 2017-11-21 | 2017-11-21 | 2017-11-21 | 2017-11-21 | 2017-11-21 | 2017-11-21 | 2017-11-21 | 2017-11-21 | 2017-11-21 | 2017-11-21 | 2017-11-21 | 2017-11-21 | 2017-11-21 | 2017-11-21 | 2017-11-21 | 2017-11-21 | 2017-11-21 | 2017-11-21
2AI103CV18300-08305 | EOF:Install Route/saftey Markers
2AI103CV18300-08335 | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material | [35 empty] | 2018-06-13 | 2018-06-13 | 2018-06-13 | 2018-06-13 | 2018-06-13 | 2018-06-13 | 2018-06-13 | 2018-06-13 | 2018-06-13 | 2018-06-13 | 2018-06-13
2AI103CV18300-08340 | EOF:Sand bedding | [35 empty] | 2018-06-27 | 2018-06-27 | 2018-06-27 | 2018-06-27 | 2018-06-27 | 2018-06-27 | 2018-06-27 | 2018-06-27 | 2018-06-27 | 2018-06-27 | 2018-06-27
2AI103CV18300-08341 | EOF:Sand Padding | [35 empty] | 2018-07-01 | 2018-07-01 | 2018-07-01 | 2018-07-01 | 2018-07-01 | 2018-07-01 | 2018-07-01 | 2018-07-01 | 2018-07-01 | 2018-07-01 | 2018-07-01
2AI103CV18300-08345 | EOF:Install Cable Tile Laying & warning Tapes | [35 empty] | 2018-07-13 | 2018-07-13 | 2018-07-13 | 2018-07-13 | 2018-07-13 | 2018-07-13 | 2018-07-13 | 2018-07-13 | 2018-07-13 | 2018-07-13 | 2018-07-13
2AI103CV18300-08350 | EOF:Backfilling & Compaction | [35 empty] | 2018-07-22 | 2018-07-22 | 2018-07-22 | 2018-07-22 | 2018-07-22 | 2018-07-22 | 2018-07-22 | 2018-07-22 | 2018-07-22 | 2018-07-22 | 2018-07-22
2AI103CV18300-08355 | EOF:Install Route/saftey Markers
2AI103CV18300-08360 | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material | [35 empty] | 2018-06-02 | 2018-06-02 | 2018-06-02 | 2018-06-02 | 2018-06-02 | 2018-06-02 | 2018-06-02 | 2018-06-02 | 2018-06-02 | 2018-06-02 | 2018-06-02
2AI103CV18300-08365 | EOF:Sand bedding | [35 empty] | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04
2AI103CV18300-08366 | EOF:Sand Padding | [35 empty] | 2018-06-21 | 2018-06-21 | 2018-06-21 | 2018-06-21 | 2018-06-21 | 2018-06-21 | 2018-06-21 | 2018-06-21 | 2018-06-21 | 2018-06-21 | 2018-06-21
2AI103CV18300-08370 | EOF:Install Cable Tile Laying & warning Tapes | [35 empty] | 2018-06-20 | 2018-06-20 | 2018-06-20 | 2018-06-20 | 2018-06-20 | 2018-06-20 | 2018-06-20 | 2018-06-20 | 2018-06-20 | 2018-06-20 | 2018-06-20
2AI103CV18300-08375 | EOF:Backfilling & Compaction | [35 empty] | 2018-06-22 | 2018-06-22 | 2018-06-22 | 2018-06-22 | 2018-06-22 | 2018-06-22 | 2018-06-22 | 2018-06-22 | 2018-06-22 | 2018-06-22 | 2018-06-22
2AI103CV18300-08380 | EOF:Install Route/saftey Markers
2AI103CV18300-08435 | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material | [33 empty] | 2018-03-29 | 2018-03-29 | 2018-03-29 | 2018-03-29 | 2018-03-29 | 2018-03-29 | 2018-03-29 | 2018-03-29 | 2018-03-29 | 2018-03-29 | 2018-03-29 | 2018-03-29 | 2018-03-29
2AI103CV18300-08440 | EOF:Sand bedding | [33 empty] | 2018-03-31 | 2018-03-31 | 2018-03-31 | 2018-03-31 | 2018-03-31 | 2018-03-31 | 2018-03-31 | 2018-03-31 | 2018-03-31 | 2018-03-31 | 2018-03-31 | 2018-03-31 | 2018-03-31
2AI103CV18300-08441 | EOF:Sand Padding | [33 empty] | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02
2AI103CV18300-08445 | EOF:Install Cable Tile Laying & warning Tapes | [33 empty] | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04
2AI103CV18300-08450 | EOF:Backfilling & Compaction | [33 empty] | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06 | 2018-04-06
2AI103CV18300-08455 | EOF:Install Route/saftey Markers | [33 empty] | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08
2AI103CV18400 | EOF: Mobile Foam Cannon and Mobile Monitor Shelter Foundation | [13 empty] | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30
2AI103CV18400-08000 | EOF: Mobile Foam Cannon and Mobile Monitor Shelter Foundation | [13 empty] | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30
2AI103CV18400-08001 | EOF:Survey Marking, Excavation & Subgrade | [13 empty] | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30
2AI103CV18400-08005 | EOF:Blinding/PCC for Fnd | [13 empty] | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08
2AI103CV18400-08010 | EOF:Rebar, Formwork for Footing | [13 empty] | 2016-09-20 | 2016-09-20 | 2016-09-20 | 2016-09-20 | 2016-09-20 | 2016-09-20 | 2016-09-20 | 2016-09-20 | 2016-09-20 | 2016-09-20 | 2016-09-20 | 2016-09-20 | 2016-09-20 | 2016-09-20 | 2016-09-20 | 2016-09-20 | 2016-09-20 | 2016-09-20 | 2016-09-20 | 2016-09-20 | 2016-09-20 | 2016-09-20 | 2016-09-20 | 2016-09-20 | 2016-09-20 | 2016-09-20 | 2016-09-20 | 2016-09-20 | 2016-09-20 | 2016-09-20 | 2016-09-20 | 2016-09-20 | 2016-09-20
2AI103CV18400-08011 | EOF:Concrete Pouring - for Footing | [15 empty] | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06
2AI103CV18400-08015 | EOF:Rebar, Formwork, Install Embedments for Pedestal | [15 empty] | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03 | 2016-10-03
2AI103CV18400-08016 | EOF:Concrete Pouring - for Pedestal | [15 empty] | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06
2AI103CV18400-08020 | EOF:Concrete Potection for Fnd | [15 empty] | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20
2AI103CV18400-08025 | EOF:Backfilling & Compaction for Fnd | [15 empty] | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21
2AI103CV18500 | EOF: Mobile Foam Cannon and Mobile Monitor Shelter Erection | [17 empty] | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07
2AI103CV18500-08000 | EOF: Mobile Foam Cannon and Mobile Monitor Shelter Erection | [17 empty] | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07
2AI103CV18500-08001 | EOF:Installation of Str. Steel Mobile Foam Cannon and Mobile Monitor Shelter | [17 empty] | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07
2AI103CV18500-08005 | EOF:Alignment & Bolting/Torqueing Mobile Foam Cannon and Mobile Monitor Shelter | [21 empty] | 2017-05-11 | 2017-05-11 | 2017-05-11 | 2017-05-11 | 2017-05-11 | 2017-05-11 | 2017-05-11 | 2017-05-11 | 2017-05-11 | 2017-05-11 | 2017-05-11 | 2017-05-11 | 2017-05-11 | 2017-05-11 | 2017-05-11 | 2017-05-11 | 2017-05-11 | 2017-05-11 | 2017-05-11 | 2017-05-11 | 2017-05-11 | 2017-05-11 | 2017-05-11 | 2017-05-11 | 2017-05-11
2AI103CV18500-08010 | EOF:Grouting Mobile Foam Cannon and Mobile Monitor Shelter | [37 empty] | 2018-08-10 | 2018-08-10 | 2018-08-10 | 2018-08-10 | 2018-08-10 | 2018-08-10 | 2018-08-10 | 2018-08-10 | 2018-08-10
2AI103CV18600 | EOF: Foundation for Steel Structure | [17 empty] | 2016-11-26 | 2016-11-26 | 2016-11-26 | 2016-11-26 | 2016-11-26 | 2016-11-26 | 2016-11-26 | 2016-11-26 | 2016-11-26 | 2016-11-26 | 2016-11-26 | 2016-11-26 | 2016-11-26 | 2016-11-26 | 2016-11-26 | 2016-11-26 | 2016-11-26 | 2016-11-26 | 2016-11-26 | 2016-11-26 | 2016-11-26 | 2016-11-26 | 2016-11-26 | 2016-11-26 | 2016-11-26 | 2016-11-26 | 2016-11-26 | 2016-11-26 | 2016-11-26
2AI103CV18600-08000 | EOF: Foundation for Tank Stairways Structural Steel | [17 empty] | 2016-11-26 | 2016-11-26 | 2016-11-26 | 2016-11-26 | 2016-11-26 | 2016-11-26 | 2016-11-26 | 2016-11-26 | 2016-11-26 | 2016-11-26 | 2016-11-26 | 2016-11-26 | 2016-11-26 | 2016-11-26 | 2016-11-26 | 2016-11-26 | 2016-11-26 | 2016-11-26 | 2016-11-26 | 2016-11-26 | 2016-11-26 | 2016-11-26 | 2016-11-26 | 2016-11-26 | 2016-11-26 | 2016-11-26 | 2016-11-26 | 2016-11-26 | 2016-11-26
2AI103CV18600-08001 | EOF:Survey Marking, Excavation & Subgrade | [17 empty] | 2016-12-14 | 2016-12-14 | 2016-12-14 | 2016-12-14 | 2016-12-14 | 2016-12-14 | 2016-12-14 | 2016-12-14 | 2016-12-14 | 2016-12-14 | 2016-12-14 | 2016-12-14 | 2016-12-14 | 2016-12-14 | 2016-12-14 | 2016-12-14 | 2016-12-14 | 2016-12-14 | 2016-12-14 | 2016-12-14 | 2016-12-14 | 2016-12-14 | 2016-12-14 | 2016-12-14 | 2016-12-14 | 2016-12-14 | 2016-12-14 | 2016-12-14 | 2016-12-14
2AI103CV18600-08002 | EOF:Survey Marking, Excavation & Subgrade | [17 empty] | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08
2AI103CV18600-08005 | EOF:Blinding/PCC for Fnd | [17 empty] | 2016-12-21 | 2016-12-21 | 2016-12-21 | 2016-12-21 | 2016-12-21 | 2016-12-21 | 2016-12-21 | 2016-12-21 | 2016-12-21 | 2016-12-21 | 2016-12-21 | 2016-12-21 | 2016-12-21 | 2016-12-21 | 2016-12-21 | 2016-12-21 | 2016-12-21 | 2016-12-21 | 2016-12-21 | 2016-12-21 | 2016-12-21 | 2016-12-21 | 2016-12-21 | 2016-12-21 | 2016-12-21 | 2016-12-21 | 2016-12-21 | 2016-12-21 | 2016-12-21
2AI103CV18600-08010 | EOF:Rebar, Formwork for Footing | [17 empty] | 2016-12-22 | 2016-12-22 | 2016-12-22 | 2016-12-22 | 2016-12-22 | 2016-12-22 | 2016-12-22 | 2016-12-22 | 2016-12-22 | 2016-12-22 | 2016-12-22 | 2016-12-22 | 2016-12-22 | 2016-12-22 | 2016-12-22 | 2016-12-22 | 2016-12-22 | 2016-12-22 | 2016-12-22 | 2016-12-22 | 2016-12-22 | 2016-12-22 | 2016-12-22 | 2016-12-22 | 2016-12-22 | 2016-12-22 | 2016-12-22 | 2016-12-22 | 2016-12-22
2AI103CV18600-08011 | EOF:Concrete Pouring - for Footing | [17 empty] | 2016-12-27 | 2016-12-27 | 2016-12-27 | 2016-12-27 | 2016-12-27 | 2016-12-27 | 2016-12-27 | 2016-12-27 | 2016-12-27 | 2016-12-27 | 2016-12-27 | 2016-12-27 | 2016-12-27 | 2016-12-27 | 2016-12-27 | 2016-12-27 | 2016-12-27 | 2016-12-27 | 2016-12-27 | 2016-12-27 | 2016-12-27 | 2016-12-27 | 2016-12-27 | 2016-12-27 | 2016-12-27 | 2016-12-27 | 2016-12-27 | 2016-12-27 | 2016-12-27
2AI103CV18600-08015 | EOF:Rebar, Formwork, Install Embedments for Pedestal | [17 empty] | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29
2AI103CV18600-08016 | EOF:Concrete Pouring - for Pedestal | [19 empty] | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01 | 2017-02-01
2AI103CV18600-08020 | EOF:Concrete Potection for Fnd | [19 empty] | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06
2AI103CV18600-08025 | EOF:Backfilling & Compaction for Fnd | [19 empty] | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07
2AI103CV18600-08030 | EOF:Blinding/PCC for Fnd | [17 empty] | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15
2AI103CV18600-08035 | EOF:Rebar, Formwork for Footing | [17 empty] | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17 | 2016-12-17
2AI103CV18600-08036 | EOF:Concrete Pouring - for Footing | [17 empty] | 2016-12-22 | 2016-12-22 | 2016-12-22 | 2016-12-22 | 2016-12-22 | 2016-12-22 | 2016-12-22 | 2016-12-22 | 2016-12-22 | 2016-12-22 | 2016-12-22 | 2016-12-22 | 2016-12-22 | 2016-12-22 | 2016-12-22 | 2016-12-22 | 2016-12-22 | 2016-12-22 | 2016-12-22 | 2016-12-22 | 2016-12-22 | 2016-12-22 | 2016-12-22 | 2016-12-22 | 2016-12-22 | 2016-12-22 | 2016-12-22 | 2016-12-22 | 2016-12-22
2AI103CV18600-08040 | EOF:Rebar, Formwork, Install Embedments for Pedestal | [17 empty] | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28
2AI103CV18600-08041 | EOF:Concrete Pouring - for Pedestal | [19 empty] | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02
2AI103CV18600-08045 | EOF:Concrete Potection for Fnd | [19 empty] | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11
2AI103CV18600-08050 | EOF:Backfilling & Compaction for Fnd | [19 empty] | 2017-02-20 | 2017-02-20 | 2017-02-20 | 2017-02-20 | 2017-02-20 | 2017-02-20 | 2017-02-20 | 2017-02-20 | 2017-02-20 | 2017-02-20 | 2017-02-20 | 2017-02-20 | 2017-02-20 | 2017-02-20 | 2017-02-20 | 2017-02-20 | 2017-02-20 | 2017-02-20 | 2017-02-20 | 2017-02-20 | 2017-02-20 | 2017-02-20 | 2017-02-20 | 2017-02-20 | 2017-02-20 | 2017-02-20 | 2017-02-20
2AI103CV18600-08065 | EOF:Survey Marking, Excavation & Subgrade | [17 empty] | 2016-11-28 | 2016-11-28 | 2016-11-28 | 2016-11-28 | 2016-11-28 | 2016-11-28 | 2016-11-28 | 2016-11-28 | 2016-11-28 | 2016-11-28 | 2016-11-28 | 2016-11-28 | 2016-11-28 | 2016-11-28 | 2016-11-28 | 2016-11-28 | 2016-11-28 | 2016-11-28 | 2016-11-28 | 2016-11-28 | 2016-11-28 | 2016-11-28 | 2016-11-28 | 2016-11-28 | 2016-11-28 | 2016-11-28 | 2016-11-28 | 2016-11-28 | 2016-11-28
2AI103CV18600-08070 | EOF:Blinding/PCC for Fnd | [17 empty] | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05
2AI103CV18600-08075 | EOF:Rebar, Formwork for Footing | [17 empty] | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07 | 2016-12-07
2AI103CV18600-08076 | EOF:Concrete Pouring - for Footing | [17 empty] | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13
2AI103CV18600-08080 | EOF:Rebar, Formwork, Install Embedments for Pedestal | [17 empty] | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28
2AI103CV18600-08081 | EOF:Concrete Pouring - for Pedestal | [19 empty] | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29
2AI103CV18600-08085 | EOF:Concrete Potection for Fnd | [19 empty] | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06
2AI103CV18600-08090 | EOF:Backfilling & Compaction for Fnd | [19 empty] | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08
2AI103CV18600-08105 | EOF:Survey Marking, Excavation & Subgrade | [17 empty] | 2016-11-26 | 2016-11-26 | 2016-11-26 | 2016-11-26 | 2016-11-26 | 2016-11-26 | 2016-11-26 | 2016-11-26 | 2016-11-26 | 2016-11-26 | 2016-11-26 | 2016-11-26 | 2016-11-26 | 2016-11-26 | 2016-11-26 | 2016-11-26 | 2016-11-26 | 2016-11-26 | 2016-11-26 | 2016-11-26 | 2016-11-26 | 2016-11-26 | 2016-11-26 | 2016-11-26 | 2016-11-26 | 2016-11-26 | 2016-11-26 | 2016-11-26 | 2016-11-26
2AI103CV18600-08110 | EOF:Blinding/PCC for Fnd | [17 empty] | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04
2AI103CV18600-08115 | EOF:Rebar, Formwork for Footing | [17 empty] | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05
2AI103CV18600-08116 | EOF:Concrete Pouring - for Footing | [17 empty] | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12 | 2016-12-12
2AI103CV18600-08120 | EOF:Rebar, Formwork, Install Embedments for Pedestal | [17 empty] | 2016-12-22 | 2016-12-22 | 2016-12-22 | 2016-12-22 | 2016-12-22 | 2016-12-22 | 2016-12-22 | 2016-12-22 | 2016-12-22 | 2016-12-22 | 2016-12-22 | 2016-12-22 | 2016-12-22 | 2016-12-22 | 2016-12-22 | 2016-12-22 | 2016-12-22 | 2016-12-22 | 2016-12-22 | 2016-12-22 | 2016-12-22 | 2016-12-22 | 2016-12-22 | 2016-12-22 | 2016-12-22 | 2016-12-22 | 2016-12-22 | 2016-12-22 | 2016-12-22
2AI103CV18600-08121 | EOF:Concrete Pouring - for Pedestal | [17 empty] | 2017-01-25 | 2017-01-25 | 2017-01-25 | 2017-01-25 | 2017-01-25 | 2017-01-25 | 2017-01-25 | 2017-01-25 | 2017-01-25 | 2017-01-25 | 2017-01-25 | 2017-01-25 | 2017-01-25 | 2017-01-25 | 2017-01-25 | 2017-01-25 | 2017-01-25 | 2017-01-25 | 2017-01-25 | 2017-01-25 | 2017-01-25 | 2017-01-25 | 2017-01-25 | 2017-01-25 | 2017-01-25 | 2017-01-25 | 2017-01-25 | 2017-01-25 | 2017-01-25
2AI103CV18600-08125 | EOF:Concrete Potection for Fnd | [19 empty] | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05 | 2017-02-05
2AI103CV18600-08130 | EOF:Backfilling & Compaction for Fnd | [19 empty] | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07 | 2017-02-07
2AI103CV18700 | EOF: Structural Steel Erection | [19 empty] | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04
2AI103CV18700-08000 | EOF: Tank Stairways - Structural Steel Erection | [19 empty] | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04
2AI103CV18700-08001 | Installation of Main steel structure | [19 empty] | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06
2AI103CV18700-08005 | Installation of Main steel structure | [19 empty] | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05
2AI103CV18700-08010 | Alignment/Welding/Bolting | [19 empty] | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05
2AI103CV18700-08015 | Torque Bolts (wherever applicable) | [19 empty] | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05
2AI103CV18700-08020 | Grouting (wherever applicable) | [35 empty] | 2018-06-10 | 2018-06-10 | 2018-06-10 | 2018-06-10 | 2018-06-10 | 2018-06-10 | 2018-06-10 | 2018-06-10 | 2018-06-10 | 2018-06-10 | 2018-06-10
2AI103CV18700-08025 | Installation of gratings/handrail/ladder | [23 empty] | 2017-07-04 | 2017-07-04 | 2017-07-04 | 2017-07-04 | 2017-07-04 | 2017-07-04 | 2017-07-04 | 2017-07-04 | 2017-07-04 | 2017-07-04 | 2017-07-04 | 2017-07-04 | 2017-07-04 | 2017-07-04 | 2017-07-04 | 2017-07-04 | 2017-07-04 | 2017-07-04 | 2017-07-04 | 2017-07-04 | 2017-07-04 | 2017-07-04 | 2017-07-04
2AI103CV18700-08030 | Alignment/Welding/Bolting | [19 empty] | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06
2AI103CV18700-08035 | Torque Bolts (wherever applicable) | [19 empty] | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06
2AI103CV18700-08040 | Grouting (wherever applicable) | [35 empty] | 2018-07-03 | 2018-07-03 | 2018-07-03 | 2018-07-03 | 2018-07-03 | 2018-07-03 | 2018-07-03 | 2018-07-03 | 2018-07-03 | 2018-07-03 | 2018-07-03
2AI103CV18700-08045 | Installation of gratings/handrail/ladder | [23 empty] | 2017-07-04 | 2017-07-04 | 2017-07-04 | 2017-07-04 | 2017-07-04 | 2017-07-04 | 2017-07-04 | 2017-07-04 | 2017-07-04 | 2017-07-04 | 2017-07-04 | 2017-07-04 | 2017-07-04 | 2017-07-04 | 2017-07-04 | 2017-07-04 | 2017-07-04 | 2017-07-04 | 2017-07-04 | 2017-07-04 | 2017-07-04 | 2017-07-04 | 2017-07-04
2AI103CV18700-08050 | Installation of Main steel structure | [19 empty] | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09
2AI103CV18700-08055 | Alignment/Welding/Bolting | [19 empty] | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09
2AI103CV18700-08060 | Torque Bolts (wherever applicable) | [19 empty] | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09 | 2017-03-09
2AI103CV18700-08065 | Grouting (wherever applicable) | [37 empty] | 2018-08-23 | 2018-08-23 | 2018-08-23 | 2018-08-23 | 2018-08-23 | 2018-08-23 | 2018-08-23 | 2018-08-23 | 2018-08-23
2AI103CV18700-08070 | Installation of gratings/handrail/ladder | [23 empty] | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07
2AI103CV18700-08075 | Installation of Main steel structure | [19 empty] | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04
2AI103CV18700-08080 | Alignment/Welding/Bolting | [19 empty] | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04
2AI103CV18700-08085 | Torque Bolts (wherever applicable) | [19 empty] | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04
2AI103CV18700-08090 | Grouting (wherever applicable) | [37 empty] | 2018-09-26 | 2018-09-26 | 2018-09-26 | 2018-09-26 | 2018-09-26 | 2018-09-26 | 2018-09-26 | 2018-09-26 | 2018-09-26
2AI103CV18700-08095 | Installation of gratings/handrail/ladder | [23 empty] | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07
2AI103CV18800 | EOF: Pump Foundation | [17 empty] | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30
2AI103CV18800-08000 | EOF:Survey Marking, Excavation & Subgrade | [17 empty] | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30
2AI103CV18800-08005 | EOF: 621-G-302 A/B Foam Pump Foundation | [17 empty] | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30
2AI103CV18800-08006 | EOF:Blinding/PCC for Fnd | [17 empty] | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04
2AI103CV18800-08010 | EOF: 621-G-302 C/D Foam Pump Foundation | [17 empty] | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05
2AI103CV18800-08011 | EOF:Rebar, Formwork for Footing | [17 empty] | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05
2AI103CV18800-08015 | EOF:Rebar, Formwork, Install Embedments for Pedestal | [17 empty] | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05
2AI103CV18800-08016 | Concrete Pouring - for Pedestal | [17 empty] | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13
2AI103CV18800-08018 | Concrete Pouring - for Footing | [17 empty] | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13
2AI103CV18800-08020 | EOF:Concrete Potection for Fnd | [17 empty] | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24
2AI103CV18800-08025 | EOF:Backfilling & Compaction for Fnd | [17 empty] | 2016-12-27 | 2016-12-27 | 2016-12-27 | 2016-12-27 | 2016-12-27 | 2016-12-27 | 2016-12-27 | 2016-12-27 | 2016-12-27 | 2016-12-27 | 2016-12-27 | 2016-12-27 | 2016-12-27 | 2016-12-27 | 2016-12-27 | 2016-12-27 | 2016-12-27 | 2016-12-27 | 2016-12-27 | 2016-12-27 | 2016-12-27 | 2016-12-27 | 2016-12-27 | 2016-12-27 | 2016-12-27 | 2016-12-27 | 2016-12-27 | 2016-12-27 | 2016-12-27
2AI103CV18800-08030 | EOF:Survey Marking, Excavation & Subgrade | [17 empty] | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05
2AI103CV18800-08035 | EOF:Blinding/PCC for Fnd | [17 empty] | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08
2AI103CV18800-08040 | EOF:Rebar, Formwork for Footing | [17 empty] | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10
2AI103CV18800-08041 | Concrete Pouring - for Footing | [17 empty] | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15
2AI103CV18800-08045 | EOF:Rebar, Formwork, Install Embedments for Pedestal | [17 empty] | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10
2AI103CV18800-08046 | Concrete Pouring - for Pedestal | [17 empty] | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15
2AI103CV18800-08050 | EOF:Concrete Potection for Fnd | [17 empty] | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24
2AI103CV18800-08055 | EOF:Backfilling & Compaction for Fnd | [17 empty] | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02
2AI103CV19000 | EOF: Road crossings & EIT Duct banks | [11 empty] | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26
2AI103CV19000-08000 | EOF: EIT Duct banks | [11 empty] | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26
2AI103CV19000-08001 | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material | [11 empty] | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26
2AI103CV19000-08005 | EOF:Blinding/PCC for Ductbank | [11 empty] | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03 | 2016-07-03
2AI103CV19000-08010 | EOF:Rebar, Formwork & PVC conduits installation for Duct Bank | [11 empty] | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04 | 2016-07-04
2AI103CV19000-08011 | EOF:Concrete Pouring | [11 empty] | 2016-07-12 | 2016-07-12 | 2016-07-12 | 2016-07-12 | 2016-07-12 | 2016-07-12 | 2016-07-12 | 2016-07-12 | 2016-07-12 | 2016-07-12 | 2016-07-12 | 2016-07-12 | 2016-07-12 | 2016-07-12 | 2016-07-12 | 2016-07-12 | 2016-07-12 | 2016-07-12 | 2016-07-12 | 2016-07-12 | 2016-07-12 | 2016-07-12 | 2016-07-12 | 2016-07-12 | 2016-07-12 | 2016-07-12 | 2016-07-12 | 2016-07-12 | 2016-07-12 | 2016-07-12 | 2016-07-12 | 2016-07-12 | 2016-07-12 | 2016-07-12 | 2016-07-12
2AI103CV19000-08015 | EOF:Concrete Potection | [13 empty] | 2016-07-28 | 2016-07-28 | 2016-07-28 | 2016-07-28 | 2016-07-28 | 2016-07-28 | 2016-07-28 | 2016-07-28 | 2016-07-28 | 2016-07-28 | 2016-07-28 | 2016-07-28 | 2016-07-28 | 2016-07-28 | 2016-07-28 | 2016-07-28 | 2016-07-28 | 2016-07-28 | 2016-07-28 | 2016-07-28 | 2016-07-28 | 2016-07-28 | 2016-07-28 | 2016-07-28 | 2016-07-28 | 2016-07-28 | 2016-07-28 | 2016-07-28 | 2016-07-28 | 2016-07-28 | 2016-07-28 | 2016-07-28 | 2016-07-28
2AI103CV19000-08020 | EOF:Backfilling & Compaction | [13 empty] | 2016-08-06 | 2016-08-06 | 2016-08-06 | 2016-08-06 | 2016-08-06 | 2016-08-06 | 2016-08-06 | 2016-08-06 | 2016-08-06 | 2016-08-06 | 2016-08-06 | 2016-08-06 | 2016-08-06 | 2016-08-06 | 2016-08-06 | 2016-08-06 | 2016-08-06 | 2016-08-06 | 2016-08-06 | 2016-08-06 | 2016-08-06 | 2016-08-06 | 2016-08-06 | 2016-08-06 | 2016-08-06 | 2016-08-06 | 2016-08-06 | 2016-08-06 | 2016-08-06 | 2016-08-06 | 2016-08-06 | 2016-08-06 | 2016-08-06
2AI103CV19100 | EOF: Roads, Crossing & Paving Works | [13 empty] | 2016-08-06: 2019-03-05; 2016-08-06: 2019-03-05; 2016-08-06: 2019-03-05
2AI103CV19100-08000 | EOF:Gutch Road Work
2AI103CV19100-08001 | EOF:Grading & leveling | [13 empty] | 2016-08-06: 2019-03-20; 2016-08-06: 2019-03-20; 2016-08-06: 2019-03-20
2AI103CV19100-08005 | EOF:Asphalt Road Work | [13 empty] | 2016-08-06: 2019-03-20; 2016-08-06: 2019-03-20; 2016-08-06: 2019-03-20
2AI103CV19100-08006 | EOF:Preparation of sub grade | [13 empty] | 2016-08-06: 2019-03-23; 2016-08-06: 2019-03-23; 2016-08-06: 2019-03-23
2AI103CV19100-08010 | EOF:Reinforced Concrete Paving
2AI103CV19100-08011 | EOF:Asphalt Work | [13 empty] | 2016-08-06: 2019-03-31
2AI103CV19100-08015 | EOF:Asphalt Paving | [13 empty] | 2016-08-06: 2019-03-05; 2016-08-06: 2019-03-05; 2016-08-06: 2019-03-05
2AI103CV19100-08016 | EOF:Kerb-stone installation
2AI103CV19100-08020 | EOF:Bollards & Crash barrier installation
2AI103CV19100-08025 | EOF:Excavation
2AI103CV19100-08030 | EOF:Grading & leveling
2AI103CV19100-08035 | EOF:Gatch Filling
2AI103CV19100-08040 | EOF:Compaction
2AI103CV19100-08045 | EOF:Excavation
2AI103CV19100-08050 | EOF:Grading & leveling
2AI103CV19100-08055 | EOF:Preparation of sub grade
2AI103CV19100-08060 | EOF:Concrete Work
2AI103CV19100-08065 | EOF:Excavation | [13 empty] | 2016-08-06: 2019-04-08
2AI103CV19100-08070 | EOF:Grading & leveling | [13 empty] | 2016-08-06: 2019-04-08
2AI103CV19100-08075 | EOF:Preparation of sub grade | [13 empty] | 2016-08-06: 2019-04-08
2AI103CV19100-08080 | EOF:Asphalt Work | [13 empty] | 2016-08-06: 2019-03-05; 2016-08-06: 2019-03-05; 2016-08-06: 2019-03-05
2AI103CV19200 | EOF: Foam System Package (52-Z-301 A/B) Foundation | [17 empty] | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30
2AI103CV19200-08000 | EOF: Foam System Package (52-Z-301 A) Foundation | [17 empty] | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30
2AI103CV19200-08001 | EOF:Survey Marking, Excavation & Subgrade | [17 empty] | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30
2AI103CV19200-08005 | EOF: Foam System Package (52-Z-301 B) Foundation | [17 empty] | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05
2AI103CV19200-08006 | EOF:Blinding/PCC for Fnd | [17 empty] | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04 | 2016-12-04
2AI103CV19200-08010 | EOF:Rebar, Formwork for Footing | [17 empty] | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05
2AI103CV19200-08011 | Concrete Pouring - for Footing | [17 empty] | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13
2AI103CV19200-08015 | EOF:Rebar, Formwork, Install Embedments for Pedestal | [17 empty] | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05
2AI103CV19200-08016 | Concrete Pouring - for Pedestal | [17 empty] | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13
2AI103CV19200-08020 | EOF:Concrete Potection for Fnd | [17 empty] | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24
2AI103CV19200-08025 | EOF:Backfilling & Compaction for Fnd | [17 empty] | 2016-12-27 | 2016-12-27 | 2016-12-27 | 2016-12-27 | 2016-12-27 | 2016-12-27 | 2016-12-27 | 2016-12-27 | 2016-12-27 | 2016-12-27 | 2016-12-27 | 2016-12-27 | 2016-12-27 | 2016-12-27 | 2016-12-27 | 2016-12-27 | 2016-12-27 | 2016-12-27 | 2016-12-27 | 2016-12-27 | 2016-12-27 | 2016-12-27 | 2016-12-27 | 2016-12-27 | 2016-12-27 | 2016-12-27 | 2016-12-27 | 2016-12-27 | 2016-12-27
2AI103CV19200-08030 | EOF:Survey Marking, Excavation & Subgrade | [17 empty] | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05
2AI103CV19200-08035 | EOF:Blinding/PCC for Fnd | [17 empty] | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08
2AI103CV19200-08040 | EOF:Rebar, Formwork for Footing | [17 empty] | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10
2AI103CV19200-08041 | Concrete Pouring - for Footing | [17 empty] | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15
2AI103CV19200-08045 | EOF:Rebar, Formwork, Install Embedments for Pedestal | [17 empty] | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10 | 2016-12-10
2AI103CV19200-08046 | Concrete Pouring - for Pedestal | [17 empty] | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15
2AI103CV19200-08050 | EOF:Concrete Potection for Fnd | [17 empty] | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24
2AI103CV19200-08055 | EOF:Backfilling & Compaction for Fnd | [17 empty] | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02 | 2017-01-02
2AI103CV19400 | EOF: Foam System Package (52-Z-301 A/B) Shelter Foundation | [17 empty] | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30
2AI103CV19400-08000 | EOF: Foam System Package (52-Z-301 A) Shelter Foundation | [17 empty] | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30
2AI103CV19400-08002 | EOF:Survey Marking, Excavation & Subgrade | [17 empty] | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30
2AI103CV19400-08005 | EOF: Foam System Package (52-Z-301 B) Shelter Foundation | [17 empty] | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30
2AI103CV19400-08006 | EOF:Blinding/PCC for Fnd | [19 empty] | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11
2AI103CV19400-08010 | EOF:Rebar, Formwork for Footing | [19 empty] | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13
2AI103CV19400-08011 | Concrete Pouring - for Footing | [19 empty] | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16
2AI103CV19400-08015 | EOF:Rebar, Formwork, Install Embedments for Pedestal | [19 empty] | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18
2AI103CV19400-08016 | Concrete Pouring - for Pedestal | [19 empty] | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27
2AI103CV19400-08020 | EOF:Concrete Potection for Fnd | [19 empty] | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01
2AI103CV19400-08025 | EOF:Backfilling & Compaction for Fnd | [19 empty] | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07
2AI103CV19400-08030 | EOF:Survey Marking, Excavation & Subgrade | [17 empty] | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30
2AI103CV19400-08035 | EOF:Blinding/PCC for Fnd | [19 empty] | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11
2AI103CV19400-08040 | EOF:Rebar, Formwork for Footing | [19 empty] | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13
2AI103CV19400-08041 | Concrete Pouring - for Footing | [19 empty] | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16
2AI103CV19400-08045 | EOF:Rebar, Formwork, Install Embedments for Pedestal | [19 empty] | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18
2AI103CV19400-08046 | Concrete Pouring - for Pedestal | [19 empty] | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27
2AI103CV19400-08050 | EOF:Concrete Potection for Fnd | [19 empty] | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01
2AI103CV19400-08055 | EOF:Backfilling & Compaction for Fnd | [19 empty] | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07 | 2017-03-07
2AI103CV19600 | EOF: Ground Supported Platforms Foundation | [19 empty] | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13
2AI103CV19600-08000 | EOF: Ground Supported Platforms Foundation | [19 empty] | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13
2AI103CV19600-08001 | EOF:Survey Marking, Excavation & Subgrade | [19 empty] | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13
2AI103CV19600-08005 | EOF:Blinding/PCC for Fnd | [19 empty] | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16
2AI103CV19600-08010 | EOF:Rebar, Formwork for Footing | [19 empty] | 2017-03-18 | 2017-03-18 | 2017-03-18 | 2017-03-18 | 2017-03-18 | 2017-03-18 | 2017-03-18 | 2017-03-18 | 2017-03-18 | 2017-03-18 | 2017-03-18 | 2017-03-18 | 2017-03-18 | 2017-03-18 | 2017-03-18 | 2017-03-18 | 2017-03-18 | 2017-03-18 | 2017-03-18 | 2017-03-18 | 2017-03-18 | 2017-03-18 | 2017-03-18 | 2017-03-18 | 2017-03-18 | 2017-03-18 | 2017-03-18
2AI103CV19600-08011 | Concrete Pouring - for Footing | [19 empty] | 2017-03-22 | 2017-03-22 | 2017-03-22 | 2017-03-22 | 2017-03-22 | 2017-03-22 | 2017-03-22 | 2017-03-22 | 2017-03-22 | 2017-03-22 | 2017-03-22 | 2017-03-22 | 2017-03-22 | 2017-03-22 | 2017-03-22 | 2017-03-22 | 2017-03-22 | 2017-03-22 | 2017-03-22 | 2017-03-22 | 2017-03-22 | 2017-03-22 | 2017-03-22 | 2017-03-22 | 2017-03-22 | 2017-03-22 | 2017-03-22
2AI103CV19600-08015 | EOF:Rebar, Formwork, Install Embedments for Pedestal | [21 empty] | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30
2AI103CV19600-08016 | Concrete Pouring - for Pedestal | [21 empty] | 2017-04-05 | 2017-04-05 | 2017-04-05 | 2017-04-05 | 2017-04-05 | 2017-04-05 | 2017-04-05 | 2017-04-05 | 2017-04-05 | 2017-04-05 | 2017-04-05 | 2017-04-05 | 2017-04-05 | 2017-04-05 | 2017-04-05 | 2017-04-05 | 2017-04-05 | 2017-04-05 | 2017-04-05 | 2017-04-05 | 2017-04-05 | 2017-04-05 | 2017-04-05 | 2017-04-05 | 2017-04-05
2AI103CV19600-08020 | EOF:Concrete Potection for Fnd | [21 empty] | 2017-04-23 | 2017-04-23 | 2017-04-23 | 2017-04-23 | 2017-04-23 | 2017-04-23 | 2017-04-23 | 2017-04-23 | 2017-04-23 | 2017-04-23 | 2017-04-23 | 2017-04-23 | 2017-04-23 | 2017-04-23 | 2017-04-23 | 2017-04-23 | 2017-04-23 | 2017-04-23 | 2017-04-23 | 2017-04-23 | 2017-04-23 | 2017-04-23 | 2017-04-23 | 2017-04-23 | 2017-04-23
2AI103CV19600-08025 | EOF:Backfilling & Compaction for Fnd | [21 empty] | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01 | 2017-05-01
2AI103CV19700 | EOF: Miscellaneous Drain Pits | [11 empty] | 2016-07-11 | 2016-07-11 | 2016-07-11 | 2016-07-11 | 2016-07-11 | 2016-07-11 | 2016-07-11 | 2016-07-11 | 2016-07-11 | 2016-07-11 | 2016-07-11 | 2016-07-11 | 2016-07-11 | 2016-07-11 | 2016-07-11 | 2016-07-11 | 2016-07-11 | 2016-07-11 | 2016-07-11 | 2016-07-11 | 2016-07-11 | 2016-07-11 | 2016-07-11 | 2016-07-11 | 2016-07-11 | 2016-07-11 | 2016-07-11 | 2016-07-11 | 2016-07-11 | 2016-07-11 | 2016-07-11 | 2016-07-11 | 2016-07-11 | 2016-07-11 | 2016-07-11
2AI103CV19700-08001 | EOF:Excavation & Subgrade | [11 empty] | 2016-07-11 | 2016-07-11 | 2016-07-11 | 2016-07-11 | 2016-07-11 | 2016-07-11 | 2016-07-11 | 2016-07-11 | 2016-07-11 | 2016-07-11 | 2016-07-11 | 2016-07-11 | 2016-07-11 | 2016-07-11 | 2016-07-11 | 2016-07-11 | 2016-07-11 | 2016-07-11 | 2016-07-11 | 2016-07-11 | 2016-07-11 | 2016-07-11 | 2016-07-11 | 2016-07-11 | 2016-07-11 | 2016-07-11 | 2016-07-11 | 2016-07-11 | 2016-07-11 | 2016-07-11 | 2016-07-11 | 2016-07-11 | 2016-07-11 | 2016-07-11 | 2016-07-11
2AI103CV19700-08005 | EOF: Miscellaneous Drain Pits | [11 empty] | 2016-07-11 | 2016-07-11 | 2016-07-11 | 2016-07-11 | 2016-07-11 | 2016-07-11 | 2016-07-11 | 2016-07-11 | 2016-07-11 | 2016-07-11 | 2016-07-11 | 2016-07-11 | 2016-07-11 | 2016-07-11 | 2016-07-11 | 2016-07-11 | 2016-07-11 | 2016-07-11 | 2016-07-11 | 2016-07-11 | 2016-07-11 | 2016-07-11 | 2016-07-11 | 2016-07-11 | 2016-07-11 | 2016-07-11 | 2016-07-11 | 2016-07-11 | 2016-07-11 | 2016-07-11 | 2016-07-11 | 2016-07-11 | 2016-07-11 | 2016-07-11 | 2016-07-11
2AI103CV19700-08006 | EOF:Blinding/PCC for Sump | [11 empty] | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21
2AI103CV19700-08010 | EOF:Rebar, Formwork for base | [13 empty] | 2016-08-11 | 2016-08-11 | 2016-08-11 | 2016-08-11 | 2016-08-11 | 2016-08-11 | 2016-08-11 | 2016-08-11 | 2016-08-11 | 2016-08-11 | 2016-08-11 | 2016-08-11 | 2016-08-11 | 2016-08-11 | 2016-08-11 | 2016-08-11 | 2016-08-11 | 2016-08-11 | 2016-08-11 | 2016-08-11 | 2016-08-11 | 2016-08-11 | 2016-08-11 | 2016-08-11 | 2016-08-11 | 2016-08-11 | 2016-08-11 | 2016-08-11 | 2016-08-11 | 2016-08-11 | 2016-08-11 | 2016-08-11 | 2016-08-11
2AI103CV19700-08011 | EOF:Concrete Pouring for base | [13 empty] | 2016-08-21 | 2016-08-21 | 2016-08-21 | 2016-08-21 | 2016-08-21 | 2016-08-21 | 2016-08-21 | 2016-08-21 | 2016-08-21 | 2016-08-21 | 2016-08-21 | 2016-08-21 | 2016-08-21 | 2016-08-21 | 2016-08-21 | 2016-08-21 | 2016-08-21 | 2016-08-21 | 2016-08-21 | 2016-08-21 | 2016-08-21 | 2016-08-21 | 2016-08-21 | 2016-08-21 | 2016-08-21 | 2016-08-21 | 2016-08-21 | 2016-08-21 | 2016-08-21 | 2016-08-21 | 2016-08-21 | 2016-08-21 | 2016-08-21
2AI103CV19700-08015 | EOF:Rebar, Formwork for wall | [13 empty] | 2016-08-28 | 2016-08-28 | 2016-08-28 | 2016-08-28 | 2016-08-28 | 2016-08-28 | 2016-08-28 | 2016-08-28 | 2016-08-28 | 2016-08-28 | 2016-08-28 | 2016-08-28 | 2016-08-28 | 2016-08-28 | 2016-08-28 | 2016-08-28 | 2016-08-28 | 2016-08-28 | 2016-08-28 | 2016-08-28 | 2016-08-28 | 2016-08-28 | 2016-08-28 | 2016-08-28 | 2016-08-28 | 2016-08-28 | 2016-08-28 | 2016-08-28 | 2016-08-28 | 2016-08-28 | 2016-08-28 | 2016-08-28 | 2016-08-28
2AI103CV19700-08016 | EOF:Concrete Pouring for wall | [15 empty] | 2016-09-24 | 2016-09-24 | 2016-09-24 | 2016-09-24 | 2016-09-24 | 2016-09-24 | 2016-09-24 | 2016-09-24 | 2016-09-24 | 2016-09-24 | 2016-09-24 | 2016-09-24 | 2016-09-24 | 2016-09-24 | 2016-09-24 | 2016-09-24 | 2016-09-24 | 2016-09-24 | 2016-09-24 | 2016-09-24 | 2016-09-24 | 2016-09-24 | 2016-09-24 | 2016-09-24 | 2016-09-24 | 2016-09-24 | 2016-09-24 | 2016-09-24 | 2016-09-24 | 2016-09-24 | 2016-09-24
2AI103CV19700-08020 | EOF:Concrete Potection | [13 empty] | 2016-09-02 | 2016-09-02 | 2016-09-02 | 2016-09-02 | 2016-09-02 | 2016-09-02 | 2016-09-02 | 2016-09-02 | 2016-09-02 | 2016-09-02 | 2016-09-02 | 2016-09-02 | 2016-09-02 | 2016-09-02 | 2016-09-02 | 2016-09-02 | 2016-09-02 | 2016-09-02 | 2016-09-02 | 2016-09-02 | 2016-09-02 | 2016-09-02 | 2016-09-02 | 2016-09-02 | 2016-09-02 | 2016-09-02 | 2016-09-02 | 2016-09-02 | 2016-09-02 | 2016-09-02 | 2016-09-02 | 2016-09-02 | 2016-09-02
2AI103CV19700-08025 | EOF:Coverslab | [13 empty] | 2016-09-02 | 2016-09-02 | 2016-09-02 | 2016-09-02 | 2016-09-02 | 2016-09-02 | 2016-09-02 | 2016-09-02 | 2016-09-02 | 2016-09-02 | 2016-09-02 | 2016-09-02 | 2016-09-02 | 2016-09-02 | 2016-09-02 | 2016-09-02 | 2016-09-02 | 2016-09-02 | 2016-09-02 | 2016-09-02 | 2016-09-02 | 2016-09-02 | 2016-09-02 | 2016-09-02 | 2016-09-02 | 2016-09-02 | 2016-09-02 | 2016-09-02 | 2016-09-02 | 2016-09-02 | 2016-09-02 | 2016-09-02 | 2016-09-02
2AI103CV19700-08030 | EOF:Backfilling & Compaction | [15 empty] | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06
2AI103CV19800 | EOF: Sanitary / Sewer Drains / Valve Pit & Manholes | [15 empty] | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04
2AI103CV19800-08000 | EOF: Sanitary / Sewer Drains | [15 empty] | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04
2AI103CV19800-08001 | EOF:Excavation & Subgrade | [15 empty] | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04
2AI103CV19800-08005 | EOF:Blinding/PCC for Sanitary/Sewer drain, Pits & manholes | [15 empty] | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04
2AI103CV19800-08010 | EOF:Rebar, Formwork for base & Wall | [15 empty] | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04
2AI103CV19800-08011 | EOF:Concrete Pouring for base & Wall | [15 empty] | 2016-10-13 | 2016-10-13 | 2016-10-13 | 2016-10-13 | 2016-10-13 | 2016-10-13 | 2016-10-13 | 2016-10-13 | 2016-10-13 | 2016-10-13 | 2016-10-13 | 2016-10-13 | 2016-10-13 | 2016-10-13 | 2016-10-13 | 2016-10-13 | 2016-10-13 | 2016-10-13 | 2016-10-13 | 2016-10-13 | 2016-10-13 | 2016-10-13 | 2016-10-13 | 2016-10-13 | 2016-10-13 | 2016-10-13 | 2016-10-13 | 2016-10-13 | 2016-10-13 | 2016-10-13 | 2016-10-13
2AI103CV19800-08015 | EOF:Rebar, Formwork for Cover slab | [15 empty] | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20 | 2016-10-20
2AI103CV19800-08016 | EOF:Concrete Pouring for cover slab | [15 empty] | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09
2AI103CV19800-08020 | EOF:Concrete Potection | [15 empty] | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16
2AI103CV19800-08025 | EOF:Installation of Manhole/Pit Cover | [15 empty] | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16 | 2016-11-16
2AI103CV19800-08030 | EOF:Backfilling & Compaction | [15 empty] | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20
2AI103CV19820 | EOF: Demolition, Rerouting of Exisitng UG Cable & Existing RMU | [7 empty] | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23
2AI103CV19820-08000 | EOF: Demolition Works of Exisitng UG Cable & Existing RMU | [11 empty] | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02
2AI103CV19820-08005 | EOF: Rerouting of Exisitng UG Cable & Existing RMU | [7 empty] | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23
2AI103CV19820-08006 | EOF: Demolition Works of Exisitng UG Cable & Existing RMU | [11 empty] | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02
2AI103CV19820-08010 | EOF:Laying of UG Cable | [7 empty] | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23 | 2016-03-23
2AI103CV19820-08015 | EOF: Shutdown for Reroting of UG Cable & Existing RMU | [11 empty] | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01
2AI103CV19820-08016 | EOF:Cable Jointing | [9 empty] | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28 | 2016-03-28
2AI103CV19820-08018 | EOF:Disconnection/isolation of Existing cable | [11 empty] | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01
2AI103CV19820-08019 | EOF:Relocation of RMU | [11 empty] | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02
2AI103CV19820-08020 | EOF:Cable termination to RMU | [11 empty] | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02
2AI103CV19820-08030 | EOF:Cable Jointing to Existing Cable | [11 empty] | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01
2AI103CV20120 | EOF: Foundation of Other Equipments (H2S Scrubber, PIG Receiver etc) | [11 empty] | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22
2AI103CV20120-08000 | EOF: Oily Water Transfer Vessel 621-V-301( having Pump - 52-G-303 A/B ) Foundation | [11 empty] | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22
2AI103CV20120-08301 | EOF:Excavation & Subgrade | [11 empty] | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22 | 2016-06-22
2AI103CV20120-08305 | EOF:Blinding/PCC for Fnd | [11 empty] | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21
2AI103CV20120-08310 | EOF:Rebar, Formwork for base | [13 empty] | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23
2AI103CV20120-08311 | Concrete Pouring - for base | [13 empty] | 2016-07-28 | 2016-07-28 | 2016-07-28 | 2016-07-28 | 2016-07-28 | 2016-07-28 | 2016-07-28 | 2016-07-28 | 2016-07-28 | 2016-07-28 | 2016-07-28 | 2016-07-28 | 2016-07-28 | 2016-07-28 | 2016-07-28 | 2016-07-28 | 2016-07-28 | 2016-07-28 | 2016-07-28 | 2016-07-28 | 2016-07-28 | 2016-07-28 | 2016-07-28 | 2016-07-28 | 2016-07-28 | 2016-07-28 | 2016-07-28 | 2016-07-28 | 2016-07-28 | 2016-07-28 | 2016-07-28 | 2016-07-28 | 2016-07-28
2AI103CV20120-08315 | EOF:Rebar, Formwork for Wall for 1st Pour | [13 empty] | 2016-08-09 | 2016-08-09 | 2016-08-09 | 2016-08-09 | 2016-08-09 | 2016-08-09 | 2016-08-09 | 2016-08-09 | 2016-08-09 | 2016-08-09 | 2016-08-09 | 2016-08-09 | 2016-08-09 | 2016-08-09 | 2016-08-09 | 2016-08-09 | 2016-08-09 | 2016-08-09 | 2016-08-09 | 2016-08-09 | 2016-08-09 | 2016-08-09 | 2016-08-09 | 2016-08-09 | 2016-08-09 | 2016-08-09 | 2016-08-09 | 2016-08-09 | 2016-08-09 | 2016-08-09 | 2016-08-09 | 2016-08-09 | 2016-08-09
2AI103CV20120-08316 | Concrete Pouring - for wall - 1st pouring | [13 empty] | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27 | 2016-08-27
2AI103CV20120-08320 | EOF:Rebar, Formwork for Wall for 2nd Pour | [15 empty] | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04 | 2016-10-04
2AI103CV20120-08321 | Concrete Pouring - for wall - 2nd pouring | [15 empty] | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18
2AI103CV20120-08325 | EOF:Concrete Potection | [13 empty] | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08
2AI103CV20120-08330 | EOF:Backfilling & Compaction | [13 empty] | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10
2AI103CV20220 | EOF: Tank Foundation | [17 empty] | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20
2AI103CV20220-08000 | EOF: Foundation for Diesel Fuel Tank(52-D-307 A/B) | [17 empty] | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20
2AI103CV20220-08001 | EOF:Survey Marking, Excavation & Subgrade | [17 empty] | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20
2AI103CV20220-08005 | EOF: Foundation for Diesel Fuel Tank(52-D-307 C/D) | [17 empty] | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20
2AI103CV20220-08006 | EOF:Blinding/PCC for Fnd | [17 empty] | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26 | 2016-12-26
2AI103CV20220-08010 | EOF:Rebar, Formwork for Footing | [19 empty] | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06
2AI103CV20220-08011 | Concrete Pouring - for Footing | [19 empty] | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14
2AI103CV20220-08015 | EOF:Rebar, Formwork, Install Embedments for Pedestal | [19 empty] | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16 | 2017-03-16
2AI103CV20220-08020 | EOF:Concrete Potection for Fnd | [21 empty] | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01
2AI103CV20220-08021 | Concrete Pouring - for Pedestal | [21 empty] | 2017-04-07 | 2017-04-07 | 2017-04-07 | 2017-04-07 | 2017-04-07 | 2017-04-07 | 2017-04-07 | 2017-04-07 | 2017-04-07 | 2017-04-07 | 2017-04-07 | 2017-04-07 | 2017-04-07 | 2017-04-07 | 2017-04-07 | 2017-04-07 | 2017-04-07 | 2017-04-07 | 2017-04-07 | 2017-04-07 | 2017-04-07 | 2017-04-07 | 2017-04-07 | 2017-04-07 | 2017-04-07
2AI103CV20220-08025 | EOF:Backfilling & Compaction for Fnd | [21 empty] | 2017-04-13 | 2017-04-13 | 2017-04-13 | 2017-04-13 | 2017-04-13 | 2017-04-13 | 2017-04-13 | 2017-04-13 | 2017-04-13 | 2017-04-13 | 2017-04-13 | 2017-04-13 | 2017-04-13 | 2017-04-13 | 2017-04-13 | 2017-04-13 | 2017-04-13 | 2017-04-13 | 2017-04-13 | 2017-04-13 | 2017-04-13 | 2017-04-13 | 2017-04-13 | 2017-04-13 | 2017-04-13
2AI103CV20220-08030 | EOF:Survey Marking, Excavation & Subgrade | [17 empty] | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20
2AI103CV20220-08335 | EOF:Blinding/PCC for Fnd | [17 empty] | 2016-12-25 | 2016-12-25 | 2016-12-25 | 2016-12-25 | 2016-12-25 | 2016-12-25 | 2016-12-25 | 2016-12-25 | 2016-12-25 | 2016-12-25 | 2016-12-25 | 2016-12-25 | 2016-12-25 | 2016-12-25 | 2016-12-25 | 2016-12-25 | 2016-12-25 | 2016-12-25 | 2016-12-25 | 2016-12-25 | 2016-12-25 | 2016-12-25 | 2016-12-25 | 2016-12-25 | 2016-12-25 | 2016-12-25 | 2016-12-25 | 2016-12-25 | 2016-12-25
2AI103CV20220-08340 | EOF:Rebar, Formwork for Footing | [19 empty] | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06
2AI103CV20220-08341 | Concrete Pouring - for Footing | [19 empty] | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14
2AI103CV20220-08345 | EOF:Rebar, Formwork, Install Embedments for Pedestal | [19 empty] | 2017-03-17 | 2017-03-17 | 2017-03-17 | 2017-03-17 | 2017-03-17 | 2017-03-17 | 2017-03-17 | 2017-03-17 | 2017-03-17 | 2017-03-17 | 2017-03-17 | 2017-03-17 | 2017-03-17 | 2017-03-17 | 2017-03-17 | 2017-03-17 | 2017-03-17 | 2017-03-17 | 2017-03-17 | 2017-03-17 | 2017-03-17 | 2017-03-17 | 2017-03-17 | 2017-03-17 | 2017-03-17 | 2017-03-17 | 2017-03-17
2AI103CV20220-08346 | Concrete Pouring - for Pedestal | [21 empty] | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01
2AI103CV20220-08350 | EOF:Concrete Potection for Fnd | [21 empty] | 2017-04-07 | 2017-04-07 | 2017-04-07 | 2017-04-07 | 2017-04-07 | 2017-04-07 | 2017-04-07 | 2017-04-07 | 2017-04-07 | 2017-04-07 | 2017-04-07 | 2017-04-07 | 2017-04-07 | 2017-04-07 | 2017-04-07 | 2017-04-07 | 2017-04-07 | 2017-04-07 | 2017-04-07 | 2017-04-07 | 2017-04-07 | 2017-04-07 | 2017-04-07 | 2017-04-07 | 2017-04-07
2AI103CV20220-08355 | EOF:Backfilling & Compaction for Fnd | [21 empty] | 2017-04-13 | 2017-04-13 | 2017-04-13 | 2017-04-13 | 2017-04-13 | 2017-04-13 | 2017-04-13 | 2017-04-13 | 2017-04-13 | 2017-04-13 | 2017-04-13 | 2017-04-13 | 2017-04-13 | 2017-04-13 | 2017-04-13 | 2017-04-13 | 2017-04-13 | 2017-04-13 | 2017-04-13 | 2017-04-13 | 2017-04-13 | 2017-04-13 | 2017-04-13 | 2017-04-13 | 2017-04-13
2AI103CV28220 | EOF: Existing Road & Fence Demolition Works | [13 empty] | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10
2AI103CV28220-08000 | EOF:Demolition Work Existing Road & Existing Fence- New Tank Area - 621 | [13 empty] | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10
2AI103CV28220-08001 | EOF:Demolition Works - Existing Road | [13 empty] | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10
2AI103CV28220-08005 | EOF:New Fencing Work - New Tank Area - 621 | [15 empty] | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20
2AI103CV28220-08006 | EOF:Demolition Works - Existing Fence
2AI103CV28220-08015 | EOF:Survey marking & Excavation for Fence Post | [21 empty] | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29
2AI103CV28220-08016 | EOF:Sub grade & Blinding | [21 empty] | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07
2AI103CV28220-08017 | EOF:Install/Cast insitu fencing fnds | [15 empty] | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20
2AI103CV28220-08020 | EOF:Fence Post installation | [21 empty] | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07 | 2017-05-07
2AI103CV28220-08025 | EOF:Fence Mesh Installation | [25 empty] | 2017-08-06 | 2017-08-06 | 2017-08-06 | 2017-08-06 | 2017-08-06 | 2017-08-06 | 2017-08-06 | 2017-08-06 | 2017-08-06 | 2017-08-06 | 2017-08-06 | 2017-08-06 | 2017-08-06 | 2017-08-06 | 2017-08-06 | 2017-08-06 | 2017-08-06 | 2017-08-06 | 2017-08-06 | 2017-08-06 | 2017-08-06
2AI103CV28220-08026 | EOF:Gate Installation & Speed bumbs | [25 empty] | 2017-08-06: 2018-11-05; 2017-08-06: 2018-11-05; 2017-08-06: 2018-11-05; 2017-08-06: 2018-11-05; 2017-08-06: 2018-11-05; 2017-08-06: 2018-11-05; 2017-08-06: 2018-11-05
2AI103HS01110 | EOF: Installation of Fire fighting & Safety Equipments
2AI103HS01110-08000 | EOF: Installation of Fire fighting & Safety Equipments
2AI103HS01110-08001 | EOF: Installation of Fire fighting & Safety Equipments
2AI103HS01120 | EOF: Installation of Safety Sign Boards
2AI103HS01120-08000 | EOF: Installation of Safety Sign Boards
2AI103HS01120-08001 | EOF:Installation - Indoor Safety Signs
2AI103HS01120-08005 | EOF:Installation - Outdoor Safety Signs
2AI103MR18900 | EOF: Pump Erection | [33 empty] | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02
2AI103MR18900-08000 | EOF: 621-G-302 A Foam Pump Erection | [33 empty] | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02
2AI103MR18900-08001 | EOF:Foundation checks/Preparation for Equipment 621-G-302 A Foam Pump Erection | [33 empty] | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04
2AI103MR18900-08002 | EOF:Installation of Equipment 621-G-302 A Foam Pump Erection | [33 empty] | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08
2AI103MR18900-08005 | EOF: 621-G-302 B Foam Pump Erection | [33 empty] | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02
2AI103MR18900-08006 | EOF:Preliminary Allignment & Grouting of Equipment 621-G-302 A Foam Pump Erection | [33 empty] | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02
2AI103MR18900-08010 | EOF: 621-G-302 C Foam Pump Erection | [33 empty] | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02
2AI103MR18900-08011 | EOF:Final Allignment & Grouting of Equipment 621-G-302 A Foam Pump Erection | [33 empty] | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02
2AI103MR18900-08015 | EOF: 621-G-302 D Foam Pump Erection | [33 empty] | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04
2AI103MR18900-08016 | EOF:QC checks & clearance for Equipment 621-G-302 A Foam Pump Erection | [33 empty] | 2018-04-04: 2018-11-05; 2018-04-04: 2018-11-05; 2018-04-04: 2018-11-05; 2018-04-04: 2018-11-05; 2018-04-04: 2018-11-05; 2018-04-04: 2018-11-05; 2018-04-04: 2018-11-05
2AI103MR18900-08025 | EOF:Foundation checks/Preparation for Equipment 621-G-302 B Foam Pump Erection | [33 empty] | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02
2AI103MR18900-08030 | EOF:Installation of Equipment 621-G-302 B Foam Pump Erection | [33 empty] | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08
2AI103MR18900-08035 | EOF:Preliminary Allignment & Grouting of Equipment 621-G-302 B Foam Pump Erection | [33 empty] | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02
2AI103MR18900-08040 | EOF:Final Allignment & Grouting of Equipment 621-G-302 B Foam Pump Erection | [33 empty] | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02
2AI103MR18900-08045 | EOF:QC checks & clearance for Equipment 621-G-302 B Foam Pump Erection | [33 empty] | 2018-04-02: 2018-11-05; 2018-04-02: 2018-11-05; 2018-04-02: 2018-11-05; 2018-04-02: 2018-11-05; 2018-04-02: 2018-11-05; 2018-04-02: 2018-11-05; 2018-04-02: 2018-11-05
2AI103MR18900-08050 | EOF:Foundation checks/Preparation for Equipment 621-G-302 C Foam Pump Erection | [33 empty] | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04
2AI103MR18900-08055 | EOF:Installation of Equipment 621-G-302 C Foam Pump Erection | [33 empty] | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08
2AI103MR18900-08060 | EOF:Preliminary Allignment & Grouting of Equipment 621-G-302 C Foam Pump Erection | [33 empty] | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02
2AI103MR18900-08065 | EOF:Final Allignment & Grouting of Equipment 621-G-302 C Foam Pump Erection | [33 empty] | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02
2AI103MR18900-08070 | EOF:QC checks & clearance for Equipment 621-G-302 C Foam Pump Erection | [37 empty] | 2018-09-16 | 2018-09-16 | 2018-09-16 | 2018-09-16 | 2018-09-16 | 2018-09-16 | 2018-09-16 | 2018-09-16 | 2018-09-16
2AI103MR18900-08075 | EOF:Foundation checks/Preparation for Equipment 621-G-302 D Foam Pump Erection | [33 empty] | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04
2AI103MR18900-08080 | EOF:Installation of Equipment 621-G-302 D Foam Pump Erection | [33 empty] | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08
2AI103MR18900-08085 | EOF:Preliminary Allignment & Grouting of Equipment 621-G-302 D Foam Pump Erection | [33 empty] | 2018-04-09 | 2018-04-09 | 2018-04-09 | 2018-04-09 | 2018-04-09 | 2018-04-09 | 2018-04-09 | 2018-04-09 | 2018-04-09 | 2018-04-09 | 2018-04-09 | 2018-04-09 | 2018-04-09
2AI103MR18900-08090 | EOF:Final Allignment & Grouting of Equipment 621-G-302 D Foam Pump Erection | [33 empty] | 2018-04-11 | 2018-04-11 | 2018-04-11 | 2018-04-11 | 2018-04-11 | 2018-04-11 | 2018-04-11 | 2018-04-11 | 2018-04-11 | 2018-04-11 | 2018-04-11 | 2018-04-11 | 2018-04-11
2AI103MR18900-08095 | EOF:QC checks & clearance for Equipment 621-G-302 D Foam Pump Erection | [37 empty] | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03
2AI103MR19300 | EOF: Foam System Package (52-Z-301 A/B) Erection | [33 empty] | 2018-04-03 | 2018-04-03 | 2018-04-03 | 2018-04-03 | 2018-04-03 | 2018-04-03 | 2018-04-03 | 2018-04-03 | 2018-04-03 | 2018-04-03 | 2018-04-03 | 2018-04-03 | 2018-04-03
2AI103MR19300-08000 | EOF: Foam System Package (52-Z-301 A) Erection | [33 empty] | 2018-04-03 | 2018-04-03 | 2018-04-03 | 2018-04-03 | 2018-04-03 | 2018-04-03 | 2018-04-03 | 2018-04-03 | 2018-04-03 | 2018-04-03 | 2018-04-03 | 2018-04-03 | 2018-04-03
2AI103MR19300-08001 | EOF:Foundation checks/Preparation for Equipment | [33 empty] | 2018-04-03 | 2018-04-03 | 2018-04-03 | 2018-04-03 | 2018-04-03 | 2018-04-03 | 2018-04-03 | 2018-04-03 | 2018-04-03 | 2018-04-03 | 2018-04-03 | 2018-04-03 | 2018-04-03
2AI103MR19300-08005 | EOF: Foam System Package (52-Z-301 B) Erection | [33 empty] | 2018-04-03 | 2018-04-03 | 2018-04-03 | 2018-04-03 | 2018-04-03 | 2018-04-03 | 2018-04-03 | 2018-04-03 | 2018-04-03 | 2018-04-03 | 2018-04-03 | 2018-04-03 | 2018-04-03
2AI103MR19300-08006 | EOF:Installation of Foam System Package (52-Z-301 A/B) Erection | [33 empty] | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08
2AI103MR19300-08010 | EOF:Preliminary Allignment & Grouting of Equipment | [33 empty] | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18
2AI103MR19300-08015 | EOF:Final Allignment & Grouting of Equipment | [37 empty] | 2018-08-07 | 2018-08-07 | 2018-08-07 | 2018-08-07 | 2018-08-07 | 2018-08-07 | 2018-08-07 | 2018-08-07 | 2018-08-07
2AI103MR19300-08020 | EOF:QC checks & clearance for Equipment | [39 empty] | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05
2AI103MR19300-08025 | EOF:Foundation checks/Preparation for Equipment | [33 empty] | 2018-04-03 | 2018-04-03 | 2018-04-03 | 2018-04-03 | 2018-04-03 | 2018-04-03 | 2018-04-03 | 2018-04-03 | 2018-04-03 | 2018-04-03 | 2018-04-03 | 2018-04-03 | 2018-04-03
2AI103MR19300-08030 | EOF:Installation of Foam System Package (52-Z-301 A/B) Erection | [33 empty] | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 2018-04-08
2AI103MR19300-08035 | EOF:Preliminary Allignment & Grouting of Equipment | [33 empty] | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18
2AI103MR19300-08040 | EOF:Final Allignment & Grouting of Equipment | [37 empty] | 2018-08-06 | 2018-08-06 | 2018-08-06 | 2018-08-06 | 2018-08-06 | 2018-08-06 | 2018-08-06 | 2018-08-06 | 2018-08-06
2AI103MR19300-08045 | EOF:QC checks & clearance for Equipment | [39 empty] | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05
2AI103MS19900 | EOF: Tank Erection | [39 empty] | 2018-10-30 | 2018-10-30 | 2018-10-30 | 2018-10-30 | 2018-10-30 | 2018-10-30 | 2018-10-30
2AI103MS19900-08000 | EOF: Erection of Diesel Fuel Tank (52-D-307 A/B) | [39 empty] | 2018-10-30 | 2018-10-30 | 2018-10-30 | 2018-10-30 | 2018-10-30 | 2018-10-30 | 2018-10-30
2AI103MS19900-08001 | EOF:Foundation checks/Preparation for Equipment | [39 empty] | 2018-10-30 | 2018-10-30 | 2018-10-30 | 2018-10-30 | 2018-10-30 | 2018-10-30 | 2018-10-30
2AI103MS19900-08005 | EOF: Erection of Diesel Fuel Tank (52-D-307 C/D) | [39 empty] | 2018-11-04 | 2018-11-04 | 2018-11-04 | 2018-11-04 | 2018-11-04 | 2018-11-04 | 2018-11-04
2AI103MS19900-08006 | EOF:Installation of Structural Support, Platforms & ladders of Equipment | [39 empty] | 2018-10-30 | 2018-10-30 | 2018-10-30 | 2018-10-30 | 2018-10-30 | 2018-10-30 | 2018-10-30
2AI103MS19900-08010 | EOF:Installation of Diesel Fuel Tank 621-D307 A/B | [39 empty] | 2018-10-30 | 2018-10-30 | 2018-10-30 | 2018-10-30 | 2018-10-30 | 2018-10-30 | 2018-10-30
2AI103MS19900-08015 | EOF:Preliminary Allignment & Grouting of Equipment | [39 empty] | 2018-11-08 | 2018-11-08 | 2018-11-08 | 2018-11-08 | 2018-11-08 | 2018-11-08 | 2018-11-08
2AI103MS19900-08020 | EOF:Final Allignment & Grouting of Equipment | [37 empty] | 2018-08-06: 2019-04-08
2AI103MS19900-08025 | EOF:Install internals of Equipment | [37 empty] | 2018-08-06: 2019-04-08
2AI103MS19900-08030 | EOF:QC checks & clearance for Equipment | [37 empty] | 2018-08-06: 2019-04-08
2AI103MS19900-08035 | EOF:Foundation checks/Preparation for Equipment | [39 empty] | 2018-11-04 | 2018-11-04 | 2018-11-04 | 2018-11-04 | 2018-11-04 | 2018-11-04 | 2018-11-04
2AI103MS19900-08040 | EOF:Installation of Structural Support, Platforms & ladders of Equipment | [39 empty] | 2018-11-04 | 2018-11-04 | 2018-11-04 | 2018-11-04 | 2018-11-04 | 2018-11-04 | 2018-11-04
2AI103MS19900-08045 | EOF:Installation of Diesel Fuel Tank 621-D307 C/D | [39 empty] | 2018-11-04 | 2018-11-04 | 2018-11-04 | 2018-11-04 | 2018-11-04 | 2018-11-04 | 2018-11-04
2AI103MS19900-08050 | EOF:Preliminary Allignment & Grouting of Equipment | [39 empty] | 2018-11-12 | 2018-11-12 | 2018-11-12 | 2018-11-12 | 2018-11-12 | 2018-11-12 | 2018-11-12
2AI103MS19900-08055 | EOF:Final Allignment & Grouting of Equipment | [37 empty] | 2018-08-06: 2019-04-08
2AI103MS19900-08060 | EOF:Install internals of Equipment | [37 empty] | 2018-08-06: 2019-04-08
2AI103MS19900-08065 | EOF:QC checks & clearance for Equipment | [37 empty] | 2018-08-06: 2019-04-08
2AI103MS20000 | EOF: Other Equipments (H2S Scrubber, PIG Receiver, Vessel etc) | [19 empty] | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06
2AI103MS20000-08000 | EOF: Oily Water Transfer Vessel 621-V-301Erection | [19 empty] | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06
2AI103MS20000-08001 | EOF:Foundation checks/Preparation for Equipment | [19 empty] | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06
2AI103MS20000-08005 | EOF:Installation of 621-V-301 Oily Water Collection Vessel | [21 empty] | 2017-04-26 | 2017-04-26 | 2017-04-26 | 2017-04-26 | 2017-04-26 | 2017-04-26 | 2017-04-26 | 2017-04-26 | 2017-04-26 | 2017-04-26 | 2017-04-26 | 2017-04-26 | 2017-04-26 | 2017-04-26 | 2017-04-26 | 2017-04-26 | 2017-04-26 | 2017-04-26 | 2017-04-26 | 2017-04-26 | 2017-04-26 | 2017-04-26 | 2017-04-26 | 2017-04-26 | 2017-04-26
2AI103MS20000-08010 | EOF:Preliminary Allignment & Grouting of Equipment | [21 empty] | 2017-04-26 | 2017-04-26 | 2017-04-26 | 2017-04-26 | 2017-04-26 | 2017-04-26 | 2017-04-26 | 2017-04-26 | 2017-04-26 | 2017-04-26 | 2017-04-26 | 2017-04-26 | 2017-04-26 | 2017-04-26 | 2017-04-26 | 2017-04-26 | 2017-04-26 | 2017-04-26 | 2017-04-26 | 2017-04-26 | 2017-04-26 | 2017-04-26 | 2017-04-26 | 2017-04-26 | 2017-04-26
2AI103MS20000-08015 | EOF:Final Allignment & Grouting of Equipment | [21 empty] | 2017-05-02 | 2017-05-02 | 2017-05-02 | 2017-05-02 | 2017-05-02 | 2017-05-02 | 2017-05-02 | 2017-05-02 | 2017-05-02 | 2017-05-02 | 2017-05-02 | 2017-05-02 | 2017-05-02 | 2017-05-02 | 2017-05-02 | 2017-05-02 | 2017-05-02 | 2017-05-02 | 2017-05-02 | 2017-05-02 | 2017-05-02 | 2017-05-02 | 2017-05-02 | 2017-05-02 | 2017-05-02
2AI103MS20000-08020 | EOF:Install Platforms & ladders of Equipment | [33 empty] | 2018-04-15 | 2018-04-15 | 2018-04-15 | 2018-04-15 | 2018-04-15 | 2018-04-15 | 2018-04-15 | 2018-04-15 | 2018-04-15 | 2018-04-15 | 2018-04-15 | 2018-04-15 | 2018-04-15
2AI103MS20000-08025 | EOF:Install internals of Equipment | [33 empty] | 2018-04-15: 2018-11-05; 2018-04-15: 2018-11-05; 2018-04-15: 2018-11-05; 2018-04-15: 2018-11-05; 2018-04-15: 2018-11-05; 2018-04-15: 2018-11-05; 2018-04-15: 2018-11-05
2AI103MS20000-08030 | EOF:QC checks & clearance for Equipment | [21 empty] | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08 | 2017-05-08
2AI104EL20100 | EOF: E,I&T Tie-Ins works associated with 52-SUBST-301& MG-1 Substation and Other EIT Tie-in scope in EOF Area | [19 empty] | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05
2AI104EL20100-08000 | EOF : Tie-Ins works associated with 11KV Power Cable from MG-1 Substation to 52-SUBST-301 | [19 empty] | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05 | 2017-03-05
2AI104EL20100-08100 | EOF: Issue AFC Drawings MG-1 SUBSTATION TIE-INS | [17 empty] | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17
2AI104PI20100 | EOF: Piping Tie-Ins works (Fire Water line & Oily Water line) | [23 empty] | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17
2AI104PI20100-08000 | EOF:Piping Tie-Ins works Fire Water line | [23 empty] | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17
2AI104PI20100-08005 | EOF:Piping Tie-Ins works Oily Water line | [23 empty] | 2017-07-17: 2019-01-25; 2017-07-17: 2019-01-25; 2017-07-17: 2019-01-25
2AI133CV01500 | EOF SS 50-SUBST-001 : Construct Foundation (Transformer) & Pit | [29 empty] | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05
2AI133CV01500-08000 | EOF SS 50-SUBST-001 : Foundation works for Transformer & Pit | [29 empty] | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05
2AI133CV01500-08005 | EOF SS 50-SUBST-001 : Survey Marking, Excavation & Subgrade preparation | [29 empty] | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05
2AI133CV01500-08010 | EOF SS 50-SUBST-001 : Blinding/PCC | [29 empty] | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17 | 2017-12-17
2AI133CV01500-08015 | EOF SS 50-SUBST-001 : Rebar & Formwork | [29 empty] | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03
2AI133CV01500-08020 | EOF SS 50-SUBST-001 : Concrete Pouring | [29 empty] | 2017-12-30 | 2017-12-30 | 2017-12-30 | 2017-12-30 | 2017-12-30 | 2017-12-30 | 2017-12-30 | 2017-12-30 | 2017-12-30 | 2017-12-30 | 2017-12-30 | 2017-12-30 | 2017-12-30 | 2017-12-30 | 2017-12-30 | 2017-12-30 | 2017-12-30
2AI133CV01500-08025 | EOF SS 50-SUBST-001 : Concrete Protection | [31 empty] | 2018-03-07 | 2018-03-07 | 2018-03-07 | 2018-03-07 | 2018-03-07 | 2018-03-07 | 2018-03-07 | 2018-03-07 | 2018-03-07 | 2018-03-07 | 2018-03-07 | 2018-03-07 | 2018-03-07 | 2018-03-07 | 2018-03-07
2AI133CV01500-08030 | EOF SS 50-SUBST-001 : Backfill / Compaction | [29 empty] | 2018-01-05 | 2018-01-05 | 2018-01-05 | 2018-01-05 | 2018-01-05 | 2018-01-05 | 2018-01-05 | 2018-01-05 | 2018-01-05 | 2018-01-05 | 2018-01-05 | 2018-01-05 | 2018-01-05 | 2018-01-05 | 2018-01-05 | 2018-01-05 | 2018-01-05
2AI133CV01500-08035 | EOF SS 50-SUBST-001 : Construction of Pit | [29 empty] | 2018-01-10 | 2018-01-10 | 2018-01-10 | 2018-01-10 | 2018-01-10 | 2018-01-10 | 2018-01-10 | 2018-01-10 | 2018-01-10 | 2018-01-10 | 2018-01-10 | 2018-01-10 | 2018-01-10 | 2018-01-10 | 2018-01-10 | 2018-01-10 | 2018-01-10
2AI133CV03500 | EOF SS 52-SUBST-301 : Construct Foundation (Transformer) & Pit | [23 empty] | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14
2AI133CV03500-08000 | EOF SS 52-SUBST-301 : Foundation works for Transformer & Pit | [23 empty] | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14
2AI133CV03500-08005 | EOF SS 52-SUBST-301 : Survey Marking, Excavation & Subgrade preparation | [23 empty] | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14
2AI133CV03500-08010 | EOF SS 52-SUBST-301 : Blinding/PCC | [23 empty] | 2017-07-22 | 2017-07-22 | 2017-07-22 | 2017-07-22 | 2017-07-22 | 2017-07-22 | 2017-07-22 | 2017-07-22 | 2017-07-22 | 2017-07-22 | 2017-07-22 | 2017-07-22 | 2017-07-22 | 2017-07-22 | 2017-07-22 | 2017-07-22 | 2017-07-22 | 2017-07-22 | 2017-07-22 | 2017-07-22 | 2017-07-22 | 2017-07-22 | 2017-07-22
2AI133CV03500-08015 | EOF SS 52-SUBST-301 : Rebar & Formwork | [23 empty] | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23
2AI133CV03500-08020 | EOF SS 52-SUBST-301 : Concrete Pouring | [25 empty] | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03
2AI133CV03500-08025 | EOF SS 52-SUBST-301 : Concrete Protection | [25 empty] | 2017-08-06 | 2017-08-06 | 2017-08-06 | 2017-08-06 | 2017-08-06 | 2017-08-06 | 2017-08-06 | 2017-08-06 | 2017-08-06 | 2017-08-06 | 2017-08-06 | 2017-08-06 | 2017-08-06 | 2017-08-06 | 2017-08-06 | 2017-08-06 | 2017-08-06 | 2017-08-06 | 2017-08-06 | 2017-08-06 | 2017-08-06
2AI133CV03500-08030 | EOF SS 52-SUBST-301 : Backfill / Compaction | [29 empty] | 2017-12-22 | 2017-12-22 | 2017-12-22 | 2017-12-22 | 2017-12-22 | 2017-12-22 | 2017-12-22 | 2017-12-22 | 2017-12-22 | 2017-12-22 | 2017-12-22 | 2017-12-22 | 2017-12-22 | 2017-12-22 | 2017-12-22 | 2017-12-22 | 2017-12-22
2AI133CV03500-08040 | EOF SS 52-SUBST-301 : Construction of Pit | [27 empty] | 2017-10-28 | 2017-10-28 | 2017-10-28 | 2017-10-28 | 2017-10-28 | 2017-10-28 | 2017-10-28 | 2017-10-28 | 2017-10-28 | 2017-10-28 | 2017-10-28 | 2017-10-28 | 2017-10-28 | 2017-10-28 | 2017-10-28 | 2017-10-28 | 2017-10-28 | 2017-10-28 | 2017-10-28
2AI133CV05500 | EOF SS 52-SUBST-302 : Construct Foundation (Transformer) & Pit | [25 empty] | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14
2AI133CV05500-08000 | EOF SS 52-SUBST-302 : Foundation works for Transformer & Pit | [25 empty] | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14
2AI133CV05500-08010 | EOF SS 52-SUBST-302 : Survey Marking, Excavation & Subgrade preparation | [25 empty] | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14 | 2017-08-14
2AI133CV05500-08020 | EOF SS 52-SUBST-302 : Blinding/PCC | [25 empty] | 2017-08-29 | 2017-08-29 | 2017-08-29 | 2017-08-29 | 2017-08-29 | 2017-08-29 | 2017-08-29 | 2017-08-29 | 2017-08-29 | 2017-08-29 | 2017-08-29 | 2017-08-29 | 2017-08-29 | 2017-08-29 | 2017-08-29 | 2017-08-29 | 2017-08-29 | 2017-08-29 | 2017-08-29 | 2017-08-29 | 2017-08-29
2AI133CV05500-08030 | EOF SS 52-SUBST-302 : Rebar & Formwork | [25 empty] | 2017-08-30 | 2017-08-30 | 2017-08-30 | 2017-08-30 | 2017-08-30 | 2017-08-30 | 2017-08-30 | 2017-08-30 | 2017-08-30 | 2017-08-30 | 2017-08-30 | 2017-08-30 | 2017-08-30 | 2017-08-30 | 2017-08-30 | 2017-08-30 | 2017-08-30 | 2017-08-30 | 2017-08-30 | 2017-08-30 | 2017-08-30
2AI133CV05500-08040 | EOF SS 52-SUBST-302 :Concrete Pouring | [25 empty] | 2017-09-12 | 2017-09-12 | 2017-09-12 | 2017-09-12 | 2017-09-12 | 2017-09-12 | 2017-09-12 | 2017-09-12 | 2017-09-12 | 2017-09-12 | 2017-09-12 | 2017-09-12 | 2017-09-12 | 2017-09-12 | 2017-09-12 | 2017-09-12 | 2017-09-12 | 2017-09-12 | 2017-09-12 | 2017-09-12 | 2017-09-12
2AI133CV05500-08050 | EOF SS 52-SUBST-302 :Concrete Protection | [27 empty] | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02
2AI133CV05500-08060 | EOF SS 52-SUBST-302 :Backfill / Compaction | [29 empty] | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22
2AI133CV05500-08070 | EOF SS 52-SUBST-302 :Construction of Pit | [27 empty] | 2017-11-12 | 2017-11-12 | 2017-11-12 | 2017-11-12 | 2017-11-12 | 2017-11-12 | 2017-11-12 | 2017-11-12 | 2017-11-12 | 2017-11-12 | 2017-11-12 | 2017-11-12 | 2017-11-12 | 2017-11-12 | 2017-11-12 | 2017-11-12 | 2017-11-12 | 2017-11-12 | 2017-11-12
2AI133CV07500 | EOF SS 52-SUBST-303 : Construct Foundation (Transformer) & Pit | [23 empty] | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01
2AI133CV07500-08000 | EOF SS 52-SUBST-303 : Foundation works for Transformer & Pit | [23 empty] | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01
2AI133CV07500-08005 | EOF SS 52-SUBST-303 : Survey Marking, Excavation & Subgrade preparation | [23 empty] | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01
2AI133CV07500-08010 | EOF SS 52-SUBST-303 : Blinding/PCC | [23 empty] | 2017-06-08 | 2017-06-08 | 2017-06-08 | 2017-06-08 | 2017-06-08 | 2017-06-08 | 2017-06-08 | 2017-06-08 | 2017-06-08 | 2017-06-08 | 2017-06-08 | 2017-06-08 | 2017-06-08 | 2017-06-08 | 2017-06-08 | 2017-06-08 | 2017-06-08 | 2017-06-08 | 2017-06-08 | 2017-06-08 | 2017-06-08 | 2017-06-08 | 2017-06-08
2AI133CV07500-08015 | EOF SS 52-SUBST-303 : Rebar & Formwork | [23 empty] | 2017-06-10 | 2017-06-10 | 2017-06-10 | 2017-06-10 | 2017-06-10 | 2017-06-10 | 2017-06-10 | 2017-06-10 | 2017-06-10 | 2017-06-10 | 2017-06-10 | 2017-06-10 | 2017-06-10 | 2017-06-10 | 2017-06-10 | 2017-06-10 | 2017-06-10 | 2017-06-10 | 2017-06-10 | 2017-06-10 | 2017-06-10 | 2017-06-10 | 2017-06-10
2AI133CV07500-08020 | EOF SS 52-SUBST-303 : Concrete Pouring | [23 empty] | 2017-06-12 | 2017-06-12 | 2017-06-12 | 2017-06-12 | 2017-06-12 | 2017-06-12 | 2017-06-12 | 2017-06-12 | 2017-06-12 | 2017-06-12 | 2017-06-12 | 2017-06-12 | 2017-06-12 | 2017-06-12 | 2017-06-12 | 2017-06-12 | 2017-06-12 | 2017-06-12 | 2017-06-12 | 2017-06-12 | 2017-06-12 | 2017-06-12 | 2017-06-12
2AI133CV07500-08025 | EOF SS 52-SUBST-303 : Concrete Protection | [23 empty] | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27 | 2017-06-27
2AI133CV07500-08030 | EOF SS 52-SUBST-303 : Backfill / Compaction | [23 empty] | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25
2AI133CV07500-08035 | EOF SS 52-SUBST-303 : Construction of Pit | [23 empty] | 2017-06-12 | 2017-06-12 | 2017-06-12 | 2017-06-12 | 2017-06-12 | 2017-06-12 | 2017-06-12 | 2017-06-12 | 2017-06-12 | 2017-06-12 | 2017-06-12 | 2017-06-12 | 2017-06-12 | 2017-06-12 | 2017-06-12 | 2017-06-12 | 2017-06-12 | 2017-06-12 | 2017-06-12 | 2017-06-12 | 2017-06-12 | 2017-06-12 | 2017-06-12
2AI133CV11300 | EOF EG Building 50-R-002 : Diesel Day Tank Foundation | [29 empty] | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23
2AI133CV11300-08005 | EOF EG Building 50-R-002 : Diesel Day Tank Foundation | [29 empty] | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23
2AI133CV11300-08006 | Survey Marking, Excavation & Subgrade preparation | [29 empty] | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23
2AI133CV11300-08010 | Blinding/PCC | [29 empty] | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23
2AI133CV11300-08020 | Rebar & Formwork - for Footing | [29 empty] | 2017-12-25 | 2017-12-25 | 2017-12-25 | 2017-12-25 | 2017-12-25 | 2017-12-25 | 2017-12-25 | 2017-12-25 | 2017-12-25 | 2017-12-25 | 2017-12-25 | 2017-12-25 | 2017-12-25 | 2017-12-25 | 2017-12-25 | 2017-12-25 | 2017-12-25
2AI133CV11300-08030 | Concrete Pouring - for Footing | [29 empty] | 2018-01-02 | 2018-01-02 | 2018-01-02 | 2018-01-02 | 2018-01-02 | 2018-01-02 | 2018-01-02 | 2018-01-02 | 2018-01-02 | 2018-01-02 | 2018-01-02 | 2018-01-02 | 2018-01-02 | 2018-01-02 | 2018-01-02 | 2018-01-02 | 2018-01-02
2AI133CV11300-08031 | Rebar, Formwork & Install Embedments - for Pedestal | [29 empty] | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06
2AI133CV11300-08032 | Concrete Pouring - for Pedestal | [29 empty] | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11
2AI133CV11300-08040 | Concrete Protection | [29 empty] | 2018-01-18 | 2018-01-18 | 2018-01-18 | 2018-01-18 | 2018-01-18 | 2018-01-18 | 2018-01-18 | 2018-01-18 | 2018-01-18 | 2018-01-18 | 2018-01-18 | 2018-01-18 | 2018-01-18 | 2018-01-18 | 2018-01-18 | 2018-01-18 | 2018-01-18
2AI133CV11300-08050 | Backfill / Compaction | [29 empty] | 2018-01-24 | 2018-01-24 | 2018-01-24 | 2018-01-24 | 2018-01-24 | 2018-01-24 | 2018-01-24 | 2018-01-24 | 2018-01-24 | 2018-01-24 | 2018-01-24 | 2018-01-24 | 2018-01-24 | 2018-01-24 | 2018-01-24 | 2018-01-24 | 2018-01-24
2AI133CV21300 | EOF EG Building 52-R-301 : Construct Diesel Day Tank Foundation | [17 empty] | 2017-01-14 | 2017-01-14 | 2017-01-14 | 2017-01-14 | 2017-01-14 | 2017-01-14 | 2017-01-14 | 2017-01-14 | 2017-01-14 | 2017-01-14 | 2017-01-14 | 2017-01-14 | 2017-01-14 | 2017-01-14 | 2017-01-14 | 2017-01-14 | 2017-01-14 | 2017-01-14 | 2017-01-14 | 2017-01-14 | 2017-01-14 | 2017-01-14 | 2017-01-14 | 2017-01-14 | 2017-01-14 | 2017-01-14 | 2017-01-14 | 2017-01-14 | 2017-01-14
2AI133CV21300-08005 | EOF EG Building 52-R-301 : Diesel Day Tank Foundation | [17 empty] | 2017-01-14 | 2017-01-14 | 2017-01-14 | 2017-01-14 | 2017-01-14 | 2017-01-14 | 2017-01-14 | 2017-01-14 | 2017-01-14 | 2017-01-14 | 2017-01-14 | 2017-01-14 | 2017-01-14 | 2017-01-14 | 2017-01-14 | 2017-01-14 | 2017-01-14 | 2017-01-14 | 2017-01-14 | 2017-01-14 | 2017-01-14 | 2017-01-14 | 2017-01-14 | 2017-01-14 | 2017-01-14 | 2017-01-14 | 2017-01-14 | 2017-01-14 | 2017-01-14
2AI133CV21300-08006 | Survey Marking, Excavation & Subgrade preparation | [17 empty] | 2017-01-14 | 2017-01-14 | 2017-01-14 | 2017-01-14 | 2017-01-14 | 2017-01-14 | 2017-01-14 | 2017-01-14 | 2017-01-14 | 2017-01-14 | 2017-01-14 | 2017-01-14 | 2017-01-14 | 2017-01-14 | 2017-01-14 | 2017-01-14 | 2017-01-14 | 2017-01-14 | 2017-01-14 | 2017-01-14 | 2017-01-14 | 2017-01-14 | 2017-01-14 | 2017-01-14 | 2017-01-14 | 2017-01-14 | 2017-01-14 | 2017-01-14 | 2017-01-14
2AI133CV21300-08015 | Blinding/PCC | [17 empty] | 2017-01-18 | 2017-01-18 | 2017-01-18 | 2017-01-18 | 2017-01-18 | 2017-01-18 | 2017-01-18 | 2017-01-18 | 2017-01-18 | 2017-01-18 | 2017-01-18 | 2017-01-18 | 2017-01-18 | 2017-01-18 | 2017-01-18 | 2017-01-18 | 2017-01-18 | 2017-01-18 | 2017-01-18 | 2017-01-18 | 2017-01-18 | 2017-01-18 | 2017-01-18 | 2017-01-18 | 2017-01-18 | 2017-01-18 | 2017-01-18 | 2017-01-18 | 2017-01-18
2AI133CV21300-08025 | Rebar & Formwork - for Footing | [17 empty] | 2017-01-19 | 2017-01-19 | 2017-01-19 | 2017-01-19 | 2017-01-19 | 2017-01-19 | 2017-01-19 | 2017-01-19 | 2017-01-19 | 2017-01-19 | 2017-01-19 | 2017-01-19 | 2017-01-19 | 2017-01-19 | 2017-01-19 | 2017-01-19 | 2017-01-19 | 2017-01-19 | 2017-01-19 | 2017-01-19 | 2017-01-19 | 2017-01-19 | 2017-01-19 | 2017-01-19 | 2017-01-19 | 2017-01-19 | 2017-01-19 | 2017-01-19 | 2017-01-19
2AI133CV21300-08035 | Concrete Pouring - for Footing | [19 empty] | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16
2AI133CV21300-08036 | Rebar, Formwork & Install Embedments - for Pedestal | [19 empty] | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06
2AI133CV21300-08037 | Concrete Pouring - for Pedestal | [19 empty] | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08
2AI133CV21300-08045 | Concrete Protection | [21 empty] | 2017-03-28 | 2017-03-28 | 2017-03-28 | 2017-03-28 | 2017-03-28 | 2017-03-28 | 2017-03-28 | 2017-03-28 | 2017-03-28 | 2017-03-28 | 2017-03-28 | 2017-03-28 | 2017-03-28 | 2017-03-28 | 2017-03-28 | 2017-03-28 | 2017-03-28 | 2017-03-28 | 2017-03-28 | 2017-03-28 | 2017-03-28 | 2017-03-28 | 2017-03-28 | 2017-03-28 | 2017-03-28
2AI133CV21300-08055 | Backfill / Compaction | [21 empty] | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01 | 2017-04-01
2AI133CV31300 | EOF EG Building 52-R-302 : Diesel Day Tank Foundation | [27 empty] | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12
2AI133CV31300-08005 | EOF EG Building 52-R-302 : Diesel Day Tank Foundation | [27 empty] | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12
2AI133CV31300-08006 | Survey Marking, Excavation & Subgrade preparation | [27 empty] | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12
2AI133CV31300-08015 | Blinding/PCC | [27 empty] | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22
2AI133CV31300-08020 | Rebar & Formwork | [27 empty] | 2017-10-28 | 2017-10-28 | 2017-10-28 | 2017-10-28 | 2017-10-28 | 2017-10-28 | 2017-10-28 | 2017-10-28 | 2017-10-28 | 2017-10-28 | 2017-10-28 | 2017-10-28 | 2017-10-28 | 2017-10-28 | 2017-10-28 | 2017-10-28 | 2017-10-28 | 2017-10-28 | 2017-10-28
2AI133CV31300-08025 | Concrete Pouring | [27 empty] | 2017-10-30 | 2017-10-30 | 2017-10-30 | 2017-10-30 | 2017-10-30 | 2017-10-30 | 2017-10-30 | 2017-10-30 | 2017-10-30 | 2017-10-30 | 2017-10-30 | 2017-10-30 | 2017-10-30 | 2017-10-30 | 2017-10-30 | 2017-10-30 | 2017-10-30 | 2017-10-30 | 2017-10-30
2AI133CV31300-08030 | Concrete Protection | [27 empty] | 2017-11-17 | 2017-11-17 | 2017-11-17 | 2017-11-17 | 2017-11-17 | 2017-11-17 | 2017-11-17 | 2017-11-17 | 2017-11-17 | 2017-11-17 | 2017-11-17 | 2017-11-17 | 2017-11-17 | 2017-11-17 | 2017-11-17 | 2017-11-17 | 2017-11-17 | 2017-11-17 | 2017-11-17
2AI133CV31300-08035 | Backfill / Compaction | [29 empty] | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22
2AI133CV41300 | EOF EG Building 52-R-303 : Construct Diesel Day Tank Foundation | [23 empty] | 2017-07-02 | 2017-07-02 | 2017-07-02 | 2017-07-02 | 2017-07-02 | 2017-07-02 | 2017-07-02 | 2017-07-02 | 2017-07-02 | 2017-07-02 | 2017-07-02 | 2017-07-02 | 2017-07-02 | 2017-07-02 | 2017-07-02 | 2017-07-02 | 2017-07-02 | 2017-07-02 | 2017-07-02 | 2017-07-02 | 2017-07-02 | 2017-07-02 | 2017-07-02
2AI133CV41300-08005 | EOF EG Building 52-R-303 : Diesel Day Tank Foundation | [23 empty] | 2017-07-02 | 2017-07-02 | 2017-07-02 | 2017-07-02 | 2017-07-02 | 2017-07-02 | 2017-07-02 | 2017-07-02 | 2017-07-02 | 2017-07-02 | 2017-07-02 | 2017-07-02 | 2017-07-02 | 2017-07-02 | 2017-07-02 | 2017-07-02 | 2017-07-02 | 2017-07-02 | 2017-07-02 | 2017-07-02 | 2017-07-02 | 2017-07-02 | 2017-07-02
2AI133CV41300-08006 | Survey Marking, Excavation & Subgrade preparation | [23 empty] | 2017-07-02 | 2017-07-02 | 2017-07-02 | 2017-07-02 | 2017-07-02 | 2017-07-02 | 2017-07-02 | 2017-07-02 | 2017-07-02 | 2017-07-02 | 2017-07-02 | 2017-07-02 | 2017-07-02 | 2017-07-02 | 2017-07-02 | 2017-07-02 | 2017-07-02 | 2017-07-02 | 2017-07-02 | 2017-07-02 | 2017-07-02 | 2017-07-02 | 2017-07-02
2AI133CV41300-08010 | Blinding/PCC | [23 empty] | 2017-07-06 | 2017-07-06 | 2017-07-06 | 2017-07-06 | 2017-07-06 | 2017-07-06 | 2017-07-06 | 2017-07-06 | 2017-07-06 | 2017-07-06 | 2017-07-06 | 2017-07-06 | 2017-07-06 | 2017-07-06 | 2017-07-06 | 2017-07-06 | 2017-07-06 | 2017-07-06 | 2017-07-06 | 2017-07-06 | 2017-07-06 | 2017-07-06 | 2017-07-06
2AI133CV41300-08015 | Rebar & Formwork - for Footing | [23 empty] | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07 | 2017-07-07
2AI133CV41300-08020 | Concrete Pouring - for Footing | [23 empty] | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10
2AI133CV41300-08021 | Rebar, Formwork & Install Embedments - for Pedestal | [25 empty] | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03
2AI133CV41300-08022 | Concrete Pouring - for Pedestal | [25 empty] | 2017-08-08 | 2017-08-08 | 2017-08-08 | 2017-08-08 | 2017-08-08 | 2017-08-08 | 2017-08-08 | 2017-08-08 | 2017-08-08 | 2017-08-08 | 2017-08-08 | 2017-08-08 | 2017-08-08 | 2017-08-08 | 2017-08-08 | 2017-08-08 | 2017-08-08 | 2017-08-08 | 2017-08-08 | 2017-08-08 | 2017-08-08
2AI133CV41300-08025 | Concrete Protection | [25 empty] | 2017-08-18 | 2017-08-18 | 2017-08-18 | 2017-08-18 | 2017-08-18 | 2017-08-18 | 2017-08-18 | 2017-08-18 | 2017-08-18 | 2017-08-18 | 2017-08-18 | 2017-08-18 | 2017-08-18 | 2017-08-18 | 2017-08-18 | 2017-08-18 | 2017-08-18 | 2017-08-18 | 2017-08-18 | 2017-08-18 | 2017-08-18
2AI133CV41300-08030 | Backfill / Compaction | [27 empty] | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06
2AI133CV99000 | EOF SS : Shelter Foundation for Transformer, Capacitor | [23 empty] | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01
2AI133CV99000-08000 | EOF SS : Shelter Foundation for Transformers of 52-SUBST-301 - SUBSTATION - FMM | [23 empty] | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14
2AI133CV99000-08001 | EOF:Survey Marking, Excavation & Subgrade | [23 empty] | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14 | 2017-07-14
2AI133CV99000-08005 | EOF SS : Shelter Foundation for Transformers of 52-SUBST-302 - SUBSTATION - STF | [25 empty] | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26
2AI133CV99000-08006 | EOF:Blinding/PCC for Fnd | [23 empty] | 2017-07-22 | 2017-07-22 | 2017-07-22 | 2017-07-22 | 2017-07-22 | 2017-07-22 | 2017-07-22 | 2017-07-22 | 2017-07-22 | 2017-07-22 | 2017-07-22 | 2017-07-22 | 2017-07-22 | 2017-07-22 | 2017-07-22 | 2017-07-22 | 2017-07-22 | 2017-07-22 | 2017-07-22 | 2017-07-22 | 2017-07-22 | 2017-07-22 | 2017-07-22
2AI133CV99000-08010 | EOF SS : Shelter Foundation for Transformers of 50-SUBST-001 - SUBSTATION - COCC | [29 empty] | 2017-12-25 | 2017-12-25 | 2017-12-25 | 2017-12-25 | 2017-12-25 | 2017-12-25 | 2017-12-25 | 2017-12-25 | 2017-12-25 | 2017-12-25 | 2017-12-25 | 2017-12-25 | 2017-12-25 | 2017-12-25 | 2017-12-25 | 2017-12-25 | 2017-12-25
2AI133CV99000-08011 | EOF:Rebar, Formwork for Footing | [23 empty] | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23
2AI133CV99000-08015 | EOF SS : Shelter Foundation for Transformers of 52-SUBST-303 - SUBSTATION - LMM | [23 empty] | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01
2AI133CV99000-08016 | EOF:Concrete Pouring - for Footing | [25 empty] | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03
2AI133CV99000-08021 | EOF:Rebar, Formwork, Install Embedments for Pedestal | [25 empty] | 2017-08-06 | 2017-08-06 | 2017-08-06 | 2017-08-06 | 2017-08-06 | 2017-08-06 | 2017-08-06 | 2017-08-06 | 2017-08-06 | 2017-08-06 | 2017-08-06 | 2017-08-06 | 2017-08-06 | 2017-08-06 | 2017-08-06 | 2017-08-06 | 2017-08-06 | 2017-08-06 | 2017-08-06 | 2017-08-06 | 2017-08-06
2AI133CV99000-08026 | EOF:Concrete Pouring - for Pedestal | [27 empty] | 2017-10-08 | 2017-10-08 | 2017-10-08 | 2017-10-08 | 2017-10-08 | 2017-10-08 | 2017-10-08 | 2017-10-08 | 2017-10-08 | 2017-10-08 | 2017-10-08 | 2017-10-08 | 2017-10-08 | 2017-10-08 | 2017-10-08 | 2017-10-08 | 2017-10-08 | 2017-10-08 | 2017-10-08
2AI133CV99000-08031 | EOF:Concrete Potection for Fnd | [29 empty] | 2017-12-25 | 2017-12-25 | 2017-12-25 | 2017-12-25 | 2017-12-25 | 2017-12-25 | 2017-12-25 | 2017-12-25 | 2017-12-25 | 2017-12-25 | 2017-12-25 | 2017-12-25 | 2017-12-25 | 2017-12-25 | 2017-12-25 | 2017-12-25 | 2017-12-25
2AI133CV99000-08036 | EOF:Backfilling & Compaction for Fnd | [29 empty] | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16
2AI133CV99000-08335 | EOF:Survey Marking, Excavation & Subgrade | [25 empty] | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26
2AI133CV99000-08340 | EOF:Blinding/PCC for Fnd | [25 empty] | 2017-08-29 | 2017-08-29 | 2017-08-29 | 2017-08-29 | 2017-08-29 | 2017-08-29 | 2017-08-29 | 2017-08-29 | 2017-08-29 | 2017-08-29 | 2017-08-29 | 2017-08-29 | 2017-08-29 | 2017-08-29 | 2017-08-29 | 2017-08-29 | 2017-08-29 | 2017-08-29 | 2017-08-29 | 2017-08-29 | 2017-08-29
2AI133CV99000-08345 | EOF:Rebar, Formwork for Footing | [25 empty] | 2017-08-30 | 2017-08-30 | 2017-08-30 | 2017-08-30 | 2017-08-30 | 2017-08-30 | 2017-08-30 | 2017-08-30 | 2017-08-30 | 2017-08-30 | 2017-08-30 | 2017-08-30 | 2017-08-30 | 2017-08-30 | 2017-08-30 | 2017-08-30 | 2017-08-30 | 2017-08-30 | 2017-08-30 | 2017-08-30 | 2017-08-30
2AI133CV99000-08346 | EOF:Concrete Pouring - for Footing | [25 empty] | 2017-09-12 | 2017-09-12 | 2017-09-12 | 2017-09-12 | 2017-09-12 | 2017-09-12 | 2017-09-12 | 2017-09-12 | 2017-09-12 | 2017-09-12 | 2017-09-12 | 2017-09-12 | 2017-09-12 | 2017-09-12 | 2017-09-12 | 2017-09-12 | 2017-09-12 | 2017-09-12 | 2017-09-12 | 2017-09-12 | 2017-09-12
2AI133CV99000-08350 | EOF:Rebar, Formwork & Install Embedments for Pedestal | [25 empty] | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19
2AI133CV99000-08351 | EOF:Concrete Pouring - for Pedestal | [27 empty] | 2017-10-28 | 2017-10-28 | 2017-10-28 | 2017-10-28 | 2017-10-28 | 2017-10-28 | 2017-10-28 | 2017-10-28 | 2017-10-28 | 2017-10-28 | 2017-10-28 | 2017-10-28 | 2017-10-28 | 2017-10-28 | 2017-10-28 | 2017-10-28 | 2017-10-28 | 2017-10-28 | 2017-10-28
2AI133CV99000-08355 | EOF:Concrete Potection for Fnd | [31 empty] | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27
2AI133CV99000-08360 | EOF:Backfilling & Compaction for Fnd | [31 empty] | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27
2AI133CV99000-08365 | EOF:Survey Marking, Excavation & Subgrade | [29 empty] | 2017-12-25 | 2017-12-25 | 2017-12-25 | 2017-12-25 | 2017-12-25 | 2017-12-25 | 2017-12-25 | 2017-12-25 | 2017-12-25 | 2017-12-25 | 2017-12-25 | 2017-12-25 | 2017-12-25 | 2017-12-25 | 2017-12-25 | 2017-12-25 | 2017-12-25
2AI133CV99000-08370 | EOF:Blinding/PCC for Fnd | [29 empty] | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26
2AI133CV99000-08375 | EOF:Rebar, Formwork for Footing | [29 empty] | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26
2AI133CV99000-08376 | EOF:Concrete Pouring - for Footing | [29 empty] | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26
2AI133CV99000-08380 | EOF:Rebar, Formwork & Install Embedments for Pedestal | [29 empty] | 2017-12-29 | 2017-12-29 | 2017-12-29 | 2017-12-29 | 2017-12-29 | 2017-12-29 | 2017-12-29 | 2017-12-29 | 2017-12-29 | 2017-12-29 | 2017-12-29 | 2017-12-29 | 2017-12-29 | 2017-12-29 | 2017-12-29 | 2017-12-29 | 2017-12-29
2AI133CV99000-08381 | EOF:Concrete Pouring - for Pedestal | [29 empty] | 2018-01-07 | 2018-01-07 | 2018-01-07 | 2018-01-07 | 2018-01-07 | 2018-01-07 | 2018-01-07 | 2018-01-07 | 2018-01-07 | 2018-01-07 | 2018-01-07 | 2018-01-07 | 2018-01-07 | 2018-01-07 | 2018-01-07 | 2018-01-07 | 2018-01-07
2AI133CV99000-08385 | EOF:Concrete Potection for Fnd | [31 empty] | 2018-03-10 | 2018-03-10 | 2018-03-10 | 2018-03-10 | 2018-03-10 | 2018-03-10 | 2018-03-10 | 2018-03-10 | 2018-03-10 | 2018-03-10 | 2018-03-10 | 2018-03-10 | 2018-03-10 | 2018-03-10 | 2018-03-10
2AI133CV99000-08390 | EOF:Backfilling & Compaction for Fnd | [35 empty] | 2018-06-24 | 2018-06-24 | 2018-06-24 | 2018-06-24 | 2018-06-24 | 2018-06-24 | 2018-06-24 | 2018-06-24 | 2018-06-24 | 2018-06-24 | 2018-06-24
2AI133CV99000-08395 | EOF:Excavation & Subgrade | [23 empty] | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01
2AI133CV99000-08400 | EOF:Blinding/PCC for Fnd | [23 empty] | 2017-06-08 | 2017-06-08 | 2017-06-08 | 2017-06-08 | 2017-06-08 | 2017-06-08 | 2017-06-08 | 2017-06-08 | 2017-06-08 | 2017-06-08 | 2017-06-08 | 2017-06-08 | 2017-06-08 | 2017-06-08 | 2017-06-08 | 2017-06-08 | 2017-06-08 | 2017-06-08 | 2017-06-08 | 2017-06-08 | 2017-06-08 | 2017-06-08 | 2017-06-08
2AI133CV99000-08405 | EOF:Rebar, Formwork for Footing | [23 empty] | 2017-06-09 | 2017-06-09 | 2017-06-09 | 2017-06-09 | 2017-06-09 | 2017-06-09 | 2017-06-09 | 2017-06-09 | 2017-06-09 | 2017-06-09 | 2017-06-09 | 2017-06-09 | 2017-06-09 | 2017-06-09 | 2017-06-09 | 2017-06-09 | 2017-06-09 | 2017-06-09 | 2017-06-09 | 2017-06-09 | 2017-06-09 | 2017-06-09 | 2017-06-09
2AI133CV99000-08406 | EOF:Concrete Pouring - for Footing | [23 empty] | 2017-06-12 | 2017-06-12 | 2017-06-12 | 2017-06-12 | 2017-06-12 | 2017-06-12 | 2017-06-12 | 2017-06-12 | 2017-06-12 | 2017-06-12 | 2017-06-12 | 2017-06-12 | 2017-06-12 | 2017-06-12 | 2017-06-12 | 2017-06-12 | 2017-06-12 | 2017-06-12 | 2017-06-12 | 2017-06-12 | 2017-06-12 | 2017-06-12 | 2017-06-12
2AI133CV99000-08410 | EOF:Rebar, Formwork & Install Embedments for Pedestal | [23 empty] | 2017-06-13 | 2017-06-13 | 2017-06-13 | 2017-06-13 | 2017-06-13 | 2017-06-13 | 2017-06-13 | 2017-06-13 | 2017-06-13 | 2017-06-13 | 2017-06-13 | 2017-06-13 | 2017-06-13 | 2017-06-13 | 2017-06-13 | 2017-06-13 | 2017-06-13 | 2017-06-13 | 2017-06-13 | 2017-06-13 | 2017-06-13 | 2017-06-13 | 2017-06-13
2AI133CV99000-08411 | EOF:Concrete Pouring - for Pedestal | [23 empty] | 2017-06-22 | 2017-06-22 | 2017-06-22 | 2017-06-22 | 2017-06-22 | 2017-06-22 | 2017-06-22 | 2017-06-22 | 2017-06-22 | 2017-06-22 | 2017-06-22 | 2017-06-22 | 2017-06-22 | 2017-06-22 | 2017-06-22 | 2017-06-22 | 2017-06-22 | 2017-06-22 | 2017-06-22 | 2017-06-22 | 2017-06-22 | 2017-06-22 | 2017-06-22
2AI133CV99000-08415 | EOF:Concrete Potection for Fnd | [25 empty] | 2017-08-13 | 2017-08-13 | 2017-08-13 | 2017-08-13 | 2017-08-13 | 2017-08-13 | 2017-08-13 | 2017-08-13 | 2017-08-13 | 2017-08-13 | 2017-08-13 | 2017-08-13 | 2017-08-13 | 2017-08-13 | 2017-08-13 | 2017-08-13 | 2017-08-13 | 2017-08-13 | 2017-08-13 | 2017-08-13 | 2017-08-13
2AI133CV99000-08420 | EOF:Backfilling & Compaction for Fnd | [25 empty] | 2017-08-17 | 2017-08-17 | 2017-08-17 | 2017-08-17 | 2017-08-17 | 2017-08-17 | 2017-08-17 | 2017-08-17 | 2017-08-17 | 2017-08-17 | 2017-08-17 | 2017-08-17 | 2017-08-17 | 2017-08-17 | 2017-08-17 | 2017-08-17 | 2017-08-17 | 2017-08-17 | 2017-08-17 | 2017-08-17 | 2017-08-17
2AI133CV99100 | EOF SS : Shelter Erection for Transformer, Capacitor | [29 empty] | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26
2AI133CV99100-08000 | EOF SS : Shelter Erection for Transformer, Capacitor of 52-SUBST-301 - SUBSTATION - FMM | [29 empty] | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11
2AI133CV99100-08001 | EOF:Installation of Str. Steel | [29 empty] | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11
2AI133CV99100-08005 | EOF SS : Shelter Erection for Transformer, Capacitor of 52-SUBST-302 - SUBSTATION - STF | [31 empty] | 2018-02-11 | 2018-02-11 | 2018-02-11 | 2018-02-11 | 2018-02-11 | 2018-02-11 | 2018-02-11 | 2018-02-11 | 2018-02-11 | 2018-02-11 | 2018-02-11 | 2018-02-11 | 2018-02-11 | 2018-02-11 | 2018-02-11
2AI133CV99100-08006 | EOF:Alignment & Bolting/Torqueing | [29 empty] | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21
2AI133CV99100-08010 | EOF SS : Shelter Erection for Transformer, Capacitor of 50-SUBST-001 - SUBSTATION - COCC | [37 empty] | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24
2AI133CV99100-08011 | EOF:Grouting | [33 empty] | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07
2AI133CV99100-08015 | EOF SS : Shelter Erection for Transformer, Capacitor of 52-SUBST-303 - SUBSTATION - LMM | [29 empty] | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26
2AI133CV99100-08016 | EOF:Installation of Str. Steel | [31 empty] | 2018-02-11 | 2018-02-11 | 2018-02-11 | 2018-02-11 | 2018-02-11 | 2018-02-11 | 2018-02-11 | 2018-02-11 | 2018-02-11 | 2018-02-11 | 2018-02-11 | 2018-02-11 | 2018-02-11 | 2018-02-11 | 2018-02-11
2AI133CV99100-08020 | EOF:Alignment & Bolting/Torqueing | [31 empty] | 2018-02-11 | 2018-02-11 | 2018-02-11 | 2018-02-11 | 2018-02-11 | 2018-02-11 | 2018-02-11 | 2018-02-11 | 2018-02-11 | 2018-02-11 | 2018-02-11 | 2018-02-11 | 2018-02-11 | 2018-02-11 | 2018-02-11
2AI133CV99100-08021 | Installation of gratings/handrail/stair/ladder (wherever applicable) | [33 empty] | 2018-05-10 | 2018-05-10 | 2018-05-10 | 2018-05-10 | 2018-05-10 | 2018-05-10 | 2018-05-10 | 2018-05-10 | 2018-05-10 | 2018-05-10 | 2018-05-10 | 2018-05-10 | 2018-05-10
2AI133CV99100-08025 | EOF:Grouting | [37 empty] | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23
2AI133CV99100-08030 | EOF:Installation of Str. Steel | [37 empty] | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24
2AI133CV99100-08031 | Wall & Roof Cladding | [33 empty] | 2018-05-10 | 2018-05-10 | 2018-05-10 | 2018-05-10 | 2018-05-10 | 2018-05-10 | 2018-05-10 | 2018-05-10 | 2018-05-10 | 2018-05-10 | 2018-05-10 | 2018-05-10 | 2018-05-10
2AI133CV99100-08035 | EOF:Alignment & Bolting/Torqueing | [37 empty] | 2018-09-26 | 2018-09-26 | 2018-09-26 | 2018-09-26 | 2018-09-26 | 2018-09-26 | 2018-09-26 | 2018-09-26 | 2018-09-26
2AI133CV99100-08040 | EOF:Grouting | [37 empty] | 2018-09-26 | 2018-09-26 | 2018-09-26 | 2018-09-26 | 2018-09-26 | 2018-09-26 | 2018-09-26 | 2018-09-26 | 2018-09-26
2AI133CV99100-08045 | EOF:Installation of Str. Steel | [29 empty] | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26 | 2017-12-26
2AI133CV99100-08050 | EOF:Alignment & Bolting/Torqueing | [29 empty] | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22
2AI133CV99100-08055 | EOF:Grouting | [37 empty] | 2018-08-27 | 2018-08-27 | 2018-08-27 | 2018-08-27 | 2018-08-27 | 2018-08-27 | 2018-08-27 | 2018-08-27 | 2018-08-27
2AI133CV99100-08060 | Installation of gratings/handrail/stair/ladder (wherever applicable) | [37 empty] | 2018-09-26 | 2018-09-26 | 2018-09-26 | 2018-09-26 | 2018-09-26 | 2018-09-26 | 2018-09-26 | 2018-09-26 | 2018-09-26
2AI133CV99100-08065 | Installation of gratings/handrail/stair/ladder (wherever applicable) | [33 empty] | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05
2AI133CV99100-08070 | Wall & Roof Cladding | [33 empty] | 2018-05-05: 2018-10-02; 2018-05-05: 2018-10-02; 2018-05-05: 2018-10-02; 2018-05-05: 2018-10-02; 2018-05-05: 2018-10-02; 2018-05-05: 2018-10-02; 2018-05-05: 2018-10-02
2AI133CV99100-08075 | Wall & Roof Cladding | [33 empty] | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05
2AI133CV99100-08085 | Installation of gratings/handrail/stair/ladder (wherever applicable) | [33 empty] | 2018-05-05: 2018-12-12; 2018-05-05: 2018-12-12; 2018-05-05: 2018-12-12; 2018-05-05: 2018-12-12; 2018-05-05: 2018-12-12
2AI133CV99100-08095 | Wall & Roof Cladding | [37 empty] | 2018-08-18 | 2018-08-18 | 2018-08-18 | 2018-08-18 | 2018-08-18 | 2018-08-18 | 2018-08-18 | 2018-08-18 | 2018-08-18
2AI133CV99200 | EOF SS : Shelter Foundation for Diesel Tank & Inert Agent | [23 empty] | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05
2AI133CV99200-08000 | EOF SS : Shelter Foundation for Diesel Tank & Inert Agent of 52-SUBST-301 - SUBSTATION - FMM | [23 empty] | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05
2AI133CV99200-08001 | EOF:Survey Marking, Excavation & Subgrade | [23 empty] | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05
2AI133CV99200-08005 | EOF SS : Shelter Foundation for Diesel Tank & Inert Agent of 52-SUBST-302 - SUBSTATION - STF | [27 empty] | 2017-10-13 | 2017-10-13 | 2017-10-13 | 2017-10-13 | 2017-10-13 | 2017-10-13 | 2017-10-13 | 2017-10-13 | 2017-10-13 | 2017-10-13 | 2017-10-13 | 2017-10-13 | 2017-10-13 | 2017-10-13 | 2017-10-13 | 2017-10-13 | 2017-10-13 | 2017-10-13 | 2017-10-13
2AI133CV99200-08006 | EOF:Blinding/PCC for Fnd | [23 empty] | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23 | 2017-07-23
2AI133CV99200-08010 | EOF SS : Shelter Foundation for Diesel Tank & Inert Agent of 50-SUBST-001 - SUBSTATION - COCC | [29 empty] | 2017-12-15 | 2017-12-15 | 2017-12-15 | 2017-12-15 | 2017-12-15 | 2017-12-15 | 2017-12-15 | 2017-12-15 | 2017-12-15 | 2017-12-15 | 2017-12-15 | 2017-12-15 | 2017-12-15 | 2017-12-15 | 2017-12-15 | 2017-12-15 | 2017-12-15
2AI133CV99200-08011 | EOF:Rebar, Formwork for Footing | [27 empty] | 2017-09-24 | 2017-09-24 | 2017-09-24 | 2017-09-24 | 2017-09-24 | 2017-09-24 | 2017-09-24 | 2017-09-24 | 2017-09-24 | 2017-09-24 | 2017-09-24 | 2017-09-24 | 2017-09-24 | 2017-09-24 | 2017-09-24 | 2017-09-24 | 2017-09-24 | 2017-09-24 | 2017-09-24
2AI133CV99200-08015 | EOF SS : Shelter Foundation for Diesel Tank & Inert Agent of 52-SUBST-303 - SUBSTATION - LMM | [27 empty] | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30
2AI133CV99200-08016 | EOF:Concrete Pouring - for Footing | [27 empty] | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02
2AI133CV99200-08021 | EOF:Rebar, Formwork, Install Embedments for Pedestal | [27 empty] | 2017-09-23 | 2017-09-23 | 2017-09-23 | 2017-09-23 | 2017-09-23 | 2017-09-23 | 2017-09-23 | 2017-09-23 | 2017-09-23 | 2017-09-23 | 2017-09-23 | 2017-09-23 | 2017-09-23 | 2017-09-23 | 2017-09-23 | 2017-09-23 | 2017-09-23 | 2017-09-23 | 2017-09-23
2AI133CV99200-08026 | EOF:Concrete Pouring - for Pedestal | [27 empty] | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02
2AI133CV99200-08030 | EOF:Survey Marking, Excavation & Subgrade | [27 empty] | 2017-10-13 | 2017-10-13 | 2017-10-13 | 2017-10-13 | 2017-10-13 | 2017-10-13 | 2017-10-13 | 2017-10-13 | 2017-10-13 | 2017-10-13 | 2017-10-13 | 2017-10-13 | 2017-10-13 | 2017-10-13 | 2017-10-13 | 2017-10-13 | 2017-10-13 | 2017-10-13 | 2017-10-13
2AI133CV99200-08031 | EOF:Concrete Potection for Fnd | [27 empty] | 2017-10-10 | 2017-10-10 | 2017-10-10 | 2017-10-10 | 2017-10-10 | 2017-10-10 | 2017-10-10 | 2017-10-10 | 2017-10-10 | 2017-10-10 | 2017-10-10 | 2017-10-10 | 2017-10-10 | 2017-10-10 | 2017-10-10 | 2017-10-10 | 2017-10-10 | 2017-10-10 | 2017-10-10
2AI133CV99200-08035 | EOF:Blinding/PCC for Fnd | [27 empty] | 2017-10-25 | 2017-10-25 | 2017-10-25 | 2017-10-25 | 2017-10-25 | 2017-10-25 | 2017-10-25 | 2017-10-25 | 2017-10-25 | 2017-10-25 | 2017-10-25 | 2017-10-25 | 2017-10-25 | 2017-10-25 | 2017-10-25 | 2017-10-25 | 2017-10-25 | 2017-10-25 | 2017-10-25
2AI133CV99200-08036 | EOF:Backfilling & Compaction for Fnd | [31 empty] | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05
2AI133CV99200-08040 | EOF:Rebar, Formwork for Footing | [27 empty] | 2017-10-26 | 2017-10-26 | 2017-10-26 | 2017-10-26 | 2017-10-26 | 2017-10-26 | 2017-10-26 | 2017-10-26 | 2017-10-26 | 2017-10-26 | 2017-10-26 | 2017-10-26 | 2017-10-26 | 2017-10-26 | 2017-10-26 | 2017-10-26 | 2017-10-26 | 2017-10-26 | 2017-10-26
2AI133CV99200-08041 | EOF:Concrete Pouring - for Footing | [29 empty] | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03
2AI133CV99200-08045 | EOF:Rebar, Formwork, Install Embedments for Pedestal | [27 empty] | 2017-10-26 | 2017-10-26 | 2017-10-26 | 2017-10-26 | 2017-10-26 | 2017-10-26 | 2017-10-26 | 2017-10-26 | 2017-10-26 | 2017-10-26 | 2017-10-26 | 2017-10-26 | 2017-10-26 | 2017-10-26 | 2017-10-26 | 2017-10-26 | 2017-10-26 | 2017-10-26 | 2017-10-26
2AI133CV99200-08046 | EOF:Concrete Pouring - for Pedestal | [29 empty] | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03
2AI133CV99200-08050 | EOF:Concrete Potection for Fnd | [29 empty] | 2018-01-07 | 2018-01-07 | 2018-01-07 | 2018-01-07 | 2018-01-07 | 2018-01-07 | 2018-01-07 | 2018-01-07 | 2018-01-07 | 2018-01-07 | 2018-01-07 | 2018-01-07 | 2018-01-07 | 2018-01-07 | 2018-01-07 | 2018-01-07 | 2018-01-07
2AI133CV99200-08055 | EOF:Backfilling & Compaction for Fnd | [31 empty] | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27
2AI133CV99200-08060 | EOF:Survey Marking, Excavation & Subgrade | [29 empty] | 2017-12-15 | 2017-12-15 | 2017-12-15 | 2017-12-15 | 2017-12-15 | 2017-12-15 | 2017-12-15 | 2017-12-15 | 2017-12-15 | 2017-12-15 | 2017-12-15 | 2017-12-15 | 2017-12-15 | 2017-12-15 | 2017-12-15 | 2017-12-15 | 2017-12-15
2AI133CV99200-08065 | EOF:Blinding/PCC for Fnd | [29 empty] | 2017-12-21 | 2017-12-21 | 2017-12-21 | 2017-12-21 | 2017-12-21 | 2017-12-21 | 2017-12-21 | 2017-12-21 | 2017-12-21 | 2017-12-21 | 2017-12-21 | 2017-12-21 | 2017-12-21 | 2017-12-21 | 2017-12-21 | 2017-12-21 | 2017-12-21
2AI133CV99200-08070 | EOF:Rebar, Formwork for Footing | [29 empty] | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23
2AI133CV99200-08071 | EOF:Concrete Pouring - for Footing | [29 empty] | 2017-12-31 | 2017-12-31 | 2017-12-31 | 2017-12-31 | 2017-12-31 | 2017-12-31 | 2017-12-31 | 2017-12-31 | 2017-12-31 | 2017-12-31 | 2017-12-31 | 2017-12-31 | 2017-12-31 | 2017-12-31 | 2017-12-31 | 2017-12-31 | 2017-12-31
2AI133CV99200-08075 | EOF:Rebar, Formwork, Install Embedments for Pedestal | [29 empty] | 2018-01-02 | 2018-01-02 | 2018-01-02 | 2018-01-02 | 2018-01-02 | 2018-01-02 | 2018-01-02 | 2018-01-02 | 2018-01-02 | 2018-01-02 | 2018-01-02 | 2018-01-02 | 2018-01-02 | 2018-01-02 | 2018-01-02 | 2018-01-02 | 2018-01-02
2AI133CV99200-08076 | EOF:Concrete Pouring - for Pedestal | [29 empty] | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11 | 2018-01-11
2AI133CV99200-08080 | EOF:Concrete Potection for Fnd | [29 empty] | 2018-01-15 | 2018-01-15 | 2018-01-15 | 2018-01-15 | 2018-01-15 | 2018-01-15 | 2018-01-15 | 2018-01-15 | 2018-01-15 | 2018-01-15 | 2018-01-15 | 2018-01-15 | 2018-01-15 | 2018-01-15 | 2018-01-15 | 2018-01-15 | 2018-01-15
2AI133CV99200-08085 | EOF:Backfilling & Compaction for Fnd | [29 empty] | 2018-01-23 | 2018-01-23 | 2018-01-23 | 2018-01-23 | 2018-01-23 | 2018-01-23 | 2018-01-23 | 2018-01-23 | 2018-01-23 | 2018-01-23 | 2018-01-23 | 2018-01-23 | 2018-01-23 | 2018-01-23 | 2018-01-23 | 2018-01-23 | 2018-01-23
2AI133CV99200-08090 | EOF:Survey Marking, Excavation & Subgrade | [27 empty] | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30
2AI133CV99200-08095 | EOF:Blinding/PCC for Fnd | [27 empty] | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02
2AI133CV99200-08100 | EOF:Rebar, Formwork for Footing | [27 empty] | 2017-10-03 | 2017-10-03 | 2017-10-03 | 2017-10-03 | 2017-10-03 | 2017-10-03 | 2017-10-03 | 2017-10-03 | 2017-10-03 | 2017-10-03 | 2017-10-03 | 2017-10-03 | 2017-10-03 | 2017-10-03 | 2017-10-03 | 2017-10-03 | 2017-10-03 | 2017-10-03 | 2017-10-03
2AI133CV99200-08101 | EOF:Concrete Pouring - for Footing | [27 empty] | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08
2AI133CV99200-08105 | EOF:Rebar, Formwork, Install Embedments for Pedestal | [27 empty] | 2017-10-03 | 2017-10-03 | 2017-10-03 | 2017-10-03 | 2017-10-03 | 2017-10-03 | 2017-10-03 | 2017-10-03 | 2017-10-03 | 2017-10-03 | 2017-10-03 | 2017-10-03 | 2017-10-03 | 2017-10-03 | 2017-10-03 | 2017-10-03 | 2017-10-03 | 2017-10-03 | 2017-10-03
2AI133CV99200-08106 | EOF:Concrete Pouring - for Pedestal | [27 empty] | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08
2AI133CV99200-08110 | EOF:Concrete Potection for Fnd | [27 empty] | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16
2AI133CV99200-08115 | EOF:Backfilling & Compaction for Fnd | [29 empty] | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06
2AI133CV99300 | EOF SS : Shelter Erection for Diesel Tank & Inert Agent | [27 empty] | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22
2AI133CV99300-08000 | Shelter Erection for Diesel Tank & Inert Agent of 52-SUBST-301 - SUBSTATION - FMM | [27 empty] | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22
2AI133CV99300-08005 | Shelter Erection for Diesel Tank & Inert Agent of 52-SUBST-302 - SUBSTATION - STF | [29 empty] | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22
2AI133CV99300-08006 | EOF:Installation of Str. Steel | [27 empty] | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22
2AI133CV99300-08010 | Shelter Erection for Diesel Tank & Inert Agent of 50-SUBST-001 - SUBSTATION - COCC | [35 empty] | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23
2AI133CV99300-08011 | EOF:Alignment & Bolting/Torqueing | [27 empty] | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22
2AI133CV99300-08015 | Shelter Erection for Diesel Tank & Inert Agent of 52-SUBST-303 - SUBSTATION - LMM | [27 empty] | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15
2AI133CV99300-08016 | EOF:Grouting | [37 empty] | 2018-08-06 | 2018-08-06 | 2018-08-06 | 2018-08-06 | 2018-08-06 | 2018-08-06 | 2018-08-06 | 2018-08-06 | 2018-08-06
2AI133CV99300-08021 | EOF:Installation of Str. Steel | [29 empty] | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22
2AI133CV99300-08022 | EOF:Alignment & Bolting/Torqueing | [29 empty] | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22
2AI133CV99300-08025 | EOF:Grouting | [35 empty] | 2018-06-08 | 2018-06-08 | 2018-06-08 | 2018-06-08 | 2018-06-08 | 2018-06-08 | 2018-06-08 | 2018-06-08 | 2018-06-08 | 2018-06-08 | 2018-06-08
2AI133CV99300-08026 | EOF:Installation of gratings/handrail/stair/ladder (wherever applicable) | [37 empty] | 2018-08-06 | 2018-08-06 | 2018-08-06 | 2018-08-06 | 2018-08-06 | 2018-08-06 | 2018-08-06 | 2018-08-06 | 2018-08-06
2AI133CV99300-08030 | EOF:Installation of Str. Steel | [35 empty] | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23
2AI133CV99300-08035 | EOF:Alignment & Bolting/Torqueing | [35 empty] | 2018-06-24 | 2018-06-24 | 2018-06-24 | 2018-06-24 | 2018-06-24 | 2018-06-24 | 2018-06-24 | 2018-06-24 | 2018-06-24 | 2018-06-24 | 2018-06-24
2AI133CV99300-08036 | EOF:Wall & Roof Cladding | [37 empty] | 2018-08-06 | 2018-08-06 | 2018-08-06 | 2018-08-06 | 2018-08-06 | 2018-08-06 | 2018-08-06 | 2018-08-06 | 2018-08-06
2AI133CV99300-08040 | EOF:Grouting | [37 empty] | 2018-08-06: 2018-12-21; 2018-08-06: 2018-12-21; 2018-08-06: 2018-12-21; 2018-08-06: 2018-12-21; 2018-08-06: 2018-12-21
2AI133CV99300-08045 | EOF:Installation of Str. Steel | [27 empty] | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15
2AI133CV99300-08050 | EOF:Alignment & Bolting/Torqueing | [29 empty] | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04
2AI133CV99300-08055 | EOF:Grouting | [29 empty] | 2017-12-04: 2018-10-17; 2017-12-04: 2018-10-17; 2017-12-04: 2018-10-17; 2017-12-04: 2018-10-17; 2017-12-04: 2018-10-17; 2017-12-04: 2018-10-17; 2017-12-04: 2018-10-17
2AI133CV99300-08060 | EOF:Installation of gratings/handrail/stair/ladder (wherever applicable) | [29 empty] | 2017-12-04: 2018-12-15; 2017-12-04: 2018-12-15; 2017-12-04: 2018-12-15; 2017-12-04: 2018-12-15; 2017-12-04: 2018-12-15
2AI133CV99300-08065 | EOF:Installation of gratings/handrail/stair/ladder (wherever applicable) | [35 empty] | 2018-06-08 | 2018-06-08 | 2018-06-08 | 2018-06-08 | 2018-06-08 | 2018-06-08 | 2018-06-08 | 2018-06-08 | 2018-06-08 | 2018-06-08 | 2018-06-08
2AI133CV99300-08070 | EOF:Wall & Roof Cladding | [35 empty] | 2018-06-08: 2018-12-15; 2018-06-08: 2018-12-15; 2018-06-08: 2018-12-15; 2018-06-08: 2018-12-15; 2018-06-08: 2018-12-15
2AI133CV99300-08075 | EOF:Installation of gratings/handrail/stair/ladder (wherever applicable) | [39 empty] | 2018-10-17 | 2018-10-17 | 2018-10-17 | 2018-10-17 | 2018-10-17 | 2018-10-17 | 2018-10-17
2AI133CV99300-08085 | EOF:Wall & Roof Cladding | [39 empty] | 2018-10-21 | 2018-10-21 | 2018-10-21 | 2018-10-21 | 2018-10-21 | 2018-10-21 | 2018-10-21
2AI133CV99300-08095 | EOF:Wall & Roof Cladding | [39 empty] | 2018-10-28 | 2018-10-28 | 2018-10-28 | 2018-10-28 | 2018-10-28 | 2018-10-28 | 2018-10-28
2AI133CV99400 | COCC : Construct Car Shelter Foundation & Miscellanious Shelter Foundation | [19 empty] | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11
2AI133CV99400-08000 | COCC: Excavation & Subgrade | [19 empty] | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11
2AI133CV99400-08005 | COCC: Blinding/PCC for Fnd | [19 empty] | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13 | 2017-02-13
2AI133CV99400-08010 | COCC: Rebar, Formwork for Footing | [19 empty] | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04
2AI133CV99400-08011 | COCC:Concrete Pouring for Footing | [19 empty] | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06
2AI133CV99400-08015 | COCC: Rebar, Formwork & Install Embedments for Pedestal | [19 empty] | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28 | 2017-02-28
2AI133CV99400-08016 | COCC:Concrete Pouring for Pedestal | [19 empty] | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08
2AI133CV99400-08020 | COCC: Concrete Potection for Fnd | [19 empty] | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14
2AI133CV99400-08025 | COCC: Backfilling & Compaction for Fnd | [19 empty] | 2017-03-20 | 2017-03-20 | 2017-03-20 | 2017-03-20 | 2017-03-20 | 2017-03-20 | 2017-03-20 | 2017-03-20 | 2017-03-20 | 2017-03-20 | 2017-03-20 | 2017-03-20 | 2017-03-20 | 2017-03-20 | 2017-03-20 | 2017-03-20 | 2017-03-20 | 2017-03-20 | 2017-03-20 | 2017-03-20 | 2017-03-20 | 2017-03-20 | 2017-03-20 | 2017-03-20 | 2017-03-20 | 2017-03-20 | 2017-03-20
2AI133CV99400-08141 | COCC : Shelter Foundation for Car Park | [19 empty] | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11 | 2017-02-11
2AI133CV99500 | COCC : Car Shelter Erection & Miscellanious Shelter | [33 empty] | 2018-04-12 | 2018-04-12 | 2018-04-12 | 2018-04-12 | 2018-04-12 | 2018-04-12 | 2018-04-12 | 2018-04-12 | 2018-04-12 | 2018-04-12 | 2018-04-12 | 2018-04-12 | 2018-04-12
2AI133CV99500-08000 | COCC: Installation of Main steel structure | [33 empty] | 2018-04-12 | 2018-04-12 | 2018-04-12 | 2018-04-12 | 2018-04-12 | 2018-04-12 | 2018-04-12 | 2018-04-12 | 2018-04-12 | 2018-04-12 | 2018-04-12 | 2018-04-12 | 2018-04-12
2AI133CV99500-08005 | COCC: Alignment/Welding/Bolting for Shelter | [33 empty] | 2018-04-28 | 2018-04-28 | 2018-04-28 | 2018-04-28 | 2018-04-28 | 2018-04-28 | 2018-04-28 | 2018-04-28 | 2018-04-28 | 2018-04-28 | 2018-04-28 | 2018-04-28 | 2018-04-28
2AI133CV99500-08006 | COCC:Torque Bolts | [33 empty] | 2018-04-30 | 2018-04-30 | 2018-04-30 | 2018-04-30 | 2018-04-30 | 2018-04-30 | 2018-04-30 | 2018-04-30 | 2018-04-30 | 2018-04-30 | 2018-04-30 | 2018-04-30 | 2018-04-30
2AI133CV99500-08010 | COCC: Grouting of Shelter | [37 empty] | 2018-08-06 | 2018-08-06 | 2018-08-06 | 2018-08-06 | 2018-08-06 | 2018-08-06 | 2018-08-06 | 2018-08-06 | 2018-08-06
2AI133CV99500-08011 | COCC:Installation of gratings/handrail/stair/ladder | [37 empty] | 2018-08-06 | 2018-08-06 | 2018-08-06 | 2018-08-06 | 2018-08-06 | 2018-08-06 | 2018-08-06 | 2018-08-06 | 2018-08-06
2AI133CV99500-08012 | COCC:Wall & Roof Cladding | [33 empty] | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05
2AI133CV99500-08141 | COCC : Shelter Erection for Car park | [33 empty] | 2018-04-12 | 2018-04-12 | 2018-04-12 | 2018-04-12 | 2018-04-12 | 2018-04-12 | 2018-04-12 | 2018-04-12 | 2018-04-12 | 2018-04-12 | 2018-04-12 | 2018-04-12 | 2018-04-12
2AI133EL01000 | EOF SS 50-SUBST-001 :Install Transformers | [31 empty] | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05
2AI133EL01000-08000 | EOF SS 50-SUBST-001 :Install Transformers | [31 empty] | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05
2AI133EL01000-08001 | EOF:Installation of Supports | [31 empty] | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23
2AI133EL01000-08005 | EOF:Installation of Transformer | [31 empty] | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05
2AI133EL01000-08010 | EOF:Allignment | [31 empty] | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05
2AI133EL01100 | EOF SS 50-SUBST-001 : Cable laying, glanding, termination & continuity check | [31 empty] | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05
2AI133EL01100-08000 | 621-SUBST-0001 : Cable laying | [31 empty] | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05
2AI133EL01100-08001 | EOF:Fabricate Tray Supports | [31 empty] | 2018-02-05: 2019-04-08
2AI133EL01100-08005 | 621-SUBST-0001 : Cable glanding, termination & continuity check | [33 empty] | 2018-05-14 | 2018-05-14 | 2018-05-14 | 2018-05-14 | 2018-05-14 | 2018-05-14 | 2018-05-14 | 2018-05-14 | 2018-05-14 | 2018-05-14 | 2018-05-14 | 2018-05-14 | 2018-05-14
2AI133EL01100-08006 | EOF: Install cable trays | [35 empty] | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07
2AI133EL01100-08011 | EOF: Installcable trays covers | [37 empty] | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03
2AI133EL01100-08015 | EOF: Cable Laying - LV | [31 empty] | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07
2AI133EL01100-08020 | EOF: Cable Glanding for LV cables | [33 empty] | 2018-05-14 | 2018-05-14 | 2018-05-14 | 2018-05-14 | 2018-05-14 | 2018-05-14 | 2018-05-14 | 2018-05-14 | 2018-05-14 | 2018-05-14 | 2018-05-14 | 2018-05-14 | 2018-05-14
2AI133EL01100-08025 | EOF: Continuity Checks & Terminations for LV cables | [33 empty] | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15
2AI133EL01100-08030 | EOF: Tagging for LV cables | [33 empty] | 2018-05-16 | 2018-05-16 | 2018-05-16 | 2018-05-16 | 2018-05-16 | 2018-05-16 | 2018-05-16 | 2018-05-16 | 2018-05-16 | 2018-05-16 | 2018-05-16 | 2018-05-16 | 2018-05-16
2AI133EL01100-08035 | EOF: Cable Laying - HV | [31 empty] | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05
2AI133EL01100-08040 | EOF: Cable Glanding for HV cables | [31 empty] | 2018-02-05: 2019-04-08
2AI133EL01100-08045 | EOF: Continuity Checks & Terminations for HV cables | [31 empty] | 2018-02-05: 2019-04-08
2AI133EL01100-08050 | EOF: Tagging for HV cables | [31 empty] | 2018-02-05: 2019-04-08
2AI133EL01200 | EOF:Earthing Work | [31 empty] | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05
2AI133EL01200-08000 | EOF:Earthing Work | [31 empty] | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05
2AI133EL01200-08001 | COCC: Earth rod Installation | [31 empty] | 2018-03-05: 2018-10-13; 2018-03-05: 2018-10-13; 2018-03-05: 2018-10-13; 2018-03-05: 2018-10-13; 2018-03-05: 2018-10-13; 2018-03-05: 2018-10-13; 2018-03-05: 2018-10-13
2AI133EL01200-08005 | COCC: Earth Cable Laying | [31 empty] | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05
2AI133EL01200-08010 | COCC: Cad welding | [33 empty] | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28
2AI133EL01200-08015 | COCC: Earth Bus Installation | [37 empty] | 2018-07-27 | 2018-07-27 | 2018-07-27 | 2018-07-27 | 2018-07-27 | 2018-07-27 | 2018-07-27 | 2018-07-27 | 2018-07-27
2AI133EL01200-08020 | COCC: Earth Boss Installation | [35 empty] | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21
2AI133EL01200-08025 | COCC: Earth cable Termination | [35 empty] | 2018-07-11 | 2018-07-11 | 2018-07-11 | 2018-07-11 | 2018-07-11 | 2018-07-11 | 2018-07-11 | 2018-07-11 | 2018-07-11 | 2018-07-11 | 2018-07-11
2AI133EL01200-08030 | COCC: Earth Pit Installation | [37 empty] | 2018-08-25 | 2018-08-25 | 2018-08-25 | 2018-08-25 | 2018-08-25 | 2018-08-25 | 2018-08-25 | 2018-08-25 | 2018-08-25
2AI133EL01300 | EOF SS 50-SUBST-001 : Install HV Switchboard with RCP, Power Factor & Bus Ducts | [29 empty] | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2017-11-24
2AI133EL01300-08000 | EOF SS 50-SUBST-001 : Install HV Switchboard with RCP, Power Factor & Bus Ducts | [29 empty] | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2017-11-24
2AI133EL01300-08001 | Foundation Checks/Preparation | [29 empty] | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2017-11-24
2AI133EL01300-08005 | Installation on Foundation | [29 empty] | 2017-11-25 | 2017-11-25 | 2017-11-25 | 2017-11-25 | 2017-11-25 | 2017-11-25 | 2017-11-25 | 2017-11-25 | 2017-11-25 | 2017-11-25 | 2017-11-25 | 2017-11-25 | 2017-11-25 | 2017-11-25 | 2017-11-25 | 2017-11-25 | 2017-11-25
2AI133EL01300-08010 | Preliminary Alignment & Grouting | [29 empty] | 2017-11-26 | 2017-11-26 | 2017-11-26 | 2017-11-26 | 2017-11-26 | 2017-11-26 | 2017-11-26 | 2017-11-26 | 2017-11-26 | 2017-11-26 | 2017-11-26 | 2017-11-26 | 2017-11-26 | 2017-11-26 | 2017-11-26 | 2017-11-26 | 2017-11-26
2AI133EL01300-08015 | Final Alignment | [29 empty] | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27
2AI133EL01400 | EOF SS 50-SUBST-001 : Install LV Switchboards with RCP, MCC & Bus Ducts(incl. Lighting/small power) | [33 empty] | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23
2AI133EL01400-08000 | EOF SS 50-SUBST-001 : Install LV Switchboards with RCP, MCC & Bus Ducts(incl. Lighting/small power) | [33 empty] | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23
2AI133EL01400-08025 | EOF:Installation of Supports | [33 empty] | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23
2AI133EL01400-08030 | EOF:Installation of LV Switchgear, RCP & MCC | [33 empty] | 2018-03-25 | 2018-03-25 | 2018-03-25 | 2018-03-25 | 2018-03-25 | 2018-03-25 | 2018-03-25 | 2018-03-25 | 2018-03-25 | 2018-03-25 | 2018-03-25 | 2018-03-25 | 2018-03-25
2AI133EL01400-08035 | EOF:Installation of Bus duct | [35 empty] | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26
2AI133EL01400-08040 | EOF:Allignment of LV Switchgear, RCP & MCC | [33 empty] | 2018-03-26 | 2018-03-26 | 2018-03-26 | 2018-03-26 | 2018-03-26 | 2018-03-26 | 2018-03-26 | 2018-03-26 | 2018-03-26 | 2018-03-26 | 2018-03-26 | 2018-03-26 | 2018-03-26
2AI133EL01400-08045 | EOF:Allignment of Bus duct | [37 empty] | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03
2AI133EL01500 | EOF SS 50-SUBST-001 : Install Distribution boards and Annunciator Panels | [33 empty] | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23
2AI133EL01500-08000 | EOF SS 50-SUBST-001 : Install Distribution boards and Annunciator Panels | [33 empty] | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23
2AI133EL01500-08001 | EOF:Installation of Supports | [33 empty] | 2018-03-24 | 2018-03-24 | 2018-03-24 | 2018-03-24 | 2018-03-24 | 2018-03-24 | 2018-03-24 | 2018-03-24 | 2018-03-24 | 2018-03-24 | 2018-03-24 | 2018-03-24 | 2018-03-24
2AI133EL01500-08005 | EOF:Installation of Distribution Board | [33 empty] | 2018-03-25 | 2018-03-25 | 2018-03-25 | 2018-03-25 | 2018-03-25 | 2018-03-25 | 2018-03-25 | 2018-03-25 | 2018-03-25 | 2018-03-25 | 2018-03-25 | 2018-03-25 | 2018-03-25
2AI133EL01500-08010 | EOF:Installation of Annunciator Panels | [33 empty] | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02
2AI133EL01500-08015 | EOF:Allignment | [33 empty] | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23
2AI133EL01600 | EOF SS 50-SUBST-001 : Install UPS with Battery bank and Isolator Switch | [33 empty] | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23
2AI133EL01600-08000 | EOF SS 50-SUBST-001 : Install UPS with Battery bank and Isolator Switch | [33 empty] | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23
2AI133EL01600-08001 | EOF:Installation of Supports | [33 empty] | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23
2AI133EL01600-08005 | EOF:Installation of UPS | [33 empty] | 2018-03-25 | 2018-03-25 | 2018-03-25 | 2018-03-25 | 2018-03-25 | 2018-03-25 | 2018-03-25 | 2018-03-25 | 2018-03-25 | 2018-03-25 | 2018-03-25 | 2018-03-25 | 2018-03-25
2AI133EL01600-08010 | EOF:Installation of battery Charger | [33 empty] | 2018-05-12 | 2018-05-12 | 2018-05-12 | 2018-05-12 | 2018-05-12 | 2018-05-12 | 2018-05-12 | 2018-05-12 | 2018-05-12 | 2018-05-12 | 2018-05-12 | 2018-05-12 | 2018-05-12
2AI133EL01600-08015 | EOF:Installation of Isolator Switch | [33 empty] | 2018-05-13 | 2018-05-13 | 2018-05-13 | 2018-05-13 | 2018-05-13 | 2018-05-13 | 2018-05-13 | 2018-05-13 | 2018-05-13 | 2018-05-13 | 2018-05-13 | 2018-05-13 | 2018-05-13
2AI133EL01600-08020 | EOF:Installation of Batteries | [33 empty] | 2018-05-14 | 2018-05-14 | 2018-05-14 | 2018-05-14 | 2018-05-14 | 2018-05-14 | 2018-05-14 | 2018-05-14 | 2018-05-14 | 2018-05-14 | 2018-05-14 | 2018-05-14 | 2018-05-14
2AI133EL01700 | EOF SS 52-SUBST-302 : Install E-SCADA | [33 empty] | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28
2AI133EL01700-08000 | EOF SS 52-SUBST-302 : Install E-SCADA | [33 empty] | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28
2AI133EL03000 | EOF SS 52-SUBST-301 : Install Transformers | [29 empty] | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23
2AI133EL03000-08000 | 621-SUBST-0301 : Install Transformers | [29 empty] | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23
2AI133EL03000-08001 | EOF:Installation of Supports | [29 empty] | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23
2AI133EL03000-08005 | EOF:Installation of Transformer | [29 empty] | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24
2AI133EL03000-08010 | EOF:Allignment | [29 empty] | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24
2AI133EL03100 | EOF SS 52-SUBST-301 : Cable laying, glanding/termination,checks (incl UG cable laying to Existing SS for Tie-in) | [29 empty] | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24
2AI133EL03100-08000 | 621-SUBST-0301 : Cable laying | [29 empty] | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24
2AI133EL03100-08005 | 621-SUBST-0301 : Cable glanding/termination,checks | [29 empty] | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06
2AI133EL03100-08006 | EOF: Install Tray support and Hangers | [29 empty] | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24
2AI133EL03100-08010 | EOF: Install cable trays | [29 empty] | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24
2AI133EL03100-08013 | EOF: Cable Laying - LV | [29 empty] | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24 | 2017-12-24
2AI133EL03100-08014 | EOF: Cable Laying - HV | [29 empty] | 2018-01-13 | 2018-01-13 | 2018-01-13 | 2018-01-13 | 2018-01-13 | 2018-01-13 | 2018-01-13 | 2018-01-13 | 2018-01-13 | 2018-01-13 | 2018-01-13 | 2018-01-13 | 2018-01-13 | 2018-01-13 | 2018-01-13 | 2018-01-13 | 2018-01-13
2AI133EL03100-08015 | EOF: Installcable trays covers | [29 empty] | 2018-01-13 | 2018-01-13 | 2018-01-13 | 2018-01-13 | 2018-01-13 | 2018-01-13 | 2018-01-13 | 2018-01-13 | 2018-01-13 | 2018-01-13 | 2018-01-13 | 2018-01-13 | 2018-01-13 | 2018-01-13 | 2018-01-13 | 2018-01-13 | 2018-01-13
2AI133EL03100-08020 | EOF: Cable Glanding for LV cables | [29 empty] | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06
2AI133EL03100-08025 | EOF: Continuity Checks & Terminations for LV cables | [29 empty] | 2018-01-08 | 2018-01-08 | 2018-01-08 | 2018-01-08 | 2018-01-08 | 2018-01-08 | 2018-01-08 | 2018-01-08 | 2018-01-08 | 2018-01-08 | 2018-01-08 | 2018-01-08 | 2018-01-08 | 2018-01-08 | 2018-01-08 | 2018-01-08 | 2018-01-08
2AI133EL03100-08030 | EOF: Tagging for LV cables | [29 empty] | 2018-01-08 | 2018-01-08 | 2018-01-08 | 2018-01-08 | 2018-01-08 | 2018-01-08 | 2018-01-08 | 2018-01-08 | 2018-01-08 | 2018-01-08 | 2018-01-08 | 2018-01-08 | 2018-01-08 | 2018-01-08 | 2018-01-08 | 2018-01-08 | 2018-01-08
2AI133EL03100-08040 | EOF: Cable Glanding for HV cables | [29 empty] | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21
2AI133EL03100-08045 | EOF: Continuity Checks & Terminations for HV cables | [29 empty] | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21
2AI133EL03100-08050 | EOF: Tagging for HV cables | [29 empty] | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21
2AI133EL03200 | EOF SS 52-SUBST-301 : Earthing Lightning Protection Works | [31 empty] | 2018-02-12 | 2018-02-12 | 2018-02-12 | 2018-02-12 | 2018-02-12 | 2018-02-12 | 2018-02-12 | 2018-02-12 | 2018-02-12 | 2018-02-12 | 2018-02-12 | 2018-02-12 | 2018-02-12 | 2018-02-12 | 2018-02-12
2AI133EL03200-08000 | EOF SS 52-SUBST-301 : Earthing Work | [31 empty] | 2018-02-12 | 2018-02-12 | 2018-02-12 | 2018-02-12 | 2018-02-12 | 2018-02-12 | 2018-02-12 | 2018-02-12 | 2018-02-12 | 2018-02-12 | 2018-02-12 | 2018-02-12 | 2018-02-12 | 2018-02-12 | 2018-02-12
2AI133EL03200-08001 | EOF SS 52-SUBST-301 : Earth rod Installation | [33 empty] | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28
2AI133EL03200-08005 | EOF SS 52-SUBST-301 : Earth Cable Laying | [31 empty] | 2018-02-12 | 2018-02-12 | 2018-02-12 | 2018-02-12 | 2018-02-12 | 2018-02-12 | 2018-02-12 | 2018-02-12 | 2018-02-12 | 2018-02-12 | 2018-02-12 | 2018-02-12 | 2018-02-12 | 2018-02-12 | 2018-02-12
2AI133EL03200-08010 | EOF SS 52-SUBST-301 : Cad welding | [33 empty] | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28
2AI133EL03200-08015 | EOF SS 52-SUBST-301 : Earth Bus Installation | [31 empty] | 2018-02-12 | 2018-02-12 | 2018-02-12 | 2018-02-12 | 2018-02-12 | 2018-02-12 | 2018-02-12 | 2018-02-12 | 2018-02-12 | 2018-02-12 | 2018-02-12 | 2018-02-12 | 2018-02-12 | 2018-02-12 | 2018-02-12
2AI133EL03200-08020 | EOF SS 52-SUBST-301 : Earth Boss Installation | [33 empty] | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28
2AI133EL03200-08025 | EOF SS 52-SUBST-301 : Earth cable Termination | [31 empty] | 2018-02-12 | 2018-02-12 | 2018-02-12 | 2018-02-12 | 2018-02-12 | 2018-02-12 | 2018-02-12 | 2018-02-12 | 2018-02-12 | 2018-02-12 | 2018-02-12 | 2018-02-12 | 2018-02-12 | 2018-02-12 | 2018-02-12
2AI133EL03200-08045 | EOF SS 52-SUBST-301 : Earth Pit Installation | [33 empty] | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28
2AI133EL03300 | EOF SS 52-SUBST-301 : Install HV Switchboard with RCP, Power Factor & Bus Ducts (Including Modification work) | [29 empty] | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28
2AI133EL03300-08000 | EOF SS 52-SUBST-301 : Install HV Switchboard with RCP, Power Factor & Bus Ducts (Including Modification work) | [29 empty] | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28
2AI133EL03300-08001 | EOF:Installation of Supports | [29 empty] | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28
2AI133EL03300-08005 | EOF:Installation of HV Switchgear, RCP | [29 empty] | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28
2AI133EL03300-08010 | EOF:Installation of Bus duct | [29 empty] | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28
2AI133EL03300-08015 | EOF:Allignment of HV Switchgear, RCP | [29 empty] | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28
2AI133EL03300-08020 | EOF:Allignment of Bus duct | [29 empty] | 2017-12-28: 2018-12-18; 2017-12-28: 2018-12-18; 2017-12-28: 2018-12-18; 2017-12-28: 2018-12-18; 2017-12-28: 2018-12-18
2AI133EL03300-08100 | MODIFICATION WORK IN EXISTING 11kV SWITCHGEAR AND IT'S ASSOCIATED WORKS IN MG-1 SUBSTATION | [31 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
2AI133EL03400 | EOF SS 52-SUBST-301 : Install LV Switchboards with RCP, MCC & Bus Ducts(incl. Lighting/small power,Modification work) | [29 empty] | 2017-12-14 | 2017-12-14 | 2017-12-14 | 2017-12-14 | 2017-12-14 | 2017-12-14 | 2017-12-14 | 2017-12-14 | 2017-12-14 | 2017-12-14 | 2017-12-14 | 2017-12-14 | 2017-12-14 | 2017-12-14 | 2017-12-14 | 2017-12-14 | 2017-12-14
2AI133EL03400-08000 | EOF SS 52-SUBST-301 : Install LV Switchboards with RCP, MCC & Bus Ducts(incl. Lighting/small power,Modification work) | [29 empty] | 2017-12-14 | 2017-12-14 | 2017-12-14 | 2017-12-14 | 2017-12-14 | 2017-12-14 | 2017-12-14 | 2017-12-14 | 2017-12-14 | 2017-12-14 | 2017-12-14 | 2017-12-14 | 2017-12-14 | 2017-12-14 | 2017-12-14 | 2017-12-14 | 2017-12-14
2AI133EL03400-08001 | EOF:Installation of Supports | [29 empty] | 2017-12-14 | 2017-12-14 | 2017-12-14 | 2017-12-14 | 2017-12-14 | 2017-12-14 | 2017-12-14 | 2017-12-14 | 2017-12-14 | 2017-12-14 | 2017-12-14 | 2017-12-14 | 2017-12-14 | 2017-12-14 | 2017-12-14 | 2017-12-14 | 2017-12-14
2AI133EL03400-08005 | EOF:Installation of LV Switchgear, RCP & MCC | [29 empty] | 2017-12-16 | 2017-12-16 | 2017-12-16 | 2017-12-16 | 2017-12-16 | 2017-12-16 | 2017-12-16 | 2017-12-16 | 2017-12-16 | 2017-12-16 | 2017-12-16 | 2017-12-16 | 2017-12-16 | 2017-12-16 | 2017-12-16 | 2017-12-16 | 2017-12-16
2AI133EL03400-08010 | EOF:Installation of Bus duct | [33 empty] | 2018-03-24 | 2018-03-24 | 2018-03-24 | 2018-03-24 | 2018-03-24 | 2018-03-24 | 2018-03-24 | 2018-03-24 | 2018-03-24 | 2018-03-24 | 2018-03-24 | 2018-03-24 | 2018-03-24
2AI133EL03400-08015 | EOF:Allignment of LV Switchgear, RCP & MCC | [29 empty] | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01
2AI133EL03400-08020 | EOF:Allignment of Bus duct | [33 empty] | 2018-03-24 | 2018-03-24 | 2018-03-24 | 2018-03-24 | 2018-03-24 | 2018-03-24 | 2018-03-24 | 2018-03-24 | 2018-03-24 | 2018-03-24 | 2018-03-24 | 2018-03-24 | 2018-03-24
2AI133EL03400-08030 | EOF:Installation of Lighting & Small Power Panels | [29 empty] | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01
2AI133EL03500 | EOF SS 52-SUBST-301 : Install Distribution boards and Annunciator Panels | [29 empty] | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01
2AI133EL03500-08000 | EOF SS 52-SUBST-301 : Install Distribution boards and Annunciator Panels | [29 empty] | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01
2AI133EL03500-08001 | EOF:Installation of Supports | [29 empty] | 2018-01-09 | 2018-01-09 | 2018-01-09 | 2018-01-09 | 2018-01-09 | 2018-01-09 | 2018-01-09 | 2018-01-09 | 2018-01-09 | 2018-01-09 | 2018-01-09 | 2018-01-09 | 2018-01-09 | 2018-01-09 | 2018-01-09 | 2018-01-09 | 2018-01-09
2AI133EL03500-08005 | EOF:Installation of Distribution Board | [29 empty] | 2018-01-10 | 2018-01-10 | 2018-01-10 | 2018-01-10 | 2018-01-10 | 2018-01-10 | 2018-01-10 | 2018-01-10 | 2018-01-10 | 2018-01-10 | 2018-01-10 | 2018-01-10 | 2018-01-10 | 2018-01-10 | 2018-01-10 | 2018-01-10 | 2018-01-10
2AI133EL03500-08010 | EOF:Installation of Annunciator Panels | [29 empty] | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01
2AI133EL03500-08015 | EOF:Allignment | [29 empty] | 2018-01-10 | 2018-01-10 | 2018-01-10 | 2018-01-10 | 2018-01-10 | 2018-01-10 | 2018-01-10 | 2018-01-10 | 2018-01-10 | 2018-01-10 | 2018-01-10 | 2018-01-10 | 2018-01-10 | 2018-01-10 | 2018-01-10 | 2018-01-10 | 2018-01-10
2AI133EL03600 | EOF SS 52-SUBST-301 : Install UPS with Battery bank and Isolator Switch | [29 empty] | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20
2AI133EL03600-08000 | EOF SS 52-SUBST-301 : Install UPS with Battery bank and Isolator Switch | [29 empty] | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20
2AI133EL03600-08001 | EOF:Installation of Supports | [29 empty] | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20
2AI133EL03600-08005 | EOF:Installation of UPS | [29 empty] | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22
2AI133EL03600-08010 | EOF:Installation of battery Charger | [29 empty] | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20
2AI133EL03600-08015 | EOF:Installation of Isolator Switch | [33 empty] | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28
2AI133EL03600-08020 | EOF:Installation of Batteries | [29 empty] | 2018-01-23 | 2018-01-23 | 2018-01-23 | 2018-01-23 | 2018-01-23 | 2018-01-23 | 2018-01-23 | 2018-01-23 | 2018-01-23 | 2018-01-23 | 2018-01-23 | 2018-01-23 | 2018-01-23 | 2018-01-23 | 2018-01-23 | 2018-01-23 | 2018-01-23
2AI133EL03700 | EOF SS 52-SUBST-301 : Install E-SCADA | [33 empty] | 2018-04-15 | 2018-04-15 | 2018-04-15 | 2018-04-15 | 2018-04-15 | 2018-04-15 | 2018-04-15 | 2018-04-15 | 2018-04-15 | 2018-04-15 | 2018-04-15 | 2018-04-15 | 2018-04-15
2AI133EL03700-08000 | EOF SS 52-SUBST-301 : Install E-SCADA | [33 empty] | 2018-04-15 | 2018-04-15 | 2018-04-15 | 2018-04-15 | 2018-04-15 | 2018-04-15 | 2018-04-15 | 2018-04-15 | 2018-04-15 | 2018-04-15 | 2018-04-15 | 2018-04-15 | 2018-04-15
2AI133EL05000 | EOF SS 52-SUBST-302 : Install Transformers | [31 empty] | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26
2AI133EL05000-08000 | 621-SUBST-0302 : Install Transformers | [31 empty] | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26
2AI133EL05000-08001 | EOF:Installation of Supports | [31 empty] | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26
2AI133EL05000-08005 | EOF:Installation of Transformer | [31 empty] | 2018-01-28 | 2018-01-28 | 2018-01-28 | 2018-01-28 | 2018-01-28 | 2018-01-28 | 2018-01-28 | 2018-01-28 | 2018-01-28 | 2018-01-28 | 2018-01-28 | 2018-01-28 | 2018-01-28 | 2018-01-28 | 2018-01-28
2AI133EL05000-08010 | EOF:Allignment | [31 empty] | 2018-02-08 | 2018-02-08 | 2018-02-08 | 2018-02-08 | 2018-02-08 | 2018-02-08 | 2018-02-08 | 2018-02-08 | 2018-02-08 | 2018-02-08 | 2018-02-08 | 2018-02-08 | 2018-02-08 | 2018-02-08 | 2018-02-08
2AI133EL05100 | EOF SS 52-SUBST-302 : Cable laying, glanding, termination & continuity check | [31 empty] | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05
2AI133EL05100-08000 | 621-SUBST-0302 : Cable laying | [31 empty] | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07
2AI133EL05100-08005 | 621-SUBST-0302 : Cable glanding, termination & continuity check | [31 empty] | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05
2AI133EL05100-08015 | EOF: Install Tray support and Hangers | [31 empty] | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07
2AI133EL05100-08020 | EOF: Install cable trays | [37 empty] | 2018-08-08 | 2018-08-08 | 2018-08-08 | 2018-08-08 | 2018-08-08 | 2018-08-08 | 2018-08-08 | 2018-08-08 | 2018-08-08
2AI133EL05100-08025 | EOF: Installcable trays covers | [37 empty] | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03
2AI133EL05100-08029 | EOF: Cable Laying - LV | [33 empty] | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02
2AI133EL05100-08030 | EOF: Cable Glanding for LV cables | [31 empty] | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05
2AI133EL05100-08035 | EOF: Continuity Checks & Terminations for LV cables | [35 empty] | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02
2AI133EL05100-08040 | EOF: Tagging for LV cables | [35 empty] | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02
2AI133EL05100-08045 | EOF: Cable Laying - HV | [35 empty] | 2018-07-02: 2019-04-08
2AI133EL05100-08050 | EOF: Cable Glanding for HV cables | [39 empty] | 2018-10-08 | 2018-10-08 | 2018-10-08 | 2018-10-08 | 2018-10-08 | 2018-10-08 | 2018-10-08
2AI133EL05100-08055 | EOF: Continuity Checks & Terminations for HV cables | [39 empty] | 2018-10-08 | 2018-10-08 | 2018-10-08 | 2018-10-08 | 2018-10-08 | 2018-10-08 | 2018-10-08
2AI133EL05100-08060 | EOF: Tagging for HV cables | [39 empty] | 2018-10-08 | 2018-10-08 | 2018-10-08 | 2018-10-08 | 2018-10-08 | 2018-10-08 | 2018-10-08
2AI133EL05200 | EOF SS 52-SUBST-302 : Earthing Lightning Protection Works | [33 empty] | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07
2AI133EL05200-08000 | EOF:Earthing Work | [33 empty] | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07
2AI133EL05200-08001 | COCC: Earth rod Installation | [33 empty] | 2018-05-07: 2019-04-08
2AI133EL05200-08005 | COCC: Earth Cable Laying | [33 empty] | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07
2AI133EL05200-08010 | COCC: Cad welding | [33 empty] | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15
2AI133EL05200-08015 | COCC: Earth Bus Installation | [33 empty] | 2018-05-15: 2019-01-07; 2018-05-15: 2019-01-07; 2018-05-15: 2019-01-07; 2018-05-15: 2019-01-07; 2018-05-15: 2019-01-07
2AI133EL05200-08020 | COCC: Earth Boss Installation | [33 empty] | 2018-05-15: 2019-04-08
2AI133EL05200-08025 | COCC: Earth cable Termination | [37 empty] | 2018-08-06 | 2018-08-06 | 2018-08-06 | 2018-08-06 | 2018-08-06 | 2018-08-06 | 2018-08-06 | 2018-08-06 | 2018-08-06
2AI133EL05200-08045 | COCC: Earth Pit Installation | [37 empty] | 2018-08-06: 2019-04-08
2AI133EL05300 | EOF SS 52-SUBST-302 : Install HV Switchboard with RCP, Capacitor & Bus Ducts | [27 empty] | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20
2AI133EL05300-08000 | 621-SUBST-0302 : Install HV Switchboard with RCP, Power Factor & Bus Ducts | [27 empty] | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20
2AI133EL05300-08001 | EOF:Installation of Supports | [29 empty] | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2017-11-24
2AI133EL05300-08005 | EOF:Installation of HV Switchgear, RCP | [29 empty] | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2017-11-24 | 2017-11-24
2AI133EL05300-08010 | EOF:Installation of Bus duct | [27 empty] | 2017-11-22 | 2017-11-22 | 2017-11-22 | 2017-11-22 | 2017-11-22 | 2017-11-22 | 2017-11-22 | 2017-11-22 | 2017-11-22 | 2017-11-22 | 2017-11-22 | 2017-11-22 | 2017-11-22 | 2017-11-22 | 2017-11-22 | 2017-11-22 | 2017-11-22 | 2017-11-22 | 2017-11-22
2AI133EL05300-08015 | EOF:Allignment of HV Switchgear, RCP | [27 empty] | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20
2AI133EL05300-08020 | EOF:Allignment of Bus duct | [29 empty] | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05
2AI133EL05400 | EOF SS 52-SUBST-302 : Install LV Switchboards with RCP, MCC & Bus Ducts(incl. Lighting/small power) | [29 empty] | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06
2AI133EL05400-08000 | 621-SUBST-0302 : Install LV Switchboards with RCP, MCC & Bus Ducts(incl. Lighting/small power) | [29 empty] | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06
2AI133EL05400-08001 | EOF:Installation of Supports | [29 empty] | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06
2AI133EL05400-08005 | EOF:Installation of LV Switchgear, RCP & MCC | [29 empty] | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06
2AI133EL05400-08010 | EOF:Installation of Bus duct | [33 empty] | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28
2AI133EL05400-08015 | EOF:Allignment of LV Switchgear, RCP & MCC | [29 empty] | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06
2AI133EL05400-08020 | EOF:Allignment of Bus duct | [35 empty] | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02
2AI133EL05500 | EOF SS 52-SUBST-302 : Install Distribution boards and Annunciator Panels | [29 empty] | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01
2AI133EL05500-08000 | 621-SUBST-0302 : Install Distribution boards and Annunciator Panels | [29 empty] | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01
2AI133EL05500-08001 | EOF:Installation of Supports | [29 empty] | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16
2AI133EL05500-08005 | EOF:Installation of Distribution Board | [29 empty] | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16
2AI133EL05500-08010 | EOF:Installation of Annunciator Panels | [29 empty] | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01
2AI133EL05500-08015 | EOF:Allignment | [29 empty] | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16
2AI133EL05600 | EOF SS 52-SUBST-302 : Install UPS, Battery Charger with Battery bank and Isolator Switch | [33 empty] | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23
2AI133EL05600-08000 | 621-SUBST-0302 : Install UPS with Battery bank and Isolator Switch | [33 empty] | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23
2AI133EL05600-08001 | EOF:Installation of Supports | [33 empty] | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28
2AI133EL05600-08005 | EOF:Installation of UPS | [33 empty] | 2018-03-29 | 2018-03-29 | 2018-03-29 | 2018-03-29 | 2018-03-29 | 2018-03-29 | 2018-03-29 | 2018-03-29 | 2018-03-29 | 2018-03-29 | 2018-03-29 | 2018-03-29 | 2018-03-29
2AI133EL05600-08006 | EOF:Installation of battery Charger | [33 empty] | 2018-03-30 | 2018-03-30 | 2018-03-30 | 2018-03-30 | 2018-03-30 | 2018-03-30 | 2018-03-30 | 2018-03-30 | 2018-03-30 | 2018-03-30 | 2018-03-30 | 2018-03-30 | 2018-03-30
2AI133EL05600-08010 | EOF:Installation of Isolator Switch | [33 empty] | 2018-03-30 | 2018-03-30 | 2018-03-30 | 2018-03-30 | 2018-03-30 | 2018-03-30 | 2018-03-30 | 2018-03-30 | 2018-03-30 | 2018-03-30 | 2018-03-30 | 2018-03-30 | 2018-03-30
2AI133EL05600-08015 | EOF:Installation of Batteries | [33 empty] | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23 | 2018-03-23
2AI133EL05700 | EOF SS 52-SUBST-302 : Install E-SCADA | [33 empty] | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02
2AI133EL05700-08000 | EOF SS 52-SUBST-302 : Install E-SCADA | [33 empty] | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02
2AI133EL07000 | EOF SS 52-SUBST-303 : Install Transformers | [27 empty] | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02
2AI133EL07000-08000 | EOF SS 52-SUBST-303 : Install Transformers | [27 empty] | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02
2AI133EL07000-08001 | EOF:Installation of Supports | [27 empty] | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02
2AI133EL07000-08005 | EOF:Installation of Transformer | [27 empty] | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12
2AI133EL07000-08010 | EOF:Allignment | [27 empty] | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12 | 2017-10-12
2AI133EL07100 | EOF SS 52-SUBST-303 : Cable laying, glanding, termination & continuity check | [29 empty] | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01
2AI133EL07100-08000 | 621-SUBST-0303 : Cable laying | [29 empty] | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01
2AI133EL07100-08001 | EOF:Fabricate Tray Supports | [29 empty] | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01
2AI133EL07100-08003 | EOF: Install Tray support and Hangers | [29 empty] | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01
2AI133EL07100-08005 | 621-SUBST-0303 : Cable glanding, termination & continuity check | [29 empty] | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01
2AI133EL07100-08006 | EOF: Install cable trays | [29 empty] | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01
2AI133EL07100-08089 | EOF: Cable Laying - LV | [29 empty] | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01
2AI133EL07100-08090 | EOF: Cable Glanding for LV cables | [29 empty] | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01
2AI133EL07100-08095 | EOF: Continuity Checks & Terminations for LV cables | [29 empty] | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01
2AI133EL07100-08100 | EOF: Tagging for LV cables | [29 empty] | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01
2AI133EL07100-08109 | EOF: Cable Laying - HV | [29 empty] | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22
2AI133EL07100-08110 | EOF: Cable Glanding for HV cables | [29 empty] | 2018-01-22: 2019-04-08
2AI133EL07100-08111 | EOF: Installcable trays covers | [29 empty] | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22
2AI133EL07100-08115 | EOF: Continuity Checks & Terminations for HV cables | [29 empty] | 2018-01-22: 2019-04-08
2AI133EL07100-08120 | EOF: Tagging for HV cables | [29 empty] | 2018-01-22: 2019-04-08
2AI133EL07200 | EOF SS 52-SUBST-303 : Earthing Lightning Protection Works | [29 empty] | 2018-01-14 | 2018-01-14 | 2018-01-14 | 2018-01-14 | 2018-01-14 | 2018-01-14 | 2018-01-14 | 2018-01-14 | 2018-01-14 | 2018-01-14 | 2018-01-14 | 2018-01-14 | 2018-01-14 | 2018-01-14 | 2018-01-14 | 2018-01-14 | 2018-01-14
2AI133EL07200-08000 | EOF:Earthing Work | [29 empty] | 2018-01-14 | 2018-01-14 | 2018-01-14 | 2018-01-14 | 2018-01-14 | 2018-01-14 | 2018-01-14 | 2018-01-14 | 2018-01-14 | 2018-01-14 | 2018-01-14 | 2018-01-14 | 2018-01-14 | 2018-01-14 | 2018-01-14 | 2018-01-14 | 2018-01-14
2AI133EL07200-08001 | COCC: Earth rod Installation | [29 empty] | 2018-01-14 | 2018-01-14 | 2018-01-14 | 2018-01-14 | 2018-01-14 | 2018-01-14 | 2018-01-14 | 2018-01-14 | 2018-01-14 | 2018-01-14 | 2018-01-14 | 2018-01-14 | 2018-01-14 | 2018-01-14 | 2018-01-14 | 2018-01-14 | 2018-01-14
2AI133EL07200-08005 | COCC: Earth Cable Laying | [29 empty] | 2018-01-15 | 2018-01-15 | 2018-01-15 | 2018-01-15 | 2018-01-15 | 2018-01-15 | 2018-01-15 | 2018-01-15 | 2018-01-15 | 2018-01-15 | 2018-01-15 | 2018-01-15 | 2018-01-15 | 2018-01-15 | 2018-01-15 | 2018-01-15 | 2018-01-15
2AI133EL07200-08010 | COCC: Cad welding | [29 empty] | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16
2AI133EL07200-08015 | COCC: Earth Bus Installation | [29 empty] | 2018-01-23 | 2018-01-23 | 2018-01-23 | 2018-01-23 | 2018-01-23 | 2018-01-23 | 2018-01-23 | 2018-01-23 | 2018-01-23 | 2018-01-23 | 2018-01-23 | 2018-01-23 | 2018-01-23 | 2018-01-23 | 2018-01-23 | 2018-01-23 | 2018-01-23
2AI133EL07200-08020 | COCC: Earth Boss Installation | [29 empty] | 2018-01-23: 2019-04-08
2AI133EL07200-08025 | COCC: Earth cable Termination | [31 empty] | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05 | 2018-03-05
2AI133EL07200-08030 | COCC: Earth Pit Installation | [31 empty] | 2018-02-04 | 2018-02-04 | 2018-02-04 | 2018-02-04 | 2018-02-04 | 2018-02-04 | 2018-02-04 | 2018-02-04 | 2018-02-04 | 2018-02-04 | 2018-02-04 | 2018-02-04 | 2018-02-04 | 2018-02-04 | 2018-02-04
2AI133EL07300 | EOF SS 52-SUBST-303 : Install HV Switchboard with RCP, Power Factor & Bus Ducts | [29 empty] | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04
2AI133EL07300-08000 | EOF SS 52-SUBST-303 : Install HV Switchboard with RCP, Power Factor & Bus Ducts | [29 empty] | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04
2AI133EL07300-08001 | Foundation Checks/Preparation | [29 empty] | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04
2AI133EL07300-08005 | Installation on Foundation | [29 empty] | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04
2AI133EL07300-08010 | Preliminary Alignment & Grouting | [29 empty] | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04
2AI133EL07300-08015 | Final Alignment | [31 empty] | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05
2AI133EL07400 | EOF SS 52-SUBST-303 : Install LV Switchboards with RCP, MCC & Bus Ducts(incl. Lighting/small power) | [29 empty] | 2017-12-02 | 2017-12-02 | 2017-12-02 | 2017-12-02 | 2017-12-02 | 2017-12-02 | 2017-12-02 | 2017-12-02 | 2017-12-02 | 2017-12-02 | 2017-12-02 | 2017-12-02 | 2017-12-02 | 2017-12-02 | 2017-12-02 | 2017-12-02 | 2017-12-02
2AI133EL07400-08000 | EOF SS 52-SUBST-303 : Install LV Switchboards with RCP, MCC & Bus Ducts(incl. Lighting/small power) | [29 empty] | 2017-12-02 | 2017-12-02 | 2017-12-02 | 2017-12-02 | 2017-12-02 | 2017-12-02 | 2017-12-02 | 2017-12-02 | 2017-12-02 | 2017-12-02 | 2017-12-02 | 2017-12-02 | 2017-12-02 | 2017-12-02 | 2017-12-02 | 2017-12-02 | 2017-12-02
2AI133EL07400-08001 | EOF:Installation of Supports | [29 empty] | 2017-12-02 | 2017-12-02 | 2017-12-02 | 2017-12-02 | 2017-12-02 | 2017-12-02 | 2017-12-02 | 2017-12-02 | 2017-12-02 | 2017-12-02 | 2017-12-02 | 2017-12-02 | 2017-12-02 | 2017-12-02 | 2017-12-02 | 2017-12-02 | 2017-12-02
2AI133EL07400-08005 | EOF:Installation of LV Switchgear, MCC | [29 empty] | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05
2AI133EL07400-08010 | EOF:Allignment of LV Switchgear, MCC | [29 empty] | 2017-12-08 | 2017-12-08 | 2017-12-08 | 2017-12-08 | 2017-12-08 | 2017-12-08 | 2017-12-08 | 2017-12-08 | 2017-12-08 | 2017-12-08 | 2017-12-08 | 2017-12-08 | 2017-12-08 | 2017-12-08 | 2017-12-08 | 2017-12-08 | 2017-12-08
2AI133EL07400-08015 | EOF:Installation of Bus duct | [29 empty] | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01
2AI133EL07400-08025 | EOF:Allignment of Bus duct | [29 empty] | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01
2AI133EL07500 | EOF SS 52-SUBST-303 : Install Distribution boards and Annunciator Panels | [29 empty] | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01
2AI133EL07500-08000 | EOF SS 52-SUBST-303 : Install Distribution boards and Annunciator Panels | [29 empty] | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01
2AI133EL07500-08001 | EOF:Installation of Supports | [29 empty] | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16 | 2018-01-16
2AI133EL07500-08005 | EOF:Installation of Distribution Board | [29 empty] | 2018-01-17 | 2018-01-17 | 2018-01-17 | 2018-01-17 | 2018-01-17 | 2018-01-17 | 2018-01-17 | 2018-01-17 | 2018-01-17 | 2018-01-17 | 2018-01-17 | 2018-01-17 | 2018-01-17 | 2018-01-17 | 2018-01-17 | 2018-01-17 | 2018-01-17
2AI133EL07500-08010 | EOF:Installation of Annunciator Panels | [29 empty] | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01
2AI133EL07500-08015 | EOF:Allignment of Distribution Board | [29 empty] | 2018-01-17 | 2018-01-17 | 2018-01-17 | 2018-01-17 | 2018-01-17 | 2018-01-17 | 2018-01-17 | 2018-01-17 | 2018-01-17 | 2018-01-17 | 2018-01-17 | 2018-01-17 | 2018-01-17 | 2018-01-17 | 2018-01-17 | 2018-01-17 | 2018-01-17
2AI133EL07500-08025 | EOF:Allignment of Annunciator Panels | [29 empty] | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01
2AI133EL07600 | EOF SS 52-SUBST-303 : Install UPS with Battery bank and Isolator Switch | [29 empty] | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20
2AI133EL07600-08000 | EOF SS 52-SUBST-303 : Install UPS with Battery bank and Isolator Switch | [29 empty] | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20
2AI133EL07600-08001 | EOF:Installation of Supports | [29 empty] | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20
2AI133EL07600-08005 | EOF:Installation of UPS | [29 empty] | 2018-01-23 | 2018-01-23 | 2018-01-23 | 2018-01-23 | 2018-01-23 | 2018-01-23 | 2018-01-23 | 2018-01-23 | 2018-01-23 | 2018-01-23 | 2018-01-23 | 2018-01-23 | 2018-01-23 | 2018-01-23 | 2018-01-23 | 2018-01-23 | 2018-01-23
2AI133EL07600-08010 | EOF:Installation of Isolator Switch | [29 empty] | 2018-01-23: 2019-04-08
2AI133EL07600-08015 | EOF:Installation of Batteries | [29 empty] | 2018-01-23 | 2018-01-23 | 2018-01-23 | 2018-01-23 | 2018-01-23 | 2018-01-23 | 2018-01-23 | 2018-01-23 | 2018-01-23 | 2018-01-23 | 2018-01-23 | 2018-01-23 | 2018-01-23 | 2018-01-23 | 2018-01-23 | 2018-01-23 | 2018-01-23
2AI133EL07700 | EOF SS 52-SUBST-303 : Install E-SCADA | [33 empty] | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24
2AI133EL07700-08000 | EOF:Installation of E-SCADA Cabinet/Panel/Cabling | [33 empty] | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24
2AI133EL11000 | EOF EG Building 50-R-002 : Install Emergency Generator | [37 empty] | 2018-08-04 | 2018-08-04 | 2018-08-04 | 2018-08-04 | 2018-08-04 | 2018-08-04 | 2018-08-04 | 2018-08-04 | 2018-08-04
2AI133EL11000-08000 | EOF EG Building 50-R-002 : Install Emergency Generator | [37 empty] | 2018-08-04 | 2018-08-04 | 2018-08-04 | 2018-08-04 | 2018-08-04 | 2018-08-04 | 2018-08-04 | 2018-08-04 | 2018-08-04
2AI133EL11000-08001 | EOF:Installation of Generators | [37 empty] | 2018-08-04 | 2018-08-04 | 2018-08-04 | 2018-08-04 | 2018-08-04 | 2018-08-04 | 2018-08-04 | 2018-08-04 | 2018-08-04
2AI133EL11000-08005 | EOF:Allignment | [37 empty] | 2018-08-10 | 2018-08-10 | 2018-08-10 | 2018-08-10 | 2018-08-10 | 2018-08-10 | 2018-08-10 | 2018-08-10 | 2018-08-10
2AI133EL11100 | EOF EG Building 50-R-002 : Cable laying, glanding, termination & continuity check | [39 empty] | 2018-09-29 | 2018-09-29 | 2018-09-29 | 2018-09-29 | 2018-09-29 | 2018-09-29 | 2018-09-29
2AI133EL11100-08000 | EOF EG Building 50-R-002 : Cable laying | [39 empty] | 2018-09-29 | 2018-09-29 | 2018-09-29 | 2018-09-29 | 2018-09-29 | 2018-09-29 | 2018-09-29
2AI133EL11100-08005 | EOF EG Building 50-R-002 : Cable glanding, termination & continuity check | [39 empty] | 2018-09-29 | 2018-09-29 | 2018-09-29 | 2018-09-29 | 2018-09-29 | 2018-09-29 | 2018-09-29
2AI133EL11100-08006 | EOF:Fabricate Tray Supports | [39 empty] | 2018-09-29 | 2018-09-29 | 2018-09-29 | 2018-09-29 | 2018-09-29 | 2018-09-29 | 2018-09-29
2AI133EL11100-08010 | EOF: Install cable trays | [39 empty] | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30
2AI133EL11100-08014 | EOF: Cable Laying - LV | [39 empty] | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30
2AI133EL11100-08015 | EOF: Installcable trays covers | [37 empty] | 2018-08-10: 2019-04-08
2AI133EL11100-08020 | EOF: Cable Glanding for LV cables | [39 empty] | 2018-09-29 | 2018-09-29 | 2018-09-29 | 2018-09-29 | 2018-09-29 | 2018-09-29 | 2018-09-29
2AI133EL11100-08025 | EOF: Continuity Checks & Terminations for LV cables | [39 empty] | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30
2AI133EL11100-08030 | EOF: Tagging for LV cables | [39 empty] | 2018-09-29 | 2018-09-29 | 2018-09-29 | 2018-09-29 | 2018-09-29 | 2018-09-29 | 2018-09-29
2AI133EL11200 | EOF EG Building 50-R-002 : Install Distribution boards, Lighting & small power | [37 empty] | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22
2AI133EL11200-08000 | EOF EG Building 50-R-002 : Install Distribution boards, Lighting & small power | [37 empty] | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22
2AI133EL11200-08001 | EOF:Installation of Supports | [37 empty] | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22
2AI133EL11200-08005 | EOF:Installation of Distribution Board | [37 empty] | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23
2AI133EL11200-08010 | EOF:Allignment | [37 empty] | 2018-09-26 | 2018-09-26 | 2018-09-26 | 2018-09-26 | 2018-09-26 | 2018-09-26 | 2018-09-26 | 2018-09-26 | 2018-09-26
2AI133EL21000 | EOF EG Building 52-R-301 : Install Emergency Generator | [35 empty] | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23
2AI133EL21000-08000 | EOF EG Building 52-R-301 : Install Emergency Generator | [35 empty] | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23
2AI133EL21000-08001 | EOF:Installation of Generators | [35 empty] | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23
2AI133EL21000-08005 | EOF:Allignment | [35 empty] | 2018-06-25 | 2018-06-25 | 2018-06-25 | 2018-06-25 | 2018-06-25 | 2018-06-25 | 2018-06-25 | 2018-06-25 | 2018-06-25 | 2018-06-25 | 2018-06-25
2AI133EL21100 | EOF EG Building 52-R-301 : Install Distribution boards, Lighting & small power | [35 empty] | 2018-06-25: 2019-04-08
2AI133EL21100-08000 | EOF EG Building 52-R-301 : Install Distribution boards | [35 empty] | 2018-06-25: 2019-04-08
2AI133EL21100-08001 | EOF:Installation of Supports | [35 empty] | 2018-06-25: 2019-04-08
2AI133EL21100-08005 | EOF:Installation of Distribution Board | [35 empty] | 2018-06-25: 2019-04-08
2AI133EL21100-08010 | EOF:Allignment | [35 empty] | 2018-06-25: 2019-04-08
2AI133EL21200 | EOF EG Building 52-R-301 : Cable laying, glanding, termination & continuity check | [33 empty] | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02
2AI133EL21200-08000 | EOF EG Building 52-R-301 : Cable laying | [33 empty] | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02
2AI133EL21200-08001 | EOF:Fabricate Tray Supports | [33 empty] | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02
2AI133EL21200-08005 | EOF EG Building 52-R-301 : Cable glanding, termination & continuity check | [35 empty] | 2018-07-06 | 2018-07-06 | 2018-07-06 | 2018-07-06 | 2018-07-06 | 2018-07-06 | 2018-07-06 | 2018-07-06 | 2018-07-06 | 2018-07-06 | 2018-07-06
2AI133EL21200-08006 | EOF: Install Tray support and Hangers | [33 empty] | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02
2AI133EL21200-08010 | EOF: Install cable trays | [35 empty] | 2018-07-05 | 2018-07-05 | 2018-07-05 | 2018-07-05 | 2018-07-05 | 2018-07-05 | 2018-07-05 | 2018-07-05 | 2018-07-05 | 2018-07-05 | 2018-07-05
2AI133EL21200-08014 | EOF: Cable Laying | [35 empty] | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02
2AI133EL21200-08015 | EOF: Installcable trays covers | [35 empty] | 2018-07-05 | 2018-07-05 | 2018-07-05 | 2018-07-05 | 2018-07-05 | 2018-07-05 | 2018-07-05 | 2018-07-05 | 2018-07-05 | 2018-07-05 | 2018-07-05
2AI133EL21200-08020 | EOF: Cable Glanding | [35 empty] | 2018-07-06 | 2018-07-06 | 2018-07-06 | 2018-07-06 | 2018-07-06 | 2018-07-06 | 2018-07-06 | 2018-07-06 | 2018-07-06 | 2018-07-06 | 2018-07-06
2AI133EL21200-08025 | EOF: Continuity Checks & Terminations | [35 empty] | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07 | 2018-07-07
2AI133EL21200-08030 | EOF: Tagging | [35 empty] | 2018-07-08 | 2018-07-08 | 2018-07-08 | 2018-07-08 | 2018-07-08 | 2018-07-08 | 2018-07-08 | 2018-07-08 | 2018-07-08 | 2018-07-08 | 2018-07-08
2AI133EL31000 | EOF EG Building 52-R-302 : Install Emergency Generator | [35 empty] | 2018-07-06 | 2018-07-06 | 2018-07-06 | 2018-07-06 | 2018-07-06 | 2018-07-06 | 2018-07-06 | 2018-07-06 | 2018-07-06 | 2018-07-06 | 2018-07-06
2AI133EL31000-08000 | EOF:Installation of Generators | [35 empty] | 2018-07-06 | 2018-07-06 | 2018-07-06 | 2018-07-06 | 2018-07-06 | 2018-07-06 | 2018-07-06 | 2018-07-06 | 2018-07-06 | 2018-07-06 | 2018-07-06
2AI133EL31000-08001 | EOF:Installation of Generators | [35 empty] | 2018-07-06 | 2018-07-06 | 2018-07-06 | 2018-07-06 | 2018-07-06 | 2018-07-06 | 2018-07-06 | 2018-07-06 | 2018-07-06 | 2018-07-06 | 2018-07-06
2AI133EL31000-08005 | EOF:Allignment | [35 empty] | 2018-07-09 | 2018-07-09 | 2018-07-09 | 2018-07-09 | 2018-07-09 | 2018-07-09 | 2018-07-09 | 2018-07-09 | 2018-07-09 | 2018-07-09 | 2018-07-09
2AI133EL31100 | EOF EG Building 52-R-302 : Install Distribution boards, Lighting & small power | [37 empty] | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22
2AI133EL31100-08000 | EOF EG Building 52-R-302 : Install Distribution boards, Lighting & small power | [37 empty] | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22
2AI133EL31100-08001 | EOF:Installation of Supports | [37 empty] | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22
2AI133EL31100-08005 | EOF:Installation of Distribution Board | [37 empty] | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23
2AI133EL31100-08010 | EOF:Allignment | [37 empty] | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-24
2AI133EL31200 | EOF EG Building 52-R-302 : Cable laying, glanding, termination & continuity check | [33 empty] | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24
2AI133EL31200-08000 | EOF EG Building 52-R-302 :Cable laying | [33 empty] | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24
2AI133EL31200-08001 | Cable Drum Checks & Transport to Site | [33 empty] | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24
2AI133EL31200-08004 | Cable Pulling | [33 empty] | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24
2AI133EL31200-08005 | EOF EG Building 52-R-302 : Cableglanding, termination & continuity check | [33 empty] | 2018-04-24: 2018-10-08; 2018-04-24: 2018-10-08; 2018-04-24: 2018-10-08; 2018-04-24: 2018-10-08; 2018-04-24: 2018-10-08; 2018-04-24: 2018-10-08; 2018-04-24: 2018-10-08
2AI133EL31200-08006 | Cable Dressing & Fastening | [33 empty] | 2018-04-25 | 2018-04-25 | 2018-04-25 | 2018-04-25 | 2018-04-25 | 2018-04-25 | 2018-04-25 | 2018-04-25 | 2018-04-25 | 2018-04-25 | 2018-04-25 | 2018-04-25 | 2018-04-25
2AI133EL31200-08009 | Cable Marking | [33 empty] | 2018-04-26 | 2018-04-26 | 2018-04-26 | 2018-04-26 | 2018-04-26 | 2018-04-26 | 2018-04-26 | 2018-04-26 | 2018-04-26 | 2018-04-26 | 2018-04-26 | 2018-04-26 | 2018-04-26
2AI133EL31200-08015 | EOF: Cable Glanding | [33 empty] | 2018-04-26: 2018-10-08; 2018-04-26: 2018-10-08; 2018-04-26: 2018-10-08; 2018-04-26: 2018-10-08; 2018-04-26: 2018-10-08; 2018-04-26: 2018-10-08; 2018-04-26: 2018-10-08
2AI133EL31200-08020 | EOF: Continuity Checks & Terminations | [33 empty] | 2018-04-26: 2018-10-08; 2018-04-26: 2018-10-08; 2018-04-26: 2018-10-08; 2018-04-26: 2018-10-08; 2018-04-26: 2018-10-08; 2018-04-26: 2018-10-08; 2018-04-26: 2018-10-08
2AI133EL31200-08025 | EOF: Tagging | [33 empty] | 2018-04-26: 2018-10-08; 2018-04-26: 2018-10-08; 2018-04-26: 2018-10-08; 2018-04-26: 2018-10-08; 2018-04-26: 2018-10-08; 2018-04-26: 2018-10-08; 2018-04-26: 2018-10-08
2AI133EL41000 | EOF EG Building 52-R-303 : Install Emergency Generator | [35 empty] | 2018-06-20 | 2018-06-20 | 2018-06-20 | 2018-06-20 | 2018-06-20 | 2018-06-20 | 2018-06-20 | 2018-06-20 | 2018-06-20 | 2018-06-20 | 2018-06-20
2AI133EL41000-08000 | EOF EG Building 52-R-303 : Install Emergency Generator | [37 empty] | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22
2AI133EL41000-08001 | EOF:Installation of Generators | [35 empty] | 2018-06-20 | 2018-06-20 | 2018-06-20 | 2018-06-20 | 2018-06-20 | 2018-06-20 | 2018-06-20 | 2018-06-20 | 2018-06-20 | 2018-06-20 | 2018-06-20
2AI133EL41000-08005 | EOF:Allignment | [35 empty] | 2018-06-21 | 2018-06-21 | 2018-06-21 | 2018-06-21 | 2018-06-21 | 2018-06-21 | 2018-06-21 | 2018-06-21 | 2018-06-21 | 2018-06-21 | 2018-06-21
2AI133EL41100 | EOF EG Building 52-R-303 : Cable laying, glanding, termination & continuity check | [39 empty] | 2018-10-08 | 2018-10-08 | 2018-10-08 | 2018-10-08 | 2018-10-08 | 2018-10-08 | 2018-10-08
2AI133EL41100-08000 | EOF EG Building 52-R-303 : Cable laying | [39 empty] | 2018-10-08 | 2018-10-08 | 2018-10-08 | 2018-10-08 | 2018-10-08 | 2018-10-08 | 2018-10-08
2AI133EL41100-08001 | EOF:Fabricate Tray Supports | [35 empty] | 2018-06-21: 2019-04-08
2AI133EL41100-08004 | EOF: Install Tray support and Hangers | [35 empty] | 2018-06-21: 2019-04-08
2AI133EL41100-08005 | EOF EG Building 52-R-303 : Cableglanding, termination & continuity check | [39 empty] | 2018-10-13 | 2018-10-13 | 2018-10-13 | 2018-10-13 | 2018-10-13 | 2018-10-13 | 2018-10-13
2AI133EL41100-08006 | EOF: Install cable trays | [39 empty] | 2018-10-08 | 2018-10-08 | 2018-10-08 | 2018-10-08 | 2018-10-08 | 2018-10-08 | 2018-10-08
2AI133EL41100-08009 | EOF: Cable Laying | [39 empty] | 2018-10-08 | 2018-10-08 | 2018-10-08 | 2018-10-08 | 2018-10-08 | 2018-10-08 | 2018-10-08
2AI133EL41100-08010 | EOF: Installcable trays covers | [39 empty] | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05
2AI133EL41100-08015 | EOF: Cable Glanding | [39 empty] | 2018-10-13 | 2018-10-13 | 2018-10-13 | 2018-10-13 | 2018-10-13 | 2018-10-13 | 2018-10-13
2AI133EL41100-08020 | EOF: Continuity Checks & Terminations | [39 empty] | 2018-10-14 | 2018-10-14 | 2018-10-14 | 2018-10-14 | 2018-10-14 | 2018-10-14 | 2018-10-14
2AI133EL41100-08025 | EOF: Tagging | [39 empty] | 2018-10-15 | 2018-10-15 | 2018-10-15 | 2018-10-15 | 2018-10-15 | 2018-10-15 | 2018-10-15
2AI133EL41200 | EOF EG Building 52-R-303 : Install Distribution boards, Lighting & small power | [39 empty] | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05
2AI133EL41200-08000 | EOF EG Building 52-R-303 : Install Distribution boards, Lighting & small power | [39 empty] | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05
2AI133EL41200-08001 | EOF:Installation of Supports | [39 empty] | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05
2AI133EL41200-08005 | EOF:Installation of Distribution Board | [39 empty] | 2018-11-07 | 2018-11-07 | 2018-11-07 | 2018-11-07 | 2018-11-07 | 2018-11-07 | 2018-11-07
2AI133EL41200-08010 | EOF:Allignment | [39 empty] | 2018-11-09 | 2018-11-09 | 2018-11-09 | 2018-11-09 | 2018-11-09 | 2018-11-09 | 2018-11-09
2AI133HS01150 | EOF SS: Installation of Fire fighting & Safety Equipments
2AI133HS01150-08000 | EOF SS: Installation of Fire fighting & Safety Equipments
2AI133HS01150-08001 | Fabrication & Installation of Support Structures
2AI133HS01150-08005 | Installation of Instruments on Support Structures
2AI133HS01150-08010 | Alignment/Levelling and grouting
2AI133HS01160 | EOF SS: Installation of Safety Sign Boards
2AI133HS01160-08000 | EOF SS: Installation of Safety Sign Boards
2AI133HS01160-08001 | Fabrication & Installation of Support Structures
2AI133HS01160-08005 | Installation of Instruments on Support Structures
2AI133HS01160-08015 | Alignment/Levelling and grouting
2AI133IC01000 | EOF SS 50-SUBST-001 : Cable laying, glanding, termination & continuity check | [33 empty] | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05
2AI133IC01000-08000 | EOF SS 50-SUBST-001 : Cable laying, glanding, termination & continuity check | [33 empty] | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05
2AI133IC01000-08001 | EOF:Cable Tray Installation | [33 empty] | 2018-05-12 | 2018-05-12 | 2018-05-12 | 2018-05-12 | 2018-05-12 | 2018-05-12 | 2018-05-12 | 2018-05-12 | 2018-05-12 | 2018-05-12 | 2018-05-12 | 2018-05-12 | 2018-05-12
2AI133IC01000-08005 | EOF SS 50-SUBST-001 : Cable laying, glanding, termination & continuity check | [33 empty] | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05
2AI133IC01000-08006 | EOF:Cable laying | [33 empty] | 2018-05-14 | 2018-05-14 | 2018-05-14 | 2018-05-14 | 2018-05-14 | 2018-05-14 | 2018-05-14 | 2018-05-14 | 2018-05-14 | 2018-05-14 | 2018-05-14 | 2018-05-14 | 2018-05-14
2AI133IC01000-08010 | EOF:Glanding & termination | [33 empty] | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05
2AI133IC01000-08015 | EOF:Continuity check | [33 empty] | 2018-05-05: 2018-10-13; 2018-05-05: 2018-10-13; 2018-05-05: 2018-10-13; 2018-05-05: 2018-10-13; 2018-05-05: 2018-10-13; 2018-05-05: 2018-10-13; 2018-05-05: 2018-10-13
2AI133IC01100 | EOF SS 50-SUBST-001 : Install - IRP Cabinets | [33 empty] | 2018-04-28 | 2018-04-28 | 2018-04-28 | 2018-04-28 | 2018-04-28 | 2018-04-28 | 2018-04-28 | 2018-04-28 | 2018-04-28 | 2018-04-28 | 2018-04-28 | 2018-04-28 | 2018-04-28
2AI133IC01100-08000 | EOF SS 52-SUBST-302 : Install - IRP Cabinets | [33 empty] | 2018-04-28 | 2018-04-28 | 2018-04-28 | 2018-04-28 | 2018-04-28 | 2018-04-28 | 2018-04-28 | 2018-04-28 | 2018-04-28 | 2018-04-28 | 2018-04-28 | 2018-04-28 | 2018-04-28
2AI133IC01200 | EOF SS 50-SUBST-001 : Install - ICSS related equipments | [33 empty] | 2018-04-28: 2019-04-08
2AI133IC01200-08000 | EOF SS 52-SUBST-302 : Install - ICSS related equipments | [33 empty] | 2018-04-28: 2019-04-08
2AI133IC03000 | EOF SS 52-SUBST-301 : Cable laying, glanding, termination & continuity check | [31 empty] | 2018-03-17 | 2018-03-17 | 2018-03-17 | 2018-03-17 | 2018-03-17 | 2018-03-17 | 2018-03-17 | 2018-03-17 | 2018-03-17 | 2018-03-17 | 2018-03-17 | 2018-03-17 | 2018-03-17 | 2018-03-17 | 2018-03-17
2AI133IC03000-08000 | 621-SUBST-301 : Cable laying | [31 empty] | 2018-03-17 | 2018-03-17 | 2018-03-17 | 2018-03-17 | 2018-03-17 | 2018-03-17 | 2018-03-17 | 2018-03-17 | 2018-03-17 | 2018-03-17 | 2018-03-17 | 2018-03-17 | 2018-03-17 | 2018-03-17 | 2018-03-17
2AI133IC03000-08001 | EOF:Cable Tray Installation | [31 empty] | 2018-03-17 | 2018-03-17 | 2018-03-17 | 2018-03-17 | 2018-03-17 | 2018-03-17 | 2018-03-17 | 2018-03-17 | 2018-03-17 | 2018-03-17 | 2018-03-17 | 2018-03-17 | 2018-03-17 | 2018-03-17 | 2018-03-17
2AI133IC03000-08005 | 621-SUBST-301 : Glanding, termination & continuity check | [31 empty] | 2018-03-22 | 2018-03-22 | 2018-03-22 | 2018-03-22 | 2018-03-22 | 2018-03-22 | 2018-03-22 | 2018-03-22 | 2018-03-22 | 2018-03-22 | 2018-03-22 | 2018-03-22 | 2018-03-22 | 2018-03-22 | 2018-03-22
2AI133IC03000-08006 | EOF:Cable laying | [33 empty] | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28
2AI133IC03000-08010 | EOF:Glanding & termination | [31 empty] | 2018-03-22 | 2018-03-22 | 2018-03-22 | 2018-03-22 | 2018-03-22 | 2018-03-22 | 2018-03-22 | 2018-03-22 | 2018-03-22 | 2018-03-22 | 2018-03-22 | 2018-03-22 | 2018-03-22 | 2018-03-22 | 2018-03-22
2AI133IC03000-08015 | EOF:Continuity check | [31 empty] | 2018-03-22 | 2018-03-22 | 2018-03-22 | 2018-03-22 | 2018-03-22 | 2018-03-22 | 2018-03-22 | 2018-03-22 | 2018-03-22 | 2018-03-22 | 2018-03-22 | 2018-03-22 | 2018-03-22 | 2018-03-22 | 2018-03-22
2AI133IC03100 | EOF SS 52-SUBST-301 : Install - IRP Cabinets | [31 empty] | 2018-03-22: 2019-04-08
2AI133IC03100-08000 | EOF SS 52-SUBST-301 : Install - IRP Cabinets | [31 empty] | 2018-03-22: 2019-04-08
2AI133IC03200 | EOF SS 52-SUBST-301 : Install - ICSS related equipments | [31 empty] | 2018-03-22: 2019-04-08
2AI133IC03200-08000 | EOF SS 52-SUBST-301 : Install - ICSS related equipments & Other Instrument/Equipment | [31 empty] | 2018-03-22: 2019-04-08
2AI133IC05000 | EOF SS 52-SUBST-302 : Cable laying, glanding, termination & continuity check | [31 empty] | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05
2AI133IC05000-08000 | 621-SUBST-0302 : Cable laying | [31 empty] | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05
2AI133IC05000-08001 | EOF:Cable Tray Installation | [31 empty] | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05 | 2018-02-05
2AI133IC05000-08003 | EOF:Cable laying | [33 empty] | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07
2AI133IC05000-08005 | 621-SUBST-0302 : Cable glanding, termination & continuity check | [33 empty] | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28
2AI133IC05000-08006 | EOF:Glanding | [33 empty] | 2018-05-10 | 2018-05-10 | 2018-05-10 | 2018-05-10 | 2018-05-10 | 2018-05-10 | 2018-05-10 | 2018-05-10 | 2018-05-10 | 2018-05-10 | 2018-05-10 | 2018-05-10 | 2018-05-10
2AI133IC05000-08010 | EOF:Continuity check & termination | [33 empty] | 2018-05-20 | 2018-05-20 | 2018-05-20 | 2018-05-20 | 2018-05-20 | 2018-05-20 | 2018-05-20 | 2018-05-20 | 2018-05-20 | 2018-05-20 | 2018-05-20 | 2018-05-20 | 2018-05-20
2AI133IC05000-08020 | EOF:Tagging | [33 empty] | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28
2AI133IC05100 | EOF SS 52-SUBST-302 : Install - IRP Cabinets | [31 empty] | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18
2AI133IC05100-08000 | EOF SS 52-SUBST-302 : Install - IRP Cabinets | [31 empty] | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18
2AI133IC05200 | EOF SS 52-SUBST-302 : Install - ICSS related equipments | [33 empty] | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28
2AI133IC05200-08000 | EOF SS 52-SUBST-302 : Install - ICSS related equipments | [33 empty] | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28
2AI133IC07000 | EOF SS 52-SUBST-303 : Cable laying, glanding, termination & continuity check | [33 empty] | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02
2AI133IC07000-08000 | 621-SUBST-0303 : Cable laying | [33 empty] | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02
2AI133IC07000-08001 | EOF: Install Tray support and Hangers | [33 empty] | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02
2AI133IC07000-08005 | 621-SUBST-0303 : Cable glanding, termination & continuity check | [33 empty] | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02
2AI133IC07000-08006 | EOF: Install cable trays | [33 empty] | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02
2AI133IC07000-08010 | EOF:Cable laying | [33 empty] | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02
2AI133IC07000-08015 | EOF:Glanding & termination | [33 empty] | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02
2AI133IC07000-08020 | EOF:Continuity check | [33 empty] | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02
2AI133IC07100 | EOF SS 52-SUBST-303 : Install - IRP Cabinets
2AI133IC07100-08000 | EOF SS 52-SUBST-303 : Install - IRP Cabinets
2AI133IC07200 | EOF SS 52-SUBST-303 : Install - ICSS related equipments | [37 empty] | 2018-09-08 | 2018-09-08 | 2018-09-08 | 2018-09-08 | 2018-09-08 | 2018-09-08 | 2018-09-08 | 2018-09-08 | 2018-09-08
2AI133IC07200-08000 | EOF SS 52-SUBST-303 : Install - ICSS related equipments | [37 empty] | 2018-09-08 | 2018-09-08 | 2018-09-08 | 2018-09-08 | 2018-09-08 | 2018-09-08 | 2018-09-08 | 2018-09-08 | 2018-09-08
2AI133IC11000 | EOF EG Building 50-R-002 : Instrument Cable laying, glanding, termination & continuity checks | [39 empty] | 2018-09-29 | 2018-09-29 | 2018-09-29 | 2018-09-29 | 2018-09-29 | 2018-09-29 | 2018-09-29
2AI133IC11000-08000 | EOF EG Building 50-R-002 : Instrument Cable laying | [39 empty] | 2018-09-29 | 2018-09-29 | 2018-09-29 | 2018-09-29 | 2018-09-29 | 2018-09-29 | 2018-09-29
2AI133IC11000-08001 | EOF:Cable laying | [39 empty] | 2018-09-29 | 2018-09-29 | 2018-09-29 | 2018-09-29 | 2018-09-29 | 2018-09-29 | 2018-09-29
2AI133IC11000-08005 | EOF:Cable laying | [39 empty] | 2018-09-29 | 2018-09-29 | 2018-09-29 | 2018-09-29 | 2018-09-29 | 2018-09-29 | 2018-09-29
2AI133IC11000-08006 | EOF:Glanding & termination | [39 empty] | 2018-10-13 | 2018-10-13 | 2018-10-13 | 2018-10-13 | 2018-10-13 | 2018-10-13 | 2018-10-13
2AI133IC11000-08010 | EOF:Continuity check | [39 empty] | 2018-10-13 | 2018-10-13 | 2018-10-13 | 2018-10-13 | 2018-10-13 | 2018-10-13 | 2018-10-13
2AI133IC21000 | EOF EG Building 52-R-301 : Instrument Cable laying, glanding, termination & continuity checks | [39 empty] | 2018-09-29 | 2018-09-29 | 2018-09-29 | 2018-09-29 | 2018-09-29 | 2018-09-29 | 2018-09-29
2AI133IC21000-08000 | EOF EG Building 52-R-301 : Instrument Cable laying | [39 empty] | 2018-09-29 | 2018-09-29 | 2018-09-29 | 2018-09-29 | 2018-09-29 | 2018-09-29 | 2018-09-29
2AI133IC21000-08001 | EOF:Cable laying | [39 empty] | 2018-09-29 | 2018-09-29 | 2018-09-29 | 2018-09-29 | 2018-09-29 | 2018-09-29 | 2018-09-29
2AI133IC21000-08005 | EOF EG Building 52-R-301 : Instrument Cable glanding, termination & continuity checks | [39 empty] | 2018-09-29 | 2018-09-29 | 2018-09-29 | 2018-09-29 | 2018-09-29 | 2018-09-29 | 2018-09-29
2AI133IC21000-08006 | EOF:Glanding & termination | [37 empty] | 2018-09-08: 2019-04-08
2AI133IC21000-08010 | EOF:Continuity check | [37 empty] | 2018-09-08: 2019-04-08
2AI133IC31000 | EOF EG Building 52-R-302 : Instrument Cable laying, glanding, termination & continuity checks | [39 empty] | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05
2AI133IC31000-08000 | EOF EG Building 52-R-302 : Instrument Cable laying | [39 empty] | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05
2AI133IC31000-08001 | EOF:Cable laying | [39 empty] | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05
2AI133IC31000-08005 | EOF EG Building 52-R-302 : Instrument Cable glanding, termination & continuity checks | [39 empty] | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05
2AI133IC31000-08006 | EOF:Glanding & termination | [39 empty] | 2018-11-07 | 2018-11-07 | 2018-11-07 | 2018-11-07 | 2018-11-07 | 2018-11-07 | 2018-11-07
2AI133IC31000-08010 | EOF:Continuity check | [39 empty] | 2018-11-07 | 2018-11-07 | 2018-11-07 | 2018-11-07 | 2018-11-07 | 2018-11-07 | 2018-11-07
2AI133IC41000 | EOF EG Building 52-R-303 : Instrument Cable laying, glanding, termination & continuity checks | [39 empty] | 2018-11-08 | 2018-11-08 | 2018-11-08 | 2018-11-08 | 2018-11-08 | 2018-11-08 | 2018-11-08
2AI133IC41000-08000 | EOF EG Building 52-R-303 : Instrument Cable laying | [39 empty] | 2018-11-08 | 2018-11-08 | 2018-11-08 | 2018-11-08 | 2018-11-08 | 2018-11-08 | 2018-11-08
2AI133IC41000-08001 | EOF:Cable laying | [39 empty] | 2018-11-08 | 2018-11-08 | 2018-11-08 | 2018-11-08 | 2018-11-08 | 2018-11-08 | 2018-11-08
2AI133IC41000-08005 | EOF EG Building 52-R-303 : Instrument Cable glanding, termination & continuity checks | [39 empty] | 2018-11-08 | 2018-11-08 | 2018-11-08 | 2018-11-08 | 2018-11-08 | 2018-11-08 | 2018-11-08
2AI133IC41000-08006 | EOF:Glanding & termination | [39 empty] | 2018-11-10 | 2018-11-10 | 2018-11-10 | 2018-11-10 | 2018-11-10 | 2018-11-10 | 2018-11-10
2AI133IC41000-08010 | EOF:Continuity check | [39 empty] | 2018-11-12 | 2018-11-12 | 2018-11-12 | 2018-11-12 | 2018-11-12 | 2018-11-12 | 2018-11-12
2AI133MS11000 | EOF EG Building 50-R-002 : Diesel Day Tank Installation | [35 empty] | 2018-06-17 | 2018-06-17 | 2018-06-17 | 2018-06-17 | 2018-06-17 | 2018-06-17 | 2018-06-17 | 2018-06-17 | 2018-06-17 | 2018-06-17 | 2018-06-17
2AI133MS11000-08000 | EOF EG Building 50-R-002 : Diesel Day Tank Foundation | [35 empty] | 2018-06-17 | 2018-06-17 | 2018-06-17 | 2018-06-17 | 2018-06-17 | 2018-06-17 | 2018-06-17 | 2018-06-17 | 2018-06-17 | 2018-06-17 | 2018-06-17
2AI133MS11000-08001 | EOF:Installation of Equipment | [35 empty] | 2018-06-17 | 2018-06-17 | 2018-06-17 | 2018-06-17 | 2018-06-17 | 2018-06-17 | 2018-06-17 | 2018-06-17 | 2018-06-17 | 2018-06-17 | 2018-06-17
2AI133MS11000-08005 | EOF:Preliminary Allignment & Grouting of Equipment | [35 empty] | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23
2AI133MS11000-08010 | EOF:Final Allignment & Grouting of Equipment | [35 empty] | 2018-06-23: 2018-12-03; 2018-06-23: 2018-12-03; 2018-06-23: 2018-12-03; 2018-06-23: 2018-12-03; 2018-06-23: 2018-12-03
2AI133MS21000 | EOF EG Building 52-R-301 : Diesel Day Tank Installation | [29 empty] | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28
2AI133MS21000-08000 | EOF EG Building 52-R-301 : Diesel Day Tank Installation | [29 empty] | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28
2AI133MS21000-08001 | EOF:Installation of Equipment | [29 empty] | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28 | 2017-12-28
2AI133MS21000-08010 | EOF:Preliminary Allignment & Grouting of Equipment | [31 empty] | 2018-02-08 | 2018-02-08 | 2018-02-08 | 2018-02-08 | 2018-02-08 | 2018-02-08 | 2018-02-08 | 2018-02-08 | 2018-02-08 | 2018-02-08 | 2018-02-08 | 2018-02-08 | 2018-02-08 | 2018-02-08 | 2018-02-08
2AI133MS21000-08020 | EOF:Final Allignment & Grouting of Equipment | [31 empty] | 2018-02-10 | 2018-02-10 | 2018-02-10 | 2018-02-10 | 2018-02-10 | 2018-02-10 | 2018-02-10 | 2018-02-10 | 2018-02-10 | 2018-02-10 | 2018-02-10 | 2018-02-10 | 2018-02-10 | 2018-02-10 | 2018-02-10
2AI133MS31000 | EOF EG Building 52-R-302 : Diesel Day Tank Installation | [31 empty] | 2018-01-31 | 2018-01-31 | 2018-01-31 | 2018-01-31 | 2018-01-31 | 2018-01-31 | 2018-01-31 | 2018-01-31 | 2018-01-31 | 2018-01-31 | 2018-01-31 | 2018-01-31 | 2018-01-31 | 2018-01-31 | 2018-01-31
2AI133MS31000-08000 | EOF EG Building 52-R-302 : Diesel Day Tank Installation | [31 empty] | 2018-01-31 | 2018-01-31 | 2018-01-31 | 2018-01-31 | 2018-01-31 | 2018-01-31 | 2018-01-31 | 2018-01-31 | 2018-01-31 | 2018-01-31 | 2018-01-31 | 2018-01-31 | 2018-01-31 | 2018-01-31 | 2018-01-31
2AI133MS31000-08001 | EOF:Installation of Diesel Day Tank Installation | [31 empty] | 2018-01-31 | 2018-01-31 | 2018-01-31 | 2018-01-31 | 2018-01-31 | 2018-01-31 | 2018-01-31 | 2018-01-31 | 2018-01-31 | 2018-01-31 | 2018-01-31 | 2018-01-31 | 2018-01-31 | 2018-01-31 | 2018-01-31
2AI133MS31000-08005 | EOF:Preliminary Allignment & Grouting of Equipment | [37 empty] | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03 | 2018-09-03
2AI133MS31000-08010 | EOF:Final Allignment & Grouting of Equipment | [37 empty] | 2018-09-03: 2019-03-04; 2018-09-03: 2019-03-04; 2018-09-03: 2019-03-04
2AI133MS41000 | EOF EG Building 52-R-303 : Diesel Day Tank Installation | [29 empty] | 2017-12-22 | 2017-12-22 | 2017-12-22 | 2017-12-22 | 2017-12-22 | 2017-12-22 | 2017-12-22 | 2017-12-22 | 2017-12-22 | 2017-12-22 | 2017-12-22 | 2017-12-22 | 2017-12-22 | 2017-12-22 | 2017-12-22 | 2017-12-22 | 2017-12-22
2AI133MS41000-08000 | EOF EG Building 52-R-303 : Diesel Day Tank Installation | [37 empty] | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22
2AI133MS41000-08001 | EOF:Installation of Diesel Day Tank Installation | [29 empty] | 2017-12-22 | 2017-12-22 | 2017-12-22 | 2017-12-22 | 2017-12-22 | 2017-12-22 | 2017-12-22 | 2017-12-22 | 2017-12-22 | 2017-12-22 | 2017-12-22 | 2017-12-22 | 2017-12-22 | 2017-12-22 | 2017-12-22 | 2017-12-22 | 2017-12-22
2AI133MS41000-08005 | EOF:Preliminary Allignment & Grouting of Equipment | [29 empty] | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22
2AI133MS41000-08010 | EOF:Final Allignment & Grouting of Equipment | [33 empty] | 2018-05-04 | 2018-05-04 | 2018-05-04 | 2018-05-04 | 2018-05-04 | 2018-05-04 | 2018-05-04 | 2018-05-04 | 2018-05-04 | 2018-05-04 | 2018-05-04 | 2018-05-04 | 2018-05-04
2AI133PC01000 | EOF:Fire Water Tie-In / Ring main & hydrants /Deluge System
2AI133PC01000-08000 | EOF:Fire Water Tie-In / Ring main & hydrants /Deluge System
2AI133PC01100 | EOF:Foam System Package / Overhead Water tank / Foam Concentrate tank / drains / Diesel Tanks/ Foam Pumps
2AI133PC01100-08000 | EOF:Foam System Package / Overhead Water tank / Foam Concentrate tank / drains / Diesel Tanks/ Foam Pumps
2AI133PC01200 | EOF:Filling / mixing manifold / Auto sampling Package / Pig receiver /Drain
2AI133PC01200-08000 | EOF:Filling / mixing manifold / Auto sampling Package / Pig receiver /Drain
2AI133PC01300 | EOF:Loading Mixing manifold / Trim Pumps / Auto sampling Package / drain Sump & Pump
2AI133PC01300-08000 | EOF:Loading Mixing manifold / Trim Pumps / Auto sampling Package / drain Sump & Pump
2AI133PC01400 | EOF:Floating Tanks / Mixers / Oily Water collection System / Drain / Oily Water transfer Pump
2AI133PC01400-08000 | EOF:Floating Tanks / Mixers / Oily Water collection System / Drain / Oily Water transfer Pump
2AI133PC01500 | EOF/COCC: Liquidation of pre-comm punch points ('B' items) | [33 empty] | 2018-05-04: 2019-04-08
2AI133PC01500-08000 | EOF/COCC: Liquidation of pre-comm punch points ('B' items) | [33 empty] | 2018-05-04: 2019-04-08
2AI133TE01000 | COCC: SS 50-SUBST-001 : FO & Telephone Cabling, Telecom System install, Cable Terminations & continuity checks | [29 empty] | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01
2AI133TE01000-08000 | 621-SUBST-0301 : FO & Telephone Cabling Works | [29 empty] | 2018-01-01: 2019-04-08
2AI133TE01000-08001 | Cable Drum Checks & Transport to Site | [29 empty] | 2018-01-01: 2019-04-08
2AI133TE01000-08005 | 621-SUBST-0301 : Telephone System Installation | [29 empty] | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01
2AI133TE01000-08006 | Cable Pulling | [29 empty] | 2018-01-01: 2019-04-08
2AI133TE01000-08010 | 621-SUBST-0301 : Cable Terminations | [29 empty] | 2018-01-01: 2019-04-08
2AI133TE01000-08011 | Cable Dressing & Fastening | [29 empty] | 2018-01-01: 2019-04-08
2AI133TE01000-08015 | COCC: Installation - Telecom System | [29 empty] | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01
2AI133TE01000-08021 | Cable Marking | [29 empty] | 2018-01-01: 2019-04-08
2AI133TE01000-08025 | COCC: Cable Terminations & continuity checks | [29 empty] | 2018-01-01: 2019-04-08
2AI133TE03000 | EOF SS 52-SUBST-301 : FO & Telephone Cabling, Telecom System install, Cable Terminations & continuity checks | [29 empty] | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01
2AI133TE03000-08000 | 621-SUBST-301 : FO & Telephone Cable Laying | [35 empty] | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04
2AI133TE03000-08005 | 621-SUBST-301 : Installation - Telecom System | [29 empty] | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01
2AI133TE03000-08010 | 621-SUBST-301 : Cable Terminations | [29 empty] | 2018-01-01: 2019-04-08
2AI133TE05000 | EOF SS 52-SUBST-302 : FO & Telephone Cabling, Telecom System install, Cable Terminations & continuity checks | [33 empty] | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02
2AI133TE05000-08000 | EOF:FO & Telephone Cable Laying | [33 empty] | 2018-04-02: 2019-04-08
2AI133TE05000-08005 | EOF:Installation - Telecom System | [33 empty] | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02
2AI133TE05000-08010 | EOF:Cable Terminations & continuity checks | [33 empty] | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21
2AI133TE07000 | EOF SS 52-SUBST-303 : FO & Telephone Cabling, Telecom System install, Cable Terminations & continuity checks | [29 empty] | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01
2AI133TE07000-08000 | EOF:FO & Telephone Cable Laying | [29 empty] | 2018-01-01: 2018-11-05; 2018-01-01: 2018-11-05; 2018-01-01: 2018-11-05; 2018-01-01: 2018-11-05; 2018-01-01: 2018-11-05; 2018-01-01: 2018-11-05; 2018-01-01: 2018-11-05
2AI133TE07000-08005 | EOF:Installation - Telecom System | [29 empty] | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01
2AI133TE07000-08010 | EOF:Cable Terminations & continuity checks | [33 empty] | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02
2AI133TE11000 | EOF EG Building 50-R-002 : FO & Telephone Cabling, Telecom System install, Cable Terminations & continuity checks | [29 empty] | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01
2AI133TE11000-08000 | EOF:FO & Telephone Cable Laying | [29 empty] | 2018-01-01: 2019-04-08
2AI133TE11000-08005 | EOF:Installation - Telecom System | [29 empty] | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01
2AI133TE11000-08010 | EOF:Cable Terminations & continuity checks | [29 empty] | 2018-01-01: 2019-04-08
2AI133TE21000 | EOF EG Building 52-R-301 : FO & Telephone Cabling, Telecom System install, Cable Terminations & continuity checks | [29 empty] | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03
2AI133TE21000-08000 | EOF:FO & Telephone Cable Laying | [33 empty] | 2018-04-22 | 2018-04-22 | 2018-04-22 | 2018-04-22 | 2018-04-22 | 2018-04-22 | 2018-04-22 | 2018-04-22 | 2018-04-22 | 2018-04-22 | 2018-04-22 | 2018-04-22 | 2018-04-22
2AI133TE21000-08005 | EOF EG Building 52-R-301 : Telecom system install, Cable Terminations & continuity checks | [29 empty] | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03 | 2018-01-03
2AI133TE31000 | EOF EG Building 52-R-302 : FO & Telephone Cabling, Telecom System install, Cable Terminations & continuity checks | [29 empty] | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01
2AI133TE31000-08000 | EOF:FO & Telephone Cable Laying | [29 empty] | 2018-01-01: 2019-04-08
2AI133TE31000-08005 | EOF:Installation - Telecom System | [29 empty] | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01
2AI133TE31000-08010 | EOF:Cable Terminations & continuity checks | [29 empty] | 2018-01-01: 2019-04-08
2AI133TE41000 | EOF EG Building 52-R-303 : FO & Telephone Cabling, Telecom System install, Cable Terminations & continuity checks | [29 empty] | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01
2AI133TE41000-08000 | EOF:FO & Telephone Cable Laying | [29 empty] | 2018-01-01: 2019-04-08
2AI133TE41000-08005 | EOF:Installation - Telecom System | [29 empty] | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01
2AI133TE41000-08010 | EOF:Cable Terminations & continuity checks | [29 empty] | 2018-01-01: 2019-04-08
2AI141CV01000 | COCC : Site preparation | [5 empty] | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18
2AI141CV01000-08001 | COCC :Verification of Survey for existing grade Level & Marking | [5 empty] | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18
2AI141CV01000-08005 | COCC :Excavation Notification | [5 empty] | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18
2AI141CV01000-08015 | COCC : Site clearance & Stripping & disposal of Contaminated material(If any) | [9 empty] | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25
2AI141CV01000-08020 | COCC : Grading, Cutting & Stockpiling | [21 empty] | 2017-05-11 | 2017-05-11 | 2017-05-11 | 2017-05-11 | 2017-05-11 | 2017-05-11 | 2017-05-11 | 2017-05-11 | 2017-05-11 | 2017-05-11 | 2017-05-11 | 2017-05-11 | 2017-05-11 | 2017-05-11 | 2017-05-11 | 2017-05-11 | 2017-05-11 | 2017-05-11 | 2017-05-11 | 2017-05-11 | 2017-05-11 | 2017-05-11 | 2017-05-11 | 2017-05-11 | 2017-05-11
2AI141CV01000-08025 | COCC : Grading, Filling & Compaction | [13 empty] | 2016-09-01 | 2016-09-01 | 2016-09-01 | 2016-09-01 | 2016-09-01 | 2016-09-01 | 2016-09-01 | 2016-09-01 | 2016-09-01 | 2016-09-01 | 2016-09-01 | 2016-09-01 | 2016-09-01 | 2016-09-01 | 2016-09-01 | 2016-09-01 | 2016-09-01 | 2016-09-01 | 2016-09-01 | 2016-09-01 | 2016-09-01 | 2016-09-01 | 2016-09-01 | 2016-09-01 | 2016-09-01 | 2016-09-01 | 2016-09-01 | 2016-09-01 | 2016-09-01 | 2016-09-01 | 2016-09-01 | 2016-09-01 | 2016-09-01
2AI141CV01000-08030 | COCC : Disposal of Surplus Material | [9 empty] | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25
2AI141CV01000-08100 | COCC : Site preparation (Including COCC Buliding,Carparking & Subsatation) | [5 empty] | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18 | 2016-01-18
2AI141CV01100 | COCC : Trench & other Civil Works (including construction scope for migration readiness) | [5 empty] | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12
2AI141CV01100-08000 | COCC : Trench (Manual Excavation) | [5 empty] | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12
2AI141CV01100-08005 | COCC : EIT Duct banks | [21 empty] | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29
2AI141CV01100-08010 | COCC : Pipe Supports | [27 empty] | 2017-11-09 | 2017-11-09 | 2017-11-09 | 2017-11-09 | 2017-11-09 | 2017-11-09 | 2017-11-09 | 2017-11-09 | 2017-11-09 | 2017-11-09 | 2017-11-09 | 2017-11-09 | 2017-11-09 | 2017-11-09 | 2017-11-09 | 2017-11-09 | 2017-11-09 | 2017-11-09 | 2017-11-09
2AI141CV01100-08015 | COCC : EIT Supports | [15 empty] | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18
2AI141CV01100-08020 | COCC : Fence Works | [15 empty] | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18
2AI141CV01100-08021 | COCC : Prepare Mould/Formwork, Rebar & Insert embedments (at Pre-cast Yard) | [27 empty] | 2017-11-09 | 2017-11-09 | 2017-11-09 | 2017-11-09 | 2017-11-09 | 2017-11-09 | 2017-11-09 | 2017-11-09 | 2017-11-09 | 2017-11-09 | 2017-11-09 | 2017-11-09 | 2017-11-09 | 2017-11-09 | 2017-11-09 | 2017-11-09 | 2017-11-09 | 2017-11-09 | 2017-11-09
2AI141CV01100-08025 | COCC: Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material | [5 empty] | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12 | 2016-01-12
2AI141CV01100-08030 | COCC : Concrete Pouring | [27 empty] | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20
2AI141CV01100-08035 | COCC:Bedding (incl. clean sand layer) | [5 empty] | 2016-01-13 | 2016-01-13 | 2016-01-13 | 2016-01-13 | 2016-01-13 | 2016-01-13 | 2016-01-13 | 2016-01-13 | 2016-01-13 | 2016-01-13 | 2016-01-13 | 2016-01-13 | 2016-01-13 | 2016-01-13 | 2016-01-13 | 2016-01-13 | 2016-01-13 | 2016-01-13 | 2016-01-13 | 2016-01-13 | 2016-01-13 | 2016-01-13 | 2016-01-13 | 2016-01-13 | 2016-01-13 | 2016-01-13 | 2016-01-13 | 2016-01-13 | 2016-01-13 | 2016-01-13 | 2016-01-13 | 2016-01-13 | 2016-01-13 | 2016-01-13 | 2016-01-13 | 2016-01-13 | 2016-01-13 | 2016-01-13 | 2016-01-13 | 2016-01-13 | 2016-01-13
2AI141CV01100-08040 | COCC : Concrete Protection | [29 empty] | 2017-11-26 | 2017-11-26 | 2017-11-26 | 2017-11-26 | 2017-11-26 | 2017-11-26 | 2017-11-26 | 2017-11-26 | 2017-11-26 | 2017-11-26 | 2017-11-26 | 2017-11-26 | 2017-11-26 | 2017-11-26 | 2017-11-26 | 2017-11-26 | 2017-11-26
2AI141CV01100-08045 | COCC:Backfilling with clean sand layer | [5 empty] | 2016-01-15 | 2016-01-15 | 2016-01-15 | 2016-01-15 | 2016-01-15 | 2016-01-15 | 2016-01-15 | 2016-01-15 | 2016-01-15 | 2016-01-15 | 2016-01-15 | 2016-01-15 | 2016-01-15 | 2016-01-15 | 2016-01-15 | 2016-01-15 | 2016-01-15 | 2016-01-15 | 2016-01-15 | 2016-01-15 | 2016-01-15 | 2016-01-15 | 2016-01-15 | 2016-01-15 | 2016-01-15 | 2016-01-15 | 2016-01-15 | 2016-01-15 | 2016-01-15 | 2016-01-15 | 2016-01-15 | 2016-01-15 | 2016-01-15 | 2016-01-15 | 2016-01-15 | 2016-01-15 | 2016-01-15 | 2016-01-15 | 2016-01-15 | 2016-01-15 | 2016-01-15
2AI141CV01100-08050 | COCC : Survey Marking, Excavation & Subgrade preparation | [35 empty] | 2018-07-08 | 2018-07-08 | 2018-07-08 | 2018-07-08 | 2018-07-08 | 2018-07-08 | 2018-07-08 | 2018-07-08 | 2018-07-08 | 2018-07-08 | 2018-07-08
2AI141CV01100-08055 | COCC:Install Cable Tiles & Warning Tapes | [5 empty] | 2016-01-17 | 2016-01-17 | 2016-01-17 | 2016-01-17 | 2016-01-17 | 2016-01-17 | 2016-01-17 | 2016-01-17 | 2016-01-17 | 2016-01-17 | 2016-01-17 | 2016-01-17 | 2016-01-17 | 2016-01-17 | 2016-01-17 | 2016-01-17 | 2016-01-17 | 2016-01-17 | 2016-01-17 | 2016-01-17 | 2016-01-17 | 2016-01-17 | 2016-01-17 | 2016-01-17 | 2016-01-17 | 2016-01-17 | 2016-01-17 | 2016-01-17 | 2016-01-17 | 2016-01-17 | 2016-01-17 | 2016-01-17 | 2016-01-17 | 2016-01-17 | 2016-01-17 | 2016-01-17 | 2016-01-17 | 2016-01-17 | 2016-01-17 | 2016-01-17 | 2016-01-17
2AI141CV01100-08060 | COCC : Blinding/PCC | [35 empty] | 2018-07-08 | 2018-07-08 | 2018-07-08 | 2018-07-08 | 2018-07-08 | 2018-07-08 | 2018-07-08 | 2018-07-08 | 2018-07-08 | 2018-07-08 | 2018-07-08
2AI141CV01100-08065 | COCC:Backfilling and Compaction | [7 empty] | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24
2AI141CV01100-08070 | COCC : Installation of pre-cast foundations and Leveling | [35 empty] | 2018-07-25 | 2018-07-25 | 2018-07-25 | 2018-07-25 | 2018-07-25 | 2018-07-25 | 2018-07-25 | 2018-07-25 | 2018-07-25 | 2018-07-25 | 2018-07-25
2AI141CV01100-08075 | COCC:Install Route/saftey Markers
2AI141CV01100-08080 | COCC : Backfill and Compaction (wherever applicable) | [37 empty] | 2018-08-26 | 2018-08-26 | 2018-08-26 | 2018-08-26 | 2018-08-26 | 2018-08-26 | 2018-08-26 | 2018-08-26 | 2018-08-26
2AI141CV01100-08085 | COCC: Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material | [21 empty] | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29 | 2017-04-29
2AI141CV01100-08090 | COCC : Prepare Mould/Formwork, Rebar & Insert embedments (at Pre-cast Yard) | [25 empty] | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29 | 2017-07-29
2AI141CV01100-08095 | COCC: Subgrade and Blinding | [21 empty] | 2017-05-13 | 2017-05-13 | 2017-05-13 | 2017-05-13 | 2017-05-13 | 2017-05-13 | 2017-05-13 | 2017-05-13 | 2017-05-13 | 2017-05-13 | 2017-05-13 | 2017-05-13 | 2017-05-13 | 2017-05-13 | 2017-05-13 | 2017-05-13 | 2017-05-13 | 2017-05-13 | 2017-05-13 | 2017-05-13 | 2017-05-13 | 2017-05-13 | 2017-05-13 | 2017-05-13 | 2017-05-13
2AI141CV01100-08100 | COCC : Concrete Pouring | [25 empty] | 2017-07-30 | 2017-07-30 | 2017-07-30 | 2017-07-30 | 2017-07-30 | 2017-07-30 | 2017-07-30 | 2017-07-30 | 2017-07-30 | 2017-07-30 | 2017-07-30 | 2017-07-30 | 2017-07-30 | 2017-07-30 | 2017-07-30 | 2017-07-30 | 2017-07-30 | 2017-07-30 | 2017-07-30 | 2017-07-30 | 2017-07-30
2AI141CV01100-08105 | COCC: Rebar, Formwork & PVC conduits installation(duct bank) | [21 empty] | 2017-05-15 | 2017-05-15 | 2017-05-15 | 2017-05-15 | 2017-05-15 | 2017-05-15 | 2017-05-15 | 2017-05-15 | 2017-05-15 | 2017-05-15 | 2017-05-15 | 2017-05-15 | 2017-05-15 | 2017-05-15 | 2017-05-15 | 2017-05-15 | 2017-05-15 | 2017-05-15 | 2017-05-15 | 2017-05-15 | 2017-05-15 | 2017-05-15 | 2017-05-15 | 2017-05-15 | 2017-05-15
2AI141CV01100-08110 | COCC : Concrete Protection | [25 empty] | 2017-08-01 | 2017-08-01 | 2017-08-01 | 2017-08-01 | 2017-08-01 | 2017-08-01 | 2017-08-01 | 2017-08-01 | 2017-08-01 | 2017-08-01 | 2017-08-01 | 2017-08-01 | 2017-08-01 | 2017-08-01 | 2017-08-01 | 2017-08-01 | 2017-08-01 | 2017-08-01 | 2017-08-01 | 2017-08-01 | 2017-08-01
2AI141CV01100-08115 | COCC: Concrete Pouring | [21 empty] | 2017-05-18 | 2017-05-18 | 2017-05-18 | 2017-05-18 | 2017-05-18 | 2017-05-18 | 2017-05-18 | 2017-05-18 | 2017-05-18 | 2017-05-18 | 2017-05-18 | 2017-05-18 | 2017-05-18 | 2017-05-18 | 2017-05-18 | 2017-05-18 | 2017-05-18 | 2017-05-18 | 2017-05-18 | 2017-05-18 | 2017-05-18 | 2017-05-18 | 2017-05-18 | 2017-05-18 | 2017-05-18
2AI141CV01100-08120 | COCC : Survey Marking, Excavation & Subgrade preparation | [29 empty] | 2018-01-18 | 2018-01-18 | 2018-01-18 | 2018-01-18 | 2018-01-18 | 2018-01-18 | 2018-01-18 | 2018-01-18 | 2018-01-18 | 2018-01-18 | 2018-01-18 | 2018-01-18 | 2018-01-18 | 2018-01-18 | 2018-01-18 | 2018-01-18 | 2018-01-18
2AI141CV01100-08125 | COCC: Coating | [23 empty] | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30
2AI141CV01100-08130 | COCC : Blinding/PCC | [29 empty] | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26 | 2018-01-26
2AI141CV01100-08135 | COCC: Backfill and Compaction | [23 empty] | 2017-06-11 | 2017-06-11 | 2017-06-11 | 2017-06-11 | 2017-06-11 | 2017-06-11 | 2017-06-11 | 2017-06-11 | 2017-06-11 | 2017-06-11 | 2017-06-11 | 2017-06-11 | 2017-06-11 | 2017-06-11 | 2017-06-11 | 2017-06-11 | 2017-06-11 | 2017-06-11 | 2017-06-11 | 2017-06-11 | 2017-06-11 | 2017-06-11 | 2017-06-11
2AI141CV01100-08140 | COCC : Installation of pre-cast foundations and Leveling | [31 empty] | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18 | 2018-03-18
2AI141CV01100-08145 | COCC : Backfill and Compaction (wherever applicable) | [33 empty] | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02
2AI141CV01100-08150 | COCC: Survey marking & Excavation | [15 empty] | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18
2AI141CV01100-08160 | COCC: Sub grade & Blinding | [15 empty] | 2016-10-26 | 2016-10-26 | 2016-10-26 | 2016-10-26 | 2016-10-26 | 2016-10-26 | 2016-10-26 | 2016-10-26 | 2016-10-26 | 2016-10-26 | 2016-10-26 | 2016-10-26 | 2016-10-26 | 2016-10-26 | 2016-10-26 | 2016-10-26 | 2016-10-26 | 2016-10-26 | 2016-10-26 | 2016-10-26 | 2016-10-26 | 2016-10-26 | 2016-10-26 | 2016-10-26 | 2016-10-26 | 2016-10-26 | 2016-10-26 | 2016-10-26 | 2016-10-26 | 2016-10-26 | 2016-10-26
2AI141CV01100-08170 | COCC: Install/Cast insitu fencing fnds (including tie beams - if any) | [15 empty] | 2016-10-26 | 2016-10-26 | 2016-10-26 | 2016-10-26 | 2016-10-26 | 2016-10-26 | 2016-10-26 | 2016-10-26 | 2016-10-26 | 2016-10-26 | 2016-10-26 | 2016-10-26 | 2016-10-26 | 2016-10-26 | 2016-10-26 | 2016-10-26 | 2016-10-26 | 2016-10-26 | 2016-10-26 | 2016-10-26 | 2016-10-26 | 2016-10-26 | 2016-10-26 | 2016-10-26 | 2016-10-26 | 2016-10-26 | 2016-10-26 | 2016-10-26 | 2016-10-26 | 2016-10-26 | 2016-10-26
2AI141CV01100-08180 | COCC: Fix Railing/wire mesh installation | [15 empty] | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31 | 2016-10-31
2AI141CV01100-08190 | COCC: Gate Installation & Speed bumbs | [15 empty] | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07
2AI141EL01000 | COCC CCR Field & Building : Earthing & Lightning Protection Works | [33 empty] | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21
2AI141EL01000-08000 | COCC CCR Field & Building : Earthing & Lightning Protection Works(outside the Building) | [33 empty] | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21
2AI141EL01000-08001 | COCC: Earth rod Installation | [33 empty] | 2018-04-21: 2018-10-14; 2018-04-21: 2018-10-14; 2018-04-21: 2018-10-14; 2018-04-21: 2018-10-14; 2018-04-21: 2018-10-14; 2018-04-21: 2018-10-14; 2018-04-21: 2018-10-14
2AI141EL01000-08005 | COCC: Earth Cable Laying | [33 empty] | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21
2AI141EL01000-08010 | COCC: Cad welding | [37 empty] | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22 | 2018-09-22
2AI141EL01000-08015 | COCC: Earth Bus Installation | [37 empty] | 2018-08-25 | 2018-08-25 | 2018-08-25 | 2018-08-25 | 2018-08-25 | 2018-08-25 | 2018-08-25 | 2018-08-25 | 2018-08-25
2AI141EL01000-08020 | COCC: Earth Boss Installation | [35 empty] | 2018-07-23 | 2018-07-23 | 2018-07-23 | 2018-07-23 | 2018-07-23 | 2018-07-23 | 2018-07-23 | 2018-07-23 | 2018-07-23 | 2018-07-23 | 2018-07-23
2AI141EL01000-08025 | COCC: Earth cable Termination | [37 empty] | 2018-08-25 | 2018-08-25 | 2018-08-25 | 2018-08-25 | 2018-08-25 | 2018-08-25 | 2018-08-25 | 2018-08-25 | 2018-08-25
2AI141EL01000-08028 | COCC: Earth Pit Installation | [39 empty] | 2018-10-12 | 2018-10-12 | 2018-10-12 | 2018-10-12 | 2018-10-12 | 2018-10-12 | 2018-10-12
2AI141EL01100 | COCC CCR Building : Cable laying, glanding & termination | [31 empty] | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07
2AI141EL01100-08000 | COCC CCR Field & Building : Install Electrical Cable trays & Supports | [35 empty] | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02
2AI141EL01100-08001 | COCC:Fabricate Tray Supports | [35 empty] | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02
2AI141EL01100-08002 | COCC: Install Tray support | [35 empty] | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02
2AI141EL01100-08005 | COCC CCR Field & Building : Electrical Cable Laying | [31 empty] | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07
2AI141EL01100-08006 | COCC: Cable Laying - LV | [31 empty] | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07
2AI141EL01100-08007 | COCC: Install cable trays | [35 empty] | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02
2AI141EL01100-08010 | COCC CCR Field & Building : Electrical Cable Laying | [33 empty] | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21
2AI141EL01100-08011 | COCC: Installcable trays covers | [35 empty] | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02 | 2018-07-02
2AI141EL01100-08015 | COCC: Cable Glanding for LV cables | [35 empty] | 2018-06-02 | 2018-06-02 | 2018-06-02 | 2018-06-02 | 2018-06-02 | 2018-06-02 | 2018-06-02 | 2018-06-02 | 2018-06-02 | 2018-06-02 | 2018-06-02
2AI141EL01100-08020 | COCC: Continuity Checks & Terminations for LV cables | [35 empty] | 2018-06-03 | 2018-06-03 | 2018-06-03 | 2018-06-03 | 2018-06-03 | 2018-06-03 | 2018-06-03 | 2018-06-03 | 2018-06-03 | 2018-06-03 | 2018-06-03
2AI141EL01100-08025 | COCC: Tagging for LV cables | [37 empty] | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23 | 2018-09-23
2AI141EL01100-08028 | COCC: Cable Laying - HV | [33 empty] | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02
2AI141EL01100-08030 | COCC: Cable Glanding for HV cables | [33 empty] | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21 | 2018-04-21
2AI141EL01100-08035 | COCC: Continuity Checks & Terminations for HV cables | [33 empty] | 2018-04-22 | 2018-04-22 | 2018-04-22 | 2018-04-22 | 2018-04-22 | 2018-04-22 | 2018-04-22 | 2018-04-22 | 2018-04-22 | 2018-04-22 | 2018-04-22 | 2018-04-22 | 2018-04-22
2AI141EL01100-08040 | COCC: Tagging for HV cables | [33 empty] | 2018-04-23 | 2018-04-23 | 2018-04-23 | 2018-04-23 | 2018-04-23 | 2018-04-23 | 2018-04-23 | 2018-04-23 | 2018-04-23 | 2018-04-23 | 2018-04-23 | 2018-04-23 | 2018-04-23
2AI141EL01200 | COCC CCR Building : Electrical Equipment & Panels Installation | [31 empty] | 2018-03-15 | 2018-03-15 | 2018-03-15 | 2018-03-15 | 2018-03-15 | 2018-03-15 | 2018-03-15 | 2018-03-15 | 2018-03-15 | 2018-03-15 | 2018-03-15 | 2018-03-15 | 2018-03-15 | 2018-03-15 | 2018-03-15
2AI141EL01200-08000 | COCC: Electrical Equipment Installation | [31 empty] | 2018-03-15 | 2018-03-15 | 2018-03-15 | 2018-03-15 | 2018-03-15 | 2018-03-15 | 2018-03-15 | 2018-03-15 | 2018-03-15 | 2018-03-15 | 2018-03-15 | 2018-03-15 | 2018-03-15 | 2018-03-15 | 2018-03-15
2AI141EL01200-08005 | COCC: Electrical Panels Installation | [31 empty] | 2018-03-15 | 2018-03-15 | 2018-03-15 | 2018-03-15 | 2018-03-15 | 2018-03-15 | 2018-03-15 | 2018-03-15 | 2018-03-15 | 2018-03-15 | 2018-03-15 | 2018-03-15 | 2018-03-15 | 2018-03-15 | 2018-03-15
2AI141IC01000 | COCC CCR Building : Field & Building Cable Trays and Conduits | [35 empty] | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26
2AI141IC01000-08000 | COCC CCR Field & Building : Field & Building Cable Trays and Conduits | [35 empty] | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26
2AI141IC01000-08001 | COCC: Field & Building Cable Trays Installation | [35 empty] | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23
2AI141IC01000-08005 | COCC: Field & Building Conduits Installation | [35 empty] | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26 | 2018-05-26
2AI141IC01100 | COCC CCR Building : Field Junction Boxes | [35 empty] | 2018-05-27 | 2018-05-27 | 2018-05-27 | 2018-05-27 | 2018-05-27 | 2018-05-27 | 2018-05-27 | 2018-05-27 | 2018-05-27 | 2018-05-27 | 2018-05-27
2AI141IC01100-08000 | COCC CCR Field & Building : Junction Boxes | [35 empty] | 2018-05-27 | 2018-05-27 | 2018-05-27 | 2018-05-27 | 2018-05-27 | 2018-05-27 | 2018-05-27 | 2018-05-27 | 2018-05-27 | 2018-05-27 | 2018-05-27
2AI141IC01100-08001 | COCC: Installation of supports | [35 empty] | 2018-06-21 | 2018-06-21 | 2018-06-21 | 2018-06-21 | 2018-06-21 | 2018-06-21 | 2018-06-21 | 2018-06-21 | 2018-06-21 | 2018-06-21 | 2018-06-21
2AI141IC01100-08005 | COCC: Installation of Junction Boxes | [35 empty] | 2018-05-27 | 2018-05-27 | 2018-05-27 | 2018-05-27 | 2018-05-27 | 2018-05-27 | 2018-05-27 | 2018-05-27 | 2018-05-27 | 2018-05-27 | 2018-05-27
2AI141IC01100-08010 | COCC:Leveling & Grouting | [35 empty] | 2018-05-27: 2019-04-08
2AI141IC01200 | COCC CCR Building : Field & Building Cable laying, glanding & termination | [33 empty] | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02
2AI141IC01200-08000 | COCC: Instrument Cable Laying | [33 empty] | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02
2AI141IC01200-08005 | COCC: Cable Glanding and Termination | [35 empty] | 2018-06-02 | 2018-06-02 | 2018-06-02 | 2018-06-02 | 2018-06-02 | 2018-06-02 | 2018-06-02 | 2018-06-02 | 2018-06-02 | 2018-06-02 | 2018-06-02
2AI141IC01300 | COCC CCR Building : Panel base frame Installation | [35 empty] | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04
2AI141IC01300-08000 | COCC CCR Building : Panel base frame Installation | [35 empty] | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04
2AI141IC01500 | COCC CCR Building : Equipment & Panels Installation (ICSS) | [33 empty] | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05
2AI141IC01500-08000 | COCC CCR Building : ICSS installation | [33 empty] | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05
2AI141IC01500-08005 | COCC CCR Building : Other Equipment & Panels Installation | [35 empty] | 2018-07-20 | 2018-07-20 | 2018-07-20 | 2018-07-20 | 2018-07-20 | 2018-07-20 | 2018-07-20 | 2018-07-20 | 2018-07-20 | 2018-07-20 | 2018-07-20
2AI141PC01000 | COCC CCR Building : ICSS SAT
2AI141PC01000-08000 | COCC CCR Building : ICSS SAT
2AI141PC02000 | COCC: EOF SS 50-SUBST-001 : 110V DC Battery Charger | [35 empty] | 2018-07-20: 2019-03-23; 2018-07-20: 2019-03-23; 2018-07-20: 2019-03-23
2AI141PC02000-08000 | COCC: EOF SS 50-SUBST-001 : 110V DC Battery Charger | [35 empty] | 2018-07-20: 2019-03-23; 2018-07-20: 2019-03-23; 2018-07-20: 2019-03-23
2AI141PC02000-08001 | COCC: Polarity check | [35 empty] | 2018-07-20: 2019-03-23; 2018-07-20: 2019-03-23; 2018-07-20: 2019-03-23
2AI141PC02000-08005 | COCC: Charging test | [35 empty] | 2018-07-20: 2019-03-23; 2018-07-20: 2019-03-23; 2018-07-20: 2019-03-23
2AI141PC02000-08010 | COCC: Discharging test | [35 empty] | 2018-07-20: 2019-03-24; 2018-07-20: 2019-03-24; 2018-07-20: 2019-03-24
2AI141PC02100 | COCC: EOF SS 50-SUBST-001 : SS Earthing & Lightning | [35 empty] | 2018-07-20: 2019-01-26; 2018-07-20: 2019-01-26; 2018-07-20: 2019-01-26
2AI141PC02100-08000 | COCC: EOF SS 50-SUBST-001 : SS Earthing & Lightning | [35 empty] | 2018-07-20: 2019-01-26; 2018-07-20: 2019-01-26; 2018-07-20: 2019-01-26
2AI141PC02100-08001 | COCC: Continuity testing | [35 empty] | 2018-07-20: 2019-04-08
2AI141PC02100-08005 | COCC: Earth resistance measurement | [35 empty] | 2018-07-20: 2019-01-26; 2018-07-20: 2019-01-26; 2018-07-20: 2019-01-26
2AI141PC02200 | COCC: EOF SS 50-SUBST-001 : HV Switchgear testing | [35 empty] | 2018-07-20: 2018-12-29; 2018-07-20: 2018-12-29; 2018-07-20: 2018-12-29; 2018-07-20: 2018-12-29; 2018-07-20: 2018-12-29
2AI141PC02200-08000 | COCC: EOF SS 50-SUBST-001 : HV Switchgear testing | [35 empty] | 2018-07-20: 2018-12-29; 2018-07-20: 2018-12-29; 2018-07-20: 2018-12-29; 2018-07-20: 2018-12-29; 2018-07-20: 2018-12-29
2AI141PC02200-08001 | EOF: CT,PT,Breaker Testing | [35 empty] | 2018-07-20: 2019-01-05; 2018-07-20: 2019-01-05; 2018-07-20: 2019-01-05; 2018-07-20: 2019-01-05; 2018-07-20: 2019-01-05
2AI141PC02200-08005 | EOF: IR, Ductor testing | [35 empty] | 2018-07-20: 2019-01-06; 2018-07-20: 2019-01-06; 2018-07-20: 2019-01-06; 2018-07-20: 2019-01-06; 2018-07-20: 2019-01-06
2AI141PC02200-08010 | EOF: Relay & Functional Testing | [35 empty] | 2018-07-20: 2018-12-29; 2018-07-20: 2018-12-29; 2018-07-20: 2018-12-29; 2018-07-20: 2018-12-29; 2018-07-20: 2018-12-29
2AI141PC02200-08015 | EOF Primary Injection Testing | [35 empty] | 2018-07-20: 2018-12-30; 2018-07-20: 2018-12-30; 2018-07-20: 2018-12-30; 2018-07-20: 2018-12-30; 2018-07-20: 2018-12-30
2AI141PC02200-08020 | EOF: Hi-pot Test | [35 empty] | 2018-07-20: 2019-01-05; 2018-07-20: 2019-01-05; 2018-07-20: 2019-01-05; 2018-07-20: 2019-01-05; 2018-07-20: 2019-01-05
2AI141PC02200-08025 | EOF: Stability Testing | [35 empty] | 2018-07-20: 2019-01-06; 2018-07-20: 2019-01-06; 2018-07-20: 2019-01-06; 2018-07-20: 2019-01-06; 2018-07-20: 2019-01-06
2AI141PC02300 | COCC: EOF SS 50-SUBST-001 : 24V DC Battery Charger | [35 empty] | 2018-07-20: 2019-03-23; 2018-07-20: 2019-03-23; 2018-07-20: 2019-03-23
2AI141PC02300-08000 | COCC: EOF SS 50-SUBST-001 : 24V DC Battery Charger | [35 empty] | 2018-07-20: 2019-03-23; 2018-07-20: 2019-03-23; 2018-07-20: 2019-03-23
2AI141PC02300-08001 | COCC: Polarity check | [35 empty] | 2018-07-20: 2019-03-23; 2018-07-20: 2019-03-23; 2018-07-20: 2019-03-23
2AI141PC02300-08005 | COCC: Charging test | [35 empty] | 2018-07-20: 2019-03-24; 2018-07-20: 2019-03-24; 2018-07-20: 2019-03-24
2AI141PC02300-08010 | COCC: Discharging test | [35 empty] | 2018-07-20: 2019-03-27; 2018-07-20: 2019-03-27; 2018-07-20: 2019-03-27
2AI141PC02400 | COCC: EOF SS 50-SUBST-001 : LV Switchgear testing | [35 empty] | 2018-07-20: 2018-12-22; 2018-07-20: 2018-12-22; 2018-07-20: 2018-12-22; 2018-07-20: 2018-12-22; 2018-07-20: 2018-12-22
2AI141PC02400-08000 | COCC: EOF SS 50-SUBST-001 : LV Switchgear testing | [35 empty] | 2018-07-20: 2018-12-22; 2018-07-20: 2018-12-22; 2018-07-20: 2018-12-22; 2018-07-20: 2018-12-22; 2018-07-20: 2018-12-22
2AI141PC02400-08001 | EOF: CT,PT Testing | [35 empty] | 2018-07-20: 2018-12-22; 2018-07-20: 2018-12-22; 2018-07-20: 2018-12-22; 2018-07-20: 2018-12-22; 2018-07-20: 2018-12-22
2AI141PC02400-08005 | EOF: IR, Ductor testing | [35 empty] | 2018-07-20: 2018-12-23; 2018-07-20: 2018-12-23; 2018-07-20: 2018-12-23; 2018-07-20: 2018-12-23; 2018-07-20: 2018-12-23
2AI141PC02400-08010 | EOF: Relay & Functional Testing | [35 empty] | 2018-07-20: 2018-12-23; 2018-07-20: 2018-12-23; 2018-07-20: 2018-12-23; 2018-07-20: 2018-12-23; 2018-07-20: 2018-12-23
2AI141PC02400-08015 | EOF Primary Injection Testing | [35 empty] | 2018-07-20: 2019-01-03; 2018-07-20: 2019-01-03; 2018-07-20: 2019-01-03; 2018-07-20: 2019-01-03; 2018-07-20: 2019-01-03
2AI141PC02400-08020 | EOF: Hi-pot Test | [35 empty] | 2018-07-20: 2019-01-26; 2018-07-20: 2019-01-26; 2018-07-20: 2019-01-26
2AI141PC02400-08025 | EOF: Stability Testing | [35 empty] | 2018-07-20: 2019-01-26; 2018-07-20: 2019-01-26; 2018-07-20: 2019-01-26
2AI141PC02600 | COCC: EOF SS 50-SUBST-001 : 110V AC UPS | [35 empty] | 2018-07-20: 2019-01-27; 2018-07-20: 2019-01-27; 2018-07-20: 2019-01-27
2AI141PC02600-08000 | COCC: EOF SS 50-SUBST-001 : 110V AC UPS | [35 empty] | 2018-07-20: 2019-01-27; 2018-07-20: 2019-01-27; 2018-07-20: 2019-01-27
2AI141PC02600-08001 | COCC: Polarity check | [35 empty] | 2018-07-20: 2019-01-27; 2018-07-20: 2019-01-27; 2018-07-20: 2019-01-27
2AI141PC02600-08005 | COCC: Charging test | [35 empty] | 2018-07-20: 2019-01-27; 2018-07-20: 2019-01-27; 2018-07-20: 2019-01-27
2AI141PC02600-08010 | COCC: Discharging test | [35 empty] | 2018-07-20: 2019-01-28; 2018-07-20: 2019-01-28; 2018-07-20: 2019-01-28
2AI141PC02700 | COCC: EOF SS 50-SUBST-001 : Transformer Testing | [35 empty] | 2018-07-20: 2018-12-22; 2018-07-20: 2018-12-22; 2018-07-20: 2018-12-22; 2018-07-20: 2018-12-22; 2018-07-20: 2018-12-22
2AI141PC02700-08000 | COCC: EOF SS 50-SUBST-001 : Transformer Testing | [35 empty] | 2018-07-20: 2018-12-22; 2018-07-20: 2018-12-22; 2018-07-20: 2018-12-22; 2018-07-20: 2018-12-22; 2018-07-20: 2018-12-22
2AI141PC02700-08001 | EOF:IR testing/WR testing/Turns ratio testing | [35 empty] | 2018-07-20: 2018-12-22; 2018-07-20: 2018-12-22; 2018-07-20: 2018-12-22; 2018-07-20: 2018-12-22; 2018-07-20: 2018-12-22
2AI141PC02700-08005 | EOF:Functional Test | [35 empty] | 2018-07-20: 2018-12-22; 2018-07-20: 2018-12-22; 2018-07-20: 2018-12-22; 2018-07-20: 2018-12-22; 2018-07-20: 2018-12-22
2AI141PC02700-08010 | EOF:BDV Testing | [35 empty] | 2018-07-20: 2018-12-22; 2018-07-20: 2018-12-22; 2018-07-20: 2018-12-22; 2018-07-20: 2018-12-22; 2018-07-20: 2018-12-22
2AI141PC02900 | COCC: EOF SS 50-SUBST-001 : Electrical Tie-ins for Permanent Power & Energize | [35 empty] | 2018-07-20: 2019-04-13
2AI141PC02900-08000 | COCC: EOF SS 50-SUBST-001 : Electrical Tie-ins for Permanent Power & Energize | [35 empty] | 2018-07-20: 2019-04-13
2AI141PC02900-08001 | COCC: Incoming cables IR and continuity test | [35 empty] | 2018-07-20: 2019-04-13
2AI141PC02900-08005 | COCC: Incoming HV cables hipot testing | [35 empty] | 2018-07-20: 2019-04-15
2AI141PC02900-08010 | EOF: Cable Termination | [35 empty] | 2018-07-20: 2019-04-17
2AI141PC02900-08015 | EOF: Ready for Energisation of Substation 50-SUBST-001 | [35 empty] | 2018-07-20: 2019-04-20
2AI141PC03000 | COCC: EOF SS 50-SUBST-001 : Energize EDG Building 50-R-002 | [35 empty] | 2018-07-20: 2019-04-08
2AI141PC03000-08000 | COCC: EOF SS 50-SUBST-001 : Energize EDG Building 50-R-002 | [35 empty] | 2018-07-20: 2019-04-08
2AI141PC03000-08001 | COCC: GCP Testing, Switch Gear Testing | [35 empty] | 2018-07-20: 2019-04-08
2AI141PC03000-08010 | COCC: EOF SS 50-SUBST-001 : Energize EDG Building 50-R-002
2AI141PC03100 | COCC: EOF SS 50-SUBST-001 : Lighting & Small Power | [25 empty] | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03
2AI141PC03100-08000 | COCC: EOF SS 50-SUBST-001 : Lighting & Small Power | [25 empty] | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03
2AI141PC03100-08001 | COCC: Continuity & IR testing | [25 empty] | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03 | 2017-08-03
2AI141PC03100-08005 | COCC: Lux testing | [25 empty] | 2017-08-12 | 2017-08-12 | 2017-08-12 | 2017-08-12 | 2017-08-12 | 2017-08-12 | 2017-08-12 | 2017-08-12 | 2017-08-12 | 2017-08-12 | 2017-08-12 | 2017-08-12 | 2017-08-12 | 2017-08-12 | 2017-08-12 | 2017-08-12 | 2017-08-12 | 2017-08-12 | 2017-08-12 | 2017-08-12 | 2017-08-12
2AI141TE01000 | COCC CCR Building : Cabinet and Panel Installation | [33 empty] | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07
2AI141TE01000-08000 | COCC CCR Building : Cabinet and Panel Installation | [33 empty] | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07
2AI141TE01000-08001 | Fabrication & Installation of Supports / Frames | [33 empty] | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07
2AI141TE01000-08015 | Installation of Equipment/Panels | [33 empty] | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 2018-05-07
2AI141TE01000-08020 | Leveling & Grouting | [35 empty] | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04
2AI141TE01100 | COCC CCR Building : FO & Telephone Cabling, Cable Terminations & continuity checks | [35 empty] | 2018-06-04: 2019-04-08
2AI141TE01100-08000 | COCC CCR Building : FO & Telephone Cabling works | [35 empty] | 2018-06-04: 2019-04-08
2AI141TE01100-08001 | Cable Drum Checks & Transport to Site | [35 empty] | 2018-06-04: 2019-04-08
2AI141TE01100-08005 | COCC CCR Building : Cable Terminations & continuity checks | [35 empty] | 2018-06-04: 2019-04-08
2AI141TE01100-08006 | COCC: Cable Laying (FO, Coaxial, bare etc) | [35 empty] | 2018-06-04: 2019-04-08
2AI141TE01100-08010 | COCC: Splicing of FO Cable | [35 empty] | 2018-06-04: 2019-04-08
2AI141TE01100-08015 | Glanding | [35 empty] | 2018-06-04: 2019-04-08
2AI141TE01100-08025 | Continuity Checks & Terminations | [35 empty] | 2018-06-04: 2019-04-08
2AI141TE01100-08035 | Tagging | [35 empty] | 2018-06-04: 2019-04-08
2AI141TE01200 | COCC CCR Building : Outdoor Eqipment Inst. (CCTV, Access Control) | [29 empty] | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01
2AI141TE01200-08000 | COCC CCR Building : Eqipment Inst. (CCTV, Access Control) | [29 empty] | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01
2AI141TE01200-08001 | Installation of Support Structures (wherever applicable) | [29 empty] | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01
2AI141TE01200-08005 | Installation of Equipment/Panels | [29 empty] | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01
2AI141TE01200-08010 | Leveling & Grouting | [29 empty] | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01
2AI151CV99920-08000 | EOF: Delivery of Structural steel for Shelters - Lot-1 | [15 empty] | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20
2AI151CV99920-08005 | EOF: Delivery of Structural steel for Ground Support Platforms - Lot-1 | [21 empty] | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16
2AI151CV99920-08010 | EOF: Delivery of steel for Pipesupports, EIT/HSE supports & misc steel (handrails, ladders,etc) - Lot-1 | [21 empty] | 2017-04-25 | 2017-04-25 | 2017-04-25 | 2017-04-25 | 2017-04-25 | 2017-04-25 | 2017-04-25 | 2017-04-25 | 2017-04-25 | 2017-04-25 | 2017-04-25 | 2017-04-25 | 2017-04-25 | 2017-04-25 | 2017-04-25 | 2017-04-25 | 2017-04-25 | 2017-04-25 | 2017-04-25 | 2017-04-25 | 2017-04-25 | 2017-04-25 | 2017-04-25 | 2017-04-25 | 2017-04-25
2AI151CV99930-08000 | EOF: Delivery of Structural steel for Shelters - Lot-2 | [19 empty] | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06
2AI151CV99930-08005 | EOF: Delivery of Structural steel for Ground Support Platforms - Lot-2 | [21 empty] | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18
2AI151CV99930-08010 | EOF: Delivery of steel for Pipesupports, EIT/HSE supports & misc steel (handrails, ladders,etc) - Lot-2 | [29 empty] | 2017-11-25 | 2017-11-25 | 2017-11-25 | 2017-11-25 | 2017-11-25 | 2017-11-25 | 2017-11-25 | 2017-11-25 | 2017-11-25 | 2017-11-25 | 2017-11-25 | 2017-11-25 | 2017-11-25 | 2017-11-25 | 2017-11-25 | 2017-11-25 | 2017-11-25
2AI151CV99940-08000 | EOF: Delivery of Structural steel for Shelters - Lot-3 | [19 empty] | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06
2AI151CV99940-08005 | EOF: Delivery of Structural steel for Ground Support Platforms - Lot-3 | [23 empty] | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01
2AI151CV99940-08010 | EOF: Delivery of steel for Pipesupports, EIT/HSE supports & misc steel (handrails, ladders,etc) - Lot-3 | [19 empty] | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06
2AP000EL00107-08000 | 11KV & 3.3KV SWITCHGEAR & HV BUSDUCT - First Lot | [25 empty] | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18
2AP000EL00107-08005 | 11KV & 3.3KV SWITCHGEAR & HV BUSDUCT- Final Lot | [29 empty] | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23
2AP000EL00207-08000 | DISTRIBUTION & LIGHTING TRANSFORMER - First Lot | [21 empty] | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15
2AP000EL00207-08005 | DISTRIBUTION & LIGHTING TRANSFORMER- Final Lot | [21 empty] | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09
2AP000EL00207-08010 | Transformer Rectifier | [31 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
2AP000EL00507-08000 | EMERGENCY DIESEL GENERATOR SETS - First Lot | [31 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
2AP000EL00507-08005 | EMERGENCY DIESEL GENERATOR SETS- Final Lot | [31 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
2AP000EL00607-08000 | 440V LV SWITCHGEAR & LV BUSDUCT - First Lot | [25 empty] | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18
2AP000EL00607-08005 | 440V LV SWITCHGEAR & LV BUSDUCT- Final Lot | [29 empty] | 2017-12-13 | 2017-12-13 | 2017-12-13 | 2017-12-13 | 2017-12-13 | 2017-12-13 | 2017-12-13 | 2017-12-13 | 2017-12-13 | 2017-12-13 | 2017-12-13 | 2017-12-13 | 2017-12-13 | 2017-12-13 | 2017-12-13 | 2017-12-13 | 2017-12-13
2AP000EL00707-08000 | AC UPS & DC UPS - First Lot | [29 empty] | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21 | 2018-01-21
2AP000EL00707-08005 | AC UPS & DC UPS- Final Lot | [29 empty] | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23
2AP000EL00807-08000 | E-SCADA SYSTEM Lot 1 | [29 empty] | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23
2AP000EL00807-08005 | E-SCADA SYSTEM lot 2 | [29 empty] | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23 | 2017-12-23
2AP000EL00907-08000 | EOF : Delivery of HV & LV (Power, Control & Earthing) Cable - First Lot-1 | [19 empty] | 2017-02-22 | 2017-02-22 | 2017-02-22 | 2017-02-22 | 2017-02-22 | 2017-02-22 | 2017-02-22 | 2017-02-22 | 2017-02-22 | 2017-02-22 | 2017-02-22 | 2017-02-22 | 2017-02-22 | 2017-02-22 | 2017-02-22 | 2017-02-22 | 2017-02-22 | 2017-02-22 | 2017-02-22 | 2017-02-22 | 2017-02-22 | 2017-02-22 | 2017-02-22 | 2017-02-22 | 2017-02-22 | 2017-02-22 | 2017-02-22
2AP000EL00907-08005 | EOF : Delivery of HV & LV (Power, Control & Earthing) Cable - Lot-2 | [25 empty] | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26
2AP000EL00907-08010 | EOF : Delivery of HV & LV (Power, Control & Earthing) Cable - Last Lot-3 | [31 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
2AP000EL01007-08005 | INDUSTRIAL TYPE LIGHTING & POWER PANELS - First Lot | [29 empty] | 2018-01-15 | 2018-01-15 | 2018-01-15 | 2018-01-15 | 2018-01-15 | 2018-01-15 | 2018-01-15 | 2018-01-15 | 2018-01-15 | 2018-01-15 | 2018-01-15 | 2018-01-15 | 2018-01-15 | 2018-01-15 | 2018-01-15 | 2018-01-15 | 2018-01-15
2AP000EL01007-08010 | INDUSTRIAL TYPE LIGHTING & POWER PANELS- Final Lot | [31 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
2AP000EL01007-08011 | EOF : Delivery of Interposing Relay Panel | [31 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
2AP000EL01007-08015 | HAZARDOUS TYPE LIGHTING & POWER PANELS - First Lot | [29 empty] | 2018-01-14 | 2018-01-14 | 2018-01-14 | 2018-01-14 | 2018-01-14 | 2018-01-14 | 2018-01-14 | 2018-01-14 | 2018-01-14 | 2018-01-14 | 2018-01-14 | 2018-01-14 | 2018-01-14 | 2018-01-14 | 2018-01-14 | 2018-01-14 | 2018-01-14
2AP000EL01007-08020 | HAZARDOUS TYPE LIGHTING & POWER PANELS- Final Lot | [31 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
2AP000EL01407-08000 | EOF : Delivery of Lighting Poles & Lighting Fixtures - First Lot-1 | [31 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
2AP000EL01407-08005 | EOF : Delivery of Lighting Poles & Lighting Fixtures - Lot-2 | [31 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
2AP000EL01407-08010 | EOF : Delivery of Lighting Poles & Lighting Fixtures - Last Lot-3 | [31 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
2AP000EL01707-08000 | EOF : Delivery of Junction Box - First Lot-1 | [31 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
2AP000EL01707-08005 | EOF : Delivery of Junction Box - Lot-2 | [31 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
2AP000EL01707-08010 | EOF : Delivery of Junction Box - Last Lot-3 | [31 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
2AP000EL01807-08000 | EOF : Delivery of Junction Box - First Lot-1 | [31 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
2AP000EL01807-08005 | EOF : Delivery of Junction Box - Lot-2 | [31 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
2AP000EL01807-08010 | EOF : Delivery of Junction Box - Last Lot-3 | [31 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
2AP000EL01907-08000 | EOF : Delivery of Receptacles & Sockets - First Lot-1 | [31 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
2AP000EL01907-08005 | EOF : Delivery of Receptacles & Sockets - Lot-2 | [31 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
2AP000EL01907-08010 | EOF : Delivery of Receptacles & Sockets - Last Lot-3 | [31 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
2AP000EL02107-08000 | EOF : Delivery of Earthing & Lightning Protection Materials - First Lot-1 | [31 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
2AP000EL02107-08005 | EOF : Delivery of Earthing & Lightning Protection Materials - Lot-2 | [31 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
2AP000EL02107-08010 | EOF : Delivery of Earthing & Lightning Protection Materials - Last Lot-3 | [31 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
2AP000EL02207-08000 | EOF : Delivery of Electrical Cable Trays, Cable Ladders & Accessories - First Lot-1 | [31 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
2AP000EL02207-08005 | EOF : Delivery of Electrical Cable Trays, Cable Ladders & Accessories - Lot-2 | [31 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
2AP000EL02207-08010 | EOF : Delivery of Electrical Cable Trays, Cable Ladders & Accessories - Last Lot-3 | [31 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
2AP000EL02307-08000 | EOF : Delivery of Cable Termination & Jointing Kits - First Lot - 1 | [31 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
2AP000EL02307-08005 | EOF : Delivery of Cable Termination & Jointing Kits - Lot - 2 | [31 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
2AP000EL02307-08010 | EOF : Delivery of Cable Termination & Jointing Kits - Last Lot - 3 | [31 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
2AP000EL02407-08000 | EOF : Delivery of Cable Glands - First Lot - 1 | [31 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
2AP000EL02407-08005 | EOF : Delivery of Cable Glands - Lot - 2 | [31 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
2AP000EL02407-08010 | EOF : Delivery of Cable Glands - Last Lot - 3 | [31 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
2AP000EL02607-08000 | ELECTRICAL HEAT TRACING SYSTEM - First Lot | [31 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
2AP000EL02607-08005 | ELECTRICAL HEAT TRACING SYSTEM- Final Lot | [31 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
2AP000HS00107-08100 | EOF: Delivery of Fire fighting Equipments - First Lot | [31 empty] | 2018-02-24: 2019-03-10; 2018-02-24: 2019-03-10; 2018-02-24: 2019-03-10
2AP000HS00107-08105 | EOF: Delivery of Fire fighting Equipments - Last Lot | [31 empty] | 2018-02-24: 2019-03-10; 2018-02-24: 2019-03-10; 2018-02-24: 2019-03-10
2AP000HS00207-08100 | EOF: Delivery of Safety Equipments - First Lot | [31 empty] | 2018-02-24: 2018-11-08; 2018-02-24: 2018-11-08; 2018-02-24: 2018-11-08; 2018-02-24: 2018-11-08; 2018-02-24: 2018-11-08; 2018-02-24: 2018-11-08; 2018-02-24: 2018-11-08
2AP000HS00207-08105 | EOF: Delivery of Safety Equipments - Last Lot | [31 empty] | 2018-02-24: 2019-03-10; 2018-02-24: 2019-03-10; 2018-02-24: 2019-03-10
2AP000HS00507-08000 | 52-Z-301 A: Foam System Package Incl. 52-D-303 A/B; 52-D-307 A-D; 52-G-302 A-D | [31 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
2AP000HS00507-08005 | 52-Z-301 B: Foam System Package Incl. 52-D-303 A/B; 52-D-307 A-D; 52-G-302 A-D | [31 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
2AP000HS00507-08010 | EOF: Foam drain tank-52-D-305A | [21 empty] | 2017-04-11 | 2017-04-11 | 2017-04-11 | 2017-04-11 | 2017-04-11 | 2017-04-11 | 2017-04-11 | 2017-04-11 | 2017-04-11 | 2017-04-11 | 2017-04-11 | 2017-04-11 | 2017-04-11 | 2017-04-11 | 2017-04-11 | 2017-04-11 | 2017-04-11 | 2017-04-11 | 2017-04-11 | 2017-04-11 | 2017-04-11 | 2017-04-11 | 2017-04-11 | 2017-04-11 | 2017-04-11
2AP000HS00507-08015 | EOF: Foam drain tank-52-D-305B | [21 empty] | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12
2AP000HS00507-08020 | EOF: 621-G-302 A Foam Pump | [33 empty] | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07
2AP000HS00507-08025 | EOF: 621-G-302 B Foam Pump | [33 empty] | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07
2AP000HS00507-08030 | EOF: 621-G-302 C Foam Pump | [33 empty] | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07
2AP000HS00507-08035 | EOF: 621-G-302 D Foam Pump | [33 empty] | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07
2AP000IC00107-08000 | EOF : Delivery of Control Valves - First Lot-1 | [29 empty] | 2017-12-18 | 2017-12-18 | 2017-12-18 | 2017-12-18 | 2017-12-18 | 2017-12-18 | 2017-12-18 | 2017-12-18 | 2017-12-18 | 2017-12-18 | 2017-12-18 | 2017-12-18 | 2017-12-18 | 2017-12-18 | 2017-12-18 | 2017-12-18 | 2017-12-18
2AP000IC00107-08005 | EOF : Delivery of Control Valves - Lot-2 | [31 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
2AP000IC00107-08010 | EOF : Delivery of Control Valves - Last Lot-3 | [31 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
2AP000IC00207-08000 | EOF : Delivery of Shutdown Valves (Ball/Butterfly Type) & ESD Valves - First Lot-1 | [31 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
2AP000IC00207-08005 | EOF : Delivery of Shutdown Valves (Ball/Butterfly Type) & ESD Valves - Lot-2 | [31 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
2AP000IC00207-08010 | EOF : Delivery of Shutdown Valves (Ball/Butterfly Type) & ESD Valves - Last Lot-3 | [31 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
2AP000IC00407-08000 | EOF : Delivery of Motor Operated Valves (Ball/Butterfly/Gate Type) - First Lot-1 | [27 empty] | 2017-11-13 | 2017-11-13 | 2017-11-13 | 2017-11-13 | 2017-11-13 | 2017-11-13 | 2017-11-13 | 2017-11-13 | 2017-11-13 | 2017-11-13 | 2017-11-13 | 2017-11-13 | 2017-11-13 | 2017-11-13 | 2017-11-13 | 2017-11-13 | 2017-11-13 | 2017-11-13 | 2017-11-13
2AP000IC00407-08005 | EOF : Delivery of Motor Operated Valves (Ball/Butterfly/Gate Type) - Lot-2 | [31 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
2AP000IC00407-08010 | EOF : Delivery of Motor Operated Valves (Ball/Butterfly/Gate Type) - Last Lot-3 | [31 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
2AP000IC00907-08000 | EOF : Delivery of Level Gauges, Pressure Gauges & Temperature Guages - First Lot-1 | [31 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
2AP000IC01007-08000 | EOF : Delivery of Level Gauges, Pressure Gauges & Temperature Guages - Lot-2 | [31 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
2AP000IC01307-08000 | EOF : Delivery of Level Gauges, Pressure Gauges & Temperature Guages - Last Lot-3 | [31 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
2AP000IC01407-08010 | EOF : Delivery of Level Transmitters & Level Switches - First Lot - 1 | [31 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
2AP000IC01707-08010 | EOF : Delivery of Level Transmitters & Level Switches - Lot - 2 | [31 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
2AP000IC01807-08015 | EOF : Delivery of Level Transmitters & Level Switches - Last Lot -3 | [31 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
2AP000IC02207-08005 | EOF : Delivery of Flowmeters - First Lot-1 | [31 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
2AP000IC02607-08005 | EOF : Delivery of Flowmeters - Lot-2 | [31 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
2AP000IC03307-08000 | EOF : Delivery of Instrumentation Cable- Lot-1 | [31 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
2AP000IC03307-08005 | EOF : Delivery of Instrumentation Cable- Lot-2 | [31 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
2AP000IC03307-08010 | EOF : Delivery of Instrumentation Cable- Lot-3 | [31 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
2AP000IC03407-08000 | EOF : Delivery of Instrument Junction Boxes - Lot-1 | [31 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
2AP000IC03407-08005 | EOF : Delivery of Instrument Junction Boxes - Lot-2 | [31 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
2AP000IC03407-08010 | EOF : Delivery of Instrument Junction Boxes - Lot-3 | [31 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
2AP000IC03507-08000 | EOF : Delivery of Instrument Cable Glands - Lot-1 | [31 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
2AP000IC03507-08005 | EOF : Delivery of Instrument Cable Glands - Lot-2 | [31 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
2AP000IC03507-08010 | EOF : Delivery of Instrument Cable Glands - Lot-3 | [31 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
2AP000IC04007-08000 | EOF : Delivery of Instrumentation other misc Bulk Materials- Lot-1 | [31 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
2AP000IC04007-08005 | EOF : Delivery of Instrumentation other misc Bulk Materials- Lot-2 | [31 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
2AP000IC04007-08010 | EOF : Delivery of Instrumentation other misc Bulk Materials- Lot-3 | [31 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
2AP000IC04207-08000 | EOF : Delivery of Instrumentation Tubes & Fittings-Lot-1 | [31 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
2AP000IC04207-08005 | EOF : Delivery of Instrumentation Tubes & Fittings-Lot-2 | [31 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
2AP000IC04207-08010 | EOF : Delivery of Instrumentation Tubes & Fittings-Lot-3 | [31 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
2AP000IC04307-08000 | EOF : Delivery of Sunshade-Lot-1 | [31 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
2AP000IC04307-08005 | EOF : Delivery of Sunshade-Lot-2 | [31 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
2AP000IC04307-08010 | EOF : Delivery of Sunshade-Lot-3 | [31 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
2AP000IC04407-08000 | EOF : Delivery of Instrumentation Cable Tray- Lot-1 | [31 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
2AP000IC04407-08005 | EOF : Delivery of Instrumentation Cable Tray- Lot-2 | [31 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
2AP000IC04407-08010 | EOF : Delivery of Instrumentation Cable Tray- Lot-3 | [31 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
2AP000IC05507-08005 | EOF : Delivery of Flowmeters - Last Lot-3 | [31 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
2AP000IC06807-08100 | EOF : Delivery of Integrated Control And Safety System (ICSS) - First Lot | [31 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
2AP000MR00307-08040 | EOF: 621-G-303 A Oily Water Transfer Pump | [33 empty] | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18
2AP000MR00307-08045 | EOF: 621-G-303 B Oily Water Transfer Pump | [33 empty] | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18
2AP000MR01807-08000 | EOF: 621-G-301 A Trim Pump | [31 empty] | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28
2AP000MR01807-08005 | EOF: 621-G-301 B Trim Pump | [31 empty] | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28
2AP000MR01807-08010 | 52-GM-301A:Variable Speed Drives | [31 empty] | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28
2AP000MR01807-08015 | 52-GM-301B:Variable Speed Drives | [31 empty] | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28
2AP000MS00107-08000 | EOF: 621-V-301 Oily Water Collection Vessell | [21 empty] | 2017-04-24 | 2017-04-24 | 2017-04-24 | 2017-04-24 | 2017-04-24 | 2017-04-24 | 2017-04-24 | 2017-04-24 | 2017-04-24 | 2017-04-24 | 2017-04-24 | 2017-04-24 | 2017-04-24 | 2017-04-24 | 2017-04-24 | 2017-04-24 | 2017-04-24 | 2017-04-24 | 2017-04-24 | 2017-04-24 | 2017-04-24 | 2017-04-24 | 2017-04-24 | 2017-04-24 | 2017-04-24
2AP000MS00507-08000 | EOF: Overhead Water Tank (52-D-309 A) | [19 empty] | 2017-02-12 | 2017-02-12 | 2017-02-12 | 2017-02-12 | 2017-02-12 | 2017-02-12 | 2017-02-12 | 2017-02-12 | 2017-02-12 | 2017-02-12 | 2017-02-12 | 2017-02-12 | 2017-02-12 | 2017-02-12 | 2017-02-12 | 2017-02-12 | 2017-02-12 | 2017-02-12 | 2017-02-12 | 2017-02-12 | 2017-02-12 | 2017-02-12 | 2017-02-12 | 2017-02-12 | 2017-02-12 | 2017-02-12 | 2017-02-12
2AP000MS00507-08005 | EOF: Overhead Water Tank (52-D-309 B) | [19 empty] | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12
2AP000MS00507-08010 | EOF: Diesel Engine drain tank-52-D-304A | [19 empty] | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12
2AP000MS00507-08015 | EOF: Diesel Engine drain tank-52-D-304B | [19 empty] | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12
2AP000MS00507-08030 | EOF: Flushing Water drain tank-52-D-306A | [21 empty] | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12
2AP000MS00507-08035 | EOF: Flushing Water drain tank-52-D-306B | [21 empty] | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12 | 2017-04-12
2AP000MS00507-08040 | EOF: Water drain tank-52-D-308 A | [19 empty] | 2017-02-12 | 2017-02-12 | 2017-02-12 | 2017-02-12 | 2017-02-12 | 2017-02-12 | 2017-02-12 | 2017-02-12 | 2017-02-12 | 2017-02-12 | 2017-02-12 | 2017-02-12 | 2017-02-12 | 2017-02-12 | 2017-02-12 | 2017-02-12 | 2017-02-12 | 2017-02-12 | 2017-02-12 | 2017-02-12 | 2017-02-12 | 2017-02-12 | 2017-02-12 | 2017-02-12 | 2017-02-12 | 2017-02-12 | 2017-02-12
2AP000MS00507-08045 | EOF: Water drain tank-52-D-308 B | [19 empty] | 2017-02-12 | 2017-02-12 | 2017-02-12 | 2017-02-12 | 2017-02-12 | 2017-02-12 | 2017-02-12 | 2017-02-12 | 2017-02-12 | 2017-02-12 | 2017-02-12 | 2017-02-12 | 2017-02-12 | 2017-02-12 | 2017-02-12 | 2017-02-12 | 2017-02-12 | 2017-02-12 | 2017-02-12 | 2017-02-12 | 2017-02-12 | 2017-02-12 | 2017-02-12 | 2017-02-12 | 2017-02-12 | 2017-02-12 | 2017-02-12
2AP000MS00507-08050 | EOF: Diesel Fuel Tank 621-D307 A | [27 empty] | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02
2AP000MS00507-08055 | EOF: Diesel Fuel Tank 621-D307 B | [27 empty] | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02
2AP000MS00507-08060 | EOF: Diesel Fuel Tank 621-D307 C | [27 empty] | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02
2AP000MS00507-08065 | EOF: Diesel Fuel Tank 621-D307 D | [27 empty] | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02
2AP000MS00507-08075 | EG Building 52-R-301 : Diesel Day Tank | [29 empty] | 2017-12-30 | 2017-12-30 | 2017-12-30 | 2017-12-30 | 2017-12-30 | 2017-12-30 | 2017-12-30 | 2017-12-30 | 2017-12-30 | 2017-12-30 | 2017-12-30 | 2017-12-30 | 2017-12-30 | 2017-12-30 | 2017-12-30 | 2017-12-30 | 2017-12-30
2AP000MS00507-08085 | EG Building 52-R-303 : Diesel Day Tank | [29 empty] | 2017-12-21 | 2017-12-21 | 2017-12-21 | 2017-12-21 | 2017-12-21 | 2017-12-21 | 2017-12-21 | 2017-12-21 | 2017-12-21 | 2017-12-21 | 2017-12-21 | 2017-12-21 | 2017-12-21 | 2017-12-21 | 2017-12-21 | 2017-12-21 | 2017-12-21
2AP000MS00507-08095 | EG Building 52-R-302 : Diesel Day Tank | [29 empty] | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20
2AP000MS00507-08105 | EG Building 50-R-002 : Diesel Day Tank | [33 empty] | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15
2AP000PI00107-08000 | EOF : Delivery of CS/LTCS Pipes (Seamless) - Lot -1 | [17 empty] | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09 | 2017-01-09
2AP000PI00107-08005 | EOF : Delivery of CS/LTCS Pipes (Seamless) - Lot -2 | [25 empty] | 2017-09-17 | 2017-09-17 | 2017-09-17 | 2017-09-17 | 2017-09-17 | 2017-09-17 | 2017-09-17 | 2017-09-17 | 2017-09-17 | 2017-09-17 | 2017-09-17 | 2017-09-17 | 2017-09-17 | 2017-09-17 | 2017-09-17 | 2017-09-17 | 2017-09-17 | 2017-09-17 | 2017-09-17 | 2017-09-17 | 2017-09-17
2AP000PI00107-08010 | EOF : Delivery of CS/LTCS Pipes (Seamless) - Lot -3 | [31 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
2AP000PI00107-08015 | EOF : Delivery of CS/LTCS Pipes (Welded) - Lot -1 | [15 empty] | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05
2AP000PI00107-08020 | EOF : Delivery of CS/LTCS Pipes (Welded) - Lot -2 | [15 empty] | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05 | 2016-11-05
2AP000PI00107-08025 | EOF : Delivery of CS/LTCS Pipes (Welded) - Lot -3 | [27 empty] | 2017-09-27 | 2017-09-27 | 2017-09-27 | 2017-09-27 | 2017-09-27 | 2017-09-27 | 2017-09-27 | 2017-09-27 | 2017-09-27 | 2017-09-27 | 2017-09-27 | 2017-09-27 | 2017-09-27 | 2017-09-27 | 2017-09-27 | 2017-09-27 | 2017-09-27 | 2017-09-27 | 2017-09-27
2AP000PI00107-08030 | EOF : Delivery of SS/SDSS Pipes (Seemless) - Lot -1 | [27 empty] | 2017-11-09 | 2017-11-09 | 2017-11-09 | 2017-11-09 | 2017-11-09 | 2017-11-09 | 2017-11-09 | 2017-11-09 | 2017-11-09 | 2017-11-09 | 2017-11-09 | 2017-11-09 | 2017-11-09 | 2017-11-09 | 2017-11-09 | 2017-11-09 | 2017-11-09 | 2017-11-09 | 2017-11-09
2AP000PI00107-08035 | EOF : Delivery of SS/SDSS Pipes (Seemless) - Lot -2 | [29 empty] | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22
2AP000PI00107-08040 | EOF : Delivery of SS/SDSS Pipes (Seemless) - Lot -3 | [29 empty] | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22
2AP000PI00107-08045 | EOF : Delivery of SS/SDSS Pipes (Welded) - Lot -1 | [29 empty] | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22
2AP000PI00107-08050 | EOF : Delivery of SS/SDSS Pipes (Welded) - Lot -2 | [29 empty] | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22
2AP000PI00107-08055 | EOF : Delivery of SS/SDSS Pipes (Welded) - Lot -3 | [29 empty] | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22 | 2018-01-22
2AP000PI00207-08000 | EOF : Delivery of non-metallic pipes & fitting (GRE/ FBE/HBE) - Lot -1 | [21 empty] | 2017-05-25 | 2017-05-25 | 2017-05-25 | 2017-05-25 | 2017-05-25 | 2017-05-25 | 2017-05-25 | 2017-05-25 | 2017-05-25 | 2017-05-25 | 2017-05-25 | 2017-05-25 | 2017-05-25 | 2017-05-25 | 2017-05-25 | 2017-05-25 | 2017-05-25 | 2017-05-25 | 2017-05-25 | 2017-05-25 | 2017-05-25 | 2017-05-25 | 2017-05-25 | 2017-05-25 | 2017-05-25
2AP000PI00207-08005 | EOF : Delivery of non-metallic pipes & fitting (GRE/ FBE/HBE) - Lot -2 | [27 empty] | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01
2AP000PI00207-08010 | EOF : Delivery of non-metallic pipes & fitting (GRE/ FBE/HBE) - Lot -3 | [27 empty] | 2017-09-24 | 2017-09-24 | 2017-09-24 | 2017-09-24 | 2017-09-24 | 2017-09-24 | 2017-09-24 | 2017-09-24 | 2017-09-24 | 2017-09-24 | 2017-09-24 | 2017-09-24 | 2017-09-24 | 2017-09-24 | 2017-09-24 | 2017-09-24 | 2017-09-24 | 2017-09-24 | 2017-09-24
2AP000PI00307-08015 | EOF : Delivery of Pipe Fittings, Flanges and Blinds - Lot -1 | [19 empty] | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02
2AP000PI00307-08020 | EOF : Delivery of Pipe Fittings, Flanges and Blinds - Lot -2 | [27 empty] | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01 | 2017-10-01
2AP000PI00307-08025 | EOF : Delivery of Pipe Fittings, Flanges and Blinds - Lot -3 | [33 empty] | 2018-05-22 | 2018-05-22 | 2018-05-22 | 2018-05-22 | 2018-05-22 | 2018-05-22 | 2018-05-22 | 2018-05-22 | 2018-05-22 | 2018-05-22 | 2018-05-22 | 2018-05-22 | 2018-05-22
2AP000PI00407-08000 | EOF : Delivery of Piping Valves (Ball/GGC type) - Lot -1 | [27 empty] | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22
2AP000PI00407-08005 | EOF : Delivery of Piping Valves (Ball/GGC type) - Lot -2 | [33 empty] | 2018-04-01 | 2018-04-01 | 2018-04-01 | 2018-04-01 | 2018-04-01 | 2018-04-01 | 2018-04-01 | 2018-04-01 | 2018-04-01 | 2018-04-01 | 2018-04-01 | 2018-04-01 | 2018-04-01
2AP000PI00407-08010 | EOF : Delivery of Piping Valves (Ball/GGC type) - Lot -3 | [37 empty] | 2018-09-15 | 2018-09-15 | 2018-09-15 | 2018-09-15 | 2018-09-15 | 2018-09-15 | 2018-09-15 | 2018-09-15 | 2018-09-15
2AP000PI00407-08015 | EOF : Delivery of Other Piping Valves (Butterfly/Plug/Check/Special type) - Lot -1 | [23 empty] | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19
2AP000PI00407-08020 | EOF : Delivery of Other Piping Valves (Butterfly/Plug/Check/Special type) - Lot -2 | [31 empty] | 2018-02-13 | 2018-02-13 | 2018-02-13 | 2018-02-13 | 2018-02-13 | 2018-02-13 | 2018-02-13 | 2018-02-13 | 2018-02-13 | 2018-02-13 | 2018-02-13 | 2018-02-13 | 2018-02-13 | 2018-02-13 | 2018-02-13
2AP000PI00407-08025 | EOF : Delivery of Other Piping Valves (Butterfly/Plug/Check/Special type) - Lot -3 | [35 empty] | 2018-07-19 | 2018-07-19 | 2018-07-19 | 2018-07-19 | 2018-07-19 | 2018-07-19 | 2018-07-19 | 2018-07-19 | 2018-07-19 | 2018-07-19 | 2018-07-19
2AP000PI00507-08000 | EOF : Delivery of Piping supports (Primary) - Lot -1 | [35 empty] | 2018-06-21 | 2018-06-21 | 2018-06-21 | 2018-06-21 | 2018-06-21 | 2018-06-21 | 2018-06-21 | 2018-06-21 | 2018-06-21 | 2018-06-21 | 2018-06-21
2AP000PI00507-08005 | EOF : Delivery of Piping supports (Primary) - Lot -2 | [37 empty] | 2018-08-26 | 2018-08-26 | 2018-08-26 | 2018-08-26 | 2018-08-26 | 2018-08-26 | 2018-08-26 | 2018-08-26 | 2018-08-26
2AP000PI00507-08010 | EOF : Delivery of Piping supports (Primary) - Lot -3 | [39 empty] | 2018-10-16 | 2018-10-16 | 2018-10-16 | 2018-10-16 | 2018-10-16 | 2018-10-16 | 2018-10-16
2AP000PI00507-08015 | EOF : Delivery Of Misc. Piping Items (Gaskets/Fasteners/Springs/Strut/Hanger /Sliding Plate/Etc) - Lot -1 | [17 empty] | 2017-01-11 | 2017-01-11 | 2017-01-11 | 2017-01-11 | 2017-01-11 | 2017-01-11 | 2017-01-11 | 2017-01-11 | 2017-01-11 | 2017-01-11 | 2017-01-11 | 2017-01-11 | 2017-01-11 | 2017-01-11 | 2017-01-11 | 2017-01-11 | 2017-01-11 | 2017-01-11 | 2017-01-11 | 2017-01-11 | 2017-01-11 | 2017-01-11 | 2017-01-11 | 2017-01-11 | 2017-01-11 | 2017-01-11 | 2017-01-11 | 2017-01-11 | 2017-01-11
2AP000PI00507-08020 | EOF : Delivery Of Misc. Piping Items (Gaskets/Fasteners/Springs/Strut/Hanger /Sliding Plate/Etc) - Lot -2 | [23 empty] | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27
2AP000PI00507-08025 | EOF : Delivery Of Misc. Piping Items (Gaskets/Fasteners/Springs/Strut/Hanger /Sliding Plate/Etc) - Lot -3 | [31 empty] | 2018-03-22 | 2018-03-22 | 2018-03-22 | 2018-03-22 | 2018-03-22 | 2018-03-22 | 2018-03-22 | 2018-03-22 | 2018-03-22 | 2018-03-22 | 2018-03-22 | 2018-03-22 | 2018-03-22 | 2018-03-22 | 2018-03-22
2AP000SE00607-08000 | EOF : Delivery of Safety Signs - First Lot 1
2AP000SE00607-08005 | EOF : Delivery of Safety Signs - Lot 2
2AP000SE00607-08010 | EOF : Delivery of Safety Signs - Last Lot 3
2AP000ST00200-08000 | Structural Steel Lot - 1 | [19 empty] | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01 | 2017-03-01
2AP000ST00200-08005 | Structural Steel Lot - 2 | [19 empty] | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06
2AP000ST00200-08010 | Structural Steel Lot - 3 | [19 empty] | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06
2AP000ST00200-08015 | Steel Building material Lot - 1 | [25 empty] | 2017-09-11 | 2017-09-11 | 2017-09-11 | 2017-09-11 | 2017-09-11 | 2017-09-11 | 2017-09-11 | 2017-09-11 | 2017-09-11 | 2017-09-11 | 2017-09-11 | 2017-09-11 | 2017-09-11 | 2017-09-11 | 2017-09-11 | 2017-09-11 | 2017-09-11 | 2017-09-11 | 2017-09-11 | 2017-09-11 | 2017-09-11
2AP000ST00200-08020 | Steel Building material Lot - 2 | [27 empty] | 2017-11-04 | 2017-11-04 | 2017-11-04 | 2017-11-04 | 2017-11-04 | 2017-11-04 | 2017-11-04 | 2017-11-04 | 2017-11-04 | 2017-11-04 | 2017-11-04 | 2017-11-04 | 2017-11-04 | 2017-11-04 | 2017-11-04 | 2017-11-04 | 2017-11-04 | 2017-11-04 | 2017-11-04
2AP000ST00200-08025 | Steel Building material Lot - 3 | [27 empty] | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15
2AP000ST00707-08020 | Fencing & Gate Material Lot - 1 | [13 empty] | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24
2AP000ST00707-08025 | Fencing & Gate Material Lot - 2 | [13 empty] | 2016-08-23 | 2016-08-23 | 2016-08-23 | 2016-08-23 | 2016-08-23 | 2016-08-23 | 2016-08-23 | 2016-08-23 | 2016-08-23 | 2016-08-23 | 2016-08-23 | 2016-08-23 | 2016-08-23 | 2016-08-23 | 2016-08-23 | 2016-08-23 | 2016-08-23 | 2016-08-23 | 2016-08-23 | 2016-08-23 | 2016-08-23 | 2016-08-23 | 2016-08-23 | 2016-08-23 | 2016-08-23 | 2016-08-23 | 2016-08-23 | 2016-08-23 | 2016-08-23 | 2016-08-23 | 2016-08-23 | 2016-08-23 | 2016-08-23
2AP000ST00707-08030 | Fencing & Gate Material Lot - 3 | [25 empty] | 2017-08-23 | 2017-08-23 | 2017-08-23 | 2017-08-23 | 2017-08-23 | 2017-08-23 | 2017-08-23 | 2017-08-23 | 2017-08-23 | 2017-08-23 | 2017-08-23 | 2017-08-23 | 2017-08-23 | 2017-08-23 | 2017-08-23 | 2017-08-23 | 2017-08-23 | 2017-08-23 | 2017-08-23 | 2017-08-23 | 2017-08-23
2AP000ST00807-08005 | Gate & Crash Barrier Lot - 1 | [31 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
2AP000ST00807-08010 | Gate & Crash Barrier Lot - 2 | [31 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
2AP000ST00807-08015 | Gate & Crash Barrier Lot - 3 | [31 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
2AP000TE00107-08000 | EOF : Delivery of Telecom Equipments - First Lot | [23 empty] | 2017-07-12 | 2017-07-12 | 2017-07-12 | 2017-07-12 | 2017-07-12 | 2017-07-12 | 2017-07-12 | 2017-07-12 | 2017-07-12 | 2017-07-12 | 2017-07-12 | 2017-07-12 | 2017-07-12 | 2017-07-12 | 2017-07-12 | 2017-07-12 | 2017-07-12 | 2017-07-12 | 2017-07-12 | 2017-07-12 | 2017-07-12 | 2017-07-12 | 2017-07-12
2AP000TE00107-08005 | EOF : Delivery of Telecom Equipments - Last Lot | [27 empty] | 2017-11-12 | 2017-11-12 | 2017-11-12 | 2017-11-12 | 2017-11-12 | 2017-11-12 | 2017-11-12 | 2017-11-12 | 2017-11-12 | 2017-11-12 | 2017-11-12 | 2017-11-12 | 2017-11-12 | 2017-11-12 | 2017-11-12 | 2017-11-12 | 2017-11-12 | 2017-11-12 | 2017-11-12
2AP000TE00207-08000 | EOF:Telecom Cable - First Lot | [27 empty] | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05
2AP000TE00207-08005 | EOF:Telecom Cable -Last Lot | [37 empty] | 2018-08-13 | 2018-08-13 | 2018-08-13 | 2018-08-13 | 2018-08-13 | 2018-08-13 | 2018-08-13 | 2018-08-13 | 2018-08-13
2AP000TE00207-08010 | EOF:Delivery of Fibre Optic Cables - First Lot | [27 empty] | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05
2AP000TE00207-08015 | EOF:Delivery of Fibre Optic Cables-Last Lot | [31 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
2AP000TE00207-08020 | EOF: Miscellaneous Telecom Items - First Lot | [23 empty] | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03 | 2017-07-03
2AP000TE00207-08025 | EOF: Miscellaneous Telecom Items-Last Lot | [31 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
2AP100CV08100-08000 | Submition & Approval of RAM FOR HYSD BARS | [5 empty] | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28 | 2015-12-28
2AP100CV08100-08005 | Submition & Approval of RAM FOR CAP PRIME & CAP SEAL | time axis 2015-10-22 to 2015-10-22
2AP100CV08100-08010 | Submition & Approval of RAM FOR CEMENT (OPC & SRPC) | time axis 2015-10-27 to 2015-10-27
2AP100CV08100-08015 | Submition & Approval of RAM FOR POLYTHENE SHEET | time axis 2015-10-27 to 2015-10-27
2AP100CV08100-08020 | Submition & Approval of RAM FOR BITUMENT FILLER BOARD (Jolly Bitulex) | time axis 2015-10-27 to 2015-10-27
2AP100CV08100-08025 | Submition & Approval of RAM FOR RELEASEFORM | time axis 2015-10-27 to 2015-10-27
2AP100CV08100-08030 | Submition & Approval of RAM FOR REPAIR CEMENT/CHEMICAL etc (FORSOC) | time axis 2015-10-27 to 2015-10-27
2AP100CV08100-08035 | Submition & Approval of RAM FOR HEMPADUR 85671 (EPOXY COATING) | time axis 2015-11-04 to 2015-11-04
2AP100CV08100-08040 | Submition & Approval of RAM FOR PG-10 (POLYSHILPIDE SEALENT) | time axis 2015-11-04 to 2015-11-04
2AP100CV08100-08045 | Submition & Approval of RAM FOR HEMPADUR MASTIC 45881/45880 | time axis 2015-11-04 to 2015-11-04
2AP100CV08100-08050 | Submition & Approval of RAM FOR CONBEXTRA GP (NON-SHRINK GROUT) | [5 empty] | 2016-01-17 | 2016-01-17 | 2016-01-17 | 2016-01-17 | 2016-01-17 | 2016-01-17 | 2016-01-17 | 2016-01-17 | 2016-01-17 | 2016-01-17 | 2016-01-17 | 2016-01-17 | 2016-01-17 | 2016-01-17 | 2016-01-17 | 2016-01-17 | 2016-01-17 | 2016-01-17 | 2016-01-17 | 2016-01-17 | 2016-01-17 | 2016-01-17 | 2016-01-17 | 2016-01-17 | 2016-01-17 | 2016-01-17 | 2016-01-17 | 2016-01-17 | 2016-01-17 | 2016-01-17 | 2016-01-17 | 2016-01-17 | 2016-01-17 | 2016-01-17 | 2016-01-17 | 2016-01-17 | 2016-01-17 | 2016-01-17 | 2016-01-17 | 2016-01-17 | 2016-01-17
2AP100CV08100-08055 | Submition & Approval of RAM FOR BINDING WIRE FOR REINFORCEMENT | time axis 2015-11-19 to 2015-11-19
2AP100CV08100-08060 | Submition & Approval of RAM FOR CHAIN LINK FENCE | [11 empty] | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02 | 2016-07-02
2AP100CV08100-08065 | Submition & Approval of RAM FOR HIGH SECURITY FENCE | [15 empty] | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03 | 2016-11-03
2AP100CV08100-08070 | Submition & Approval of RAM FOR HAND HOLE AND MANHOLE COVERS | [15 empty] | 2016-10-05 | 2016-10-05 | 2016-10-05 | 2016-10-05 | 2016-10-05 | 2016-10-05 | 2016-10-05 | 2016-10-05 | 2016-10-05 | 2016-10-05 | 2016-10-05 | 2016-10-05 | 2016-10-05 | 2016-10-05 | 2016-10-05 | 2016-10-05 | 2016-10-05 | 2016-10-05 | 2016-10-05 | 2016-10-05 | 2016-10-05 | 2016-10-05 | 2016-10-05 | 2016-10-05 | 2016-10-05 | 2016-10-05 | 2016-10-05 | 2016-10-05 | 2016-10-05 | 2016-10-05 | 2016-10-05
2AP100CV08100-08075 | Submition & Approval of RAM FOR ROAD ASPHALT | [15 empty] | 2016-11-15 | 2016-11-15 | 2016-11-15 | 2016-11-15 | 2016-11-15 | 2016-11-15 | 2016-11-15 | 2016-11-15 | 2016-11-15 | 2016-11-15 | 2016-11-15 | 2016-11-15 | 2016-11-15 | 2016-11-15 | 2016-11-15 | 2016-11-15 | 2016-11-15 | 2016-11-15 | 2016-11-15 | 2016-11-15 | 2016-11-15 | 2016-11-15 | 2016-11-15 | 2016-11-15 | 2016-11-15 | 2016-11-15 | 2016-11-15 | 2016-11-15 | 2016-11-15 | 2016-11-15 | 2016-11-15
2AP100EL08100-08100 | Submition & Approval of RAM FOR CONCRETE CABLE TILE {FOR U/G CABLE PROTECTION) | [5 empty] | 2015-12-02 | 2015-12-02 | 2015-12-02 | 2015-12-02 | 2015-12-02 | 2015-12-02 | 2015-12-02 | 2015-12-02 | 2015-12-02 | 2015-12-02 | 2015-12-02 | 2015-12-02 | 2015-12-02 | 2015-12-02 | 2015-12-02 | 2015-12-02 | 2015-12-02 | 2015-12-02 | 2015-12-02 | 2015-12-02 | 2015-12-02 | 2015-12-02 | 2015-12-02 | 2015-12-02 | 2015-12-02 | 2015-12-02 | 2015-12-02 | 2015-12-02 | 2015-12-02 | 2015-12-02 | 2015-12-02 | 2015-12-02 | 2015-12-02 | 2015-12-02 | 2015-12-02 | 2015-12-02 | 2015-12-02 | 2015-12-02 | 2015-12-02 | 2015-12-02 | 2015-12-02
2AP100MS08100-08080 | Submition & Approval of RAM for Welding Consumables | [7 empty] | 2016-03-19 | 2016-03-19 | 2016-03-19 | 2016-03-19 | 2016-03-19 | 2016-03-19 | 2016-03-19 | 2016-03-19 | 2016-03-19 | 2016-03-19 | 2016-03-19 | 2016-03-19 | 2016-03-19 | 2016-03-19 | 2016-03-19 | 2016-03-19 | 2016-03-19 | 2016-03-19 | 2016-03-19 | 2016-03-19 | 2016-03-19 | 2016-03-19 | 2016-03-19 | 2016-03-19 | 2016-03-19 | 2016-03-19 | 2016-03-19 | 2016-03-19 | 2016-03-19 | 2016-03-19 | 2016-03-19 | 2016-03-19 | 2016-03-19 | 2016-03-19 | 2016-03-19 | 2016-03-19 | 2016-03-19 | 2016-03-19 | 2016-03-19
2AP100MS08100-08085 | Submition & Approval of RAM for Coating Material | [11 empty] | 2016-06-02 | 2016-06-02 | 2016-06-02 | 2016-06-02 | 2016-06-02 | 2016-06-02 | 2016-06-02 | 2016-06-02 | 2016-06-02 | 2016-06-02 | 2016-06-02 | 2016-06-02 | 2016-06-02 | 2016-06-02 | 2016-06-02 | 2016-06-02 | 2016-06-02 | 2016-06-02 | 2016-06-02 | 2016-06-02 | 2016-06-02 | 2016-06-02 | 2016-06-02 | 2016-06-02 | 2016-06-02 | 2016-06-02 | 2016-06-02 | 2016-06-02 | 2016-06-02 | 2016-06-02 | 2016-06-02 | 2016-06-02 | 2016-06-02 | 2016-06-02 | 2016-06-02
2AP100MS08100-08090 | Submition & Approval of RAM for Painting Material | [9 empty] | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17
2AP100MS08100-08095 | Submition & Approval of RAM for Abrasive Blasting Material (Garnet) | [9 empty] | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17
2AP100MS08100-08105 | Submition & Approval of RAM for Fireproofing Meerial | [31 empty] | 2018-03-14 | 2018-03-14 | 2018-03-14 | 2018-03-14 | 2018-03-14 | 2018-03-14 | 2018-03-14 | 2018-03-14 | 2018-03-14 | 2018-03-14 | 2018-03-14 | 2018-03-14 | 2018-03-14 | 2018-03-14 | 2018-03-14
2AP100MS08100-08115 | Submition & Approval of RAM for Pipe Insulation Material (Heat Conservation) | [31 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
2AP100MS08100-08125 | Submition & Approval of RAM for Pipe Insulation Material (Personnel Protection) | [35 empty] | 2018-06-12 | 2018-06-12 | 2018-06-12 | 2018-06-12 | 2018-06-12 | 2018-06-12 | 2018-06-12 | 2018-06-12 | 2018-06-12 | 2018-06-12 | 2018-06-12
2AR000TF10001-08000 | Layout for Sub-contractor Site office & laydown Area | time axis 2015-08-17 to 2015-08-17
2AR000TF10001-08005 | Sanitary & Plumbing Layout | time axis 2015-08-17 to 2015-08-17
2AR000TF10001-08010 | Sub-contractor Site office Layout | time axis 2015-08-17 to 2015-08-17
2AR000TF10001-08015 | External Electrical Service Layout for Site office & Laydown Area | time axis 2015-08-31 to 2015-08-31
2AR000TF10001-08020 | Lighting Layout for sub-contractor Main Site office | time axis 2015-08-31 to 2015-08-31
2AR000TF10001-08025 | Small Power Layout for Contractor Main Site office | time axis 2015-08-31 to 2015-08-31
2AR000TF10001-08030 | Fire Alarm Layout for Sub Contractor Main Site office | time axis 2015-08-31 to 2015-08-31
2AR000TF10001-08035 | Electrical Single Line Diagram | time axis 2015-08-31 to 2015-08-31
2AR000TF10001-08040 | Electrical Load Schedule | time axis 2015-08-31 to 2015-08-31
BLK-CP-DE04-1000 | [38 empty] | 2018-09-25 | 2018-09-25 | 2018-09-25 | 2018-09-25 | 2018-09-25 | 2018-09-25 | 2018-09-25 | 2018-09-25 | 2018-09-25
BLK-CP-DE04-1001 | [38 empty] | 2018-08-05 | 2018-08-05 | 2018-08-05 | 2018-08-05 | 2018-08-05 | 2018-08-05 | 2018-08-05 | 2018-08-05 | 2018-08-05
BLK-CP-DE04-1002 | [34 empty] | 2018-04-12 | 2018-04-12 | 2018-04-12 | 2018-04-12 | 2018-04-12 | 2018-04-12 | 2018-04-12 | 2018-04-12 | 2018-04-12 | 2018-04-12 | 2018-04-12 | 2018-04-12 | 2018-04-12
BLK-ELE-DE01-1001 | [24 empty] | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25
BLK-ELE-DE01-1002 | [22 empty] | 2017-05-03 | 2017-05-03 | 2017-05-03 | 2017-05-03 | 2017-05-03 | 2017-05-03 | 2017-05-03 | 2017-05-03 | 2017-05-03 | 2017-05-03 | 2017-05-03 | 2017-05-03 | 2017-05-03 | 2017-05-03 | 2017-05-03 | 2017-05-03 | 2017-05-03 | 2017-05-03 | 2017-05-03 | 2017-05-03 | 2017-05-03 | 2017-05-03 | 2017-05-03 | 2017-05-03 | 2017-05-03
BLK-ELE-DE01-1005 | [26 empty] | 2017-08-07 | 2017-08-07 | 2017-08-07 | 2017-08-07 | 2017-08-07 | 2017-08-07 | 2017-08-07 | 2017-08-07 | 2017-08-07 | 2017-08-07 | 2017-08-07 | 2017-08-07 | 2017-08-07 | 2017-08-07 | 2017-08-07 | 2017-08-07 | 2017-08-07 | 2017-08-07 | 2017-08-07 | 2017-08-07 | 2017-08-07
BLK-ELE-DE01-1007 | [28 empty] | 2017-10-06 | 2017-10-06 | 2017-10-06 | 2017-10-06 | 2017-10-06 | 2017-10-06 | 2017-10-06 | 2017-10-06 | 2017-10-06 | 2017-10-06 | 2017-10-06 | 2017-10-06 | 2017-10-06 | 2017-10-06 | 2017-10-06 | 2017-10-06 | 2017-10-06 | 2017-10-06 | 2017-10-06
BLK-ELE-DE01-1008 | [28 empty] | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05
BLK-ELE-DE01-1010 | [32 empty] | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27
BLK-ELE-DE01-1011 | [30 empty] | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05
BLK-ELE-DE01-1014 | [28 empty] | 2017-11-19 | 2017-11-19 | 2017-11-19 | 2017-11-19 | 2017-11-19 | 2017-11-19 | 2017-11-19 | 2017-11-19 | 2017-11-19 | 2017-11-19 | 2017-11-19 | 2017-11-19 | 2017-11-19 | 2017-11-19 | 2017-11-19 | 2017-11-19 | 2017-11-19 | 2017-11-19 | 2017-11-19
BLK-ELE-DE01-1017 | [28 empty] | 2017-11-19: 2018-10-31; 2017-11-19: 2018-10-31; 2017-11-19: 2018-10-31; 2017-11-19: 2018-10-31; 2017-11-19: 2018-10-31; 2017-11-19: 2018-10-31; 2017-11-19: 2018-10-31
BLK-ELE-DE01-1023 | [28 empty] | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06 | 2017-11-06
BLK-ELE-DE01-1025 | [34 empty] | 2018-05-08 | 2018-05-08 | 2018-05-08 | 2018-05-08 | 2018-05-08 | 2018-05-08 | 2018-05-08 | 2018-05-08 | 2018-05-08 | 2018-05-08 | 2018-05-08 | 2018-05-08 | 2018-05-08
BLK-ELE-DE01-1026 | [24 empty] | 2017-07-26 | 2017-07-26 | 2017-07-26 | 2017-07-26 | 2017-07-26 | 2017-07-26 | 2017-07-26 | 2017-07-26 | 2017-07-26 | 2017-07-26 | 2017-07-26 | 2017-07-26 | 2017-07-26 | 2017-07-26 | 2017-07-26 | 2017-07-26 | 2017-07-26 | 2017-07-26 | 2017-07-26 | 2017-07-26 | 2017-07-26 | 2017-07-26 | 2017-07-26
BLK-ELE-DE01-1027 | [24 empty] | 2017-07-26: 2018-12-12; 2017-07-26: 2018-12-12; 2017-07-26: 2018-12-12; 2017-07-26: 2018-12-12; 2017-07-26: 2018-12-12
BLK-ELE-DE01-1028 | [24 empty] | 2017-07-26: 2018-12-12; 2017-07-26: 2018-12-12; 2017-07-26: 2018-12-12; 2017-07-26: 2018-12-12; 2017-07-26: 2018-12-12
BLK-ELE-DE01-1029 | [38 empty] | 2018-08-20 | 2018-08-20 | 2018-08-20 | 2018-08-20 | 2018-08-20 | 2018-08-20 | 2018-08-20 | 2018-08-20 | 2018-08-20
BLK-ELE-DE01-1030 | [40 empty] | 2018-10-13 | 2018-10-13 | 2018-10-13 | 2018-10-13 | 2018-10-13 | 2018-10-13 | 2018-10-13
BLK-ELE-DE01-1031 | [36 empty] | 2018-06-28 | 2018-06-28 | 2018-06-28 | 2018-06-28 | 2018-06-28 | 2018-06-28 | 2018-06-28 | 2018-06-28 | 2018-06-28 | 2018-06-28 | 2018-06-28
BLK-INSTR-DE02-1002 | [24 empty] | 2017-07-12 | 2017-07-12 | 2017-07-12 | 2017-07-12 | 2017-07-12 | 2017-07-12 | 2017-07-12 | 2017-07-12 | 2017-07-12 | 2017-07-12 | 2017-07-12 | 2017-07-12 | 2017-07-12 | 2017-07-12 | 2017-07-12 | 2017-07-12 | 2017-07-12 | 2017-07-12 | 2017-07-12 | 2017-07-12 | 2017-07-12 | 2017-07-12 | 2017-07-12
BLK-INSTR-DE02-1004 | [30 empty] | 2017-12-02 | 2017-12-02 | 2017-12-02 | 2017-12-02 | 2017-12-02 | 2017-12-02 | 2017-12-02 | 2017-12-02 | 2017-12-02 | 2017-12-02 | 2017-12-02 | 2017-12-02 | 2017-12-02 | 2017-12-02 | 2017-12-02 | 2017-12-02 | 2017-12-02
BLK-INSTR-DE02-1005 | [24 empty] | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09
BLK-INSTR-DE02-1008 | [30 empty] | 2018-01-18 | 2018-01-18 | 2018-01-18 | 2018-01-18 | 2018-01-18 | 2018-01-18 | 2018-01-18 | 2018-01-18 | 2018-01-18 | 2018-01-18 | 2018-01-18 | 2018-01-18 | 2018-01-18 | 2018-01-18 | 2018-01-18 | 2018-01-18 | 2018-01-18
BLK-INSTR-DE02-1011 | [30 empty] | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06 | 2018-01-06
BLK-INSTR-DE02-1014 | [30 empty] | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27
BLK-INSTR-DE02-1017 | [30 empty] | 2017-11-27: 2018-12-23; 2017-11-27: 2018-12-23; 2017-11-27: 2018-12-23; 2017-11-27: 2018-12-23; 2017-11-27: 2018-12-23
BLK-INSTR-DE02-1020 | [34 empty] | 2018-04-12 | 2018-04-12 | 2018-04-12 | 2018-04-12 | 2018-04-12 | 2018-04-12 | 2018-04-12 | 2018-04-12 | 2018-04-12 | 2018-04-12 | 2018-04-12 | 2018-04-12 | 2018-04-12
BLK-INSTR-DE02-1021 | [34 empty] | 2018-04-12: 2018-12-12; 2018-04-12: 2018-12-12; 2018-04-12: 2018-12-12; 2018-04-12: 2018-12-12; 2018-04-12: 2018-12-12
BLK-INSTR-DE02-1022 | [34 empty] | 2018-04-12: 2018-12-12; 2018-04-12: 2018-12-12; 2018-04-12: 2018-12-12; 2018-04-12: 2018-12-12; 2018-04-12: 2018-12-12
BLK-INSTR-DE02-1023 | [34 empty] | 2018-04-12: 2018-12-12; 2018-04-12: 2018-12-12; 2018-04-12: 2018-12-12; 2018-04-12: 2018-12-12; 2018-04-12: 2018-12-12
BLK-INSTR-DE02-1024 | [38 empty] | 2018-08-25 | 2018-08-25 | 2018-08-25 | 2018-08-25 | 2018-08-25 | 2018-08-25 | 2018-08-25 | 2018-08-25 | 2018-08-25
BLK-INSTR-DE02-1025 | [38 empty] | 2018-08-05 | 2018-08-05 | 2018-08-05 | 2018-08-05 | 2018-08-05 | 2018-08-05 | 2018-08-05 | 2018-08-05 | 2018-08-05
BLK-INSTR-DE02-1026 | [38 empty] | 2018-08-05 | 2018-08-05 | 2018-08-05 | 2018-08-05 | 2018-08-05 | 2018-08-05 | 2018-08-05 | 2018-08-05 | 2018-08-05
BLK-INSTR-DE02-1027 | [38 empty] | 2018-08-05 | 2018-08-05 | 2018-08-05 | 2018-08-05 | 2018-08-05 | 2018-08-05 | 2018-08-05 | 2018-08-05 | 2018-08-05
BLK-TEL-DE03-1001 | [26 empty] | 2017-09-01 | 2017-09-01 | 2017-09-01 | 2017-09-01 | 2017-09-01 | 2017-09-01 | 2017-09-01 | 2017-09-01 | 2017-09-01 | 2017-09-01 | 2017-09-01 | 2017-09-01 | 2017-09-01 | 2017-09-01 | 2017-09-01 | 2017-09-01 | 2017-09-01 | 2017-09-01 | 2017-09-01 | 2017-09-01 | 2017-09-01
BLK-TEL-DE03-1003 | [28 empty] | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05
BLK-TEL-DE03-1005 | [30 empty] | 2017-12-30 | 2017-12-30 | 2017-12-30 | 2017-12-30 | 2017-12-30 | 2017-12-30 | 2017-12-30 | 2017-12-30 | 2017-12-30 | 2017-12-30 | 2017-12-30 | 2017-12-30 | 2017-12-30 | 2017-12-30 | 2017-12-30 | 2017-12-30 | 2017-12-30
CIV-COCC-DE01-1000 | [30 empty] | 2017-12-30: 2018-11-27; 2017-12-30: 2018-11-27; 2017-12-30: 2018-11-27; 2017-12-30: 2018-11-27; 2017-12-30: 2018-11-27
CIV-COCC-DE01-1010 | [24 empty] | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31
CIV-COCC-DE01-1020 | [24 empty] | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31
CIV-COCC-DE01-1040 | [20 empty] | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21
CIV-CON-DE01-1000 | [14 empty] | 2016-08-31 | 2016-08-31 | 2016-08-31 | 2016-08-31 | 2016-08-31 | 2016-08-31 | 2016-08-31 | 2016-08-31 | 2016-08-31 | 2016-08-31 | 2016-08-31 | 2016-08-31 | 2016-08-31 | 2016-08-31 | 2016-08-31 | 2016-08-31 | 2016-08-31 | 2016-08-31 | 2016-08-31 | 2016-08-31 | 2016-08-31 | 2016-08-31 | 2016-08-31 | 2016-08-31 | 2016-08-31 | 2016-08-31 | 2016-08-31 | 2016-08-31 | 2016-08-31 | 2016-08-31 | 2016-08-31 | 2016-08-31 | 2016-08-31
CIV-CON-DE01-1001 | [16 empty] | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18
CIV-CON-DE01-1002 | [16 empty] | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18 | 2016-10-18
CIV-CON-DE01-1003 | [16 empty] | 2016-11-14 | 2016-11-14 | 2016-11-14 | 2016-11-14 | 2016-11-14 | 2016-11-14 | 2016-11-14 | 2016-11-14 | 2016-11-14 | 2016-11-14 | 2016-11-14 | 2016-11-14 | 2016-11-14 | 2016-11-14 | 2016-11-14 | 2016-11-14 | 2016-11-14 | 2016-11-14 | 2016-11-14 | 2016-11-14 | 2016-11-14 | 2016-11-14 | 2016-11-14 | 2016-11-14 | 2016-11-14 | 2016-11-14 | 2016-11-14 | 2016-11-14 | 2016-11-14 | 2016-11-14 | 2016-11-14
CIV-CON-DE01-1004 | [16 empty] | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20
CIV-CON-DE01-1007 | [18 empty] | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24 | 2016-12-24
CIV-CON-DE01-1008 | [16 empty] | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07
CIV-CON-DE01-1009 | [18 empty] | 2016-12-18 | 2016-12-18 | 2016-12-18 | 2016-12-18 | 2016-12-18 | 2016-12-18 | 2016-12-18 | 2016-12-18 | 2016-12-18 | 2016-12-18 | 2016-12-18 | 2016-12-18 | 2016-12-18 | 2016-12-18 | 2016-12-18 | 2016-12-18 | 2016-12-18 | 2016-12-18 | 2016-12-18 | 2016-12-18 | 2016-12-18 | 2016-12-18 | 2016-12-18 | 2016-12-18 | 2016-12-18 | 2016-12-18 | 2016-12-18 | 2016-12-18 | 2016-12-18
CIV-CON-DE01-1010 | [20 empty] | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21
CIV-CON-DE01-1011 | [20 empty] | 2017-03-20 | 2017-03-20 | 2017-03-20 | 2017-03-20 | 2017-03-20 | 2017-03-20 | 2017-03-20 | 2017-03-20 | 2017-03-20 | 2017-03-20 | 2017-03-20 | 2017-03-20 | 2017-03-20 | 2017-03-20 | 2017-03-20 | 2017-03-20 | 2017-03-20 | 2017-03-20 | 2017-03-20 | 2017-03-20 | 2017-03-20 | 2017-03-20 | 2017-03-20 | 2017-03-20 | 2017-03-20 | 2017-03-20 | 2017-03-20
CIV-CON-DE01-1012 | [26 empty] | 2017-08-15 | 2017-08-15 | 2017-08-15 | 2017-08-15 | 2017-08-15 | 2017-08-15 | 2017-08-15 | 2017-08-15 | 2017-08-15 | 2017-08-15 | 2017-08-15 | 2017-08-15 | 2017-08-15 | 2017-08-15 | 2017-08-15 | 2017-08-15 | 2017-08-15 | 2017-08-15 | 2017-08-15 | 2017-08-15 | 2017-08-15
CIV-CON-DE01-1013 | [18 empty] | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07
CIV-CON-DE01-1015 | [18 empty] | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29
CIV-CON-DE01-1016 | [24 empty] | 2017-07-15 | 2017-07-15 | 2017-07-15 | 2017-07-15 | 2017-07-15 | 2017-07-15 | 2017-07-15 | 2017-07-15 | 2017-07-15 | 2017-07-15 | 2017-07-15 | 2017-07-15 | 2017-07-15 | 2017-07-15 | 2017-07-15 | 2017-07-15 | 2017-07-15 | 2017-07-15 | 2017-07-15 | 2017-07-15 | 2017-07-15 | 2017-07-15 | 2017-07-15
CIV-CON-DE02-1000 | [8 empty] | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18
CIV-CON-DE02-1001 | [8 empty] | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18
CIV-CON-DE02-1002 | [8 empty] | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18 | 2016-02-18
CIV-CON-DE02-1003 | [10 empty] | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17
CIV-CON-DE02-1004 | [10 empty] | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17 | 2016-05-17
CIV-CON-DE02-1005 | [20 empty] | 2017-02-03 | 2017-02-03 | 2017-02-03 | 2017-02-03 | 2017-02-03 | 2017-02-03 | 2017-02-03 | 2017-02-03 | 2017-02-03 | 2017-02-03 | 2017-02-03 | 2017-02-03 | 2017-02-03 | 2017-02-03 | 2017-02-03 | 2017-02-03 | 2017-02-03 | 2017-02-03 | 2017-02-03 | 2017-02-03 | 2017-02-03 | 2017-02-03 | 2017-02-03 | 2017-02-03 | 2017-02-03 | 2017-02-03 | 2017-02-03
CIV-CON-DE02-1006 | [20 empty] | 2017-02-03 | 2017-02-03 | 2017-02-03 | 2017-02-03 | 2017-02-03 | 2017-02-03 | 2017-02-03 | 2017-02-03 | 2017-02-03 | 2017-02-03 | 2017-02-03 | 2017-02-03 | 2017-02-03 | 2017-02-03 | 2017-02-03 | 2017-02-03 | 2017-02-03 | 2017-02-03 | 2017-02-03 | 2017-02-03 | 2017-02-03 | 2017-02-03 | 2017-02-03 | 2017-02-03 | 2017-02-03 | 2017-02-03 | 2017-02-03
CIV-CON-DE02-1007 | [24 empty] | 2017-07-04 | 2017-07-04 | 2017-07-04 | 2017-07-04 | 2017-07-04 | 2017-07-04 | 2017-07-04 | 2017-07-04 | 2017-07-04 | 2017-07-04 | 2017-07-04 | 2017-07-04 | 2017-07-04 | 2017-07-04 | 2017-07-04 | 2017-07-04 | 2017-07-04 | 2017-07-04 | 2017-07-04 | 2017-07-04 | 2017-07-04 | 2017-07-04 | 2017-07-04
CIV-CON-DE02-1008 | [24 empty] | 2017-06-23 | 2017-06-23 | 2017-06-23 | 2017-06-23 | 2017-06-23 | 2017-06-23 | 2017-06-23 | 2017-06-23 | 2017-06-23 | 2017-06-23 | 2017-06-23 | 2017-06-23 | 2017-06-23 | 2017-06-23 | 2017-06-23 | 2017-06-23 | 2017-06-23 | 2017-06-23 | 2017-06-23 | 2017-06-23 | 2017-06-23 | 2017-06-23 | 2017-06-23
CIV-CON-DE02-1009 | [24 empty] | 2017-06-28 | 2017-06-28 | 2017-06-28 | 2017-06-28 | 2017-06-28 | 2017-06-28 | 2017-06-28 | 2017-06-28 | 2017-06-28 | 2017-06-28 | 2017-06-28 | 2017-06-28 | 2017-06-28 | 2017-06-28 | 2017-06-28 | 2017-06-28 | 2017-06-28 | 2017-06-28 | 2017-06-28 | 2017-06-28 | 2017-06-28 | 2017-06-28 | 2017-06-28
CIV-CON-DE02-1010 | [24 empty] | 2017-06-15 | 2017-06-15 | 2017-06-15 | 2017-06-15 | 2017-06-15 | 2017-06-15 | 2017-06-15 | 2017-06-15 | 2017-06-15 | 2017-06-15 | 2017-06-15 | 2017-06-15 | 2017-06-15 | 2017-06-15 | 2017-06-15 | 2017-06-15 | 2017-06-15 | 2017-06-15 | 2017-06-15 | 2017-06-15 | 2017-06-15 | 2017-06-15 | 2017-06-15
CIV-CON-DE02-1012 | [22 empty] | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06
CIV-CON-DE02-1013 | [22 empty] | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06
CIV-CON-DE02-1014 | [22 empty] | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06
CIV-CON-DE02-1015 | [24 empty] | 2017-07-08 | 2017-07-08 | 2017-07-08 | 2017-07-08 | 2017-07-08 | 2017-07-08 | 2017-07-08 | 2017-07-08 | 2017-07-08 | 2017-07-08 | 2017-07-08 | 2017-07-08 | 2017-07-08 | 2017-07-08 | 2017-07-08 | 2017-07-08 | 2017-07-08 | 2017-07-08 | 2017-07-08 | 2017-07-08 | 2017-07-08 | 2017-07-08 | 2017-07-08
CIV-CON-DE02-1016 | [22 empty] | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14
CIV-CON-DE02-1018 | [22 empty] | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14
CIV-CON-DE02-1019 | [22 empty] | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14
CIV-CON-DE02-1020 | [22 empty] | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14
CIV-CON-DE02-1021 | [22 empty] | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14
CIV-CON-DE02-1022 | [22 empty] | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14 | 2017-05-14
CIV-CON-DE02-1023 | [22 empty] | 2017-05-16 | 2017-05-16 | 2017-05-16 | 2017-05-16 | 2017-05-16 | 2017-05-16 | 2017-05-16 | 2017-05-16 | 2017-05-16 | 2017-05-16 | 2017-05-16 | 2017-05-16 | 2017-05-16 | 2017-05-16 | 2017-05-16 | 2017-05-16 | 2017-05-16 | 2017-05-16 | 2017-05-16 | 2017-05-16 | 2017-05-16 | 2017-05-16 | 2017-05-16 | 2017-05-16 | 2017-05-16
CIV-CON-DE02-1024 | [24 empty] | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10
CIV-PIP-DE03-A1000 | [36 empty] | 2018-07-25 | 2018-07-25 | 2018-07-25 | 2018-07-25 | 2018-07-25 | 2018-07-25 | 2018-07-25 | 2018-07-25 | 2018-07-25 | 2018-07-25 | 2018-07-25
CIV-PIP-DE03-A1010 | [38 empty] | 2018-08-24 | 2018-08-24 | 2018-08-24 | 2018-08-24 | 2018-08-24 | 2018-08-24 | 2018-08-24 | 2018-08-24 | 2018-08-24
CIV-PIP-DE03-A1020 | [38 empty] | 2018-09-15 | 2018-09-15 | 2018-09-15 | 2018-09-15 | 2018-09-15 | 2018-09-15 | 2018-09-15 | 2018-09-15 | 2018-09-15
CIV-PIP-DE03-A1030 | [40 empty] | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30 | 2018-09-30
CIV-STF-DE02-1000 | [28 empty] | 2017-10-24 | 2017-10-24 | 2017-10-24 | 2017-10-24 | 2017-10-24 | 2017-10-24 | 2017-10-24 | 2017-10-24 | 2017-10-24 | 2017-10-24 | 2017-10-24 | 2017-10-24 | 2017-10-24 | 2017-10-24 | 2017-10-24 | 2017-10-24 | 2017-10-24 | 2017-10-24 | 2017-10-24
CIV-STF-DE02-1010 | [10 empty] | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25
CIV-STF-DE02-1020 | [10 empty] | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25
CIV-STF-DE02-1030 | [20 empty] | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21
CIV-STF-DE02-1040 | [30 empty] | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06
CIV-STF-DE02-1050 | [24 empty] | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27
CIV-STF-DE02-1060 | [34 empty] | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06
CIV-STF-DE02-1070 | [20 empty] | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21
CIV-STF-DE02-1080 | [24 empty] | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24
CIV-STF-DE02-1090 | [28 empty] | 2017-10-23 | 2017-10-23 | 2017-10-23 | 2017-10-23 | 2017-10-23 | 2017-10-23 | 2017-10-23 | 2017-10-23 | 2017-10-23 | 2017-10-23 | 2017-10-23 | 2017-10-23 | 2017-10-23 | 2017-10-23 | 2017-10-23 | 2017-10-23 | 2017-10-23 | 2017-10-23 | 2017-10-23
CIV-STF-DE02-1100 | [24 empty] | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09
CIV-STF-DE02-1110 | [28 empty] | 2017-11-18 | 2017-11-18 | 2017-11-18 | 2017-11-18 | 2017-11-18 | 2017-11-18 | 2017-11-18 | 2017-11-18 | 2017-11-18 | 2017-11-18 | 2017-11-18 | 2017-11-18 | 2017-11-18 | 2017-11-18 | 2017-11-18 | 2017-11-18 | 2017-11-18 | 2017-11-18 | 2017-11-18
CIV-STF-DE02-1120 | [24 empty] | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24
CIV-STF-DE02-1130 | [24 empty] | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24
CIV-STF-DE02-1140 | [20 empty] | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21
CIV-STF-DE02-1150 | [18 empty] | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17 | 2017-01-17
CIV-STF-DE02-1160 | [20 empty] | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21
CIV-STF-DE02-1170 | [24 empty] | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31
CIV-STF-DE02-1180 | [24 empty] | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01
CIV-STF-DE02-1190 | [20 empty] | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21 | 2017-03-21
CIV-STF-DE02-1210 | [24 empty] | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31
CIV-STF-DE02-1220 | [28 empty] | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18
CIV-STF-DE02-1230 | [14 empty] | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25 | 2016-07-25
CIV-STF-DE02-1240 | [28 empty] | 2017-10-24 | 2017-10-24 | 2017-10-24 | 2017-10-24 | 2017-10-24 | 2017-10-24 | 2017-10-24 | 2017-10-24 | 2017-10-24 | 2017-10-24 | 2017-10-24 | 2017-10-24 | 2017-10-24 | 2017-10-24 | 2017-10-24 | 2017-10-24 | 2017-10-24 | 2017-10-24 | 2017-10-24
CIV-STF-DE02-1250 | [24 empty] | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01
CIV-STF-DE02-1260 | [22 empty] | 2017-05-22 | 2017-05-22 | 2017-05-22 | 2017-05-22 | 2017-05-22 | 2017-05-22 | 2017-05-22 | 2017-05-22 | 2017-05-22 | 2017-05-22 | 2017-05-22 | 2017-05-22 | 2017-05-22 | 2017-05-22 | 2017-05-22 | 2017-05-22 | 2017-05-22 | 2017-05-22 | 2017-05-22 | 2017-05-22 | 2017-05-22 | 2017-05-22 | 2017-05-22 | 2017-05-22 | 2017-05-22
CIV-STF-DE02-1270 | [10 empty] | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11
CP-STF-DE03-A1000 | [14 empty] | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31
DE25-1000 | [10 empty] | 2016-05-10 | 2016-05-10 | 2016-05-10 | 2016-05-10 | 2016-05-10 | 2016-05-10 | 2016-05-10 | 2016-05-10 | 2016-05-10 | 2016-05-10 | 2016-05-10 | 2016-05-10 | 2016-05-10 | 2016-05-10 | 2016-05-10 | 2016-05-10 | 2016-05-10 | 2016-05-10 | 2016-05-10 | 2016-05-10 | 2016-05-10 | 2016-05-10 | 2016-05-10 | 2016-05-10 | 2016-05-10 | 2016-05-10 | 2016-05-10 | 2016-05-10 | 2016-05-10 | 2016-05-10 | 2016-05-10 | 2016-05-10 | 2016-05-10 | 2016-05-10 | 2016-05-10 | 2016-05-10 | 2016-05-10
DE26-1000 | [10 empty] | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27 | 2016-04-27
DE27-1000 | [8 empty] | 2016-03-17 | 2016-03-17 | 2016-03-17 | 2016-03-17 | 2016-03-17 | 2016-03-17 | 2016-03-17 | 2016-03-17 | 2016-03-17 | 2016-03-17 | 2016-03-17 | 2016-03-17 | 2016-03-17 | 2016-03-17 | 2016-03-17 | 2016-03-17 | 2016-03-17 | 2016-03-17 | 2016-03-17 | 2016-03-17 | 2016-03-17 | 2016-03-17 | 2016-03-17 | 2016-03-17 | 2016-03-17 | 2016-03-17 | 2016-03-17 | 2016-03-17 | 2016-03-17 | 2016-03-17 | 2016-03-17 | 2016-03-17 | 2016-03-17 | 2016-03-17 | 2016-03-17 | 2016-03-17 | 2016-03-17 | 2016-03-17 | 2016-03-17
DE28-1000 | [14 empty] | 2016-08-25 | 2016-08-25 | 2016-08-25 | 2016-08-25 | 2016-08-25 | 2016-08-25 | 2016-08-25 | 2016-08-25 | 2016-08-25 | 2016-08-25 | 2016-08-25 | 2016-08-25 | 2016-08-25 | 2016-08-25 | 2016-08-25 | 2016-08-25 | 2016-08-25 | 2016-08-25 | 2016-08-25 | 2016-08-25 | 2016-08-25 | 2016-08-25 | 2016-08-25 | 2016-08-25 | 2016-08-25 | 2016-08-25 | 2016-08-25 | 2016-08-25 | 2016-08-25 | 2016-08-25 | 2016-08-25 | 2016-08-25 | 2016-08-25
DE29-1000 | [14 empty] | 2016-09-19 | 2016-09-19 | 2016-09-19 | 2016-09-19 | 2016-09-19 | 2016-09-19 | 2016-09-19 | 2016-09-19 | 2016-09-19 | 2016-09-19 | 2016-09-19 | 2016-09-19 | 2016-09-19 | 2016-09-19 | 2016-09-19 | 2016-09-19 | 2016-09-19 | 2016-09-19 | 2016-09-19 | 2016-09-19 | 2016-09-19 | 2016-09-19 | 2016-09-19 | 2016-09-19 | 2016-09-19 | 2016-09-19 | 2016-09-19 | 2016-09-19 | 2016-09-19 | 2016-09-19 | 2016-09-19 | 2016-09-19 | 2016-09-19
DE30-1000 | [16 empty] | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20 | 2016-11-20
DE30-1010 | [18 empty] | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29
DE31-1000 | [20 empty] | 2017-02-19 | 2017-02-19 | 2017-02-19 | 2017-02-19 | 2017-02-19 | 2017-02-19 | 2017-02-19 | 2017-02-19 | 2017-02-19 | 2017-02-19 | 2017-02-19 | 2017-02-19 | 2017-02-19 | 2017-02-19 | 2017-02-19 | 2017-02-19 | 2017-02-19 | 2017-02-19 | 2017-02-19 | 2017-02-19 | 2017-02-19 | 2017-02-19 | 2017-02-19 | 2017-02-19 | 2017-02-19 | 2017-02-19 | 2017-02-19
DE31-1010 | [20 empty] | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23
DE31-1020 | [20 empty] | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13
DE31-1030 | [22 empty] | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25
DE32-1000 | [20 empty] | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02 | 2017-02-02
DE32-1010 | [20 empty] | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04 | 2017-03-04
DE32-1020 | [20 empty] | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08 | 2017-03-08
DE33-1000 | [16 empty] | 2016-11-23 | 2016-11-23 | 2016-11-23 | 2016-11-23 | 2016-11-23 | 2016-11-23 | 2016-11-23 | 2016-11-23 | 2016-11-23 | 2016-11-23 | 2016-11-23 | 2016-11-23 | 2016-11-23 | 2016-11-23 | 2016-11-23 | 2016-11-23 | 2016-11-23 | 2016-11-23 | 2016-11-23 | 2016-11-23 | 2016-11-23 | 2016-11-23 | 2016-11-23 | 2016-11-23 | 2016-11-23 | 2016-11-23 | 2016-11-23 | 2016-11-23 | 2016-11-23 | 2016-11-23 | 2016-11-23
DE33-1010 | [18 empty] | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29
DE34-1000 | [14 empty] | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04
DE34-1010 | [14 empty] | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30
DE34-1020 | [14 empty] | 2016-09-03 | 2016-09-03 | 2016-09-03 | 2016-09-03 | 2016-09-03 | 2016-09-03 | 2016-09-03 | 2016-09-03 | 2016-09-03 | 2016-09-03 | 2016-09-03 | 2016-09-03 | 2016-09-03 | 2016-09-03 | 2016-09-03 | 2016-09-03 | 2016-09-03 | 2016-09-03 | 2016-09-03 | 2016-09-03 | 2016-09-03 | 2016-09-03 | 2016-09-03 | 2016-09-03 | 2016-09-03 | 2016-09-03 | 2016-09-03 | 2016-09-03 | 2016-09-03 | 2016-09-03 | 2016-09-03 | 2016-09-03 | 2016-09-03
DE34-1030 | [16 empty] | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06
DE34-1040 | [16 empty] | 2016-10-29 | 2016-10-29 | 2016-10-29 | 2016-10-29 | 2016-10-29 | 2016-10-29 | 2016-10-29 | 2016-10-29 | 2016-10-29 | 2016-10-29 | 2016-10-29 | 2016-10-29 | 2016-10-29 | 2016-10-29 | 2016-10-29 | 2016-10-29 | 2016-10-29 | 2016-10-29 | 2016-10-29 | 2016-10-29 | 2016-10-29 | 2016-10-29 | 2016-10-29 | 2016-10-29 | 2016-10-29 | 2016-10-29 | 2016-10-29 | 2016-10-29 | 2016-10-29 | 2016-10-29 | 2016-10-29
DE34-1050 | [16 empty] | 2016-11-10 | 2016-11-10 | 2016-11-10 | 2016-11-10 | 2016-11-10 | 2016-11-10 | 2016-11-10 | 2016-11-10 | 2016-11-10 | 2016-11-10 | 2016-11-10 | 2016-11-10 | 2016-11-10 | 2016-11-10 | 2016-11-10 | 2016-11-10 | 2016-11-10 | 2016-11-10 | 2016-11-10 | 2016-11-10 | 2016-11-10 | 2016-11-10 | 2016-11-10 | 2016-11-10 | 2016-11-10 | 2016-11-10 | 2016-11-10 | 2016-11-10 | 2016-11-10 | 2016-11-10 | 2016-11-10
DE34-1060 | [10 empty] | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14 | 2016-04-14
DE35-1000 | [10 empty] | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25 | 2016-04-25
DE36-1000 | [20 empty] | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29
DE36-1010 | [20 empty] | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29
DE36-1020 | [20 empty] | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29
DE36-1030 | [20 empty] | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29
DE36-1040 | [20 empty] | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29 | 2017-01-29
DW-COCC-DE01-1000 | [22 empty] | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04
DW-COCC-DE01-1001 | [26 empty] | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19
DW-COCC-DE01-1002 | [34 empty] | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05
DW-COCC-DE01-1003 | [26 empty] | 2017-08-30 | 2017-08-30 | 2017-08-30 | 2017-08-30 | 2017-08-30 | 2017-08-30 | 2017-08-30 | 2017-08-30 | 2017-08-30 | 2017-08-30 | 2017-08-30 | 2017-08-30 | 2017-08-30 | 2017-08-30 | 2017-08-30 | 2017-08-30 | 2017-08-30 | 2017-08-30 | 2017-08-30 | 2017-08-30 | 2017-08-30
DW-COCC-DE01-1004 | [20 empty] | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02
DW-CP-DE06-1000 | [20 empty] | 2017-03-19 | 2017-03-19 | 2017-03-19 | 2017-03-19 | 2017-03-19 | 2017-03-19 | 2017-03-19 | 2017-03-19 | 2017-03-19 | 2017-03-19 | 2017-03-19 | 2017-03-19 | 2017-03-19 | 2017-03-19 | 2017-03-19 | 2017-03-19 | 2017-03-19 | 2017-03-19 | 2017-03-19 | 2017-03-19 | 2017-03-19 | 2017-03-19 | 2017-03-19 | 2017-03-19 | 2017-03-19 | 2017-03-19 | 2017-03-19
DW-CP-DE06-1001 | [14 empty] | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31 | 2016-07-31
DW-EDG-DE03-1000 | [24 empty] | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24
DW-EDG-DE03-1001 | [34 empty] | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05 | 2018-05-05
DW-EDG-DE03-1002 | [26 empty] | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19
DW-EDG-DE03-1003 | [20 empty] | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12
DW-EDG-DE03-1004 | [20 empty] | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12
DW-EDG-DE03-1005 | [24 empty] | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20
DW-EDG-DE03-1006 | [26 empty] | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19
DW-EDG-DE03-1007 | [34 empty] | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05
DW-EDG-DE03-1008 | [28 empty] | 2017-10-10 | 2017-10-10 | 2017-10-10 | 2017-10-10 | 2017-10-10 | 2017-10-10 | 2017-10-10 | 2017-10-10 | 2017-10-10 | 2017-10-10 | 2017-10-10 | 2017-10-10 | 2017-10-10 | 2017-10-10 | 2017-10-10 | 2017-10-10 | 2017-10-10 | 2017-10-10 | 2017-10-10
DW-EDG-DE03-1009 | [24 empty] | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20
DW-EDG-DE03-1010 | [26 empty] | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19
DW-EDG-DE03-1011 | [22 empty] | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18
DW-EDG-DE03-1012 | [22 empty] | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18
DW-EDG-DE03-1013 | [24 empty] | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20
DW-EDG-DE03-1014 | [26 empty] | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19
DW-EDG-DE03-1015 | [20 empty] | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23
DW-EDG-DE03-1016 | [20 empty] | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23
DW-INST-DE04-1000 | [22 empty] | 2017-05-17 | 2017-05-17 | 2017-05-17 | 2017-05-17 | 2017-05-17 | 2017-05-17 | 2017-05-17 | 2017-05-17 | 2017-05-17 | 2017-05-17 | 2017-05-17 | 2017-05-17 | 2017-05-17 | 2017-05-17 | 2017-05-17 | 2017-05-17 | 2017-05-17 | 2017-05-17 | 2017-05-17 | 2017-05-17 | 2017-05-17 | 2017-05-17 | 2017-05-17 | 2017-05-17 | 2017-05-17
DW-INST-DE04-1001 | [24 empty] | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01
DW-INST-DE04-1002 | [24 empty] | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01
DW-SS-DE02-1000 | [24 empty] | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20
DW-SS-DE02-1001 | [24 empty] | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20
DW-SS-DE02-1002 | [34 empty] | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05
DW-SS-DE02-1003 | [20 empty] | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12
DW-SS-DE02-1004 | [20 empty] | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12 | 2017-03-12
DW-SS-DE02-1005 | [24 empty] | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20
DW-SS-DE02-1006 | [24 empty] | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20
DW-SS-DE02-1007 | [18 empty] | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05 | 2016-12-05
DW-SS-DE02-1008 | [22 empty] | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18
DW-SS-DE02-1009 | [22 empty] | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18
DW-SS-DE02-1010 | [24 empty] | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20
DW-SS-DE02-1011 | [24 empty] | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20
DW-SS-DE02-1012 | [26 empty] | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19
DW-SS-DE02-1013 | [20 empty] | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23
DW-SS-DE02-1014 | [20 empty] | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23
DW-SS-DE02-1015 | [24 empty] | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31
DW-SS-DE02-1016 | [24 empty] | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20 | 2017-06-20
DW-SS-DE02-1017 | [22 empty] | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04
DW-SS-DE02-1018 | [34 empty] | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05 | 2018-04-05
DW-SS-DE02-1019 | [28 empty] | 2017-10-10 | 2017-10-10 | 2017-10-10 | 2017-10-10 | 2017-10-10 | 2017-10-10 | 2017-10-10 | 2017-10-10 | 2017-10-10 | 2017-10-10 | 2017-10-10 | 2017-10-10 | 2017-10-10 | 2017-10-10 | 2017-10-10 | 2017-10-10 | 2017-10-10 | 2017-10-10 | 2017-10-10
DW-TEL-DE05-1000 | [24 empty] | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19 | 2017-07-19
EI&T-COCC-DE04-1000 | [32 empty] | 2018-03-06 | 2018-03-06 | 2018-03-06 | 2018-03-06 | 2018-03-06 | 2018-03-06 | 2018-03-06 | 2018-03-06 | 2018-03-06 | 2018-03-06 | 2018-03-06 | 2018-03-06 | 2018-03-06 | 2018-03-06 | 2018-03-06
EI&T-COCC-DE04-1010 | [30 empty] | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20
EI&T-COCC-DE04-1020 | [36 empty] | 2018-07-23 | 2018-07-23 | 2018-07-23 | 2018-07-23 | 2018-07-23 | 2018-07-23 | 2018-07-23 | 2018-07-23 | 2018-07-23 | 2018-07-23 | 2018-07-23
EI&T-S301-DE05-1000 | [30 empty] | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01 | 2018-01-01
EI&T-S301-DE05-1010 | [36 empty] | 2018-06-25 | 2018-06-25 | 2018-06-25 | 2018-06-25 | 2018-06-25 | 2018-06-25 | 2018-06-25 | 2018-06-25 | 2018-06-25 | 2018-06-25 | 2018-06-25
EI&T-S302-DE06-1000 | [30 empty] | 2018-01-08 | 2018-01-08 | 2018-01-08 | 2018-01-08 | 2018-01-08 | 2018-01-08 | 2018-01-08 | 2018-01-08 | 2018-01-08 | 2018-01-08 | 2018-01-08 | 2018-01-08 | 2018-01-08 | 2018-01-08 | 2018-01-08 | 2018-01-08 | 2018-01-08
EI&T-S302-DE06-1010 | [36 empty] | 2018-07-12 | 2018-07-12 | 2018-07-12 | 2018-07-12 | 2018-07-12 | 2018-07-12 | 2018-07-12 | 2018-07-12 | 2018-07-12 | 2018-07-12 | 2018-07-12
EI&T-S303-DE07-1000 | [28 empty] | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15 | 2017-11-15
EI&T-S303-DE07-1010 | [24 empty] | 2017-06-13 | 2017-06-13 | 2017-06-13 | 2017-06-13 | 2017-06-13 | 2017-06-13 | 2017-06-13 | 2017-06-13 | 2017-06-13 | 2017-06-13 | 2017-06-13 | 2017-06-13 | 2017-06-13 | 2017-06-13 | 2017-06-13 | 2017-06-13 | 2017-06-13 | 2017-06-13 | 2017-06-13 | 2017-06-13 | 2017-06-13 | 2017-06-13 | 2017-06-13
ELC-COO-DE04-1000 | [24 empty] | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31
ELC-COO-DE04-1001 | [22 empty] | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04
ELC-COO-DE04-1002 | [28 empty] | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17
ELC-COO-DE04-1003 | [24 empty] | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31
ELC-MG1-DE07-1000 | [24 empty] | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07
ELC-SBTN-DE06-1000 | [28 empty] | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11
ELC-SBTN-DE06-1001 | [26 empty] | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20
ELC-SBTN-DE06-1002 | [22 empty] | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04 | 2017-05-04
ELC-SBTN-DE06-1003 | [28 empty] | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11
ELC-SBTN-DE06-1004 | [26 empty] | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20
ELC-SBTN-DE06-1005 | [28 empty] | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17
ELC-SBTN-DE06-1006 | [28 empty] | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30 | 2017-09-30
ELC-SBTN-DE06-1007 | [26 empty] | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19
ELC-SBTN-DE06-1008 | [24 empty] | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24
ELC-SBTN-DE06-1009 | [26 empty] | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19
ELC-SBTN-DE06-1010 | [24 empty] | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24
ELC-SBTN-DE06-1011 | [26 empty] | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19 | 2017-09-19
ELC-STF-DE05-1001 | [24 empty] | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07 | 2017-06-07
ELC-STF-DE05-1002 | [28 empty] | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18
EOD-DE01-A1000 | [6 empty] | 2016-01-10 | 2016-01-10 | 2016-01-10 | 2016-01-10 | 2016-01-10 | 2016-01-10 | 2016-01-10 | 2016-01-10 | 2016-01-10 | 2016-01-10 | 2016-01-10 | 2016-01-10 | 2016-01-10 | 2016-01-10 | 2016-01-10 | 2016-01-10 | 2016-01-10 | 2016-01-10 | 2016-01-10 | 2016-01-10 | 2016-01-10 | 2016-01-10 | 2016-01-10 | 2016-01-10 | 2016-01-10 | 2016-01-10 | 2016-01-10 | 2016-01-10 | 2016-01-10 | 2016-01-10 | 2016-01-10 | 2016-01-10 | 2016-01-10 | 2016-01-10 | 2016-01-10 | 2016-01-10 | 2016-01-10 | 2016-01-10 | 2016-01-10 | 2016-01-10 | 2016-01-10
EOD-DE01-A1010 | [8 empty] | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30
EOD-DE01-A1020 | [8 empty] | 2016-02-05 | 2016-02-05 | 2016-02-05 | 2016-02-05 | 2016-02-05 | 2016-02-05 | 2016-02-05 | 2016-02-05 | 2016-02-05 | 2016-02-05 | 2016-02-05 | 2016-02-05 | 2016-02-05 | 2016-02-05 | 2016-02-05 | 2016-02-05 | 2016-02-05 | 2016-02-05 | 2016-02-05 | 2016-02-05 | 2016-02-05 | 2016-02-05 | 2016-02-05 | 2016-02-05 | 2016-02-05 | 2016-02-05 | 2016-02-05 | 2016-02-05 | 2016-02-05 | 2016-02-05 | 2016-02-05 | 2016-02-05 | 2016-02-05 | 2016-02-05 | 2016-02-05 | 2016-02-05 | 2016-02-05 | 2016-02-05 | 2016-02-05
EOD-DE01-A1030 | [8 empty] | 2016-02-07 | 2016-02-07 | 2016-02-07 | 2016-02-07 | 2016-02-07 | 2016-02-07 | 2016-02-07 | 2016-02-07 | 2016-02-07 | 2016-02-07 | 2016-02-07 | 2016-02-07 | 2016-02-07 | 2016-02-07 | 2016-02-07 | 2016-02-07 | 2016-02-07 | 2016-02-07 | 2016-02-07 | 2016-02-07 | 2016-02-07 | 2016-02-07 | 2016-02-07 | 2016-02-07 | 2016-02-07 | 2016-02-07 | 2016-02-07 | 2016-02-07 | 2016-02-07 | 2016-02-07 | 2016-02-07 | 2016-02-07 | 2016-02-07 | 2016-02-07 | 2016-02-07 | 2016-02-07 | 2016-02-07 | 2016-02-07 | 2016-02-07
EOD-DE01-A1040 | [8 empty] | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17
EOD-DE02-A1000 | [10 empty] | 2016-04-28 | 2016-04-28 | 2016-04-28 | 2016-04-28 | 2016-04-28 | 2016-04-28 | 2016-04-28 | 2016-04-28 | 2016-04-28 | 2016-04-28 | 2016-04-28 | 2016-04-28 | 2016-04-28 | 2016-04-28 | 2016-04-28 | 2016-04-28 | 2016-04-28 | 2016-04-28 | 2016-04-28 | 2016-04-28 | 2016-04-28 | 2016-04-28 | 2016-04-28 | 2016-04-28 | 2016-04-28 | 2016-04-28 | 2016-04-28 | 2016-04-28 | 2016-04-28 | 2016-04-28 | 2016-04-28 | 2016-04-28 | 2016-04-28 | 2016-04-28 | 2016-04-28 | 2016-04-28 | 2016-04-28
GEN-DE01-A1000 | time axis 2015-10-20 to 2015-10-20
GEN-DE02-A1000 | [8 empty] | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24 | 2016-01-24
INST-DE08-1000 | [24 empty] | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01
INST-DE08-1001 | [28 empty] | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17 | 2017-10-17
INST-DE08-1002 | [24 empty] | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01
PIP-CIV-DE01-1000 | [18 empty] | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29 | 2016-12-29
PIP-CIV-DE01-1001 | [18 empty] | 2016-12-29: 2018-12-24; 2016-12-29: 2018-12-24; 2016-12-29: 2018-12-24; 2016-12-29: 2018-12-24; 2016-12-29: 2018-12-24
PIP-CIV-DE02-1000 | [22 empty] | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06 | 2017-05-06
PIP-CIV-DE02-1001 | [22 empty] | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20
PIP-CIV-DE02-1002 | [22 empty] | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20
PIP-CIV-DE02-1003 | [22 empty] | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20
PIP-CIV-DE02-1004 | [22 empty] | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20
PIP-CIV-DE02-1005 | [22 empty] | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20
PIP-CIV-DE02-1006 | [22 empty] | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20
PIP-CIV-DE02-1007 | [22 empty] | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20 | 2017-05-20
PIP-CIV-DE02-1008 | [22 empty] | 2017-05-25 | 2017-05-25 | 2017-05-25 | 2017-05-25 | 2017-05-25 | 2017-05-25 | 2017-05-25 | 2017-05-25 | 2017-05-25 | 2017-05-25 | 2017-05-25 | 2017-05-25 | 2017-05-25 | 2017-05-25 | 2017-05-25 | 2017-05-25 | 2017-05-25 | 2017-05-25 | 2017-05-25 | 2017-05-25 | 2017-05-25 | 2017-05-25 | 2017-05-25 | 2017-05-25 | 2017-05-25
PIP-CIV-DE02-1014 | [22 empty] | 2017-05-25: 2018-12-24; 2017-05-25: 2018-12-24; 2017-05-25: 2018-12-24; 2017-05-25: 2018-12-24; 2017-05-25: 2018-12-24
PIP-DE09-1001 | [28 empty] | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18 | 2017-10-18
PIP-DE09-1002 | [28 empty] | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20
PIP-DE09-1003 | [24 empty] | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01
PMT-DE01-A1000 | [10 empty] | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17 | 2016-04-17
PMT-DE02-A1000 | [12 empty] | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21 | 2016-07-21
PMT-DE03-A1000 | [20 empty] | 2017-02-21 | 2017-02-21 | 2017-02-21 | 2017-02-21 | 2017-02-21 | 2017-02-21 | 2017-02-21 | 2017-02-21 | 2017-02-21 | 2017-02-21 | 2017-02-21 | 2017-02-21 | 2017-02-21 | 2017-02-21 | 2017-02-21 | 2017-02-21 | 2017-02-21 | 2017-02-21 | 2017-02-21 | 2017-02-21 | 2017-02-21 | 2017-02-21 | 2017-02-21 | 2017-02-21 | 2017-02-21 | 2017-02-21 | 2017-02-21
PMT-DE03-A1010 | [26 empty] | 2017-08-04 | 2017-08-04 | 2017-08-04 | 2017-08-04 | 2017-08-04 | 2017-08-04 | 2017-08-04 | 2017-08-04 | 2017-08-04 | 2017-08-04 | 2017-08-04 | 2017-08-04 | 2017-08-04 | 2017-08-04 | 2017-08-04 | 2017-08-04 | 2017-08-04 | 2017-08-04 | 2017-08-04 | 2017-08-04 | 2017-08-04
PMT-DE04-A1000 | [10 empty] | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13 | 2016-04-13
PR0-INSTR-DE04-1003 | [36 empty] | 2018-07-08 | 2018-07-08 | 2018-07-08 | 2018-07-08 | 2018-07-08 | 2018-07-08 | 2018-07-08 | 2018-07-08 | 2018-07-08 | 2018-07-08 | 2018-07-08
PR0-INSTR-DE04-1006 | [38 empty] | 2018-09-25 | 2018-09-25 | 2018-09-25 | 2018-09-25 | 2018-09-25 | 2018-09-25 | 2018-09-25 | 2018-09-25 | 2018-09-25
PR0-INSTR-DE04-1013 | [38 empty] | 2018-08-11 | 2018-08-11 | 2018-08-11 | 2018-08-11 | 2018-08-11 | 2018-08-11 | 2018-08-11 | 2018-08-11 | 2018-08-11
PR0-INSTR-DE04-1018 | [36 empty] | 2018-07-19 | 2018-07-19 | 2018-07-19 | 2018-07-19 | 2018-07-19 | 2018-07-19 | 2018-07-19 | 2018-07-19 | 2018-07-19 | 2018-07-19 | 2018-07-19
PR0-INSTR-DE04-1019 | [30 empty] | 2018-01-07 | 2018-01-07 | 2018-01-07 | 2018-01-07 | 2018-01-07 | 2018-01-07 | 2018-01-07 | 2018-01-07 | 2018-01-07 | 2018-01-07 | 2018-01-07 | 2018-01-07 | 2018-01-07 | 2018-01-07 | 2018-01-07 | 2018-01-07 | 2018-01-07
PR0-INSTR-DE04-1023 | [34 empty] | 2018-04-12 | 2018-04-12 | 2018-04-12 | 2018-04-12 | 2018-04-12 | 2018-04-12 | 2018-04-12 | 2018-04-12 | 2018-04-12 | 2018-04-12 | 2018-04-12 | 2018-04-12 | 2018-04-12
PR0-INSTR-DE04-1025 | [32 empty] | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27
PR0-INSTR-DE04-1026 | [38 empty] | 2018-08-05 | 2018-08-05 | 2018-08-05 | 2018-08-05 | 2018-08-05 | 2018-08-05 | 2018-08-05 | 2018-08-05 | 2018-08-05
PR0-INSTR-DE04-1027 | [38 empty] | 2018-08-05 | 2018-08-05 | 2018-08-05 | 2018-08-05 | 2018-08-05 | 2018-08-05 | 2018-08-05 | 2018-08-05 | 2018-08-05
PR0-TEL-DE05-1001 | [32 empty] | 2018-02-06 | 2018-02-06 | 2018-02-06 | 2018-02-06 | 2018-02-06 | 2018-02-06 | 2018-02-06 | 2018-02-06 | 2018-02-06 | 2018-02-06 | 2018-02-06 | 2018-02-06 | 2018-02-06 | 2018-02-06 | 2018-02-06
PRO-DE01-1000 | [28 empty] | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02
PRO-DE01-1001 | [28 empty] | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02
PRO-DE01-1002 | [28 empty] | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02
PRO-DE01-1003 | [28 empty] | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02
PRO-DE01-1004 | [28 empty] | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16
PRO-DE01-1005 | [28 empty] | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16
PRO-DE01-1006 | [28 empty] | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16
PRO-DE01-1007 | [34 empty] | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15
PRO-DE01-1008 | [34 empty] | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07
PRO-DE01-1009 | [34 empty] | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07
PRO-DE01-1010 | [34 empty] | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07
PRO-DE01-1011 | [34 empty] | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07
PRO-DE01-1012 | [34 empty] | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18
PRO-DE01-1013 | [34 empty] | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18 | 2018-04-18
PRO-DE01-1014 | [32 empty] | 2018-03-03 | 2018-03-03 | 2018-03-03 | 2018-03-03 | 2018-03-03 | 2018-03-03 | 2018-03-03 | 2018-03-03 | 2018-03-03 | 2018-03-03 | 2018-03-03 | 2018-03-03 | 2018-03-03 | 2018-03-03 | 2018-03-03
PRO-DE01-1015 | [32 empty] | 2018-03-03 | 2018-03-03 | 2018-03-03 | 2018-03-03 | 2018-03-03 | 2018-03-03 | 2018-03-03 | 2018-03-03 | 2018-03-03 | 2018-03-03 | 2018-03-03 | 2018-03-03 | 2018-03-03 | 2018-03-03 | 2018-03-03
PRO-DE01-1016 | [32 empty] | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28
PRO-DE01-1017 | [32 empty] | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28
PRO-DE01-1019 | [22 empty] | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16 | 2017-04-16
PRO-DE01-1022 | [22 empty] | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18
PRO-DE01-1074 | [34 empty] | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07
PRO-DE01-1075 | [34 empty] | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07 | 2018-04-07
PRO-DE01-1076 | [24 empty] | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01 | 2017-06-01
PRO-DE01-1088 | [24 empty] | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30 | 2017-05-30
PRO-DE01-1097 | [28 empty] | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22
PRO-DE01-1112 | [26 empty] | 2017-09-09 | 2017-09-09 | 2017-09-09 | 2017-09-09 | 2017-09-09 | 2017-09-09 | 2017-09-09 | 2017-09-09 | 2017-09-09 | 2017-09-09 | 2017-09-09 | 2017-09-09 | 2017-09-09 | 2017-09-09 | 2017-09-09 | 2017-09-09 | 2017-09-09 | 2017-09-09 | 2017-09-09 | 2017-09-09 | 2017-09-09
PRO-DE01-1163 | [28 empty] | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05
PRO-DE01-1165 | [28 empty] | 2017-10-31 | 2017-10-31 | 2017-10-31 | 2017-10-31 | 2017-10-31 | 2017-10-31 | 2017-10-31 | 2017-10-31 | 2017-10-31 | 2017-10-31 | 2017-10-31 | 2017-10-31 | 2017-10-31 | 2017-10-31 | 2017-10-31 | 2017-10-31 | 2017-10-31 | 2017-10-31 | 2017-10-31
PRO-DE01-1167 | [28 empty] | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22 | 2017-10-22
PRO-E&I-DE03-1000 | [32 empty] | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27
PRO-E&I-DE03-1001 | [32 empty] | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27 | 2018-01-27
PRO-ELE-CP-DE01-1000 | [38 empty] | 2018-09-18 | 2018-09-18 | 2018-09-18 | 2018-09-18 | 2018-09-18 | 2018-09-18 | 2018-09-18 | 2018-09-18 | 2018-09-18
PRO-ELE-CP-DE01-1001 | [22 empty] | 2017-04-23 | 2017-04-23 | 2017-04-23 | 2017-04-23 | 2017-04-23 | 2017-04-23 | 2017-04-23 | 2017-04-23 | 2017-04-23 | 2017-04-23 | 2017-04-23 | 2017-04-23 | 2017-04-23 | 2017-04-23 | 2017-04-23 | 2017-04-23 | 2017-04-23 | 2017-04-23 | 2017-04-23 | 2017-04-23 | 2017-04-23 | 2017-04-23 | 2017-04-23 | 2017-04-23 | 2017-04-23
PRO-ELE-DE02-1002 | [26 empty] | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18 | 2017-09-18
PRO-ELE-DE02-1004 | [22 empty] | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09
PRO-ELE-DE02-1005 | [22 empty] | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15
PRO-ELE-DE02-1007 | [24 empty] | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27
PRO-ELE-DE02-1008 | [24 empty] | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27 | 2017-05-27
PRO-ELE-DE02-1010 | [30 empty] | 2017-12-11 | 2017-12-11 | 2017-12-11 | 2017-12-11 | 2017-12-11 | 2017-12-11 | 2017-12-11 | 2017-12-11 | 2017-12-11 | 2017-12-11 | 2017-12-11 | 2017-12-11 | 2017-12-11 | 2017-12-11 | 2017-12-11 | 2017-12-11 | 2017-12-11
PRO-ELE-DE02-1011 | [38 empty] | 2018-09-17 | 2018-09-17 | 2018-09-17 | 2018-09-17 | 2018-09-17 | 2018-09-17 | 2018-09-17 | 2018-09-17 | 2018-09-17
PRO-ELE-DE02-1013 | [32 empty] | 2018-03-06 | 2018-03-06 | 2018-03-06 | 2018-03-06 | 2018-03-06 | 2018-03-06 | 2018-03-06 | 2018-03-06 | 2018-03-06 | 2018-03-06 | 2018-03-06 | 2018-03-06 | 2018-03-06 | 2018-03-06 | 2018-03-06
PRO-ELE-DE02-1014 | [32 empty] | 2018-02-13 | 2018-02-13 | 2018-02-13 | 2018-02-13 | 2018-02-13 | 2018-02-13 | 2018-02-13 | 2018-02-13 | 2018-02-13 | 2018-02-13 | 2018-02-13 | 2018-02-13 | 2018-02-13 | 2018-02-13 | 2018-02-13
PRO-ELE-DE02-1016 | [32 empty] | 2018-03-11 | 2018-03-11 | 2018-03-11 | 2018-03-11 | 2018-03-11 | 2018-03-11 | 2018-03-11 | 2018-03-11 | 2018-03-11 | 2018-03-11 | 2018-03-11 | 2018-03-11 | 2018-03-11 | 2018-03-11 | 2018-03-11
PRO-ELE-DE02-1017 | [32 empty] | 2018-03-11 | 2018-03-11 | 2018-03-11 | 2018-03-11 | 2018-03-11 | 2018-03-11 | 2018-03-11 | 2018-03-11 | 2018-03-11 | 2018-03-11 | 2018-03-11 | 2018-03-11 | 2018-03-11 | 2018-03-11 | 2018-03-11
PRO-ELE-DE02-1019 | [32 empty] | 2018-03-11: 2018-12-23; 2018-03-11: 2018-12-23; 2018-03-11: 2018-12-23; 2018-03-11: 2018-12-23; 2018-03-11: 2018-12-23
PRO-ELE-DE02-1020 | [32 empty] | 2018-03-11: 2018-12-23; 2018-03-11: 2018-12-23; 2018-03-11: 2018-12-23; 2018-03-11: 2018-12-23; 2018-03-11: 2018-12-23
PRO-ELE-DE02-1021 | [30 empty] | 2017-12-20 | 2017-12-20 | 2017-12-20 | 2017-12-20 | 2017-12-20 | 2017-12-20 | 2017-12-20 | 2017-12-20 | 2017-12-20 | 2017-12-20 | 2017-12-20 | 2017-12-20 | 2017-12-20 | 2017-12-20 | 2017-12-20 | 2017-12-20 | 2017-12-20
PRO-ELE-DE02-1026 | [30 empty] | 2017-12-20 | 2017-12-20 | 2017-12-20 | 2017-12-20 | 2017-12-20 | 2017-12-20 | 2017-12-20 | 2017-12-20 | 2017-12-20 | 2017-12-20 | 2017-12-20 | 2017-12-20 | 2017-12-20 | 2017-12-20 | 2017-12-20 | 2017-12-20 | 2017-12-20
TEL-DE09-1000 | [24 empty] | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24
TEL-DE09-1001 | [24 empty] | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24 | 2017-07-24
TEL-DE09-1002 | [24 empty] | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31 | 2017-05-31
WET-DE01-A1000 | [10 empty] | 2016-05-15 | 2016-05-15 | 2016-05-15 | 2016-05-15 | 2016-05-15 | 2016-05-15 | 2016-05-15 | 2016-05-15 | 2016-05-15 | 2016-05-15 | 2016-05-15 | 2016-05-15 | 2016-05-15 | 2016-05-15 | 2016-05-15 | 2016-05-15 | 2016-05-15 | 2016-05-15 | 2016-05-15 | 2016-05-15 | 2016-05-15 | 2016-05-15 | 2016-05-15 | 2016-05-15 | 2016-05-15 | 2016-05-15 | 2016-05-15 | 2016-05-15 | 2016-05-15 | 2016-05-15 | 2016-05-15 | 2016-05-15 | 2016-05-15 | 2016-05-15 | 2016-05-15 | 2016-05-15 | 2016-05-15
WET-DE01-A1010 | [14 empty] | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23 | 2016-07-23
WET-DE01-A1020 | [18 empty] | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30 | 2016-11-30
WET-DE01-A1030 | [18 empty] | 2016-12-01 | 2016-12-01 | 2016-12-01 | 2016-12-01 | 2016-12-01 | 2016-12-01 | 2016-12-01 | 2016-12-01 | 2016-12-01 | 2016-12-01 | 2016-12-01 | 2016-12-01 | 2016-12-01 | 2016-12-01 | 2016-12-01 | 2016-12-01 | 2016-12-01 | 2016-12-01 | 2016-12-01 | 2016-12-01 | 2016-12-01 | 2016-12-01 | 2016-12-01 | 2016-12-01 | 2016-12-01 | 2016-12-01 | 2016-12-01 | 2016-12-01 | 2016-12-01
WET-DE01-A1040 | [18 empty] | 2016-12-02 | 2016-12-02 | 2016-12-02 | 2016-12-02 | 2016-12-02 | 2016-12-02 | 2016-12-02 | 2016-12-02 | 2016-12-02 | 2016-12-02 | 2016-12-02 | 2016-12-02 | 2016-12-02 | 2016-12-02 | 2016-12-02 | 2016-12-02 | 2016-12-02 | 2016-12-02 | 2016-12-02 | 2016-12-02 | 2016-12-02 | 2016-12-02 | 2016-12-02 | 2016-12-02 | 2016-12-02 | 2016-12-02 | 2016-12-02 | 2016-12-02 | 2016-12-02
WET-DE01-A1050 | [18 empty] | 2016-12-03 | 2016-12-03 | 2016-12-03 | 2016-12-03 | 2016-12-03 | 2016-12-03 | 2016-12-03 | 2016-12-03 | 2016-12-03 | 2016-12-03 | 2016-12-03 | 2016-12-03 | 2016-12-03 | 2016-12-03 | 2016-12-03 | 2016-12-03 | 2016-12-03 | 2016-12-03 | 2016-12-03 | 2016-12-03 | 2016-12-03 | 2016-12-03 | 2016-12-03 | 2016-12-03 | 2016-12-03 | 2016-12-03 | 2016-12-03 | 2016-12-03 | 2016-12-03
WET-DE01-A1060 | [8 empty] | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17
WET-DE01-A1070 | [8 empty] | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17
WET-DE01-A1080 | [8 empty] | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17
WET-DE01-A1090 | [8 empty] | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17 | 2016-02-17
WET-DE02-A1000 | [8 empty] | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18 | 2016-03-18
WET-DE02-A1010 | [20 empty] | 2017-03-19 | 2017-03-19 | 2017-03-19 | 2017-03-19 | 2017-03-19 | 2017-03-19 | 2017-03-19 | 2017-03-19 | 2017-03-19 | 2017-03-19 | 2017-03-19 | 2017-03-19 | 2017-03-19 | 2017-03-19 | 2017-03-19 | 2017-03-19 | 2017-03-19 | 2017-03-19 | 2017-03-19 | 2017-03-19 | 2017-03-19 | 2017-03-19 | 2017-03-19 | 2017-03-19 | 2017-03-19 | 2017-03-19 | 2017-03-19
WET-DE02-A1020 | [20 empty] | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23 | 2017-03-23
WET-DE02-A1030 | [20 empty] | 2017-03-24 |  | 2017-03-24 | 2017-03-24 | 2017-03-24 | 2017-03-24 | 2017-03-24 | 2017-03-24 | 2017-03-24 | 2017-03-24 | 2017-03-24 | 2017-03-24 | 2017-03-24 | 2017-03-24 | 2017-03-24 | 2017-03-24 | 2017-03-24 | 2017-03-24 | 2017-03-24 | 2017-03-24 | 2017-03-24 | 2017-03-24 | 2017-03-24 | 2017-03-24 | 2017-03-24 | 2017-03-24 | 2017-03-24
WET-DE02-A1040 | [22 empty] | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25 | 2017-03-25
WET-DE02-A1050 | [22 empty] | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15 | 2017-04-15
WET-DE02-A1060 | [22 empty] | 2017-05-05 | 2017-05-05 | 2017-05-05 | 2017-05-05 | 2017-05-05 | 2017-05-05 | 2017-05-05 | 2017-05-05 | 2017-05-05 | 2017-05-05 | 2017-05-05 | 2017-05-05 | 2017-05-05 | 2017-05-05 | 2017-05-05 | 2017-05-05 | 2017-05-05 | 2017-05-05 | 2017-05-05 | 2017-05-05 | 2017-05-05 | 2017-05-05 | 2017-05-05 | 2017-05-05 | 2017-05-05
WET-DE02-A1070 | [22 empty] | 2017-05-24 | 2017-05-24 | 2017-05-24 | 2017-05-24 | 2017-05-24 | 2017-05-24 | 2017-05-24 | 2017-05-24 | 2017-05-24 | 2017-05-24 | 2017-05-24 | 2017-05-24 | 2017-05-24 | 2017-05-24 | 2017-05-24 | 2017-05-24 | 2017-05-24 | 2017-05-24 | 2017-05-24 | 2017-05-24 | 2017-05-24 | 2017-05-24 | 2017-05-24 | 2017-05-24 | 2017-05-24
WET-DE02-A1080 | [24 empty] | 2017-07-08 | 2017-07-08 | 2017-07-08 | 2017-07-08 | 2017-07-08 | 2017-07-08 | 2017-07-08 | 2017-07-08 | 2017-07-08 | 2017-07-08 | 2017-07-08 | 2017-07-08 | 2017-07-08 | 2017-07-08 | 2017-07-08 | 2017-07-08 | 2017-07-08 | 2017-07-08 | 2017-07-08 | 2017-07-08 | 2017-07-08 | 2017-07-08 | 2017-07-08
WET-DE02-A1090 | [24 empty] | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09 | 2017-07-09
WET-DE02-A1100 | [24 empty] | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10
WET-DE03-A1000 | [20 empty] | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13 | 2017-03-13
WET-DE03-A1010 | [30 empty] | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27
WET-DE03-A1020 | [30 empty] | 2017-11-30 | 2017-11-30 | 2017-11-30 | 2017-11-30 | 2017-11-30 | 2017-11-30 | 2017-11-30 | 2017-11-30 | 2017-11-30 | 2017-11-30 | 2017-11-30 | 2017-11-30 | 2017-11-30 | 2017-11-30 | 2017-11-30 | 2017-11-30 | 2017-11-30
WET-DE04-A1000 | [30 empty] | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27 | 2017-11-27
WET-DE04-A1010 | [32 empty] | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24 | 2018-02-24
WET-DE04-A1020 | [36 empty] | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21
WET-DE04-A1030 | [36 empty] | 2018-07-27 | 2018-07-27 | 2018-07-27 | 2018-07-27 | 2018-07-27 | 2018-07-27 | 2018-07-27 | 2018-07-27 | 2018-07-27 | 2018-07-27 | 2018-07-27
WET-DE04-A1040 | [38 empty] | 2018-07-28 | 2018-07-28 | 2018-07-28 | 2018-07-28 | 2018-07-28 | 2018-07-28 | 2018-07-28 | 2018-07-28 | 2018-07-28
WET-DE04-A1050 | [40 empty] | 2018-11-06 | 2018-11-06 | 2018-11-06 | 2018-11-06 | 2018-11-06 | 2018-11-06 | 2018-11-06
WET-DE04-A1060 | [40 empty] | 2018-11-09 | 2018-11-09 | 2018-11-09 | 2018-11-09 | 2018-11-09 | 2018-11-09 | 2018-11-09
WET-DE04-A1070 | [40 empty] | 2018-11-10 | 2018-11-10 | 2018-11-10 | 2018-11-10 | 2018-11-10 | 2018-11-10 | 2018-11-10
WET-DE05-A1000 | [10 empty] | 2016-05-16 | 2016-05-16 | 2016-05-16 | 2016-05-16 | 2016-05-16 | 2016-05-16 | 2016-05-16 | 2016-05-16 | 2016-05-16 | 2016-05-16 | 2016-05-16 | 2016-05-16 | 2016-05-16 | 2016-05-16 | 2016-05-16 | 2016-05-16 | 2016-05-16 | 2016-05-16 | 2016-05-16 | 2016-05-16 | 2016-05-16 | 2016-05-16 | 2016-05-16 | 2016-05-16 | 2016-05-16 | 2016-05-16 | 2016-05-16 | 2016-05-16 | 2016-05-16 | 2016-05-16 | 2016-05-16 | 2016-05-16 | 2016-05-16 | 2016-05-16 | 2016-05-16 | 2016-05-16 | 2016-05-16
WET-DE06-A1000 | [20 empty] | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23 | 2017-02-23