## EOT-01
NBTC-244
Delay Fragnet
Level | Event Code | Activity ID | Delay Event Details | LEN | Activity Type | Original Duration | Entry Date for VO | Early Start | Early Finish | Check | Remarks | Delay Event Status (Completed/On-Going)
1 | TIME IMPACT ANALYSIS
2 | DE25 | Delay in finishing of AFC drawings for Pipe & Cable trench at new tank Area |  | 75 |  |  |  | 2016-05-10 | 2018-05-06 |  |  | Completed
Act | DE25 | DE25-1000 | Delay in finishing of AFC drawings for Pipe & Cable trench at new tank Area | 75 | Task | 726 |  | 2016-05-10 | 2018-05-06 |  |  | DA | 1000
2 | DE26 | Delay in Start of AFC drawings for Car Park Shelters other Misc Shelter |  | 71 |  |  |  | 2016-04-27 | 2017-05-31 |  |  | Completed
Act | DE26 | DE26-1000 | Delay in Start of AFC drawings for Car Park Shelters other Misc Shelter | 71 | Task | 399 |  | 2016-04-27 | 2017-05-31 |  |  | DA | 1000
2 | DE27 | Delay in finishing of AFC drawings for Demolition of Existing road and Existing |  | 79 |  |  |  | 2016-03-17 | 2017-05-22 |  |  | Completed
Act | DE27 | DE27-1000 | Delay in finishing of AFC drawings for Demolition of Existing road and Existing | 79 | Task | 431 |  | 2016-03-17 | 2017-05-22 |  |  | DA | 1000
2 | DE28 | Delay in construction of Subgrade lvl for Bund wall around storage tank (52-D-93 & 52-D-94) |  | 91 |  |  |  | 2016-08-25 | 2019-01-27 |  |  | Completed
Act | DE28 | DE28-1000 | Delay in construction of Subgrade lvl for Bund wall around storage tank (52-D-93 & 52-D-94) | 91 | Task | 885 |  | 2016-08-25 | 2019-01-27 |  |  | DA | 1000
2 | DE29 | Delay in construction of cast catch basing & Valve Pit for bund wall around storage tank |  | 88 |  |  |  | 2016-09-19 | 2018-10-22 |  |  | Completed
Act | DE29 | DE29-1000 | Delay in construction of cast catch basing & Valve Pit for bund wall around storage tank | 88 | Task | 763 |  | 2016-09-19 | 2018-10-22 |  |  | DA | 1000
2 | DE30 | Delay in finailizing engienering - distance betw Concrete pipe and Metal Pipe |  | 77 |  |  |  | 2016-11-20 | 2018-05-03 |  |  | Completed
Act | DE30 | DE30-1000 | Delay in finailizing engienering - distance betw Concrete pipe and Metal Pipe | 77 | Task | 529 |  | 2016-11-20 | 2018-05-03 |  |  | DA | 1000
Act | DE30 | DE30-1010 | Delay in finailizing engienering - distance betw Concrete pipe and Metal Pipe | 77 | Task | 520 |  | 2016-11-29 | 2018-05-03 |  |  | DA | 1010
2 | DE31 | Delay due to delayed issue drawings & Free issue material |  | 57 |  |  |  | 2017-02-19 | 2019-01-16 |  |  | Completed
Act | DE31 | DE31-1000 | Delay due to delayed issue drawings & Free issue material | 57 | Task | 696 |  | 2017-02-19 | 2019-01-16 |  |  | DA | 1000
Act | DE31 | DE31-1010 | Delay due to delayed issue drawings & Free issue material | 57 | Task | 693 |  | 2017-02-23 | 2019-01-17 |  |  | DA | 1010
Act | DE31 | DE31-1020 | Delay due to delayed issue drawings & Free issue material | 57 | Task | 676 |  | 2017-03-13 | 2019-01-18 |  |  | DA | 1020
Act | DE31 | DE31-1030 | Delay due to delayed issue drawings & Free issue material | 57 | Task | 664 |  | 2017-03-25 | 2019-01-18 |  |  | DA | 1030
2 | DE32 | Delay in Start due to Delay in Issuance of Pill Free Issue RTRP Pipe / fitting Materials & Tools |  | 96 |  |  |  | 2017-02-02 | 2019-02-06 |  |  | Completed
Act | DE32 | DE32-1000 | Delay in Start due to Delay in Issuance of Pill Free Issue RTRP Pipe / fitting Materials & Tools | 96 | Task | 734 |  | 2017-02-02 | 2019-02-06 |  |  | DA | 1000
Act | DE32 | DE32-1010 | Delay in Start due to Delay in Issuance of Pill Free Issue RTRP Pipe / fitting Materials & Tools | 96 | Task | 710 |  | 2017-03-04 | 2019-02-12 |  |  | DA | 1010
Act | DE32 | DE32-1020 | Delay in Start due to Delay in Issuance of Pill Free Issue RTRP Pipe / fitting Materials & Tools | 96 | Task | 709 |  | 2017-03-08 | 2019-02-15 |  |  | DA | 1020
2 | DE33 | Delay in Delivery of UG Piping/Cabling Material |  | 47 |  |  |  | 2016-11-23 | 2019-04-10 |  |  | Completed
Act | DE33 | DE33-1000 | Delay in Delivery of UG Piping/Cabling Material | 47 | Task | 868 |  | 2016-11-23 | 2019-04-10 |  |  | DA | 1000
Act | DE33 | DE33-1010 | Delay in Delivery of UG Piping/Cabling Material | 47 | Task | 862 |  | 2016-11-29 | 2019-04-10 |  |  | DA | 1010
2 | DE34 | Delay due to Area Clearence, Sub-contractor obstraction, VO & revised drawings in COCC area |  | 91 |  |  |  | 2016-08-04 | 2018-06-12 |  |  | Completed
Act | DE34 | DE34-1000 | Delay in Excavation & Subgrade | 30 | Task | 677 |  | 2016-08-04 | 2018-06-12 |  |  | DA | 1000
Act | DE34 | DE34-1010 | Delay in Blinding & PCC works | 29 | Task | 657 |  | 2016-08-30 | 2018-06-18 |  |  | DA | 1010
Act | DE34 | DE34-1020 | Delay in Rebar, Form work for footing | 37 | Task | 653 |  | 2016-09-03 | 2018-06-18 |  |  | DA | 1020
Act | DE34 | DE34-1030 | Delay in Concrete pouring for footing | 37 | Task | 620 |  | 2016-10-06 | 2018-06-18 |  |  | DA | 1030
Act | DE34 | DE34-1040 | Delay in Concrete pouring for pedestal | 38 | Task | 597 |  | 2016-10-29 | 2018-06-18 |  |  | DA | 1040
Act | DE34 | DE34-1050 | Delay in Concrete protection for Fnd | 36 | Task | 585 |  | 2016-11-10 | 2018-06-18 |  |  | DA | 1050
Act | DE34 | DE34-1060 | Delay in Grading cutting stockpilling | 37 | Task | 393 |  | 2016-04-14 | 2017-05-12 |  |  | DA | 1060
2 | DE35 | Delay due to non issues of AFC darwings |  | 39 |  |  |  | 2016-04-25 | 2017-05-12 |  |  | Completed
Act | DE35 | DE35-1000 | Delay due to non issues of AFC darwings resulting in delay to start Grading work | 80 | Task | 382 |  | 2016-04-25 | 2017-05-12 |  |  | DA | 1000
2 | DE36 | Delay in issue of free issue material |  | 37 |  |  |  | 2017-01-29 | 2018-07-21 |  |  | Completed
Act | DE36 | DE36-1000 | EOF : Delivery of SS/SDSS pipes (Seemless) - Lot -1 | 53 | Task | 538 |  | 2017-01-29 | 2018-07-21 |  |  | DA | 1000
Act | DE36 | DE36-1010 | EOF : Delivery of SS/SDSS pipes (Seemless) - Lot -1 | 53 | Task | 538 |  | 2017-01-29 | 2018-07-21 |  |  | DA | 1010
Act | DE36 | DE36-1020 | EOF : Delivery of SS/SDSS pipes (Welded) - Lot -1 | 51 | Task | 538 |  | 2017-01-29 | 2018-07-21 |  |  | DA | 1020
Act | DE36 | DE36-1030 | EOF : Delivery of SS/SDSS pipes (Welded) - Lot -1 | 51 | Task | 538 |  | 2017-01-29 | 2018-07-21 |  |  | DA | 1030
Act | DE36 | DE36-1040 | EOF : Delivery of non-metallic pipes & fitting (GRE/ FBE/HBE) - Lot -1 | 72 | Task | 266 |  | 2017-01-29 | 2017-10-22 |  |  | DA | 1040
Formulas:
Early Start = MIN([Early Start, row below]:[Early Start, row below])
Early Finish = MAX([Early Finish, row below]:[Early Finish, row below])

## Relationship
Delay Event Code | Predecessor | Successor | Predecessor Name | Sucessor Name | Rel. Type | Lag | Type
DE25 |  | 2AE100CV02400-08110 | NA | NA | FF | 0 | DE
DE26 |  | 2AE133CV04000-08105 | NA | NA | FS | 0 | DE
DE27 |  | 2AE142CV01000-08100 | NA | NA | FF | 0 | DE
DE28 |  | 2AI101CV01700-08015 | NA | NA | FS | 0 | DE
DE29 |  | 2AI101CV01700-08025 | NA | NA | FS | 0 | DE
DE30 | DE30-1000 | 2AI101CV18400-08060 | NA | NA | FS | 0 | DA
DE30 | DE30-1010 | 2AI101CV18400-08065 | NA | NA | FS | 0 | DA
DE31 | DE31-1000 | 2AI101PI01000-08040 | NA | NA | FS | 0 | DA
DE31 | DE31-1010 | 2AI101PI01000-08045 | NA | NA | FS | 0 | DA
DE31 | DE31-1020 | 2AI101PI01000-08046 | NA | NA | FS | 0 | DA
DE31 | DE31-1030 | 2AI101PI01000-08050 | NA | NA | FS | 0 | DA
DE32 | DE32-1000 | 2AI101PI01000-08090 | NA | NA | FS | 0 | DA
DE32 | DE32-1010 | 2AI101PI01000-08095 | NA | NA | FS | 0 | DA
DE32 | DE32-1020 | 2AI101PI01000-08100 | NA | NA | FS | 0 | DA
DE33 | DE33-1000 | 2AI103CV19100-08001 | NA | NA | FS | 0 | DA
DE33 | DE33-1010 | 2AI103CV19100-08006 | NA | NA | FS | 0 | DA
DE34 | DE34-1000 | 2AI133CV99400-08000 | NA | NA | FF | 0 | DA
DE34 | DE34-1010 | 2AI133CV99400-08005 | NA | NA | FF | 0 | DA
DE34 | DE34-1020 | 2AI133CV99400-08010 | NA | NA | FF | 0 | DA
DE34 | DE34-1030 | 2AI133CV99400-08011 | NA | NA | FF | 0 | DA
DE34 | DE34-1040 | 2AI133CV99400-08016 | NA | NA | FF | 0 | DA
DE34 | DE34-1050 | 2AI133CV99400-08020 | NA | NA | FF | 0 | DA
DE34 | DE34-1060 | 2AI141CV01000-08020 | NA | NA | FF | 0 | DA
DE35 |  | 2AI141CV01000-08025 | NA | NA | FF | 0 | DE
DE36 | DE36-1000 | 2AP000PI00107-08030 | NA | NA | FF | 0 | DA
DE36 | DE36-1010 | 2AP000PI00107-08030 | NA | NA | FF | 0 | DA
DE36 | DE36-1020 | 2AP000PI00107-08045 | NA | NA | FF | 0 | DA
DE36 | DE36-1030 | 2AP000PI00107-08045 | NA | NA | FF | 0 | DA
DE36 | DE36-1040 | 2AP000PI00207-08000 | NA | NA | FF | 0 | DA