## Mapping
[6 empty] | Window Starting |  |  | 2015-08-06 | 2015-08-13 | 2015-08-20 | 2015-08-27 | 2015-09-03 | 2015-09-10 | 2015-09-17 | 2015-09-24 | WINDOW 01 | 2015-10-01 | 2015-10-08 | 2015-10-15 | 2015-10-22 | 2015-10-29 | 2015-11-05 | 2015-11-12 | 2015-11-19 | 2015-11-26 | WINDOW 02 | 2015-12-03 | 2015-12-10 | 2015-12-17 | 2015-12-24 | 2015-12-31 | 2016-01-07 | 2016-01-14 | 2016-01-21 | WINDOW 03 | 2016-01-28 | 2016-02-04 | 2016-02-11 | 2016-02-18 | 2016-02-25 | 2016-03-03 | 2016-03-10 | 2016-03-17 | 2016-03-24 | WINDOW 04 | 2016-03-31 | 2016-04-07 | 2016-04-14 | 2016-04-21 | 2016-04-28 | 2016-05-05 | 2016-05-12 | 2016-05-19 | 2016-05-26 | WINDOW 05 | 2016-06-02 | 2016-06-09 | 2016-06-16 | 2016-06-23 | 2016-06-30 | 2016-07-07 | 2016-07-14 | 2016-07-21 | WINDOW 06 | 2016-07-28 | 2016-08-04 | 2016-08-11 | 2016-08-18 | 2016-08-25 | 2016-09-01 | 2016-09-08 | 2016-09-15 | 2016-09-22 | WINDOW 07 | 2016-09-29 | 2016-10-06 | 2016-10-13 | 2016-10-20 | 2016-10-27 | 2016-11-03 | 2016-11-10 | 2016-11-17 | 2016-11-24 | WINDOW 08 | 2016-12-01 | 2016-12-08 | 2016-12-15 | 2016-12-22 | 2016-12-29 | 2017-01-05 | 2017-01-12 | 2017-01-19 | 2017-01-26 | WINDOW 09 | 2017-02-02 | 2017-02-09 | 2017-02-16 | 2017-02-23 | 2017-03-02 | 2017-03-09 | 2017-03-16 | 2017-03-23 | WINDOW 10 | 2017-03-30 | 2017-04-06 | 2017-04-13 | 2017-04-20 | 2017-04-27 | 2017-05-04 | 2017-05-11 | 2017-05-18 | 2017-05-25 | WINDOW 11 | 2017-06-01 | 2017-06-08 | 2017-06-15 | 2017-06-22 | 2017-06-29 | 2017-07-06 | 2017-07-13 | 2017-07-20 | 2017-07-27 | WINDOW 12 | 2017-08-03 | 2017-08-10 | 2017-08-17 | 2017-08-24 | 2017-08-31 | 2017-09-07 | 2017-09-14 | 2017-09-21 | WINDOW 13 | 2017-09-28 | 2017-10-05 | 2017-10-12 | 2017-10-19 | 2017-10-26 | 2017-11-02 | 2017-11-09 | 2017-11-16 | 2017-11-23 | WINDOW 14 | 2017-11-30 | 2017-12-07 | 2017-12-14 | 2017-12-21 | 2017-12-28 | 2018-01-04 | 2018-01-11 | 2018-01-18 | 2018-01-25 | WINDOW 15 | 2018-02-01 | 2018-02-08 | 2018-02-15 | 2018-02-22 | 2018-03-01 | 2018-03-08 | 2018-03-15 | 2018-03-22 | WINDOW 16 | 2018-03-29 | 2018-04-05 | 2018-04-12 | 2018-04-19 | 2018-04-26 | 2018-05-03 | 2018-05-10 | 2018-05-17 | 2018-05-24 | WINDOW 17 | 2018-05-31 | 2018-06-07 | 2018-06-14 | 2018-06-21 | 2018-06-28 | 2018-07-05 | 2018-07-12 | 2018-07-19 | 2018-07-26 | WINDOW 18 | 2018-08-02 | 2018-08-09 | 2018-08-16 | 2018-08-23 | 2018-08-30 | 2018-09-06 | 2018-09-13 | 2018-09-20 | 2018-09-27 | WINDOW 19 | 2018-10-04 | 2018-10-11 | 2018-10-18 | 2018-10-25 | 2018-11-01 | 2018-11-08 | 2018-11-15 | 2018-11-22 | WINDOW 20 | 2018-11-29 | 2018-12-06 | 2018-12-13 | 2018-12-20 | 2018-12-27 | 2019-01-03 | 2019-01-10 | 2019-01-17 | 2019-01-24 | WINDOW 21 | 2019-01-31 | 2019-02-07 | 2019-02-14 | 2019-02-21 | 2019-02-28 | 2019-03-07 | 2019-03-14 | 2019-03-21 | 2019-03-28 | WINDOW 22 | 2019-04-04 | 2019-04-11 | 2019-04-18 | 2019-04-26 | WINDOW 23
[6 empty] | Planned Period | [10 empty] | 2015-09-30 | [9 empty] | 2015-11-30 | [8 empty] | 2016-01-22 | [9 empty] | 2016-03-25 | [9 empty] | 2016-05-27 | [8 empty] | 2016-07-22 | [9 empty] | 2016-09-23 | [9 empty] | 2016-11-25 | [9 empty] | 2017-01-27 | [8 empty] | 2017-03-24 | [9 empty] | 2017-05-26 | [9 empty] | 2017-07-28 | [8 empty] | 2017-09-22 | [9 empty] | 2017-11-24 | [9 empty] | 2018-01-26 | [8 empty] | 2018-03-23 | [9 empty] | 2018-05-25 | [9 empty] | 2018-07-27 | [9 empty] | 2018-09-28 | [8 empty] | 2018-11-23 | [9 empty] | 2019-01-25 | [9 empty] | 2019-03-29 |  |  |  |  | 2019-04-26
Delayed Period
Delayed Start
Level | Activity ID | Baseline Activity Status | As-Built Activity Status | Activity Name | Planned Start Date | Planned Finsih Date | Actual Start Date | Actual Finish Date
0 |  |  |  | CMEI WORKS FOR EOF PACKAGE
1 |  |  |  | PROJECT MANAGEMENT
2 |  |  |  | PROJECT WIDE/GENERAL - AREA 000
3 |  |  |  | MILESTONE
4 |  |  |  | Contractual Milestone
Act | 2AG000M100100-08000 | Not Started | Completed | Contract Commencement | 2015-10-01 | 2015-10-01 | 2015-10-01 | 2015-10-01
Act | 2AG000M100100-08005 | Not Started | Not Started | Mechanical Completion Certificate (MCC) for Civil Works | 2017-02-28 | 2017-02-28
Act | 2AG000M100100-08010 | Not Started | Not Started | Construction Completion / Subcontract Mechancial Completion for Civil Works | 2017-04-01 | 2017-04-01
Act | 2AG000M100100-08015 | Not Started | Not Started | Mechanical Completion Certificate (MCC) for MEI Works | 2017-12-31 | 2017-12-31
Act | 2AG000M100100-08020 | Not Started | Not Started | Construction Completion / Subcontract Mechancial Completion for MEI Works | 2018-01-31 | 2018-01-31
Act | 2AG000M100100-08025 | Not Started | Completed | LFHO Tank Foundation Completion 52-D-93 | 2016-08-08 | 2016-08-08 | 2016-09-05 | 2016-09-05
Act | 2AG000M100100-08030 | Not Started | Completed | LFHO Tank Foundation Completion 52-D-94 | 2016-08-08 | 2016-08-08 | 2016-08-22 | 2016-08-22
Act | 2AG000M100100-08035 | Not Started | Completed | LFHO Tank Foundation Completion 52-D-95 | 2016-09-13 | 2016-09-13 | 2016-10-09 | 2016-10-09
Act | 2AG000M100100-08040 | Not Started | Completed | LFHO Tank Foundation Completion 52-D-96 | 2016-09-13 | 2016-09-13 | 2016-11-05 | 2016-11-05
4 |  |  |  | Sub-Contract Milestones
Act | 2AG000M505200-08000 | Not Started | Completed | Subcontract Effective Date | 2015-08-06 | 2015-08-06 | 2015-08-06 | 2015-08-06
Act | 2AG000M505200-08015 | Not Started | Completed | Sub-contractor Approval By KOC | 2015-10-18 | 2015-10-18 | 2015-10-20 | 2015-10-20 | bar: 2015-10-15
Act | 2AG000M505200-08020 | Not Started | Completed | Kickoff Meeting | 2015-10-20 | 2015-10-20 | 2015-10-20 | 2015-10-20 | bar: 2015-10-15
Act | 2AG000M505200-08025 | Not Started | Completed | Area Clearance from client for TFC | 2015-10-18 | 2015-10-18 | 2015-10-20 | 2015-10-20 | bar: 2015-10-15
Act | 2AG000M505200-08030 | Not Started | Completed | Construction Completion of temp. facility | 2015-12-31 | 2015-12-31 | 2015-12-31 | 2015-12-31
Act | 2AG000M505200-08035 | Not Started | Completed | Issue First AFC Drawing by PIL | 2015-10-25 | 2015-10-25 | 2016-01-24 | 2016-01-24 | bar: 2015-10-22 to 2015-11-26
Act | 2AG000M505200-08045 | Not Started | Completed | Issue First Equipment/Material by PIL | 2016-03-31 | 2016-03-31 | 2016-03-12 | 2016-03-12
4 |  |  |  | Other PIL Milestone
Act | 2AG000M100100-08045 | Not Started | Completed | COCC Building : Clearance for EIT Works inside the Building | 2017-06-27 | 2017-06-27 | 2018-03-06 | 2018-03-06
Act | 2AG000M100100-08050 | Not Started | Completed | EOF SS: 52-SUBST-301 - SUBSTATION - FMM Readyness for EIT Works inside the Building | 2017-05-27 | 2017-05-27 | 2018-01-01 | 2018-01-01
Act | 2AG000M100100-08055 | Not Started | Completed | EOF SS: 52-SUBST-302 - SUBSTATION - STF Readyness for EIT Works inside the Building | 2017-05-27 | 2017-05-27 | 2018-01-08 | 2018-01-08
Act | 2AG000M100100-08060 | Not Started | Completed | EOF SS: 50-SUBST-001 - SUBSTATION - COCC Readyness for EIT Works inside the Building | 2017-05-27 | 2017-05-27 | 2018-01-20 | 2018-01-20
Act | 2AG000M100100-08065 | Not Started | Completed | EOF SS: 52-SUBST-303 - SUBSTATION - LMM Readyness for EIT Works inside the Building | 2017-05-27 | 2017-05-27 | 2017-11-15 | 2017-11-15
Act | 2AG000M100100-08070 | Not Started | Completed | 52-R-301 - EMERGENCY GENERATOR BUILDING (FMM) Readyness for EIT Works inside the Building | 2017-07-29 | 2017-07-29 | 2018-06-25 | 2018-06-25
Act | 2AG000M100100-08075 | Not Started | Completed | 50-R-002 - EMERGENCY GENERATOR BUILDING (COCC) Readyness for EIT Works inside the Building | 2017-07-29 | 2017-07-29 | 2018-07-23 | 2018-07-23
Act | 2AG000M100100-08080 | Not Started | Completed | 52-R-302 - EMERGENCY GENERATOR BUILDING (STF) Readyness for EIT Works inside the Building | 2017-08-29 | 2017-08-29 | 2018-07-12 | 2018-07-12
Act | 2AG000M100100-08085 | Not Started | Completed | 52-R-303 - EMERGENCY GENERATOR BUILDING (LMM) Readyness for EIT Works inside the Building | 2017-08-29 | 2017-08-29 | 2018-03-06 | 2018-03-06
4 |  |  |  | Piping Tie-In Items
Act | 2AI101MS01400-08005 | Not Started | Completed | EOF: LFHO Storage Tank 52-D-93 - Last Piping Tie-In Works (Piping Installation ) | 2017-12-25 | 2017-12-25 | 2018-10-01 | 2018-10-01
Act | 2AI101MS01400-08010 | Not Started | Completed | EOF: LFHO Storage Tank 52-D-94 - Last Piping Tie-In Works (Piping Installation ) | 2017-12-25 | 2017-12-25 | 2018-10-21 | 2018-10-21
Act | 2AI101MS02600-08005 | Not Started | Completed | EOF: LFHO Storage Tank 52-D-95 - Last Piping Tie-In Works (Piping Installation ) | 2018-01-24 | 2018-01-24 | 2018-10-17 | 2018-10-17
Act | 2AI101MS02600-08010 | Not Started | Completed | EOF: LFHO Storage Tank 52-D-96 - Last Piping Tie-In Works (Piping Installation ) | 2018-01-23 | 2018-01-23 | 2018-10-20 | 2018-10-20
4 |  |  |  | Tank Release By other Subcontractor
Act | 2AI101MS02600-08020 | Not Started | Completed | EOF: Sorage Tank tank 52-D-93: Release After completion of Erection by other sub contract | 2017-06-08 | 2017-06-08 | 2018-07-25 | 2018-07-25
Act | 2AI101MS02600-08025 | Not Started | Completed | EOF: Sorage Tank tank 52-D-94: Release After completion of Erection by other sub contractor | 2017-06-08 | 2017-06-08 | 2018-08-24 | 2018-08-24
Act | 2AI101MS02600-08030 | Not Started | Completed | EOF: Sorage Tank tank 52-D-95: Release After completion of Erection by other sub contractor | 2017-07-13 | 2017-07-13 | 2018-09-15 | 2018-09-15
Act | 2AI101MS02600-08035 | Not Started | Completed | EOF: Sorage Tank tank 52-D-96: Release After completion of Erection by other sub contractor | 2017-07-13 | 2017-07-13 | 2018-09-30 | 2018-09-30
Act | 2AI101MS02600-08040 | Not Started | Not Started | EOF: PIG Release Release After completion of Erection by other sub contractor | 2017-09-02 | 2017-09-02
3 |  |  |  | PROJECT MANAGEMENT
4 |  |  |  | Contractual Submissions & Approval
Act | 2AG000D101401-08000 | Not Started | Completed | Insurance | 2015-10-01 | 2015-10-15 | 2015-10-01 | 2015-10-20 | bar: 2015-10-01 to 2015-10-15
Act | 2AG000D101401-08005 | Not Started | Completed | Organization Chart | 2015-10-11 | 2015-11-21 | 2015-10-15 | 2016-07-13 | bar: 2015-10-08 to 2015-11-26
Act | 2AG000D101401-08010 | Not Started | Completed | CV's of Key Personnel | 2015-10-12 | 2015-11-22 | 2015-10-15 | 2015-12-16 | bar: 2015-10-08 to 2015-11-26
Act | 2AG000D101401-08015 | Not Started | Completed | Deliverable List | 2015-10-13 | 2015-10-27 | 2015-12-10 | 2016-02-24 | bar: 2015-10-08 to 2015-11-26
Act | 2AG000D101401-08020 | Not Started | Completed | Bank Guaranty Submital | 2015-10-13 | 2015-10-14 | 2015-09-26 | 2015-09-26
Act | 2AG000D101401-08025 | Not Started | Completed | Site HSE Plan | 2015-10-17 | 2015-11-26 | 2015-11-23 | 2016-02-20 | bar: 2015-10-15 to 2015-11-26
Act | 2AG000D101401-08030 | Not Started | Completed | Construction Execution Plan | 2015-10-18 | 2015-11-28 | 2015-11-22 | 2016-02-01 | bar: 2015-10-15 to 2015-11-26
Act | 2AG000D101401-08040 | Not Started | Completed | Project Quality Plan | 2015-10-26 | 2015-12-06 | 2015-11-11 | 2016-02-04 | bar: 2015-10-22 to 2015-11-26
Act | 2AG000D101401-08045 | Not Started | Completed | Report formats | 2015-10-26 | 2015-12-06 | 2015-10-31 | 2015-10-31 | bar: 2015-10-22 to 2015-10-29
1 |  |  |  | ENGINEERING BY PIL
2 |  |  |  | ENGINEERING (EXPORT OIL FACILITY - AREA 621 -(100)
3 |  |  |  | ENGINEERING INPUTS FROM PIL
4 |  |  |  | CIVIL / STRUCTURAL / ARCHITECTURAL
5 |  |  |  | EOF - SITE PREPARATION DRAWINGS
Act | 2AE100CV00100-08100 | Not Started | Completed | EOF: Site Preparation AFC drawings - STF | 2016-01-16 | 2016-01-20 | 2016-01-24 | 2016-01-30
Act | 2AE100CV00100-08105 | Not Started | Completed | EOF: Site Preparation AFC drawings - COCC | 2016-02-15 | 2016-02-20 | 2016-02-16 | 2016-02-16
5 |  |  |  | EOF - FOUNDATION DRAWINGS
6 |  |  |  | EOF: AFC drawings for LFHO Storage Tank (621-D-93),(621-D-94),(621-D-95),(621-D-96)
Act | 2AE101CV00800-08100 | Not Started | Completed | EOF: AFC drawings for LFHO Storage Tank (621-D-93) | 2016-04-13 | 2016-04-18 | 2016-02-01 | 2016-04-25
Act | 2AE101CV00800-08105 | Not Started | Completed | EOF: AFC drawings for LFHO Storage Tank (621-D-94) | 2016-04-13 | 2016-04-18 | 2016-02-01 | 2016-04-25
Act | 2AE101CV00800-08110 | Not Started | Completed | EOF: AFC drawings for LFHO Storage Tank (621-D-95) | 2016-05-14 | 2016-05-18 | 2016-02-01 | 2016-04-25
Act | 2AE101CV00800-08115 | Not Started | Completed | EOF: AFC drawings for LFHO Storage Tank (621-D-96) | 2016-05-14 | 2016-05-18 | 2016-02-01 | 2016-04-25
6 |  |  |  | EOF: AFC drawings for Balance Tank
Act | 2AE101CV01000-08100 | Not Started | Completed | EOF: AFC drawings for Diesel Engine Drain Tank (621-D-304A/B) | 2016-04-17 | 2016-04-21 | 2016-04-17 | 2016-04-21
Act | 2AE101CV01000-08105 | Not Started | Completed | EOF: AFC drawings for Diesel Fuel Tank (621-D-307A-D) | 2016-06-13 | 2016-06-18 | 2017-03-21 | 2017-03-21
Act | 2AE101CV01100-08100 | Not Started | Completed | EOF: AFC drawings for Foam Drain Tank (621-D-305A/B) | 2016-04-22 | 2016-04-26 | 2016-04-22 | 2016-04-26
Act | 2AE101CV01100-08105 | Not Started | Completed | EOF: AFC drawings for Flushing Water Drain Tank (621-D-306A/B) | 2016-04-27 | 2016-05-02 | 2016-04-27 | 2016-05-02
Act | 2AE101CV01100-08115 | Not Started | Completed | EOF: AFC drawings for Overhead Water Tank (621-D-309A/B) | 2016-06-14 | 2016-06-19 | 2016-06-16 | 2016-06-19
Act | 2AE101CV01100-08125 | Not Started | Completed | EOF: AFC drawings for Oily Water Transfer Vessel 621-V-301( having Pump - 52-G-303 A/B ) | 2016-10-16 | 2016-10-20 | 2016-07-25 | 2016-07-25
6 |  |  |  | EOF: AFC drawings for Pump
Act | 2AE101CV01200-08100 | Not Started | Completed | EOF: AFC drawings for Trim Pump (621-G-301A/B) | 2016-08-28 | 2016-09-01 | 2017-01-30 | 2017-01-30
6 |  |  |  | EOF: AFC drawings for Foam System Package (621-Z-301A/B)
Act | 2AE101CV01400-08100 | Not Started | Completed | EOF: AFC drawings for Foam System Package (621-Z-301A/B) | 2016-07-27 | 2016-08-01 | 2017-01-17 | 2017-05-27
6 |  |  |  | EOF: AFC drawings for Bund Wall of LFHO Storage Tank
Act | 2AE101CV01300-08100 | Not Started | Completed | EOF: AFC drawings for Bund Wall of LFHO Storage Tank | 2016-06-28 | 2016-07-03 | 2016-11-01 | 2018-05-06 | [66 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [8 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [8 empty] | 0 | [9 empty] | 8 | [9 empty] | 8 | [8 empty] | 6 | [9 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [8 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  |  |  | 0
6 |  |  |  | EOF: AFC drawings for Pipe Supports/Sleeper
Act | 2AE100CV02900-08100 | Not Started | Completed | EOF: AFC drawings for Pipe Supports | 2016-06-13 | 2016-06-18 | 2016-08-11 | 2017-03-21
Act | 2AE100CV02900-08105 | Not Started | Completed | EOF: AFC drawings for Pipe Sleepers | 2016-08-14 | 2016-08-18 | 2016-12-05 | 2017-07-24
6 |  |  |  | EOF: AFC drawings for Ground Supported Platforms
Act | 2AE100CV02600-08100 | Not Started | Completed | EOF: AFC drawings for Ground Supported Platforms | 2016-08-29 | 2016-09-03 | 2016-10-18 | 2017-10-23
6 |  |  |  | EOF: AFC drawings for EIT Supports
Act | 2AE100CV02300-08100 | Not Started | Completed | EOF: AFC drawings for EIT Supports | 2016-09-24 | 2016-09-28 | 2017-06-17 | 2017-07-09
6 |  |  |  | EOF: AFC drawings for Shelter/Sunshade
Act | 2AE100CV02700-08105 | Not Started | Completed | EOF: AFC drawings for Shelter for Trim Pump (621-G-301A/B) | 2016-08-24 | 2016-08-29 | 2017-02-07 | 2017-05-27
Act | 2AE100CV02700-08100 | Not Started | Completed | EOF: AFC drawings for Shelter for Oily Water transfer Pump (621-G-303A/B) | 2016-08-13 | 2016-08-17 | 2016-07-25 | 2016-07-25
Act | 2AE100CV02700-08110 | Not Started | Completed | EOF: AFC drawings for Shelter for Foam System Package (621-Z-301A/B) | 2016-09-24 | 2016-09-28 | 2017-03-21 | 2017-07-24
Act | 2AE100CV02700-08115 | Not Started | Completed | EOF: AFC drawings for Sunshade for Mobile Fire Monitors | 2016-09-24 | 2016-09-28 | 2016-09-24 | 2016-09-28
Act | 2AE100CV02700-08125 | Not Started | Completed | EOF AFC drawings for Miscellanious/ Pump Shelter Foundation | 2016-08-29 | 2016-09-03 | 2017-02-07 | 2017-07-24
6 |  |  |  | EOF: AFC drawings for Transformers for 52-SUBST-303, 52-SUBST-001, 52-SUBST-301 & 52-SUBST-302
Act | 2AE133CV05100-08100 | Not Started | Completed | EOF: AFC drawings for Transformers for 52-SUBST-303, 52-SUBST-001, 52-SUBST-301 & 52-SUBST-302 | 2016-06-28 | 2016-07-03 | 2016-11-12 | 2017-03-21
6 |  |  |  | EOF: AFC drawings for Diesel Fuel Day Tanks of Substations
Act | 2AE133CV05200-08100 | Not Started | Completed | EOF: AFC drawings for Diesel Fuel Day Tanks of Substations | 2016-05-29 | 2016-06-22 | 2016-05-29 | 2017-01-17
6 |  |  |  | EOF: AFC drawings for Shelter of Transformers for 52-SUBST-303/001/301/302
Act | 2AE133CV04400-08100 | Not Started | Completed | EOF: AFC drawings for Shelter of Transformers for 52-SUBST-303, 52-SUBST-001, 52-SUBST-301 & 52-SUBST-302 | 2016-07-14 | 2016-07-19 | 2017-03-21 | 2017-03-21
6 |  |  |  | EOF: AFC drawings for Shelters of Diesel Fuel Day Tanks of Substations
Act | 2AE133CV04500-08100 | Not Started | Completed | EOF: AFC drawings for Shelters of Diesel Fuel Day Tanks of Substations | 2016-07-16 | 2016-07-20 | 2016-07-16 | 2017-06-01
Act | 2AE133CV04000-08100 | Not Started | Completed | EOF: AFC drawings for Car Park Shelters & Other Misc. Shelters | 2016-07-17 | 2016-07-21 | 2016-07-17 | 2017-05-31
5 |  |  |  | EOF - TRENCHES & ROAD CROSSINGS DRAWINGS
Act | 2AE100CV02400-08100 | Not Started | Completed | EOF: AFC drawings for EIT Duct Banks | 2016-06-28 | 2016-07-03 | 2016-05-10 | 2017-03-21
Act | 2AE100CV02400-08110 | Not Started | Completed | EOF: AFC Drawing for Pipe & Cable trench at new Tank Area | 2016-07-03 | 2016-07-09 | 2016-05-10 | 2018-05-06 | [66 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [8 empty] | 0 | [9 empty] | 33 | [9 empty] | 29 | [8 empty] | 38 | [9 empty] | 54 | [9 empty] | 55 | [8 empty] | 52 | [9 empty] | 0 | [9 empty] | 36 | [9 empty] | 0 | [8 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  |  |  | 0
5 |  |  |  | EOF - U/G WORKS DRAWINGS
Act | 2AE100CV01200-08100 | Not Started | Completed | EOF: AFC drawings for Sanitary / Sewer Drains, Manholes & Misc Drain Pits | 2016-04-27 | 2016-06-16 | 2016-07-03 | 2017-05-31
Act | 2AE101CV01100-08110 | Not Started | Completed | EOF: AFC drawings for Drain Tank (621-D-308A/B) | 2016-05-14 | 2016-05-18 | 2017-08-07 | 2017-10-24
Act | 2AE100CV02800-08100 | Not Started | Completed | EOF: AFC drawings for Oily Water Collection Vessel Sump (621-SU-301) | 2016-05-26 | 2016-05-31 | 2016-07-25 | 2016-07-25
Act | 2AE100CV02500-08100 | Not Started | Completed | EOF: AFC drawings for Storm Water Drain Road Crossings | 2016-06-13 | 2016-06-18 | 2016-10-18 | 2017-10-18
5 |  |  |  | EOF - GENERAL/FINISHING DRAWINGS
Act | 2AE100CV00300-08100 | Not Started | Completed | EOF: AFC drawings for Road & Fencing Layout and Cross Section Details | 2016-04-27 | 2016-05-02 | 2016-06-02 | 2017-06-01
5 |  |  |  | COCC - FOUNDATION DRAWINGS
Act | 2AE133CV04000-08105 | Not Started | Completed | COCC: AFC drawings for Car Park Shelters & Other Misc. Shelters | 2016-04-27 | 2016-06-18 | 2017-01-17 | 2017-05-31 | [66 empty] | 0 | [9 empty] | 21 | [9 empty] | 17 | [8 empty] | 5 | [9 empty] | 0 | [9 empty] | 0 | [8 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [8 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [8 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  |  |  | 0
Act | 2AE133CV04000-08110 | Not Started | Completed | COCC: AFC drawings for Fire Water Pump Shelters | 2016-07-12 | 2016-07-17 | 2016-07-12 | 2016-07-17
Act | 2AE133CV04000-08120 | Not Started | Completed | COCC: AFC drawings for Road and Paving | 2016-06-29 | 2016-07-04 | 2017-03-21 | 2017-05-31
5 |  |  |  | COCC - MIGRATION SCOPE
Act | 2AE142CV01100-08100 | Not Started | Completed | COCC: AFC drawings for EIT Cable Trench Routing Layout | 2016-04-27 | 2016-05-02 | 2017-03-21 | 2018-01-09
Act | 2AE142CV01100-08105 | Not Started | Completed | COCC: AFC drawings for EIT Duct Banks | 2016-06-28 | 2016-07-03 | 2017-03-21 | 2017-03-21
5 |  |  |  | EOF - DEMOLISHION/MODIFICATION WORKS
Act | 2AE142CV01000-08100 | Not Started | Completed | EOF: AFC drawings for Demolition of Existing Road and Exisitng Fence Relocation | 2016-03-17 | 2016-03-21 | 2016-03-17 | 2017-05-22 | [66 empty] | 24 | [9 empty] | 31 | [9 empty] | 0 | [8 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [8 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [8 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [8 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  |  |  | 0
Act | 2AE142CV01000-08105 | Not Started | Completed | EOF: AFC drawings for Existing U/G Cable Re-Routing & Relocation of RMU | 2016-03-14 | 2016-03-18 | 2016-05-11 | 2016-05-11
5 |  |  |  | EOF: Filling Manifold Auto Sampling Package (52-Z-305) Shelter
Act | 2AE100CV02700-08120 | Not Started | Completed | EOF: AFC drawings for Filling Manifold Auto Sampling Package (52-Z-305) & (52-Z-306) Shelter Foundation | 2016-09-26 | 2016-10-01 | 2016-09-26 | 2016-10-01
Act | 2AE100CV02700-08220 | Not Started | Completed | EOF: AFC drawings for Filling Manifold Auto Sampling Package (52-Z-305)& (52-Z-306) Shelter Erection | 2016-12-24 | 2016-12-28 | 2016-12-24 | 2016-12-28
4 |  |  |  | ELECTRICAL
5 |  |  |  | EOF - CABLE TRENCH L/O
Act | 2AE100EL03600-08100 | Not Started | Completed | EOF: AFC drawings for Electrical Cable Trench & Tray Routing Layout | 2017-02-14 | 2017-05-31 | 2017-01-17 | 2018-01-09
6 |  |  |  | MG-1 SUBSTATION TIE-INS
Act | 2AI104EL20100-08100 | Not Started | Completed | EOF: Issue AFC Drawings MG-1 SUBSTATION TIE-INS | 2016-12-24 | 2016-12-28 | 2017-01-17 | 2017-06-07
6 |  |  |  | POWER CABLE BETWEEN SUBSTATION
Act | 2AI102EL01000-08100 | Not Started | Completed | EOF: Issue AFC Drawings POWER CABLE BETWEEN SUBSTATION | 2017-02-09 | 2017-02-14 | 2017-01-17 | 2017-06-07
6 |  |  |  | POWER CABLE FROM SUBSTATION
Act | 2AI102EL01100-08100 | Not Started | Completed | EOF: Issue AFC Drawings POWER CABLE FROM SUBSTATION | 2017-02-09 | 2017-02-14 | 2017-03-02 | 2017-10-18
6 |  |  |  | INSTRUMENTATION CABLE FROM SUBSTATION
Act | 2AI102IC01000-08100 | Not Started | Completed | EOF: Issue AFC Drawings INSTRUMENTATION CABLE FROM SUBSTATION | 2017-02-09 | 2017-02-14 | 2017-06-01 | 2017-06-01
6 |  |  |  | FIRE ALARM CABLE WORKS
Act | 2AI102IC01100-08100 | Not Started | Completed | EOF: Issue AFC Drawings FIRE ALARM CABLE WORKS | 2017-07-13 | 2017-07-18 | 2017-03-02 | 2018-02-27
6 |  |  |  | TELECOM CABLE LAYING TO COCC
Act | 2AI102TE01000-08100 | Not Started | Completed | EOF: Issue AFC Drawings TELECOM CABLE LAYING TO COCC | 2017-03-30 | 2017-04-04 | 2017-07-24 | 2017-12-14
6 |  |  |  | TELECOM CABLE LAYING FROM COCC TO SUBSTATION
Act | 2AI102TE01100-08100 | Not Started | Completed | EOF: Issue AFC DrawingsTELECOM CABLE LAYING FROM COCC TO SUBSTATION | 2017-03-30 | 2017-04-04 | 2017-07-24 | 2017-12-14
6 |  |  |  | EOF:AFC Drawing Cable Trench out Side STF(Between SBH LCR/SICB LCRKNPC SPLCR/NNTF LCR/NPP & MS LCR)
5 |  |  |  | EOF: COCC Building Drawing
Act | 2AE141EL00100-08100 | Not Started | Completed | EOF: COCC CCR Building 621-R-001: AFC Drawing for Single Line Diagram | 2016-08-13 | 2016-08-17 | 2017-09-19 | 2017-09-19
Act | 2AE100EL00200-08100 | Not Started | Completed | EOF: COCC CCR Building 621-R-001: AFC Drawing for Earthing & lightning Layout | 2017-01-14 | 2017-01-18 | 2017-05-31 | 2017-05-31
Act | 2AE100IC02900-08110 | Not Started | Completed | EOF: COCC CCR Building 621-R-001: AFC Drawing for Cable Schedule & Cable Cutting Schedule | 2017-01-28 | 2017-02-01 | 2018-03-02 | 2018-03-02
Act | 2AE100IC02900-08120 | Not Started | Completed | EOF: COCC CCR Building 621-Rï¿½-001: AFC Drawing for Equipment layout | 2016-09-13 | 2016-09-18 | 2017-09-19 | 2017-10-17
Act | 2AE100IC02900-08111 | Not Started | Completed | EOF: COCC CCR Building 621-R-001: AFC Drawing for Cable Termination Schedule | 2017-04-27 | 2017-05-02 | 2018-02-24 | 2018-02-27
5 |  |  |  | EOF: Substation 52-SUBT-301 FMM Drawing
Act | 2AE133EL02300-08100 | Not Started | Completed | EOF: Substation 52-SUBT-301: AFC Drawing for Equipment layout | 2016-09-13 | 2016-09-18 | 2017-10-11 | 2018-02-27
Act | 2AE133EL01000-08100 | Not Started | Completed | EOF: Substation 52-SUBT-301: AFC Drawing for Single Line Diagram | 2016-08-13 | 2016-08-17 | 2018-02-05 | 2018-02-05
Act | 2AE133EL03600-08100 | Not Started | Completed | EOF: Substation 52-SUBT-301: AFC Drawing for Earthing & lightning Layout | 2017-01-12 | 2017-01-17 | 2017-09-20 | 2017-09-20
Act | 2AE100IC02900-08200 | Not Started | Completed | EOF: Substation 52-SUBT-301: AFC Drawing for Cable Termination Schedule | 2017-04-27 | 2017-05-02 | 2018-02-24 | 2018-02-27
Act | 2AE100IC02900-08190 | Not Started | Completed | EOF: Substation 52-SUBT-301: AFC Drawing for Cable Schedule & Cable Cutting Schedule | 2017-01-28 | 2017-02-01 | 2017-12-19 | 2017-12-19
5 |  |  |  | EOF: Substation 52-SUBT-302 STF Drawing
Act | 2AE133EL02400-08100 | Not Started | Completed | EOF: Substation 52-SUBT-302: AFC Drawing for Equipment layout | 2016-09-13 | 2016-09-18 | 2017-10-11 | 2017-10-11
Act | 2AE133EL01400-08100 | Not Started | Completed | EOF: Substation 52-SUBT-302: AFC Drawing for Single Line Diagram | 2016-08-13 | 2016-08-17 | 2018-02-05 | 2018-02-05
Act | 2AE133EL03700-08100 | Not Started | Completed | EOF: Substation 52-SUBT-302: AFC Drawing for Earthing & lightning Layout | 2017-01-12 | 2017-01-17 | 2017-09-20 | 2017-09-20
Act | 2AE100EL00300-08100 | Not Started | Completed | EOF: Substation 52-SUBT-302: AFC Drawing for Cable Schedule & Cable Cutting Schedule | 2017-01-28 | 2017-02-01 | 2017-05-04 | 2017-11-27
Act | 2AE100EL00300-08110 | Not Started | Completed | EOF: Substation 52-SUBT-302: AFC Drawing for Cable Termination Schedule | 2017-04-27 | 2017-05-02 | 2018-02-24 | 2018-02-27
5 |  |  |  | EOF: Substation 52-SUBT-303 LMM Drawing
Act | 2AE133EL02500-08100 | Not Started | Completed | EOF: Substation 52-SUBT-303: AFC Drawing for Equipment layout | 2016-09-13 | 2016-09-18 | 2017-10-17 | 2017-10-17
Act | 2AE133EL02100-08100 | Not Started | Completed | EOF: Substation 52-SUBT-303: AFC Drawing for Single Line Diagram | 2016-08-13 | 2016-08-17 | 2018-02-24 | 2018-02-27
Act | 2AE133EL03800-08100 | Not Started | Completed | EOF: Substation 52-SUBT-303: AFC Drawing for Earthing & lightning Layout | 2017-01-12 | 2017-01-17 | 2017-09-30 | 2017-09-30
Act | 2AE100EL00400-08100 | Not Started | Completed | EOF: Substation 52-SUBT-303: AFC Drawing for Cable Schedule & Cable Cutting Schedule | 2017-01-28 | 2017-02-01 | 2017-09-14 | 2018-01-09
Act | 2AE100IC02900-08400 | Not Started | Completed | EOF: Substation 52-SUBT-303: AFC Drawing for Cable Termination Schedule | 2017-04-27 | 2017-05-02 | 2018-02-24 | 2018-02-27
5 |  |  |  | EOF: COCC Substation 50-SUBT-001 COCC Drawing
Act | 2AE133EL02200-08100 | Not Started | Completed | COCC: Substation 52-SUBT-001: AFC Drawing for Equipment layout | 2016-09-13 | 2016-09-18 | 2017-10-17 | 2017-10-17
Act | 2AE133EL00600-08100 | Not Started | Completed | COCC: Substation 52-SUBT-001: AFC Drawing for Single Line Diagram | 2016-08-13 | 2016-08-17 | 2017-12-23 | 2018-02-27
Act | 2AE133EL03500-08100 | Not Started | Completed | COCC: Substation 52-SUBT-001: AFC Drawing for Earthing & lightning Layout | 2017-01-12 | 2017-01-17 | 2017-05-31 | 2017-05-31
Act | 2AE100EL00200-08210 | Not Started | Completed | COCC: Substation 52-SUBT-001: AFC Drawing for Cable Schedule & Cable Cutting Schedule | 2017-01-28 | 2017-02-01 | 2018-02-24 | 2018-02-27
Act | 2AE100IC02900-08500 | Not Started | Completed | COCC: Substation 52-SUBT-001: AFC Drawing for Cable Termination Schedule | 2017-04-27 | 2017-05-02 | 2018-02-24 | 2018-02-27
5 |  |  |  | 52-R-301 - EMERGENCY GENERATOR BUILDING (FMM) Readyness for EIT Works inside the Building
Act | 2AE133EL05800-08100 | Not Started | Completed | 52-R-301 - AFC Drawing for Equipment layout | 2016-09-13 | 2016-09-18 | 2017-07-24 | 2018-02-27
Act | 2AE133EL01000-08200 | Not Started | Completed | 52-R-301 - AFC Drawing for Single Line Diagram | 2016-08-13 | 2016-08-17 | 2017-09-19 | 2018-02-27
Act | 2AE133EL03600-08200 | Not Started | Completed | 52-R-301 - AFC Drawing for Earthing & lightning Layout | 2017-01-12 | 2017-01-17 | 2018-02-24 | 2018-02-27
Act | 2AE100EL00200-08200 | Not Started | Completed | 52-R-301 - AFC Drawing for Cable Schedule & Cable Cutting Schedule | 2017-01-28 | 2017-02-01 | 2018-02-24 | 2018-02-27
Act | 2AE100IC02900-08600 | Not Started | Completed | 52-R-301 - AFC Drawing for Cable Termination Schedule | 2017-04-27 | 2017-05-02 | 2018-02-24 | 2018-02-27
5 |  |  |  | 50-R-002 - EMERGENCY GENERATOR BUILDING (COCC) Readyness for EIT Works inside the Building
Act | 2AE133EL05800-08200 | Not Started | Completed | 52-R-002 - AFC Drawing for Equipment layout | 2016-09-13 | 2016-09-18 | 2017-10-17 | 2018-02-27
Act | 2AE133EL00600-08200 | Not Started | Completed | 52-R-002 - AFC Drawing for Single Line Diagram | 2016-08-13 | 2016-08-17 | 2017-09-19 | 2018-02-27
Act | 2AE100EL00200-08300 | Not Started | Completed | 52-R-002 - AFC Drawing for Cable Schedule & Cable Cutting Schedule | 2017-01-28 | 2017-02-01 | 2018-02-24 | 2018-02-27
Act | 2AE100IC02900-08700 | Not Started | Completed | 52-R-002 - AFC Drawing for Cable Termination Schedule | 2017-04-27 | 2017-05-02 | 2018-02-24 | 2018-02-27
5 |  |  |  | 52-R-302 - EMERGENCY GENERATOR BUILDING (STF) Readyness for EIT Works inside the Building
Act | 2AE133EL05800-08300 | Not Started | Completed | 52-R-302 - AFC Drawing for Equipment layout | 2016-09-13 | 2016-09-18 | 2017-07-24 | 2018-02-27
Act | 2AE133EL01400-08200 | Not Started | Completed | 52-R-302 - AFC Drawing for Single Line Diagram | 2016-08-13 | 2016-08-17 | 2017-09-19 | 2018-02-24
Act | 2AE100EL00300-08200 | Not Started | Completed | 52-R-302 - AFC Drawing for Cable Schedule & Cable Cutting Schedule | 2017-01-28 | 2017-02-01 | 2018-02-24 | 2018-02-27
Act | 2AE100IC02900-08800 | Not Started | Completed | 52-R-302 - AFC Drawing for Cable Termination Schedule | 2017-04-27 | 2017-05-02 | 2018-02-24 | 2018-02-27
5 |  |  |  | 52-R-303 - EMERGENCY GENERATOR BUILDING (LMM) Readyness for EIT Works inside the Building
Act | 2AE133EL05800-08400 | Not Started | Completed | 52-R-303 - AFC Drawing for Equipment layout | 2016-09-13 | 2016-09-18 | 2018-02-24 | 2018-02-27
Act | 2AE133EL02100-08200 | Not Started | Completed | 52-R-303 - AFC Drawing for Single Line Diagram | 2016-08-13 | 2016-08-17 | 2017-09-19 | 2018-02-27
Act | 2AE100EL00400-08200 | Not Started | Completed | 52-R-303 - AFC Drawing for Cable Schedule & Cable Cutting Schedule | 2017-01-28 | 2017-02-01 | 2018-02-24 | 2018-02-27
Act | 2AE100IC02900-08900 | Not Started | Completed | 52-R-303 - AFC Drawing for Cable Termination Schedule | 2017-04-27 | 2017-05-02 | 2018-02-24 | 2018-02-27
4 |  |  |  | PIPING
5 |  |  |  | GA
Act | 2AE100PI01300-08100 | Not Started | Completed | EOF : Piping GAD for South Tank Farm | 2016-11-26 | 2017-02-06 | 2017-03-02 | 2018-04-11
Act | 2AE100PI01300-08110 | Not Started | Completed | EOF : Piping GAD for COCC | 2016-11-28 | 2016-12-03 | 2017-10-18 | 2017-10-18
5 |  |  |  | ISOMETRICS
Act | 2AE100PI01400-08100 | Not Started | Completed | EOF : Isometrics Book for South Tank Farm | 2017-01-26 | 2017-05-16 | 2017-11-20 | 2018-10-11 | [66 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [8 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [8 empty] | 2 | [9 empty] | 26 | [9 empty] | 0 | [8 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [8 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  |  |  | 0
Act | 2AE100PI01400-08110 | Not Started | Completed | EOF : Isometrics Book for COCC | 2016-08-10 | 2016-08-15 | 2017-06-01 | 2017-11-23
4 |  |  |  | INSTRUMENTATION
5 |  |  |  | LAYOUTS
Act | 2AE100IC02200-08100 | Not Started | Completed | EOF: AFC drawings for Cable Trench & Tray Routing Layout | 2017-02-11 | 2017-02-15 | 2017-06-01 | 2017-06-01
Act | 2AE100IC02400-08100 | Not Started | Completed | EOF: AFC drawings for Instrument Location Layout | 2017-02-26 | 2017-03-02 | 2017-06-01 | 2018-02-27
Act | 2AE100IC02900-08100 | Not Started | Completed | EOF: AFC drawings for Instrument Termination Drawing | 2017-06-12 | 2017-06-17 | 2017-12-23 | 2018-04-18
4 |  |  |  | TELECOM
5 |  |  |  | BLOCK DIAGRAMS
Act | 2AE100TE00200-08100 | Not Started | Completed | Interconnection & Termination Drawing | 2017-06-12 | 2017-06-17 | 2017-05-31 | 2018-02-27
Act | 2AE100TE00200-08110 | Not Started | Completed | EOF: AFC drawings for Cable Trench & Tray Routing Layout | 2016-08-11 | 2016-08-16 | 2017-05-31 | 2018-02-27
4 |  |  |  | CP WORKS
Act | 2AE100MC00100-08100 | Not Started | Completed | EOF: AFC drawings for CP Works Out side Tank | 2016-08-07 | 2016-08-11 | 2017-12-23 | 2017-12-26
Act | 2AE100MC00100-08110 | Not Started | Completed | EOF:AFC Drawings for CP Works at Tanks 621-D-93/94/95/96 | 2016-05-09 | 2016-05-14 | 2016-07-31 | 2016-11-16
1 |  |  |  | PROCUREMENT BY PIL
2 |  |  |  | EQUIPMENT & PACKAGES - STF Area
3 |  |  |  | MECHANICAL STATIC
Act | 2AP000MS00507-08000 | Not Started | Completed | EOF: Overhead Water Tank (52-D-309 A) | 2017-02-12 | 2017-02-16 | 2017-02-12 | 2017-02-16
Act | 2AP000MS00507-08005 | Not Started | Completed | EOF: Overhead Water Tank (52-D-309 B) | 2017-03-12 | 2017-03-16 | 2017-03-12 | 2017-03-16
Act | 2AP000MS00507-08010 | Not Started | Completed | EOF: Diesel Engine drain tank-52-D-304A | 2017-03-12 | 2017-03-16 | 2017-03-12 | 2017-03-16
Act | 2AP000MS00507-08015 | Not Started | Completed | EOF: Diesel Engine drain tank-52-D-304B | 2017-03-12 | 2017-03-16 | 2017-03-12 | 2017-03-16
Act | 2AP000HS00507-08010 | Not Started | Completed | EOF: Foam drain tank-52-D-305A | 2017-04-11 | 2017-04-16 | 2017-04-11 | 2017-04-16
Act | 2AP000HS00507-08015 | Not Started | Completed | EOF: Foam drain tank-52-D-305B | 2017-04-12 | 2017-04-17 | 2017-04-12 | 2017-04-17
Act | 2AP000MS00507-08030 | Not Started | Completed | EOF: Flushing Water drain tank-52-D-306A | 2017-04-12 | 2017-04-17 | 2017-04-12 | 2017-04-17
Act | 2AP000MS00507-08035 | Not Started | Completed | EOF: Flushing Water drain tank-52-D-306B | 2017-04-12 | 2017-04-17 | 2017-04-12 | 2017-04-17
Act | 2AP000MS00507-08040 | Not Started | Completed | EOF: Water drain tank-52-D-308 A | 2017-02-12 | 2017-02-16 | 2017-02-12 | 2017-02-16
Act | 2AP000MS00507-08045 | Not Started | Completed | EOF: Water drain tank-52-D-308 B | 2017-02-12 | 2017-02-16 | 2017-02-12 | 2017-02-16
Act | 2AP000MS00107-08000 | Not Started | Completed | EOF: 621-V-301 Oily Water Collection Vessell | 2017-05-11 | 2017-05-16 | 2017-04-24 | 2017-04-24
Act | 2AP000MS00507-08050 | Not Started | Completed | EOF: Diesel Fuel Tank 621-D307 A | 2017-05-11 | 2017-05-16 | 2017-10-02 | 2017-10-02
Act | 2AP000MS00507-08055 | Not Started | Completed | EOF: Diesel Fuel Tank 621-D307 B | 2017-05-11 | 2017-05-16 | 2017-10-02 | 2017-10-02
Act | 2AP000MS00507-08060 | Not Started | Completed | EOF: Diesel Fuel Tank 621-D307 C | 2017-06-12 | 2017-06-17 | 2017-10-02 | 2017-10-02
Act | 2AP000MS00507-08065 | Not Started | Completed | EOF: Diesel Fuel Tank 621-D307 D | 2017-06-12 | 2017-06-17 | 2017-10-02 | 2017-10-02
Act | 2AP000MS00507-08075 | Not Started | Completed | EG Building 52-R-301 : Diesel Day Tank | 2017-05-30 | 2017-06-04 | 2017-12-30 | 2017-12-30
Act | 2AP000MS00507-08085 | Not Started | Completed | EG Building 52-R-303 : Diesel Day Tank | 2017-05-30 | 2017-06-04 | 2017-12-21 | 2017-12-21
Act | 2AP000MS00507-08095 | Not Started | Completed | EG Building 52-R-302 : Diesel Day Tank | 2017-06-24 | 2017-06-28 | 2018-01-20 | 2018-01-20
Act | 2AP000MS00507-08105 | Not Started | Completed | EG Building 50-R-002 : Diesel Day Tank | 2017-06-24 | 2017-06-28 | 2018-05-15 | 2018-05-15
3 |  |  |  | MECHANICAL ROTATING
Act | 2AP000MR01807-08000 | Not Started | Completed | EOF: 621-G-301 A Trim Pump | 2017-06-12 | 2017-06-17 | 2018-02-28 | 2018-02-28
Act | 2AP000MR01807-08005 | Not Started | Completed | EOF: 621-G-301 B Trim Pump | 2017-07-12 | 2017-07-17 | 2018-02-28 | 2018-02-28
Act | 2AP000MR01807-08010 | Not Started | Completed | 52-GM-301A:Variable Speed Drives | 2017-06-12 | 2017-06-17 | 2018-02-28 | 2018-02-28
Act | 2AP000MR01807-08015 | Not Started | Completed | 52-GM-301B:Variable Speed Drives | 2017-07-12 | 2017-07-17 | 2018-02-28 | 2018-02-28
Act | 2AP000MR00307-08040 | Not Started | Completed | EOF: 621-G-303 A Oily Water Transfer Pump | 2017-06-12 | 2017-06-17 | 2018-04-18 | 2018-04-18
Act | 2AP000MR00307-08045 | Not Started | Completed | EOF: 621-G-303 B Oily Water Transfer Pump | 2017-07-12 | 2017-07-17 | 2018-04-18 | 2018-04-18
Act | 2AP000HS00507-08020 | Not Started | Completed | EOF: 621-G-302 A Foam Pump | 2017-07-12 | 2017-07-17 | 2018-04-07 | 2018-04-07
Act | 2AP000HS00507-08025 | Not Started | Completed | EOF: 621-G-302 B Foam Pump | 2017-07-12 | 2017-07-17 | 2018-04-07 | 2018-04-07
Act | 2AP000HS00507-08030 | Not Started | Completed | EOF: 621-G-302 C Foam Pump | 2017-07-12 | 2017-07-17 | 2018-04-07 | 2018-04-07
Act | 2AP000HS00507-08035 | Not Started | Completed | EOF: 621-G-302 D Foam Pump | 2017-07-12 | 2017-07-17 | 2018-04-07 | 2018-04-07
3 |  |  |  | STRUCTURAL STEEL
Act | 2AI151CV99920-08000 | Not Started | Completed | EOF: Delivery of Structural steel for Shelters - Lot-1 | 2016-10-27 | 2016-11-01 | 2016-11-20 | 2018-02-27
Act | 2AI151CV99930-08000 | Not Started | Completed | EOF: Delivery of Structural steel for Shelters - Lot-2 | 2017-01-26 | 2017-01-31 | 2017-03-06 | 2018-01-04
Act | 2AI151CV99940-08000 | Not Started | Completed | EOF: Delivery of Structural steel for Shelters - Lot-3 | 2017-03-27 | 2017-04-01 | 2017-03-06 | 2018-01-04
Act | 2AI151CV99920-08005 | Not Started | Completed | EOF: Delivery of Structural steel for Ground Support Platforms - Lot-1 | 2017-01-26 | 2017-01-31 | 2017-04-16 | 2017-04-16
Act | 2AI151CV99930-08005 | Not Started | Completed | EOF: Delivery of Structural steel for Ground Support Platforms - Lot-2 | 2017-03-12 | 2017-03-16 | 2017-04-18 | 2017-04-18
Act | 2AI151CV99940-08005 | Not Started | Completed | EOF: Delivery of Structural steel for Ground Support Platforms - Lot-3 | 2017-04-27 | 2017-05-02 | 2017-06-01 | 2018-04-22
Act | 2AI151CV99920-08010 | Not Started | Completed | EOF: Delivery of steel for Pipesupports, EIT/HSE supports & misc steel (handrails, ladders,etc) - Lot-1 | 2017-01-26 | 2017-01-31 | 2017-04-25 | 2018-05-15
Act | 2AI151CV99930-08010 | Not Started | Completed | EOF: Delivery of steel for Pipesupports, EIT/HSE supports & misc steel (handrails, ladders,etc) - Lot-2 | 2017-03-12 | 2017-03-16 | 2017-11-25 | 2018-02-27
Act | 2AI151CV99940-08010 | Not Started | Completed | EOF: Delivery of steel for Pipesupports, EIT/HSE supports & misc steel (handrails, ladders,etc) - Lot-3 | 2017-04-27 | 2017-05-02 | 2017-03-06 | 2018-05-15
3 |  |  |  | CP WORKS
Act | 2AP000EL00207-08010 | Not Started | Completed | Transformer Rectifier | 2017-06-12 | 2017-06-17 | 2018-02-24 | 2018-02-27
Act | 2AE800MC02100-08005 | Not Started | Completed | Delivery of Cathodic Protection System - First Lot | 2016-07-09 | 2016-07-13 | 2016-08-12 | 2018-02-24
3 |  |  |  | ELECTRICAL
4 |  |  |  | 11KV & 3.3KV SWITCHGEAR & HV BUSDUCT
Act | 2AP000EL00107-08000 | Not Started | Completed | 11KV & 3.3KV SWITCHGEAR & HV BUSDUCT - First Lot | 2017-08-12 | 2017-08-16 | 2017-09-18 | 2017-09-18
Act | 2AP000EL00107-08005 | Not Started | Completed | 11KV & 3.3KV SWITCHGEAR & HV BUSDUCT- Final Lot | 2017-10-12 | 2017-10-17 | 2017-12-23 | 2017-12-26
4 |  |  |  | DISTRIBUTION & LIGHTING TRANSFORMER
Act | 2AP000EL00207-08000 | Not Started | Completed | DISTRIBUTION & LIGHTING TRANSFORMER - First Lot | 2017-05-11 | 2017-05-16 | 2017-04-15 | 2017-05-09
Act | 2AP000EL00207-08005 | Not Started | Completed | DISTRIBUTION & LIGHTING TRANSFORMER- Final Lot | 2017-07-12 | 2017-07-17 | 2017-05-09 | 2018-01-14
4 |  |  |  | EMERGENCY DIESEL GENERATOR SETS
Act | 2AP000EL00507-08000 | Not Started | Completed | EMERGENCY DIESEL GENERATOR SETS - First Lot | 2017-06-13 | 2017-06-18 | 2018-02-24 | 2018-03-29
Act | 2AP000EL00507-08005 | Not Started | Completed | EMERGENCY DIESEL GENERATOR SETS- Final Lot | 2017-09-12 | 2017-09-17 | 2018-02-24 | 2018-03-08
4 |  |  |  | 440V LV SWITCHGEAR & LV BUSDUCT
Act | 2AP000EL00607-08000 | Not Started | Completed | 440V LV SWITCHGEAR & LV BUSDUCT - First Lot | 2017-07-12 | 2017-07-17 | 2017-09-18 | 2017-09-18
Act | 2AP000EL00607-08005 | Not Started | Completed | 440V LV SWITCHGEAR & LV BUSDUCT- Final Lot | 2017-10-12 | 2017-10-17 | 2017-12-13 | 2017-12-26
4 |  |  |  | AC UPS & DC UPS
Act | 2AP000EL00707-08000 | Not Started | Completed | AC UPS & DC UPS - First Lot | 2017-09-12 | 2017-09-17 | 2018-01-21 | 2018-01-24
Act | 2AP000EL00707-08005 | Not Started | Completed | AC UPS & DC UPS- Final Lot | 2017-11-12 | 2017-11-16 | 2017-12-23 | 2018-02-27
4 |  |  |  | E-SCADA SYSTEM
Act | 2AP000EL00807-08000 | Not Started | Completed | E-SCADA SYSTEM Lot 1 | 2017-06-12 | 2017-06-17 | 2017-12-23 | 2018-03-11
Act | 2AP000EL00807-08005 | Not Started | Completed | E-SCADA SYSTEM lot 2 | 2017-08-12 | 2017-08-16 | 2017-12-23 | 2018-02-27
4 |  |  |  | ELECTRICAL HEAT TRACING SYSTEM
Act | 2AP000EL02607-08000 | Not Started | Completed | ELECTRICAL HEAT TRACING SYSTEM - First Lot | 2017-03-28 | 2017-04-02 | 2018-02-24 | 2018-02-27
Act | 2AP000EL02607-08005 | Not Started | Completed | ELECTRICAL HEAT TRACING SYSTEM- Final Lot | 2017-09-26 | 2017-10-01 | 2018-02-24 | 2018-02-27
4 |  |  |  | LIGHTING & POWER PANELS & db'S
Act | 2AE100IC02900-08101 | Not Started | Completed | MAIN FUSE PANEL, POWER PANEL, SUB FEEDER POWER PANEL, CATHODIC PROTECTION DB & MOV DB | 2017-06-17 | 2017-06-21 | 2017-12-20 | 2018-02-27
Act | 2AP000EL01007-08005 | Not Started | Completed | INDUSTRIAL TYPE LIGHTING & POWER PANELS - First Lot | 2017-06-12 | 2017-06-17 | 2018-01-15 | 2018-02-27
Act | 2AP000EL01007-08010 | Not Started | Completed | INDUSTRIAL TYPE LIGHTING & POWER PANELS- Final Lot | 2017-10-12 | 2017-10-17 | 2018-02-24 | 2018-02-27
Act | 2AP000EL01007-08015 | Not Started | Completed | HAZARDOUS TYPE LIGHTING & POWER PANELS - First Lot | 2017-06-12 | 2017-06-17 | 2018-01-14 | 2018-02-27
Act | 2AP000EL01007-08020 | Not Started | Completed | HAZARDOUS TYPE LIGHTING & POWER PANELS- Final Lot | 2017-10-12 | 2017-10-17 | 2018-02-24 | 2018-02-27
4 |  |  |  | MODIFICATION WORK IN EXISTING 11kV SWITCHGEAR
Act | 2AI133EL03300-08100 | Not Started | Completed | MODIFICATION WORK IN EXISTING 11kV SWITCHGEAR AND IT'S ASSOCIATED WORKS IN MG-1 SUBSTATION | 2017-07-12 | 2017-07-17 | 2018-02-24 | 2018-02-27
4 |  |  |  | Annunciator Panels & RCP
3 |  |  |  | INSTRUMENTATION
4 |  |  |  | PIPING VALVES - SHIPMENT
Act | 2AP000IC00107-08000 | Not Started | Completed | EOF : Delivery of Control Valves - First Lot-1 | 2017-02-22 | 2017-02-27 | 2017-12-18 | 2018-04-05
Act | 2AP000IC00107-08005 | Not Started | Completed | EOF : Delivery of Control Valves - Lot-2 | 2017-07-11 | 2017-07-16 | 2018-02-24 | 2018-04-05
Act | 2AP000IC00107-08010 | Not Started | Completed | EOF : Delivery of Control Valves - Last Lot-3 | 2017-11-27 | 2017-12-02 | 2018-02-24 | 2018-04-05
Act | 2AP000IC00207-08000 | Not Started | Completed | EOF : Delivery of Shutdown Valves (Ball/Butterfly Type) & ESD Valves - First Lot-1 | 2017-02-22 | 2017-02-27 | 2018-02-24 | 2018-02-27
Act | 2AP000IC00207-08005 | Not Started | Completed | EOF : Delivery of Shutdown Valves (Ball/Butterfly Type) & ESD Valves - Lot-2 | 2017-07-11 | 2017-07-16 | 2018-02-24 | 2018-02-27
Act | 2AP000IC00207-08010 | Not Started | Completed | EOF : Delivery of Shutdown Valves (Ball/Butterfly Type) & ESD Valves - Last Lot-3 | 2017-11-27 | 2017-12-02 | 2018-02-24 | 2018-02-27
Act | 2AP000IC00407-08000 | Not Started | Completed | EOF : Delivery of Motor Operated Valves (Ball/Butterfly/Gate Type) - First Lot-1 | 2017-02-22 | 2017-02-27 | 2017-11-13 | 2018-02-27
Act | 2AP000IC00407-08005 | Not Started | Completed | EOF : Delivery of Motor Operated Valves (Ball/Butterfly/Gate Type) - Lot-2 | 2017-07-11 | 2017-07-16 | 2018-02-24 | 2018-02-27
Act | 2AP000IC00407-08010 | Not Started | Completed | EOF : Delivery of Motor Operated Valves (Ball/Butterfly/Gate Type) - Last Lot-3 | 2017-11-27 | 2017-12-02 | 2018-02-24 | 2018-02-27
4 |  |  |  | GAUGES ( PRESSURE, TEMPERATURE & LEVEL)
Act | 2AP000IC00907-08000 | Not Started | Completed | EOF : Delivery of Level Gauges, Pressure Gauges & Temperature Guages - First Lot-1 | 2017-06-12 | 2017-06-17 | 2018-02-24 | 2018-02-27
Act | 2AP000IC01007-08000 | Not Started | Completed | EOF : Delivery of Level Gauges, Pressure Gauges & Temperature Guages - Lot-2 | 2017-09-12 | 2017-09-17 | 2018-02-24 | 2018-02-27
Act | 2AP000IC01307-08000 | Not Started | Completed | EOF : Delivery of Level Gauges, Pressure Gauges & Temperature Guages - Last Lot-3 | 2017-11-12 | 2017-11-16 | 2018-02-24 | 2018-02-27
4 |  |  |  | FLOWMETER
Act | 2AP000IC02207-08005 | Not Started | Completed | EOF : Delivery of Flowmeters - First Lot-1 | 2017-07-12 | 2017-07-17 | 2018-02-24 | 2018-02-27
Act | 2AP000IC02607-08005 | Not Started | Completed | EOF : Delivery of Flowmeters - Lot-2 | 2017-09-12 | 2017-09-17 | 2018-02-24 | 2018-02-27
Act | 2AP000IC05507-08005 | Not Started | Completed | EOF : Delivery of Flowmeters - Last Lot-3 | 2017-11-12 | 2017-11-16 | 2018-02-24 | 2018-02-27
4 |  |  |  | FIRE AND GAS DEVICES
4 |  |  |  | INTEGRATED CONTROL AND SAFETY SYSTEM(ICSS) -COCC
Act | 2AP000IC06807-08100 | Not Started | Completed | EOF : Delivery of Integrated Control And Safety System (ICSS) - First Lot | 2017-10-12 | 2017-10-17 | 2018-02-24 | 2018-02-27
4 |  |  |  | TRANSMITTERS
Act | 2AP000IC01407-08010 | Not Started | Completed | EOF : Delivery of Level Transmitters & Level Switches - First Lot - 1 | 2017-07-12 | 2017-07-17 | 2018-02-24 | 2018-02-27
Act | 2AP000IC01707-08010 | Not Started | Completed | EOF : Delivery of Level Transmitters & Level Switches - Lot - 2 | 2017-09-12 | 2017-09-17 | 2018-02-24 | 2018-02-27
Act | 2AP000IC01807-08015 | Not Started | Completed | EOF : Delivery of Level Transmitters & Level Switches - Last Lot -3 | 2017-11-12 | 2017-11-16 | 2018-02-24 | 2018-02-27
4 |  |  |  | PANELS
Act | 2AP000EL01007-08011 | Not Started | Completed | EOF : Delivery of Interposing Relay Panel | 2017-10-12 | 2017-10-17 | 2018-02-24 | 2018-02-27
3 |  |  |  | TELECOM
Act | 2AP000TE00107-08000 | Not Started | Completed | EOF : Delivery of Telecom Equipments - First Lot | 2017-07-12 | 2017-07-17 | 2017-07-12 | 2017-07-17
Act | 2AP000TE00107-08005 | Not Started | Completed | EOF : Delivery of Telecom Equipments - Last Lot | 2017-11-12 | 2017-11-16 | 2017-11-12 | 2017-11-16
3 |  |  |  | SAFETY
Act | 2AP000HS00507-08000 | Not Started | Completed | 52-Z-301 A: Foam System Package Incl. 52-D-303 A/B; 52-D-307 A-D; 52-G-302 A-D | 2017-05-11 | 2017-05-16 | 2018-02-24 | 2018-02-27
Act | 2AP000HS00507-08005 | Not Started | Completed | 52-Z-301 B: Foam System Package Incl. 52-D-303 A/B; 52-D-307 A-D; 52-G-302 A-D | 2017-05-11 | 2017-05-16 | 2018-02-24 | 2018-02-27
Act | 2AP000HS00107-08100 | Not Started | In Progress | EOF: Delivery of Fire fighting Equipments - First Lot | 2017-06-26 | 2017-07-01 | 2019-03-10
Act | 2AP000HS00207-08100 | Not Started | In Progress | EOF: Delivery of Safety Equipments - First Lot | 2017-06-26 | 2017-07-01 | 2018-11-08
Act | 2AP000HS00107-08105 | Not Started | In Progress | EOF: Delivery of Fire fighting Equipments - Last Lot | 2017-10-26 | 2017-10-31 | 2019-03-10
Act | 2AP000HS00207-08105 | Not Started | In Progress | EOF: Delivery of Safety Equipments - Last Lot | 2017-10-26 | 2017-10-31 | 2019-03-10
2 |  |  |  | BULK MATERIALS
3 |  |  |  | CIVIL / STRUCTURAL / ARCHITECTURAL
4 |  |  |  | STRUCTURAL STEEL WORKS
Act | 2AP000ST00200-08000 | Not Started | Completed | Structural Steel Lot - 1 | 2016-10-29 | 2016-11-02 | 2017-03-01 | 2017-06-01
Act | 2AP000ST00200-08005 | Not Started | Completed | Structural Steel Lot - 2 | 2017-01-11 | 2017-01-16 | 2017-03-06 | 2018-05-28
Act | 2AP000ST00200-08010 | Not Started | Completed | Structural Steel Lot - 3 | 2017-07-27 | 2017-08-01 | 2017-03-06 | 2018-06-27
4 |  |  |  | FENCING & GATE MATERIAL
Act | 2AP000ST00707-08020 | Not Started | Completed | Fencing & Gate Material Lot - 1 | 2017-07-11 | 2017-07-16 | 2016-08-24 | 2017-11-20
Act | 2AP000ST00707-08025 | Not Started | Completed | Fencing & Gate Material Lot - 2 | 2017-09-03 | 2017-09-07 | 2016-08-23 | 2017-10-26
Act | 2AP000ST00707-08030 | Not Started | Completed | Fencing & Gate Material Lot - 3 | 2017-10-26 | 2017-10-31 | 2017-08-23 | 2017-10-26
4 |  |  |  | GATE & CRASH BARRIER
Act | 2AP000ST00807-08005 | Not Started | Completed | Gate & Crash Barrier Lot - 1 | 2017-04-11 | 2017-04-16 | 2018-02-24 | 2018-02-27
Act | 2AP000ST00807-08010 | Not Started | Completed | Gate & Crash Barrier Lot - 2 | 2017-06-03 | 2017-06-07 | 2018-02-24 | 2018-02-27
Act | 2AP000ST00807-08015 | Not Started | Completed | Gate & Crash Barrier Lot - 3 | 2017-07-27 | 2017-08-01 | 2018-02-24 | 2018-02-27
4 |  |  |  | STEEL BUILDINGS/ SHELTERS
Act | 2AP000ST00200-08015 | Not Started | Completed | Steel Building material Lot - 1 | 2016-12-29 | 2017-01-03 | 2017-09-11 | 2018-02-27
Act | 2AP000ST00200-08020 | Not Started | Completed | Steel Building material Lot - 2 | 2017-04-27 | 2017-05-02 | 2017-11-04 | 2018-02-27
Act | 2AP000ST00200-08025 | Not Started | Completed | Steel Building material Lot - 3 | 2017-08-27 | 2017-08-31 | 2017-11-15 | 2018-02-27
3 |  |  |  | PIPING
4 |  |  |  | Pipes - Metalic - Shipment
Act | 2AP000PI00107-08000 | Not Started | Completed | EOF : Delivery of CS/LTCS Pipes (Seamless) - Lot -1 | 2017-01-29 | 2017-02-02 | 2017-01-09 | 2018-08-27
Act | 2AP000PI00107-08005 | Not Started | Completed | EOF : Delivery of CS/LTCS Pipes (Seamless) - Lot -2 | 2017-05-29 | 2017-06-03 | 2017-09-17 | 2018-09-03
Act | 2AP000PI00107-08010 | Not Started | Completed | EOF : Delivery of CS/LTCS Pipes (Seamless) - Lot -3 | 2017-09-27 | 2017-10-02 | 2018-02-24 | 2018-09-03
Act | 2AP000PI00107-08015 | Not Started | Completed | EOF : Delivery of CS/LTCS Pipes (Welded) - Lot -1 | 2017-01-29 | 2017-02-02 | 2016-11-05 | 2017-05-30
Act | 2AP000PI00107-08020 | Not Started | Completed | EOF : Delivery of CS/LTCS Pipes (Welded) - Lot -2 | 2017-05-29 | 2017-06-03 | 2016-11-05 | 2018-09-03
Act | 2AP000PI00107-08025 | Not Started | Completed | EOF : Delivery of CS/LTCS Pipes (Welded) - Lot -3 | 2017-09-27 | 2017-10-02 | 2017-09-27 | 2018-09-03
Act | 2AP000PI00107-08030 | Not Started | Completed | EOF : Delivery of SS/SDSS Pipes (Seemless) - Lot -1 | 2017-01-29 | 2017-02-02 | 2017-11-09 | 2018-07-21 | [66 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [8 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [8 empty] | 24 | [9 empty] | 49 | [9 empty] | 49 | [8 empty] | 46 | [9 empty] | 52 | [9 empty] | 36 | [9 empty] | 0 | [8 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  |  |  | 0
Act | 2AP000PI00107-08035 | Not Started | Completed | EOF : Delivery of SS/SDSS Pipes (Seemless) - Lot -2 | 2017-05-29 | 2017-06-03 | 2018-01-22 | 2018-07-21
Act | 2AP000PI00107-08040 | Not Started | Completed | EOF : Delivery of SS/SDSS Pipes (Seemless) - Lot -3 | 2017-09-27 | 2017-10-02 | 2018-01-22 | 2018-07-21
Act | 2AP000PI00107-08045 | Not Started | Completed | EOF : Delivery of SS/SDSS Pipes (Welded) - Lot -1 | 2017-01-29 | 2017-02-02 | 2018-01-22 | 2018-07-21 | [66 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [8 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [8 empty] | 24 | [9 empty] | 49 | [9 empty] | 50 | [8 empty] | 47 | [9 empty] | 53 | [9 empty] | 36 | [9 empty] | 0 | [8 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  |  |  | 0
Act | 2AP000PI00107-08050 | Not Started | Completed | EOF : Delivery of SS/SDSS Pipes (Welded) - Lot -2 | 2017-05-29 | 2017-06-03 | 2018-01-22 | 2018-07-21
Act | 2AP000PI00107-08055 | Not Started | Completed | EOF : Delivery of SS/SDSS Pipes (Welded) - Lot -3 | 2017-09-27 | 2017-10-02 | 2018-01-22 | 2018-07-21
4 |  |  |  | Pipes - Non Metalic - Shipment
Act | 2AP000PI00207-08000 | Not Started | Completed | EOF : Delivery of non-metallic pipes & fitting (GRE/ FBE/HBE) - Lot -1 | 2017-01-29 | 2017-02-02 | 2017-05-25 | 2017-10-22 | [66 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [8 empty] | 0 | [9 empty] | 0 | [9 empty] | 12 | [8 empty] | 37 | [9 empty] | 28 | [9 empty] | 0 | [8 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [8 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  |  |  | 0
Act | 2AP000PI00207-08005 | Not Started | Completed | EOF : Delivery of non-metallic pipes & fitting (GRE/ FBE/HBE) - Lot -2 | 2017-05-29 | 2017-06-03 | 2017-10-01 | 2019-01-27
Act | 2AP000PI00207-08010 | Not Started | Completed | EOF : Delivery of non-metallic pipes & fitting (GRE/ FBE/HBE) - Lot -3 | 2017-09-26 | 2017-10-01 | 2017-09-24 | 2019-01-27
4 |  |  |  | Pipe Fittings and Flanges - Shipment
Act | 2AP000PI00307-08015 | Not Started | Completed | EOF : Delivery of Pipe Fittings, Flanges and Blinds - Lot -1 | 2017-01-29 | 2017-02-02 | 2017-02-02 | 2017-06-03
Act | 2AP000PI00307-08020 | Not Started | Completed | EOF : Delivery of Pipe Fittings, Flanges and Blinds - Lot -2 | 2017-05-29 | 2017-06-03 | 2017-10-01 | 2018-01-22
Act | 2AP000PI00307-08025 | Not Started | In Progress | EOF : Delivery of Pipe Fittings, Flanges and Blinds - Lot -3 | 2017-09-26 | 2017-10-01 | 2018-05-22
4 |  |  |  | Piping Valves - Shipment
Act | 2AP000PI00407-08000 | Not Started | Completed | EOF : Delivery of Piping Valves (Ball/GGC type) - Lot -1 | 2017-02-22 | 2017-02-27 | 2017-10-22 | 2018-03-28
Act | 2AP000PI00407-08005 | Not Started | Completed | EOF : Delivery of Piping Valves (Ball/GGC type) - Lot -2 | 2017-07-11 | 2017-07-16 | 2018-04-01 | 2018-08-19
Act | 2AP000PI00407-08010 | Not Started | Completed | EOF : Delivery of Piping Valves (Ball/GGC type) - Lot -3 | 2017-11-27 | 2017-12-02 | 2018-09-15 | 2018-10-27
Act | 2AP000PI00407-08015 | Not Started | Completed | EOF : Delivery of Other Piping Valves (Butterfly/Plug/Check/Special type) - Lot -1 | 2017-03-25 | 2017-03-29 | 2017-07-19 | 2017-10-22
Act | 2AP000PI00407-08020 | Not Started | Completed | EOF : Delivery of Other Piping Valves (Butterfly/Plug/Check/Special type) - Lot -2 | 2017-07-26 | 2017-07-31 | 2018-02-13 | 2018-06-05
Act | 2AP000PI00407-08025 | Not Started | Completed | EOF : Delivery of Other Piping Valves (Butterfly/Plug/Check/Special type) - Lot -3 | 2017-11-27 | 2017-12-02 | 2018-07-19 | 2018-10-11
4 |  |  |  | Pipe Supports and Miscellaneous Items - Shipment
Act | 2AP000PI00507-08000 | Not Started | Completed | EOF : Delivery of Piping supports (Primary) - Lot -1 | 2017-04-30 | 2017-05-04 | 2018-06-21 | 2018-08-04
Act | 2AP000PI00507-08005 | Not Started | Completed | EOF : Delivery of Piping supports (Primary) - Lot -2 | 2017-07-13 | 2017-07-18 | 2018-08-26 | 2018-10-10
Act | 2AP000PI00507-08010 | Not Started | Completed | EOF : Delivery of Piping supports (Primary) - Lot -3 | 2017-09-27 | 2017-10-02 | 2018-10-16 | 2018-12-09
Act | 2AP000PI00507-08015 | Not Started | Completed | EOF : Delivery Of Misc. Piping Items (Gaskets/Fasteners/Springs/Strut/Hanger /Sliding Plate/Etc) - Lot -1 | 2017-01-29 | 2017-02-02 | 2017-01-11 | 2017-09-09
Act | 2AP000PI00507-08020 | Not Started | In Progress | EOF : Delivery Of Misc. Piping Items (Gaskets/Fasteners/Springs/Strut/Hanger /Sliding Plate/Etc) - Lot -2 | 2017-05-29 | 2017-06-03 | 2017-05-27
Act | 2AP000PI00507-08025 | Not Started | In Progress | EOF : Delivery Of Misc. Piping Items (Gaskets/Fasteners/Springs/Strut/Hanger /Sliding Plate/Etc) - Lot -3 | 2017-09-27 | 2017-10-02 | 2018-03-22
3 |  |  |  | ELECTRICAL
4 |  |  |  | HV & LV (Power, Control & Earthing) Cable - Shipment
Act | 2AP000EL00907-08000 | Not Started | Completed | EOF : Delivery of HV & LV (Power, Control & Earthing) Cable - First Lot-1 | 2017-01-29 | 2017-02-02 | 2017-02-22 | 2018-02-25
Act | 2AP000EL00907-08005 | Not Started | Completed | EOF : Delivery of HV & LV (Power, Control & Earthing) Cable - Lot-2 | 2017-04-20 | 2017-04-25 | 2017-08-26 | 2018-02-27
Act | 2AP000EL00907-08010 | Not Started | Completed | EOF : Delivery of HV & LV (Power, Control & Earthing) Cable - Last Lot-3 | 2017-07-12 | 2017-07-17 | 2018-02-24 | 2018-02-27
4 |  |  |  | Cable Trays, Cable Ladders & Accessories - Shipment
Act | 2AP000EL02207-08000 | Not Started | Completed | EOF : Delivery of Electrical Cable Trays, Cable Ladders & Accessories - First Lot-1 | 2017-02-19 | 2017-02-23 | 2018-02-24 | 2018-02-27
Act | 2AP000EL02207-08005 | Not Started | Completed | EOF : Delivery of Electrical Cable Trays, Cable Ladders & Accessories - Lot-2 | 2017-05-01 | 2017-05-06 | 2018-02-24 | 2018-02-27
Act | 2AP000EL02207-08010 | Not Started | Completed | EOF : Delivery of Electrical Cable Trays, Cable Ladders & Accessories - Last Lot-3 | 2017-07-12 | 2017-07-17 | 2018-02-24 | 2018-02-27
4 |  |  |  | Hazardous/Industrial Type Lighting Fixtures - Shipment
Act | 2AP000EL01407-08000 | Not Started | Completed | EOF : Delivery of Lighting Poles & Lighting Fixtures - First Lot-1 | 2017-06-21 | 2017-06-26 | 2018-02-24 | 2018-02-27
Act | 2AP000EL01407-08005 | Not Started | Completed | EOF : Delivery of Lighting Poles & Lighting Fixtures - Lot-2 | 2017-08-31 | 2017-09-05 | 2018-02-24 | 2018-02-27
Act | 2AP000EL01407-08010 | Not Started | Completed | EOF : Delivery of Lighting Poles & Lighting Fixtures - Last Lot-3 | 2017-11-11 | 2017-11-15 | 2018-02-24 | 2018-02-27
4 |  |  |  | Hazardous Type Junction Box - Shipment
Act | 2AP000EL01807-08000 | Not Started | Completed | EOF : Delivery of Junction Box - First Lot-1 | 2017-05-21 | 2017-05-25 | 2018-02-24 | 2018-02-27
Act | 2AP000EL01807-08005 | Not Started | Completed | EOF : Delivery of Junction Box - Lot-2 | 2017-07-16 | 2017-07-20 | 2018-02-24 | 2018-02-27
Act | 2AP000EL01807-08010 | Not Started | Completed | EOF : Delivery of Junction Box - Last Lot-3 | 2017-09-11 | 2017-09-16 | 2018-02-24 | 2018-02-27
4 |  |  |  | Industrial Type Junction Box - Shipment
Act | 2AP000EL01707-08000 | Not Started | Completed | EOF : Delivery of Junction Box - First Lot-1 | 2017-02-08 | 2017-02-13 | 2018-02-24 | 2018-02-27
Act | 2AP000EL01707-08005 | Not Started | Completed | EOF : Delivery of Junction Box - Lot-2 | 2017-05-25 | 2017-05-30 | 2018-02-24 | 2018-02-27
Act | 2AP000EL01707-08010 | Not Started | Completed | EOF : Delivery of Junction Box - Last Lot-3 | 2017-09-11 | 2017-09-16 | 2018-02-24 | 2018-02-27
4 |  |  |  | Hazardous/Industrial Type Receptacles & Sockets - Shipment
Act | 2AP000EL01907-08000 | Not Started | Completed | EOF : Delivery of Receptacles & Sockets - First Lot-1 | 2017-07-06 | 2017-07-11 | 2018-02-24 | 2018-02-27
Act | 2AP000EL01907-08005 | Not Started | Completed | EOF : Delivery of Receptacles & Sockets - Lot-2 | 2017-08-08 | 2017-08-13 | 2018-02-24 | 2018-02-27
Act | 2AP000EL01907-08010 | Not Started | Completed | EOF : Delivery of Receptacles & Sockets - Last Lot-3 | 2017-09-11 | 2017-09-16 | 2018-02-24 | 2018-02-27
4 |  |  |  | Earthing & Lightning Protection Materials - Shipment
Act | 2AP000EL02107-08000 | Not Started | Completed | EOF : Delivery of Earthing & Lightning Protection Materials - First Lot-1 | 2017-01-18 | 2017-01-23 | 2018-02-24 | 2018-02-27
Act | 2AP000EL02107-08005 | Not Started | Completed | EOF : Delivery of Earthing & Lightning Protection Materials - Lot-2 | 2017-07-16 | 2017-07-20 | 2018-02-24 | 2018-02-27
Act | 2AP000EL02107-08010 | Not Started | Completed | EOF : Delivery of Earthing & Lightning Protection Materials - Last Lot-3 | 2017-09-11 | 2017-09-16 | 2018-02-24 | 2018-02-27
4 |  |  |  | Cable Glands - Shipment
Act | 2AP000EL02407-08000 | Not Started | Completed | EOF : Delivery of Cable Glands - First Lot - 1 | 2017-01-21 | 2017-01-25 | 2018-02-24 | 2018-02-27
Act | 2AP000EL02407-08005 | Not Started | Completed | EOF : Delivery of Cable Glands - Lot - 2 | 2017-08-01 | 2017-08-06 | 2018-02-24 | 2018-02-27
Act | 2AP000EL02407-08010 | Not Started | Completed | EOF : Delivery of Cable Glands - Last Lot - 3 | 2017-09-11 | 2017-09-16 | 2018-02-24 | 2018-02-27
4 |  |  |  | Cable Termination & Jointing Kits - Shipment
Act | 2AP000EL02307-08000 | Not Started | Completed | EOF : Delivery of Cable Termination & Jointing Kits - First Lot - 1 | 2017-06-21 | 2017-06-26 | 2018-02-24 | 2018-02-27
Act | 2AP000EL02307-08005 | Not Started | Completed | EOF : Delivery of Cable Termination & Jointing Kits - Lot - 2 | 2017-08-16 | 2017-08-21 | 2018-02-24 | 2018-02-27
Act | 2AP000EL02307-08010 | Not Started | Completed | EOF : Delivery of Cable Termination & Jointing Kits - Last Lot - 3 | 2017-10-12 | 2017-10-17 | 2018-02-24 | 2018-02-27
3 |  |  |  | INSTRUMENTATION
4 |  |  |  | Instrumentation Cable - Shipment
Act | 2AP000IC03307-08000 | Not Started | Completed | EOF : Delivery of Instrumentation Cable- Lot-1 | 2017-02-26 | 2017-03-02 | 2018-02-24 | 2018-02-27
Act | 2AP000IC03307-08005 | Not Started | Completed | EOF : Delivery of Instrumentation Cable- Lot-2 | 2017-05-13 | 2017-05-17 | 2018-02-24 | 2018-02-27
Act | 2AP000IC03307-08010 | Not Started | Completed | EOF : Delivery of Instrumentation Cable- Lot-3 | 2017-07-27 | 2017-08-01 | 2018-02-24 | 2018-02-27
4 |  |  |  | Instrumentation Cable Tray - Shipment
Act | 2AP000IC04407-08000 | Not Started | Completed | EOF : Delivery of Instrumentation Cable Tray- Lot-1 | 2017-03-29 | 2017-04-03 | 2018-02-24 | 2018-02-27
Act | 2AP000IC04407-08005 | Not Started | Completed | EOF : Delivery of Instrumentation Cable Tray- Lot-2 | 2017-05-29 | 2017-06-03 | 2018-02-24 | 2018-02-27
Act | 2AP000IC04407-08010 | Not Started | Completed | EOF : Delivery of Instrumentation Cable Tray- Lot-3 | 2017-07-27 | 2017-08-01 | 2018-02-24 | 2018-02-27
4 |  |  |  | Instrument Junction Boxes - Shipment
Act | 2AP000IC03407-08000 | Not Started | Completed | EOF : Delivery of Instrument Junction Boxes - Lot-1 | 2017-03-30 | 2017-04-04 | 2018-02-24 | 2018-02-27
Act | 2AP000IC03407-08005 | Not Started | Completed | EOF : Delivery of Instrument Junction Boxes - Lot-2 | 2017-05-29 | 2017-06-03 | 2018-02-24 | 2018-02-27
Act | 2AP000IC03407-08010 | Not Started | Completed | EOF : Delivery of Instrument Junction Boxes - Lot-3 | 2017-07-27 | 2017-08-01 | 2018-02-24 | 2018-02-27
4 |  |  |  | Instrument Cable Glands - Shipment
Act | 2AP000IC03507-08000 | Not Started | Completed | EOF : Delivery of Instrument Cable Glands - Lot-1 | 2017-06-10 | 2017-06-14 | 2018-02-24 | 2018-02-27
Act | 2AP000IC03507-08005 | Not Started | Completed | EOF : Delivery of Instrument Cable Glands - Lot-2 | 2017-08-19 | 2017-08-23 | 2018-02-24 | 2018-02-27
Act | 2AP000IC03507-08010 | Not Started | Completed | EOF : Delivery of Instrument Cable Glands - Lot-3 | 2017-10-28 | 2017-11-01 | 2018-02-24 | 2018-02-27
4 |  |  |  | Instrumentation Bulk Materials - Shipment
Act | 2AP000IC04007-08000 | Not Started | Completed | EOF : Delivery of Instrumentation other misc Bulk Materials- Lot-1 | 2017-06-21 | 2017-06-26 | 2018-02-24 | 2018-02-27
Act | 2AP000IC04007-08005 | Not Started | Completed | EOF : Delivery of Instrumentation other misc Bulk Materials- Lot-2 | 2017-08-24 | 2017-08-29 | 2018-02-24 | 2018-02-27
Act | 2AP000IC04007-08010 | Not Started | Completed | EOF : Delivery of Instrumentation other misc Bulk Materials- Lot-3 | 2017-10-28 | 2017-11-01 | 2018-02-24 | 2018-02-27
4 |  |  |  | Instrumentation Tube Fittings - Shipment
Act | 2AP000IC04207-08000 | Not Started | Completed | EOF : Delivery of Instrumentation Tubes & Fittings-Lot-1 | 2017-06-21 | 2017-06-26 | 2018-02-24 | 2018-02-27
Act | 2AP000IC04207-08005 | Not Started | Completed | EOF : Delivery of Instrumentation Tubes & Fittings-Lot-2 | 2017-07-09 | 2017-07-13 | 2018-02-24 | 2018-02-27
Act | 2AP000IC04207-08010 | Not Started | Completed | EOF : Delivery of Instrumentation Tubes & Fittings-Lot-3 | 2017-07-27 | 2017-08-01 | 2018-02-24 | 2018-02-27
4 |  |  |  | Sunshade - Shipment
Act | 2AP000IC04307-08000 | Not Started | Completed | EOF : Delivery of Sunshade-Lot-1 | 2017-06-28 | 2017-07-03 | 2018-02-24 | 2018-02-27
Act | 2AP000IC04307-08005 | Not Started | Completed | EOF : Delivery of Sunshade-Lot-2 | 2017-08-28 | 2017-09-02 | 2018-02-24 | 2018-02-27
Act | 2AP000IC04307-08010 | Not Started | Completed | EOF : Delivery of Sunshade-Lot-3 | 2017-10-28 | 2017-11-01 | 2018-02-24 | 2018-02-27
3 |  |  |  | TELECOM
Act | 2AP000TE00207-08000 | Not Started | Completed | EOF:Telecom Cable - First Lot | 2017-01-02 | 2017-01-07 | 2017-10-05 | 2017-10-05
Act | 2AP000TE00207-08005 | Not Started | Completed | EOF:Telecom Cable -Last Lot | 2017-10-01 | 2017-10-05 | 2018-08-13 | 2018-08-16
Act | 2AP000TE00207-08010 | Not Started | Completed | EOF:Delivery of Fibre Optic Cables - First Lot | 2016-12-31 | 2017-01-04 | 2017-10-05 | 2017-10-31
Act | 2AP000TE00207-08015 | Not Started | Completed | EOF:Delivery of Fibre Optic Cables-Last Lot | 2017-05-01 | 2017-05-06 | 2018-02-24 | 2018-02-27
Act | 2AP000TE00207-08020 | Not Started | Completed | EOF: Miscellaneous Telecom Items - First Lot | 2017-01-11 | 2017-01-16 | 2017-07-03 | 2017-10-22
Act | 2AP000TE00207-08025 | Not Started | Completed | EOF: Miscellaneous Telecom Items-Last Lot | 2017-09-30 | 2017-10-04 | 2018-02-24 | 2018-02-27
3 |  |  |  | SAFETY
Act | 2AP000SE00607-08000 | Not Started | Not Started | EOF : Delivery of Safety Signs - First Lot 1 | 2017-07-03 | 2017-07-08
Act | 2AP000SE00607-08005 | Not Started | Not Started | EOF : Delivery of Safety Signs - Lot 2 | 2017-09-21 | 2017-09-26
Act | 2AP000SE00607-08010 | Not Started | Not Started | EOF : Delivery of Safety Signs - Last Lot 3 | 2017-12-11 | 2017-12-16
2 |  |  |  | RAM ITEMS (FOR CONSTRUCTION)
3 |  |  |  | CIVIL / STRUCTURAL / ARCHITECTURAL
Act | 2AP100CV08100-08000 | Not Started | Completed | Submition & Approval of RAM FOR HYSD BARS | 2015-10-22 | 2015-12-02 | 2015-12-28 | 2016-01-11 | bar: 2015-10-22 to 2015-11-26
Act | 2AP100CV08100-08005 | Not Started | Completed | Submition & Approval of RAM FOR CAP PRIME & CAP SEAL | 2015-10-22 | 2015-12-02 | 2015-10-22 | 2015-12-09 | bar: 2015-10-15 to 2015-11-26
Act | 2AP100CV08100-08010 | Not Started | Completed | Submition & Approval of RAM FOR CEMENT (OPC & SRPC) | 2015-10-27 | 2015-12-07 | 2015-10-27 | 2015-11-26 | bar: 2015-10-22 to 2015-11-19
Act | 2AP100CV08100-08015 | Not Started | Completed | Submition & Approval of RAM FOR POLYTHENE SHEET | 2015-10-27 | 2015-12-07 | 2015-10-27 | 2016-01-11 | bar: 2015-10-22 to 2015-11-26
Act | 2AP100CV08100-08020 | Not Started | Completed | Submition & Approval of RAM FOR BITUMENT FILLER BOARD (Jolly Bitulex) | 2015-10-27 | 2015-12-07 | 2015-10-27 | 2016-01-11 | bar: 2015-10-22 to 2015-11-26
Act | 2AP100CV08100-08025 | Not Started | Completed | Submition & Approval of RAM FOR RELEASEFORM | 2015-10-27 | 2015-12-07 | 2015-10-27 | 2016-01-11 | bar: 2015-10-22 to 2015-11-26
Act | 2AP100CV08100-08030 | Not Started | Completed | Submition & Approval of RAM FOR REPAIR CEMENT/CHEMICAL etc (FORSOC) | 2015-10-27 | 2015-12-07 | 2015-10-27 | 2016-01-11 | bar: 2015-10-22 to 2015-11-26
Act | 2AP100CV08100-08035 | Not Started | Completed | Submition & Approval of RAM FOR HEMPADUR 85671 (EPOXY COATING) | 2015-11-04 | 2015-12-15 | 2015-11-04 | 2016-01-11 | bar: 2015-10-29 to 2015-11-26
Act | 2AP100CV08100-08040 | Not Started | Completed | Submition & Approval of RAM FOR PG-10 (POLYSHILPIDE SEALENT) | 2015-11-04 | 2015-12-15 | 2015-11-04 | 2016-01-11 | bar: 2015-10-29 to 2015-11-26
Act | 2AP100CV08100-08045 | Not Started | Completed | Submition & Approval of RAM FOR HEMPADUR MASTIC 45881/45880 | 2015-11-04 | 2015-12-15 | 2015-11-04 | 2016-01-11 | bar: 2015-10-29 to 2015-11-26
Act | 2AP100CV08100-08050 | Not Started | Completed | Submition & Approval of RAM FOR CONBEXTRA GP (NON-SHRINK GROUT) | 2015-11-04 | 2015-12-15 | 2016-01-17 | 2016-02-20 | bar: 2015-10-29 to 2015-11-26
Act | 2AP100CV08100-08055 | Not Started | Completed | Submition & Approval of RAM FOR BINDING WIRE FOR REINFORCEMENT | 2015-11-19 | 2015-12-30 | 2015-11-19 | 2015-12-28 | bar: 2015-11-12 to 2015-11-26
Act | 2AP100CV08100-08060 | Not Started | Completed | Submition & Approval of RAM FOR CHAIN LINK FENCE | 2016-04-13 | 2016-05-24 | 2016-07-02 | 2016-08-07
Act | 2AP100CV08100-08065 | Not Started | Completed | Submition & Approval of RAM FOR HIGH SECURITY FENCE | 2016-04-19 | 2016-05-30 | 2016-11-03 | 2016-11-08 | [66 empty] | 24 | [9 empty] | 0 | [9 empty] | 0 | [8 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [8 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [8 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [8 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  |  |  | 0
Act | 2AP100CV08100-08070 | Not Started | Completed | Submition & Approval of RAM FOR HAND HOLE AND MANHOLE COVERS | 2016-05-16 | 2016-06-26 | 2016-10-05 | 2017-01-02
Act | 2AP100CV08100-08075 | Not Started | Completed | Submition & Approval of RAM FOR ROAD ASPHALT | 2016-04-30 | 2016-06-11 | 2016-11-15 | 2016-12-24
3 |  |  |  | MECHANICAL-STATIC/ROTATING & PIPING
Act | 2AP100MS08100-08080 | Not Started | Completed | Submition & Approval of RAM for Welding Consumables | 2016-06-26 | 2016-07-30 | 2016-03-19 | 2016-04-10
Act | 2AP100MS08100-08085 | Not Started | Completed | Submition & Approval of RAM for Coating Material | 2016-06-26 | 2016-07-30 | 2016-06-02 | 2016-06-23
Act | 2AP100MS08100-08090 | Not Started | Completed | Submition & Approval of RAM for Painting Material | 2016-06-26 | 2016-07-30 | 2016-04-17 | 2016-04-27
Act | 2AP100MS08100-08095 | Not Started | Completed | Submition & Approval of RAM for Abrasive Blasting Material (Garnet) | 2016-06-26 | 2016-07-30 | 2016-04-17 | 2016-04-27
Act | 2AP100MS08100-08105 | Not Started | Completed | Submition & Approval of RAM for Fireproofing Meerial | 2017-01-14 | 2017-02-15 | 2018-03-14 | 2018-03-27
Act | 2AP100MS08100-08115 | Not Started | Completed | Submition & Approval of RAM for Pipe Insulation Material (Heat Conservation) | 2017-02-20 | 2017-04-02 | 2018-02-24 | 2018-04-04
Act | 2AP100MS08100-08125 | Not Started | Completed | Submition & Approval of RAM for Pipe Insulation Material (Personnel Protection) | 2017-05-16 | 2017-06-26 | 2018-06-12 | 2018-07-23
3 |  |  |  | ELECTRICAL/INSTRUMENTATION/TELICOME
Act | 2AP100EL08100-08100 | Not Started | Completed | Submition & Approval of RAM FOR CONCRETE CABLE TILE {FOR U/G CABLE PROTECTION) | 2015-12-02 | 2016-01-04 | 2015-12-02 | 2016-02-09 | bar: 2015-11-26
1 |  |  |  | PRELIMINARIES
2 |  |  |  | Temporary Facilities Construction AFC Drawing
3 |  |  |  | Engineering Drawings & Layout
4 |  |  |  | Civil Drawing for Temporary Facilities
Act | 2AR000TF10001-08000 | Not Started | Completed | Layout for Sub-contractor Site office & laydown Area | 2015-10-12 | 2015-10-26 | 2015-08-17 | 2015-08-30
Act | 2AR000TF10001-08005 | Not Started | Completed | Sanitary & Plumbing Layout | 2015-10-12 | 2015-10-26 | 2015-08-17 | 2015-08-30
Act | 2AR000TF10001-08010 | Not Started | Completed | Sub-contractor Site office Layout | 2015-10-12 | 2015-10-26 | 2015-08-17 | 2015-08-30
4 |  |  |  | Electrical Drawing for Temporary Facilities
Act | 2AR000TF10001-08015 | Not Started | Completed | External Electrical Service Layout for Site office & Laydown Area | 2015-10-26 | 2015-11-09 | 2015-08-31 | 2015-09-13
Act | 2AR000TF10001-08020 | Not Started | Completed | Lighting Layout for sub-contractor Main Site office | 2015-10-26 | 2015-11-09 | 2015-08-31 | 2015-09-13
Act | 2AR000TF10001-08025 | Not Started | Completed | Small Power Layout for Contractor Main Site office | 2015-10-26 | 2015-11-09 | 2015-08-31 | 2015-09-13
Act | 2AR000TF10001-08030 | Not Started | Completed | Fire Alarm Layout for Sub Contractor Main Site office | 2015-10-26 | 2015-11-09 | 2015-08-31 | 2015-09-13
Act | 2AR000TF10001-08035 | Not Started | Completed | Electrical Single Line Diagram | 2015-10-26 | 2015-11-09 | 2015-08-31 | 2015-09-13
Act | 2AR000TF10001-08040 | Not Started | Completed | Electrical Load Schedule | 2015-10-26 | 2015-11-09 | 2015-08-31 | 2015-09-13
2 |  |  |  | Pkg 8 - EOF/COCC (Civil, ME&I): MobilisationlPreparatory works and subm of SC Work Programme
3 |  |  |  | Area Clearance & Site Preparation
Act | 2AI000ME00320-08045 | Not Started | Completed | Survey & Setting Layout | 2015-11-10 | 2015-11-12 | 2015-10-31 | 2015-12-08 | bar: 2015-10-29 to 2015-11-26
Act | 2AI000ME00320-08050 | Not Started | Completed | Excavation Notification | 2015-11-12 | 2015-11-16 | 2015-11-03 | 2015-11-04 | bar: 2015-10-29
Act | 2AI000ME00320-08055 | Not Started | Completed | Slit Trench Excavation Work | 2015-11-16 | 2015-11-24 | 2015-11-04 | 2015-12-08 | bar: 2015-10-29 to 2015-11-26
Act | 2AI000ME00320-08060 | Not Started | Completed | Scrubbing & Grading | 2015-11-24 | 2015-11-30 | 2015-11-24 | 2015-11-30 | bar: 2015-11-19 to 2015-11-26
3 |  |  |  | Fence Installation around site premises
Act | 2AI000ME00320-08065 | Not Started | Completed | Procurement of fencing material | 2015-11-01 | 2015-12-10 | 2015-11-01 | 2015-12-10 | bar: 2015-10-29 to 2015-11-26
Act | 2AI000ME00320-08070 | Not Started | Completed | External Fencing & Gate Installation | 2015-11-26 | 2015-12-14 | 2015-11-26 | 2015-12-14 | bar: 2015-11-19 to 2015-11-26
Act | 2AI000ME00320-08075 | Not Started | Completed | Internal Fencing & Gate Installation-Yard | 2015-12-09 | 2015-12-23 | 2015-12-09 | 2015-12-23
Act | 2AI000ME00320-08080 | Not Started | Completed | Project Sign Board Fixing | 2015-12-14 | 2015-12-15 | 2015-12-14 | 2015-12-15
3 |  |  |  | Site Office Setup
Act | 2AI000ME00320-08085 | Not Started | Completed | Manufacturing Site office Cabins | 2015-10-26 | 2015-12-06 | 2015-10-26 | 2015-12-06 | bar: 2015-10-22 to 2015-11-26
Act | 2AI000ME00320-08090 | Not Started | Completed | Foundation Block Fixing - Site office | 2015-11-30 | 2015-12-05 | 2015-11-30 | 2015-12-05 | bar: 2015-11-26
Act | 2AI000ME00320-08095 | Not Started | Completed | Shipment & Delivery to site | 2015-12-06 | 2015-12-09 | 2015-12-06 | 2015-12-09
Act | 2AI000ME00320-08100 | Not Started | Completed | Installation & Assembling of Portable cabins | 2015-12-09 | 2015-12-27 | 2015-12-09 | 2015-12-27
Act | 2AI000ME00320-08105 | Not Started | Completed | Electrical & Plumbing Works | 2015-12-15 | 2015-12-22 | 2015-12-15 | 2015-12-22
Act | 2AI000ME00320-08110 | Not Started | Completed | Furnishing & Networking | 2015-12-23 | 2015-12-29 | 2015-12-23 | 2015-12-29
Act | 2AI000ME00320-08115 | Not Started | Completed | Parking Area | 2015-12-22 | 2015-12-31 | 2015-12-22 | 2015-12-31
3 |  |  |  | Store
Act | 2AI000ME00320-08120 | Not Started | Completed | Fabrication of Store Portable Cabin | 2015-11-24 | 2015-12-06 | 2015-11-24 | 2015-12-06 | bar: 2015-11-19 to 2015-11-26
Act | 2AI000ME00320-08125 | Not Started | Completed | Foundation Block Fixing for Portable cabins | 2015-12-06 | 2015-12-08 | 2015-12-06 | 2015-12-08
Act | 2AI000ME00320-08130 | Not Started | Completed | Installation of Storage Containers | 2015-12-08 | 2015-12-15 | 2015-12-08 | 2015-12-15
Act | 2AI000ME00320-08135 | Not Started | Completed | Installation of Portable cabins for store | 2015-12-08 | 2015-12-19 | 2015-12-08 | 2015-12-19
3 |  |  |  | Mess Hall
Act | 2AI000ME00320-08140 | Not Started | Completed | Foundation Block Fixing for Portable cabins | 2015-12-07 | 2015-12-07 | 2015-12-07 | 2015-12-07
Act | 2AI000ME00320-08145 | Not Started | Completed | Installation & Assembling of Mess Hall Portable cabins | 2015-12-08 | 2015-12-12 | 2015-12-08 | 2015-12-12
Act | 2AI000ME00320-08150 | Not Started | Completed | Inside Furnishing | 2015-12-13 | 2015-12-14 | 2015-12-13 | 2015-12-14
Act | 2AI000ME00320-08155 | Not Started | Completed | MEP Works Completion | 2015-12-15 | 2015-12-17 | 2015-12-15 | 2015-12-17
3 |  |  |  | Toilets
Act | 2AI000ME00320-08160 | Not Started | Completed | Foundation Block Fixing | 2015-12-08 | 2015-12-08 | 2015-12-08 | 2015-12-08
Act | 2AI000ME00320-08165 | Not Started | Completed | Installation & Assembling of Portable cabins | 2015-12-09 | 2015-12-12 | 2015-12-09 | 2015-12-12
Act | 2AI000ME00320-08170 | Not Started | Completed | MEP Works Completion | 2015-12-13 | 2015-12-15 | 2015-12-13 | 2015-12-15
3 |  |  |  | Septic tank
Act | 2AI000ME00320-08175 | Not Started | Completed | Pit Excavation | 2015-11-24 | 2015-11-25 | 2015-11-24 | 2015-11-25 | bar: 2015-11-19
Act | 2AI000ME00320-08180 | Not Started | Completed | Foundation Works | 2015-11-25 | 2015-11-28 | 2015-11-25 | 2015-11-28 | bar: 2015-11-19
Act | 2AI000ME00320-08185 | Not Started | Completed | Completion of Plumbing Works | 2015-11-28 | 2015-12-01 | 2015-11-28 | 2015-12-01 | bar: 2015-11-26
3 |  |  |  | Water Tanks
Act | 2AI000ME00320-08190 | Not Started | Completed | Foundation | 2015-11-28 | 2015-11-29 | 2015-11-28 | 2015-11-29 | bar: 2015-11-26
Act | 2AI000ME00320-08195 | Not Started | Completed | Installation | 2015-11-29 | 2015-12-03 | 2015-11-29 | 2015-12-03 | bar: 2015-11-26
Act | 2AI000ME00320-08200 | Not Started | Completed | Completion of Plumbing Works | 2015-12-03 | 2015-12-10 | 2015-12-03 | 2015-12-10 | bar: 2015-11-26
3 |  |  |  | Generator Shed
Act | 2AI000ME00320-08205 | Not Started | Completed | Installation of Generator | 2015-12-15 | 2015-12-15 | 2015-12-15 | 2015-12-15
Act | 2AI000ME00320-08210 | Not Started | Completed | Completion of Shelter | 2015-12-16 | 2015-12-17 | 2015-12-16 | 2015-12-17
Act | 2AI000ME00320-08215 | Not Started | Completed | Electrical Works | 2015-12-19 | 2015-12-22 | 2015-12-19 | 2015-12-22
Act | 2AI000ME00320-08220 | Not Started | Completed | Commissioning & Ready to Use | 2015-12-23 | 2015-12-23 | 2015-12-23 | 2015-12-23
3 |  |  |  | Rebar/Precast Area
Act | 2AI000ME00320-08225 | Not Started | Completed | Paving Works for Rebar/Precast Area | 2015-12-09 | 2015-12-16 | 2015-12-09 | 2015-12-16
3 |  |  |  | Vehicle/Equipment Maintenance Area
Act | 2AI000ME00320-08230 | Not Started | Completed | Vehicle/Equipment Maintenance Area | 2015-12-13 | 2015-12-20 | 2015-12-13 | 2015-12-20
Act | 2AI000ME00320-08235 | Not Started | Completed | Fabrication & Installation - Garage Shed | 2015-12-21 | 2015-12-28 | 2015-12-21 | 2015-12-28
Act | 2AI000ME00320-08240 | Not Started | Completed | Installation of Water Tank | 2015-12-29 | 2015-12-30 | 2015-12-29 | 2015-12-30
3 |  |  |  | Structural Material Storage Area
Act | 2AI000ME00320-08245 | Not Started | Completed | Mechanical Fabrication Yard | 2015-12-17 | 2015-12-27 | 2015-12-17 | 2015-12-27
3 |  |  |  | Internal Access Road Work
Act | 2AI000ME00320-08250 | Not Started | Completed | Grading Work | 2015-12-23 | 2015-12-24 | 2015-12-23 | 2015-12-24
Act | 2AI000ME00320-08255 | Not Started | Completed | Milled asphalt Work | 2015-12-26 | 2015-12-29 | 2015-12-26 | 2015-12-29
1 |  |  |  | CONSTRUCTION/PRE-COMM
2 |  |  |  | EXPORT OIL FACILITY - AREA 621
3 |  |  |  | NEW STORAGE TANKS
4 |  |  |  | CIVIL / STRUCTURAL / ARCHITECTURAL
5 |  |  |  | SITE PREPARATION
Act | 2AI101CV01000 | Not Started | Completed | EOF: Site preparation (New storage Tank Area) | 2016-01-25 | 2016-09-05 | 2015-12-08 | 2016-11-24
6 |  |  |  | EOF: Site preparation (New storage Tank Area) including substation
Act | 2AI101CV01000-08000 | Not Started | Completed | EOF:Verification of Survey for existing grade Level | 2016-01-25 | 2016-02-01 | 2015-12-08 | 2016-01-02
Act | 2AI101CV01000-08005 | Not Started | Completed | EOF: Excavation Notification | 2016-02-01 | 2016-02-04 | 2015-12-08 | 2015-12-10
Act | 2AI101CV01000-08010 | Not Started | Completed | EOF:Site clearance & Stripping & disposal of Contaminated material(If any) | 2016-02-04 | 2016-04-20 | 2015-12-27 | 2016-07-15
Act | 2AI101CV01000-08015 | Not Started | Completed | EOF:Grading, Cutting & Stockpiling | 2016-04-21 | 2016-08-09 | 2016-04-25 | 2016-11-24
Act | 2AI101CV01000-08020 | Not Started | Completed | EOF:Grading, Filling & Compaction | 2016-04-21 | 2016-08-18 | 2016-04-20 | 2016-11-24
Act | 2AI101CV01000-08025 | Not Started | Completed | EOF:Disposal of Surplus Material | 2016-05-10 | 2016-09-05 | 2016-04-01 | 2016-11-09
Act | 2AI101CV01000-08100 | Not Started | Completed | EOF: Site preparation (New storage Tank Area) including substation | 2016-01-25 | 2016-09-05 | 2015-12-08 | 2016-11-24
6 |  |  |  | EOF: Site preparation ( Corridor/ Road Area)
5 |  |  |  | EQUIPMENT FOUNDATION
6 |  |  |  | EOF: Balance Tank Foundation
Act | 2AI101CV21000 | Not Started | Completed | EOF: Balance Tank Foundation | 2016-06-13 | 2017-01-02 | 2016-10-30 | 2017-02-08
7 |  |  |  | EOF: Foundation for Overhead Water Tank Structural (52-D-309 A)
Act | 2AI101CV21000-08001 | Not Started | Completed | EOF:Survey Marking, Excavation & Subgrade | 2016-07-25 | 2016-07-26 | 2017-02-06 | 2017-02-08
Act | 2AI101CV21000-08006 | Not Started | Completed | EOF:Blinding/PCC for Foundation | 2016-07-26 | 2016-07-28 | 2017-02-06 | 2017-02-08
Act | 2AI101CV21000-08018 | Not Started | Completed | EOF:Rebar, Formwork for Footing | 2016-07-30 | 2016-08-07 | 2017-02-06 | 2017-02-08
Act | 2AI101CV21000-08021 | Not Started | Completed | EOF:Rebar, Formwork, Install Embedments for Pedestal | 2016-08-11 | 2016-08-22 | 2017-02-06 | 2017-02-08
Act | 2AI101CV21000-08031 | Not Started | Completed | EOF:Concrete Potection for Foundation | 2016-08-30 | 2016-09-04 | 2017-02-06 | 2017-02-08
Act | 2AI101CV21000-08036 | Not Started | Completed | EOF:Backfilling & Compaction for Foundation | 2016-09-05 | 2016-09-11 | 2017-02-06 | 2017-02-08
Act | 2AI101CV21000-08019 | Not Started | Completed | EOF:Concrete Pouring - for Footing | 2016-08-07 | 2016-08-08 | 2017-02-06 | 2017-02-08
Act | 2AI101CV21000-08026 | Not Started | Completed | EOF:Concrete Pouring - for Pedestal | 2016-08-22 | 2016-08-23 | 2017-02-06 | 2017-02-08
Act | 2AI101CV21000-08000 | Not Started | Completed | EOF: Foundation for OverheadWater Tank Structural (52-D-309 A) | 2016-07-25 | 2016-09-11 | 2017-02-06 | 2017-02-08
7 |  |  |  | EOF: Foundation for Overhead Water Tank Structural (52-D-309 B)
Act | 2AI101CV21000-08032 | Not Started | Completed | EOF:Survey Marking, Excavation & Subgrade | 2016-07-31 | 2016-08-01 | 2017-02-06 | 2017-02-08
Act | 2AI101CV21000-08037 | Not Started | Completed | EOF:Blinding/PCC for Foundation | 2016-08-01 | 2016-08-03 | 2017-02-06 | 2017-02-08
Act | 2AI101CV21000-08041 | Not Started | Completed | EOF:Rebar, Formwork for Footing | 2016-08-04 | 2016-08-09 | 2017-02-06 | 2017-02-08
Act | 2AI101CV21000-08046 | Not Started | Completed | EOF:Rebar, Formwork, Install Embedments for Pedestal | 2016-08-14 | 2016-08-18 | 2017-02-06 | 2017-02-08
Act | 2AI101CV21000-08050 | Not Started | Completed | EOF:Concrete Potection for Foundation | 2016-08-27 | 2016-08-30 | 2017-02-06 | 2017-02-08
Act | 2AI101CV21000-08055 | Not Started | Completed | EOF:Backfilling & Compaction for Foundation | 2016-08-31 | 2016-09-06 | 2017-02-06 | 2017-02-08
Act | 2AI101CV21000-08042 | Not Started | Completed | EOF:Concrete Pouring - for Footing | 2016-08-09 | 2016-08-10 | 2017-02-06 | 2017-02-08
Act | 2AI101CV21000-08047 | Not Started | Completed | EOF:Concrete Pouring - for Pedestal | 2016-08-18 | 2016-08-20 | 2017-02-06 | 2017-02-08
Act | 2AI101CV21000-08005 | Not Started | Completed | EOF: Foundation for OverheadWater Tank Structural (52-D-309 B) | 2016-07-31 | 2016-09-06 | 2017-02-06 | 2017-02-08
7 |  |  |  | EOF: Foundation for Diesel Engine drain tank-52-D-304A
Act | 2AI101CV21000-08060 | Not Started | Completed | EOF:Survey Marking, Excavation & Subgrade | 2016-09-19 | 2016-09-20 | 2016-11-07 | 2016-11-09
Act | 2AI101CV21000-08065 | Not Started | Completed | EOF:Blinding/PCC for Foundation | 2016-09-20 | 2016-09-22 | 2016-11-07 | 2016-11-09
Act | 2AI101CV21000-08070 | Not Started | Completed | EOF:Rebar, Formwork for Footing | 2016-09-24 | 2016-09-29 | 2016-11-07 | 2016-11-09
Act | 2AI101CV21000-08075 | Not Started | Completed | EOF:Rebar, Formwork, Install Embedments for Pedestal | 2016-10-04 | 2016-10-10 | 2016-11-07 | 2016-11-09
Act | 2AI101CV21000-08080 | Not Started | Completed | EOF:Concrete Potection for Foundation | 2016-10-18 | 2016-10-24 | 2016-11-07 | 2016-11-09
Act | 2AI101CV21000-08085 | Not Started | Completed | EOF:Backfilling & Compaction for Foundation | 2016-10-25 | 2016-10-31 | 2016-11-07 | 2016-11-09
Act | 2AI101CV21000-08071 | Not Started | Completed | EOF:Concrete Pouring - for Footing | 2016-09-29 | 2016-10-01 | 2016-11-07 | 2016-11-09
Act | 2AI101CV21000-08076 | Not Started | Completed | EOF:Concrete Pouring - for Pedestal | 2016-10-10 | 2016-10-11 | 2016-11-07 | 2016-11-09
Act | 2AI101CV21000-08010 | Not Started | Completed | EOF: Foundation for Diesel Engine drain tank-52-D-304A | 2016-09-19 | 2016-10-31 | 2016-11-07 | 2016-11-09
7 |  |  |  | EOF: Foundation for Diesel Engine drain tank-52-D-304B
Act | 2AI101CV21000-08090 | Not Started | Completed | EOF:Survey Marking, Excavation & Subgrade | 2016-06-13 | 2016-06-14 | 2016-11-07 | 2016-11-09
Act | 2AI101CV21000-08095 | Not Started | Completed | EOF:Blinding/PCC for Foundation | 2016-06-14 | 2016-06-16 | 2016-11-07 | 2016-11-09
Act | 2AI101CV21000-08100 | Not Started | Completed | EOF:Rebar, Formwork for Footing | 2016-06-18 | 2016-06-23 | 2016-11-07 | 2016-11-09
Act | 2AI101CV21000-08105 | Not Started | Completed | EOF:Rebar, Formwork, Install Embedments for Pedestal | 2016-06-28 | 2016-07-04 | 2016-11-07 | 2016-11-09
Act | 2AI101CV21000-08110 | Not Started | Completed | EOF:Concrete Potection for Foundation | 2016-07-06 | 2016-07-12 | 2016-11-07 | 2016-11-09
Act | 2AI101CV21000-08115 | Not Started | Completed | EOF:Backfilling & Compaction for Foundation | 2016-07-09 | 2016-07-14 | 2016-11-07 | 2016-11-09
Act | 2AI101CV21000-08101 | Not Started | Completed | EOF:Concrete Pouring - for Footing | 2016-06-23 | 2016-06-25 | 2016-11-07 | 2016-11-09
Act | 2AI101CV21000-08106 | Not Started | Completed | EOF:Concrete Pouring - for Pedestal | 2016-07-04 | 2016-07-05 | 2016-11-07 | 2016-11-09
Act | 2AI101CV21000-08015 | Not Started | Completed | EOF: Foundation for Diesel Engine drain tank-52-D-304B | 2016-06-13 | 2016-07-14 | 2016-11-07 | 2016-11-09
7 |  |  |  | EOF: Foundation for Foam drain tank-52-D-305A
Act | 2AI101CV21000-08120 | Not Started | Completed | EOF:Survey Marking, Excavation & Subgrade | 2016-09-20 | 2016-09-21 | 2016-11-07 | 2016-11-09
Act | 2AI101CV21000-08125 | Not Started | Completed | EOF:Blinding/PCC for Foundation | 2016-09-21 | 2016-09-24 | 2016-11-07 | 2016-11-09
Act | 2AI101CV21000-08130 | Not Started | Completed | EOF:Rebar, Formwork for Footing | 2016-10-10 | 2016-10-18 | 2016-11-07 | 2016-11-09
Act | 2AI101CV21000-08132 | Not Started | Completed | EOF:Rebar, Formwork, Install Embedments for Pedestal | 2016-10-19 | 2016-10-30 | 2016-11-07 | 2016-11-09
Act | 2AI101CV21000-08140 | Not Started | Completed | EOF:Concrete Potection for Foundation | 2016-11-07 | 2016-11-12 | 2016-11-07 | 2016-11-12
Act | 2AI101CV21000-08145 | Not Started | Completed | EOF:Backfilling & Compaction for Foundation | 2016-11-13 | 2016-11-19 | 2016-11-13 | 2016-11-19
Act | 2AI101CV21000-08131 | Not Started | Completed | EOF:Concrete Pouring - for Footing | 2016-10-18 | 2016-10-19 | 2016-11-07 | 2016-11-09
Act | 2AI101CV21000-08136 | Not Started | Completed | EOF:Concrete Pouring - for Pedestal | 2016-10-30 | 2016-10-31 | 2016-10-30 | 2016-10-31
Act | 2AI101CV21000-08020 | Not Started | Completed | EOF: Foundation for Foam drain tank-52-D-305A | 2016-09-20 | 2016-11-19 | 2016-10-30 | 2016-11-19
7 |  |  |  | EOF: Foundation for Foam drain tank-52-D-305B
Act | 2AI101CV21000-08150 | Not Started | Completed | EOF:Survey Marking, Excavation & Subgrade | 2016-11-19 | 2016-11-20 | 2016-11-19 | 2016-11-20
Act | 2AI101CV21000-08155 | Not Started | Completed | EOF:Blinding/PCC for Foundation | 2016-11-20 | 2016-11-22 | 2016-11-20 | 2016-11-22
Act | 2AI101CV21000-08160 | Not Started | Completed | EOF:Rebar, Formwork for Footing | 2016-11-23 | 2016-12-01 | 2016-11-07 | 2016-11-09
Act | 2AI101CV21000-08165 | Not Started | Completed | EOF:Rebar, Formwork, Install Embedments for Pedestal | 2016-12-03 | 2016-12-13 | 2016-11-07 | 2016-11-09
Act | 2AI101CV21000-08170 | Not Started | Completed | EOF:Concrete Potection for Foundation | 2016-12-21 | 2016-12-26 | 2016-11-07 | 2016-11-09
Act | 2AI101CV21000-08175 | Not Started | Completed | EOF:Backfilling & Compaction for Foundation | 2016-12-27 | 2017-01-02 | 2016-11-07 | 2016-11-09
Act | 2AI101CV21000-08161 | Not Started | Completed | EOF:Concrete Pouring - for Footing | 2016-12-01 | 2016-12-03 | 2016-11-07 | 2016-11-09
Act | 2AI101CV21000-08166 | Not Started | Completed | EOF:Concrete Pouring - for Pedestal | 2016-12-13 | 2016-12-14 | 2016-11-07 | 2016-11-09
Act | 2AI101CV21000-08025 | Not Started | Completed | EOF: Foundation for Foam drain tank-52-D-305B | 2016-11-19 | 2017-01-02 | 2016-11-07 | 2016-11-22
7 |  |  |  | EOF: Foundation for Flushing water drain tank-52-D-306A
Act | 2AI101CV21000-08180 | Not Started | Completed | EOF:Survey Marking, Excavation & Subgrade | 2016-09-21 | 2016-09-22 | 2016-11-07 | 2016-11-09
Act | 2AI101CV21000-08185 | Not Started | Completed | EOF:Blinding/PCC for Fnd | 2016-09-21 | 2016-09-24 | 2016-11-07 | 2016-11-09
Act | 2AI101CV21000-08190 | Not Started | Completed | EOF:Rebar, Formwork for Footing | 2016-09-24 | 2016-09-28 | 2016-11-07 | 2016-11-09
Act | 2AI101CV21000-08195 | Not Started | Completed | EOF:Rebar, Formwork, Install Embedments for Pedestal | 2016-09-29 | 2016-10-04 | 2016-11-07 | 2016-11-09
Act | 2AI101CV21000-08200 | Not Started | Completed | EOF:Concrete Potection for Fnd | 2016-10-12 | 2016-10-17 | 2016-11-07 | 2016-11-09
Act | 2AI101CV21000-08205 | Not Started | Completed | EOF:Backfilling & Compaction for Fnd | 2016-10-20 | 2016-10-22 | 2016-11-07 | 2016-11-09
Act | 2AI101CV21000-08191 | Not Started | Completed | EOF:Concrete Pouring - for Footing | 2016-09-28 | 2016-09-29 | 2016-11-07 | 2016-11-09
Act | 2AI101CV21000-08196 | Not Started | Completed | EOF:Concrete Pouring - for Pedestal | 2016-10-04 | 2016-10-05 | 2016-11-07 | 2016-11-09
Act | 2AI101CV21000-08030 | Not Started | Completed | EOF: Foundation for Flushing water drain tank-52-D-306A | 2016-09-21 | 2016-10-22 | 2016-11-07 | 2016-11-09
7 |  |  |  | EOF: Foundation for Flushing water drain tank-52-D-306B
Act | 2AI101CV21000-08210 | Not Started | Completed | EOF:Survey Marking, Excavation & Subgrade | 2016-10-22 | 2016-10-23 | 2016-11-07 | 2016-11-09
Act | 2AI101CV21000-08215 | Not Started | Completed | EOF:Blinding/PCC for Fnd | 2016-10-23 | 2016-10-25 | 2016-11-07 | 2016-11-09
Act | 2AI101CV21000-08220 | Not Started | Completed | EOF:Rebar, Formwork for Footing | 2016-10-26 | 2016-10-31 | 2016-11-07 | 2016-11-09
Act | 2AI101CV21000-08225 | Not Started | Completed | EOF:Rebar, Formwork, Install Embedments for Pedestal | 2016-11-03 | 2016-11-08 | 2016-11-03 | 2016-11-08
Act | 2AI101CV21000-08230 | Not Started | Completed | EOF:Concrete Potection for Fnd | 2016-11-16 | 2016-11-21 | 2016-11-16 | 2016-11-21
Act | 2AI101CV21000-08235 | Not Started | Completed | EOF:Backfilling & Compaction for Fnd | 2016-11-22 | 2016-11-27 | 2016-11-07 | 2016-11-09
Act | 2AI101CV21000-08221 | Not Started | Completed | EOF:Concrete Pouring - for Footing | 2016-10-31 | 2016-11-01 | 2016-10-31 | 2016-11-01
Act | 2AI101CV21000-08226 | Not Started | Completed | EOF:Concrete Pouring - for Pedestal | 2016-11-08 | 2016-11-09 | 2016-11-08 | 2016-11-09
Act | 2AI101CV21000-08035 | Not Started | Completed | EOF: Foundation for Flushing water drain tank-52-D-306B | 2016-10-22 | 2016-11-27 | 2016-10-31 | 2016-11-21
7 |  |  |  | EOF: Foundation for Water drain tank-52-D-308A
Act | 2AI101CV21000-08240 | Not Started | Completed | EOF:Survey Marking, Excavation & Subgrade | 2016-09-28 | 2016-09-29 | 2017-01-02 | 2017-01-04
Act | 2AI101CV21000-08245 | Not Started | Completed | EOF:Blinding/PCC for Fnd | 2016-09-29 | 2016-10-02 | 2017-01-02 | 2017-01-04
Act | 2AI101CV21000-08250 | Not Started | Completed | EOF:Rebar, Formwork for Footing | 2016-10-04 | 2016-10-09 | 2017-01-02 | 2017-01-04
Act | 2AI101CV21000-08255 | Not Started | Completed | EOF:Rebar, Formwork, Install Embedments for Pedestal | 2016-10-12 | 2016-10-17 | 2017-01-02 | 2017-01-04
Act | 2AI101CV21000-08260 | Not Started | Completed | EOF:Concrete Potection for Fnd | 2016-10-25 | 2016-10-30 | 2017-01-02 | 2017-01-04
Act | 2AI101CV21000-08265 | Not Started | Completed | EOF:Backfilling & Compaction for Fnd | 2016-11-02 | 2016-11-07 | 2017-01-02 | 2017-01-04
Act | 2AI101CV21000-08251 | Not Started | Completed | EOF:Concrete Pouring - for Footing | 2016-10-09 | 2016-10-10 | 2017-01-02 | 2017-01-04
Act | 2AI101CV21000-08256 | Not Started | Completed | EOF:Concrete Pouring - for Pedestal | 2016-10-17 | 2016-10-18 | 2017-01-02 | 2017-01-04
Act | 2AI101CV21000-08040 | Not Started | Completed | EOF: Foundation for Water drain tank-52-D-308A | 2016-09-28 | 2016-11-07 | 2017-01-02 | 2017-01-04
7 |  |  |  | EOF: Foundation for Water drain tank-52-D-308B
Act | 2AI101CV21000-08270 | Not Started | Completed | EOF:Survey Marking, Excavation & Subgrade | 2016-11-27 | 2016-11-28 | 2017-01-02 | 2017-01-04
Act | 2AI101CV21000-08275 | Not Started | Completed | EOF:Blinding/PCC for Fnd | 2016-11-28 | 2016-11-30 | 2017-01-02 | 2017-01-04
Act | 2AI101CV21000-08280 | Not Started | Completed | EOF:Rebar, Formwork for Footing | 2016-12-01 | 2016-12-06 | 2017-01-02 | 2017-01-04
Act | 2AI101CV21000-08285 | Not Started | Completed | EOF:Rebar, Formwork, Install Embedments for Pedestal | 2016-12-10 | 2016-12-14 | 2017-01-02 | 2017-01-04
Act | 2AI101CV21000-08290 | Not Started | Completed | EOF:Concrete Potection for Fnd | 2016-12-22 | 2016-12-27 | 2017-01-02 | 2017-01-04
Act | 2AI101CV21000-08295 | Not Started | Completed | EOF:Backfilling & Compaction for Fnd | 2016-12-28 | 2017-01-02 | 2016-12-28 | 2017-01-02
Act | 2AI101CV21000-08281 | Not Started | Completed | EOF:Concrete Pouring - for Footing | 2016-12-06 | 2016-12-07 | 2017-01-02 | 2017-01-04
Act | 2AI101CV21000-08286 | Not Started | Completed | EOF:Concrete Pouring - for Pedestal | 2016-12-14 | 2016-12-15 | 2017-01-02 | 2017-01-04
Act | 2AI101CV21000-08045 | Not Started | Completed | EOF: Foundation for Water drain tank-52-D-308B | 2016-11-27 | 2017-01-02 | 2016-12-28 | 2017-01-04
6 |  |  |  | EOF: Pump Foundation
Act | 2AI101CV22000 | Not Started | Completed | EOF: Pump Foundation | 2016-09-29 | 2016-11-21 | 2016-12-12 | 2017-03-07
7 |  |  |  | EOF: Foundation for Trim Pump - 52-G-301A
Act | 2AI101CV22000-08001 | Not Started | Completed | EOF:Survey Marking, Excavation & Subgrade | 2016-09-29 | 2016-10-03 | 2016-12-12 | 2016-12-14
Act | 2AI101CV22000-08006 | Not Started | Completed | EOF:Blinding/PCC for Fnd | 2016-10-03 | 2016-10-05 | 2016-12-17 | 2016-12-17
Act | 2AI101CV22000-08010 | Not Started | Completed | EOF:Rebar, Formwork for Footing | 2016-10-06 | 2016-10-15 | 2017-01-07 | 2017-02-01
Act | 2AI101CV22000-08015 | Not Started | Completed | EOF:Rebar, Formwork, Install Embedments for Pedestal | 2016-10-18 | 2016-10-26 | 2017-01-28 | 2017-02-01
Act | 2AI101CV22000-08020 | Not Started | Completed | EOF:Concrete Potection for Fnd | 2016-11-03 | 2016-11-08 | 2017-02-16 | 2017-02-23
Act | 2AI101CV22000-08025 | Not Started | Completed | EOF:Backfilling & Compaction for Fnd | 2016-11-12 | 2016-11-17 | 2017-03-01 | 2017-03-07
Act | 2AI101CV22000-08011 | Not Started | Completed | EOF:Concrete Pouring - for Footing | 2016-10-15 | 2016-10-16 | 2017-02-02 | 2017-02-02
Act | 2AI101CV22000-08016 | Not Started | Completed | EOF:Concrete Pouring - for Pedestal | 2016-10-26 | 2016-10-27 | 2017-02-02 | 2017-02-02
Act | 2AI101CV22000-08000 | Not Started | Completed | EOF: Foundation for Trim Pump - 52-G-301A | 2016-09-29 | 2016-11-17 | 2016-12-12 | 2017-03-07
7 |  |  |  | EOF: Foundation for Trim Pump - 52-G-301 B
Act | 2AI101CV22000-08030 | Not Started | Completed | EOF:Survey Marking, Excavation & Subgrade | 2016-10-03 | 2016-10-06 | 2016-12-12 | 2016-12-14
Act | 2AI101CV22000-08035 | Not Started | Completed | EOF:Blinding/PCC for Fnd | 2016-10-06 | 2016-10-09 | 2016-12-17 | 2016-12-17
Act | 2AI101CV22000-08040 | Not Started | Completed | EOF:Rebar, Formwork for Footing | 2016-10-10 | 2016-10-18 | 2017-01-07 | 2017-02-01
Act | 2AI101CV22000-08045 | Not Started | Completed | EOF:Rebar, Formwork, Install Embedments for Pedestal | 2016-10-22 | 2016-10-30 | 2017-01-28 | 2017-02-01
Act | 2AI101CV22000-08050 | Not Started | Completed | EOF:Concrete Potection for Fnd | 2016-11-07 | 2016-11-12 | 2017-02-16 | 2017-02-23
Act | 2AI101CV22000-08055 | Not Started | Completed | EOF:Backfilling & Compaction for Fnd | 2016-11-15 | 2016-11-21 | 2017-03-01 | 2017-03-07
Act | 2AI101CV22000-08041 | Not Started | Completed | EOF:Concrete Pouring - for Footing | 2016-10-18 | 2016-10-19 | 2017-02-02 | 2017-02-02
Act | 2AI101CV22000-08046 | Not Started | Completed | EOF:Concrete Pouring - for Pedestal | 2016-10-30 | 2016-10-31 | 2017-02-02 | 2017-02-02
Act | 2AI101CV22000-08005 | Not Started | Completed | EOF: Foundation for Trim Pump - 52-G-301 B | 2016-10-03 | 2016-11-21 | 2016-12-12 | 2017-03-07
6 |  |  |  | EOF: Pump Shelter Foundation
Act | 2AI101CV22200 | Not Started | Completed | EOF: Pump Shelter Foundation | 2016-11-15 | 2017-01-03 | 2017-02-04 | 2017-03-07
7 |  |  |  | EOF: Trim Pump - 52-G-301A Shelter Foundation
Act | 2AI101CV22200-08001 | Not Started | Completed | EOF:Survey Marking, Excavation & Subgrade | 2016-11-15 | 2016-11-17 | 2017-02-04 | 2017-02-04
Act | 2AI101CV22200-08006 | Not Started | Completed | EOF:Blinding/PCC for Fnd | 2016-11-17 | 2016-11-20 | 2017-02-05 | 2017-02-05
Act | 2AI101CV22200-08010 | Not Started | Completed | EOF:Rebar, Formwork for Footing | 2016-11-21 | 2016-11-27 | 2017-02-05 | 2017-02-07
Act | 2AI101CV22200-08015 | Not Started | Completed | EOF:Rebar, Formwork, Install Embedments for Pedestal | 2016-11-30 | 2016-12-07 | 2017-02-09 | 2017-02-13
Act | 2AI101CV22200-08020 | Not Started | Completed | EOF:Concrete Potection for Fnd | 2016-12-15 | 2016-12-20 | 2017-02-28 | 2017-03-06
Act | 2AI101CV22200-08025 | Not Started | Completed | EOF:Backfilling & Compaction for Fnd | 2016-12-24 | 2016-12-28 | 2017-03-01 | 2017-03-07
Act | 2AI101CV22200-08011 | Not Started | Completed | EOF:Concrete Pouring - for Footing | 2016-11-27 | 2016-11-28 | 2017-02-08 | 2017-02-08
Act | 2AI101CV22200-08016 | Not Started | Completed | EOF:Concrete Pouring - for Pedestal | 2016-12-07 | 2016-12-08 | 2017-02-14 | 2017-02-14
Act | 2AI101CV22200-08000 | Not Started | Completed | EOF: Trim Pump - 52-G-301A Shelter Foundation | 2016-11-15 | 2016-12-28 | 2017-02-04 | 2017-03-07
7 |  |  |  | EOF: Trim Pump - 52-G-301B Shelter Foundation
Act | 2AI101CV22200-08030 | Not Started | Completed | EOF:Survey Marking, Excavation & Subgrade | 2016-11-20 | 2016-11-22 | 2017-02-04 | 2017-02-04
Act | 2AI101CV22200-08035 | Not Started | Completed | EOF:Blinding/PCC for Fnd | 2016-11-22 | 2016-11-24 | 2017-02-05 | 2017-02-05
Act | 2AI101CV22200-08040 | Not Started | Completed | EOF:Rebar, Formwork for Footing | 2016-11-26 | 2016-12-01 | 2017-02-06 | 2017-02-07
Act | 2AI101CV22200-08045 | Not Started | Completed | EOF:Rebar, Formwork, Install Embedments for Pedestal | 2016-12-06 | 2016-12-13 | 2017-02-09 | 2017-02-13
Act | 2AI101CV22200-08050 | Not Started | Completed | EOF:Concrete Potection for Fnd | 2016-12-21 | 2016-12-26 | 2017-02-28 | 2017-03-06
Act | 2AI101CV22200-08055 | Not Started | Completed | EOF:Backfilling & Compaction for Fnd | 2016-12-29 | 2017-01-03 | 2017-03-01 | 2017-03-07
Act | 2AI101CV22200-08041 | Not Started | Completed | EOF:Concrete Pouring - for Footing | 2016-12-01 | 2016-12-03 | 2017-02-08 | 2017-02-08
Act | 2AI101CV22200-08046 | Not Started | Completed | EOF:Concrete Pouring - for Pedestal | 2016-12-13 | 2016-12-14 | 2017-02-14 | 2017-02-14
Act | 2AI101CV22200-08005 | Not Started | Completed | EOF: Trim Pump - 52-G-301B Shelter Foundation | 2016-11-20 | 2017-01-03 | 2017-02-04 | 2017-03-07
6 |  |  |  | EOF: Foam Pump House Building Foundation
Act | 2AI101CV22300 | Not Started | Completed | EOF: Foam Pump House Building Foundation | 2016-08-27 | 2016-11-17 | 2016-11-30 | 2017-03-10
7 |  |  |  | EOF: 621-G-302 A/B Foam Pump House Steel Building Foundation
Act | 2AI101CV22300-08001 | Not Started | Completed | EOF:Survey Marking, Excavation & Subgrade | 2016-08-27 | 2016-08-30 | 2016-11-30 | 2016-11-30
Act | 2AI101CV22300-08006 | Not Started | Completed | EOF:Blinding/PCC for Fnd | 2016-08-30 | 2016-09-01 | 2017-02-11 | 2017-02-11
Act | 2AI101CV22300-08010 | Not Started | Completed | EOF:Rebar, Formwork for Footing | 2016-09-03 | 2016-09-14 | 2017-02-13 | 2017-02-15
Act | 2AI101CV22300-08015 | Not Started | Completed | EOF:Rebar, Formwork, Install Embedments for Pedestal | 2016-09-19 | 2016-10-10 | 2017-02-18 | 2017-02-23
Act | 2AI101CV22300-08020 | Not Started | Completed | EOF:Concrete Potection for Fnd | 2016-10-18 | 2016-10-25 | 2017-03-02 | 2017-03-07
Act | 2AI101CV22300-08025 | Not Started | Completed | EOF:Backfilling & Compaction for Fnd | 2016-10-29 | 2016-11-03 | 2017-03-07 | 2017-03-10
Act | 2AI101CV22300-08011 | Not Started | Completed | EOF:Concrete Pouring - for Footing | 2016-09-14 | 2016-09-15 | 2017-02-16 | 2017-02-16
Act | 2AI101CV22300-08016 | Not Started | Completed | EOF:Concrete Pouring - for Pedestal | 2016-10-10 | 2016-10-11 | 2017-02-27 | 2017-02-27
Act | 2AI101CV22300-08000 | Not Started | Completed | EOF: 621-G-302 A/B Foam Pump House Steel Building Foundation | 2016-08-27 | 2016-11-03 | 2016-11-30 | 2017-03-10
7 |  |  |  | EOF: 621-G-302 C/D Foam Pump House Steel Building Foundation
Act | 2AI101CV22300-08030 | Not Started | Completed | EOF:Survey Marking, Excavation & Subgrade | 2016-09-11 | 2016-09-14 | 2016-12-05 | 2016-12-06
Act | 2AI101CV22300-08035 | Not Started | Completed | EOF:Blinding/PCC for Fnd | 2016-09-14 | 2016-09-17 | 2017-02-11 | 2017-02-11
Act | 2AI101CV22300-08040 | Not Started | Completed | EOF:Rebar, Formwork for Footing | 2016-09-18 | 2016-09-29 | 2017-02-12 | 2017-02-15
Act | 2AI101CV22300-08045 | Not Started | Completed | EOF:Rebar, Formwork, Install Embedments for Pedestal | 2016-10-03 | 2016-10-24 | 2017-02-18 | 2017-02-20
Act | 2AI101CV22300-08050 | Not Started | Completed | EOF:Concrete Potection for Fnd | 2016-11-01 | 2016-11-08 | 2017-03-02 | 2017-03-07
Act | 2AI101CV22300-08055 | Not Started | Completed | EOF:Backfilling & Compaction for Fnd | 2016-11-12 | 2016-11-17 | 2017-03-07 | 2017-03-10
Act | 2AI101CV22300-08041 | Not Started | Completed | EOF:Concrete Pouring - for Footing | 2016-09-29 | 2016-10-01 | 2017-02-16 | 2017-02-16
Act | 2AI101CV22300-08046 | Not Started | Completed | EOF:Concrete Pouring - for Pedestal | 2016-10-24 | 2016-10-25 | 2017-02-27 | 2017-02-27
Act | 2AI101CV22300-08005 | Not Started | Completed | EOF: 621-G-302 C/D Foam Pump House Steel Building Foundation | 2016-09-11 | 2016-11-17 | 2016-12-05 | 2017-03-10
5 |  |  |  | TANK FOUNDATION
6 |  |  |  | EOF:Lot-1-J : LFHO Storage Tank (52-D-93 & 52-D-94) : Ring wall type Foundation
Act | 2AI101CV01400 | Not Started | Completed | EOF:Lot-1-J : LFHO Storage Tank (52-D-93 & 52-D-94) : Ring wall type Foundation | 2016-04-24 | 2016-06-29 | 2016-03-29 | 2016-08-01
7 |  |  |  | EOF:LFHO Storage Tank 52-D-93 : Ring wall type Foundation
Act | 2AI101CV01400-08001 | Not Started | Completed | EOF:Survey Marking, Excavation & Subgrade | 2016-04-28 | 2016-05-04 | 2016-04-05 | 2016-04-16
Act | 2AI101CV01400-08006 | Not Started | Completed | EOF:Blinding/PCC for Fnd of Infield Storage Tank 52-D-93 | 2016-05-04 | 2016-05-10 | 2016-04-19 | 2016-04-19
Act | 2AI101CV01400-08009 | Not Started | Completed | EOF:Rebar, Formwork & Construction joint of Storage Tank 52-D-93 | 2016-05-15 | 2016-05-25 | 2016-04-24 | 2016-05-07
Act | 2AI101CV01400-08015 | Not Started | Completed | EOF:Concrete protection for Ring wall fnd of Storage Tank 52-D-93 | 2016-06-21 | 2016-06-29 | 2016-06-21 | 2016-08-01
Act | 2AI101CV01400-08011 | Not Started | Completed | EOF:Concrete Pouring - for Footing | 2016-05-25 | 2016-05-26 | 2016-05-08 | 2016-05-08
Act | 2AI101CV01400-08012 | Not Started | Completed | EOF:Rebar, Formwork & Install Embedments (Ring beam wall) | 2016-05-24 | 2016-06-13 | 2016-05-18 | 2016-06-11
Act | 2AI101CV01400-08013 | Not Started | Completed | EOF:Concrete Pouring for Ring beam wall | 2016-06-13 | 2016-06-14 | 2016-06-13 | 2016-06-13
Act | 2AI101CV01400-08005 | Not Started | Completed | EOF:LFHO Storage Tank 52-D-93 : Ring wall type Foundation | 2016-04-28 | 2016-06-29 | 2016-04-05 | 2016-08-01
7 |  |  |  | EOF:LFHO Storage Tank 52-D-94 : Ring wall type Foundation
Act | 2AI101CV01400-08020 | Not Started | Completed | EOF:Survey Marking, Excavation & Subgrade | 2016-04-24 | 2016-04-28 | 2016-03-29 | 2016-04-04
Act | 2AI101CV01400-08025 | Not Started | Completed | EOF:Blinding/PCC for Fnd of Infield Storage Tank 52-D-94 | 2016-04-28 | 2016-05-03 | 2016-04-14 | 2016-04-14
Act | 2AI101CV01400-08030 | Not Started | Completed | EOF:Rebar, Formwork & Construction joint of Storage Tank 52-D-94 | 2016-05-03 | 2016-05-15 | 2016-04-19 | 2016-05-01
Act | 2AI101CV01400-08035 | Not Started | Completed | EOF:Concrete protection for Ring wall fnd of Storage Tank 52-D-94 | 2016-06-09 | 2016-06-16 | 2016-06-11 | 2016-07-20
Act | 2AI101CV01400-08031 | Not Started | Completed | EOF:Concrete Pouring - for Footing | 2016-05-15 | 2016-05-16 | 2016-05-03 | 2016-05-03
Act | 2AI101CV01400-08032 | Not Started | Completed | EOF:Rebar, Formwork & Install Embedments (Ring beam wall) | 2016-05-18 | 2016-06-07 | 2016-05-05 | 2016-05-24
Act | 2AI101CV01400-08033 | Not Started | Completed | EOF:Concrete Pouring for Ring beam wall | 2016-06-08 | 2016-06-08 | 2016-05-25 | 2016-05-25
Act | 2AI101CV01400-08010 | Not Started | Completed | EOF:LFHO Storage Tank 52-D-94 : Ring wall type Foundation | 2016-04-24 | 2016-06-16 | 2016-03-29 | 2016-07-20
6 |  |  |  | EOF:Lot-1-J : LFHO Storage Tank (52-D-93 & 52-D-94) : Backfilling
Act | 2AI101CV01500 | Not Started | In Progress | EOF:Lot-1-J : LFHO Storage Tank (52-D-93 & 52-D-94) : Backfilling | 2016-06-16 | 2016-09-08 | 2016-06-06
7 |  |  |  | LFHO Storage Tank (52-D-93) : Backfilling
Act | 2AI101CV01500-08005 | Not Started | In Progress | LFHO Storage Tank (52-D-93) : Backfilling | 2016-06-29 | 2016-09-08 | 2016-06-26
8 |  |  |  | EOF:LFHO Storage Tank 52-D-93 : Backfilling & Compaction (Internal) for Fnd of Tank
Act | 2AI101CV01500-08000 | Not Started | Completed | EOF:Gatch Filling & Compaction (Internal) for Tank Fnd | 2016-06-29 | 2016-07-05 | 2016-06-26 | 2016-07-26
Act | 2AI101CV01500-08011 | Not Started | Completed | EOF:Geo Membrane laying (Internal) for 52-D-93 Fnd | 2016-07-05 | 2016-07-13 | 2016-07-29 | 2016-08-04
Act | 2AI101CV01500-08015 | Not Started | Completed | EOF:Sand filling (Internal) for 52-D-93 Fnd | 2016-07-13 | 2016-07-17 | 2016-08-05 | 2016-08-06
Act | 2AI101CV01500-08020 | Not Started | Completed | EOF:Install Embedments (Internal) for 52-D-93 Fnd | 2016-07-17 | 2016-07-20 | 2016-08-07 | 2016-08-07
Act | 2AI101CV01500-08025 | Not Started | Completed | EOF:Permeable Sand-gravel filling (Internal) for 52-D-93 Fnd | 2016-07-20 | 2016-07-24 | 2016-08-07 | 2016-08-09
Act | 2AI101CV01500-08030 | Not Started | Completed | EOF:Clean Sand filling after CP installation (Internal) for 52-D-93 Fnd | 2016-08-03 | 2016-08-08 | 2016-08-10 | 2016-09-01
8 |  |  |  | EOF:LFHO Storage Tank 52-D-93 : Backfilling & Compaction (External) for Fnd of Tank
Act | 2AI101CV01500-08035 | Not Started | Completed | Compacted Gatch fill & Blinding for HDPE drain canister (External) | 2016-06-29 | 2016-07-14 | 2016-06-27 | 2018-12-26
Act | 2AI101CV01500-08040 | Not Started | Completed | Crushed Gravel w/ Gatch Mix Layer (External) | 2016-07-14 | 2016-07-20 | 2018-09-09 | 2018-11-04
Act | 2AI101CV01500-08045 | Not Started | Completed | Concreting for Access staircases & Service platforms (External) | 2016-08-10 | 2016-08-14 | 2017-04-20 | 2018-12-15
Act | 2AI101CV01500-08050 | Not Started | In Progress | Asphaltic Concrete layer (External) | 2016-08-21 | 2016-09-07 | 2019-03-05
Act | 2AI101CV01500-08055 | Not Started | Completed | Install PVC leak detection pipes & HDPE drain canister (External) | 2016-08-16 | 2016-09-08 | 2018-12-03 | 2019-03-06
Act | 2AI101CV01500-08042 | Not Started | Completed | Rebar & Formwork for Access staircases & Service platforms (External) | 2016-07-20 | 2016-08-13 | 2017-04-03 | 2018-12-05
7 |  |  |  | LFHO Storage Tank (52-D-94) : Backfilling
Act | 2AI101CV01500-08010 | Not Started | In Progress | LFHO Storage Tank (52-D-94) : Backfilling | 2016-06-16 | 2016-08-27 | 2016-06-06
8 |  |  |  | EOF:LFHO Storage Tank 52-D-94 : Backfilling & Compaction (Internal) for Fnd of Tank
Act | 2AI101CV01500-08070 | Not Started | Completed | EOF:Gatch Filling & Compaction (Internal) for Tank Fnd | 2016-06-18 | 2016-06-30 | 2016-06-14 | 2016-06-30
Act | 2AI101CV01500-08075 | Not Started | Completed | EOF:Sand layer & Compaction (Internal) for 52-D-94 Fnd | 2016-06-30 | 2016-07-03 | 2016-06-30 | 2016-07-23
Act | 2AI101CV01500-08080 | Not Started | Completed | EOF:Geo Membrane laying (Internal) for 52-D-94 Fnd | 2016-07-03 | 2016-07-11 | 2016-07-19 | 2016-07-24
Act | 2AI101CV01500-08085 | Not Started | Completed | EOF:Sand filling (Internal) for 52-D-94 Fnd | 2016-07-11 | 2016-07-13 | 2016-07-25 | 2016-07-26
Act | 2AI101CV01500-08090 | Not Started | Completed | EOF:Install Embedments (Internal) for 52-D-94 Fnd | 2016-07-13 | 2016-07-16 | 2016-07-27 | 2016-07-27
Act | 2AI101CV01500-08095 | Not Started | Completed | EOF:Permeable Sand-gravel filling (Internal) for 52-D-94 Fnd | 2016-07-16 | 2016-07-19 | 2016-07-27 | 2016-08-01
Act | 2AI101CV01500-08100 | Not Started | Completed | EOF:Clean Sand filling after CP installation (Internal) for 52-D-94 Fnd | 2016-08-02 | 2016-08-08 | 2016-08-03 | 2016-08-20
8 |  |  |  | EOF:LFHO Storage Tank 52-D-94 : Backfilling & Compaction (External) for Fnd of Tank
Act | 2AI101CV01500-08105 | Not Started | Completed | Compacted Gatch fill & Blinding for HDPE drain canister (External) | 2016-06-16 | 2016-06-30 | 2016-06-06 | 2018-12-26
Act | 2AI101CV01500-08110 | Not Started | Completed | Crushed Gravel w/ Gatch Mix Layer (External) | 2016-06-30 | 2016-07-06 | 2018-10-07 | 2018-12-19
Act | 2AI101CV01500-08115 | Not Started | Completed | Concreting for Access staircases & Service platforms (External) | 2016-07-28 | 2016-08-01 | 2017-04-09 | 2018-12-10
Act | 2AI101CV01500-08120 | Not Started | In Progress | Asphaltic Concrete layer (External) | 2016-08-08 | 2016-08-25 | 2019-03-08
Act | 2AI101CV01500-08125 | Not Started | Completed | Install PVC leak detection pipes & HDPE drain canister (External) | 2016-08-09 | 2016-08-27 | 2018-11-08 | 2019-04-20
Act | 2AI101CV01500-08112 | Not Started | Completed | Rebar & Formwork for Access staircases & Service platforms (External) | 2016-07-06 | 2016-07-31 | 2017-04-03 | 2018-12-05
6 |  |  |  | EOF:Lot-1-J : LFHO Storage Tank (52-D-93 & 52-D-94) : CP works
Act | 2AI101CV01600 | Not Started | Completed | EOF:Lot-1-J : LFHO Storage Tank (52-D-93 & 52-D-94) : CP works | 2016-07-19 | 2017-07-06 | 2016-08-14 | 2016-08-24
7 |  |  |  | EOF:Lot-1-J : LFHO Storage Tank 52-D-93 : CP works
Act | 2AI101CV01600-08000 | Not Started | Completed | EOF:Lot-1-J : LFHO Storage Tank 52-D-93 : Install Cathodic Protection | 2016-07-24 | 2017-07-06 | 2016-08-24 | 2016-08-24
Act | 2AI101CV01600-08005 | Not Started | Completed | LFHO Storage Tank (52-D-93) : CP works | 2016-07-24 | 2017-07-06 | 2016-08-24 | 2016-08-24
7 |  |  |  | EOF:Lot-1-J : LFHO Storage Tank 52-D-94 : CP works
Act | 2AI101CV01600-08006 | Not Started | Completed | EOF:Lot-1-J : LFHO Storage Tank 52-D-94 : Install Cathodic Protection | 2016-07-19 | 2017-06-28 | 2016-08-14 | 2016-08-14
Act | 2AI101CV01600-08010 | Not Started | Completed | LFHO Storage Tank (52-D-94) : CP works | 2016-07-19 | 2017-06-28 | 2016-08-14 | 2016-08-14
6 |  |  |  | EOF:Lot-1-J : LFHO Storage Tank (52-D-95 & 52-D-96) : Ring wall type Foundation
Act | 2AI101CV01800 | Not Started | Completed | EOF:Lot-1-J : LFHO Storage Tank (52-D-95 & 52-D-96) : Ring wall type Foundation | 2016-06-05 | 2016-08-04 | 2016-05-06 | 2016-09-23
7 |  |  |  | EOF:LFHO Storage Tank 52-D-95 : Ring wall type Foundation
Act | 2AI101CV01800-08000 | Not Started | Completed | EOF:Survey Marking, Excavation & Subgrade | 2016-06-05 | 2016-06-09 | 2016-05-06 | 2016-05-11
Act | 2AI101CV01800-08006 | Not Started | Completed | EOF:Blinding/PCC for Fnd of Infield Pop Tank 52-D-95 | 2016-06-09 | 2016-06-15 | 2016-05-20 | 2016-05-20
Act | 2AI101CV01800-08011 | Not Started | Completed | EOF:Rebar, Formwork & Construction joint of Storage Tank 52-D-95 | 2016-06-15 | 2016-06-26 | 2016-05-25 | 2016-06-07
Act | 2AI101CV01800-08015 | Not Started | Completed | EOF:Concrete protection for Ring wall fnd of Storage Tank 52-D-95 | 2016-07-20 | 2016-07-28 | 2016-07-17 | 2016-08-29
Act | 2AI101CV01800-08012 | Not Started | Completed | EOF:Concrete Pouring - for Footing | 2016-06-26 | 2016-06-27 | 2016-06-08 | 2016-06-08
Act | 2AI101CV01800-08013 | Not Started | Completed | EOF:Rebar, Formwork & Install Embedments (Ring beam wall) | 2016-06-27 | 2016-07-18 | 2016-06-07 | 2016-07-02
Act | 2AI101CV01800-08014 | Not Started | Completed | EOF:Concrete Pouring for Ring beam wall | 2016-07-18 | 2016-07-19 | 2016-07-04 | 2016-07-04
Act | 2AI101CV01800-08005 | Not Started | Completed | LFHO Storage Tank (52-D-95) : Ring wall type Foundation | 2016-06-05 | 2016-07-28 | 2016-05-06 | 2016-08-29
7 |  |  |  | EOF:LFHO Storage Tank 52-D-96 : Ring wall type Foundation
Act | 2AI101CV01800-08020 | Not Started | Completed | EOF:Survey Marking, Excavation & Subgrade | 2016-06-09 | 2016-06-14 | 2016-05-17 | 2016-07-03
Act | 2AI101CV01800-08025 | Not Started | Completed | EOF:Blinding/PCC for Fnd of Infield Pop Tank 52-D-96 | 2016-06-15 | 2016-06-21 | 2016-06-13 | 2016-07-04
Act | 2AI101CV01800-08030 | Not Started | Completed | EOF:Rebar, Formwork & Construction joint of Storage Tank 52-D-96 | 2016-06-21 | 2016-07-05 | 2016-06-27 | 2016-07-12
Act | 2AI101CV01800-08035 | Not Started | Completed | EOF:Concrete protection for Ring wall fnd of Storage Tank 52-D-96 | 2016-07-28 | 2016-08-04 | 2016-08-28 | 2016-09-23
Act | 2AI101CV01800-08031 | Not Started | Completed | EOF:Concrete Pouring - for Footing | 2016-07-05 | 2016-07-06 | 2016-07-14 | 2016-07-14
Act | 2AI101CV01800-08032 | Not Started | Completed | EOF:Rebar, Formwork & Install Embedments (Ring beam wall) | 2016-07-06 | 2016-07-27 | 2016-07-17 | 2016-08-07
Act | 2AI101CV01800-08033 | Not Started | Completed | EOF:Concrete Pouring for Ring beam wall | 2016-07-27 | 2016-07-28 | 2016-08-08 | 2016-08-08
Act | 2AI101CV01800-08010 | Not Started | Completed | LFHO Storage Tank (52-D-96) : Ring wall type Foundation | 2016-06-09 | 2016-08-04 | 2016-05-17 | 2016-09-23
6 |  |  |  | EOF:Lot-1-J : LFHO Storage Tank (52-D-95 & 52-D-96) : Backfilling
Act | 2AI101CV01900 | Not Started | In Progress | EOF:Lot-1-J : LFHO Storage Tank (52-D-95 & 52-D-96) : Backfilling | 2016-08-01 | 2016-10-11 | 2016-07-22
7 |  |  |  | LFHO Storage Tank (52-D-95) : Backfilling
Act | 2AI101CV01900-08005 | Not Started | In Progress | LFHO Storage Tank (52-D-95) : Backfilling | 2016-08-01 | 2016-10-10 | 2016-07-22
8 |  |  |  | EOF:LFHO Storage Tank 52-D-95 : Backfilling & Compaction (Internal) for Fnd of Tank
Act | 2AI101CV01900-08000 | Not Started | Completed | EOF:Gatch Filling & Compaction (Internal) for Tank Fnd | 2016-08-01 | 2016-08-10 | 2016-07-22 | 2016-08-27
Act | 2AI101CV01900-08006 | Not Started | Completed | EOF:Sand layer & Compaction (Internal) for 52-D-95 Fnd | 2016-08-10 | 2016-08-13 | 2016-08-27 | 2016-08-27
Act | 2AI101CV01900-08011 | Not Started | Completed | EOF:Geo Membrane laying (Internal) for 52-D-95 Fnd | 2016-08-13 | 2016-08-20 | 2016-09-08 | 2016-09-17
Act | 2AI101CV01900-08015 | Not Started | Completed | EOF:Sand filling (Internal) for 52-D-95 Fnd | 2016-08-20 | 2016-08-24 | 2016-09-19 | 2016-09-21
Act | 2AI101CV01900-08020 | Not Started | Completed | EOF:Install Embedments (Internal) for 52-D-95 Fnd | 2016-08-23 | 2016-08-25 | 2016-09-29 | 2016-09-29
Act | 2AI101CV01900-08025 | Not Started | Completed | EOF:Permeable Sand-gravel filling (Internal) for 52-D-95 Fnd | 2016-08-27 | 2016-08-28 | 2016-09-22 | 2016-09-23
Act | 2AI101CV01900-08030 | Not Started | Completed | EOF:Clean Sand filling after CP installation (Internal) for 52-D-95 Fnd | 2016-09-08 | 2016-09-13 | 2016-09-25 | 2016-10-07
8 |  |  |  | EOF:LFHO Storage Tank 52-D-95 : Backfilling & Compaction (External) for Fnd of Tank
Act | 2AI101CV01900-08035 | Not Started | Completed | Compacted Gatch fill & Blinding for HDPE drain canister (External) | 2016-08-02 | 2016-08-16 | 2016-08-08 | 2018-12-26
Act | 2AI101CV01900-08040 | Not Started | Completed | Crushed Gravel w/ Gatch Mix Layer (External) | 2016-08-16 | 2016-08-21 | 2018-12-01 | 2019-01-29
Act | 2AI101CV01900-08045 | Not Started | Completed | Concreting for Access staircases & Service platforms (External) | 2016-09-11 | 2016-09-14 | 2017-04-09 | 2018-12-10
Act | 2AI101CV01900-08050 | Not Started | Not Started | Asphaltic Concrete layer (External) | 2016-09-21 | 2016-10-09
Act | 2AI101CV01900-08055 | Not Started | In Progress | Install PVC leak detection pipes & HDPE drain canister (External) | 2016-09-17 | 2016-10-10 | 2019-01-12
Act | 2AI101CV01900-08042 | Not Started | Completed | Rebar & Formwork for Access staircases & Service platforms (External) | 2016-08-21 | 2016-09-13 | 2017-04-03 | 2018-12-05
7 |  |  |  | LFHO Storage Tank (52-D-96) : Backfilling
Act | 2AI101CV01900-08010 | Not Started | In Progress | LFHO Storage Tank (52-D-96) : Backfilling | 2016-08-04 | 2016-10-11 | 2016-09-08
8 |  |  |  | EOF:LFHO Storage Tank 52-D-96 : Backfilling & Compaction (Internal) for Fnd of Tank
Act | 2AI101CV01900-08070 | Not Started | Completed | EOF:Gatch Filling & Compaction (Internal) for Tank Fnd | 2016-08-04 | 2016-08-11 | 2016-09-08 | 2016-10-09
Act | 2AI101CV01900-08075 | Not Started | Completed | EOF:Sand layer & Compaction (Internal) for 52-D-96 Fnd | 2016-08-11 | 2016-08-14 | 2016-10-10 | 2016-10-10
Act | 2AI101CV01900-08080 | Not Started | Completed | EOF:Geo Membrane laying (Internal) for 52-D-96 Fnd | 2016-08-14 | 2016-08-21 | 2016-10-03 | 2016-10-09
Act | 2AI101CV01900-08085 | Not Started | Completed | EOF:Sand filling (Internal) for 52-D-96 Fnd | 2016-08-21 | 2016-08-25 | 2016-10-10 | 2016-10-15
Act | 2AI101CV01900-08090 | Not Started | Completed | EOF:Install Embedments (Internal) for 52-D-96 Fnd | 2016-08-23 | 2016-08-25 | 2016-10-17 | 2016-10-18
Act | 2AI101CV01900-08095 | Not Started | Completed | EOF:Permeable Sand-gravel filling (Internal) for 52-D-96 Fnd | 2016-08-25 | 2016-08-28 | 2016-10-18 | 2016-10-20
Act | 2AI101CV01900-08100 | Not Started | Completed | EOF:Clean Sand filling after CP installation (Internal) for 52-D-96 Fnd | 2016-09-07 | 2016-09-13 | 2016-10-22 | 2016-11-03
8 |  |  |  | EOF:LFHO Storage Tank 52-D-96 : Backfilling & Compaction (External) for Fnd of Tank
Act | 2AI101CV01900-08105 | Not Started | Completed | Compacted Gatch fill & Blinding for HDPE drain canister (External) | 2016-08-04 | 2016-08-18 | 2016-09-25 | 2018-12-16
Act | 2AI101CV01900-08110 | Not Started | Completed | Crushed Gravel w/ Gatch Mix Layer (External) | 2016-08-18 | 2016-08-24 | 2018-12-22 | 2019-02-07
Act | 2AI101CV01900-08112 | Not Started | Completed | Rebar & Formwork for Access staircases & Service platforms (External) | 2016-08-25 | 2016-09-18 | 2017-04-03 | 2018-12-05
Act | 2AI101CV01900-08115 | Not Started | Completed | Concreting for Access staircases & Service platforms (External) | 2016-09-17 | 2016-09-19 | 2017-04-09 | 2018-12-10
Act | 2AI101CV01900-08120 | Not Started | Not Started | Asphaltic Concrete layer (External) | 2016-09-22 | 2016-10-10
Act | 2AI101CV01900-08125 | Not Started | In Progress | Install PVC leak detection pipes & HDPE drain canister (External) | 2016-09-18 | 2016-10-11 | 2019-01-28
6 |  |  |  | EOF:Lot-1-J : LFHO Storage Tank (52-D-95 & 52-D-96) : CP works
Act | 2AI101CV02000 | Not Started | Completed | EOF:Lot-1-J : LFHO Storage Tank (52-D-95 & 52-D-96) : CP works | 2016-08-28 | 2017-06-28 | 2016-09-26 | 2016-10-31
7 |  |  |  | EOF:Lot-1-J : LFHO Storage Tank 52-D-95 : CP works
Act | 2AI101CV02000-08005 | Not Started | Completed | EOF:Lot-1-J : LFHO Storage Tank 52-D-95 : Install Cathodic Protection | 2016-08-29 | 2017-06-28 | 2016-09-26 | 2016-09-29
7 |  |  |  | EOF:Lot-1-J : LFHO Storage Tank 52-D-96 : CP works
Act | 2AI101CV02000-08010 | Not Started | Completed | EOF:Lot-1-J : LFHO Storage Tank 52-D-96 : Install Cathodic Protection | 2016-08-28 | 2017-06-28 | 2016-10-24 | 2016-10-31
5 |  |  |  | DYKE WALL/BUND WALL
6 |  |  |  | Lot-1-J : LFHO Storage Tank (52-D-93 & 52-D-94) : Construct Bund Wall
Act | 2AI101CV01700 | Not Started | In Progress | EOF:Lot-1-J : LFHO Storage Tank (52-D-93 & 52-D-94) : Construct Bund Wall | 2016-08-09 | 2017-10-28 | 2016-09-08
7 |  |  |  | LFHO Storage Tank (52-D-93) & (52-D-94): Construct Bund Wall
Act | 2AI101CV01700-08010 | Not Started | Completed | EOF:Survey Marking, Excavation & Disposal of unsutiable Material for Bund Wall around Storage tank (52-D-93 & 52-D-94) | 2016-08-09 | 2016-12-27 | 2016-09-08 | 2019-02-06 | [66 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [8 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [8 empty] | 0 | [9 empty] | 8 | [9 empty] | 8 | [8 empty] | 6 | [9 empty] | 0 | [9 empty] | 7 | [9 empty] | 0 | [8 empty] | 0 | [9 empty] | 33 | [9 empty] | 0 |  |  |  |  | 0
Act | 2AI101CV01700-08015 | Not Started | Completed | EOF: Prepare Subgrade lvl for Bund Wall around Storage tank (52-D-93 & 52-D-94) | 2016-08-25 | 2017-01-12 | 2016-12-25 | 2019-01-27 | [66 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [8 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [8 empty] | 2 | [9 empty] | 27 | [9 empty] | 28 | [8 empty] | 26 | [9 empty] | 16 | [9 empty] | 26 | [9 empty] | 0 | [8 empty] | 0 | [9 empty] | 33 | [9 empty] | 0 |  |  |  |  | 0
Act | 2AI101CV01700-08020 | Not Started | Completed | EOF:Slope Preparation for Bund Wall around Storage tank (52-D-93 & 52-D-94) | 2016-09-12 | 2017-01-30 | 2016-12-29 | 2019-01-29 | [66 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [8 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [8 empty] | 2 | [9 empty] | 27 | [9 empty] | 28 | [8 empty] | 26 | [9 empty] | 16 | [9 empty] | 26 | [9 empty] | 0 | [8 empty] | 0 | [9 empty] | 33 | [9 empty] | 0 |  |  |  |  | 0
Act | 2AI101CV01700-08025 | Not Started | Completed | EOF:Install/Cast Catch basin (inside) & Valve pit (outside) for Bund Wall around Storage tank (52-D-93 & 52-D-94) | 2016-09-19 | 2017-03-20 | 2016-10-29 | 2018-10-22 | [66 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [8 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [8 empty] | 24 | [9 empty] | 49 | [9 empty] | 50 | [8 empty] | 48 | [9 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [8 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  |  |  | 0
Act | 2AI101CV01700-08030 | Not Started | Completed | EOF:Lay Drain Pipe (CB to Valve pit) for Bund Wall around Storage tank (52-D-93 & 52-D-94) | 2017-01-03 | 2017-04-01 | 2017-08-24 | 2018-10-10
Act | 2AI101CV01700-08035 | Not Started | Completed | EOF:Sand layer (Inside) upto Linear Menbrane Lvl for Bund Wall around Storage tank (52-D-93 & 52-D-94) | 2017-06-08 | 2017-08-23 | 2017-05-18 | 2019-04-10
Act | 2AI101CV01700-08040 | Not Started | Completed | EOF:Install Linar Membrane (incl. base & inside slope) for Bund Wall around Storage tank (52-D-93 & 52-D-94) | 2017-06-20 | 2017-09-04 | 2017-05-23 | 2019-04-26
Act | 2AI101CV01700-08045 | Not Started | In Progress | EOF:Gatch Filling & Compaction for Bund Wall around Storage tank (52-D-93 & 52-D-94) | 2017-07-15 | 2017-09-28 | 2017-06-15
Act | 2AI101CV01700-08050 | Not Started | Completed | EOF:Prepare Access ramp (with Compact fill & Gatch layer) for Bund Wall around Storage tank(52-D-93 & 52-D-94) | 2017-08-09 | 2017-10-18 | 2018-09-22 | 2018-10-29
Act | 2AI101CV01700-08055 | Not Started | In Progress | EOF:Rebar, Form work & Concreting for Stair cases for Bund Wall around Storage tank (52-D-93 & 52-D-94) | 2017-08-15 | 2017-10-28 | 2017-05-19
Act | 2AI101CV01700-08060 | Not Started | In Progress | EOF:Asphalt Lining for Inside slope for Bund Wall (52-D-93 & 52-D-94) | 2017-08-30 | 2017-10-28 | 2018-03-26
Act | 2AI101CV01700-08005 | Not Started | In Progress | LFHO Storage Tank (52-D-93) & (52-D-94): Construct Bund Wall | 2016-08-09 | 2017-10-28 | 2016-09-08
6 |  |  |  | Lot-1-J : LFHO Storage Tank (52-D-95 & 52-D-96) : Construct Bund Wall
Act | 2AI101CV02100 | Not Started | In Progress | EOF:Lot-1-J : LFHO Storage Tank (52-D-95 & 52-D-96) : Construct Bund Wall | 2016-08-21 | 2017-12-19 | 2016-09-08
7 |  |  |  | LFHO Storage Tank (52-D-95) & (52-D-96) : Construct Bund Wall
Act | 2AI101CV02100-08005 | Not Started | In Progress | LFHO Storage Tank (52-D-95) & (52-D-96) : Construct Bund Wall | 2016-08-21 | 2017-12-19 | 2016-09-08
Act | 2AI101CV02100-08015 | Not Started | Completed | EOF: Survey Marking, Excavation & Disposal of unsutiable Material for Bund Wall around Storage tank 52-D-96 & 52-D-95 | 2016-08-21 | 2017-01-08 | 2016-09-08 | 2019-04-10
Act | 2AI101CV02100-08020 | Not Started | Completed | EOF: Prepare Subgrade lvl for Bund Wall around Storage tank 52-D-96 & 52-D-95 | 2016-09-06 | 2017-01-24 | 2016-10-06 | 2019-02-06
Act | 2AI101CV02100-08025 | Not Started | Completed | EOF:Slope Preparation for Bund Wall around Storage tank 52-D-96 & 52-D-95 | 2016-09-24 | 2017-02-11 | 2016-10-06 | 2019-04-10
Act | 2AI101CV02100-08030 | Not Started | Completed | EOF:Install/Cast Catch basin (inside) & Valve pit (outside) for Bund Wall around Storage tank 52-D-96 & 52-D-95 | 2016-10-01 | 2017-04-01 | 2016-10-15 | 2018-12-19
Act | 2AI101CV02100-08035 | Not Started | Completed | EOF:Lay Drain Pipe (CB to Valve pit) for Bund Wall around Storage tank 52-D-96 & 52-D-95 | 2017-01-15 | 2017-04-12 | 2017-08-25 | 2018-10-10
Act | 2AI101CV02100-08040 | Not Started | In Progress | EOF:Sand layer (Inside) upto Linear Menbrane Lvl for Bund Wall around Storage tank 52-D-96 & 52-D-95 | 2017-07-13 | 2017-09-27 | 2017-05-29
Act | 2AI101CV02100-08045 | Not Started | In Progress | EOF:Install Linar Membrane (incl. base & inside slope) for Bund Wall around Storage tank 52-D-96 & 52-D-95 | 2017-07-29 | 2017-10-12 | 2018-02-03
Act | 2AI101CV02100-08050 | Not Started | In Progress | EOF:Gatch Filling & Compaction for Bund Wall around Storage tank 52-D-96 & 52-D-95 | 2017-08-22 | 2017-11-06 | 2018-02-12
Act | 2AI101CV02100-08055 | Not Started | Completed | EOF:Prepare Access ramp (with Compact fill & Gatch layer) for Bund Wall around Storage tank 52-D-96 & 52-D-95 | 2017-09-17 | 2017-11-26 | 2018-11-05 | 2019-01-20
Act | 2AI101CV02100-08060 | Not Started | In Progress | EOF:Rebar, Form work & Concreting for Stair cases for Bund Wall around Storage tank 52-D-96 & 52-D-95 | 2017-09-23 | 2017-12-05 | 2017-06-15
Act | 2AI101CV02100-08065 | Not Started | In Progress | EOF:Asphalt Lining for Inside slope for Bund Wall 52-D-96 & 52-D-95 | 2017-10-22 | 2017-12-19 | 2018-03-24
5 |  |  |  | SHELTER ERECTION
6 |  |  |  | EOF: Pump Shelter
Act | 2AI101CV22100 | Not Started | Completed | EOF: Pump Shelter | 2016-12-28 | 2017-02-28 | 2017-11-25 | 2018-10-10
7 |  |  |  | EOF: 621-G-302 A Trim Pump Shelter
Act | 2AI101CV22100-08001 | Not Started | Completed | EOF:Installation of Str. Steel for 621-G-302 A Trim Pump Shelter | 2016-12-28 | 2017-01-18 | 2017-11-27 | 2018-04-09
Act | 2AI101CV22100-08006 | Not Started | Completed | EOF:Alignment & Bolting/Torqueing for 621-G-302 A Trim Pump Shelter | 2017-01-18 | 2017-02-08 | 2017-12-11 | 2018-04-12
Act | 2AI101CV22100-08010 | Not Started | Completed | EOF:Grouting of 621-G-302 A Trim Pump Shelter | 2017-02-08 | 2017-02-22 | 2018-10-08 | 2018-10-10
Act | 2AI101CV22100-08000 | Not Started | Completed | EOF: 621-G-302 A Trim Pump Shelter | 2016-12-28 | 2017-02-22 | 2017-11-27 | 2018-10-10
7 |  |  |  | EOF: 621-G-302 B Trim Pump Shelter
Act | 2AI101CV22100-08015 | Not Started | Completed | EOF:Installation of Str. Steel for 621-G-302 B Trim Pump Shelter | 2017-01-03 | 2017-01-24 | 2017-11-25 | 2018-04-26
Act | 2AI101CV22100-08020 | Not Started | Completed | EOF:Alignment & Bolting/Torqueing for 621-G-302 B Trim Pump Shelter | 2017-01-24 | 2017-02-14 | 2017-12-11 | 2018-06-30
Act | 2AI101CV22100-08025 | Not Started | Completed | EOF:Grouting of 621-G-302 B Trim Pump Shelter | 2017-02-14 | 2017-02-28 | 2018-10-08 | 2018-10-10
Act | 2AI101CV22100-08005 | Not Started | Completed | EOF: 621-G-302 B Trim Pump Shelter | 2017-01-03 | 2017-02-28 | 2017-11-25 | 2018-10-10
5 |  |  |  | STRUCTURAL STEEL
6 |  |  |  | EOF: Foam Pump House Building structural works
Act | 2AI101CV01200 | Not Started | In Progress | EOF: Foam Pump House Building structural works | 2016-11-14 | 2017-02-18 | 2017-11-04
7 |  |  |  | EOF: 621-G-302 A/B Foam Pump House Building structural works
Act | 2AI101CV01200-08001 | Not Started | Completed | EOF:Installation of Str. Steel for 621-G-302 A/B Foam Pump House Building | 2016-11-14 | 2016-12-31 | 2017-11-04 | 2018-05-25
Act | 2AI101CV01200-08006 | Not Started | Completed | EOF:Alignment & Bolting/Torqueing for621-G-302 A/B Foam Pump House Building | 2016-11-19 | 2017-01-02 | 2017-11-10 | 2018-07-03
Act | 2AI101CV01200-08010 | Not Started | Completed | EOF:Grouting of 621-G-302 A/B Foam Pump House Building | 2017-01-02 | 2017-01-19 | 2018-08-06 | 2018-08-08
Act | 2AI101CV01200-08000 | Not Started | Completed | EOF: 621-G-302 A/B Foam Pump House Building structural works | 2016-11-14 | 2017-01-19 | 2017-11-04 | 2018-08-08
7 |  |  |  | EOF: 621-G-302 C/D Foam Pump House Building structural works
Act | 2AI101CV01200-08015 | Not Started | In Progress | EOF:Installation of Str. Steel for 621-G-302 C/D Foam Pump House Building | 2016-12-13 | 2017-01-29 | 2017-11-05
Act | 2AI101CV01200-08020 | Not Started | In Progress | EOF:Alignment & Bolting/Torqueing for 621-G-302 C/D Foam Pump House Building | 2016-12-18 | 2017-01-31 | 2017-11-10
Act | 2AI101CV01200-08025 | Not Started | Completed | EOF:Grouting of 621-G-302 C/D Foam Pump House Building | 2017-01-31 | 2017-02-18 | 2018-10-04 | 2018-10-05
Act | 2AI101CV01200-08005 | Not Started | In Progress | EOF: 621-G-302 C/D Foam Pump House Building structural works | 2016-12-13 | 2017-02-18 | 2017-11-05
5 |  |  |  | MISCELLANEOUS CIVIL WORKS
6 |  |  |  | EOF: Constrution of Sump
Act | 2AI101CV11000 | Not Started | Completed | EOF: Construction of Sump | 2016-11-01 | 2017-01-24 | 2016-06-22 | 2016-11-09
7 |  |  |  | EOF: Oily Water Collection Vessel Sump (52-SU-301) Construction
Act | 2AI101CV11000-08001 | Not Started | Completed | EOF:Excavation & Subgrade for Sump | 2016-11-01 | 2016-11-09 | 2016-06-22 | 2016-07-16
Act | 2AI101CV11000-08005 | Not Started | Completed | EOF:Blinding/PCC for Sump Fnd | 2016-11-09 | 2016-11-13 | 2016-07-21 | 2016-07-21
Act | 2AI101CV11000-08010 | Not Started | Completed | EOF:Rebar, Formwork for base of Sump | 2016-11-13 | 2016-11-21 | 2016-07-23 | 2016-07-27
Act | 2AI101CV11000-08015 | Not Started | Completed | EOF:Rebar, Formwork for wall of Sump | 2016-11-26 | 2016-12-12 | 2016-08-09 | 2016-10-17
Act | 2AI101CV11000-08020 | Not Started | Completed | EOF:Concrete Protection for Sump | 2016-12-21 | 2016-12-28 | 2016-09-08 | 2016-11-03
Act | 2AI101CV11000-08025 | Not Started | Completed | EOF:Cover slab for Sump | 2016-12-28 | 2017-01-05 | 2016-11-03 | 2016-11-03
Act | 2AI101CV11000-08030 | Not Started | Completed | EOF:Backfilling & Compaction Around Sump | 2017-01-05 | 2017-01-24 | 2016-09-10 | 2016-11-09
Act | 2AI101CV11000-08011 | Not Started | Completed | EOF:Concrete Pouring for base of Sump | 2016-11-21 | 2016-11-22 | 2016-07-28 | 2016-09-30
Act | 2AI101CV11000-08016 | Not Started | Completed | EOF:Concrete Pouring for Wall of Sump | 2016-12-10 | 2016-12-13 | 2016-08-27 | 2016-10-18
Act | 2AI101CV11000-08000 | Not Started | Completed | EOF: Oily Water Collection Vessel Sump (52-SU-301) Construction | 2016-11-01 | 2017-01-24 | 2016-06-22 | 2016-11-09
6 |  |  |  | EOF: UG Trench and Other Civl Worrks
Act | 2AI101CV18400 | Not Started | In Progress | EOF: UG Trench and Other Civl Worrks | 2016-03-18 | 2017-12-30 | 2016-02-16
7 |  |  |  | EOF: Pipe Trench
Act | 2AI101CV18400-08000 | Not Started | In Progress | EOF: Pipe Trench | 2016-11-14 | 2017-12-24 | 2016-11-17
Act | 2AI101CV18400-08025 | Not Started | Completed | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material | 2016-11-14 | 2017-08-29 | 2016-11-17 | 2018-12-05
Act | 2AI101CV18400-08040 | Not Started | Completed | EOF: Bedding (incl. clean sand layer) | 2016-11-17 | 2017-09-02 | 2016-12-06 | 2018-12-05
Act | 2AI101CV18400-08300 | Not Started | Not Started | EOF:Install Route/saftey Markers | 2017-06-13 | 2017-12-24
Act | 2AI101CV18400-08285 | Not Started | In Progress | EOF: Backfilling and Compaction | 2017-03-23 | 2017-12-18 | 2017-01-31
8 |  |  |  | EOF:Pipe Trench - Main Filling/Loading Pipe Line (Incl. Fire Water Main line) to Storage Tank
Act | 2AI101CV18400-08001 | Not Started | Completed | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material | 2016-12-31 | 2017-03-01 | 2017-01-15 | 2018-11-07
Act | 2AI101CV18400-08006 | Not Started | Completed | EOF: Bedding (incl. clean sand layer) | 2017-01-10 | 2017-03-04 | 2017-01-28 | 2018-11-09
Act | 2AI101CV18400-08013 | Not Started | Not Started | EOF:Install Route/saftey Markers | 2017-12-07 | 2017-12-19
Act | 2AI101CV18400-08007 | Not Started | In Progress | EOF: Backfilling and Compaction | 2017-10-30 | 2017-12-13 | 2017-07-13
8 |  |  |  | EOF:Pipe Trench - Loading Line from Storage Tank till Trim Pump
Act | 2AI101CV18400-08015 | Not Started | Completed | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material | 2016-12-13 | 2017-01-29 | 2017-01-10 | 2018-11-07
Act | 2AI101CV18400-08020 | Not Started | Completed | EOF: Bedding (incl. clean sand layer) | 2016-12-25 | 2017-02-04 | 2017-01-15 | 2018-12-05
Act | 2AI101CV18400-08026 | Not Started | Not Started | EOF:Install Route/saftey Markers | 2017-12-07 | 2017-12-19
Act | 2AI101CV18400-08021 | Not Started | Completed | EOF: Backfilling and Compaction | 2017-10-29 | 2017-12-07 | 2017-04-03 | 2019-02-06
8 |  |  |  | EOF:Pipe Trench - 12" Pipe Line from Storage Tank till Oily Water Vessel
Act | 2AI101CV18400-08030 | Not Started | Completed | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material | 2016-11-30 | 2017-01-18 | 2017-07-16 | 2018-11-07 | [66 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [8 empty] | 0 | [9 empty] | 0 | [9 empty] | 8 | [8 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [8 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [8 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  |  |  | 0
Act | 2AI101CV18400-08035 | Not Started | Completed | EOF: Bedding (incl. clean sand layer) | 2016-12-18 | 2017-01-24 | 2017-07-26 | 2018-11-07 | [66 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [8 empty] | 0 | [9 empty] | 0 | [9 empty] | 8 | [8 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [8 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [8 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  |  |  | 0
Act | 2AI101CV18400-08041 | Not Started | Not Started | EOF:Install Route/saftey Markers | 2017-07-06 | 2017-07-18
Act | 2AI101CV18400-08036 | Not Started | Completed | EOF: Backfilling and Compaction | 2017-06-01 | 2017-07-06 | 2018-03-05 | 2019-03-06
8 |  |  |  | EOF:Pipe Trench - Filling/Loading Branch Line to Storage Tank 52-D-94
Act | 2AI101CV18400-08275 | Not Started | Completed | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material | 2017-06-08 | 2017-07-02 | 2017-07-18 | 2017-12-06
Act | 2AI101CV18400-08280 | Not Started | Completed | EOF: Bedding (incl. clean sand layer) | 2017-06-11 | 2017-07-04 | 2017-07-27 | 2017-12-07
Act | 2AI101CV18400-08286 | Not Started | Not Started | EOF:Install Route/saftey Markers | 2017-11-14 | 2017-11-20
Act | 2AI101CV18400-08281 | Not Started | Completed | EOF: Backfilling and Compaction | 2017-10-29 | 2017-11-14 | 2018-04-02 | 2019-02-06
8 |  |  |  | EOF:Pipe Trench - Filling/Loading Branch Line to Storage Tank 52-D-93
Act | 2AI101CV18400-08290 | Not Started | Completed | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material | 2017-06-08 | 2017-07-04 | 2017-07-18 | 2017-11-28
Act | 2AI101CV18400-08295 | Not Started | Completed | EOF: Bedding (incl. clean sand layer) | 2017-06-13 | 2017-07-06 | 2017-07-27 | 2017-11-30
Act | 2AI101CV18400-08301 | Not Started | Not Started | EOF:Install Route/saftey Markers | 2017-11-22 | 2017-11-28
Act | 2AI101CV18400-08296 | Not Started | Completed | EOF: Backfilling and Compaction | 2017-10-30 | 2017-11-22 | 2018-04-02 | 2019-04-10
8 |  |  |  | EOF:Pipe Trench - Filling/Loading Branch Line to Storage Tank 52-D-95
Act | 2AI101CV18400-08305 | Not Started | Completed | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material | 2017-07-13 | 2017-08-12 | 2017-08-26 | 2018-02-07
Act | 2AI101CV18400-08310 | Not Started | Completed | EOF: Bedding (incl. clean sand layer) | 2017-07-22 | 2017-08-14 | 2017-09-26 | 2018-02-07
Act | 2AI101CV18400-08316 | Not Started | Not Started | EOF:Install Route/saftey Markers | 2017-11-21 | 2017-11-27
Act | 2AI101CV18400-08311 | Not Started | Completed | EOF: Backfilling and Compaction | 2017-10-29 | 2017-11-21 | 2018-04-02 | 2019-01-26
8 |  |  |  | EOF:Pipe Trench - Filling/Loading Branch Line to Storage Tank 52-D-96
Act | 2AI101CV18400-08320 | Not Started | Completed | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material | 2017-07-05 | 2017-07-29 | 2017-10-02 | 2018-02-07
Act | 2AI101CV18400-08325 | Not Started | Completed | EOF: Bedding (incl. clean sand layer) | 2017-07-11 | 2017-08-01 | 2017-10-02 | 2018-02-07
Act | 2AI101CV18400-08331 | Not Started | Not Started | EOF:Install Route/saftey Markers | 2017-11-21 | 2017-11-27
Act | 2AI101CV18400-08326 | Not Started | Completed | EOF: Backfilling and Compaction | 2017-10-29 | 2017-11-21 | 2018-04-02 | 2019-02-06
8 |  |  |  | EOF: Pipe Trench Fire Water Line to Tank 52-5-94
Act | 2AI101CV18400-08425 | Not Started | Completed | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material | 2017-06-08 | 2017-07-08 | 2017-05-23 | 2018-04-06
Act | 2AI101CV18400-08430 | Not Started | Completed | EOF: Bedding (incl. clean sand layer) | 2017-07-08 | 2017-07-31 | 2017-06-01 | 2018-04-08
Act | 2AI101CV18400-08436 | Not Started | Not Started | EOF:Install Route/saftey Markers | 2017-11-30 | 2017-12-06
Act | 2AI101CV18400-08431 | Not Started | Completed | EOF: Backfilling and Compaction | 2017-11-07 | 2017-11-30 | 2017-10-02 | 2018-07-04
8 |  |  |  | EOF: Pipe Trench Fire Water Line to Tank 52-5-93
Act | 2AI101CV18400-08440 | Not Started | Completed | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material | 2017-07-08 | 2017-08-06 | 2017-05-11 | 2018-04-07
Act | 2AI101CV18400-08445 | Not Started | Completed | EOF: Bedding (incl. clean sand layer) | 2017-07-15 | 2017-08-09 | 2017-06-01 | 2018-07-04
Act | 2AI101CV18400-08450 | Not Started | Completed | EOF: Backfilling and Compaction | 2017-11-13 | 2017-12-06 | 2017-10-02 | 2018-07-04
Act | 2AI101CV18400-08451 | Not Started | Not Started | EOF:Install Route/saftey Markers | 2017-12-06 | 2017-12-12
8 |  |  |  | EOF: Pipe Trench Fire Water Line to Tank 52-5-95
Act | 2AI101CV18400-08455 | Not Started | Completed | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material | 2017-08-06 | 2017-08-29 | 2017-07-14 | 2018-12-05
Act | 2AI101CV18400-08460 | Not Started | Completed | EOF: Bedding (incl. clean sand layer) | 2017-08-12 | 2017-09-02 | 2017-07-18 | 2018-12-05
Act | 2AI101CV18400-08465 | Not Started | Completed | EOF: Backfilling and Compaction | 2017-11-25 | 2017-12-18 | 2018-01-01 | 2019-04-10
Act | 2AI101CV18400-08466 | Not Started | Not Started | EOF:Install Route/saftey Markers | 2017-12-18 | 2017-12-24
8 |  |  |  | EOF: Pipe Trench Fire Water Line to Tank 52-5-96
Act | 2AI101CV18400-08470 | Not Started | Completed | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material | 2017-07-13 | 2017-08-06 | 2017-07-14 | 2018-12-05
Act | 2AI101CV18400-08475 | Not Started | Completed | EOF: Bedding (incl. clean sand layer) | 2017-07-19 | 2017-08-09 | 2017-07-18 | 2018-12-05
Act | 2AI101CV18400-08480 | Not Started | Completed | EOF: Backfilling and Compaction | 2017-11-19 | 2017-12-12 | 2017-12-23 | 2019-04-10
Act | 2AI101CV18400-08481 | Not Started | Not Started | EOF:Install Route/saftey Markers | 2017-12-12 | 2017-12-18
8 |  |  |  | EOF: Pipe Trench Fire Water Ring Line out side Bund Wall
Act | 2AI101CV18400-08485 | Not Started | Completed | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material | 2016-12-07 | 2017-02-01 | 2017-02-06 | 2018-12-05
Act | 2AI101CV18400-08490 | Not Started | Completed | EOF: Bedding (incl. clean sand layer) | 2017-02-01 | 2017-03-26 | 2017-01-28 | 2018-12-05
Act | 2AI101CV18400-08495 | Not Started | Completed | EOF: Backfilling and Compaction | 2017-11-07 | 2017-11-30 | 2017-06-24 | 2019-04-10
Act | 2AI101CV18400-08496 | Not Started | Not Started | EOF:Install Route/saftey Markers | 2017-11-30 | 2017-12-06
8 |  |  |  | EOF: Effluent water(WK) Line
Act | 2AI101CV18400-08500 | Not Started | Completed | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material | 2017-01-18 | 2017-06-13 | 2017-12-04 | 2018-12-05
Act | 2AI101CV18400-08505 | Not Started | Completed | EOF: Bedding (incl. clean sand layer) | 2017-01-22 | 2017-06-29 | 2017-12-04 | 2018-12-05
Act | 2AI101CV18400-08510 | Not Started | In Progress | EOF: Backfilling and Compaction | 2017-03-23 | 2017-07-12 | 2018-02-05
Act | 2AI101CV18400-08511 | Not Started | Not Started | EOF:Install Route/saftey Markers | 2017-06-13 | 2017-07-24
8 |  |  |  | EOF:Pipe Trench - Oily Water line
8 |  |  |  | EOF:Pipe Trench - Foam line
Act | 2AI101CV18400-08045 | Not Started | Completed | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material | 2016-11-14 | 2017-01-23 | 2017-05-23 | 2018-11-24
Act | 2AI101CV18400-08050 | Not Started | Completed | EOF: Bedding (incl. clean sand layer) | 2016-11-17 | 2017-01-26 | 2017-06-01 | 2018-11-25
Act | 2AI101CV18400-08055 | Not Started | In Progress | EOF: Backfilling and Compaction | 2017-09-05 | 2017-10-10 | 2017-09-23
Act | 2AI101CV18400-08056 | Not Started | Not Started | EOF:Install Route/saftey Markers | 2017-10-10 | 2017-10-16
8 |  |  |  | EOF:Pipe Trench - Other Lines
Act | 2AI101CV18400-08060 | Not Started | Completed | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material | 2016-11-20 | 2017-02-15 | 2016-11-17 | 2018-05-03 | [66 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [8 empty] | 0 | [9 empty] | 31 | [9 empty] | 12 | [8 empty] | 29 | [9 empty] | 54 | [9 empty] | 54 | [8 empty] | 52 | [9 empty] | 33 | [9 empty] | 0 | [9 empty] | 0 | [8 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  |  |  | 0
Act | 2AI101CV18400-08065 | Not Started | Completed | EOF: Bedding (incl. clean sand layer) | 2016-11-29 | 2017-02-19 | 2016-12-06 | 2018-05-03 | [66 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [8 empty] | 0 | [9 empty] | 31 | [9 empty] | 28 | [8 empty] | 34 | [9 empty] | 59 | [9 empty] | 57 | [8 empty] | 55 | [9 empty] | 30 | [9 empty] | 0 | [9 empty] | 0 | [8 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  |  |  | 0
Act | 2AI101CV18400-08070 | Not Started | In Progress | EOF: Backfilling and Compaction | 2017-09-09 | 2017-12-02 | 2017-01-31
Act | 2AI101CV18400-08071 | Not Started | Not Started | EOF:Install Route/saftey Markers | 2017-12-02 | 2017-12-07
7 |  |  |  | EOF: EIT Cable Trench
Act | 2AI101CV18400-08005 | Not Started | In Progress | EOF: EIT Cable Trench | 2016-03-18 | 2017-12-30 | 2016-02-16
8 |  |  |  | EOF: Electrical Cable Trench to re-route existing UG Cable
Act | 2AI101CV18400-08075 | Not Started | Completed | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material | 2016-03-18 | 2016-04-04 | 2016-02-16 | 2016-03-23
Act | 2AI101CV18400-08080 | Not Started | Completed | EOF:Sand bedding | 2016-03-28 | 2016-04-06 | 2016-03-18 | 2016-03-26
Act | 2AI101CV18400-08085 | Not Started | Completed | EOF:Install Cable Tile Laying & warning Tapes | 2016-04-19 | 2016-04-28 | 2016-03-27 | 2016-07-04
Act | 2AI101CV18400-08090 | Not Started | Completed | EOF:Backfilling & Compaction | 2016-04-24 | 2016-05-04 | 2016-03-29 | 2016-07-05
Act | 2AI101CV18400-08095 | Not Started | Completed | EOF:Install Route/saftey Markers | 2016-05-04 | 2016-05-10 | 2016-10-12 | 2016-10-13
Act | 2AI101CV18400-08081 | Not Started | Completed | EOF:Sand Padding | 2016-04-18 | 2016-04-26 | 2016-03-26 | 2016-03-26
8 |  |  |  | EOF: CP Cable Trench for Tank 52-D-93
Act | 2AI101CV18400-08175 | Not Started | Completed | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material | 2016-12-25 | 2017-01-05 | 2017-11-06 | 2017-11-08
Act | 2AI101CV18400-08180 | Not Started | Completed | EOF:Sand bedding | 2016-12-31 | 2017-01-09 | 2017-11-06 | 2017-11-08
Act | 2AI101CV18400-08185 | Not Started | Completed | EOF:Install Cable Tile Laying & warning Tapes | 2017-07-06 | 2017-07-13 | 2017-11-06 | 2017-11-08
Act | 2AI101CV18400-08190 | Not Started | Completed | EOF:Backfilling & Compaction | 2017-07-13 | 2017-07-20 | 2017-11-06 | 2017-11-08
Act | 2AI101CV18400-08195 | Not Started | Completed | EOF:Install Route/saftey Markers | 2017-07-20 | 2017-07-25 | 2017-11-06 | 2017-11-08
Act | 2AI101CV18400-08181 | Not Started | Completed | EOF:Sand Padding | 2017-06-29 | 2017-07-09 | 2017-11-06 | 2017-11-08
8 |  |  |  | EOF: CP Cable Trench for Tank 52-D-94
Act | 2AI101CV18400-08200 | Not Started | Completed | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material | 2016-12-25 | 2017-01-05 | 2017-11-06 | 2017-11-08
Act | 2AI101CV18400-08205 | Not Started | Completed | EOF:Sand bedding | 2016-12-29 | 2017-01-09 | 2017-11-06 | 2017-11-08
Act | 2AI101CV18400-08210 | Not Started | Completed | EOF:Install Cable Tile Laying & warning Tapes | 2017-06-24 | 2017-07-01 | 2017-11-06 | 2017-11-08
Act | 2AI101CV18400-08215 | Not Started | Completed | EOF:Backfilling & Compaction | 2017-07-01 | 2017-07-08 | 2017-11-06 | 2017-11-08
Act | 2AI101CV18400-08220 | Not Started | Completed | EOF:Install Route/saftey Markers | 2017-07-08 | 2017-07-12 | 2017-11-06 | 2017-11-08
Act | 2AI101CV18400-08206 | Not Started | Completed | EOF:Sand Padding | 2017-06-19 | 2017-06-29 | 2017-11-06 | 2017-11-08
8 |  |  |  | EOF: CP Cable Trench for Tank 52-D-95
Act | 2AI101CV18400-08225 | Not Started | Completed | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material | 2016-12-25 | 2017-01-04 | 2017-11-06 | 2017-11-08
Act | 2AI101CV18400-08230 | Not Started | Completed | EOF:Sand bedding | 2016-12-28 | 2017-01-08 | 2017-11-06 | 2017-11-08
Act | 2AI101CV18400-08235 | Not Started | Completed | EOF:Install Cable Tile Laying & warning Tapes | 2017-06-29 | 2017-07-06 | 2017-11-06 | 2017-11-08
Act | 2AI101CV18400-08240 | Not Started | Completed | EOF:Backfilling & Compaction | 2017-07-06 | 2017-07-13 | 2017-11-06 | 2017-11-08
Act | 2AI101CV18400-08245 | Not Started | Completed | EOF:Install Route/saftey Markers | 2017-07-13 | 2017-07-18 | 2017-11-06 | 2017-11-08
Act | 2AI101CV18400-08231 | Not Started | Completed | EOF:Sand Padding | 2017-06-19 | 2017-06-29 | 2017-11-06 | 2017-11-08
8 |  |  |  | EOF: CP Cable Trench for Tank 52-D-96
Act | 2AI101CV18400-08250 | Not Started | Completed | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material | 2016-12-25 | 2017-01-04 | 2017-11-06 | 2017-11-08
Act | 2AI101CV18400-08255 | Not Started | Completed | EOF:Sand bedding | 2016-12-28 | 2017-01-08 | 2017-11-06 | 2017-11-08
Act | 2AI101CV18400-08260 | Not Started | Completed | EOF:Install Cable Tile Laying & warning Tapes | 2017-06-28 | 2017-07-05 | 2017-11-06 | 2017-11-08
Act | 2AI101CV18400-08265 | Not Started | Completed | EOF:Backfilling & Compaction | 2017-07-05 | 2017-07-12 | 2017-11-06 | 2017-11-08
Act | 2AI101CV18400-08270 | Not Started | Completed | EOF:Install Route/saftey Markers | 2017-07-12 | 2017-07-17 | 2017-11-06 | 2017-11-08
Act | 2AI101CV18400-08256 | Not Started | Completed | EOF:Sand Padding | 2017-06-19 | 2017-06-29 | 2017-11-06 | 2017-11-08
8 |  |  |  | EOF: Telecom Cable Trench (Inside STF Area)
Act | 2AI101CV18400-08100 | Not Started | Completed | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material | 2017-02-27 | 2017-07-05 | 2017-05-05 | 2018-06-14
Act | 2AI101CV18400-08105 | Not Started | Completed | EOF:Sand bedding | 2017-04-09 | 2017-07-17 | 2017-05-06 | 2018-07-01
Act | 2AI101CV18400-08110 | Not Started | Completed | EOF:Install Cable Tile Laying & warning Tapes | 2017-09-07 | 2017-12-17 | 2017-07-03 | 2018-07-01
Act | 2AI101CV18400-08115 | Not Started | Completed | EOF:Backfilling & Compaction | 2017-09-11 | 2017-12-19 | 2017-07-03 | 2018-07-01
Act | 2AI101CV18400-08120 | Not Started | Completed | EOF:Install Route/saftey Markers | 2017-12-06 | 2017-12-30 | 2018-07-01 | 2018-07-01
Act | 2AI101CV18400-08106 | Not Started | Completed | EOF:Sand Padding | 2017-09-06 | 2017-12-14 | 2017-07-03 | 2018-07-01
8 |  |  |  | EOF: Instrumentation Cable Trench (Inside STF Area)
Act | 2AI101CV18400-08125 | Not Started | In Progress | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material | 2017-02-27 | 2017-06-26 | 2017-03-04
Act | 2AI101CV18400-08130 | Not Started | In Progress | EOF:Sand bedding | 2017-03-22 | 2017-07-08 | 2017-03-05
Act | 2AI101CV18400-08135 | Not Started | In Progress | EOF:Install Cable Tile Laying & warning Tapes | 2017-06-19 | 2017-10-05 | 2017-11-07
Act | 2AI101CV18400-08140 | Not Started | In Progress | EOF:Backfilling & Compaction | 2017-08-01 | 2017-10-16 | 2017-11-21
Act | 2AI101CV18400-08145 | Not Started | Not Started | EOF:Install Route/saftey Markers | 2017-10-14 | 2017-10-31
Act | 2AI101CV18400-08131 | Not Started | In Progress | EOF:Sand Padding | 2017-06-18 | 2017-10-03 | 2017-05-21
8 |  |  |  | EOF:Electrical Cable Trench (STF Inside Area)
Act | 2AI101CV18400-08150 | Not Started | In Progress | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material | 2017-02-26 | 2017-07-22 | 2017-01-11
Act | 2AI101CV18400-08155 | Not Started | In Progress | EOF:Sand bedding | 2017-03-14 | 2017-09-28 | 2017-01-28
Act | 2AI101CV18400-08160 | Not Started | In Progress | EOF:Install Cable Tile Laying & warning Tapes | 2017-07-01 | 2017-10-16 | 2017-07-29
Act | 2AI101CV18400-08165 | Not Started | In Progress | EOF:Backfilling & Compaction | 2017-07-12 | 2017-10-26 | 2017-07-31
Act | 2AI101CV18400-08170 | Not Started | Not Started | EOF:Install Route/saftey Markers | 2017-10-26 | 2017-11-19
Act | 2AI101CV18400-08156 | Not Started | In Progress | EOF:Sand Padding | 2017-03-18 | 2017-10-02 | 2017-05-07
7 |  |  |  | EOF: Foundation for Relocation of existing RMU
Act | 2AI101CV18400-08345 | Not Started | Completed | EOF:Survey Marking, Excavation & Subgrade | 2016-03-18 | 2016-03-19 | 2016-03-24 | 2016-03-24
Act | 2AI101CV18400-08346 | Not Started | Completed | EOF:Blinding/PCC for Foundation | 2016-03-19 | 2016-03-21 | 2016-03-26 | 2016-03-26
Act | 2AI101CV18400-08350 | Not Started | Completed | EOF:Rebar & Formwork - for Footing | 2016-03-22 | 2016-03-26 | 2016-03-27 | 2016-03-27
Act | 2AI101CV18400-08360 | Not Started | Completed | EOF:Concrete Potection for Foundation | 2016-03-30 | 2016-04-02 | 2016-03-29 | 2016-04-01
Act | 2AI101CV18400-08365 | Not Started | Completed | EOF:Backfilling & Compaction for Foundation | 2016-04-03 | 2016-04-04 | 2016-07-03 | 2016-07-03
Act | 2AI101CV18400-08355 | Not Started | Completed | EOF:Concrete Pouring - for Footing | 2016-03-26 | 2016-03-27 | 2016-03-27 | 2016-03-27
Act | 2AI101CV18400-08010 | Not Started | Completed | EOF: Foundation for Relocation of existing RMU | 2016-03-18 | 2016-04-04 | 2016-03-24 | 2016-07-03
5 |  |  |  | ROADS & PAVING
6 |  |  |  | EOF: Roads, Crossing & Paving Works
Act | 2AI101CV01100 | Not Started | In Progress | EOF: Roads, Crossing & Paving Works | 2016-08-10 | 2017-12-31 | 2016-08-30
7 |  |  |  | EOF: Gutch Road Work
Act | 2AI101CV01100-08021 | Not Started | Not Started | EOF:Excavation | 2016-08-30 | 2016-10-10
Act | 2AI101CV01100-08026 | Not Started | Not Started | EOF:Grading & leveling | 2016-10-10 | 2016-11-12
Act | 2AI101CV01100-08030 | Not Started | Not Started | EOF:Gutch Filling | 2016-11-12 | 2016-12-17
Act | 2AI101CV01100-08035 | Not Started | Not Started | EOF:Compaction | 2016-12-17 | 2017-01-12
Act | 2AI101CV01100-08000 | Not Started | Not Started | EOF: Gutch Road Work | 2016-08-30 | 2017-01-12
7 |  |  |  | EOF: Asphalt Road Work
Act | 2AI101CV01100-08001 | Not Started | In Progress | EOF:Grading & leveling | 2016-11-15 | 2017-02-11 | 2018-05-03
Act | 2AI101CV01100-08006 | Not Started | In Progress | EOF:Preparation of sub grade | 2016-11-27 | 2017-04-04 | 2018-05-04
Act | 2AI101CV01100-08011 | Not Started | In Progress | EOF:Asphalt Work | 2017-07-15 | 2017-11-20 | 2018-05-05
Act | 2AI101CV01100-08016 | Not Started | Not Started | EOF:Bollards & Crash barrier installation | 2017-11-20 | 2017-12-31
Act | 2AI101CV01100-08005 | Not Started | In Progress | EOF: Asphalt Road Work | 2016-11-15 | 2017-12-31 | 2018-05-03
7 |  |  |  | EOF: Reinforced Concrete Paving
Act | 2AI101CV01100-08040 | Not Started | In Progress | EOF:Excavation | 2016-09-29 | 2017-02-11 | 2019-03-30
Act | 2AI101CV01100-08045 | Not Started | In Progress | EOF:Grading & leveling | 2016-10-08 | 2017-02-19 | 2019-03-31
Act | 2AI101CV01100-08050 | Not Started | In Progress | EOF:Preparation of sub grade | 2016-10-16 | 2017-02-27 | 2019-04-02
Act | 2AI101CV01100-08055 | Not Started | Not Started | EOF:Concrete Work | 2017-02-28 | 2017-06-19
Act | 2AI101CV01100-08010 | Not Started | In Progress | EOF: Reinforced Concrete Paving | 2016-09-29 | 2017-06-19 | 2019-03-30
7 |  |  |  | EOF: Asphalt Paving
Act | 2AI101CV01100-08060 | Not Started | Not Started | EOF:Excavation | 2016-11-08 | 2017-02-16
Act | 2AI101CV01100-08065 | Not Started | Not Started | EOF:Grading & leveling | 2016-12-06 | 2017-03-06
Act | 2AI101CV01100-08070 | Not Started | Not Started | EOF:Preparation of sub grade | 2016-12-31 | 2017-03-20
Act | 2AI101CV01100-08075 | Not Started | Not Started | EOF:Asphalt Work | 2017-09-11 | 2017-11-26
Act | 2AI101CV01100-08015 | Not Started | Not Started | EOF: Asphalt Paving | 2016-11-08 | 2017-11-26
7 |  |  |  | EOF: Road Crossing
Act | 2AI101CV01100-08140 | Not Started | Completed | EOF:Embankment for Road crossing | 2016-11-26 | 2017-01-17 | 2016-11-21 | 2016-12-28
Act | 2AI101CV01100-08090 | Not Started | Completed | EOF:Excavation & Subgrade for duct bank | 2016-08-18 | 2016-11-06 | 2016-10-01 | 2016-10-30
Act | 2AI101CV01100-08100 | Not Started | Completed | EOF:Blinding/PCC for duct bank | 2016-08-20 | 2016-11-12 | 2016-10-22 | 2016-11-14
Act | 2AI101CV01100-08110 | Not Started | Completed | EOF:Rebar, Formwork, embadents fixing and Concreting for duct bank | 2016-08-10 | 2016-11-17 | 2016-10-26 | 2016-11-21
Act | 2AI101CV01100-08120 | Not Started | Completed | EOF:Concrete Protection duct bank | 2016-08-22 | 2016-11-26 | 2016-11-06 | 2016-11-25
Act | 2AI101CV01100-08130 | Not Started | Completed | EOF:Backfilling duct bank | 2016-10-02 | 2016-12-01 | 2016-11-21 | 2016-12-28
Act | 2AI101CV01100-08020 | Not Started | Completed | EOF: Road Crossing and Concrete cable duct banks | 2016-08-10 | 2017-01-17 | 2016-10-01 | 2016-12-28
7 |  |  |  | EOF: Grade slab for Pump shelters/Mobile shelters
Act | 2AI101CV01100-08027 | Not Started | In Progress | EOF: Sub base & Base preparation | 2017-06-19 | 2017-07-01 | 2016-08-30
Act | 2AI101CV01100-08028 | Not Started | In Progress | EOF: Formwork | 2017-07-01 | 2017-07-30 | 2016-09-20
Act | 2AI101CV01100-08029 | Not Started | In Progress | EOF: Reinforcement | 2017-07-04 | 2017-08-02 | 2016-09-20
Act | 2AI101CV01100-08032 | Not Started | In Progress | EOF: Concrete Pouring | 2017-08-02 | 2017-08-10 | 2016-09-24
Act | 2AI101CV01100-08033 | Not Started | In Progress | EOF: Finishing | 2017-08-10 | 2017-09-11 | 2016-10-21
Act | 2AI101CV01100-08025 | Not Started | In Progress | EOF: Grade slab for Pump shelters/Mobile shelters | 2017-06-19 | 2017-09-11 | 2016-08-30
4 |  |  |  | MECHANICAL - STATIC
5 |  |  |  | STATIC EQUIPMENT
6 |  |  |  | EOF: Balance Tanks Erection
Act | 2AI101MS01900 | Not Started | Completed | EOF: Balance Tanks Erection | 2017-03-12 | 2017-08-27 | 2017-03-12 | 2017-08-09
7 |  |  |  | EOF: Overhead Water Tank (52-D-309 A) Erection
Act | 2AI101MS01900-08001 | Not Started | Completed | EOF:Foundation checks/Preparation for Equipment | 2017-03-12 | 2017-03-13 | 2017-03-12 | 2017-03-13
Act | 2AI101MS01900-08006 | Not Started | Completed | EOF:Installation of Structural Support | 2017-03-13 | 2017-03-18 | 2017-03-13 | 2017-03-18
Act | 2AI101MS01900-08011 | Not Started | Completed | EOF:Installation of Equipment | 2017-03-18 | 2017-03-25 | 2017-03-18 | 2017-03-25
Act | 2AI101MS01900-08016 | Not Started | Completed | EOF:Preliminary Allignment & Grouting of Equipment | 2017-03-25 | 2017-03-27 | 2017-03-25 | 2017-03-27
Act | 2AI101MS01900-08021 | Not Started | Completed | EOF:Final Allignment & Grouting of Equipment | 2017-03-27 | 2017-03-29 | 2017-03-27 | 2017-03-29
Act | 2AI101MS01900-08026 | Not Started | Completed | EOF:Install Platforms & ladders of Equipment | 2017-03-29 | 2017-04-03 | 2017-03-29 | 2017-04-03
Act | 2AI101MS01900-08031 | Not Started | Completed | EOF:Install internals of Equipment | 2017-04-03 | 2017-04-10 | 2017-04-03 | 2017-04-10
Act | 2AI101MS01900-08036 | Not Started | Completed | EOF:QC checks & clearance for Equipment | 2017-04-10 | 2017-04-12 | 2017-04-03 | 2017-04-10
Act | 2AI101MS01900-08000 | Not Started | Completed | EOF: OverheadWater Tank (52-D-309 A) Erection | 2017-03-12 | 2017-04-12 | 2017-03-12 | 2017-04-10
7 |  |  |  | EOF: Overhead Water Tank (52-D-309 B) Erection
Act | 2AI101MS01900-08041 | Not Started | Completed | EOF:Foundation checks/Preparation for Equipment | 2017-04-09 | 2017-04-10 | 2017-04-09 | 2017-04-10
Act | 2AI101MS01900-08046 | Not Started | Completed | EOF:Installation of Structural Support | 2017-04-10 | 2017-04-15 | 2017-04-10 | 2017-04-15
Act | 2AI101MS01900-08050 | Not Started | Completed | EOF:Installation of Equipment | 2017-04-15 | 2017-04-22 | 2017-04-15 | 2017-04-29
Act | 2AI101MS01900-08055 | Not Started | Completed | EOF:Preliminary Allignment & Grouting of Equipment | 2017-04-22 | 2017-04-24 | 2017-04-29 | 2017-04-29
Act | 2AI101MS01900-08060 | Not Started | Completed | EOF:Final Allignment & Grouting of Equipment | 2017-04-24 | 2017-04-26 | 2017-04-29 | 2017-04-29
Act | 2AI101MS01900-08065 | Not Started | Completed | EOF:Install Platforms & ladders of Equipment | 2017-04-26 | 2017-05-01 | 2017-04-29 | 2017-05-01
Act | 2AI101MS01900-08070 | Not Started | Completed | EOF:Install internals of Equipment | 2017-05-01 | 2017-05-08 | 2017-04-03 | 2017-04-10
Act | 2AI101MS01900-08075 | Not Started | Completed | EOF:QC checks & clearance for Equipment | 2017-05-08 | 2017-05-10 | 2017-04-03 | 2017-04-10
Act | 2AI101MS01900-08005 | Not Started | Completed | EOF: OverheadWater Tank (52-D-309 B) Erection | 2017-04-09 | 2017-05-10 | 2017-04-03 | 2017-05-01
7 |  |  |  | EOF: Diesel Engine drain tank-52-D-304A Erection
Act | 2AI101MS01900-08115 | Not Started | Completed | EOF: Diesel Engine drain tank-52-D-304A Erection | 2017-04-09 | 2017-05-14 | 2017-04-09 | 2017-05-14
Act | 2AI101MS01900-08010 | Not Started | Completed | EOF: Diesel Engine drain tank-52-D-304AErection | 2017-04-09 | 2017-05-14 | 2017-04-09 | 2017-05-14
7 |  |  |  | EOF: Diesel Engine drain tank-52-D-304B Erection
Act | 2AI101MS01900-08120 | Not Started | Completed | EOF: Diesel Engine drain tank-52-D-304B Erection | 2017-05-14 | 2017-06-18 | 2017-05-14 | 2017-06-18
Act | 2AI101MS01900-08015 | Not Started | Completed | EOF: Diesel Engine drain tank-52-D-304BErection | 2017-05-14 | 2017-06-18 | 2017-05-14 | 2017-06-18
7 |  |  |  | EOF: Foam drain tank-52-D-305A Erection
Act | 2AI101MS01900-08125 | Not Started | Completed | EOF: Foam drain tank-52-D-305A Erection | 2017-06-18 | 2017-07-23 | 2017-06-18 | 2017-07-23
Act | 2AI101MS01900-08020 | Not Started | Completed | EOF: Foam drain tank-52-D-305AErection | 2017-06-18 | 2017-07-23 | 2017-06-18 | 2017-07-23
7 |  |  |  | EOF: Foam drain tank-52-D-305B Erection
Act | 2AI101MS01900-08130 | Not Started | Completed | EOF: Foam drain tank-52-D-305B Erection | 2017-07-23 | 2017-08-27 | 2017-07-29 | 2017-08-09
Act | 2AI101MS01900-08025 | Not Started | Completed | EOF: Foam drain tank-52-D-305B Erection | 2017-07-23 | 2017-08-27 | 2017-07-29 | 2017-08-09
7 |  |  |  | EOF: Flushing water drain tank-52-D-306A Erection
Act | 2AI101MS01900-08135 | Not Started | Completed | EOF: Flushing water drain tank-52-D-306A Erection | 2017-05-10 | 2017-06-14 | 2017-05-10 | 2017-06-14
Act | 2AI101MS01900-08030 | Not Started | Completed | EOF: Flushing water drain tank-52-D-306AErection | 2017-05-10 | 2017-06-14 | 2017-05-10 | 2017-06-14
7 |  |  |  | EOF: Flushing water drain tank-52-D-306B Erection
Act | 2AI101MS01900-08140 | Not Started | Completed | EOF: Flushing water drain tank-52-D-306B Erection | 2017-06-14 | 2017-07-19 | 2017-06-14 | 2017-07-19
Act | 2AI101MS01900-08035 | Not Started | Completed | EOF: Flushing water drain tank-52-D-306B Erection | 2017-06-14 | 2017-07-19 | 2017-06-14 | 2017-07-19
7 |  |  |  | EOF: Water drain tank-52-D-308A Erection
Act | 2AI101MS01900-08145 | Not Started | Completed | EOF: Water drain tank-52-D-308A Erection | 2017-03-12 | 2017-04-16 | 2017-03-12 | 2017-04-16
Act | 2AI101MS01900-08040 | Not Started | Completed | EOF: Water drain tank-52-D-308AErection | 2017-03-12 | 2017-04-16 | 2017-03-12 | 2017-04-16
7 |  |  |  | EOF: Water drain tank-52-D-308B Erection
Act | 2AI101MS01900-08150 | Not Started | Completed | EOF: Water drain tank-52-D-308B Erection | 2017-04-16 | 2017-05-21 | 2017-04-16 | 2017-05-21
Act | 2AI101MS01900-08045 | Not Started | Completed | EOF: Water drain tank-52-D-308BErection | 2017-04-16 | 2017-05-21 | 2017-04-16 | 2017-05-21
4 |  |  |  | MECHANICAL - ROTATING
5 |  |  |  | EOF: Pump Erection
Act | 2AI101MS03000 | Not Started | In Progress | EOF: Pump Erection | 2017-06-28 | 2017-08-19 | 2018-03-01
6 |  |  |  | EOF: 621-G-301 A Trim Pump Erection
Act | 2AI101MS03000-08001 | Not Started | Completed | EOF:Foundation checks/Preparation for Equipment 621-G-301 A Trim Pump Erection | 2017-06-28 | 2017-06-29 | 2018-03-01 | 2018-03-02
Act | 2AI101MS03000-08006 | Not Started | Completed | EOF:Installation of Equipment 621-G-301 A Trim Pump Erection | 2017-06-29 | 2017-07-08 | 2018-03-03 | 2018-03-03
Act | 2AI101MS03000-08011 | Not Started | Completed | EOF:Preliminary Allignment & Grouting of Equipment 621-G-301 A Trim Pump Erection | 2017-07-08 | 2017-07-13 | 2018-04-23 | 2018-07-04
Act | 2AI101MS03000-08016 | Not Started | Completed | EOF:Final Allignment & Grouting of Equipment 621-G-301 A Trim Pump Erection | 2017-07-13 | 2017-07-18 | 2018-08-03 | 2018-08-22
Act | 2AI101MS03000-08020 | Not Started | Completed | EOF:QC checks & clearance for Equipment 621-G-301 A Trim Pump Erection | 2017-07-18 | 2017-07-19 | 2018-08-23 | 2018-08-23
Act | 2AI101MS03000-08000 | Not Started | Completed | EOF: 621-G-301 A Trim Pump Erection | 2017-06-28 | 2017-07-19 | 2018-03-01 | 2018-08-23
6 |  |  |  | EOF: 621-G-301 B Trim Pump Erection
Act | 2AI101MS03000-08025 | Not Started | Completed | EOF:Foundation checks/Preparation for Equipment 621-G-301 B Trim Pump Erection | 2017-07-23 | 2017-07-24 | 2018-03-02 | 2018-03-03
Act | 2AI101MS03000-08030 | Not Started | Completed | EOF:Installation of Equipment 621-G-301 B Trim Pump Erection | 2017-07-24 | 2017-08-01 | 2018-03-04 | 2018-03-04
Act | 2AI101MS03000-08035 | Not Started | Completed | EOF:Preliminary Allignment & Grouting of Equipment 621-G-301 B Trim Pump Erection | 2017-08-01 | 2017-08-07 | 2018-04-21 | 2018-07-04
Act | 2AI101MS03000-08040 | Not Started | Completed | EOF:Final Allignment & Grouting of Equipment 621-G-301 B Trim Pump Erection | 2017-08-07 | 2017-08-12 | 2018-08-05 | 2018-08-23
Act | 2AI101MS03000-08045 | Not Started | Completed | EOF:QC checks & clearance for Equipment 621-G-301 B Trim Pump Erection | 2017-08-12 | 2017-08-13 | 2018-08-24 | 2018-08-24
Act | 2AI101MS03000-08005 | Not Started | Completed | EOF: 621-G-301 B Trim Pump Erection | 2017-07-23 | 2017-08-13 | 2018-03-02 | 2018-08-24
6 |  |  |  | EOF: 621-G-303 A Oily Water Transfer Pump Erection
Act | 2AI101MS03000-08050 | Not Started | Completed | EOF:Foundation checks/Preparation for Equipment 621-G-303 A Oily Water Transfer Pump | 2017-07-08 | 2017-07-09 | 2018-05-26 | 2018-05-26
Act | 2AI101MS03000-08055 | Not Started | Completed | EOF:Installation of Equipment 621-G-303 A Oily Water Transfer Pump | 2017-07-09 | 2017-07-17 | 2018-05-27 | 2018-05-27
Act | 2AI101MS03000-08060 | Not Started | Completed | EOF:Preliminary Allignment & Grouting of Equipment 621-G-303 A Oily Water Transfer Pump | 2017-07-17 | 2017-07-23 | 2018-05-27 | 2018-05-28
Act | 2AI101MS03000-08065 | Not Started | Not Started | EOF:Final Allignment & Grouting of Equipment 621-G-303 A Oily Water Transfer Pump | 2017-07-23 | 2017-07-27
Act | 2AI101MS03000-08070 | Not Started | Not Started | EOF:QC checks & clearance for Equipment 621-G-303 A Oily Water Transfer Pump | 2017-07-27 | 2017-07-29
Act | 2AI101MS03000-08010 | Not Started | In Progress | EOF: 621-G-303 A Oily Water Transfer Pump Erection | 2017-07-08 | 2017-07-29 | 2018-05-26
6 |  |  |  | EOF: 621-G-303 B Oily Water Transfer Pump Erection
Act | 2AI101MS03000-08075 | Not Started | Completed | EOF:Foundation checks/Preparation for Equipment 621-G-303 B Oily Water Transfer Pump | 2017-07-29 | 2017-07-30 | 2018-05-26 | 2018-05-26
Act | 2AI101MS03000-08080 | Not Started | Completed | EOF:Installation of Equipment 621-G-303 B Oily Water Transfer Pump | 2017-07-30 | 2017-08-07 | 2018-05-27 | 2018-05-27
Act | 2AI101MS03000-08085 | Not Started | Completed | EOF:Preliminary Allignment & Grouting of Equipment 621-G-303 B Oily Water Transfer Pump | 2017-08-07 | 2017-08-13 | 2018-05-27 | 2018-05-28
Act | 2AI101MS03000-08090 | Not Started | Not Started | EOF:Final Allignment & Grouting of Equipment 621-G-303 B Oily Water Transfer Pump | 2017-08-13 | 2017-08-17
Act | 2AI101MS03000-08095 | Not Started | Not Started | EOF:QC checks & clearance for Equipment 621-G-303 B Oily Water Transfer Pump | 2017-08-17 | 2017-08-19
Act | 2AI101MS03000-08015 | Not Started | In Progress | EOF: 621-G-303 B Oily Water Transfer Pump Erection | 2017-07-29 | 2017-08-19 | 2018-05-26
4 |  |  |  | PIPING
5 |  |  |  | EOF: UG Piping works
Act | 2AI101PI01000 | Not Started | Completed | EOF: UG Piping works | 2017-02-02 | 2017-12-03 | 2017-01-16 | 2019-02-21
6 |  |  |  | EOF: UG Piping works for Non Metallic
Act | 2AI101PI01000-08000 | Not Started | Completed | EOF: UG Piping works for Non Metallic | 2017-02-02 | 2017-07-08 | 2017-02-06 | 2019-02-20
Act | 2AI101PI01000-08330 | Not Started | Completed | EOF:Laying of Piping Spools | 2017-02-02 | 2017-06-28 | 2017-02-06 | 2019-02-15
Act | 2AI101PI01000-08335 | Not Started | Completed | EOF:Jointing/Fusion Welding | 2017-02-13 | 2017-07-03 | 2017-02-06 | 2019-02-17
Act | 2AI101PI01000-08340 | Not Started | Completed | EOF:NDE/QC Checks of Pipes | 2017-02-18 | 2017-07-08 | 2017-02-06 | 2019-02-20
7 |  |  |  | Effluent water(WK) Line
Act | 2AI101PI01000-08135 | Not Started | Completed | EOF:Laying of Piping Spools | 2017-02-02 | 2017-06-28 | 2018-01-01 | 2018-01-03
Act | 2AI101PI01000-08140 | Not Started | Completed | EOF:Jointing/Fusion Welding | 2017-02-13 | 2017-07-03 | 2018-01-01 | 2018-01-03
Act | 2AI101PI01000-08145 | Not Started | Completed | EOF:NDE/QC Checks of Pipes | 2017-02-18 | 2017-07-08 | 2018-01-01 | 2018-01-03
7 |  |  |  | Oily Water Line
Act | 2AI101PI01000-08090 | Not Started | Completed | EOF:Laying of Piping Spools | 2017-02-02 | 2017-06-28 | 2017-12-21 | 2019-02-06 | [66 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [8 empty] | 0 | [9 empty] | 0 | [9 empty] | 12 | [8 empty] | 37 | [9 empty] | 61 | [9 empty] | 30 | [8 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [8 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  |  |  | 0
Act | 2AI101PI01000-08095 | Not Started | Completed | EOF:Jointing/Fusion Welding | 2017-03-04 | 2017-07-01 | 2017-11-28 | 2019-02-12 | [66 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [8 empty] | 0 | [9 empty] | 0 | [9 empty] | 12 | [8 empty] | 37 | [9 empty] | 61 | [9 empty] | 30 | [8 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [8 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  |  |  | 0
Act | 2AI101PI01000-08100 | Not Started | Completed | EOF:NDE/QC Checks of Pipes | 2017-03-08 | 2017-07-04 | 2018-04-02 | 2019-02-15 | [66 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [8 empty] | 0 | [9 empty] | 0 | [9 empty] | 12 | [8 empty] | 37 | [9 empty] | 61 | [9 empty] | 30 | [8 empty] | 26 | [9 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [8 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  |  |  | 0
7 |  |  |  | Other Lines
Act | 2AI101PI01000-08001 | Not Started | Completed | EOF:Laying of Piping Spools | 2017-02-19 | 2017-05-11 | 2017-02-06 | 2019-02-15
Act | 2AI101PI01000-08006 | Not Started | Completed | EOF:Jointing/Fusion Welding | 2017-02-25 | 2017-05-17 | 2017-02-06 | 2019-02-17
Act | 2AI101PI01000-08011 | Not Started | Completed | EOF:NDE/QC Checks of Pipes | 2017-03-11 | 2017-05-29 | 2017-02-06 | 2019-02-20
6 |  |  |  | EOF: UG Piping works for Metallic (CS/LTCS)
Act | 2AI101PI01000-08005 | Not Started | Completed | EOF: UG Piping works for Metallic (CS/LTCS) | 2017-02-02 | 2017-12-03 | 2017-01-16 | 2019-02-21
Act | 2AI101PI01000-08345 | Not Started | Completed | EOF:Installation of pipes | 2017-02-02 | 2017-11-25 | 2017-01-16 | 2019-01-03
Act | 2AI101PI01000-08350 | Not Started | Completed | EOF:Alignment/Fit-up | 2017-02-28 | 2017-11-28 | 2017-01-16 | 2019-01-04
Act | 2AI101PI01000-08360 | Not Started | Completed | EOF:NDE/PWHT/QC Checks of Pipes | 2017-03-02 | 2017-12-02 | 2017-01-30 | 2019-01-08
Act | 2AI101PI01000-08355 | Not Started | Completed | EOF:Welding/Bolting of Pipes | 2017-03-01 | 2017-11-29 | 2017-01-17 | 2019-01-05
Act | 2AI101PI01000-08365 | Not Started | Completed | EOF:Coating/Wrapping | 2017-09-03 | 2017-12-03 | 2017-06-06 | 2019-02-21
7 |  |  |  | EOF: UG Piping works Filling Line
8 |  |  |  | EOF: UG Piping works Filling Line Main pipe from PIG to Tank
Act | 2AI101PI01000-08150 | Not Started | Completed | EOF:Installation of pipes | 2017-02-02 | 2017-03-14 | 2017-04-22 | 2018-05-26
Act | 2AI101PI01000-08155 | Not Started | Completed | EOF:Alignment/Fit-up | 2017-03-25 | 2017-05-03 | 2017-04-25 | 2018-05-27
Act | 2AI101PI01000-08160 | Not Started | Completed | EOF:NDE/PWHT/QC Checks of Pipes | 2017-03-29 | 2017-05-08 | 2017-06-25 | 2018-05-25
Act | 2AI101PI01000-08156 | Not Started | Completed | EOF:Welding/Bolting of Pipes | 2017-03-27 | 2017-05-06 | 2017-05-09 | 2018-05-29
Act | 2AI101PI01000-08161 | Not Started | Completed | EOF:Coating/Wrapping | 2017-10-16 | 2017-11-02 | 2018-05-15 | 2018-05-26
8 |  |  |  | EOF: UG Piping works Filling Line-Branch Line to Tank 52-D-94
Act | 2AI101PI01000-08165 | Not Started | Completed | EOF:Installation of pipes | 2017-07-08 | 2017-07-29 | 2017-11-04 | 2018-01-02
Act | 2AI101PI01000-08170 | Not Started | Completed | EOF:Alignment/Fit-up | 2017-08-14 | 2017-09-04 | 2017-06-25 | 2017-12-16
Act | 2AI101PI01000-08175 | Not Started | Completed | EOF:NDE/PWHT/QC Checks of Pipes | 2017-08-16 | 2017-09-06 | 2017-07-07 | 2017-12-16
Act | 2AI101PI01000-08171 | Not Started | Completed | EOF:Welding/Bolting of Pipes | 2017-08-15 | 2017-09-05 | 2017-06-25 | 2017-12-16
Act | 2AI101PI01000-08176 | Not Started | Completed | EOF:Coating/Wrapping | 2017-10-16 | 2017-10-30 | 2018-05-26 | 2018-05-30
8 |  |  |  | EOF: UG Piping works Filling Line-Branch Line to Tank 52-D-93
Act | 2AI101PI01000-08016 | Not Started | Completed | EOF:Installation of pipes | 2017-07-08 | 2017-07-29 | 2017-10-28 | 2018-01-05
Act | 2AI101PI01000-08035 | Not Started | Completed | EOF:Alignment/Fit-up | 2017-08-14 | 2017-09-04 | 2017-07-04 | 2017-12-17
Act | 2AI101PI01000-08055 | Not Started | Completed | EOF:NDE/PWHT/QC Checks of Pipes | 2017-08-17 | 2017-09-07 | 2017-07-12 | 2017-12-17
Act | 2AI101PI01000-08036 | Not Started | Completed | EOF:Welding/Bolting of Pipes | 2017-08-15 | 2017-09-05 | 2017-07-07 | 2017-12-17
Act | 2AI101PI01000-08056 | Not Started | Completed | EOF:Coating/Wrapping | 2017-10-09 | 2017-10-18 | 2018-04-17 | 2018-04-18
8 |  |  |  | EOF: UG Piping works Filling Line-Branch Line to Tank 52-D-95
Act | 2AI101PI01000-08180 | Not Started | Completed | EOF:Installation of pipes | 2017-07-25 | 2017-08-15 | 2017-10-28 | 2018-03-07
Act | 2AI101PI01000-08185 | Not Started | Completed | EOF:Alignment/Fit-up | 2017-08-17 | 2017-09-04 | 2017-07-14 | 2018-04-23
Act | 2AI101PI01000-08190 | Not Started | Completed | EOF:NDE/PWHT/QC Checks of Pipes | 2017-08-23 | 2017-09-06 | 2017-07-29 | 2018-05-27
Act | 2AI101PI01000-08186 | Not Started | Completed | EOF:Welding/Bolting of Pipes | 2017-08-19 | 2017-09-05 | 2017-07-14 | 2018-05-26
Act | 2AI101PI01000-08191 | Not Started | Completed | EOF:Coating/Wrapping | 2017-10-16 | 2017-10-25 | 2018-06-26 | 2018-07-02
8 |  |  |  | EOF: UG Piping works Filling Line-Branch Line to Tank 52-D- 96
Act | 2AI101PI01000-08195 | Not Started | Completed | EOF:Installation of pipes | 2017-07-16 | 2017-08-02 | 2017-10-02 | 2018-03-07
Act | 2AI101PI01000-08200 | Not Started | Completed | EOF:Alignment/Fit-up | 2017-08-21 | 2017-09-04 | 2017-07-15 | 2018-05-26
Act | 2AI101PI01000-08205 | Not Started | Completed | EOF:NDE/PWHT/QC Checks of Pipes | 2017-08-23 | 2017-09-06 | 2017-08-06 | 2018-05-28
Act | 2AI101PI01000-08201 | Not Started | Completed | EOF:Welding/Bolting of Pipes | 2017-08-22 | 2017-09-05 | 2017-07-16 | 2018-05-27
Act | 2AI101PI01000-08206 | Not Started | Completed | EOF:Coating/Wrapping | 2017-10-16 | 2017-10-30 | 2018-07-12 | 2018-07-20
7 |  |  |  | EOF: UG Piping works Loading Line
8 |  |  |  | EOF: UG Piping works Loading Line Main pipe from PIG to Tank
Act | 2AI101PI01000-08210 | Not Started | Completed | EOF:Installation of pipes | 2017-02-02 | 2017-03-02 | 2017-03-08 | 2018-04-19
Act | 2AI101PI01000-08215 | Not Started | Completed | EOF:Alignment/Fit-up | 2017-04-05 | 2017-05-03 | 2017-03-09 | 2018-04-20
Act | 2AI101PI01000-08220 | Not Started | Completed | EOF:NDE/PWHT/QC Checks of Pipes | 2017-04-09 | 2017-05-07 | 2017-03-30 | 2018-04-23
Act | 2AI101PI01000-08216 | Not Started | Completed | EOF:Welding/Bolting of Pipes | 2017-04-08 | 2017-05-06 | 2017-03-11 | 2018-04-20
Act | 2AI101PI01000-08221 | Not Started | Completed | EOF:Coating/Wrapping | 2017-10-26 | 2017-11-16 | 2018-05-28 | 2018-07-27
8 |  |  |  | EOF: UG Piping works Loading Line Main pipe from Trim Pump to Tank
Act | 2AI101PI01000-08925 | Not Started | Completed | EOF:Installation of pipes | 2017-02-02 | 2017-03-02 | 2017-02-25 | 2018-05-26
Act | 2AI101PI01000-08930 | Not Started | Completed | EOF:Alignment/Fit-up | 2017-04-05 | 2017-05-03 | 2017-02-26 | 2018-05-29
Act | 2AI101PI01000-08935 | Not Started | Completed | EOF:NDE/PWHT/QC Checks of Pipes | 2017-04-09 | 2017-05-07 | 2017-02-28 | 2018-06-03
Act | 2AI101PI01000-08931 | Not Started | Completed | EOF:Welding/Bolting of Pipes | 2017-04-08 | 2017-05-06 | 2017-02-27 | 2018-06-02
Act | 2AI101PI01000-08936 | Not Started | Completed | EOF:Coating/Wrapping | 2017-10-26 | 2017-11-16 | 2018-06-25 | 2018-07-26
8 |  |  |  | EOF: UG Piping works Loading Line-Branch Line to Tank 52-D-94
Act | 2AI101PI01000-08225 | Not Started | Completed | EOF:Installation of pipes | 2017-07-08 | 2017-07-29 | 2017-09-23 | 2017-11-28
Act | 2AI101PI01000-08230 | Not Started | Completed | EOF:Alignment/Fit-up | 2017-08-14 | 2017-09-04 | 2017-03-29 | 2017-12-18
Act | 2AI101PI01000-08235 | Not Started | Completed | EOF:NDE/PWHT/QC Checks of Pipes | 2017-08-17 | 2017-09-07 | 2017-03-30 | 2017-12-18
Act | 2AI101PI01000-08231 | Not Started | Completed | EOF:Welding/Bolting of Pipes | 2017-08-15 | 2017-09-05 | 2017-03-29 | 2017-12-18
Act | 2AI101PI01000-08236 | Not Started | Completed | EOF:Coating/Wrapping | 2017-10-26 | 2017-11-09 | 2018-05-25 | 2018-06-01
8 |  |  |  | EOF: UG Piping works Loading Line-Branch Line to Tank 52-D-93
Act | 2AI101PI01000-08075 | Not Started | Completed | EOF:Installation of pipes | 2017-07-08 | 2017-07-29 | 2017-09-23 | 2017-12-07
Act | 2AI101PI01000-08080 | Not Started | Completed | EOF:Alignment/Fit-up | 2017-08-14 | 2017-09-04 | 2017-03-17 | 2017-12-17
Act | 2AI101PI01000-08085 | Not Started | Completed | EOF:NDE/PWHT/QC Checks of Pipes | 2017-08-17 | 2017-09-07 | 2017-03-20 | 2017-12-17
Act | 2AI101PI01000-08081 | Not Started | Completed | EOF:Welding/Bolting of Pipes | 2017-08-15 | 2017-09-05 | 2017-03-17 | 2017-12-17
Act | 2AI101PI01000-08086 | Not Started | Completed | EOF:Coating/Wrapping | 2017-10-26 | 2017-11-09 | 2018-04-18 | 2018-05-26
8 |  |  |  | EOF: UG Piping works Loading Line-Branch Line to Tank 52-D-95
Act | 2AI101PI01000-08240 | Not Started | Completed | EOF:Installation of pipes | 2017-07-25 | 2017-08-15 | 2017-10-01 | 2018-02-24
Act | 2AI101PI01000-08245 | Not Started | Completed | EOF:Alignment/Fit-up | 2017-08-14 | 2017-09-04 | 2017-03-25 | 2018-04-26
Act | 2AI101PI01000-08250 | Not Started | Completed | EOF:NDE/PWHT/QC Checks of Pipes | 2017-08-16 | 2017-09-06 | 2017-03-29 | 2018-04-26
Act | 2AI101PI01000-08246 | Not Started | Completed | EOF:Welding/Bolting of Pipes | 2017-08-15 | 2017-09-05 | 2017-03-25 | 2018-04-26
Act | 2AI101PI01000-08251 | Not Started | Completed | EOF:Coating/Wrapping | 2017-10-26 | 2017-11-09 | 2018-06-29 | 2018-07-08
8 |  |  |  | EOF: UG Piping works Loading Line-Branch Line to Tank 52-D- 96
Act | 2AI101PI01000-08255 | Not Started | Completed | EOF:Installation of pipes | 2017-07-13 | 2017-08-03 | 2017-08-29 | 2018-03-07
Act | 2AI101PI01000-08260 | Not Started | Completed | EOF:Alignment/Fit-up | 2017-08-14 | 2017-09-04 | 2017-03-26 | 2018-04-04
Act | 2AI101PI01000-08265 | Not Started | Completed | EOF:NDE/PWHT/QC Checks of Pipes | 2017-08-17 | 2017-09-07 | 2017-03-29 | 2018-04-06
Act | 2AI101PI01000-08261 | Not Started | Completed | EOF:Welding/Bolting of Pipes | 2017-08-15 | 2017-09-05 | 2017-03-26 | 2018-04-05
Act | 2AI101PI01000-08266 | Not Started | Completed | EOF:Coating/Wrapping | 2017-10-26 | 2017-11-09 | 2018-06-29 | 2018-07-08
7 |  |  |  | EOF: UG Piping works Fire Water Line
8 |  |  |  | EOF: UG Piping works Fire Water Line: Main Header inside Bund Wall
Act | 2AI101PI01000-08105 | Not Started | Completed | EOF:Installation of pipes | 2017-02-08 | 2017-03-29 | 2017-05-27 | 2018-12-10
Act | 2AI101PI01000-08110 | Not Started | Completed | EOF:Alignment/Fit-up | 2017-03-15 | 2017-05-03 | 2017-05-03 | 2018-12-12
Act | 2AI101PI01000-08115 | Not Started | Completed | EOF:NDE/PWHT/QC Checks of Pipes | 2017-05-03 | 2017-06-21 | 2017-05-27 | 2018-12-18
Act | 2AI101PI01000-08111 | Not Started | Completed | EOF:Welding/Bolting of Pipes | 2017-03-16 | 2017-05-04 | 2017-05-04 | 2018-12-15
Act | 2AI101PI01000-08116 | Not Started | Completed | EOF:Coating/Wrapping | 2017-10-11 | 2017-11-09 | 2017-07-17 | 2018-12-20
8 |  |  |  | EOF: UG Piping works Fire Water Line: Fire Water Ring Out side Bund wall
Act | 2AI101PI01000-08315 | Not Started | Completed | EOF:Installation of pipes | 2017-02-05 | 2017-04-10 | 2017-03-22 | 2019-01-03
Act | 2AI101PI01000-08320 | Not Started | Completed | EOF:Alignment/Fit-up | 2017-02-28 | 2017-05-03 | 2017-04-04 | 2019-01-04
Act | 2AI101PI01000-08325 | Not Started | Completed | EOF:NDE/PWHT/QC Checks of Pipes | 2017-03-02 | 2017-05-06 | 2017-05-06 | 2019-01-08
Act | 2AI101PI01000-08321 | Not Started | Completed | EOF:Welding/Bolting of Pipes | 2017-03-01 | 2017-05-04 | 2017-04-04 | 2019-01-05
Act | 2AI101PI01000-08326 | Not Started | Completed | EOF:Coating/Wrapping | 2017-10-11 | 2017-11-27 | 2017-06-06 | 2019-02-21
8 |  |  |  | EOF: UG Piping works Fire Water Line: Branches to Tank 52-D-94
Act | 2AI101PI01000-08120 | Not Started | Completed | EOF:Installation of pipes | 2017-10-14 | 2017-11-07 | 2017-06-06 | 2018-08-03
Act | 2AI101PI01000-08125 | Not Started | Completed | EOF:Alignment/Fit-up | 2017-10-17 | 2017-11-11 | 2017-05-20 | 2018-08-09
Act | 2AI101PI01000-08130 | Not Started | Completed | EOF:NDE/PWHT/QC Checks of Pipes | 2017-10-21 | 2017-11-14 | 2017-06-07 | 2018-08-12
Act | 2AI101PI01000-08126 | Not Started | Completed | EOF:Welding/Bolting of Pipes | 2017-10-18 | 2017-11-12 | 2017-05-20 | 2018-08-15
Act | 2AI101PI01000-08131 | Not Started | Completed | EOF:Coating/Wrapping | 2017-11-01 | 2017-11-15 | 2017-10-15 | 2018-10-09
8 |  |  |  | EOF: UG Piping works Fire Water Line: Branches to Tank 52-D-93
Act | 2AI101PI01000-08270 | Not Started | Completed | EOF:Installation of pipes | 2017-10-19 | 2017-11-13 | 2017-06-06 | 2018-07-20
Act | 2AI101PI01000-08275 | Not Started | Completed | EOF:Alignment/Fit-up | 2017-10-23 | 2017-11-16 | 2017-05-12 | 2018-08-09
Act | 2AI101PI01000-08280 | Not Started | Completed | EOF:NDE/PWHT/QC Checks of Pipes | 2017-10-26 | 2017-11-20 | 2017-06-07 | 2018-08-28
Act | 2AI101PI01000-08276 | Not Started | Completed | EOF:Welding/Bolting of Pipes | 2017-10-24 | 2017-11-18 | 2017-05-12 | 2018-08-09
Act | 2AI101PI01000-08281 | Not Started | Completed | EOF:Coating/Wrapping | 2017-11-07 | 2017-11-21 | 2017-11-06 | 2018-10-20
8 |  |  |  | EOF: UG Piping works Fire Water Line: Branches to Tank 52-D-95
Act | 2AI101PI01000-08285 | Not Started | Completed | EOF:Installation of pipes | 2017-10-31 | 2017-11-25 | 2017-07-24 | 2018-10-26
Act | 2AI101PI01000-08290 | Not Started | Completed | EOF:Alignment/Fit-up | 2017-11-04 | 2017-11-28 | 2017-05-08 | 2018-10-28
Act | 2AI101PI01000-08295 | Not Started | Completed | EOF:NDE/PWHT/QC Checks of Pipes | 2017-11-07 | 2017-12-02 | 2017-06-05 | 2018-11-01
Act | 2AI101PI01000-08291 | Not Started | Completed | EOF:Welding/Bolting of Pipes | 2017-11-05 | 2017-11-29 | 2017-05-08 | 2018-10-30
Act | 2AI101PI01000-08296 | Not Started | Completed | EOF:Coating/Wrapping | 2017-11-19 | 2017-12-03 | 2018-01-01 | 2018-12-28
8 |  |  |  | EOF: UG Piping works Fire Water Line: Branches to Tank 52-D-96
Act | 2AI101PI01000-08300 | Not Started | Completed | EOF:Installation of pipes | 2017-10-25 | 2017-11-19 | 2017-07-25 | 2018-10-19
Act | 2AI101PI01000-08305 | Not Started | Completed | EOF:Alignment/Fit-up | 2017-10-29 | 2017-11-22 | 2017-05-08 | 2018-10-19
Act | 2AI101PI01000-08310 | Not Started | Completed | EOF:NDE/PWHT/QC Checks of Pipes | 2017-11-01 | 2017-11-26 | 2017-06-05 | 2018-11-01
Act | 2AI101PI01000-08306 | Not Started | Completed | EOF:Welding/Bolting of Pipes | 2017-10-30 | 2017-11-23 | 2017-05-09 | 2018-10-28
Act | 2AI101PI01000-08311 | Not Started | Completed | EOF:Coating/Wrapping | 2017-11-13 | 2017-11-27 | 2018-01-01 | 2018-12-05
7 |  |  |  | EOF: UG Piping works Foam Pumping System Line
8 |  |  |  | EOF: UG Piping works Foam Line to Tank 52-D-93
Act | 2AI101PI01000-08032 | Not Started | Completed | EOF:Installation of pipes | 2017-02-02 | 2017-03-16 | 2017-06-06 | 2018-10-10
Act | 2AI101PI01000-08033 | Not Started | Completed | EOF:Alignment/Fit-up | 2017-03-22 | 2017-05-03 | 2017-06-06 | 2018-10-11
Act | 2AI101PI01000-08039 | Not Started | Completed | EOF:NDE/PWHT/QC Checks of Pipes | 2017-05-03 | 2017-06-14 | 2017-06-08 | 2018-10-15
Act | 2AI101PI01000-08037 | Not Started | Completed | EOF:Welding/Bolting of Pipes | 2017-03-23 | 2017-05-04 | 2017-06-07 | 2018-10-13
Act | 2AI101PI01000-08041 | Not Started | Completed | EOF:Coating/Wrapping | 2017-08-30 | 2017-09-13 | 2017-10-25 | 2018-12-30
8 |  |  |  | EOF: UG Piping works Foam Line to Tank 52-D-94
Act | 2AI101PI01000-08043 | Not Started | Completed | EOF:Installation of pipes | 2017-02-02 | 2017-03-16 | 2017-07-19 | 2018-10-08
Act | 2AI101PI01000-08047 | Not Started | Completed | EOF:Alignment/Fit-up | 2017-03-22 | 2017-05-03 | 2017-06-05 | 2018-10-13
Act | 2AI101PI01000-08051 | Not Started | Completed | EOF:NDE/PWHT/QC Checks of Pipes | 2017-05-03 | 2017-06-14 | 2017-06-05 | 2018-10-15
Act | 2AI101PI01000-08049 | Not Started | Completed | EOF:Welding/Bolting of Pipes | 2017-03-22 | 2017-05-03 | 2017-06-05 | 2018-10-15
Act | 2AI101PI01000-08053 | Not Started | Completed | EOF:Coating/Wrapping | 2017-08-30 | 2017-09-13 | 2017-11-06 | 2018-12-30
8 |  |  |  | EOF: UG Piping works Foam Line to Tank 52-D-95
Act | 2AI101PI01000-08061 | Not Started | Completed | EOF:Installation of pipes | 2017-02-02 | 2017-03-16 | 2017-10-02 | 2018-08-27
Act | 2AI101PI01000-08062 | Not Started | Completed | EOF:Alignment/Fit-up | 2017-03-22 | 2017-05-03 | 2017-06-05 | 2018-09-01
Act | 2AI101PI01000-08067 | Not Started | Completed | EOF:NDE/PWHT/QC Checks of Pipes | 2017-05-03 | 2017-06-14 | 2017-06-05 | 2018-09-25
Act | 2AI101PI01000-08063 | Not Started | Completed | EOF:Welding/Bolting of Pipes | 2017-03-23 | 2017-05-04 | 2017-06-05 | 2018-09-06
Act | 2AI101PI01000-08069 | Not Started | Completed | EOF:Coating/Wrapping | 2017-08-30 | 2017-09-13 | 2018-01-01 | 2018-11-24
8 |  |  |  | EOF: UG Piping works Foam Line to Tank 52-D-96
Act | 2AI101PI01000-08071 | Not Started | Completed | EOF:Installation of pipes | 2017-02-02 | 2017-03-16 | 2017-09-23 | 2018-08-25
Act | 2AI101PI01000-08072 | Not Started | Completed | EOF:Alignment/Fit-up | 2017-03-22 | 2017-05-03 | 2017-06-05 | 2018-09-27
Act | 2AI101PI01000-08077 | Not Started | Completed | EOF:NDE/PWHT/QC Checks of Pipes | 2017-05-03 | 2017-06-14 | 2017-06-05 | 2018-09-30
Act | 2AI101PI01000-08073 | Not Started | Completed | EOF:Welding/Bolting of Pipes | 2017-03-23 | 2017-05-04 | 2017-06-05 | 2018-09-27
Act | 2AI101PI01000-08079 | Not Started | Completed | EOF:Coating/Wrapping | 2017-08-30 | 2017-09-13 | 2018-01-01 | 2018-11-24
7 |  |  |  | EOF: UG Piping works Other Line
Act | 2AI101PI01000-08020 | Not Started | Completed | EOF:Installation of pipes | 2017-03-01 | 2017-05-04 | 2017-01-16 | 2018-05-21
Act | 2AI101PI01000-08025 | Not Started | Completed | EOF:Alignment/Fit-up | 2017-03-07 | 2017-05-10 | 2017-01-16 | 2018-05-30
Act | 2AI101PI01000-08030 | Not Started | Completed | EOF:NDE/PWHT/QC Checks of Pipes | 2017-05-10 | 2017-07-13 | 2017-01-30 | 2018-05-30
Act | 2AI101PI01000-08026 | Not Started | Completed | EOF:Welding/Bolting of Pipes | 2017-03-08 | 2017-05-11 | 2017-01-17 | 2018-05-30
Act | 2AI101PI01000-08031 | Not Started | Completed | EOF:Coating/Wrapping | 2017-09-03 | 2017-10-19 | 2018-06-22 | 2018-08-08
6 |  |  |  | EOF: UG Piping works for Metallic (SS/SDSS)
Act | 2AI101PI01000-08040 | Not Started | Completed | EOF:Installation of pipes | 2017-02-19 | 2017-11-08 | 2018-05-26 | 2019-01-16 | [66 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [8 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [8 empty] | 34 | [9 empty] | 59 | [9 empty] | 57 | [8 empty] | 55 | [9 empty] | 53 | [9 empty] | 1 | [9 empty] | 0 | [8 empty] | 56 | [9 empty] | 0 | [9 empty] | 0 |  |  |  |  | 0
Act | 2AI101PI01000-08045 | Not Started | Completed | EOF:Alignment/Fit-up | 2017-02-23 | 2017-11-13 | 2018-06-21 | 2019-01-17 | [66 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [8 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [8 empty] | 34 | [9 empty] | 59 | [9 empty] | 57 | [8 empty] | 55 | [9 empty] | 53 | [9 empty] | 1 | [9 empty] | 0 | [8 empty] | 56 | [9 empty] | 0 | [9 empty] | 0 |  |  |  |  | 0
Act | 2AI101PI01000-08050 | Not Started | Completed | EOF:NDE/PWHT/QC Checks of Pipes | 2017-03-25 | 2017-11-25 | 2018-10-11 | 2019-01-18 | [66 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [8 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [8 empty] | 0 | [9 empty] | 59 | [9 empty] | 57 | [8 empty] | 55 | [9 empty] | 53 | [9 empty] | 26 | [9 empty] | 63 | [8 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  |  |  | 0
Act | 2AI101PI01000-08046 | Not Started | Completed | EOF:Welding/Bolting of Pipes | 2017-03-13 | 2017-11-19 | 2018-06-21 | 2019-01-18 | [66 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [8 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [8 empty] | 0 | [9 empty] | 59 | [9 empty] | 57 | [8 empty] | 55 | [9 empty] | 53 | [9 empty] | 1 | [9 empty] | 0 | [8 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  |  |  | 0
Act | 2AI101PI01000-08010 | Not Started | Completed | EOF: UG Piping works for Metallic (SS/SDSS) | 2017-02-19 | 2017-11-25 | 2018-05-26 | 2019-01-18
6 |  |  |  | EOF: UG Piping works for Metallic (CU-NI & Other Alloy)
5 |  |  |  | EOF: AG Piping works
Act | 2AI101PI01100 | Not Started | Completed | EOF: AG Piping works | 2017-06-03 | 2018-01-24 | 2017-12-11 | 2019-04-16
6 |  |  |  | EOF: AG Piping works for Non Metallic
Act | 2AI101PI01100-08001 | Not Started | Completed | EOF:Installation of pipes | 2017-06-04 | 2017-10-01 | 2018-05-26 | 2019-02-25
Act | 2AI101PI01100-08006 | Not Started | Completed | EOF: Jointing/Fusion welding | 2017-06-14 | 2017-10-07 | 2018-04-17 | 2019-02-26
Act | 2AI101PI01100-08011 | Not Started | Completed | EOF:NDE/PWHT/QC Checks of Pipes | 2017-06-19 | 2017-10-11 | 2018-07-28 | 2019-02-26
Act | 2AI101PI01100-08016 | Not Started | Completed | EOF:Install Permanent Supporting for Pipes | 2017-10-11 | 2017-12-11 | 2018-09-29 | 2019-02-26
Act | 2AI101PI01100-08020 | Not Started | Completed | EOF:Install piping valves | 2017-11-18 | 2017-12-17 | 2018-09-29 | 2019-03-18
Act | 2AI101PI01100-08000 | Not Started | Completed | EOF: AG Piping works for Non Metallic | 2017-06-04 | 2017-12-17 | 2018-04-17 | 2019-03-18
6 |  |  |  | EOF: AG Piping works for Metallic (CS/LTCS)
Act | 2AI101PI01100-08005 | Not Started | Completed | EOF: AG Piping works Metallic (CS/LTCS) | 2017-06-03 | 2018-01-24 | 2017-12-11 | 2019-04-16
7 |  |  |  | Fire Water Line
8 |  |  |  | EOF: AG Piping works: Fire Water Line on Tank 52-D-94
Act | 2AI101PI01100-08200 | Not Started | Completed | EOF:Installation of pipes | 2017-07-08 | 2017-08-29 | 2018-09-12 | 2019-01-12
Act | 2AI101PI01100-08205 | Not Started | Completed | EOF:Alignment/Fit-up | 2017-07-17 | 2017-09-04 | 2018-09-12 | 2019-01-13
Act | 2AI101PI01100-08210 | Not Started | Completed | EOF:NDE/PWHT/QC Checks of Pipes | 2017-07-18 | 2017-09-05 | 2018-12-13 | 2019-01-17
Act | 2AI101PI01100-08215 | Not Started | Completed | EOF:Install Permanent Supporting for Pipes | 2017-07-30 | 2017-09-17 | 2018-09-12 | 2019-01-09
Act | 2AI101PI01100-08220 | Not Started | Completed | EOF:Install piping valves | 2017-09-12 | 2017-09-18 | 2018-12-03 | 2019-01-19
Act | 2AI101PI01100-08206 | Not Started | Completed | EOF:Welding/Bolting of Pipes | 2017-07-18 | 2017-09-05 | 2018-09-14 | 2019-01-14
8 |  |  |  | EOF: AG Piping works: Fire Water Line on Tank 52-D-93
Act | 2AI101PI01100-08225 | Not Started | Completed | EOF:Installation of pipes | 2017-07-08 | 2017-08-29 | 2018-08-18 | 2018-12-05
Act | 2AI101PI01100-08230 | Not Started | Completed | EOF:Alignment/Fit-up | 2017-07-17 | 2017-09-04 | 2018-08-19 | 2018-12-08
Act | 2AI101PI01100-08235 | Not Started | Completed | EOF:NDE/PWHT/QC Checks of Pipes | 2017-07-19 | 2017-09-06 | 2018-09-05 | 2018-11-30
Act | 2AI101PI01100-08240 | Not Started | Completed | EOF:Install Permanent Supporting for Pipes | 2017-07-30 | 2017-09-17 | 2018-08-18 | 2018-12-05
Act | 2AI101PI01100-08245 | Not Started | Completed | EOF:Install piping valves | 2017-09-12 | 2017-09-18 | 2018-11-30 | 2018-11-30
Act | 2AI101PI01100-08231 | Not Started | Completed | EOF:Welding/Bolting of Pipes | 2017-07-18 | 2017-09-05 | 2018-08-19 | 2018-12-10
8 |  |  |  | EOF: AG Piping works: Fire Water Line on Tank 52-D-95
Act | 2AI101PI01100-08250 | Not Started | Completed | EOF:Installation of pipes | 2017-07-13 | 2017-09-04 | 2018-10-24 | 2019-03-12
Act | 2AI101PI01100-08255 | Not Started | Completed | EOF:Alignment/Fit-up | 2017-07-18 | 2017-09-05 | 2018-10-24 | 2019-03-14
Act | 2AI101PI01100-08260 | Not Started | Completed | EOF:NDE/PWHT/QC Checks of Pipes | 2017-07-20 | 2017-09-07 | 2018-11-25 | 2019-03-15
Act | 2AI101PI01100-08265 | Not Started | Completed | EOF:Install Permanent Supporting for Pipes | 2017-07-30 | 2017-09-17 | 2018-10-10 | 2019-01-09
Act | 2AI101PI01100-08270 | Not Started | Completed | EOF:Install piping valves | 2017-09-25 | 2017-10-01 | 2018-12-03 | 2019-03-16
Act | 2AI101PI01100-08256 | Not Started | Completed | EOF:Welding/Bolting of Pipes | 2017-07-19 | 2017-09-06 | 2018-10-24 | 2019-03-15
8 |  |  |  | EOF: AG Piping works: Fire Water Line on Tank 52-D-96
Act | 2AI101PI01100-08275 | Not Started | Completed | EOF:Installation of pipes | 2017-07-13 | 2017-09-04 | 2018-10-30 | 2019-03-11
Act | 2AI101PI01100-08280 | Not Started | Completed | EOF:Alignment/Fit-up | 2017-07-18 | 2017-09-05 | 2018-10-30 | 2019-03-12
Act | 2AI101PI01100-08285 | Not Started | Completed | EOF:NDE/PWHT/QC Checks of Pipes | 2017-07-20 | 2017-09-07 | 2018-11-24 | 2019-03-14
Act | 2AI101PI01100-08290 | Not Started | Completed | EOF:Install Permanent Supporting for Pipes | 2017-07-30 | 2017-09-17 | 2018-10-25 | 2019-03-14
Act | 2AI101PI01100-08295 | Not Started | Completed | EOF:Install piping valves | 2017-09-25 | 2017-10-01 | 2018-12-03 | 2019-03-15
Act | 2AI101PI01100-08281 | Not Started | Completed | EOF:Welding/Bolting of Pipes | 2017-07-19 | 2017-09-06 | 2018-10-30 | 2019-03-12
7 |  |  |  | Foam Pumping System Line
8 |  |  |  | EOF: AG Piping works: Foam line on Tank 52-D-94
Act | 2AI101PI01100-08100 | Not Started | Completed | EOF:Installation of pipes | 2017-07-08 | 2017-08-06 | 2018-09-29 | 2018-11-25
Act | 2AI101PI01100-08105 | Not Started | Completed | EOF:Alignment/Fit-up | 2017-08-05 | 2017-09-04 | 2018-10-04 | 2018-11-30
Act | 2AI101PI01100-08110 | Not Started | Completed | EOF:NDE/PWHT/QC Checks of Pipes | 2017-08-07 | 2017-09-06 | 2018-12-08 | 2018-12-09
Act | 2AI101PI01100-08115 | Not Started | Completed | EOF:Install Permanent Supporting for Pipes | 2017-08-08 | 2017-09-12 | 2018-09-29 | 2018-12-09
Act | 2AI101PI01100-08120 | Not Started | Completed | EOF:Install piping valves | 2017-09-07 | 2017-09-13 | 2018-12-10 | 2018-12-15
Act | 2AI101PI01100-08106 | Not Started | Completed | EOF:Welding/Bolting of Pipes | 2017-08-06 | 2017-09-05 | 2018-10-05 | 2018-12-04
8 |  |  |  | EOF: AG Piping works: Foam Line on Tank 52-D-93
Act | 2AI101PI01100-08125 | Not Started | Completed | EOF:Installation of pipes | 2017-07-08 | 2017-08-06 | 2018-09-08 | 2018-12-05
Act | 2AI101PI01100-08130 | Not Started | Completed | EOF:Alignment/Fit-up | 2017-08-05 | 2017-09-04 | 2018-09-08 | 2018-11-25
Act | 2AI101PI01100-08135 | Not Started | Completed | EOF:NDE/PWHT/QC Checks of Pipes | 2017-08-07 | 2017-09-06 | 2018-12-10 | 2018-12-13
Act | 2AI101PI01100-08140 | Not Started | Completed | EOF:Install Permanent Supporting for Pipes | 2017-08-08 | 2017-09-12 | 2018-09-10 | 2018-12-07
Act | 2AI101PI01100-08145 | Not Started | Completed | EOF:Install piping valves | 2017-09-07 | 2017-09-13 | 2018-12-03 | 2018-12-12
Act | 2AI101PI01100-08131 | Not Started | Completed | EOF:Welding/Bolting of Pipes | 2017-08-06 | 2017-09-05 | 2018-09-09 | 2018-11-30
8 |  |  |  | EOF: AG Piping works: Foam Line on Tank 52-D-95
Act | 2AI101PI01100-08150 | Not Started | Completed | EOF:Installation of pipes | 2017-09-20 | 2017-10-19 | 2018-10-28 | 2019-01-26
Act | 2AI101PI01100-08155 | Not Started | Completed | EOF:Alignment/Fit-up | 2017-09-21 | 2017-10-22 | 2018-11-04 | 2019-01-28
Act | 2AI101PI01100-08160 | Not Started | Completed | EOF:NDE/PWHT/QC Checks of Pipes | 2017-09-24 | 2017-10-24 | 2018-11-12 | 2019-01-31
Act | 2AI101PI01100-08165 | Not Started | Completed | EOF:Install Permanent Supporting for Pipes | 2017-09-25 | 2017-10-30 | 2018-10-28 | 2018-12-05
Act | 2AI101PI01100-08170 | Not Started | Completed | EOF:Install piping valves | 2017-10-25 | 2017-10-31 | 2019-01-07 | 2019-03-13
Act | 2AI101PI01100-08156 | Not Started | Completed | EOF:Welding/Bolting of Pipes | 2017-09-23 | 2017-10-23 | 2018-11-10 | 2019-01-30
8 |  |  |  | EOF: AG Piping works: Foam Line on Tank 52-D-96
Act | 2AI101PI01100-08175 | Not Started | Completed | EOF:Installation of pipes | 2017-09-20 | 2017-10-19 | 2018-12-04 | 2019-03-26
Act | 2AI101PI01100-08180 | Not Started | Completed | EOF:Alignment/Fit-up | 2017-09-21 | 2017-10-22 | 2018-12-06 | 2019-03-28
Act | 2AI101PI01100-08185 | Not Started | Completed | EOF:NDE/PWHT/QC Checks of Pipes | 2017-09-24 | 2017-10-24 | 2018-12-09 | 2019-03-29
Act | 2AI101PI01100-08190 | Not Started | Completed | EOF:Install Permanent Supporting for Pipes | 2017-10-08 | 2017-10-25 | 2018-12-01 | 2019-01-09
Act | 2AI101PI01100-08195 | Not Started | Completed | EOF:Install piping valves | 2017-10-21 | 2017-10-26 | 2019-01-07 | 2019-04-10
Act | 2AI101PI01100-08181 | Not Started | Completed | EOF:Welding/Bolting of Pipes | 2017-09-23 | 2017-10-23 | 2018-12-06 | 2019-03-29
7 |  |  |  | Miscellanies Line
8 |  |  |  | EOF: AG Piping Work Near Trim Pump
Act | 2AI101PI01100-08325 | Not Started | Completed | EOF:Installation of pipes | 2017-07-19 | 2017-08-17 | 2018-06-04 | 2018-10-15
Act | 2AI101PI01100-08330 | Not Started | Completed | EOF:Alignment/Fit-up | 2017-07-29 | 2017-08-19 | 2018-06-04 | 2018-10-10
Act | 2AI101PI01100-08335 | Not Started | Completed | EOF:NDE/PWHT/QC Checks of Pipes | 2017-07-31 | 2017-08-21 | 2018-11-05 | 2019-02-06
Act | 2AI101PI01100-08340 | Not Started | Completed | EOF:Install Permanent Supporting for Pipes | 2017-08-05 | 2017-08-22 | 2018-09-03 | 2019-02-06
Act | 2AI101PI01100-08345 | Not Started | Completed | EOF:Install piping valves | 2017-09-14 | 2017-09-25 | 2018-09-01 | 2019-04-16
Act | 2AI101PI01100-08331 | Not Started | Completed | EOF:Welding/Bolting of Pipes | 2017-07-30 | 2017-08-20 | 2018-06-04 | 2018-10-10
8 |  |  |  | EOF: AG Piping Work: NearTank 52-D-94 Area
Act | 2AI101PI01100-08350 | Not Started | Completed | EOF:Installation of pipes | 2017-10-19 | 2017-11-20 | 2018-06-04 | 2019-01-09
Act | 2AI101PI01100-08355 | Not Started | Completed | EOF:Alignment/Fit-up | 2017-10-28 | 2017-11-21 | 2018-06-04 | 2019-01-10
Act | 2AI101PI01100-08360 | Not Started | Completed | EOF:NDE/PWHT/QC Checks of Pipes | 2017-10-30 | 2017-11-23 | 2018-09-03 | 2019-02-06
Act | 2AI101PI01100-08365 | Not Started | Completed | EOF:Install Permanent Supporting for Pipes | 2017-10-31 | 2017-11-25 | 2018-09-03 | 2019-02-06
Act | 2AI101PI01100-08370 | Not Started | Completed | EOF:Install piping valves | 2017-12-11 | 2017-12-25 | 2018-09-03 | 2019-02-06
Act | 2AI101PI01100-08356 | Not Started | Completed | EOF:Welding/Bolting of Pipes | 2017-10-29 | 2017-11-22 | 2018-01-13 | 2019-01-10
8 |  |  |  | EOF: AG Piping Work: Near Tank 52-D-93 Area
Act | 2AI101PI01100-08375 | Not Started | Completed | EOF:Installation of pipes | 2017-10-29 | 2017-11-29 | 2018-06-04 | 2019-01-09
Act | 2AI101PI01100-08380 | Not Started | Completed | EOF:Alignment/Fit-up | 2017-11-06 | 2017-11-30 | 2018-06-05 | 2019-01-09
Act | 2AI101PI01100-08385 | Not Started | Completed | EOF:NDE/PWHT/QC Checks of Pipes | 2017-11-08 | 2017-12-03 | 2018-06-04 | 2018-09-05
Act | 2AI101PI01100-08390 | Not Started | Completed | EOF:Install Permanent Supporting for Pipes | 2017-11-09 | 2017-12-04 | 2018-09-03 | 2018-09-05
Act | 2AI101PI01100-08395 | Not Started | Completed | EOF:Install piping valves | 2017-12-11 | 2017-12-25 | 2018-09-03 | 2018-09-05
Act | 2AI101PI01100-08381 | Not Started | Completed | EOF:Welding/Bolting of Pipes | 2017-11-07 | 2017-12-02 | 2018-06-04 | 2019-01-09
8 |  |  |  | EOF: AG Piping Work: Near Tank 52-D-95 Area
Act | 2AI101PI01100-08400 | Not Started | Completed | EOF:Installation of pipes | 2017-11-18 | 2017-12-19 | 2018-07-05 | 2019-01-09
Act | 2AI101PI01100-08405 | Not Started | Completed | EOF:Alignment/Fit-up | 2017-11-27 | 2017-12-21 | 2018-07-07 | 2019-01-09
Act | 2AI101PI01100-08410 | Not Started | Completed | EOF:NDE/PWHT/QC Checks of Pipes | 2017-11-28 | 2017-12-23 | 2018-08-02 | 2018-12-29
Act | 2AI101PI01100-08415 | Not Started | Completed | EOF:Install Permanent Supporting for Pipes | 2017-11-30 | 2017-12-25 | 2018-09-03 | 2019-01-01
Act | 2AI101PI01100-08420 | Not Started | Completed | EOF:Install piping valves | 2018-01-10 | 2018-01-24 | 2018-09-03 | 2019-01-04
Act | 2AI101PI01100-08406 | Not Started | Completed | EOF:Welding/Bolting of Pipes | 2017-11-27 | 2017-12-21 | 2018-07-07 | 2019-01-09
8 |  |  |  | EOF: AG Piping Work: Near Tank 52-D-96 Area
Act | 2AI101PI01100-08425 | Not Started | Completed | EOF:Installation of pipes | 2017-11-13 | 2017-12-14 | 2018-07-05 | 2019-01-12
Act | 2AI101PI01100-08430 | Not Started | Completed | EOF:Alignment/Fit-up | 2017-11-21 | 2017-12-16 | 2018-07-07 | 2019-01-13
Act | 2AI101PI01100-08435 | Not Started | Completed | EOF:NDE/PWHT/QC Checks of Pipes | 2017-11-23 | 2017-12-18 | 2018-08-02 | 2019-01-17
Act | 2AI101PI01100-08440 | Not Started | Completed | EOF:Install Permanent Supporting for Pipes | 2017-11-25 | 2017-12-19 | 2018-09-03 | 2019-01-14
Act | 2AI101PI01100-08445 | Not Started | Completed | EOF:Install piping valves | 2018-01-09 | 2018-01-23 | 2018-09-03 | 2019-01-15
Act | 2AI101PI01100-08431 | Not Started | Completed | EOF:Welding/Bolting of Pipes | 2017-11-22 | 2017-12-17 | 2018-07-07 | 2019-01-14
8 |  |  |  | EOF: AG Piping Work Near PIG
Act | 2AI101PI01100-08300 | Not Started | Completed | EOF:Installation of pipes | 2017-09-02 | 2017-09-25 | 2018-09-03 | 2019-03-13
Act | 2AI101PI01100-08305 | Not Started | Completed | EOF:Alignment/Fit-up | 2017-09-03 | 2017-09-27 | 2018-08-13 | 2018-08-24
Act | 2AI101PI01100-08310 | Not Started | Completed | EOF:NDE/PWHT/QC Checks of Pipes | 2017-09-05 | 2017-09-30 | 2018-11-05 | 2019-03-15
Act | 2AI101PI01100-08315 | Not Started | Completed | EOF:Install Permanent Supporting for Pipes | 2017-09-10 | 2017-10-01 | 2018-11-05 | 2018-12-05
Act | 2AI101PI01100-08320 | Not Started | Completed | EOF:Install piping valves | 2017-10-21 | 2017-10-26 | 2018-11-05 | 2019-03-20
Act | 2AI101PI01100-08306 | Not Started | Completed | EOF:Welding/Bolting of Pipes | 2017-09-04 | 2017-09-28 | 2018-08-15 | 2018-08-24
7 |  |  |  | EOF: AG Piping Work: Oily Water Drine Line
8 |  |  |  | EOF: AG Oily Water Drine Line For Tank 52-D-94 Area
Act | 2AI101PI01100-08450 | Not Started | Completed | EOF:Installation of pipes | 2017-11-25 | 2017-12-19 | 2017-12-11 | 2019-01-10
Act | 2AI101PI01100-08455 | Not Started | Completed | EOF:Alignment/Fit-up | 2017-11-27 | 2017-12-20 | 2018-05-07 | 2019-01-14
Act | 2AI101PI01100-08460 | Not Started | Completed | EOF:NDE/PWHT/QC Checks of Pipes | 2017-11-28 | 2017-12-21 | 2019-01-07 | 2019-01-27
Act | 2AI101PI01100-08465 | Not Started | Completed | EOF:Install Permanent Supporting for Pipes | 2017-12-05 | 2017-12-23 | 2019-01-07 | 2019-01-09
Act | 2AI101PI01100-08470 | Not Started | Completed | EOF:Install piping valves | 2017-12-18 | 2017-12-24 | 2019-01-07 | 2019-01-27
Act | 2AI101PI01100-08456 | Not Started | Completed | EOF:Welding/Bolting of Pipes | 2017-11-27 | 2017-12-20 | 2018-07-02 | 2019-01-16
8 |  |  |  | EOF: AG Oily Water Drine Line For Tank 52-D-93 Area
Act | 2AI101PI01100-08475 | Not Started | Completed | EOF:Installation of pipes | 2017-11-02 | 2017-11-27 | 2018-06-04 | 2018-11-07
Act | 2AI101PI01100-08480 | Not Started | Completed | EOF:Alignment/Fit-up | 2017-11-05 | 2017-11-28 | 2018-06-04 | 2018-12-05
Act | 2AI101PI01100-08485 | Not Started | Completed | EOF:NDE/PWHT/QC Checks of Pipes | 2017-11-07 | 2017-11-30 | 2018-06-10 | 2019-01-04
Act | 2AI101PI01100-08490 | Not Started | Completed | EOF:Install Permanent Supporting for Pipes | 2017-11-14 | 2017-12-02 | 2018-11-05 | 2019-01-05
Act | 2AI101PI01100-08495 | Not Started | Completed | EOF:Install piping valves | 2017-11-27 | 2017-12-03 | 2018-11-05 | 2019-01-06
Act | 2AI101PI01100-08481 | Not Started | Completed | EOF:Welding/Bolting of Pipes | 2017-11-06 | 2017-11-29 | 2018-06-04 | 2018-12-05
8 |  |  |  | EOF: AG Oily Water Drine Line For Tank 52-D-95 Area
Act | 2AI101PI01100-08500 | Not Started | Completed | EOF:Installation of pipes | 2017-11-28 | 2017-12-19 | 2018-06-23 | 2019-04-10
Act | 2AI101PI01100-08505 | Not Started | Completed | EOF:Alignment/Fit-up | 2017-12-03 | 2017-12-20 | 2018-06-24 | 2019-04-10
Act | 2AI101PI01100-08510 | Not Started | Completed | EOF:NDE/PWHT/QC Checks of Pipes | 2017-12-05 | 2017-12-23 | 2018-11-05 | 2019-03-30
Act | 2AI101PI01100-08515 | Not Started | Completed | EOF:Install Permanent Supporting for Pipes | 2017-12-10 | 2017-12-24 | 2018-11-05 | 2019-03-30
Act | 2AI101PI01100-08520 | Not Started | Completed | EOF:Install piping valves | 2017-12-19 | 2017-12-25 | 2018-11-05 | 2019-04-02
Act | 2AI101PI01100-08506 | Not Started | Completed | EOF:Welding/Bolting of Pipes | 2017-12-04 | 2017-12-21 | 2018-06-25 | 2019-04-10
8 |  |  |  | EOF: AG Oily Water Drine Line For Tank 52-D-96 Area
Act | 2AI101PI01100-08525 | Not Started | Completed | EOF:Installation of pipes | 2017-11-25 | 2017-12-19 | 2018-06-28 | 2019-01-15
Act | 2AI101PI01100-08530 | Not Started | Completed | EOF:Alignment/Fit-up | 2017-11-27 | 2017-12-20 | 2018-06-28 | 2019-01-20
Act | 2AI101PI01100-08535 | Not Started | Completed | EOF:NDE/PWHT/QC Checks of Pipes | 2017-11-29 | 2017-12-23 | 2018-11-05 | 2019-01-24
Act | 2AI101PI01100-08540 | Not Started | Completed | EOF:Install Permanent Supporting for Pipes | 2017-12-06 | 2017-12-24 | 2018-11-05 | 2019-01-25
Act | 2AI101PI01100-08545 | Not Started | Completed | EOF:Install piping valves | 2017-12-19 | 2017-12-25 | 2018-11-05 | 2019-01-24
Act | 2AI101PI01100-08531 | Not Started | Completed | EOF:Welding/Bolting of Pipes | 2017-11-28 | 2017-12-21 | 2018-06-28 | 2019-01-22
7 |  |  |  | Other Line
Act | 2AI101PI01100-08025 | Not Started | Completed | EOF:Installation of pipes | 2017-06-03 | 2017-08-29 | 2019-02-04 | 2019-02-06
Act | 2AI101PI01100-08030 | Not Started | Completed | EOF:Alignment/Fit-up | 2017-06-11 | 2017-09-04 | 2019-02-04 | 2019-02-06
Act | 2AI101PI01100-08035 | Not Started | Completed | EOF:NDE/PWHT/QC Checks of Pipes | 2017-06-15 | 2017-09-07 | 2019-02-04 | 2019-02-06
Act | 2AI101PI01100-08040 | Not Started | Completed | EOF:Install Permanent Supporting for Pipes | 2017-07-06 | 2017-09-12 | 2019-02-04 | 2019-02-06
Act | 2AI101PI01100-08045 | Not Started | Completed | EOF:Install piping valves | 2017-08-10 | 2017-09-21 | 2019-02-04 | 2019-02-06
Act | 2AI101PI01100-08031 | Not Started | Completed | EOF:Welding/Bolting of Pipes | 2017-06-12 | 2017-09-05 | 2019-02-04 | 2019-02-06
6 |  |  |  | EOF: AG Piping works for Metallic (SS/SDSS)
Act | 2AI101PI01100-08050 | Not Started | Completed | EOF:Installation of pipes | 2017-06-03 | 2017-08-29 | 2018-10-02 | 2019-03-20
Act | 2AI101PI01100-08055 | Not Started | Completed | EOF:Alignment/Fit-up | 2017-06-11 | 2017-09-04 | 2018-06-23 | 2019-03-22
Act | 2AI101PI01100-08060 | Not Started | Completed | EOF:NDE/PWHT/QC Checks of Pipes | 2017-06-18 | 2017-09-10 | 2018-09-03 | 2019-03-26
Act | 2AI101PI01100-08065 | Not Started | Completed | EOF:Install Permanent Supporting for Pipes | 2017-07-17 | 2017-09-16 | 2018-10-08 | 2019-03-28
Act | 2AI101PI01100-08070 | Not Started | Completed | EOF:Install piping valves | 2017-09-16 | 2017-10-21 | 2018-10-08 | 2019-03-29
Act | 2AI101PI01100-08056 | Not Started | Completed | EOF:Welding/Bolting of Pipes | 2017-06-12 | 2017-09-05 | 2018-06-23 | 2019-03-24
Act | 2AI101PI01100-08010 | Not Started | Completed | EOF: AG Piping works for Metallic (SS/SDSS) | 2017-06-03 | 2017-10-21 | 2018-06-23 | 2019-03-29
6 |  |  |  | EOF: AG Piping works for Metallic (CU-NI & Other Alloy)
5 |  |  |  | EOF: Hydrotesting
Act | 2AI101PI01300 | Not Started | In Progress | EOF: Hydrotesting | 2017-07-04 | 2018-01-10 | 2017-05-01
6 |  |  |  | EOF: Pressure testing for Non Metallic
Act | 2AI101PI01300-08000 | Not Started | Completed | EOF: Pressure testing for Non Metallic | 2017-07-04 | 2017-10-29 | 2017-05-01 | 2019-04-16
7 |  |  |  | EOF: Hydrotesting-Effluent Water Line
Act | 2AI101PI01300-08100 | Not Started | Completed | EOF:Test pack preparation & Ready for Test | 2017-07-08 | 2017-07-13 | 2019-02-04 | 2019-02-06
Act | 2AI101PI01300-08105 | Not Started | Completed | EOF:Reinstatement | 2017-07-19 | 2017-07-24 | 2019-02-04 | 2019-02-06
Act | 2AI101PI01300-08101 | Not Started | Completed | EOF:Pressure testing & Approval | 2017-07-09 | 2017-07-23 | 2019-02-04 | 2019-02-06
Act | 2AI101PI01300-08106 | Not Started | Completed | EOF:Flange management | 2017-07-20 | 2017-07-25 | 2019-02-04 | 2019-02-06
7 |  |  |  | EOF: Hydrotesting-Oily Water Line
Act | 2AI101PI01300-08080 | Not Started | Completed | EOF:Test pack preparation & Ready for Test | 2017-07-04 | 2017-07-10 | 2018-03-10 | 2019-04-07
Act | 2AI101PI01300-08085 | Not Started | Completed | EOF:Reinstatement | 2017-07-25 | 2017-07-31 | 2018-02-05 | 2019-04-09
Act | 2AI101PI01300-08081 | Not Started | Completed | EOF:Pressure testing & Approval | 2017-07-10 | 2017-07-25 | 2018-03-20 | 2019-04-07
Act | 2AI101PI01300-08086 | Not Started | Completed | EOF:Flange management | 2017-07-31 | 2017-08-06 | 2018-02-05 | 2019-04-09
7 |  |  |  | Other Lines
Act | 2AI101PI01300-08001 | Not Started | Completed | EOF:Test pack preparation & Ready for Test | 2017-10-11 | 2017-10-17 | 2017-05-01 | 2019-04-16
Act | 2AI101PI01300-08006 | Not Started | Completed | EOF:Reinstatement | 2017-10-23 | 2017-10-28 | 2017-05-06 | 2019-04-16
Act | 2AI101PI01300-08002 | Not Started | Completed | EOF:Pressure testing & Approval | 2017-10-12 | 2017-10-26 | 2017-05-06 | 2019-04-16
Act | 2AI101PI01300-08007 | Not Started | Completed | EOF:Flange management | 2017-10-24 | 2017-10-29 | 2017-05-06 | 2019-04-16
6 |  |  |  | EOF: Pressure testing for Metallic (CS/LTCS)
Act | 2AI101PI01300-08005 | Not Started | In Progress | EOF: Pressure testing for Metallic (CS/LTCS) | 2017-08-12 | 2018-01-10 | 2017-05-04
Act | 2AI101PI01300-08115 | Not Started | Completed | EOF:Reinstatement | 2017-08-30 | 2018-01-08 | 2019-04-08 | 2019-04-10
Act | 2AI101PI01300-08110 | Not Started | Completed | EOF:Pressure testing & Approval | 2017-08-29 | 2018-01-06 | 2019-04-08 | 2019-04-10
Act | 2AI101PI01300-08120 | Not Started | Completed | EOF:Flange management | 2017-09-09 | 2018-01-10 | 2019-04-08 | 2019-04-10
7 |  |  |  | EOF: Hydrotesting-Drin Line
Act | 2AI101PI01300-08090 | Not Started | Completed | EOF:Test pack preparation & Ready for Test | 2017-11-28 | 2017-12-06 | 2018-03-18 | 2019-01-07
Act | 2AI101PI01300-08095 | Not Started | In Progress | EOF:Reinstatement | 2017-12-14 | 2017-12-26 | 2018-04-02
Act | 2AI101PI01300-08091 | Not Started | Completed | EOF:Pressure testing & Approval | 2017-11-30 | 2017-12-24 | 2018-03-20 | 2019-01-07
Act | 2AI101PI01300-08096 | Not Started | Completed | EOF:Flange management | 2017-12-14 | 2017-12-26 | 2018-04-02 | 2019-01-10
7 |  |  |  | EOF: Hydrotesting-Foam Line
Act | 2AI101PI01300-08040 | Not Started | Completed | EOF:Test pack preparation & Ready for Test | 2017-08-12 | 2017-11-01 | 2017-10-17 | 2019-03-27
Act | 2AI101PI01300-08045 | Not Started | In Progress | EOF:Reinstatement | 2017-08-14 | 2017-11-04 | 2017-12-04
Act | 2AI101PI01300-08041 | Not Started | Completed | EOF:Pressure testing & Approval | 2017-08-13 | 2017-11-02 | 2017-10-18 | 2019-03-29
Act | 2AI101PI01300-08046 | Not Started | Completed | EOF:Flange management | 2017-08-15 | 2017-11-05 | 2017-12-04 | 2019-04-01
7 |  |  |  | EOF: Hydrotesting-Fire Water Line
Act | 2AI101PI01300-08050 | Not Started | Completed | EOF:Test pack preparation & Ready for Test | 2017-09-17 | 2017-09-25 | 2017-05-04 | 2019-03-06
Act | 2AI101PI01300-08055 | Not Started | In Progress | EOF:Reinstatement | 2017-09-25 | 2017-10-12 | 2017-05-07
Act | 2AI101PI01300-08051 | Not Started | Completed | EOF:Pressure testing & Approval | 2017-09-18 | 2017-10-11 | 2017-05-07 | 2019-03-17
Act | 2AI101PI01300-08056 | Not Started | Completed | EOF:Flange management | 2017-09-26 | 2017-10-14 | 2017-05-07 | 2019-03-20
7 |  |  |  | EOF: Hydrotesting-Loading Line
Act | 2AI101PI01300-08060 | Not Started | Completed | EOF:Test pack preparation & Ready for Test | 2017-09-21 | 2017-10-03 | 2017-12-10 | 2019-03-21
Act | 2AI101PI01300-08065 | Not Started | In Progress | EOF:Reinstatement | 2017-10-16 | 2017-10-28 | 2018-01-01
Act | 2AI101PI01300-08061 | Not Started | Completed | EOF:Pressure testing & Approval | 2017-10-03 | 2017-10-26 | 2017-12-17 | 2019-03-22
Act | 2AI101PI01300-08066 | Not Started | Completed | EOF:Flange management | 2017-10-17 | 2017-10-29 | 2018-01-01 | 2019-03-25
7 |  |  |  | EOF: Hydrotesting-Fillling Line
Act | 2AI101PI01300-08070 | Not Started | Completed | EOF:Test pack preparation & Ready for Test | 2017-09-17 | 2017-09-28 | 2018-04-02 | 2019-01-15
Act | 2AI101PI01300-08075 | Not Started | In Progress | EOF:Reinstatement | 2017-10-05 | 2017-10-17 | 2018-04-13
Act | 2AI101PI01300-08071 | Not Started | Completed | EOF:Pressure testing & Approval | 2017-09-28 | 2017-10-16 | 2018-04-08 | 2019-01-16
Act | 2AI101PI01300-08076 | Not Started | Completed | EOF:Flange management | 2017-10-07 | 2017-10-18 | 2018-04-13 | 2019-01-19
7 |  |  |  | Miscellanies Line
8 |  |  |  | EOF: AG Piping Work Near Trim Pump
Act | 2AI101PI01300-08400 | Not Started | Completed | EOF:Test pack preparation & Ready for Test | 2017-08-21 | 2017-08-29 | 2019-01-12 | 2019-03-19
Act | 2AI101PI01300-08410 | Not Started | In Progress | EOF:Reinstatement | 2017-08-30 | 2017-09-13 | 2019-04-08
Act | 2AI101PI01300-08405 | Not Started | Completed | EOF:Pressure testing & Approval | 2017-08-29 | 2017-09-12 | 2019-01-14 | 2019-03-20
Act | 2AI101PI01300-08415 | Not Started | Completed | EOF:Flange management | 2017-09-09 | 2017-09-14 | 2019-04-08 | 2019-04-10
8 |  |  |  | EOF: AG Piping Work: NearTank 52-D-94 Area
Act | 2AI101PI01300-08420 | Not Started | Completed | EOF:Test pack preparation & Ready for Test | 2017-11-23 | 2017-11-29 | 2018-11-21 | 2019-03-02
Act | 2AI101PI01300-08430 | Not Started | In Progress | EOF:Reinstatement | 2017-12-03 | 2017-12-14 | 2019-01-20
Act | 2AI101PI01300-08425 | Not Started | Completed | EOF:Pressure testing & Approval | 2017-11-29 | 2017-12-11 | 2018-11-21 | 2019-03-05
Act | 2AI101PI01300-08435 | Not Started | Completed | EOF:Flange management | 2017-12-10 | 2017-12-16 | 2018-11-25 | 2019-03-06
8 |  |  |  | EOF: AG Piping Work: Near Tank 52-D-93 Area
Act | 2AI101PI01300-08440 | Not Started | Completed | EOF:Test pack preparation & Ready for Test | 2017-12-03 | 2017-12-09 | 2018-10-01 | 2019-03-05
Act | 2AI101PI01300-08450 | Not Started | In Progress | EOF:Reinstatement | 2017-12-10 | 2017-12-21 | 2019-03-10
Act | 2AI101PI01300-08445 | Not Started | Completed | EOF:Pressure testing & Approval | 2017-12-09 | 2017-12-20 | 2018-10-09 | 2019-03-05
Act | 2AI101PI01300-08455 | Not Started | Completed | EOF:Flange management | 2017-12-17 | 2017-12-23 | 2018-10-12 | 2019-03-08
8 |  |  |  | EOF: AG Piping Work: Near Tank 52-D-95 Area
Act | 2AI101PI01300-08460 | Not Started | Completed | EOF:Test pack preparation & Ready for Test | 2017-12-23 | 2017-12-28 | 2018-12-01 | 2019-04-06
Act | 2AI101PI01300-08470 | Not Started | In Progress | EOF:Reinstatement | 2017-12-27 | 2018-01-08 | 2019-01-21
Act | 2AI101PI01300-08465 | Not Started | Completed | EOF:Pressure testing & Approval | 2017-12-25 | 2018-01-06 | 2018-12-02 | 2019-04-07
Act | 2AI101PI01300-08475 | Not Started | Completed | EOF:Flange management | 2018-01-04 | 2018-01-10 | 2019-01-21 | 2019-04-11
8 |  |  |  | EOF: AG Piping Work: Near Tank 52-D-96 Area
Act | 2AI101PI01300-08480 | Not Started | Completed | EOF:Test pack preparation & Ready for Test | 2017-12-18 | 2017-12-24 | 2018-11-29 | 2019-03-28
Act | 2AI101PI01300-08490 | Not Started | In Progress | EOF:Reinstatement | 2017-12-26 | 2018-01-07 | 2019-01-26
Act | 2AI101PI01300-08485 | Not Started | Completed | EOF:Pressure testing & Approval | 2017-12-24 | 2018-01-04 | 2018-12-01 | 2019-04-02
Act | 2AI101PI01300-08495 | Not Started | Completed | EOF:Flange management | 2018-01-03 | 2018-01-09 | 2019-01-26 | 2019-04-06
8 |  |  |  | EOF: AG Piping Work Near PIG
Act | 2AI101PI01300-08500 | Not Started | Completed | EOF:Test pack preparation & Ready for Test | 2017-09-30 | 2017-10-05 | 2019-03-09 | 2019-03-21
Act | 2AI101PI01300-08510 | Not Started | In Progress | EOF:Reinstatement | 2017-10-08 | 2017-10-19 | 2019-04-08
Act | 2AI101PI01300-08505 | Not Started | Completed | EOF:Pressure testing & Approval | 2017-10-05 | 2017-10-17 | 2019-03-09 | 2019-03-22
Act | 2AI101PI01300-08515 | Not Started | Completed | EOF:Flange management | 2017-10-15 | 2017-10-21 | 2019-04-08 | 2019-04-10
7 |  |  |  | Other Lines
Act | 2AI101PI01300-08011 | Not Started | Completed | EOF:Test pack preparation & Ready for Test | 2017-08-24 | 2017-09-17 | 2019-04-08 | 2019-04-10
Act | 2AI101PI01300-08016 | Not Started | Completed | EOF:Reinstatement | 2017-09-03 | 2017-09-26 | 2019-03-29 | 2019-03-29
Act | 2AI101PI01300-08012 | Not Started | Completed | EOF:Pressure testing & Approval | 2017-08-26 | 2017-09-25 | 2019-04-08 | 2019-04-10
Act | 2AI101PI01300-08017 | Not Started | Completed | EOF:Flange management | 2017-09-04 | 2017-09-27 | 2019-03-30 | 2019-03-30
6 |  |  |  | EOF: Pressure testing for Metallic (SS/SDSS)
Act | 2AI101PI01300-08020 | Not Started | Completed | EOF:Test pack preparation & Ready for Test | 2017-11-30 | 2017-12-06 | 2018-08-06 | 2019-03-12
Act | 2AI101PI01300-08025 | Not Started | Completed | EOF:Reinstatement | 2017-12-10 | 2017-12-24 | 2018-09-13 | 2019-03-14
Act | 2AI101PI01300-08021 | Not Started | Completed | EOF:Pressure testing & Approval | 2017-12-02 | 2017-12-23 | 2018-09-12 | 2019-03-12
Act | 2AI101PI01300-08026 | Not Started | Completed | EOF:Flange management | 2017-12-11 | 2017-12-25 | 2018-09-13 | 2019-03-16
Act | 2AI101PI01300-08010 | Not Started | Completed | EOF: Pressure testing for Metallic (SS/SDSS) | 2017-11-30 | 2017-12-25 | 2018-08-06 | 2019-03-16
6 |  |  |  | EOF: Pressure testing for Metallic (CU-NI & Other Alloy)
4 |  |  |  | ELECTRICAL
5 |  |  |  | EOF: UG Electrical cable Works
Act | 2AI101EL01000 | Not Started | In Progress | EOF: UG Electrical cable Works | 2017-02-02 | 2017-12-16 | 2017-01-28
6 |  |  |  | EOF: UG Electrical cable Works
Act | 2AI101EL01000-08000 | Not Started | In Progress | EOF: UG Electrical cable Works | 2017-02-02 | 2017-12-16 | 2017-01-28
7 |  |  |  | EOF: UG Electrical cable Works - LV
Act | 2AI101EL01000-08001 | Not Started | Completed | EOF: Cable Drum Checks & Transport to Site- LV Cables | 2017-02-02 | 2017-07-22 | 2017-01-28 | 2018-10-20
Act | 2AI101EL01000-08005 | Not Started | Completed | EOF: Cable Pulling - LV Cables | 2017-02-05 | 2017-07-24 | 2017-01-28 | 2019-02-02
Act | 2AI101EL01000-08010 | Not Started | Completed | EOF: Cable Dressing & Fastening - LV Cables | 2017-02-07 | 2017-07-26 | 2017-04-13 | 2019-02-02
Act | 2AI101EL01000-08040 | Not Started | Completed | EOF: Cable Marking | 2017-02-09 | 2017-07-29 | 2017-05-13 | 2019-02-03
7 |  |  |  | EOF: UG Electrical cable Works - HV
Act | 2AI101EL01000-08045 | Not Started | Completed | EOF: Cable Drum Checks & Transport to Site- HV Cables | 2017-02-28 | 2017-09-26 | 2017-09-04 | 2017-09-26
Act | 2AI101EL01000-08050 | Not Started | Completed | EOF: Cable Pulling - HV Cables | 2017-02-28 | 2017-09-26 | 2017-09-04 | 2017-09-26
Act | 2AI101EL01000-08055 | Not Started | Completed | EOF: Cable Dressing & Fastening - HV Cables | 2017-08-26 | 2017-09-30 | 2017-08-26 | 2017-09-30
Act | 2AI101EL01000-08060 | Not Started | Completed | EOF: Cable Marking | 2017-03-05 | 2017-10-01 | 2017-09-04 | 2017-10-01
Act | 2AI101EL01000-08051 | Not Started | Completed | EOF: Cable Spicing - HV | 2017-03-02 | 2017-09-28 | 2017-09-04 | 2017-09-28
7 |  |  |  | EOF: UG Electrical cable Works - Earthing
Act | 2AI101EL01000-08025 | Not Started | In Progress | EOF: Cable Pulling - Base/Insulated earthing | 2017-05-16 | 2017-11-07 | 2017-07-03
Act | 2AI101EL01000-08030 | Not Started | Completed | EOF: Base/Insulated earthing cable thermoweld jointing/connections | 2017-05-20 | 2017-11-11 | 2017-07-05 | 2018-05-16
Act | 2AI101EL01000-08070 | Not Started | Completed | EOF: Earth Pit and Earth Bar Installation | 2017-11-11 | 2017-12-16 | 2018-05-29 | 2019-02-15
Act | 2AI101EL01000-08024 | Not Started | Completed | EOF: Cable Drum Checks & Transport to Site- earthing Cables | 2017-05-13 | 2017-11-04 | 2017-07-03 | 2019-04-10
5 |  |  |  | EOF: AG Cable laying, CP, DB'S/JB, Panels, Lighting Pole, Fixtures, Cable Glaning & Termination
Act | 2AI101EL01100 | Not Started | In Progress | EOF:AG Cable laying, CP, DB'S/JB, Panels, Lighting Pole, Fixtures, Cable Glaning & Termination Electrical Works | 2016-07-19 | 2017-12-31 | 2016-08-04
6 |  |  |  | EOF:Install Electrical Cable trays & Supports
6 |  |  |  | EOF:Installation of Lighting Poles & Fixtures
Act | 2AI101EL01100-08040 | Not Started | In Progress | EOF:Installation of supports | 2017-07-13 | 2017-12-21 | 2017-03-06
Act | 2AI101EL01100-08045 | Not Started | In Progress | EOF:Install light pole | 2017-07-17 | 2017-12-25 | 2017-11-16
Act | 2AI101EL01100-08050 | Not Started | In Progress | EOF:Install Lighting fixtures | 2017-07-23 | 2017-12-31 | 2017-11-16
Act | 2AI101EL01100-08015 | Not Started | In Progress | EOF:Installation of Lighting Poles & Fixtures | 2017-07-13 | 2017-12-31 | 2017-03-06
6 |  |  |  | EOF:Installation of DB'S / JB & Panels
Act | 2AI101EL01100-08140 | Not Started | Completed | EOF:Install JB's/DB's | 2017-08-03 | 2017-10-31 | 2017-12-02 | 2018-10-09
Act | 2AI101EL01100-08150 | Not Started | Completed | EOF:Leveling & Grouting | 2017-08-19 | 2017-11-02 | 2018-04-02 | 2018-10-10
Act | 2AI101EL01100-08138 | Not Started | Completed | EOF:Installation of supports | 2017-08-01 | 2017-10-29 | 2017-11-26 | 2018-10-08
Act | 2AI101EL01100-08005 | Not Started | Completed | EOF:Installation of DB'S / JB & Panels | 2017-08-01 | 2017-11-02 | 2017-11-26 | 2018-10-10
6 |  |  |  | EOF:AG Cable Laying
6 |  |  |  | EOF: CP Works
Act | 2AI101EL01100-08020 | Not Started | Completed | EOF: CP Works | 2016-07-19 | 2017-07-06 | 2016-08-04 | 2019-03-15
7 |  |  |  | EOF:Cathodic Prottection for Tank 52-D-93
Act | 2AI101EL01100-08055 | Not Started | Completed | EOF:Installation of CP Anodes (incl. civil works) | 2016-07-24 | 2016-08-03 | 2016-08-12 | 2016-08-24
Act | 2AI101EL01100-08060 | Not Started | Completed | EOF:Installation of Transformer/JBs | 2017-06-17 | 2017-07-04 | 2018-09-04 | 2019-03-14
Act | 2AI101EL01100-08065 | Not Started | Completed | EOF:Cable laying & Termination | 2017-06-07 | 2017-07-06 | 2018-05-16 | 2019-03-14
7 |  |  |  | EOF:Cathodic Prottection for Tank 52-D-94
Act | 2AI101EL01100-08070 | Not Started | Completed | EOF:Installation of CP Anodes (incl. civil works) | 2016-07-19 | 2016-08-02 | 2016-08-04 | 2016-08-14
Act | 2AI101EL01100-08075 | Not Started | Completed | EOF:Installation of Transformer/JBs | 2017-06-17 | 2017-06-26 | 2018-09-04 | 2018-09-27
Act | 2AI101EL01100-08080 | Not Started | Completed | EOF:Cable laying & Termination | 2017-05-30 | 2017-06-28 | 2018-05-15 | 2019-03-15
7 |  |  |  | EOF:Cathodic Prottection for Tank 52-D-95
Act | 2AI101EL01100-08085 | Not Started | Completed | EOF:Installation of CP Anodes (incl. civil works) | 2016-08-29 | 2016-09-07 | 2016-09-26 | 2016-09-29
Act | 2AI101EL01100-08090 | Not Started | Completed | EOF:Installation of Transformer/JBs | 2017-06-17 | 2017-06-26 | 2018-11-05 | 2019-02-06
Act | 2AI101EL01100-08095 | Not Started | Completed | EOF:Cable laying & Termination | 2017-05-30 | 2017-06-28 | 2018-05-15 | 2019-03-15
7 |  |  |  | EOF:Cathodic Prottection for Tank 52-D-96
Act | 2AI101EL01100-08100 | Not Started | Completed | EOF:Installation of CP Anodes (incl. civil works) | 2016-08-28 | 2016-09-07 | 2016-10-24 | 2016-10-31
Act | 2AI101EL01100-08105 | Not Started | Completed | EOF:Installation of Transformer/JBs | 2017-06-17 | 2017-06-26 | 2018-11-05 | 2019-02-06
Act | 2AI101EL01100-08110 | Not Started | Completed | EOF:Cable laying & Termination | 2017-05-30 | 2017-06-28 | 2018-05-15 | 2019-03-15
6 |  |  |  | EOF:Cable Glanding & Terminations
Act | 2AI101EL01100-08115 | Not Started | In Progress | EOF:Cable Glanding | 2017-07-27 | 2017-10-05 | 2018-11-05
Act | 2AI101EL01100-08120 | Not Started | In Progress | EOF:Hi-Po test & Terminations | 2017-10-05 | 2017-11-27 | 2018-11-05
Act | 2AI101EL01100-08113 | Not Started | Completed | EOF: Cable Laying | 2017-04-25 | 2017-09-24 | 2018-04-02 | 2019-01-09
Act | 2AI101EL01100-08130 | Not Started | In Progress | EOF:Tagging | 2017-11-27 | 2017-12-20 | 2018-09-25
Act | 2AI101EL01100-08025 | Not Started | In Progress | EOF:Cable Glanding & Terminations | 2017-04-25 | 2017-12-20 | 2018-04-02
4 |  |  |  | INSTRUMENTATION
5 |  |  |  | EOF: UG Instrumentation cable works
Act | 2AI101IC01000 | Not Started | Completed | EOF: UG Instrumentation cable works | 2017-03-26 | 2017-10-02 | 2017-04-10 | 2019-04-25
6 |  |  |  | EOF: UG Instrumentation cable works
Act | 2AI101IC01000-08001 | Not Started | Completed | Cable Drum Checks & Transport to Site | 2017-03-26 | 2017-09-28 | 2017-04-10 | 2019-04-10
Act | 2AI101IC01000-08010 | Not Started | Completed | Cable Pulling | 2017-03-27 | 2017-09-30 | 2017-04-16 | 2019-04-10
Act | 2AI101IC01000-08020 | Not Started | Completed | Cable Dressing & Fastening | 2017-03-28 | 2017-10-01 | 2017-04-16 | 2019-04-10
Act | 2AI101IC01000-08030 | Not Started | Completed | Cable Marking | 2017-03-29 | 2017-10-02 | 2017-04-29 | 2019-04-25
Act | 2AI101IC01000-08000 | Not Started | Completed | EOF: UG Instrumentation cable works | 2017-03-26 | 2017-10-02 | 2017-04-10 | 2019-04-25
5 |  |  |  | EOF: AG cable laying,Tubing, Field&Inline Inst. Installation, Cable Glading &Termination (Incl. F&G)
Act | 2AI101IC01100 | Not Started | In Progress | EOF: AG cable laying,Tubing, Field&Inline Inst. Installation, Cable Glading & Termination (incl. F&G System) | 2017-02-27 | 2017-12-31 | 2017-06-27
6 |  |  |  | EOF: Install Instrument Cable trays & Supports
Act | 2AI101IC01100-08001 | Not Started | Completed | EOF:Fabricate Tray Supports | 2017-02-27 | 2017-09-25 | 2017-06-27 | 2019-03-06
Act | 2AI101IC01100-08011 | Not Started | Completed | EOF:Install Tray Supports | 2017-03-01 | 2017-09-27 | 2017-06-27 | 2019-03-06
Act | 2AI101IC01100-08100 | Not Started | Completed | EOF:Install Cable Trays | 2017-03-05 | 2017-10-01 | 2017-06-28 | 2018-07-26
Act | 2AI101IC01100-08110 | Not Started | Completed | EOF:Install Cable Tray Covers | 2017-05-21 | 2017-10-19 | 2018-08-29 | 2019-03-06
Act | 2AI101IC01100-08000 | Not Started | Completed | EOF:Install Instrument Cable trays & Supports | 2017-02-27 | 2017-10-19 | 2017-06-27 | 2019-03-06
6 |  |  |  | EOF: Install Instrument JBs
Act | 2AI101IC01100-08120 | Not Started | In Progress | EOF: Supports Installation | 2017-05-30 | 2017-12-03 | 2018-01-06
Act | 2AI101IC01100-08130 | Not Started | In Progress | EOF: Mounting JB's | 2017-06-11 | 2017-12-14 | 2018-01-06
Act | 2AI101IC01100-08140 | Not Started | In Progress | EOF: Leveling & Grouting | 2017-06-22 | 2017-12-26 | 2018-01-06
Act | 2AI101IC01100-08005 | Not Started | In Progress | EOF:Install Instrument JBs | 2017-05-30 | 2017-12-26 | 2018-01-06
6 |  |  |  | EOF: AG cable laying
Act | 2AI101IC01100-08006 | Not Started | In Progress | EOF:AG Cable laying | 2017-03-18 | 2017-10-14 | 2018-08-29
Act | 2AI101IC01100-08004 | Not Started | Completed | EOF:Cable Drum Checks & Transport to Site | 2017-03-14 | 2017-10-10 | 2018-08-29 | 2019-04-10
Act | 2AI101IC01100-08035 | Not Started | In Progress | EOF:Cable Dressing & Fastening | 2017-03-21 | 2017-10-17 | 2018-08-29
Act | 2AI101IC01100-08045 | Not Started | Completed | EOF:Cable Marking | 2017-06-11 | 2017-10-29 | 2018-05-07 | 2018-05-09
Act | 2AI101IC01100-08010 | Not Started | In Progress | EOF: AG cable laying | 2017-03-14 | 2017-10-29 | 2018-05-07
6 |  |  |  | EOF: Calibration of Valves/Instruments
Act | 2AI101IC01100-08021 | Not Started | Completed | Receipt of Valves/Instruments at Calibration shop | 2017-09-25 | 2017-12-18 | 2018-07-28 | 2019-04-10
Act | 2AI101IC01100-08031 | Not Started | Completed | Testing of Valves/Instruments at Calibration shop | 2017-09-28 | 2017-12-21 | 2018-07-28 | 2019-04-15
Act | 2AI101IC01100-08040 | Not Started | Completed | QC checks & clearance for installation | 2017-10-01 | 2017-12-24 | 2018-07-29 | 2019-04-16
Act | 2AI101IC01100-08015 | Not Started | Completed | EOF: Calibration of Valves/Instruments | 2017-09-25 | 2017-12-24 | 2018-07-28 | 2019-04-16
6 |  |  |  | EOF: Install Inst. Valves/Inline mounted Instruments
Act | 2AI101IC01100-08050 | Not Started | In Progress | EOF: Mechanical/Piping Clearence and preparatory works | 2017-09-28 | 2017-12-25 | 2018-08-06
Act | 2AI101IC01100-08060 | Not Started | In Progress | EOF: Installation of Valves/Inline Instruments | 2017-10-04 | 2017-12-28 | 2018-08-06
Act | 2AI101IC01100-08020 | Not Started | In Progress | EOF: Install Inst. Valves/Inline mounted Instruments | 2017-09-28 | 2017-12-28 | 2018-08-06
6 |  |  |  | EOF: Fabricate/Install Inst. tubing & Instrument Hookup
Act | 2AI101IC01100-08070 | Not Started | Completed | EOF: Fabrication & Installation of Support Structures | 2017-10-03 | 2017-12-26 | 2018-04-21 | 2018-04-25
Act | 2AI101IC01100-08080 | Not Started | In Progress | EOF: Installation of Instruments on Support Structures | 2017-10-05 | 2017-12-28 | 2018-04-21
Act | 2AI101IC01100-08090 | Not Started | In Progress | EOF: Alignment/Levelling and grouting | 2017-10-09 | 2017-12-31 | 2018-04-21
Act | 2AI101IC01100-08025 | Not Started | In Progress | EOF: Fabricate/Install Inst. tubing & Instrument Hookup | 2017-10-03 | 2017-12-31 | 2018-04-21
6 |  |  |  | EOF: Cable Glading & Termination
Act | 2AI101IC01100-08016 | Not Started | Completed | EOF:Cable Glading & Termination | 2017-09-28 | 2017-12-31 | 2018-02-05 | 2019-04-17
Act | 2AI101IC01100-08030 | Not Started | Completed | EOF:Cable Glading & Termination | 2017-09-28 | 2017-12-31 | 2018-02-05 | 2019-04-17
4 |  |  |  | TELECOM
5 |  |  |  | EOF: UG Telecom cable works
Act | 2AI101TE01000 | Not Started | Completed | EOF:UG Telecom cable works | 2017-04-11 | 2017-09-09 | 2017-05-08 | 2018-07-02
6 |  |  |  | EOF: UG Telecom cable works
Act | 2AI101TE01000-08001 | Not Started | Completed | EOF: Laying Cable Duct | 2017-04-11 | 2017-09-04 | 2017-05-08 | 2018-07-02
Act | 2AI101TE01000-08005 | Not Started | Completed | EOF: Cable laying | 2017-04-13 | 2017-09-06 | 2018-01-11 | 2018-07-02
Act | 2AI101TE01000-08015 | Not Started | Completed | EOF: Splicing of telecom cable | 2017-05-03 | 2017-09-09 | 2018-07-02 | 2018-07-02
Act | 2AI101TE01000-08000 | Not Started | Completed | EOF:Cable Glading & Termination | 2017-04-11 | 2017-09-09 | 2017-05-08 | 2018-07-02
5 |  |  |  | EOF: AG Cable laying, Telecom Equipments / CCTV & Security System Installation & Cable Termination
Act | 2AI101TE01100 | Not Started | Completed | EOF: AG Cable laying, Telecom Equipments / CCTV & Security System Installation & Cable Termination | 2017-06-05 | 2017-12-16 | 2018-02-05 | 2018-05-09
6 |  |  |  | EOF: AG Cable laying
Act | 2AI101TE01100-08001 | Not Started | Completed | EOF:AG Cable laying | 2017-06-05 | 2017-09-12 | 2018-05-07 | 2018-05-09
Act | 2AI101TE01100-08000 | Not Started | Completed | EOF: AG Cable laying | 2017-06-05 | 2017-09-12 | 2018-05-07 | 2018-05-09
6 |  |  |  | EOF: Telecom Equipments / CCTV & Security System Installation
Act | 2AI101TE01100-08006 | Not Started | Completed | EOF:Telecom Equipments Installation | 2017-09-19 | 2017-12-10 | 2018-02-05 | 2018-02-07
Act | 2AI101TE01100-08010 | Not Started | Completed | EOF:CCTV & Security System Installation | 2017-09-19 | 2017-12-10 | 2018-02-05 | 2018-02-07
Act | 2AI101TE01100-08005 | Not Started | Completed | EOF: Telecom Equipments / CCTV & Security System Installation | 2017-09-19 | 2017-12-10 | 2018-02-05 | 2018-02-07
6 |  |  |  | EOF: Cable Termination
Act | 2AI101TE01100-08016 | Not Started | Completed | EOF:Cable Termination | 2017-11-16 | 2017-12-16 | 2018-04-21 | 2018-04-25
Act | 2AI101TE01100-08015 | Not Started | Completed | EOF: Cable Termination | 2017-11-16 | 2017-12-16 | 2018-04-21 | 2018-04-25
4 |  |  |  | FIRE-PROOFING
5 |  |  |  | EOF: Fire Proofing of Structures/equipments
Act | 2AI101CV03100-08000 | Not Started | Not Started | EOF: Fire Proofing of LFHO at Storage Tank - 52-D-93 Area | 2017-11-26 | 2017-12-25
Act | 2AI101CV03100-08005 | Not Started | Not Started | EOF: Fire Proofing of LFHO at Storage Tank - 52-D-94 Area | 2017-11-26 | 2017-12-25
Act | 2AI101CV03100 | Not Started | In Progress | EOF: Fire Proofing of Structures/equipments | 2017-08-13 | 2018-01-24 | 2019-04-17
Act | 2AI101CV03100-08010 | Not Started | Not Started | EOF: Fire Proofing of LFHO at Storage Tank - 52-D-95 Area | 2017-12-26 | 2018-01-24
Act | 2AI101CV03100-08015 | Not Started | Not Started | EOF: Fire Proofing of LFHO at Storage Tank - 52-D-96 Area | 2017-12-26 | 2018-01-24
Act | 2AI101CV03100-08020 | Not Started | Not Started | EOF: Fire Proofing of Diesel Generator Day Tank - 50-R-002 | 2017-11-14 | 2017-11-30
Act | 2AI101CV03100-08025 | Not Started | Not Started | EOF: Fire Proofing of Diesel Generator Day Tank - 52-R-302 | 2017-10-12 | 2017-10-29
Act | 2AI101CV03100-08030 | Not Started | In Progress | EOF: Fire Proofing of Trimp Pump - 621-G-301 | 2017-08-13 | 2017-08-27 | 2019-04-17
Act | 2AI101CV03100-08040 | Not Started | Not Started | EOF: Fire Proofing of Diesel Generator Day Tank - 52-R-303 | 2017-10-29 | 2017-11-14
Act | 2AI101CV03100-08035 | Not Started | Not Started | EOF: Fire Proofing of Diesel Generator Day Tank - 52-R-301 | 2017-10-29 | 2017-11-14
4 |  |  |  | PAINTING
5 |  |  |  | EOF: Touch-up painting of Piping
Act | 2AI101PI18100-08001 | Not Started | In Progress | EOF: Touch-Up Painting for Metallic (CS/LTCS) | 2017-07-03 | 2018-01-06 | 2017-06-05
Act | 2AI101PI18100-08005 | Not Started | In Progress | EOF: Touch-Up Painting for Metallic (SS/SDSS) | 2017-11-07 | 2017-12-24 | 2018-08-25
Act | 2AI101PI18100 | Not Started | In Progress | EOF: Touch-up painting of Piping | 2017-07-03 | 2018-01-06 | 2017-06-05
Act | 2AI101PI18100-08000 | Not Started | In Progress | EOF: Touch-up painting of Piping | 2017-07-03 | 2018-01-06 | 2017-06-05
5 |  |  |  | EOF: Touch-up painting of Structures
Act | 2AI101CV18200-08000 | Not Started | In Progress | EOF: Touch-up painting of Structures | 2017-05-01 | 2017-07-10 | 2018-03-21
Act | 2AI101CV18200 | Not Started | In Progress | EOF: Touch-up painting of Structures | 2017-05-01 | 2017-07-10 | 2018-03-21
3 |  |  |  | LOADING / FILLING MIXING MANIFOLDS (LMM / FMM)
4 |  |  |  | CIVIL / STRUCTURAL / ARCHITECTURAL
5 |  |  |  | EQUIPMENT FOUNDATION
6 |  |  |  | EOF: Filling Manifold Auto Sampling Package (52-Z-305 & 306) Shelter Foundation
Act | 2AI102CV01100 | Not Started | Completed | EOF: Filling Manifold Auto Sampling Package (52-Z-305 & 306) Shelter Foundation | 2016-10-24 | 2016-12-20 | 2016-12-13 | 2016-12-13
7 |  |  |  | EOF: Filling Manifold Auto Sampling Package (52-Z-305) Shelter Foundation
Act | 2AI102CV01100-08001 | Not Started | Completed | EOF:Survey Marking, Excavation & Subgrade | 2016-10-24 | 2016-10-29 | 2016-12-13 | 2016-12-13
Act | 2AI102CV01100-08006 | Not Started | Completed | EOF:Blinding/PCC for Fnd | 2016-10-29 | 2016-10-30 | 2016-12-13 | 2016-12-13
Act | 2AI102CV01100-08010 | Not Started | Completed | EOF:Rebar, Formwork for Footing | 2016-10-31 | 2016-11-08 | 2016-12-13 | 2016-12-13
Act | 2AI102CV01100-08015 | Not Started | Completed | EOF:Rebar, Formwork, Install Embedments for Pedestal | 2016-11-12 | 2016-11-21 | 2016-12-13 | 2016-12-13
Act | 2AI102CV01100-08020 | Not Started | Completed | EOF:Concrete Potection for Fnd | 2016-11-30 | 2016-12-05 | 2016-12-13 | 2016-12-13
Act | 2AI102CV01100-08025 | Not Started | Completed | EOF:Backfilling & Compaction for Fnd | 2016-12-08 | 2016-12-13 | 2016-12-13 | 2016-12-13
Act | 2AI102CV01100-08011 | Not Started | Completed | EOF:Concrete Pouring - for Footing | 2016-11-08 | 2016-11-09 | 2016-12-13 | 2016-12-13
Act | 2AI102CV01100-08016 | Not Started | Completed | EOF:Concrete Pouring - for Pedestal | 2016-11-21 | 2016-11-22 | 2016-12-13 | 2016-12-13
Act | 2AI102CV01100-08000 | Not Started | Completed | EOF: Filling Manifold Auto Sampling Package (52-Z-305) Shelter Foundation | 2016-10-24 | 2016-12-13 | 2016-12-13 | 2016-12-13
7 |  |  |  | EOF: Filling Manifold Auto Sampling Package (52-Z-306) Shelter Foundation
Act | 2AI102CV01100-08030 | Not Started | Completed | EOF:Survey Marking, Excavation & Subgrade | 2016-11-05 | 2016-11-09 | 2016-12-13 | 2016-12-13
Act | 2AI102CV01100-08035 | Not Started | Completed | EOF:Blinding/PCC for Fnd | 2016-11-09 | 2016-11-10 | 2016-12-13 | 2016-12-13
Act | 2AI102CV01100-08040 | Not Started | Completed | EOF:Rebar, Formwork for Footing | 2016-11-12 | 2016-11-17 | 2016-12-13 | 2016-12-13
Act | 2AI102CV01100-08045 | Not Started | Completed | EOF:Rebar, Formwork, Install Embedments for Pedestal | 2016-11-21 | 2016-11-30 | 2016-12-13 | 2016-12-13
Act | 2AI102CV01100-08050 | Not Started | Completed | EOF:Concrete Potection for Fnd | 2016-12-07 | 2016-12-12 | 2016-12-13 | 2016-12-13
Act | 2AI102CV01100-08055 | Not Started | Completed | EOF:Backfilling & Compaction for Fnd | 2016-12-15 | 2016-12-20 | 2016-12-13 | 2016-12-13
Act | 2AI102CV01100-08041 | Not Started | Completed | EOF:Concrete Pouring - for Footing | 2016-11-17 | 2016-11-19 | 2016-12-13 | 2016-12-13
Act | 2AI102CV01100-08046 | Not Started | Completed | EOF:Concrete Pouring - for Pedestal | 2016-11-30 | 2016-12-01 | 2016-12-13 | 2016-12-13
Act | 2AI102CV01100-08005 | Not Started | Completed | EOF: Filling Manifold Auto Sampling Package (52-Z-306) Shelter Foundation | 2016-11-05 | 2016-12-20 | 2016-12-13 | 2016-12-13
5 |  |  |  | SHELTER ERECTION
6 |  |  |  | EOF: Filling Manifold Auto Sampling Package (52-Z-305 & 306) Shelter Erection
Act | 2AI102CV01400 | Not Started | Completed | EOF: Filling Manifold Auto Sampling Package (52-Z-305 & 306) Shelter Erection | 2017-01-09 | 2017-03-12 | 2017-01-09 | 2017-03-12
7 |  |  |  | EOF: Filling Manifold Auto Sampling Package (52-Z-305) Shelter Erection
Act | 2AI102CV01400-08001 | Not Started | Completed | EOF:Installation of Str. Steel for Filling Manifold Auto Sampling Package (52-Z-305) Shelter | 2017-01-09 | 2017-01-26 | 2017-01-09 | 2017-01-26
Act | 2AI102CV01400-08006 | Not Started | Completed | EOF:Alignment & Bolting/Torqueing for Filling Manifold Auto Sampling Package (52-Z-305) Shelter | 2017-01-26 | 2017-02-13 | 2017-01-28 | 2017-02-13
Act | 2AI102CV01400-08011 | Not Started | Completed | EOF:Grouting of Filling Manifold Auto Sampling Package (52-Z-305) Shelter | 2017-02-05 | 2017-02-15 | 2017-02-05 | 2017-02-15
Act | 2AI102CV01400-08030 | Not Started | Completed | Installation of gratings/handrail/stair/ladder | 2017-02-16 | 2017-02-27 | 2017-02-16 | 2017-02-24
Act | 2AI102CV01400-08040 | Not Started | Completed | Wall & Roof Cladding | 2017-02-15 | 2017-03-01 | 2017-02-15 | 2017-02-24
Act | 2AI102CV01400-08005 | Not Started | Completed | EOF: Filling Manifold Auto Sampling Package (52-Z-305) Shelter Erection | 2017-01-09 | 2017-03-01 | 2017-01-09 | 2017-02-24
7 |  |  |  | EOF: Filling Manifold Auto Sampling Package (52-Z-306) Shelter Erection
Act | 2AI102CV01400-08015 | Not Started | Completed | EOF:Installation of Str. Steel for Filling Manifold Auto Sampling Package (52-Z-306) Shelter | 2017-01-26 | 2017-02-13 | 2017-01-26 | 2017-02-13
Act | 2AI102CV01400-08020 | Not Started | Completed | EOF:Alignment & Bolting/Torqueing for Filling Manifold Auto Sampling Package (52-Z-306) Shelter | 2017-01-29 | 2017-02-15 | 2017-01-29 | 2017-02-15
Act | 2AI102CV01400-08025 | Not Started | Completed | EOF:Grouting of Filling Manifold Auto Sampling Package (52-Z-306) Shelter | 2017-02-15 | 2017-02-26 | 2017-02-15 | 2017-02-24
Act | 2AI102CV01400-08035 | Not Started | Completed | Installation of gratings/handrail/stair/ladder | 2017-02-26 | 2017-03-08 | 2017-02-06 | 2017-02-08
Act | 2AI102CV01400-08045 | Not Started | Completed | Wall & Roof Cladding | 2017-02-26 | 2017-03-12 | 2017-02-23 | 2017-03-12
Act | 2AI102CV01400-08010 | Not Started | Completed | EOF: Filling Manifold Auto Sampling Package (52-Z-306) Shelter Erection | 2017-01-26 | 2017-03-12 | 2017-01-26 | 2017-03-12
3 |  |  |  | OTHER WORKS - EOF
4 |  |  |  | CIVIL / STRUCTURAL / ARCHITECTURAL
5 |  |  |  | FOUNDATION
6 |  |  |  | EOF: Mobile Foam Cannon and Mobile Monitor Shelter Foundation
Act | 2AI103CV18400 | Not Started | Completed | EOF: Mobile Foam Cannon and Mobile Monitor Shelter Foundation | 2016-10-22 | 2017-01-11 | 2016-08-30 | 2016-10-21
7 |  |  |  | EOF: Mobile Foam Cannon and Mobile Monitor Shelter Foundation
Act | 2AI103CV18400-08001 | Not Started | Completed | EOF:Survey Marking, Excavation & Subgrade | 2016-10-22 | 2016-10-25 | 2016-08-30 | 2016-09-16
Act | 2AI103CV18400-08005 | Not Started | Completed | EOF:Blinding/PCC for Fnd | 2016-10-31 | 2016-11-02 | 2016-09-08 | 2016-09-30
Act | 2AI103CV18400-08010 | Not Started | Completed | EOF:Rebar, Formwork for Footing | 2016-11-05 | 2016-11-26 | 2016-09-20 | 2016-10-03
Act | 2AI103CV18400-08015 | Not Started | Completed | EOF:Rebar, Formwork, Install Embedments for Pedestal | 2016-11-29 | 2016-12-22 | 2016-10-03 | 2016-10-03
Act | 2AI103CV18400-08020 | Not Started | Completed | EOF:Concrete Potection for Fnd | 2016-12-24 | 2016-12-31 | 2016-10-20 | 2016-10-20
Act | 2AI103CV18400-08025 | Not Started | Completed | EOF:Backfilling & Compaction for Fnd | 2017-01-03 | 2017-01-11 | 2016-10-21 | 2016-10-21
Act | 2AI103CV18400-08011 | Not Started | Completed | EOF:Concrete Pouring - for Footing | 2016-11-26 | 2016-11-27 | 2016-10-06 | 2016-10-06
Act | 2AI103CV18400-08016 | Not Started | Completed | EOF:Concrete Pouring - for Pedestal | 2016-12-22 | 2016-12-24 | 2016-10-06 | 2016-10-06
Act | 2AI103CV18400-08000 | Not Started | Completed | EOF: Mobile Foam Cannon and Mobile Monitor Shelter Foundation | 2016-10-22 | 2017-01-11 | 2016-08-30 | 2016-10-21
6 |  |  |  | EOF: Foundation for Steel Structure
Act | 2AI103CV18600 | Not Started | Completed | EOF: Foundation for Steel Structure | 2017-04-12 | 2017-07-20 | 2016-11-26 | 2017-03-30
7 |  |  |  | EOF: Foundation for Tank Stairways Structural Steel
Act | 2AI103CV18600-08000 | Not Started | Completed | EOF: Foundation for Tank Stairways Structural Steel | 2017-04-12 | 2017-07-20 | 2016-11-26 | 2017-03-30
8 |  |  |  | EOF: Foundation for Tank Stairways Structural Steel -52-D-94
Act | 2AI103CV18600-08001 | Not Started | Completed | EOF:Survey Marking, Excavation & Subgrade | 2017-04-15 | 2017-04-23 | 2016-12-14 | 2017-03-01
Act | 2AI103CV18600-08005 | Not Started | Completed | EOF:Blinding/PCC for Fnd | 2017-04-22 | 2017-04-25 | 2016-12-21 | 2017-03-02
Act | 2AI103CV18600-08010 | Not Started | Completed | EOF:Rebar, Formwork for Footing | 2017-04-12 | 2017-04-30 | 2016-12-22 | 2017-03-04
Act | 2AI103CV18600-08015 | Not Started | Completed | EOF:Rebar, Formwork, Install Embedments for Pedestal | 2017-05-03 | 2017-05-24 | 2016-12-29 | 2017-03-08
Act | 2AI103CV18600-08020 | Not Started | Completed | EOF:Concrete Potection for Fnd | 2017-05-28 | 2017-06-07 | 2017-02-06 | 2017-03-26
Act | 2AI103CV18600-08025 | Not Started | Completed | EOF:Backfilling & Compaction for Fnd | 2017-06-04 | 2017-06-12 | 2017-02-07 | 2017-03-30
Act | 2AI103CV18600-08011 | Not Started | Completed | EOF:Concrete Pouring - for Footing | 2017-04-30 | 2017-05-03 | 2016-12-27 | 2017-03-05
Act | 2AI103CV18600-08016 | Not Started | Completed | EOF:Concrete Pouring - for Pedestal | 2017-05-24 | 2017-05-28 | 2017-02-01 | 2017-03-11
8 |  |  |  | EOF: Foundation for Tank Stairways Structural Steel -52-D-93
Act | 2AI103CV18600-08002 | Not Started | Completed | EOF:Survey Marking, Excavation & Subgrade | 2017-04-16 | 2017-04-24 | 2016-12-08 | 2017-03-01
Act | 2AI103CV18600-08030 | Not Started | Completed | EOF:Blinding/PCC for Fnd | 2017-04-24 | 2017-04-27 | 2016-12-15 | 2017-03-02
Act | 2AI103CV18600-08035 | Not Started | Completed | EOF:Rebar, Formwork for Footing | 2017-04-15 | 2017-05-02 | 2016-12-17 | 2017-03-04
Act | 2AI103CV18600-08040 | Not Started | Completed | EOF:Rebar, Formwork, Install Embedments for Pedestal | 2017-05-06 | 2017-05-27 | 2016-12-28 | 2017-03-08
Act | 2AI103CV18600-08045 | Not Started | Completed | EOF:Concrete Potection for Fnd | 2017-05-30 | 2017-06-10 | 2017-02-11 | 2017-03-26
Act | 2AI103CV18600-08050 | Not Started | Completed | EOF:Backfilling & Compaction for Fnd | 2017-06-06 | 2017-06-14 | 2017-02-20 | 2017-03-30
Act | 2AI103CV18600-08036 | Not Started | Completed | EOF:Concrete Pouring - for Footing | 2017-05-02 | 2017-05-06 | 2016-12-22 | 2017-03-05
Act | 2AI103CV18600-08041 | Not Started | Completed | EOF:Concrete Pouring - for Pedestal | 2017-05-27 | 2017-05-30 | 2017-02-02 | 2017-03-11
8 |  |  |  | EOF: Foundation for Tank Stairways Structural Steel -52-D-95
Act | 2AI103CV18600-08065 | Not Started | Completed | EOF:Survey Marking, Excavation & Subgrade | 2017-05-14 | 2017-05-22 | 2016-11-28 | 2016-12-01
Act | 2AI103CV18600-08070 | Not Started | Completed | EOF:Blinding/PCC for Fnd | 2017-05-22 | 2017-05-25 | 2016-12-05 | 2017-02-28
Act | 2AI103CV18600-08075 | Not Started | Completed | EOF:Rebar, Formwork for Footing | 2017-05-13 | 2017-05-30 | 2016-12-07 | 2017-03-02
Act | 2AI103CV18600-08080 | Not Started | Completed | EOF:Rebar, Formwork, Install Embedments for Pedestal | 2017-06-03 | 2017-06-24 | 2016-12-28 | 2017-03-08
Act | 2AI103CV18600-08085 | Not Started | Completed | EOF:Concrete Potection for Fnd | 2017-06-27 | 2017-07-08 | 2017-02-06 | 2017-03-25
Act | 2AI103CV18600-08090 | Not Started | Completed | EOF:Backfilling & Compaction for Fnd | 2017-07-04 | 2017-07-12 | 2017-02-08 | 2017-03-30
Act | 2AI103CV18600-08076 | Not Started | Completed | EOF:Concrete Pouring - for Footing | 2017-05-30 | 2017-06-03 | 2016-12-13 | 2017-03-02
Act | 2AI103CV18600-08081 | Not Started | Completed | EOF:Concrete Pouring - for Pedestal | 2017-06-24 | 2017-06-27 | 2017-01-29 | 2017-03-09
8 |  |  |  | EOF: Foundation for Tank Stairways Structural Steel -52-D-96
Act | 2AI103CV18600-08105 | Not Started | Completed | EOF:Survey Marking, Excavation & Subgrade | 2017-05-22 | 2017-05-30 | 2016-11-26 | 2016-11-27
Act | 2AI103CV18600-08110 | Not Started | Completed | EOF:Blinding/PCC for Fnd | 2017-05-30 | 2017-06-03 | 2016-12-04 | 2016-12-08
Act | 2AI103CV18600-08115 | Not Started | Completed | EOF:Rebar, Formwork for Footing | 2017-05-21 | 2017-06-07 | 2016-12-05 | 2017-02-25
Act | 2AI103CV18600-08120 | Not Started | Completed | EOF:Rebar, Formwork, Install Embedments for Pedestal | 2017-06-11 | 2017-07-02 | 2016-12-22 | 2017-01-23
Act | 2AI103CV18600-08125 | Not Started | Completed | EOF:Concrete Potection for Fnd | 2017-07-05 | 2017-07-16 | 2017-02-05 | 2017-02-07
Act | 2AI103CV18600-08130 | Not Started | Completed | EOF:Backfilling & Compaction for Fnd | 2017-07-12 | 2017-07-20 | 2017-02-07 | 2017-02-26
Act | 2AI103CV18600-08116 | Not Started | Completed | EOF:Concrete Pouring - for Footing | 2017-06-07 | 2017-06-11 | 2016-12-12 | 2017-02-25
Act | 2AI103CV18600-08121 | Not Started | Completed | EOF:Concrete Pouring - for Pedestal | 2017-07-02 | 2017-07-05 | 2017-01-25 | 2017-01-25
6 |  |  |  | EOF: Pump Foundation
Act | 2AI103CV18800 | Not Started | Completed | EOF: Pump Foundation | 2016-08-13 | 2016-09-26 | 2016-11-30 | 2017-01-07
7 |  |  |  | EOF: 621-G-302 A/B Foam Pump Foundation
Act | 2AI103CV18800-08000 | Not Started | Completed | EOF:Survey Marking, Excavation & Subgrade | 2016-08-24 | 2016-08-27 | 2016-11-30 | 2016-11-30
Act | 2AI103CV18800-08006 | Not Started | Completed | EOF:Blinding/PCC for Fnd | 2016-08-27 | 2016-08-29 | 2016-12-04 | 2016-12-04
Act | 2AI103CV18800-08011 | Not Started | Completed | EOF:Rebar, Formwork for Footing | 2016-08-29 | 2016-09-03 | 2016-12-05 | 2016-12-10
Act | 2AI103CV18800-08015 | Not Started | Completed | EOF:Rebar, Formwork, Install Embedments for Pedestal | 2016-09-05 | 2016-09-10 | 2016-12-05 | 2016-12-10
Act | 2AI103CV18800-08020 | Not Started | Completed | EOF:Concrete Potection for Fnd | 2016-09-17 | 2016-09-21 | 2016-12-24 | 2016-12-26
Act | 2AI103CV18800-08025 | Not Started | Completed | EOF:Backfilling & Compaction for Fnd | 2016-09-24 | 2016-09-26 | 2016-12-27 | 2017-01-02
Act | 2AI103CV18800-08018 | Not Started | Completed | Concrete Pouring - for Footing | 2016-09-03 | 2016-09-04 | 2016-12-13 | 2016-12-13
Act | 2AI103CV18800-08016 | Not Started | Completed | Concrete Pouring - for Pedestal | 2016-09-10 | 2016-09-11 | 2016-12-13 | 2016-12-13
Act | 2AI103CV18800-08005 | Not Started | Completed | EOF: 621-G-302 A/B Foam Pump Foundation | 2016-08-24 | 2016-09-26 | 2016-11-30 | 2017-01-02
7 |  |  |  | EOF: 621-G-302 C/D Foam Pump Foundation
Act | 2AI103CV18800-08030 | Not Started | Completed | EOF:Survey Marking, Excavation & Subgrade | 2016-08-13 | 2016-08-15 | 2016-12-05 | 2016-12-06
Act | 2AI103CV18800-08035 | Not Started | Completed | EOF:Blinding/PCC for Fnd | 2016-08-15 | 2016-08-17 | 2016-12-08 | 2016-12-08
Act | 2AI103CV18800-08040 | Not Started | Completed | EOF:Rebar, Formwork for Footing | 2016-08-17 | 2016-08-22 | 2016-12-10 | 2016-12-13
Act | 2AI103CV18800-08045 | Not Started | Completed | EOF:Rebar, Formwork, Install Embedments for Pedestal | 2016-08-23 | 2016-08-28 | 2016-12-10 | 2016-12-13
Act | 2AI103CV18800-08050 | Not Started | Completed | EOF:Concrete Potection for Fnd | 2016-09-05 | 2016-09-10 | 2016-12-24 | 2016-12-26
Act | 2AI103CV18800-08055 | Not Started | Completed | EOF:Backfilling & Compaction for Fnd | 2016-09-13 | 2016-09-15 | 2017-01-02 | 2017-01-07
Act | 2AI103CV18800-08041 | Not Started | Completed | Concrete Pouring - for Footing | 2016-08-22 | 2016-08-23 | 2016-12-15 | 2016-12-15
Act | 2AI103CV18800-08046 | Not Started | Completed | Concrete Pouring - for Pedestal | 2016-08-28 | 2016-08-29 | 2016-12-15 | 2016-12-15
Act | 2AI103CV18800-08010 | Not Started | Completed | EOF: 621-G-302 C/D Foam Pump Foundation | 2016-08-13 | 2016-09-15 | 2016-12-05 | 2017-01-07
6 |  |  |  | EOF: Foam System Package (52-Z-301 A/B) Foundation
Act | 2AI103CV19200 | Not Started | Completed | EOF: Foam System Package (52-Z-301 A/B) Foundation | 2016-08-18 | 2016-10-01 | 2016-11-30 | 2017-01-07
7 |  |  |  | EOF: Foam System Package (52-Z-301 A) Foundation
Act | 2AI103CV19200-08001 | Not Started | Completed | EOF:Survey Marking, Excavation & Subgrade | 2016-08-24 | 2016-08-27 | 2016-11-30 | 2016-11-30
Act | 2AI103CV19200-08006 | Not Started | Completed | EOF:Blinding/PCC for Fnd | 2016-08-27 | 2016-08-29 | 2016-12-04 | 2016-12-04
Act | 2AI103CV19200-08010 | Not Started | Completed | EOF:Rebar, Formwork for Footing | 2016-08-29 | 2016-09-05 | 2016-12-05 | 2016-12-10
Act | 2AI103CV19200-08015 | Not Started | Completed | EOF:Rebar, Formwork, Install Embedments for Pedestal | 2016-09-07 | 2016-09-15 | 2016-12-05 | 2016-12-10
Act | 2AI103CV19200-08020 | Not Started | Completed | EOF:Concrete Potection for Fnd | 2016-09-17 | 2016-09-21 | 2016-12-24 | 2016-12-26
Act | 2AI103CV19200-08025 | Not Started | Completed | EOF:Backfilling & Compaction for Fnd | 2016-09-25 | 2016-10-01 | 2016-12-27 | 2017-01-02
Act | 2AI103CV19200-08011 | Not Started | Completed | Concrete Pouring - for Footing | 2016-09-05 | 2016-09-06 | 2016-12-13 | 2016-12-13
Act | 2AI103CV19200-08016 | Not Started | Completed | Concrete Pouring - for Pedestal | 2016-09-15 | 2016-09-17 | 2016-12-13 | 2016-12-13
Act | 2AI103CV19200-08000 | Not Started | Completed | EOF: Foam System Package (52-Z-301 A) Foundation | 2016-08-24 | 2016-10-01 | 2016-11-30 | 2017-01-02
7 |  |  |  | EOF: Foam System Package (52-Z-301 B) Foundation
Act | 2AI103CV19200-08030 | Not Started | Completed | EOF:Survey Marking, Excavation & Subgrade | 2016-08-18 | 2016-08-21 | 2016-12-05 | 2016-12-06
Act | 2AI103CV19200-08035 | Not Started | Completed | EOF:Blinding/PCC for Fnd | 2016-08-21 | 2016-08-23 | 2016-12-08 | 2016-12-08
Act | 2AI103CV19200-08040 | Not Started | Completed | EOF:Rebar, Formwork for Footing | 2016-08-23 | 2016-08-30 | 2016-12-10 | 2016-12-13
Act | 2AI103CV19200-08045 | Not Started | Completed | EOF:Rebar, Formwork, Install Embedments for Pedestal | 2016-09-01 | 2016-09-10 | 2016-12-10 | 2016-12-13
Act | 2AI103CV19200-08050 | Not Started | Completed | EOF:Concrete Potection for Fnd | 2016-09-11 | 2016-09-15 | 2016-12-24 | 2016-12-26
Act | 2AI103CV19200-08055 | Not Started | Completed | EOF:Backfilling & Compaction for Fnd | 2016-09-19 | 2016-09-25 | 2017-01-02 | 2017-01-07
Act | 2AI103CV19200-08041 | Not Started | Completed | Concrete Pouring - for Footing | 2016-08-30 | 2016-08-31 | 2016-12-15 | 2016-12-15
Act | 2AI103CV19200-08046 | Not Started | Completed | Concrete Pouring - for Pedestal | 2016-09-10 | 2016-09-11 | 2016-12-15 | 2016-12-15
Act | 2AI103CV19200-08005 | Not Started | Completed | EOF: Foam System Package (52-Z-301 B) Foundation | 2016-08-18 | 2016-09-25 | 2016-12-05 | 2017-01-07
6 |  |  |  | EOF: Foam System Package (52-Z-301 A/B) Shelter Foundation
Act | 2AI103CV19400 | Not Started | Completed | EOF: Foam System Package (52-Z-301 A/B) Shelter Foundation | 2016-10-27 | 2016-12-05 | 2016-11-30 | 2017-03-10
7 |  |  |  | EOF: Foam System Package (52-Z-301 A) Shelter Foundation
Act | 2AI103CV19400-08002 | Not Started | Completed | EOF:Survey Marking, Excavation & Subgrade | 2016-10-27 | 2016-10-30 | 2016-11-30 | 2016-11-30
Act | 2AI103CV19400-08006 | Not Started | Completed | EOF:Blinding/PCC for Fnd | 2016-10-30 | 2016-11-01 | 2017-02-11 | 2017-02-11
Act | 2AI103CV19400-08010 | Not Started | Completed | EOF:Rebar, Formwork for Footing | 2016-11-01 | 2016-11-09 | 2017-02-13 | 2017-02-15
Act | 2AI103CV19400-08015 | Not Started | Completed | EOF:Rebar, Formwork, Install Embedments for Pedestal | 2016-11-12 | 2016-11-20 | 2017-02-18 | 2017-02-23
Act | 2AI103CV19400-08020 | Not Started | Completed | EOF:Concrete Potection for Fnd | 2016-11-21 | 2016-11-26 | 2017-03-01 | 2017-03-07
Act | 2AI103CV19400-08025 | Not Started | Completed | EOF:Backfilling & Compaction for Fnd | 2016-11-29 | 2016-12-05 | 2017-03-07 | 2017-03-10
Act | 2AI103CV19400-08011 | Not Started | Completed | Concrete Pouring - for Footing | 2016-11-09 | 2016-11-10 | 2017-02-16 | 2017-02-16
Act | 2AI103CV19400-08016 | Not Started | Completed | Concrete Pouring - for Pedestal | 2016-11-20 | 2016-11-21 | 2017-02-27 | 2017-02-27
Act | 2AI103CV19400-08000 | Not Started | Completed | EOF: Foam System Package (52-Z-301 A) Shelter Foundation | 2016-10-27 | 2016-12-05 | 2016-11-30 | 2017-03-10
7 |  |  |  | EOF: Foam System Package (52-Z-301 B) Shelter Foundation
Act | 2AI103CV19400-08030 | Not Started | Completed | EOF:Survey Marking, Excavation & Subgrade | 2016-10-27 | 2016-10-30 | 2016-11-30 | 2016-11-30
Act | 2AI103CV19400-08035 | Not Started | Completed | EOF:Blinding/PCC for Fnd | 2016-10-30 | 2016-11-01 | 2017-02-11 | 2017-02-11
Act | 2AI103CV19400-08040 | Not Started | Completed | EOF:Rebar, Formwork for Footing | 2016-11-01 | 2016-11-08 | 2017-02-13 | 2017-02-15
Act | 2AI103CV19400-08045 | Not Started | Completed | EOF:Rebar, Formwork, Install Embedments for Pedestal | 2016-11-10 | 2016-11-19 | 2017-02-18 | 2017-02-20
Act | 2AI103CV19400-08050 | Not Started | Completed | EOF:Concrete Potection for Fnd | 2016-11-20 | 2016-11-24 | 2017-03-01 | 2017-03-07
Act | 2AI103CV19400-08055 | Not Started | Completed | EOF:Backfilling & Compaction for Fnd | 2016-11-28 | 2016-12-04 | 2017-03-07 | 2017-03-08
Act | 2AI103CV19400-08041 | Not Started | Completed | Concrete Pouring - for Footing | 2016-11-08 | 2016-11-09 | 2017-02-16 | 2017-02-16
Act | 2AI103CV19400-08046 | Not Started | Completed | Concrete Pouring - for Pedestal | 2016-11-19 | 2016-11-20 | 2017-02-27 | 2017-02-27
Act | 2AI103CV19400-08005 | Not Started | Completed | EOF: Foam System Package (52-Z-301 B) Shelter Foundation | 2016-10-27 | 2016-12-04 | 2016-11-30 | 2017-03-08
6 |  |  |  | EOF: Ground Supported Platforms Foundation
Act | 2AI103CV19600 | Not Started | Completed | EOF: Ground Supported Platforms Foundation | 2016-09-20 | 2016-11-29 | 2017-03-13 | 2019-02-02
7 |  |  |  | EOF: Ground Supported Platforms Foundation
Act | 2AI103CV19600-08001 | Not Started | Completed | EOF:Survey Marking, Excavation & Subgrade | 2016-09-20 | 2016-09-25 | 2017-03-13 | 2019-01-02
Act | 2AI103CV19600-08005 | Not Started | Completed | EOF:Blinding/PCC for Fnd | 2016-09-25 | 2016-09-27 | 2017-03-16 | 2019-01-03
Act | 2AI103CV19600-08015 | Not Started | Completed | EOF:Rebar, Formwork, Install Embedments for Pedestal | 2016-10-19 | 2016-11-06 | 2017-03-30 | 2019-01-14
Act | 2AI103CV19600-08020 | Not Started | Completed | EOF:Concrete Potection for Fnd | 2016-11-15 | 2016-11-20 | 2017-04-23 | 2019-01-18
Act | 2AI103CV19600-08025 | Not Started | Completed | EOF:Backfilling & Compaction for Fnd | 2016-11-23 | 2016-11-29 | 2017-05-01 | 2019-02-02
Act | 2AI103CV19600-08011 | Not Started | Completed | Concrete Pouring - for Footing | 2016-10-15 | 2016-10-17 | 2017-03-22 | 2019-01-10
Act | 2AI103CV19600-08016 | Not Started | Completed | Concrete Pouring - for Pedestal | 2016-11-06 | 2016-11-08 | 2017-04-05 | 2019-01-17
Act | 2AI103CV19600-08010 | Not Started | Completed | EOF:Rebar, Formwork for Footing | 2016-09-27 | 2016-10-15 | 2017-03-18 | 2019-01-07
Act | 2AI103CV19600-08000 | Not Started | Completed | EOF: Ground Supported Platforms Foundation | 2016-09-20 | 2016-11-29 | 2017-03-13 | 2019-02-02
6 |  |  |  | EOF: Foundation of Other Equipments (H2S Scrubber, PIG Receiver etc)
Act | 2AI103CV20120 | Not Started | Completed | EOF: Foundation of Other Equipments (H2S Scrubber, PIG Receiver etc) | 2016-08-18 | 2016-10-23 | 2016-06-22 | 2016-11-09
7 |  |  |  | EOF: Oily Water Transfer Vessel 621-V-301( having Pump - 52-G-303 A/B ) Foundation
Act | 2AI103CV20120-08000 | Not Started | Completed | EOF: Oily Water Transfer Vessel 621-V-301( having Pump - 52-G-303 A/B ) Foundation | 2016-08-18 | 2016-10-23 | 2016-06-22 | 2016-11-09
Act | 2AI103CV20120-08301 | Not Started | Completed | EOF:Excavation & Subgrade | 2016-08-18 | 2016-08-27 | 2016-06-22 | 2016-07-16
Act | 2AI103CV20120-08305 | Not Started | Completed | EOF:Blinding/PCC for Fnd | 2016-08-27 | 2016-08-29 | 2016-07-21 | 2016-07-21
Act | 2AI103CV20120-08310 | Not Started | Completed | EOF:Rebar, Formwork for base | 2016-08-30 | 2016-09-05 | 2016-07-23 | 2016-07-27
Act | 2AI103CV20120-08315 | Not Started | Completed | EOF:Rebar, Formwork for Wall for 1st Pour | 2016-09-08 | 2016-09-20 | 2016-08-09 | 2016-08-26
Act | 2AI103CV20120-08320 | Not Started | Completed | EOF:Rebar, Formwork for Wall for 2nd Pour | 2016-09-24 | 2016-10-08 | 2016-10-04 | 2016-10-17
Act | 2AI103CV20120-08325 | Not Started | Completed | EOF:Concrete Potection | 2016-10-09 | 2016-10-16 | 2016-09-08 | 2016-11-03
Act | 2AI103CV20120-08330 | Not Started | Completed | EOF:Backfilling & Compaction | 2016-10-19 | 2016-10-23 | 2016-09-10 | 2016-11-09
Act | 2AI103CV20120-08311 | Not Started | Completed | Concrete Pouring - for base | 2016-09-05 | 2016-09-06 | 2016-07-28 | 2016-10-01
Act | 2AI103CV20120-08316 | Not Started | Completed | Concrete Pouring - for wall - 1st pouring | 2016-09-20 | 2016-09-21 | 2016-08-27 | 2016-08-27
Act | 2AI103CV20120-08321 | Not Started | Completed | Concrete Pouring - for wall - 2nd pouring | 2016-10-08 | 2016-10-09 | 2016-10-18 | 2016-10-18
6 |  |  |  | EOF: Tank Foundation
Act | 2AI103CV20220 | Not Started | Completed | EOF: Tank Foundation | 2016-07-12 | 2016-10-05 | 2016-12-20 | 2017-04-19
7 |  |  |  | EOF: Foundation for Diesel Fuel Tank (52-D-307 A/B)
Act | 2AI103CV20220-08001 | Not Started | Completed | EOF:Survey Marking, Excavation & Subgrade | 2016-07-12 | 2016-07-16 | 2016-12-20 | 2016-12-24
Act | 2AI103CV20220-08006 | Not Started | Completed | EOF:Blinding/PCC for Fnd | 2016-07-16 | 2016-07-18 | 2016-12-26 | 2016-12-26
Act | 2AI103CV20220-08010 | Not Started | Completed | EOF:Rebar, Formwork for Footing | 2016-07-18 | 2016-07-24 | 2017-03-06 | 2017-03-08
Act | 2AI103CV20220-08015 | Not Started | Completed | EOF:Rebar, Formwork, Install Embedments for Pedestal | 2016-07-26 | 2016-08-01 | 2017-03-16 | 2017-03-29
Act | 2AI103CV20220-08020 | Not Started | Completed | EOF:Concrete Potection for Fnd | 2016-08-04 | 2016-08-09 | 2017-04-01 | 2017-04-01
Act | 2AI103CV20220-08025 | Not Started | Completed | EOF:Backfilling & Compaction for Fnd | 2016-08-13 | 2016-08-17 | 2017-04-13 | 2017-04-19
Act | 2AI103CV20220-08011 | Not Started | Completed | Concrete Pouring - for Footing | 2016-07-24 | 2016-07-25 | 2017-03-14 | 2017-03-14
Act | 2AI103CV20220-08021 | Not Started | Completed | Concrete Pouring - for Pedestal | 2016-08-01 | 2016-08-02 | 2017-04-07 | 2017-04-12
Act | 2AI103CV20220-08000 | Not Started | Completed | EOF: Foundation for Diesel Fuel Tank(52-D-307 A/B) | 2016-07-12 | 2016-08-17 | 2016-12-20 | 2017-04-19
7 |  |  |  | EOF: Foundation for Diesel Fuel Tank (52-D-307 C/D)
Act | 2AI103CV20220-08030 | Not Started | Completed | EOF:Survey Marking, Excavation & Subgrade | 2016-09-01 | 2016-09-05 | 2016-12-20 | 2016-12-24
Act | 2AI103CV20220-08335 | Not Started | Completed | EOF:Blinding/PCC for Fnd | 2016-09-05 | 2016-09-07 | 2016-12-25 | 2016-12-25
Act | 2AI103CV20220-08340 | Not Started | Completed | EOF:Rebar, Formwork for Footing | 2016-09-07 | 2016-09-13 | 2017-03-06 | 2017-03-08
Act | 2AI103CV20220-08345 | Not Started | Completed | EOF:Rebar, Formwork, Install Embedments for Pedestal | 2016-09-15 | 2016-09-21 | 2017-03-17 | 2017-03-29
Act | 2AI103CV20220-08350 | Not Started | Completed | EOF:Concrete Potection for Fnd | 2016-09-24 | 2016-09-28 | 2017-04-07 | 2017-04-12
Act | 2AI103CV20220-08355 | Not Started | Completed | EOF:Backfilling & Compaction for Fnd | 2016-10-02 | 2016-10-05 | 2017-04-13 | 2017-04-19
Act | 2AI103CV20220-08341 | Not Started | Completed | Concrete Pouring - for Footing | 2016-09-13 | 2016-09-14 | 2017-03-14 | 2017-03-14
Act | 2AI103CV20220-08346 | Not Started | Completed | Concrete Pouring - for Pedestal | 2016-09-21 | 2016-09-22 | 2017-04-01 | 2017-04-01
Act | 2AI103CV20220-08005 | Not Started | Completed | EOF: Foundation for Diesel Fuel Tank(52-D-307 C/D) | 2016-09-01 | 2016-10-05 | 2016-12-20 | 2017-04-19
5 |  |  |  | STRUCTURAL STEEL
6 |  |  |  | EOF: Structural Steel of Ground Supported Platforms
Act | 2AI103CV01200 | Not Started | In Progress | EOF: Structural Steel of Ground Supported Platforms | 2016-11-29 | 2017-10-23 | 2017-04-22
7 |  |  |  | EOF: Structural Steel of Ground Supported /Equipment Mounted Platforms
Act | 2AI103CV01200-08001 | Not Started | Completed | EOF:Installation of Str. Steel of Ground Supported Platforms | 2016-11-29 | 2017-01-05 | 2017-04-22 | 2019-03-11
Act | 2AI103CV01200-08006 | Not Started | Completed | EOF:Alignment & Bolting/Torqueing of Ground Supported Platforms | 2016-12-07 | 2017-01-09 | 2017-05-10 | 2019-03-19
Act | 2AI103CV01200-08010 | Not Started | Completed | EOF:Grouting of Ground Supported Platforms | 2016-12-13 | 2017-01-11 | 2017-11-14 | 2019-04-09
Act | 2AI103CV01200-08000 | Not Started | Completed | EOF: Structural Steel of Ground Supported /Equipment Mounted Platforms | 2016-11-29 | 2017-01-11 | 2017-04-22 | 2019-04-09
7 |  |  |  | EOF: Pipe Support & EIT Supports Erection
Act | 2AI103CV01200-08005 | Not Started | In Progress | EOF: Pipe Support & EIT Supports Erection | 2017-05-11 | 2017-10-23 | 2017-07-25
Act | 2AI103CV01200-08015 | Not Started | In Progress | EOF:Installation of Str. Steel of Ground Supported Platforms | 2017-05-11 | 2017-10-16 | 2017-07-25
Act | 2AI103CV01200-08020 | Not Started | In Progress | EOF:Alignment & Bolting/Torqueing of Ground Supported Platforms | 2017-05-16 | 2017-10-19 | 2017-07-25
Act | 2AI103CV01200-08025 | Not Started | In Progress | EOF:Grouting of Ground Supported Platforms | 2017-07-16 | 2017-10-23 | 2017-12-10
6 |  |  |  | EOF: Structural Steel Erection
Act | 2AI103CV18700 | Not Started | Completed | EOF: Structural Steel Erection | 2017-06-12 | 2017-12-03 | 2017-03-04 | 2018-11-22
7 |  |  |  | EOF: Tank Stairways - Structural Steel Erection
Act | 2AI103CV18700-08000 | Not Started | Completed | EOF: Tank Stairways - Structural Steel Erection | 2017-06-12 | 2017-12-03 | 2017-03-04 | 2018-11-22
8 |  |  |  | EOF: Tank Stairways - Structural Steel Erection 52-D-94
Act | 2AI103CV18700-08005 | Not Started | Completed | Installation of Main steel structure | 2017-06-12 | 2017-08-09 | 2017-03-05 | 2018-06-05
Act | 2AI103CV18700-08010 | Not Started | Completed | Alignment/Welding/Bolting | 2017-06-15 | 2017-08-13 | 2017-03-05 | 2018-06-07
Act | 2AI103CV18700-08015 | Not Started | Completed | Torque Bolts (wherever applicable) | 2017-06-19 | 2017-08-16 | 2017-03-05 | 2018-06-10
Act | 2AI103CV18700-08020 | Not Started | Completed | Grouting (wherever applicable) | 2017-07-23 | 2017-08-20 | 2018-06-10 | 2018-06-12
Act | 2AI103CV18700-08025 | Not Started | Completed | Installation of gratings/handrail/ladder | 2017-08-05 | 2017-08-28 | 2017-07-04 | 2018-11-20
8 |  |  |  | EOF: Tank Stairways - Structural Steel Erection 52-D-93
Act | 2AI103CV18700-08001 | Not Started | Completed | Installation of Main steel structure | 2017-08-13 | 2017-10-10 | 2017-03-06 | 2018-06-14
Act | 2AI103CV18700-08030 | Not Started | Completed | Alignment/Welding/Bolting | 2017-08-16 | 2017-10-14 | 2017-03-06 | 2018-07-02
Act | 2AI103CV18700-08035 | Not Started | Completed | Torque Bolts (wherever applicable) | 2017-08-20 | 2017-10-17 | 2017-03-06 | 2018-07-02
Act | 2AI103CV18700-08040 | Not Started | Completed | Grouting (wherever applicable) | 2017-09-11 | 2017-10-21 | 2018-07-03 | 2018-07-05
Act | 2AI103CV18700-08045 | Not Started | Completed | Installation of gratings/handrail/ladder | 2017-10-05 | 2017-10-29 | 2017-07-04 | 2018-11-20
8 |  |  |  | EOF: Tank Stairways - Structural Steel Erection 52-D-95
Act | 2AI103CV18700-08050 | Not Started | Completed | Installation of Main steel structure | 2017-08-30 | 2017-10-28 | 2017-03-09 | 2018-07-25
Act | 2AI103CV18700-08055 | Not Started | Completed | Alignment/Welding/Bolting | 2017-09-03 | 2017-10-31 | 2017-03-09 | 2018-07-25
Act | 2AI103CV18700-08060 | Not Started | Completed | Torque Bolts (wherever applicable) | 2017-09-06 | 2017-11-04 | 2017-03-09 | 2018-08-22
Act | 2AI103CV18700-08065 | Not Started | Completed | Grouting (wherever applicable) | 2017-09-28 | 2017-11-07 | 2018-08-23 | 2018-08-27
Act | 2AI103CV18700-08070 | Not Started | Completed | Installation of gratings/handrail/ladder | 2017-10-23 | 2017-11-15 | 2017-07-07 | 2018-11-21
8 |  |  |  | EOF: Tank Stairways - Structural Steel Erection 52-D-96
Act | 2AI103CV18700-08075 | Not Started | Completed | Installation of Main steel structure | 2017-09-17 | 2017-11-14 | 2017-03-04 | 2018-08-07
Act | 2AI103CV18700-08080 | Not Started | Completed | Alignment/Welding/Bolting | 2017-09-20 | 2017-11-18 | 2017-03-04 | 2018-09-04
Act | 2AI103CV18700-08085 | Not Started | Completed | Torque Bolts (wherever applicable) | 2017-09-24 | 2017-11-21 | 2017-03-04 | 2018-09-04
Act | 2AI103CV18700-08090 | Not Started | Completed | Grouting (wherever applicable) | 2017-10-16 | 2017-11-25 | 2018-09-26 | 2018-10-01
Act | 2AI103CV18700-08095 | Not Started | Completed | Installation of gratings/handrail/ladder | 2017-11-09 | 2017-12-03 | 2017-07-07 | 2018-11-22
5 |  |  |  | SHELTER ERECTION
6 |  |  |  | EOF: Mobile Foam Cannon and Mobile Monitor Shelter Erection
Act | 2AI103CV18500 | Not Started | Completed | EOF: Mobile Foam Cannon and Mobile Monitor Shelter Erection | 2017-01-11 | 2017-02-25 | 2016-12-07 | 2018-08-12
7 |  |  |  | EOF: Mobile Foam Cannon and Mobile Monitor Shelter Erection
Act | 2AI103CV18500-08001 | Not Started | Completed | EOF:Installation of Str. Steel Mobile Foam Cannon and Mobile Monitor Shelter | 2017-01-11 | 2017-01-29 | 2016-12-07 | 2018-04-26
Act | 2AI103CV18500-08005 | Not Started | Completed | EOF:Alignment & Bolting/Torqueing Mobile Foam Cannon and Mobile Monitor Shelter | 2017-01-29 | 2017-02-12 | 2017-05-11 | 2018-07-26
Act | 2AI103CV18500-08010 | Not Started | Completed | EOF:Grouting Mobile Foam Cannon and Mobile Monitor Shelter | 2017-02-12 | 2017-02-25 | 2018-08-10 | 2018-08-12
Act | 2AI103CV18500-08000 | Not Started | Completed | EOF: Mobile Foam Cannon and Mobile Monitor Shelter Erection | 2017-01-11 | 2017-02-25 | 2016-12-07 | 2018-08-12
5 |  |  |  | MISCELLANEOUS CIVIL WORKS
6 |  |  |  | TRENCH WORKS
7 |  |  |  | EOF: RCC Cable trench
Act | 2AI103CV18300 | Not Started | In Progress | EOF: RCC Cable trench | 2017-01-09 | 2017-12-26 | 2016-12-19
8 |  |  |  | EOF: RCC Cable Trench (New tank area from Substation 621-SUBS-302)
8 |  |  |  | EOF: Cable Trench
Act | 2AI103CV18300-08000 | Not Started | In Progress | EOF: Cable trench | 2017-01-09 | 2017-12-26 | 2016-12-19
9 |  |  |  | EOF: MG-1 SUBSTATION TIE-INS CABLE TRENCH
10 |  |  |  | Cable Trench from MG-1 Substation to 52-SUBST-301
Act | 2AI103CV18300-08035 | Not Started | Completed | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material | 2017-01-09 | 2017-05-17 | 2016-12-19 | 2017-11-09
Act | 2AI103CV18300-08040 | Not Started | Completed | EOF:Sand bedding | 2017-01-23 | 2017-05-29 | 2017-02-28 | 2017-11-11
Act | 2AI103CV18300-08045 | Not Started | Completed | EOF:Install Cable Tile Laying & warning Tapes | 2017-04-05 | 2017-08-07 | 2017-03-23 | 2018-01-04
Act | 2AI103CV18300-08050 | Not Started | Completed | EOF:Backfilling & Compaction | 2017-05-15 | 2017-08-19 | 2017-04-16 | 2018-01-06
Act | 2AI103CV18300-08055 | Not Started | Completed | EOF:Install Route/saftey Markers | 2017-08-19 | 2017-09-05 | 2017-07-18 | 2018-11-23
Act | 2AI103CV18300-08041 | Not Started | Completed | EOF:Sand Padding | 2017-04-01 | 2017-08-05 | 2017-03-22 | 2018-01-03
9 |  |  |  | EOF: POWER CABLE BETWEEN SUBSTATION
10 |  |  |  | EOF: Power Cable in boundery limit of 52-SUBST-301/50-SUBST-001/52-SUBST-302/52-SUBST-303
10 |  |  |  | Cable Trench from 52-SUBST-301 to 52-SUBST-302
10 |  |  |  | Cable Trench from 52-SUBST-301 to 52-SUBST-303
9 |  |  |  | EOF: POWER CABLE FROM SUBSTATION
10 |  |  |  | Cable Trench from 52-SUBST-301 to Filling Mixing Manifold Transformers
10 |  |  |  | LV Power Cable laying from 50-SUBST-001 to COCC Building Transformers
Act | 2AI103CV18300-08125 | Not Started | Completed | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material | 2017-03-04 | 2017-06-05 | 2018-07-01 | 2018-07-02
Act | 2AI103CV18300-08135 | Not Started | Completed | EOF:Sand bedding | 2017-03-07 | 2017-06-07 | 2018-07-03 | 2018-07-03
Act | 2AI103CV18300-08145 | Not Started | Completed | EOF:Install Cable Tile Laying & warning Tapes | 2017-03-19 | 2017-07-05 | 2018-07-06 | 2018-07-06
Act | 2AI103CV18300-08150 | Not Started | Completed | EOF:Backfilling & Compaction | 2017-05-10 | 2017-07-17 | 2018-07-07 | 2018-07-07
Act | 2AI103CV18300-08155 | Not Started | Completed | EOF:Install Route/saftey Markers | 2017-07-17 | 2017-08-07 | 2018-07-07 | 2018-07-07
Act | 2AI103CV18300-08136 | Not Started | Completed | EOF:Sand Padding | 2017-03-05 | 2017-06-05 | 2018-07-07 | 2018-07-07
10 |  |  |  | LV Power Cable laying from 52-SUBST-302 to Storage Tanks Transformer
Act | 2AI103CV18300-08160 | Not Started | In Progress | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material | 2017-03-04 | 2017-06-05 | 2017-05-01
Act | 2AI103CV18300-08165 | Not Started | In Progress | EOF:Sand bedding | 2017-03-07 | 2017-06-07 | 2017-05-04
Act | 2AI103CV18300-08170 | Not Started | In Progress | EOF:Install Cable Tile Laying & warning Tapes | 2017-03-19 | 2017-07-05 | 2017-07-29
Act | 2AI103CV18300-08175 | Not Started | In Progress | EOF:Backfilling & Compaction | 2017-05-10 | 2017-07-17 | 2017-07-31
Act | 2AI103CV18300-08180 | Not Started | Not Started | EOF:Install Route/saftey Markers | 2017-07-17 | 2017-08-07
Act | 2AI103CV18300-08166 | Not Started | In Progress | EOF:Sand Padding | 2017-03-05 | 2017-06-05 | 2017-06-24
10 |  |  |  | LV Power Cable laying from 52-SUBST-302 to Loading Mixing Manifold
9 |  |  |  | EOF: INSTRUMENTATION CABLE FROM SUBSTATION
10 |  |  |  | Instrument Cable laying from 52-SUBST-301 to Filling Mixing Manifold Junction Boxes
10 |  |  |  | Instrument Cable laying from 52-SUBST-302 to Storage Tank Junction Boxes
Act | 2AI103CV18300-08285 | Not Started | In Progress | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material | 2017-02-14 | 2017-05-18 | 2017-03-04
Act | 2AI103CV18300-08290 | Not Started | In Progress | EOF:Sand bedding | 2017-02-18 | 2017-05-21 | 2017-03-05
Act | 2AI103CV18300-08295 | Not Started | In Progress | EOF:Install Cable Tile Laying & warning Tapes | 2017-03-19 | 2017-07-05 | 2017-11-07
Act | 2AI103CV18300-08300 | Not Started | In Progress | EOF:Backfilling & Compaction | 2017-05-10 | 2017-07-17 | 2017-11-21
Act | 2AI103CV18300-08305 | Not Started | Not Started | EOF:Install Route/saftey Markers | 2017-07-17 | 2017-07-29
Act | 2AI103CV18300-08291 | Not Started | In Progress | EOF:Sand Padding | 2017-03-16 | 2017-06-17 | 2017-05-21
9 |  |  |  | EOF: FIRE ALARM CABLE WORKS
10 |  |  |  | Fire Alarm Cable Laying from 52-SUBST-301 to Filling Mixing Manifold Junction Boxes
10 |  |  |  | Fire Alarm Cable Laying from 52-SUBST-301 to Storage Tank Junction Boxes
Act | 2AI103CV18300-08335 | Not Started | Completed | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material | 2017-07-18 | 2017-10-19 | 2018-06-13 | 2018-06-18
Act | 2AI103CV18300-08340 | Not Started | Completed | EOF:Sand bedding | 2017-08-01 | 2017-10-24 | 2018-06-27 | 2018-07-02
Act | 2AI103CV18300-08345 | Not Started | Completed | EOF:Install Cable Tile Laying & warning Tapes | 2017-08-17 | 2017-10-30 | 2018-07-13 | 2018-07-18
Act | 2AI103CV18300-08350 | Not Started | Completed | EOF:Backfilling & Compaction | 2017-08-26 | 2017-11-01 | 2018-07-22 | 2018-07-27
Act | 2AI103CV18300-08355 | Not Started | Not Started | EOF:Install Route/saftey Markers | 2017-11-01 | 2017-11-13
Act | 2AI103CV18300-08341 | Not Started | Completed | EOF:Sand Padding | 2017-08-05 | 2017-10-28 | 2018-07-01 | 2018-07-06
9 |  |  |  | EOF: TELECOM CABLE LAYING TO COCC
10 |  |  |  | Fiber Optic Cable Laying from in boundery Limt of COCC Area
Act | 2AI103CV18300-08360 | Not Started | Completed | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material | 2017-04-04 | 2017-07-06 | 2018-06-02 | 2018-12-23
Act | 2AI103CV18300-08365 | Not Started | Completed | EOF:Sand bedding | 2017-04-08 | 2017-07-09 | 2018-06-04 | 2018-12-24
Act | 2AI103CV18300-08370 | Not Started | Completed | EOF:Install Cable Tile Laying & warning Tapes | 2017-05-04 | 2017-07-23 | 2018-06-20 | 2019-01-30
Act | 2AI103CV18300-08375 | Not Started | Completed | EOF:Backfilling & Compaction | 2017-05-18 | 2017-07-25 | 2018-06-22 | 2019-01-31
Act | 2AI103CV18300-08380 | Not Started | Not Started | EOF:Install Route/saftey Markers | 2017-07-25 | 2017-08-06
Act | 2AI103CV18300-08366 | Not Started | Completed | EOF:Sand Padding | 2017-04-19 | 2017-07-20 | 2018-06-21 | 2019-01-31
9 |  |  |  | EOF: TELECOM CABLE LAYING FROM COCC TO SUBSTATION
10 |  |  |  | Fiber Optic Cable Laying from New COCC to 52-SUBST-301
10 |  |  |  | Fiber Optic Cable Laying from New COCC to 50-SUBST-001
10 |  |  |  | Fiber Optic Cable Laying from boundery limit to 52-SUBST-302
Act | 2AI103CV18300-08435 | Not Started | Completed | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material | 2017-04-04 | 2017-07-24 | 2018-03-29 | 2018-06-12
Act | 2AI103CV18300-08440 | Not Started | Completed | EOF:Sand bedding | 2017-07-24 | 2017-11-05 | 2018-03-31 | 2018-06-14
Act | 2AI103CV18300-08445 | Not Started | Completed | EOF:Install Cable Tile Laying & warning Tapes | 2017-09-20 | 2017-12-14 | 2018-04-04 | 2018-06-18
Act | 2AI103CV18300-08450 | Not Started | Completed | EOF:Backfilling & Compaction | 2017-10-02 | 2017-12-20 | 2018-04-06 | 2018-06-20
Act | 2AI103CV18300-08455 | Not Started | Completed | EOF:Install Route/saftey Markers | 2017-11-27 | 2017-12-26 | 2018-04-08 | 2018-06-21
Act | 2AI103CV18300-08441 | Not Started | Completed | EOF:Sand Padding | 2017-08-30 | 2017-12-12 | 2018-04-02 | 2018-06-16
10 |  |  |  | Fiber Optic Cable Laying from New COCC to 52-SUBST-303
6 |  |  |  | EOF: Road crossings & EIT Duct banks
Act | 2AI103CV19000 | Not Started | Completed | EOF: Road crossings & EIT Duct banks | 2016-07-21 | 2016-12-19 | 2016-06-26 | 2018-09-26
7 |  |  |  | EOF: EIT Duct banks
Act | 2AI103CV19000-08001 | Not Started | Completed | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material | 2016-07-21 | 2016-11-21 | 2016-06-26 | 2018-08-07
Act | 2AI103CV19000-08005 | Not Started | Completed | EOF:Blinding/PCC for Ductbank | 2016-07-25 | 2016-11-24 | 2016-07-03 | 2018-08-16
Act | 2AI103CV19000-08010 | Not Started | Completed | EOF:Rebar, Formwork & PVC conduits installation for Duct Bank | 2016-07-31 | 2016-11-30 | 2016-07-04 | 2017-07-21
Act | 2AI103CV19000-08015 | Not Started | Completed | EOF:Concrete Potection | 2016-08-20 | 2016-12-14 | 2016-07-28 | 2018-05-08
Act | 2AI103CV19000-08020 | Not Started | Completed | EOF:Backfilling & Compaction | 2016-08-24 | 2016-12-19 | 2016-08-06 | 2018-09-26
Act | 2AI103CV19000-08011 | Not Started | Completed | EOF:Concrete Pouring | 2016-08-07 | 2016-12-07 | 2016-07-12 | 2017-07-22
Act | 2AI103CV19000-08000 | Not Started | Completed | EOF: EIT Duct banks | 2016-07-21 | 2016-12-19 | 2016-06-26 | 2018-09-26
5 |  |  |  | EOF: UG, Trenches & other Civil Works
Act | 2AI102CV01500 | Not Started | In Progress | EOF: UG, Trenches & other Civil Works | 2017-02-05 | 2017-10-24 | 2016-07-21
6 |  |  |  | EOF: HSE Safety Equipments & Safety Misc. Foundation
Act | 2AI102CV01500-08000 | Not Started | In Progress | EOF: HSE Safety Equipments & Safety Misc. Foundation | 2017-05-02 | 2017-10-24 | 2016-11-29
Act | 2AI102CV01500-08121 | Not Started | In Progress | EOF: HSE Safety Equipments & Safety Misc. Foundation | 2017-05-02 | 2017-10-24 | 2016-11-29
6 |  |  |  | EOF: Pipe Supports & Pipe Sleepers
Act | 2AI102CV01500-08015 | Not Started | Completed | EOF: Pipe Supports / Pipe Sleepers | 2017-02-18 | 2017-08-17 | 2016-07-21 | 2018-10-30
Act | 2AI102CV01500-08122 | Not Started | Completed | EOF: Pipe Supports & Pipe Sleepers | 2017-02-18 | 2017-08-17 | 2016-07-21 | 2018-10-30
6 |  |  |  | EOF: EIT Supports
Act | 2AI102CV01500-08020 | Not Started | In Progress | EOF: EIT items Misc. Foundation | 2017-02-05 | 2017-06-25 | 2016-11-05
Act | 2AI102CV01500-08123 | Not Started | In Progress | EOF: EIT items Misc. Foundation | 2017-02-05 | 2017-06-25 | 2016-11-05
5 |  |  |  | U/G WORKS: SUMP/DRAIN PITS, MH, etc.
6 |  |  |  | EOF: Construction of Sumps
7 |  |  |  | EOF: Manholes & Miscellaneous Drain Pits
Act | 2AI103CV19700-08001 | Not Started | Completed | EOF:Excavation & Subgrade | 2016-09-18 | 2016-12-26 | 2016-07-11 | 2018-12-20
Act | 2AI103CV19700-08006 | Not Started | Completed | EOF:Blinding/PCC for Sump | 2016-09-24 | 2017-01-01 | 2016-07-21 | 2018-12-24
Act | 2AI103CV19700-08010 | Not Started | Completed | EOF:Rebar, Formwork for base | 2016-09-29 | 2017-01-07 | 2016-08-11 | 2018-12-26
Act | 2AI103CV19700-08015 | Not Started | Completed | EOF:Rebar, Formwork for wall | 2016-10-13 | 2017-01-21 | 2016-08-28 | 2019-01-05
Act | 2AI103CV19700-08020 | Not Started | In Progress | EOF:Concrete Potection | 2016-11-06 | 2017-02-13 | 2016-09-02
Act | 2AI103CV19700-08025 | Not Started | In Progress | EOF:Coverslab | 2017-01-02 | 2017-02-21 | 2016-09-02
Act | 2AI103CV19700-08030 | Not Started | In Progress | EOF:Backfilling & Compaction | 2017-01-08 | 2017-02-27 | 2016-10-06
Act | 2AI103CV19700 | Not Started | In Progress | EOF: Miscellaneous Drain Pits | 2016-09-18 | 2017-02-27 | 2016-07-11
Act | 2AI103CV19700-08011 | Not Started | Completed | EOF:Concrete Pouring for base | 2016-10-11 | 2017-01-18 | 2016-08-21 | 2018-12-28
Act | 2AI103CV19700-08016 | Not Started | Completed | EOF:Concrete Pouring for wall | 2016-10-25 | 2017-02-01 | 2016-09-24 | 2019-04-10
Act | 2AI103CV19700-08005 | Not Started | In Progress | EOF: Miscellaneous Drain Pits | 2016-09-18 | 2017-02-27 | 2016-07-11
6 |  |  |  | EOF: Sanitary/Sewer drain, Pits & manholes
Act | 2AI103CV19800 | Not Started | In Progress | EOF: Sanitary / Sewer Drains / Valve Pit & Manholes | 2016-10-05 | 2017-04-27 | 2016-10-04
7 |  |  |  | EOF: Sanitary / Sewer Drains
Act | 2AI103CV19800-08001 | Not Started | Completed | EOF:Excavation & Subgrade | 2016-10-05 | 2017-03-12 | 2016-10-04 | 2019-04-10
Act | 2AI103CV19800-08005 | Not Started | Completed | EOF:Blinding/PCC for Sanitary/Sewer drain, Pits & manholes | 2016-10-08 | 2017-03-14 | 2016-10-04 | 2019-04-11
Act | 2AI103CV19800-08010 | Not Started | Completed | EOF:Rebar, Formwork for base & Wall | 2016-10-19 | 2017-03-26 | 2016-10-04 | 2019-04-12
Act | 2AI103CV19800-08015 | Not Started | Completed | EOF:Rebar, Formwork for Cover slab | 2016-10-26 | 2017-04-02 | 2016-10-20 | 2019-04-12
Act | 2AI103CV19800-08020 | Not Started | In Progress | EOF:Concrete Potection | 2016-11-13 | 2017-04-19 | 2016-11-16
Act | 2AI103CV19800-08025 | Not Started | In Progress | EOF:Installation of Manhole/Pit Cover | 2016-11-28 | 2017-04-23 | 2016-11-16
Act | 2AI103CV19800-08030 | Not Started | In Progress | EOF:Backfilling & Compaction | 2016-12-03 | 2017-04-27 | 2016-11-20
Act | 2AI103CV19800-08011 | Not Started | Completed | EOF:Concrete Pouring for base & Wall | 2016-10-23 | 2017-03-29 | 2016-10-13 | 2019-04-12
Act | 2AI103CV19800-08016 | Not Started | Completed | EOF:Concrete Pouring for cover slab | 2016-11-01 | 2017-04-08 | 2016-11-09 | 2019-04-13
Act | 2AI103CV19800-08000 | Not Started | In Progress | EOF: Sanitary / Sewer Drains | 2016-10-05 | 2017-04-27 | 2016-10-04
5 |  |  |  | DEMOLISION/ MODIFICATION WORK
6 |  |  |  | EOF: Existing Road & Fence Demolition Works
Act | 2AI103CV28220 | Not Started | In Progress | EOF: Existing Road & Fence Demolition Works | 2016-08-09 | 2017-09-14 | 2016-09-10
7 |  |  |  | EOF:Demolition Work - New Tank Area - 621
Act | 2AI103CV28220-08001 | Not Started | Completed | EOF:Demolition Works - Existing Road | 2017-04-27 | 2017-09-14 | 2016-09-10 | 2016-09-14
Act | 2AI103CV28220-08006 | Not Started | Not Started | EOF:Demolition Works - Existing Fence | 2016-12-31 | 2017-05-20
Act | 2AI103CV28220-08000 | Not Started | In Progress | EOF:Demolition Work Existing Road & Existing Fence- New Tank Area - 621 | 2016-12-31 | 2017-09-14 | 2016-09-10
7 |  |  |  | EOF:New Fencing Work - New Tank Area - 621
Act | 2AI103CV28220-08015 | Not Started | In Progress | EOF:Survey marking & Excavation for Fence Post | 2016-08-09 | 2016-10-24 | 2017-04-29
Act | 2AI103CV28220-08020 | Not Started | In Progress | EOF:Fence Post installation | 2016-10-30 | 2017-01-02 | 2017-05-07
Act | 2AI103CV28220-08025 | Not Started | In Progress | EOF:Fence Mesh Installation | 2016-11-02 | 2017-02-07 | 2017-08-06
Act | 2AI103CV28220-08016 | Not Started | In Progress | EOF:Sub grade & Blinding | 2016-10-24 | 2016-12-27 | 2017-05-07 | [67 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [8 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [8 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [8 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [8 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  |  |  | 13
Act | 2AI103CV28220-08017 | Not Started | In Progress | EOF:Install/Cast insitu fencing fnds | 2016-10-27 | 2016-12-31 | 2016-11-20
Act | 2AI103CV28220-08026 | Not Started | In Progress | EOF:Gate Installation & Speed bumbs | 2017-01-03 | 2017-02-19 | 2018-11-05
Act | 2AI103CV28220-08005 | Not Started | In Progress | EOF:New Fencing Work - New Tank Area - 621 | 2016-08-09 | 2017-02-19 | 2016-11-20
5 |  |  |  | ROADS & PAVING
6 |  |  |  | EOF: Roads, Crossing & Paving Works
Act | 2AI103CV19100 | Not Started | In Progress | EOF: Roads, Crossing & Paving Works | 2016-09-19 | 2017-10-10 | 2019-03-20
7 |  |  |  | EOF:Asphalt Road Work
Act | 2AI103CV19100-08001 | Not Started | Completed | EOF:Grading & leveling | 2016-11-23 | 2017-01-31 | 2019-03-20 | 2019-04-10 | [66 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [8 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [8 empty] | 2 | [9 empty] | 27 | [9 empty] | 28 | [8 empty] | 26 | [9 empty] | 26 | [9 empty] | 35 | [9 empty] | 63 | [8 empty] | 0 | [9 empty] | 62 | [9 empty] | 4 |  |  |  |  | 0
Act | 2AI103CV19100-08006 | Not Started | Completed | EOF:Preparation of sub grade | 2016-11-29 | 2017-04-11 | 2019-03-23 | 2019-04-10 | [66 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [8 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [8 empty] | 2 | [9 empty] | 27 | [9 empty] | 28 | [8 empty] | 26 | [9 empty] | 26 | [9 empty] | 35 | [9 empty] | 63 | [8 empty] | 0 | [9 empty] | 62 | [9 empty] | 3 |  |  |  |  | 0
Act | 2AI103CV19100-08011 | Not Started | In Progress | EOF:Asphalt Work | 2017-04-29 | 2017-10-10 | 2019-03-31 | [67 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [8 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [8 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [8 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [8 empty] | 55 | [9 empty] | 0 | [9 empty] | 0 |  |  |  |  | 0
Act | 2AI103CV19100-08016 | Not Started | Not Started | EOF:Kerb-stone installation | 2017-04-11 | 2017-06-14 | [68 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [8 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [8 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [8 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [8 empty] | 56 | [9 empty] | 0 | [9 empty] | 0 |  |  |  |  | 0
Act | 2AI103CV19100-08020 | Not Started | Not Started | EOF:Bollards & Crash barrier installation | 2017-06-14 | 2017-07-25
Act | 2AI103CV19100-08005 | Not Started | In Progress | EOF:Asphalt Road Work | 2016-11-23 | 2017-10-10 | 2019-03-20
7 |  |  |  | EOF:Gutch Road Work
Act | 2AI103CV19100-08025 | Not Started | Not Started | EOF:Excavation | 2016-09-19 | 2016-10-18
Act | 2AI103CV19100-08030 | Not Started | Not Started | EOF:Grading & leveling | 2016-10-18 | 2016-11-15
Act | 2AI103CV19100-08035 | Not Started | Not Started | EOF:Gatch Filling | 2016-11-15 | 2016-12-08
Act | 2AI103CV19100-08040 | Not Started | Not Started | EOF:Compaction | 2016-12-08 | 2016-12-25
Act | 2AI103CV19100-08000 | Not Started | Not Started | EOF:Gutch Road Work | 2016-09-19 | 2016-12-25
7 |  |  |  | EOF:Reinforced Concrete Paving
Act | 2AI103CV19100-08045 | Not Started | Not Started | EOF:Excavation | 2017-01-12 | 2017-02-12
Act | 2AI103CV19100-08050 | Not Started | Not Started | EOF:Grading & leveling | 2017-02-12 | 2017-03-14
Act | 2AI103CV19100-08055 | Not Started | Not Started | EOF:Preparation of sub grade | 2017-03-14 | 2017-04-08
Act | 2AI103CV19100-08060 | Not Started | Not Started | EOF:Concrete Work | 2017-04-08 | 2017-05-03
Act | 2AI103CV19100-08010 | Not Started | Not Started | EOF:Reinforced Concrete Paving | 2017-01-12 | 2017-05-03
7 |  |  |  | EOF:Asphalt Paving
Act | 2AI103CV19100-08065 | Not Started | In Progress | EOF:Excavation | 2017-01-12 | 2017-03-14 | 2019-04-08
Act | 2AI103CV19100-08070 | Not Started | In Progress | EOF:Grading & leveling | 2017-02-06 | 2017-03-20 | 2019-04-08
Act | 2AI103CV19100-08075 | Not Started | In Progress | EOF:Preparation of sub grade | 2017-02-09 | 2017-03-23 | 2019-04-08
Act | 2AI103CV19100-08080 | Not Started | Not Started | EOF:Asphalt Work | 2017-03-23 | 2017-05-03
Act | 2AI103CV19100-08015 | Not Started | In Progress | EOF:Asphalt Paving | 2017-01-12 | 2017-05-03 | 2019-04-08
4 |  |  |  | HSE
5 |  |  |  | EOF: Installation of Fire fighting & Safety Equipments
Act | 2AI103HS01110-08001 | Not Started | Not Started | EOF: Installation of Fire fighting & Safety Equipments | 2017-08-22 | 2017-10-31
Act | 2AI103HS01110 | Not Started | Not Started | EOF: Installation of Fire fighting & Safety Equipments | 2017-08-22 | 2017-10-31
Act | 2AI103HS01110-08000 | Not Started | Not Started | EOF: Installation of Fire fighting & Safety Equipments | 2017-08-22 | 2017-10-31
5 |  |  |  | EOF: Installation of Safety Sign Boards
Act | 2AI103HS01120-08001 | Not Started | Not Started | EOF:Installation - Indoor Safety Signs | 2017-10-30 | 2017-12-27
Act | 2AI103HS01120-08005 | Not Started | Not Started | EOF:Installation - Outdoor Safety Signs | 2017-10-07 | 2017-12-27
Act | 2AI103HS01120 | Not Started | Not Started | EOF: Installation of Safety Sign Boards | 2017-10-07 | 2017-12-27
Act | 2AI103HS01120-08000 | Not Started | Not Started | EOF: Installation of Safety Sign Boards | 2017-10-07 | 2017-12-27
4 |  |  |  | MECHANICAL - STATIC
5 |  |  |  | EOF: Tank Erection
Act | 2AI103MS19900 | Not Started | Completed | EOF: Tank Erection | 2017-06-08 | 2017-07-31 | 2018-10-30 | 2019-04-13
6 |  |  |  | EOF: Diesel Fuel Tank 621-D307 A/B Erection
Act | 2AI103MS19900-08001 | Not Started | Completed | EOF:Foundation checks/Preparation for Equipment | 2017-06-08 | 2017-06-10 | 2018-10-30 | 2018-10-30
Act | 2AI103MS19900-08006 | Not Started | Completed | EOF:Installation of Structural Support, Platforms & ladders of Equipment | 2017-06-10 | 2017-06-13 | 2018-10-30 | 2018-10-30
Act | 2AI103MS19900-08010 | Not Started | Completed | EOF:Installation of Diesel Fuel Tank 621-D307 A/B | 2017-06-13 | 2017-06-19 | 2018-10-30 | 2018-10-30
Act | 2AI103MS19900-08015 | Not Started | Completed | EOF:Preliminary Allignment & Grouting of Equipment | 2017-06-19 | 2017-06-21 | 2018-11-08 | 2018-12-01
Act | 2AI103MS19900-08020 | Not Started | Completed | EOF:Final Allignment & Grouting of Equipment | 2017-06-21 | 2017-06-25 | 2019-04-08 | 2019-04-11
Act | 2AI103MS19900-08025 | Not Started | Completed | EOF:Install internals of Equipment | 2017-06-25 | 2017-06-28 | 2019-04-08 | 2019-04-12
Act | 2AI103MS19900-08030 | Not Started | Completed | EOF:QC checks & clearance for Equipment | 2017-06-28 | 2017-06-29 | 2019-04-08 | 2019-04-13
Act | 2AI103MS19900-08000 | Not Started | Completed | EOF: Erection of Diesel Fuel Tank (52-D-307 A/B) | 2017-06-08 | 2017-06-29 | 2018-10-30 | 2019-04-13
6 |  |  |  | EOF: Diesel Fuel Tank 621-D307 C/D Erection
Act | 2AI103MS19900-08035 | Not Started | Completed | EOF:Foundation checks/Preparation for Equipment | 2017-07-10 | 2017-07-11 | 2018-11-04 | 2018-11-04
Act | 2AI103MS19900-08040 | Not Started | Completed | EOF:Installation of Structural Support, Platforms & ladders of Equipment | 2017-07-11 | 2017-07-15 | 2018-11-04 | 2018-11-04
Act | 2AI103MS19900-08045 | Not Started | Completed | EOF:Installation of Diesel Fuel Tank 621-D307 C/D | 2017-07-15 | 2017-07-20 | 2018-11-04 | 2018-11-04
Act | 2AI103MS19900-08050 | Not Started | Completed | EOF:Preliminary Allignment & Grouting of Equipment | 2017-07-20 | 2017-07-23 | 2018-11-12 | 2018-11-12
Act | 2AI103MS19900-08055 | Not Started | Completed | EOF:Final Allignment & Grouting of Equipment | 2017-07-23 | 2017-07-26 | 2019-04-08 | 2019-04-11
Act | 2AI103MS19900-08060 | Not Started | Completed | EOF:Install internals of Equipment | 2017-07-26 | 2017-07-30 | 2019-04-08 | 2019-04-12
Act | 2AI103MS19900-08065 | Not Started | Completed | EOF:QC checks & clearance for Equipment | 2017-07-30 | 2017-07-31 | 2019-04-08 | 2019-04-13
Act | 2AI103MS19900-08005 | Not Started | Completed | EOF: Erection of Diesel Fuel Tank (52-D-307 C/D) | 2017-07-10 | 2017-07-31 | 2018-11-04 | 2019-04-13
5 |  |  |  | EOF: Other Equipments (H2S Scrubber, PIG Receiver, Vessel etc)
Act | 2AI103MS20000 | Not Started | Completed | EOF: Other Equipments (H2S Scrubber, PIG Receiver, Vessel etc) | 2017-06-22 | 2017-07-08 | 2017-02-06 | 2018-11-07
6 |  |  |  | EOF: Oily Water Transfer Vessel 621-V-301Erection
Act | 2AI103MS20000-08001 | Not Started | Completed | EOF:Foundation checks/Preparation for Equipment | 2017-06-22 | 2017-06-24 | 2017-02-06 | 2017-02-08
Act | 2AI103MS20000-08005 | Not Started | Completed | EOF:Installation of 621-V-301 Oily Water Collection Vessel | 2017-06-24 | 2017-06-26 | 2017-04-26 | 2017-04-26
Act | 2AI103MS20000-08010 | Not Started | Completed | EOF:Preliminary Allignment & Grouting of Equipment | 2017-06-26 | 2017-06-28 | 2017-04-26 | 2017-04-26
Act | 2AI103MS20000-08015 | Not Started | Completed | EOF:Final Allignment & Grouting of Equipment | 2017-06-28 | 2017-06-29 | 2017-05-02 | 2017-05-03
Act | 2AI103MS20000-08020 | Not Started | Completed | EOF:Install Platforms & ladders of Equipment | 2017-06-29 | 2017-07-03 | 2018-04-15 | 2018-06-20
Act | 2AI103MS20000-08025 | Not Started | Completed | EOF:Install internals of Equipment | 2017-07-03 | 2017-07-06 | 2018-11-05 | 2018-11-07
Act | 2AI103MS20000-08030 | Not Started | Completed | EOF:QC checks & clearance for Equipment | 2017-07-06 | 2017-07-08 | 2017-05-08 | 2017-05-10
Act | 2AI103MS20000-08000 | Not Started | Completed | EOF: Oily Water Transfer Vessel 621-V-301Erection | 2017-06-22 | 2017-07-08 | 2017-02-06 | 2018-11-07
4 |  |  |  | MECHANICAL - ROTATING
5 |  |  |  | EOF: Pump Erection
Act | 2AI103MR18900 | Not Started | Completed | EOF: Pump Erection | 2017-08-03 | 2017-09-02 | 2018-04-02 | 2018-11-07
6 |  |  |  | EOF: 621-G-302 A Foam Pump Erection
Act | 2AI103MR18900-08001 | Not Started | Completed | EOF:Foundation checks/Preparation for Equipment 621-G-302 A Foam Pump Erection | 2017-08-03 | 2017-08-05 | 2018-04-04 | 2018-04-05
Act | 2AI103MR18900-08002 | Not Started | Completed | EOF:Installation of Equipment 621-G-302 A Foam Pump Erection | 2017-08-05 | 2017-08-08 | 2018-04-08 | 2018-04-08
Act | 2AI103MR18900-08006 | Not Started | Completed | EOF:Preliminary Allignment & Grouting of Equipment 621-G-302 A Foam Pump Erection | 2017-08-08 | 2017-08-10 | 2018-04-02 | 2018-04-04
Act | 2AI103MR18900-08011 | Not Started | Completed | EOF:Final Allignment & Grouting of Equipment 621-G-302 A Foam Pump Erection | 2017-08-10 | 2017-08-14 | 2018-04-02 | 2018-04-04
Act | 2AI103MR18900-08016 | Not Started | Completed | EOF:QC checks & clearance for Equipment 621-G-302 A Foam Pump Erection | 2017-08-14 | 2017-08-15 | 2018-11-05 | 2018-11-07
Act | 2AI103MR18900-08000 | Not Started | Completed | EOF: 621-G-302 A Foam Pump Erection | 2017-08-03 | 2017-08-15 | 2018-04-02 | 2018-11-07
6 |  |  |  | EOF: 621-G-302 B Foam Pump Erection
Act | 2AI103MR18900-08025 | Not Started | Completed | EOF:Foundation checks/Preparation for Equipment 621-G-302 B Foam Pump Erection | 2017-08-09 | 2017-08-10 | 2018-04-02 | 2018-04-05
Act | 2AI103MR18900-08030 | Not Started | Completed | EOF:Installation of Equipment 621-G-302 B Foam Pump Erection | 2017-08-10 | 2017-08-14 | 2018-04-08 | 2018-04-08
Act | 2AI103MR18900-08035 | Not Started | Completed | EOF:Preliminary Allignment & Grouting of Equipment 621-G-302 B Foam Pump Erection | 2017-08-14 | 2017-08-16 | 2018-04-02 | 2018-04-04
Act | 2AI103MR18900-08040 | Not Started | Completed | EOF:Final Allignment & Grouting of Equipment 621-G-302 B Foam Pump Erection | 2017-08-16 | 2017-08-20 | 2018-04-02 | 2018-04-04
Act | 2AI103MR18900-08045 | Not Started | Completed | EOF:QC checks & clearance for Equipment 621-G-302 B Foam Pump Erection | 2017-08-20 | 2017-08-21 | 2018-11-05 | 2018-11-07
Act | 2AI103MR18900-08005 | Not Started | Completed | EOF: 621-G-302 B Foam Pump Erection | 2017-08-09 | 2017-08-21 | 2018-04-02 | 2018-11-07
6 |  |  |  | EOF: 621-G-302 C Foam Pump Erection
Act | 2AI103MR18900-08050 | Not Started | Completed | EOF:Foundation checks/Preparation for Equipment 621-G-302 C Foam Pump Erection | 2017-08-15 | 2017-08-16 | 2018-04-04 | 2018-04-05
Act | 2AI103MR18900-08055 | Not Started | Completed | EOF:Installation of Equipment 621-G-302 C Foam Pump Erection | 2017-08-16 | 2017-08-20 | 2018-04-08 | 2018-04-08
Act | 2AI103MR18900-08060 | Not Started | Completed | EOF:Preliminary Allignment & Grouting of Equipment 621-G-302 C Foam Pump Erection | 2017-08-20 | 2017-08-22 | 2018-04-02 | 2018-04-04
Act | 2AI103MR18900-08065 | Not Started | Completed | EOF:Final Allignment & Grouting of Equipment 621-G-302 C Foam Pump Erection | 2017-08-22 | 2017-08-26 | 2018-04-02 | 2018-04-04
Act | 2AI103MR18900-08070 | Not Started | Completed | EOF:QC checks & clearance for Equipment 621-G-302 C Foam Pump Erection | 2017-08-26 | 2017-08-27 | 2018-09-16 | 2018-09-16
Act | 2AI103MR18900-08010 | Not Started | Completed | EOF: 621-G-302 C Foam Pump Erection | 2017-08-15 | 2017-08-27 | 2018-04-02 | 2018-09-16
6 |  |  |  | EOF: 621-G-302 D Foam Pump Erection
Act | 2AI103MR18900-08075 | Not Started | Completed | EOF:Foundation checks/Preparation for Equipment 621-G-302 D Foam Pump Erection | 2017-08-21 | 2017-08-22 | 2018-04-04 | 2018-04-05
Act | 2AI103MR18900-08080 | Not Started | Completed | EOF:Installation of Equipment 621-G-302 D Foam Pump Erection | 2017-08-22 | 2017-08-26 | 2018-04-08 | 2018-04-08
Act | 2AI103MR18900-08085 | Not Started | Completed | EOF:Preliminary Allignment & Grouting of Equipment 621-G-302 D Foam Pump Erection | 2017-08-26 | 2017-08-28 | 2018-04-09 | 2018-04-09
Act | 2AI103MR18900-08090 | Not Started | Completed | EOF:Final Allignment & Grouting of Equipment 621-G-302 D Foam Pump Erection | 2017-08-28 | 2017-08-31 | 2018-04-11 | 2018-04-11
Act | 2AI103MR18900-08095 | Not Started | Completed | EOF:QC checks & clearance for Equipment 621-G-302 D Foam Pump Erection | 2017-08-31 | 2017-09-02 | 2018-09-03 | 2018-09-05
Act | 2AI103MR18900-08015 | Not Started | Completed | EOF: 621-G-302 D Foam Pump Erection | 2017-08-21 | 2017-09-02 | 2018-04-04 | 2018-09-05
5 |  |  |  | EOF: Foam System Package (52-Z-301 A/B) Erection
Act | 2AI103MR19300 | Not Started | Completed | EOF: Foam System Package (52-Z-301 A/B) Erection | 2017-05-16 | 2017-06-01 | 2018-04-03 | 2018-11-07
6 |  |  |  | EOF: Foam System Package (52-Z-301 A) Erection
Act | 2AI103MR19300-08001 | Not Started | Completed | EOF:Foundation checks/Preparation for Equipment | 2017-05-22 | 2017-05-23 | 2018-04-03 | 2018-04-04
Act | 2AI103MR19300-08006 | Not Started | Completed | EOF:Installation of Foam System Package (52-Z-301 A/B) Erection | 2017-05-23 | 2017-05-27 | 2018-04-08 | 2018-04-08
Act | 2AI103MR19300-08010 | Not Started | Completed | EOF:Preliminary Allignment & Grouting of Equipment | 2017-05-27 | 2017-05-29 | 2018-04-18 | 2018-04-18
Act | 2AI103MR19300-08015 | Not Started | Completed | EOF:Final Allignment & Grouting of Equipment | 2017-05-29 | 2017-05-31 | 2018-08-07 | 2018-08-07
Act | 2AI103MR19300-08020 | Not Started | Completed | EOF:QC checks & clearance for Equipment | 2017-05-31 | 2017-06-01 | 2018-11-05 | 2018-11-07
Act | 2AI103MR19300-08000 | Not Started | Completed | EOF: Foam System Package (52-Z-301 A) Erection | 2017-05-22 | 2017-06-01 | 2018-04-03 | 2018-11-07
6 |  |  |  | EOF: Foam System Package (52-Z-301 B) Erection
Act | 2AI103MR19300-08025 | Not Started | Completed | EOF:Foundation checks/Preparation for Equipment | 2017-05-16 | 2017-05-17 | 2018-04-03 | 2018-04-04
Act | 2AI103MR19300-08030 | Not Started | Completed | EOF:Installation of Foam System Package (52-Z-301 A/B) Erection | 2017-05-17 | 2017-05-21 | 2018-04-08 | 2018-04-08
Act | 2AI103MR19300-08035 | Not Started | Completed | EOF:Preliminary Allignment & Grouting of Equipment | 2017-05-21 | 2017-05-23 | 2018-04-18 | 2018-04-18
Act | 2AI103MR19300-08040 | Not Started | Completed | EOF:Final Allignment & Grouting of Equipment | 2017-05-23 | 2017-05-25 | 2018-08-06 | 2018-08-28
Act | 2AI103MR19300-08045 | Not Started | Completed | EOF:QC checks & clearance for Equipment | 2017-05-25 | 2017-05-27 | 2018-11-05 | 2018-11-07
Act | 2AI103MR19300-08005 | Not Started | Completed | EOF: Foam System Package (52-Z-301 B) Erection | 2017-05-16 | 2017-05-27 | 2018-04-03 | 2018-11-07
4 |  |  |  | ELECTRICAL
5 |  |  |  | EOF: Demolition, Rerouting of Exisitng UG Cable & Existing RMU
Act | 2AI103CV19820 | Not Started | Completed | EOF: Demolition, Rerouting of Exisitng UG Cable & Existing RMU | 2016-04-06 | 2016-04-25 | 2016-03-23 | 2016-07-02
6 |  |  |  | EOF: Demolition Works of Exisitng UG Cable & Existing RMU
Act | 2AI103CV19820-08006 | Not Started | Completed | EOF: Demolition Works of Exisitng UG Cable & Existing RMU | 2016-04-21 | 2016-04-25 | 2016-07-02 | 2016-07-02
Act | 2AI103CV19820-08000 | Not Started | Completed | EOF: Demolition Works of Exisitng UG Cable & Existing RMU | 2016-04-21 | 2016-04-25 | 2016-07-02 | 2016-07-02
6 |  |  |  | EOF: Rerouting of Exisitng UG Cable & Existing RMU
Act | 2AI103CV19820-08010 | Not Started | Completed | EOF:Laying of UG Cable | 2016-04-06 | 2016-04-17 | 2016-03-23 | 2016-03-26
Act | 2AI103CV19820-08016 | Not Started | Completed | EOF:Cable Jointing | 2016-04-12 | 2016-04-19 | 2016-03-28 | 2016-03-28
Act | 2AI103CV19820-08005 | Not Started | Completed | EOF: Rerouting of Exisitng UG Cable & Existing RMU | 2016-04-06 | 2016-04-19 | 2016-03-23 | 2016-03-28
6 |  |  |  | EOF: Shutdown for Reroting of UG Cable & Existing RMU
Act | 2AI103CV19820-08018 | Not Started | Completed | EOF:Disconnection/isolation of Existing cable | 2016-04-18 | 2016-04-18 | 2016-07-01 | 2016-07-01
Act | 2AI103CV19820-08020 | Not Started | Completed | EOF:Cable termination to RMU | 2016-04-20 | 2016-04-20 | 2016-07-02 | 2016-07-02
Act | 2AI103CV19820-08019 | Not Started | Completed | EOF:Relocation of RMU | 2016-04-19 | 2016-04-20 | 2016-07-02 | 2016-07-02
Act | 2AI103CV19820-08030 | Not Started | Completed | EOF:Cable Jointing to Existing Cable | 2016-04-20 | 2016-04-20 | 2016-07-01 | 2016-07-01
Act | 2AI103CV19820-08015 | Not Started | Completed | EOF: Shutdown for Reroting of UG Cable & Existing RMU | 2016-04-18 | 2016-04-20 | 2016-07-01 | 2016-07-02
3 |  |  |  | TIE-INS : EOF AREA
4 |  |  |  | PIPING
5 |  |  |  | EOF: Piping Tie-Ins works (Fire water line & Oily water line)
Act | 2AI104PI20100-08000 | Not Started | Completed | EOF:Piping Tie-Ins works Fire Water line | 2017-09-25 | 2017-12-07 | 2017-07-17 | 2019-01-24
Act | 2AI104PI20100-08005 | Not Started | Completed | EOF:Piping Tie-Ins works Oily Water line | 2017-08-06 | 2017-12-30 | 2019-01-25 | 2019-02-04
Act | 2AI104PI20100 | Not Started | Completed | EOF: Piping Tie-Ins works (Fire Water line & Oily Water line) | 2017-08-06 | 2017-12-30 | 2017-07-17 | 2019-02-04
4 |  |  |  | ELECTRICAL, INSTRUMENTATION & TELECOM
5 |  |  |  | EOF: E,I&T Tie-Ins works associated with 52-SUBST-301& MG-1 Substation and other EIT Tie-in scope
Act | 2AI104EL20100 | Not Started | In Progress | EOF: E,I&T Tie-Ins works associated with 52-SUBST-301& MG-1 Substation and Other EIT Tie-in scope in EOF Area | 2017-02-26 | 2017-08-02 | 2017-03-05
Act | 2AI104EL20100-08000 | Not Started | In Progress | EOF : Tie-Ins works associated with 11KV Power Cable from MG-1 Substation to 52-SUBST-301 | 2017-02-26 | 2017-08-02 | 2017-03-05
5 |  |  |  | EOF: Power Cable Between Substation
Act | 2AI102EL01000 | Not Started | Completed | EOF: Power Cable Between Substation | 2017-02-02 | 2017-08-02 | 2017-03-06 | 2017-12-06
Act | 2AI102EL01000-08141 | Not Started | Completed | EOF: Power Cable Laying from from MG-1 Substation to 52-SUBST-301 | 2017-02-02 | 2017-08-02 | 2017-03-06 | 2017-12-06
5 |  |  |  | EOF: Power Cable from Substation
Act | 2AI102EL01100 | Not Started | Completed | EOF: AG Cable laying, CP, DB'S/JB, Panels, Lighting Pole, Fixtures, Cable Glaning & Termination Electrical Works | 2017-03-04 | 2017-05-18 | 2019-03-04 | 2019-04-10
Act | 2AI102EL01100-08142 | Not Started | Completed | LV Power Cable laying from 50-SUBST-001 | 2017-03-04 | 2017-05-01 | 2019-03-04 | 2019-03-06
Act | 2AI102EL01100-08141 | Not Started | Completed | LV Power Cable laying from 52-SUBST-302 | 2017-03-04 | 2017-05-18 | 2019-03-04 | 2019-04-10
5 |  |  |  | EOF: Instrument Cable from Substation
Act | 2AI102IC01000 | Not Started | Completed | EOF: Instrument Cable from Substation | 2017-03-14 | 2017-06-04 | 2017-05-01 | 2019-04-10
Act | 2AI102IC01000-08141 | Not Started | Completed | Instrument Cable laying from 52-SUBST-302 to Storage Tank Junction Boxes | 2017-03-14 | 2017-06-04 | 2017-05-01 | 2019-04-10
5 |  |  |  | EOF: Fire Alarm Cable Works
Act | 2AI102IC01100 | Not Started | Completed | EOF: AG cable laying, Tubing, Field, Inline Instrument Installation, Cable Glading & Termination Instrument Works | 2017-08-02 | 2017-10-23 | 2018-10-03 | 2018-10-05
Act | 2AI102IC01100-08141 | Not Started | Completed | Fire Alarm Cable Laying from 52-SUBST-301 | 2017-08-02 | 2017-10-23 | 2018-10-03 | 2018-10-05
5 |  |  |  | EOF: Telecom Cable Laying to COCC
Act | 2AI102TE01000 | Not Started | Completed | EOF: Telecom Cable Laying to COCC | 2017-04-17 | 2017-07-08 | 2018-06-17 | 2019-01-29
Act | 2AI102TE01000-08141 | Not Started | Completed | Fiber Optic Cable Laying in boudery Limit of COCC Area | 2017-04-17 | 2017-07-08 | 2018-06-17 | 2019-01-29
5 |  |  |  | EOF: Telecom Cable Laying from COCC to Substation
Act | 2AI102TE01100 | Not Started | Completed | EOF: Telecom Cable Laying from COCC to Substation | 2017-08-28 | 2017-11-06 | 2019-04-08 | 2019-04-10
Act | 2AI102TE01100-08141 | Not Started | Completed | Fiber Optic Cable Laying from Boundery Limit to 52-SUBST-302 | 2017-08-28 | 2017-11-06 | 2019-04-08 | 2019-04-10
2 |  |  |  | CRUDE OIL CONTROL CENTER (COCC) - AREA 621
3 |  |  |  | BUILDINGS - COCC
4 |  |  |  | COCC :SITE PREPARATION
5 |  |  |  | COCC : Site preparation
Act | 2AI141CV01000 | Not Started | Completed | COCC : Site preparation | 2016-03-15 | 2016-08-04 | 2016-01-18 | 2017-05-12
6 |  |  |  | COCC : Site preparation (Including COCC Buliding,Carparking & Subsatation)
Act | 2AI141CV01000-08001 | Not Started | Completed | COCC :Verification of Survey for existing grade Level & Marking | 2016-03-15 | 2016-03-18 | 2016-01-18 | 2016-01-18
Act | 2AI141CV01000-08005 | Not Started | Completed | COCC :Excavation Notification | 2016-03-18 | 2016-03-22 | 2016-01-18 | 2016-04-24
Act | 2AI141CV01000-08015 | Not Started | Completed | COCC : Site clearance & Stripping & disposal of Contaminated material(If any) | 2016-03-22 | 2016-05-19 | 2016-04-25 | 2017-04-29
Act | 2AI141CV01000-08020 | Not Started | Completed | COCC : Grading, Cutting & Stockpiling | 2016-04-14 | 2016-06-29 | 2017-05-11 | 2017-05-12 | [66 empty] | 24 | [9 empty] | 61 | [9 empty] | 39 | [8 empty] | 5 | [9 empty] | 0 | [9 empty] | 0 | [8 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [8 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [8 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  |  |  | 0
Act | 2AI141CV01000-08025 | Not Started | Completed | COCC : Grading, Filling & Compaction | 2016-04-25 | 2016-08-04 | 2016-09-01 | 2017-05-12 | [66 empty] | 22 | [9 empty] | 61 | [9 empty] | 38 | [8 empty] | 5 | [9 empty] | 0 | [9 empty] | 0 | [8 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [8 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [8 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  |  |  | 0
Act | 2AI141CV01000-08030 | Not Started | Completed | COCC : Disposal of Surplus Material | 2016-05-25 | 2016-07-05 | 2016-04-25 | 2017-04-29
Act | 2AI141CV01000-08100 | Not Started | Completed | COCC : Site preparation (Including COCC Buliding,Carparking & Subsatation) | 2016-03-15 | 2016-08-04 | 2016-01-18 | 2017-05-12
5 |  |  |  | COCC : Trench (Manual Excavation) & other Civil Works
Act | 2AI141CV01100 | Not Started | In Progress | COCC : Trench & other Civil Works (including construction scope for migration readiness) | 2016-07-12 | 2018-01-15 | 2016-01-12
6 |  |  |  | COCC : Trench (Manual Excavation)
Act | 2AI141CV01100-08000 | Not Started | In Progress | COCC : Trench (Manual Excavation) | 2016-07-12 | 2016-09-29 | 2016-01-12
Act | 2AI141CV01100-08025 | Not Started | Completed | COCC: Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material | 2016-07-12 | 2016-09-14 | 2016-01-12 | 2018-11-07
Act | 2AI141CV01100-08035 | Not Started | Completed | COCC:Bedding (incl. clean sand layer) | 2016-07-24 | 2016-09-18 | 2016-01-13 | 2018-11-10
Act | 2AI141CV01100-08045 | Not Started | Completed | COCC:Backfilling with clean sand layer | 2016-07-26 | 2016-09-20 | 2016-01-15 | 2018-11-14
Act | 2AI141CV01100-08055 | Not Started | Completed | COCC:Install Cable Tiles & Warning Tapes | 2016-07-30 | 2016-09-24 | 2016-01-17 | 2018-11-18
Act | 2AI141CV01100-08065 | Not Started | Completed | COCC:Backfilling and Compaction | 2016-08-21 | 2016-09-27 | 2016-01-24 | 2018-11-22
Act | 2AI141CV01100-08075 | Not Started | Not Started | COCC:Install Route/saftey Markers | 2016-09-15 | 2016-09-29
6 |  |  |  | COCC : EIT Duct banks
Act | 2AI141CV01100-08005 | Not Started | Completed | COCC : EIT Duct banks | 2016-07-16 | 2016-11-27 | 2017-04-29 | 2018-01-28
Act | 2AI141CV01100-08085 | Not Started | Completed | COCC: Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material | 2016-07-16 | 2016-11-15 | 2017-04-29 | 2018-01-22
Act | 2AI141CV01100-08095 | Not Started | Completed | COCC: Subgrade and Blinding | 2016-07-18 | 2016-11-17 | 2017-05-13 | 2018-01-22
Act | 2AI141CV01100-08105 | Not Started | Completed | COCC: Rebar, Formwork & PVC conduits installation(duct bank) | 2016-07-20 | 2016-11-20 | 2017-05-15 | 2018-01-20
Act | 2AI141CV01100-08115 | Not Started | Completed | COCC: Concrete Pouring | 2016-07-23 | 2016-11-22 | 2017-05-18 | 2018-01-13
Act | 2AI141CV01100-08125 | Not Started | Completed | COCC: Coating | 2016-08-06 | 2016-11-24 | 2017-05-30 | 2018-01-27
Act | 2AI141CV01100-08135 | Not Started | Completed | COCC: Backfill and Compaction | 2016-08-20 | 2016-11-27 | 2017-06-11 | 2018-01-28
6 |  |  |  | COCC : Pipe Supports
Act | 2AI141CV01100-08010 | Not Started | Completed | COCC : Pipe Supports | 2016-12-14 | 2017-02-25 | 2017-11-09 | 2019-04-13
7 |  |  |  | COCC :Pre-Cast Concrete - Pipe Supports
Act | 2AI141CV01100-08021 | Not Started | Completed | COCC : Prepare Mould/Formwork, Rebar & Insert embedments (at Pre-cast Yard) | 2016-12-14 | 2017-02-13 | 2017-11-09 | 2017-11-14
Act | 2AI141CV01100-08030 | Not Started | Completed | COCC : Concrete Pouring | 2016-12-25 | 2017-02-15 | 2017-11-20 | 2017-11-24
Act | 2AI141CV01100-08040 | Not Started | Completed | COCC : Concrete Protection | 2016-12-31 | 2017-02-18 | 2017-11-26 | 2017-12-01
7 |  |  |  | COCC :Install Pre-Cast Fnds - Pipe Supports/Sleepers
Act | 2AI141CV01100-08050 | Not Started | Completed | COCC : Survey Marking, Excavation & Subgrade preparation | 2016-12-14 | 2016-12-19 | 2018-07-08 | 2019-02-16
Act | 2AI141CV01100-08060 | Not Started | Completed | COCC : Blinding/PCC | 2016-12-17 | 2016-12-21 | 2018-07-08 | 2019-02-16
Act | 2AI141CV01100-08070 | Not Started | Completed | COCC : Installation of pre-cast foundations and Leveling | 2017-02-16 | 2017-02-21 | 2018-07-25 | 2019-04-12
Act | 2AI141CV01100-08080 | Not Started | Completed | COCC : Backfill and Compaction (wherever applicable) | 2017-02-20 | 2017-02-25 | 2018-08-26 | 2019-04-13
6 |  |  |  | COCC : EIT Supports
Act | 2AI141CV01100-08015 | Not Started | Completed | COCC : EIT Supports | 2017-08-17 | 2018-01-15 | 2016-10-18 | 2019-03-30
7 |  |  |  | COCC :Pre-Cast Concrete - EIT Supports
Act | 2AI141CV01100-08090 | Not Started | Completed | COCC : Prepare Mould/Formwork, Rebar & Insert embedments (at Pre-cast Yard) | 2017-08-17 | 2017-10-18 | 2017-07-29 | 2017-07-31
Act | 2AI141CV01100-08100 | Not Started | Completed | COCC : Concrete Pouring | 2017-08-20 | 2017-10-23 | 2017-07-30 | 2017-08-01
Act | 2AI141CV01100-08110 | Not Started | Completed | COCC : Concrete Protection | 2017-09-09 | 2017-10-28 | 2017-08-01 | 2018-02-07
7 |  |  |  | COCC :Install Pre-Cast Fnds - EIT Supports
Act | 2AI141CV01100-08120 | Not Started | Completed | COCC : Survey Marking, Excavation & Subgrade preparation | 2017-08-31 | 2017-11-06 | 2018-01-18 | 2019-03-30
Act | 2AI141CV01100-08130 | Not Started | Completed | COCC : Blinding/PCC | 2017-09-04 | 2017-11-08 | 2018-01-26 | 2019-03-04
Act | 2AI141CV01100-08140 | Not Started | Completed | COCC : Installation of pre-cast foundations and Leveling | 2017-09-14 | 2017-11-19 | 2018-03-18 | 2019-03-06
Act | 2AI141CV01100-08145 | Not Started | Completed | COCC : Backfill and Compaction (wherever applicable) | 2017-10-04 | 2017-11-22 | 2018-04-02 | 2019-03-08
7 |  |  |  | COCC : Fence Works
Act | 2AI141CV01100-08020 | Not Started | Completed | COCC : Fence Works | 2017-09-07 | 2018-01-15 | 2016-10-18 | 2017-02-23
Act | 2AI141CV01100-08150 | Not Started | Completed | COCC: Survey marking & Excavation | 2017-09-07 | 2017-12-12 | 2016-10-18 | 2017-02-18
Act | 2AI141CV01100-08160 | Not Started | Completed | COCC: Sub grade & Blinding | 2017-09-19 | 2017-12-24 | 2016-10-26 | 2017-02-19
Act | 2AI141CV01100-08170 | Not Started | Completed | COCC: Install/Cast insitu fencing fnds (including tie beams - if any) | 2017-09-21 | 2017-12-26 | 2016-10-26 | 2017-02-21
Act | 2AI141CV01100-08180 | Not Started | Completed | COCC: Fix Railing/wire mesh installation | 2017-10-08 | 2017-12-28 | 2016-10-31 | 2017-02-23
Act | 2AI141CV01100-08190 | Not Started | Completed | COCC: Gate Installation & Speed bumbs | 2017-12-11 | 2018-01-15 | 2016-11-07 | 2016-11-07
4 |  |  |  | CIVIL / STRUCTURAL / ARCHITECTURAL
5 |  |  |  | ROADS & PAVING
6 |  |  |  | COCC :Roads, Crossing & Paving Works
Act | 2AI102CV01600 | Not Started | In Progress | COCC :Roads, Crossing & Paving Works | 2016-07-19 | 2017-08-24 | 2017-04-29
7 |  |  |  | COCC: Roads including Crossing Works
Act | 2AI102CV01600-08141 | Not Started | In Progress | COCC: Roads including Crossing Works | 2016-07-27 | 2017-01-19 | 2017-04-29
8 |  |  |  | COCC: Road Crossings-Sleeve
Act | 2AI102CV01600-08100 | Not Started | Completed | COCC: Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material | 2016-07-27 | 2016-10-03 | 2017-04-29 | 2018-01-22
Act | 2AI102CV01600-08110 | Not Started | Completed | COCC: Subgrade and Blinding | 2016-08-10 | 2016-10-10 | 2017-05-13 | 2018-01-22
Act | 2AI102CV01600-08120 | Not Started | Completed | COCC: Rebar, Formwork & Install Pipe sleeves | 2016-08-13 | 2016-10-17 | 2017-05-15 | 2018-01-20
Act | 2AI102CV01600-08130 | Not Started | Completed | COCC: Concrete Pouring | 2016-08-28 | 2016-10-19 | 2017-05-18 | 2018-01-13
Act | 2AI102CV01600-08140 | Not Started | Completed | COCC: Coating | 2016-09-14 | 2016-10-25 | 2017-05-30 | 2018-01-27
Act | 2AI102CV01600-08150 | Not Started | Completed | COCC: Backfill / Compaction | 2016-09-21 | 2016-11-02 | 2017-06-11 | 2018-01-28
8 |  |  |  | COCC: Roads upto Grade
Act | 2AI102CV01600-08010 | Not Started | In Progress | COCC: Rough Grading for Road Works | 2016-08-04 | 2016-11-23 | 2018-08-26
Act | 2AI102CV01600-08020 | Not Started | In Progress | COCC: Fine Grading (Gatch Subgrade) | 2016-08-10 | 2016-11-29 | 2018-09-29
Act | 2AI102CV01600-08030 | Not Started | In Progress | COCC: Finish Grading (Crushed gravel layer & Grading Top soil) | 2016-08-16 | 2016-12-05 | 2018-10-04
8 |  |  |  | COCC: Roads Finishing works
Act | 2AI102CV01600-08040 | Not Started | In Progress | COCC: Re-combaction of sub-grade | 2016-09-14 | 2016-12-11 | 2018-10-02
Act | 2AI102CV01600-08050 | Not Started | In Progress | COCC: Base Preparation & Kerbing (incl. Filling/Comp with Gatch & Crushed gravel layer) | 2016-09-20 | 2016-12-17 | 2018-10-03
Act | 2AI102CV01600-08060 | Not Started | In Progress | COCC: Asphalt base course | 2016-09-26 | 2016-12-22 | 2018-10-03
Act | 2AI102CV01600-08070 | Not Started | In Progress | COCC: Asphalt binding course | 2016-10-01 | 2016-12-27 | 2019-01-02
Act | 2AI102CV01600-08080 | Not Started | In Progress | COCC: Asphalt Wearing course | 2016-10-06 | 2017-01-02 | 2019-03-04
Act | 2AI102CV01600-08090 | Not Started | In Progress | COCC: Final Coat (incl. Road marking) | 2016-10-24 | 2017-01-19 | 2019-04-08
7 |  |  |  | COCC: Paving Works
Act | 2AI102CV01600-08142 | Not Started | In Progress | COCC: Paving Work | 2017-06-04 | 2017-08-24 | 2018-03-24
8 |  |  |  | COCC: Concrete Paving
Act | 2AI102CV01600-08025 | Not Started | In Progress | COCC: Sub base & Base preparation | 2016-07-19 | 2016-10-09 | 2018-03-24
Act | 2AI102CV01600-08035 | Not Started | In Progress | COCC: Formwork | 2016-07-25 | 2016-10-15 | 2018-03-25
Act | 2AI102CV01600-08045 | Not Started | In Progress | COCC: Reinforcement | 2016-07-31 | 2016-10-20 | 2018-03-23
Act | 2AI102CV01600-08055 | Not Started | In Progress | COCC: Concrete Pouring | 2016-08-06 | 2016-10-26 | 2018-03-29
Act | 2AI102CV01600-08065 | Not Started | In Progress | COCC: Finishing | 2016-08-11 | 2016-11-01 | 2018-04-03
8 |  |  |  | COCC: Interlock Paving/walkways
Act | 2AI102CV01600-08075 | Not Started | In Progress | COCC: Excavation/trimming | 2016-07-23 | 2016-10-12 | 2018-03-24
Act | 2AI102CV01600-08085 | Not Started | In Progress | COCC: Compacted Sub base preparation | 2016-07-28 | 2016-10-18 | 2018-03-25
Act | 2AI102CV01600-08095 | Not Started | In Progress | COCC: Install Kerb stone | 2016-08-03 | 2016-10-24 | 2018-03-26
Act | 2AI102CV01600-08105 | Not Started | In Progress | COCC: Sand/gatch layer | 2016-08-09 | 2016-10-30 | 2018-04-01
Act | 2AI102CV01600-08115 | Not Started | In Progress | COCC: Laying of Interlock Paving blocks | 2016-08-15 | 2016-11-05 | 2018-04-07
3 |  |  |  | 50-R-001 : CONTROL ROOM BUILDING
4 |  |  |  | ELECTRICAL
5 |  |  |  | COCC CCR Building : Earthing Lightning Protection Works
Act | 2AI141EL01000 | Not Started | Completed | COCC CCR Field & Building : Earthing & Lightning Protection Works | 2017-06-29 | 2017-09-09 | 2018-04-21 | 2019-03-22
6 |  |  |  | COCC: Earthing Work
Act | 2AI141EL01000-08001 | Not Started | Completed | COCC: Earth rod Installation | 2017-06-29 | 2017-07-20 | 2018-10-14 | 2018-10-18
Act | 2AI141EL01000-08005 | Not Started | Completed | COCC: Earth Cable Laying | 2017-07-20 | 2017-08-24 | 2018-04-21 | 2018-08-24
Act | 2AI141EL01000-08010 | Not Started | Completed | COCC: Cad welding | 2017-07-23 | 2017-08-27 | 2018-09-22 | 2019-03-22
Act | 2AI141EL01000-08015 | Not Started | Completed | COCC: Earth Bus Installation | 2017-07-30 | 2017-08-28 | 2018-08-25 | 2018-08-28
Act | 2AI141EL01000-08020 | Not Started | Completed | COCC: Earth Boss Installation | 2017-07-31 | 2017-08-30 | 2018-07-23 | 2018-07-23
Act | 2AI141EL01000-08025 | Not Started | Completed | COCC: Earth cable Termination | 2017-08-19 | 2017-09-05 | 2018-08-25 | 2018-09-07
Act | 2AI141EL01000-08028 | Not Started | Completed | COCC: Earth Pit Installation | 2017-08-28 | 2017-09-09 | 2018-10-12 | 2018-10-14
Act | 2AI141EL01000-08000 | Not Started | Completed | COCC CCR Field & Building : Earthing & Lightning Protection Works(outside the Building) | 2017-06-29 | 2017-09-09 | 2018-04-21 | 2019-03-22
6 |  |  |  | COCC: Lightining Protection
5 |  |  |  | COCC CCR Building : Cable laying, glanding & termination
Act | 2AI141EL01100 | Not Started | Completed | COCC CCR Building : Cable laying, glanding & termination | 2017-07-17 | 2017-11-18 | 2018-02-07 | 2019-03-16
6 |  |  |  | COCC CCR Field & Building : Install Electrical Cable trays & Supports
Act | 2AI141EL01100-08001 | Not Started | Completed | COCC:Fabricate Tray Supports | 2017-07-17 | 2017-09-04 | 2018-07-02 | 2018-07-04
Act | 2AI141EL01100-08007 | Not Started | Completed | COCC: Install cable trays | 2017-08-17 | 2017-09-19 | 2018-07-02 | 2018-07-04
Act | 2AI141EL01100-08011 | Not Started | Completed | COCC: Installcable trays covers | 2017-09-19 | 2017-10-03 | 2018-07-02 | 2018-07-04
Act | 2AI141EL01100-08002 | Not Started | Completed | COCC: Install Tray support | 2017-08-15 | 2017-09-07 | 2018-07-02 | 2018-07-04
Act | 2AI141EL01100-08000 | Not Started | Completed | COCC CCR Field & Building : Install Electrical Cable trays & Supports | 2017-07-17 | 2017-10-03 | 2018-07-02 | 2018-07-04
6 |  |  |  | COCC CCR Field & Building : Electrical Cable Laying
Act | 2AI141EL01100-08005 | Not Started | Completed | COCC CCR Field & Building : Electrical Cable Laying | 2017-07-20 | 2017-11-05 | 2018-02-07 | 2018-11-01
7 |  |  |  | COCC: Cable laying for LV
Act | 2AI141EL01100-08006 | Not Started | Completed | COCC: Cable Laying - LV | 2017-09-19 | 2017-11-05 | 2018-02-07 | 2018-11-01
7 |  |  |  | COCC: Cable laying for HV
Act | 2AI141EL01100-08028 | Not Started | Completed | COCC: Cable Laying - HV | 2017-07-20 | 2017-08-24 | 2018-04-02 | 2018-04-04
6 |  |  |  | COCC CCR Field & Building : Cable Glanding & Terminations
Act | 2AI141EL01100-08010 | Not Started | Completed | COCC CCR Field & Building : Electrical Cable Laying | 2017-08-24 | 2017-11-18 | 2018-04-21 | 2019-03-16
7 |  |  |  | COCC: Cable laying, glanding & termination for LV
Act | 2AI141EL01100-08015 | Not Started | Completed | COCC: Cable Glanding for LV cables | 2017-10-12 | 2017-11-11 | 2018-06-02 | 2019-03-15
Act | 2AI141EL01100-08020 | Not Started | Completed | COCC: Continuity Checks & Terminations for LV cables | 2017-10-28 | 2017-11-14 | 2018-06-03 | 2019-03-16
Act | 2AI141EL01100-08025 | Not Started | Completed | COCC: Tagging for LV cables | 2017-11-12 | 2017-11-18 | 2018-09-23 | 2019-03-16
7 |  |  |  | COCC: Cable laying, glanding & termination for HV
Act | 2AI141EL01100-08030 | Not Started | Completed | COCC: Cable Glanding for HV cables | 2017-08-24 | 2017-09-17 | 2018-04-21 | 2018-04-23
Act | 2AI141EL01100-08035 | Not Started | Completed | COCC: Continuity Checks & Terminations for HV cables | 2017-09-17 | 2017-10-01 | 2018-04-22 | 2018-04-24
Act | 2AI141EL01100-08040 | Not Started | Completed | COCC: Tagging for HV cables | 2017-10-01 | 2017-10-08 | 2018-04-23 | 2018-04-24
5 |  |  |  | COCC CCR Building : Electrical Equipment & Panels Installation
Act | 2AI141EL01200-08000 | Not Started | Completed | COCC: Electrical Equipment Installation | 2017-10-17 | 2017-12-09 | 2018-03-15 | 2019-03-06
Act | 2AI141EL01200-08005 | Not Started | Completed | COCC: Electrical Panels Installation | 2017-10-17 | 2017-12-09 | 2018-03-15 | 2019-03-06
Act | 2AI141EL01200 | Not Started | Completed | COCC CCR Building : Electrical Equipment & Panels Installation | 2017-10-17 | 2017-12-09 | 2018-03-15 | 2019-03-06
4 |  |  |  | INSTRUMENTATION
5 |  |  |  | COCC CCR Building : Field & Building Cable Trays and Conduits
Act | 2AI141IC01000-08001 | Not Started | Completed | COCC: Field & Building Cable Trays Installation | 2017-06-27 | 2017-08-19 | 2018-06-23 | 2018-08-02
Act | 2AI141IC01000-08005 | Not Started | Completed | COCC: Field & Building Conduits Installation | 2017-07-15 | 2017-09-05 | 2018-05-26 | 2018-05-28
Act | 2AI141IC01000 | Not Started | Completed | COCC CCR Building : Field & Building Cable Trays and Conduits | 2017-06-27 | 2017-09-05 | 2018-05-26 | 2018-08-02
Act | 2AI141IC01000-08000 | Not Started | Completed | COCC CCR Field & Building : Field & Building Cable Trays and Conduits | 2017-06-27 | 2017-09-05 | 2018-05-26 | 2018-08-02
5 |  |  |  | COCC CCR Building : Field Junction Boxes
Act | 2AI141IC01100-08001 | Not Started | Completed | COCC: Installation of supports | 2017-06-27 | 2017-08-01 | 2018-06-21 | 2018-07-27
Act | 2AI141IC01100-08005 | Not Started | Completed | COCC: Installation of Junction Boxes | 2017-06-28 | 2017-08-08 | 2018-05-27 | 2018-08-17
Act | 2AI141IC01100 | Not Started | Completed | COCC CCR Building : Field Junction Boxes | 2017-06-27 | 2017-08-10 | 2018-05-27 | 2019-04-10
Act | 2AI141IC01100-08010 | Not Started | Completed | COCC:Leveling & Grouting | 2017-07-01 | 2017-08-10 | 2019-04-08 | 2019-04-10
Act | 2AI141IC01100-08000 | Not Started | Completed | COCC CCR Field & Building : Junction Boxes | 2017-06-27 | 2017-08-10 | 2018-05-27 | 2019-04-10
5 |  |  |  | COCC CCR Building : Field & Building Cable laying, glanding & termination
Act | 2AI141IC01200-08000 | Not Started | Completed | COCC: Instrument Cable Laying | 2017-08-24 | 2017-10-16 | 2018-04-02 | 2018-09-29
Act | 2AI141IC01200-08005 | Not Started | Completed | COCC: Cable Glanding and Termination | 2017-09-19 | 2017-10-24 | 2018-06-02 | 2018-10-19
Act | 2AI141IC01200 | Not Started | Completed | COCC CCR Building : Field & Building Cable laying, glanding & termination | 2017-08-24 | 2017-10-24 | 2018-04-02 | 2018-10-19
5 |  |  |  | COCC CCR Building : Panel base frame Installation
Act | 2AI141IC01300-08000 | Not Started | Completed | COCC CCR Building : Panel base frame Installation | 2017-10-17 | 2017-11-21 | 2018-06-04 | 2018-06-22
Act | 2AI141IC01300 | Not Started | Completed | COCC CCR Building : Panel base frame Installation | 2017-10-17 | 2017-11-21 | 2018-06-04 | 2018-06-22
5 |  |  |  | COCC CCR Building : Fire Alarm Instrument & Panel
5 |  |  |  | COCC CCR Building : Equipment & Panels Installation (ICSS)
Act | 2AI141IC01500-08000 | Not Started | Completed | COCC CCR Building : ICSS installation | 2017-10-17 | 2017-11-27 | 2018-05-05 | 2018-06-22
Act | 2AI141IC01500-08005 | Not Started | Completed | COCC CCR Building : Other Equipment & Panels Installation | 2017-10-17 | 2017-11-27 | 2018-07-20 | 2019-04-10
Act | 2AI141IC01500 | Not Started | Completed | COCC CCR Building : Equipment & Panels Installation (ICSS) | 2017-10-17 | 2017-11-27 | 2018-05-05 | 2019-04-10
4 |  |  |  | TELECOMMUNICATION
5 |  |  |  | COCC CCR Building : Cabinet and Panel Installation
Act | 2AI141TE01000 | Not Started | Completed | COCC CCR Building : Cabinet and Panel Installation | 2017-07-17 | 2017-10-18 | 2018-05-07 | 2018-06-06
6 |  |  |  | COCC CCR Building : Cabinet and Panel Installation
Act | 2AI141TE01000-08001 | Not Started | Completed | Fabrication & Installation of Supports / Frames | 2017-07-17 | 2017-08-21 | 2018-05-07 | 2018-06-06
Act | 2AI141TE01000-08015 | Not Started | Completed | Installation of Equipment/Panels | 2017-07-17 | 2017-08-21 | 2018-05-07 | 2018-06-06
Act | 2AI141TE01000-08020 | Not Started | Completed | Leveling & Grouting | 2017-09-19 | 2017-10-18 | 2018-06-04 | 2018-06-06
Act | 2AI141TE01000-08000 | Not Started | Completed | COCC CCR Building : Cabinet and Panel Installation | 2017-07-17 | 2017-10-18 | 2018-05-07 | 2018-06-06
5 |  |  |  | COCC CCR Building : FO & Telephone Cabling, Cable Terminations & continuity checks
Act | 2AI141TE01100 | Not Started | Completed | COCC CCR Building : FO & Telephone Cabling, Cable Terminations & continuity checks | 2017-06-27 | 2017-11-28 | 2019-04-08 | 2019-04-10
6 |  |  |  | COCC CCR Building : FO & Telephone Cabling works
Act | 2AI141TE01100-08001 | Not Started | Completed | Cable Drum Checks & Transport to Site | 2017-06-27 | 2017-08-01 | 2019-04-08 | 2019-04-10
Act | 2AI141TE01100-08006 | Not Started | Completed | COCC: Cable Laying (FO, Coaxial, bare etc) | 2017-08-01 | 2017-09-11 | 2019-04-08 | 2019-04-10
Act | 2AI141TE01100-08010 | Not Started | Completed | COCC: Splicing of FO Cable | 2017-08-21 | 2017-09-19 | 2019-04-08 | 2019-04-10
Act | 2AI141TE01100-08000 | Not Started | Completed | COCC CCR Building : FO & Telephone Cabling works | 2017-06-27 | 2017-09-19 | 2019-04-08 | 2019-04-10
6 |  |  |  | COCC CCR Building : Cable Terminations & continuity checks
Act | 2AI141TE01100-08015 | Not Started | Completed | Glanding | 2017-09-19 | 2017-10-12 | 2019-04-08 | 2019-04-10
Act | 2AI141TE01100-08005 | Not Started | Completed | COCC CCR Building : Cable Terminations & continuity checks | 2017-09-19 | 2017-11-28 | 2019-04-08 | 2019-04-10
Act | 2AI141TE01100-08025 | Not Started | Completed | Continuity Checks & Terminations | 2017-10-12 | 2017-11-11 | 2019-04-08 | 2019-04-10
Act | 2AI141TE01100-08035 | Not Started | Completed | Tagging | 2017-11-11 | 2017-11-28 | 2019-04-08 | 2019-04-10
5 |  |  |  | COCC CCR Building : Outdoor Eqipment Inst. (CCTV, Access Control)
Act | 2AI141TE01200-08001 | Not Started | Completed | Installation of Support Structures (wherever applicable) | 2017-10-18 | 2017-11-22 | 2018-01-01 | 2018-01-03
Act | 2AI141TE01200-08005 | Not Started | Completed | Installation of Equipment/Panels | 2017-10-24 | 2017-11-28 | 2018-01-01 | 2018-01-03
Act | 2AI141TE01200-08010 | Not Started | Completed | Leveling & Grouting | 2017-10-29 | 2017-12-03 | 2018-01-01 | 2018-01-03
Act | 2AI141TE01200 | Not Started | Completed | COCC CCR Building : Outdoor Eqipment Inst. (CCTV, Access Control) | 2017-10-18 | 2017-12-03 | 2018-01-01 | 2018-01-03
Act | 2AI141TE01200-08000 | Not Started | Completed | COCC CCR Building : Eqipment Inst. (CCTV, Access Control) | 2017-10-18 | 2017-12-03 | 2018-01-01 | 2018-01-03
3 |  |  |  | PIPING
4 |  |  |  | UG Piping works
Act | 2AI102PI01000 | Not Started | Completed | UG Piping works | 2017-02-02 | 2017-05-16 | 2018-01-10 | 2019-01-12
5 |  |  |  | Metallic (CS/LTCS) Piping Works
Act | 2AI102PI01000-08145 | Not Started | Completed | COCC: Installation of pipes | 2017-02-02 | 2017-05-01 | 2018-01-10 | 2018-12-29
Act | 2AI102PI01000-08150 | Not Started | Completed | COCC:Alignment/Fit-up | 2017-02-08 | 2017-05-04 | 2018-01-15 | 2018-12-28
Act | 2AI102PI01000-08160 | Not Started | Completed | COCC:NDE/PWHT/QC Checks of Pipes | 2017-02-14 | 2017-05-13 | 2018-01-30 | 2018-12-30
Act | 2AI102PI01000-08155 | Not Started | Completed | COCC:Welding/Bolting | 2017-02-11 | 2017-05-07 | 2018-01-15 | 2018-12-29
Act | 2AI102PI01000-08165 | Not Started | Completed | COCC:Coating/Wrapping | 2017-02-18 | 2017-05-16 | 2018-01-31 | 2019-01-12
Act | 2AI102PI01000-08141 | Not Started | Completed | COCC: Metallic (CS/LTCS) Piping Works | 2017-02-02 | 2017-05-16 | 2018-01-10 | 2019-01-12
5 |  |  |  | Metallic (CU-NI & Other Alloy) Piping Works
4 |  |  |  | AG Piping works
Act | 2AI102PI01100 | Not Started | Completed | AG Piping works | 2017-06-03 | 2017-11-16 | 2018-07-02 | 2018-12-31
5 |  |  |  | Metallic (CS/LTCS) Piping Works
Act | 2AI102PI01100-08145 | Not Started | Completed | EOF:Installation of pipes | 2017-07-08 | 2017-10-30 | 2018-08-06 | 2018-12-29
Act | 2AI102PI01100-08150 | Not Started | Completed | COCC:Alignment/Fit-up | 2017-07-11 | 2017-11-02 | 2018-07-02 | 2018-12-29
Act | 2AI102PI01100-08160 | Not Started | Completed | EOF:NDE/PWHT/QC Checks of Pipes | 2017-07-23 | 2017-11-07 | 2018-09-03 | 2018-12-30
Act | 2AI102PI01100-08165 | Not Started | Completed | EOF:Install Permanent Supporting for Pipes | 2017-07-31 | 2017-11-12 | 2018-09-04 | 2018-12-31
Act | 2AI102PI01100-08170 | Not Started | Completed | COCC:Install piping valves | 2017-09-05 | 2017-11-16 | 2018-09-04 | 2018-12-31
Act | 2AI102PI01100-08155 | Not Started | Completed | COCC:Welding/Bolting | 2017-07-13 | 2017-11-05 | 2018-08-07 | 2018-12-29
Act | 2AI102PI01100-08141 | Not Started | Completed | Metallic (CS/LTCS) Piping Works | 2017-07-08 | 2017-11-16 | 2018-07-02 | 2018-12-31
5 |  |  |  | Metallic (SS/SDSS) Piping Works
Act | 2AI102PI01100-08175 | Not Started | Completed | EOF:Installation of pipes | 2017-06-03 | 2017-08-02 | 2018-10-05 | 2018-12-12
Act | 2AI102PI01100-08180 | Not Started | Completed | COCC:Alignment/Fit-up | 2017-06-08 | 2017-08-08 | 2018-10-07 | 2018-12-12
Act | 2AI102PI01100-08190 | Not Started | Completed | EOF:NDE/PWHT/QC Checks of Pipes | 2017-06-15 | 2017-08-15 | 2018-12-03 | 2018-12-12
Act | 2AI102PI01100-08195 | Not Started | Completed | COCC: Install Permanent Supporting for Pipes | 2017-07-22 | 2017-08-21 | 2018-12-04 | 2018-12-14
Act | 2AI102PI01100-08200 | Not Started | Completed | COCC: Install piping valves | 2017-08-09 | 2017-08-21 | 2018-11-30 | 2018-12-12
Act | 2AI102PI01100-08185 | Not Started | Completed | COCC:Welding/Bolting | 2017-06-12 | 2017-08-12 | 2018-10-08 | 2018-12-12
Act | 2AI102PI01100-08142 | Not Started | Completed | Metallic (SS/SDSS) Piping Works | 2017-06-03 | 2017-08-21 | 2018-10-05 | 2018-12-14
5 |  |  |  | Metallic (CU-NI & Other Alloy) Piping Works
4 |  |  |  | EOF: Hydrotesting
Act | 2AI102PI01300 | Not Started | Completed | EOF: Hydrotesting | 2017-07-17 | 2017-12-30 | 2018-01-16 | 2018-12-30
5 |  |  |  | Metallic (CS/LTCS) Piping Works
Act | 2AI102PI01300-08000 | Not Started | Completed | EOF:Test pack preparation & Ready for Test | 2017-09-17 | 2017-12-19 | 2018-01-16 | 2018-12-28
Act | 2AI102PI01300-08005 | Not Started | Completed | EOF:Reinstatement | 2017-11-22 | 2017-12-27 | 2018-01-16 | 2018-12-30
Act | 2AI102PI01300-08002 | Not Started | Completed | EOF:Pressure Testing & Approval | 2017-09-23 | 2017-12-25 | 2018-01-16 | 2018-12-28
Act | 2AI102PI01300-08035 | Not Started | Completed | EOF:Flange Management | 2017-11-25 | 2017-12-30 | 2018-01-16 | 2018-12-30
Act | 2AI102PI01300-08141 | Not Started | Completed | Metallic (CS/LTCS) Piping Works | 2017-09-17 | 2017-12-30 | 2018-01-16 | 2018-12-30
5 |  |  |  | Metallic (SS/SDSS) Piping Works
Act | 2AI102PI01300-08010 | Not Started | Completed | COCC: Test pack preparation & Ready for Test | 2017-07-17 | 2017-09-07 | 2018-10-08 | 2018-12-11
Act | 2AI102PI01300-08015 | Not Started | Completed | COCC: Pressure Testing & Approval | 2017-07-23 | 2017-09-13 | 2018-10-09 | 2018-12-12
Act | 2AI102PI01300-08030 | Not Started | Completed | COCC: Reinstatement | 2017-08-09 | 2017-09-16 | 2018-10-09 | 2018-12-12
Act | 2AI102PI01300-08040 | Not Started | Completed | COCC: Flange Management | 2017-08-12 | 2017-09-18 | 2018-10-10 | 2018-12-12
Act | 2AI102PI01300-08142 | Not Started | Completed | Metallic (SS/SDSS) Piping Works | 2017-07-17 | 2017-09-18 | 2018-10-08 | 2018-12-12
5 |  |  |  | Metallic (CU-NI & Other Alloy) Piping Works
4 |  |  |  | PAINTING
5 |  |  |  | EOF: Touch-up painting of Piping
Act | 2AI102PI01400 | Not Started | Completed | EOF: Touch-up painting of Piping | 2017-07-11 | 2017-12-27 | 2018-02-05 | 2019-01-17
Act | 2AI102PI01400-08000 | Not Started | Completed | COCC:Touch-up painting of CS Pipe | 2017-10-07 | 2017-12-27 | 2018-02-05 | 2019-01-17
Act | 2AI102PI01400-08010 | Not Started | Completed | COCC: Touch-up painting of SS Pipe | 2017-07-11 | 2017-10-01 | 2019-01-07 | 2019-01-17
Act | 2AI102PI01400-08141 | Not Started | Completed | COCC: Touch-up painting of Piping | 2017-07-11 | 2017-12-27 | 2018-02-05 | 2019-01-17
5 |  |  |  | EOF: Touch-up painting of Structures
Act | 2AI102CV28200 | Not Started | In Progress | EOF: Touch-up painting of Structures | 2017-10-07 | 2017-12-27 | 2018-06-05
Act | 2AI102CV28200-08000 | Not Started | In Progress | COCC: Touch-up painting of Structures / Shelters | 2017-10-07 | 2017-12-27 | 2018-06-05
Act | 2AI102CV28200-08141 | Not Started | In Progress | COCC: Touch-up painting of Structures / Shelters | 2017-10-07 | 2017-12-27 | 2018-06-05
4 |  |  |  | INSULATION
5 |  |  |  | EOF: Insulation of Piping
Act | 2AI102PI01200 | Not Started | Completed | COCC: Insulation of Piping | 2017-10-09 | 2017-12-18 | 2017-10-09 | 2017-10-09
Act | 2AI102PI01200-08005 | Not Started | Completed | COCC: Surface Preparation | 2017-10-09 | 2017-12-04 | 2017-10-09 | 2017-10-09
Act | 2AI102PI01200-08010 | Not Started | Completed | COCC: Cladding Fabrication | 2017-10-11 | 2017-12-11 | 2017-10-09 | 2017-10-09
Act | 2AI102PI01200-08015 | Not Started | Completed | COCC: Lagging | 2017-10-14 | 2017-12-14 | 2017-10-09 | 2017-10-09
Act | 2AI102PI01200-08020 | Not Started | Completed | COCC: Cladding/Fastening/Sealing | 2017-10-16 | 2017-12-18 | 2017-10-09 | 2017-10-09
Act | 2AI102PI01200-08141 | Not Started | Completed | COCC: Insulation of Piping | 2017-10-09 | 2017-12-18 | 2017-10-09 | 2017-10-09
3 |  |  |  | Car Park Shelter
4 |  |  |  | COCC : Construct Car Shelter Foundation & Miscellanious Shelter Foundation
Act | 2AI133CV99400 | Not Started | Completed | COCC : Construct Car Shelter Foundation & Miscellanious Shelter Foundation | 2016-08-04 | 2017-01-08 | 2017-02-11 | 2018-08-18
Act | 2AI133CV99400-08000 | Not Started | Completed | COCC: Excavation & Subgrade | 2016-08-04 | 2016-10-31 | 2017-02-11 | 2018-06-12 | [66 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [8 empty] | 0 | [9 empty] | 0 | [9 empty] | 9 | [8 empty] | 21 | [9 empty] | 46 | [9 empty] | 39 | [8 empty] | 23 | [9 empty] | 30 | [9 empty] | 0 | [9 empty] | 0 | [8 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  |  |  | 0
Act | 2AI133CV99400-08005 | Not Started | Completed | COCC: Blinding/PCC for Fnd | 2016-08-30 | 2016-11-06 | 2017-02-13 | 2018-06-18 | [66 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [8 empty] | 0 | [9 empty] | 0 | [9 empty] | 9 | [8 empty] | 21 | [9 empty] | 46 | [9 empty] | 39 | [8 empty] | 23 | [9 empty] | 30 | [9 empty] | 0 | [9 empty] | 0 | [8 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  |  |  | 0
Act | 2AI133CV99400-08010 | Not Started | Completed | COCC: Rebar, Formwork for Footing | 2016-09-03 | 2016-11-26 | 2017-03-04 | 2018-06-18 | [66 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [8 empty] | 0 | [9 empty] | 0 | [9 empty] | 9 | [8 empty] | 21 | [9 empty] | 46 | [9 empty] | 39 | [8 empty] | 23 | [9 empty] | 30 | [9 empty] | 0 | [9 empty] | 0 | [8 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  |  |  | 0
Act | 2AI133CV99400-08015 | Not Started | Completed | COCC: Rebar, Formwork & Install Embedments for Pedestal | 2016-10-11 | 2016-12-22 | 2017-02-28 | 2018-06-22 | [66 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [8 empty] | 0 | [9 empty] | 0 | [9 empty] | 9 | [8 empty] | 0 | [9 empty] | 46 | [9 empty] | 39 | [8 empty] | 23 | [9 empty] | 30 | [9 empty] | 0 | [9 empty] | 0 | [8 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  |  |  | 0
Act | 2AI133CV99400-08020 | Not Started | Completed | COCC: Concrete Potection for Fnd | 2016-11-10 | 2017-01-02 | 2017-03-14 | 2018-06-18 | [66 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [8 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [8 empty] | 0 | [9 empty] | 46 | [9 empty] | 39 | [8 empty] | 23 | [9 empty] | 30 | [9 empty] | 0 | [9 empty] | 0 | [8 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  |  |  | 0
Act | 2AI133CV99400-08025 | Not Started | Completed | COCC: Backfilling & Compaction for Fnd | 2016-11-23 | 2017-01-08 | 2017-03-20 | 2018-08-18 | [66 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [8 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [8 empty] | 0 | [9 empty] | 46 | [9 empty] | 39 | [8 empty] | 23 | [9 empty] | 30 | [9 empty] | 0 | [9 empty] | 0 | [8 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  |  |  | 0
Act | 2AI133CV99400-08011 | Not Started | Completed | COCC:Concrete Pouring for Footing | 2016-10-06 | 2016-12-01 | 2017-03-06 | 2018-06-18 | [66 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [8 empty] | 0 | [9 empty] | 0 | [9 empty] | 9 | [8 empty] | 21 | [9 empty] | 46 | [9 empty] | 39 | [8 empty] | 23 | [9 empty] | 30 | [9 empty] | 0 | [9 empty] | 0 | [8 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  |  |  | 0
Act | 2AI133CV99400-08016 | Not Started | Completed | COCC:Concrete Pouring for Pedestal | 2016-10-29 | 2016-12-27 | 2017-03-08 | 2018-06-18 | [66 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [8 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [8 empty] | 0 | [9 empty] | 46 | [9 empty] | 39 | [8 empty] | 23 | [9 empty] | 30 | [9 empty] | 0 | [9 empty] | 0 | [8 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  |  |  | 0
Act | 2AI133CV99400-08141 | Not Started | Completed | COCC : Shelter Foundation for Car Park | 2016-08-04 | 2017-01-08 | 2017-02-11 | 2018-08-18
4 |  |  |  | COCC : Car Shelter Erection & Miscellanious Shelter
Act | 2AI133CV99500 | Not Started | Completed | COCC : Car Shelter Erection & Miscellanious Shelter | 2017-01-14 | 2017-06-13 | 2018-04-12 | 2019-02-10
Act | 2AI133CV99500-08141 | Not Started | Completed | COCC : Shelter Erection for Car park | 2017-01-14 | 2017-06-13 | 2018-04-12 | 2019-02-10
Act | 2AI133CV99500-08005 | Not Started | Completed | COCC: Alignment/Welding/Bolting for Shelter | 2017-01-25 | 2017-05-24 | 2018-04-28 | 2019-01-15
Act | 2AI133CV99500-08010 | Not Started | Completed | COCC: Grouting of Shelter | 2017-02-09 | 2017-06-04 | 2018-08-06 | 2019-01-28
Act | 2AI133CV99500-08006 | Not Started | Completed | COCC:Torque Bolts | 2017-01-31 | 2017-05-30 | 2018-04-30 | 2019-01-17
Act | 2AI133CV99500-08011 | Not Started | Completed | COCC:Installation of gratings/handrail/stair/ladder | 2017-02-28 | 2017-06-07 | 2018-08-06 | 2019-02-05
Act | 2AI133CV99500-08012 | Not Started | Completed | COCC:Wall & Roof Cladding | 2017-03-06 | 2017-06-13 | 2018-05-05 | 2019-02-10
Act | 2AI133CV99500-08000 | Not Started | Completed | COCC: Installation of Main steel structure | 2017-01-14 | 2017-05-21 | 2018-04-12 | 2019-01-14
2 |  |  |  | SUBSTATIONS
3 |  |  |  | EOF SUBSTATIONS (PART OF AREA 621)
4 |  |  |  | CIVIL / STRUCTURAL / ARCHITECTURAL
5 |  |  |  | EOF SS : Shelter Foundation for Transformer, Capacitor
Act | 2AI133CV99000 | Not Started | Completed | EOF SS : Shelter Foundation for Transformer, Capacitor | 2016-11-19 | 2017-02-09 | 2017-06-01 | 2018-07-04
6 |  |  |  | EOF SS : Shelter Foundation for Transformers of 52-SUBST-301 - SUBSTATION - FMM
Act | 2AI133CV99000-08001 | Not Started | Completed | EOF:Survey Marking, Excavation & Subgrade | 2016-11-19 | 2016-11-20 | 2017-07-14 | 2017-07-17
Act | 2AI133CV99000-08006 | Not Started | Completed | EOF:Blinding/PCC for Fnd | 2016-11-20 | 2016-11-22 | 2017-07-22 | 2017-07-22
Act | 2AI133CV99000-08011 | Not Started | Completed | EOF:Rebar, Formwork for Footing | 2016-11-23 | 2016-12-01 | 2017-07-23 | 2017-07-27
Act | 2AI133CV99000-08021 | Not Started | Completed | EOF:Rebar, Formwork, Install Embedments for Pedestal | 2016-12-07 | 2016-12-18 | 2017-08-06 | 2017-10-25
Act | 2AI133CV99000-08031 | Not Started | Completed | EOF:Concrete Potection for Fnd | 2016-12-29 | 2017-01-03 | 2017-12-25 | 2018-01-04
Act | 2AI133CV99000-08036 | Not Started | Completed | EOF:Backfilling & Compaction for Fnd | 2017-01-07 | 2017-01-12 | 2018-01-16 | 2018-01-16
Act | 2AI133CV99000-08026 | Not Started | Completed | EOF:Concrete Pouring - for Pedestal | 2016-12-21 | 2016-12-22 | 2017-10-08 | 2017-12-17
Act | 2AI133CV99000-08016 | Not Started | Completed | EOF:Concrete Pouring - for Footing | 2016-12-01 | 2016-12-03 | 2017-08-03 | 2017-08-03
Act | 2AI133CV99000-08000 | Not Started | Completed | EOF SS : Shelter Foundation for Transformers of 52-SUBST-301 - SUBSTATION - FMM | 2016-11-19 | 2017-01-12 | 2017-07-14 | 2018-01-16
6 |  |  |  | EOF SS : Shelter Foundation for Transformers of 52-SUBST-302 - SUBSTATION - STF
Act | 2AI133CV99000-08335 | Not Started | Completed | EOF:Survey Marking, Excavation & Subgrade | 2016-11-20 | 2016-11-21 | 2017-08-26 | 2017-08-27
Act | 2AI133CV99000-08340 | Not Started | Completed | EOF:Blinding/PCC for Fnd | 2016-11-21 | 2016-11-23 | 2017-08-29 | 2017-08-29
Act | 2AI133CV99000-08345 | Not Started | Completed | EOF:Rebar, Formwork for Footing | 2016-12-01 | 2016-12-10 | 2017-08-30 | 2018-01-16
Act | 2AI133CV99000-08350 | Not Started | Completed | EOF:Rebar, Formwork & Install Embedments for Pedestal | 2016-12-11 | 2016-12-21 | 2017-09-19 | 2018-01-18
Act | 2AI133CV99000-08355 | Not Started | Completed | EOF:Concrete Potection for Fnd | 2016-12-28 | 2017-01-02 | 2018-01-27 | 2018-01-30
Act | 2AI133CV99000-08360 | Not Started | Completed | EOF:Backfilling & Compaction for Fnd | 2017-01-05 | 2017-01-11 | 2018-01-27 | 2018-03-24
Act | 2AI133CV99000-08346 | Not Started | Completed | EOF:Concrete Pouring - for Footing | 2016-12-10 | 2016-12-11 | 2017-09-12 | 2018-01-16
Act | 2AI133CV99000-08351 | Not Started | Completed | EOF:Concrete Pouring - for Pedestal | 2016-12-21 | 2016-12-22 | 2017-10-28 | 2018-01-18
Act | 2AI133CV99000-08005 | Not Started | Completed | EOF SS : Shelter Foundation for Transformers of 52-SUBST-302 - SUBSTATION - STF | 2016-11-20 | 2017-01-11 | 2017-08-26 | 2018-03-24
6 |  |  |  | EOF SS : Shelter Foundation for Transformers of 50-SUBST-001 - SUBSTATION - COCC
Act | 2AI133CV99000-08365 | Not Started | Completed | EOF:Survey Marking, Excavation & Subgrade | 2016-12-08 | 2016-12-10 | 2017-12-25 | 2018-01-03
Act | 2AI133CV99000-08370 | Not Started | Completed | EOF:Blinding/PCC for Fnd | 2016-12-10 | 2016-12-12 | 2017-12-26 | 2018-01-05
Act | 2AI133CV99000-08375 | Not Started | Completed | EOF:Rebar, Formwork for Footing | 2016-12-13 | 2016-12-21 | 2017-12-26 | 2018-01-06
Act | 2AI133CV99000-08380 | Not Started | Completed | EOF:Rebar, Formwork & Install Embedments for Pedestal | 2016-12-25 | 2017-01-04 | 2017-12-29 | 2018-02-01
Act | 2AI133CV99000-08385 | Not Started | Completed | EOF:Concrete Potection for Fnd | 2017-01-11 | 2017-01-16 | 2018-03-10 | 2018-06-22
Act | 2AI133CV99000-08390 | Not Started | Completed | EOF:Backfilling & Compaction for Fnd | 2017-01-19 | 2017-01-25 | 2018-06-24 | 2018-07-04
Act | 2AI133CV99000-08376 | Not Started | Completed | EOF:Concrete Pouring - for Footing | 2016-12-21 | 2016-12-22 | 2017-12-26 | 2017-12-26
Act | 2AI133CV99000-08381 | Not Started | Completed | EOF:Concrete Pouring - for Pedestal | 2017-01-04 | 2017-01-05 | 2018-01-07 | 2018-02-04
Act | 2AI133CV99000-08010 | Not Started | Completed | EOF SS : Shelter Foundation for Transformers of 50-SUBST-001 - SUBSTATION - COCC | 2016-12-08 | 2017-01-25 | 2017-12-25 | 2018-07-04
6 |  |  |  | EOF SS : Shelter Foundation for Transformers of 52-SUBST-303 - SUBSTATION - LMM
Act | 2AI133CV99000-08395 | Not Started | Completed | EOF:Excavation & Subgrade | 2016-12-25 | 2016-12-26 | 2017-06-01 | 2017-06-06
Act | 2AI133CV99000-08400 | Not Started | Completed | EOF:Blinding/PCC for Fnd | 2016-12-26 | 2016-12-28 | 2017-06-08 | 2017-06-08
Act | 2AI133CV99000-08405 | Not Started | Completed | EOF:Rebar, Formwork for Footing | 2016-12-29 | 2017-01-07 | 2017-06-09 | 2017-07-17
Act | 2AI133CV99000-08410 | Not Started | Completed | EOF:Rebar, Formwork & Install Embedments for Pedestal | 2017-01-08 | 2017-01-18 | 2017-06-13 | 2017-07-26
Act | 2AI133CV99000-08415 | Not Started | Completed | EOF:Concrete Potection for Fnd | 2017-01-26 | 2017-01-31 | 2017-08-13 | 2017-08-16
Act | 2AI133CV99000-08420 | Not Started | Completed | EOF:Backfilling & Compaction for Fnd | 2017-02-04 | 2017-02-09 | 2017-08-17 | 2017-08-31
Act | 2AI133CV99000-08406 | Not Started | Completed | EOF:Concrete Pouring - for Footing | 2017-01-07 | 2017-01-08 | 2017-06-12 | 2017-07-17
Act | 2AI133CV99000-08411 | Not Started | Completed | EOF:Concrete Pouring - for Pedestal | 2017-01-18 | 2017-01-19 | 2017-06-22 | 2017-07-27
Act | 2AI133CV99000-08015 | Not Started | Completed | EOF SS : Shelter Foundation for Transformers of 52-SUBST-303 - SUBSTATION - LMM | 2016-12-25 | 2017-02-09 | 2017-06-01 | 2017-08-31
5 |  |  |  | EOF SS : Shelter Foundation for Diesel Tank & Inert Agent
Act | 2AI133CV99200 | Not Started | Completed | EOF SS : Shelter Foundation for Diesel Tank & Inert Agent | 2016-10-15 | 2017-02-28 | 2017-07-05 | 2018-02-07
6 |  |  |  | EOF SS : Shelter Foundation for Diesel Tank & Inert Agent of 52-SUBST-301 - SUBSTATION - FMM
Act | 2AI133CV99200-08001 | Not Started | Completed | EOF:Survey Marking, Excavation & Subgrade | 2016-11-19 | 2016-11-20 | 2017-07-05 | 2017-07-05
Act | 2AI133CV99200-08006 | Not Started | Completed | EOF:Blinding/PCC for Fnd | 2016-11-20 | 2016-11-22 | 2017-07-23 | 2017-07-23
Act | 2AI133CV99200-08011 | Not Started | Completed | EOF:Rebar, Formwork for Footing | 2016-11-22 | 2016-11-30 | 2017-09-24 | 2017-10-01
Act | 2AI133CV99200-08021 | Not Started | Completed | EOF:Rebar, Formwork, Install Embedments for Pedestal | 2016-12-01 | 2016-12-12 | 2017-09-23 | 2017-10-01
Act | 2AI133CV99200-08031 | Not Started | Completed | EOF:Concrete Potection for Fnd | 2016-12-20 | 2016-12-25 | 2017-10-10 | 2017-10-22
Act | 2AI133CV99200-08036 | Not Started | Completed | EOF:Backfilling & Compaction for Fnd | 2016-12-28 | 2017-01-03 | 2018-02-05 | 2018-02-07
Act | 2AI133CV99200-08026 | Not Started | Completed | EOF:Concrete Pouring - for Pedestal | 2016-12-12 | 2016-12-13 | 2017-10-02 | 2017-10-02
Act | 2AI133CV99200-08016 | Not Started | Completed | EOF:Concrete Pouring - for Footing | 2016-11-30 | 2016-12-01 | 2017-10-02 | 2017-10-02
Act | 2AI133CV99200-08000 | Not Started | Completed | EOF SS : Shelter Foundation for Diesel Tank & Inert Agent of 52-SUBST-301 - SUBSTATION - FMM | 2016-11-19 | 2017-01-03 | 2017-07-05 | 2018-02-07
6 |  |  |  | EOF SS : Shelter Foundation for Diesel Tank & Inert Agent of 52-SUBST-302 - SUBSTATION - STF
Act | 2AI133CV99200-08030 | Not Started | Completed | EOF:Survey Marking, Excavation & Subgrade | 2016-11-05 | 2016-11-06 | 2017-10-13 | 2017-10-24
Act | 2AI133CV99200-08035 | Not Started | Completed | EOF:Blinding/PCC for Fnd | 2016-11-06 | 2016-11-08 | 2017-10-25 | 2017-10-25
Act | 2AI133CV99200-08040 | Not Started | Completed | EOF:Rebar, Formwork for Footing | 2016-11-08 | 2016-11-16 | 2017-10-26 | 2018-01-02
Act | 2AI133CV99200-08045 | Not Started | Completed | EOF:Rebar, Formwork, Install Embedments for Pedestal | 2016-11-20 | 2016-11-30 | 2017-10-26 | 2018-01-02
Act | 2AI133CV99200-08050 | Not Started | Completed | EOF:Concrete Potection for Fnd | 2016-12-08 | 2016-12-13 | 2018-01-07 | 2018-01-09
Act | 2AI133CV99200-08055 | Not Started | Completed | EOF:Backfilling & Compaction for Fnd | 2016-12-17 | 2016-12-22 | 2018-01-27 | 2018-01-28
Act | 2AI133CV99200-08041 | Not Started | Completed | EOF:Concrete Pouring - for Footing | 2016-11-16 | 2016-11-17 | 2018-01-03 | 2018-01-03
Act | 2AI133CV99200-08046 | Not Started | Completed | EOF:Concrete Pouring - for Pedestal | 2016-11-30 | 2016-12-01 | 2018-01-03 | 2018-01-03
Act | 2AI133CV99200-08005 | Not Started | Completed | EOF SS : Shelter Foundation for Diesel Tank & Inert Agent of 52-SUBST-302 - SUBSTATION - STF | 2016-11-05 | 2016-12-22 | 2017-10-13 | 2018-01-28
6 |  |  |  | EOF SS : Shelter Foundation for Diesel Tank & Inert Agent of 50-SUBST-001 - SUBSTATION - COCC
Act | 2AI133CV99200-08060 | Not Started | Completed | EOF:Survey Marking, Excavation & Subgrade | 2016-10-15 | 2016-10-16 | 2017-12-15 | 2017-12-20
Act | 2AI133CV99200-08065 | Not Started | Completed | EOF:Blinding/PCC for Fnd | 2016-10-16 | 2016-10-18 | 2017-12-21 | 2017-12-21
Act | 2AI133CV99200-08070 | Not Started | Completed | EOF:Rebar, Formwork for Footing | 2016-10-18 | 2016-10-26 | 2017-12-23 | 2017-12-30
Act | 2AI133CV99200-08075 | Not Started | Completed | EOF:Rebar, Formwork, Install Embedments for Pedestal | 2016-10-30 | 2016-11-09 | 2018-01-02 | 2018-01-11
Act | 2AI133CV99200-08080 | Not Started | Completed | EOF:Concrete Potection for Fnd | 2016-11-17 | 2016-11-22 | 2018-01-15 | 2018-01-22
Act | 2AI133CV99200-08085 | Not Started | Completed | EOF:Backfilling & Compaction for Fnd | 2016-11-26 | 2016-12-01 | 2018-01-23 | 2018-01-26
Act | 2AI133CV99200-08071 | Not Started | Completed | EOF:Concrete Pouring - for Footing | 2016-10-26 | 2016-10-27 | 2017-12-31 | 2017-12-31
Act | 2AI133CV99200-08076 | Not Started | Completed | EOF:Concrete Pouring - for Pedestal | 2016-11-09 | 2016-11-10 | 2018-01-11 | 2018-01-11
Act | 2AI133CV99200-08010 | Not Started | Completed | EOF SS : Shelter Foundation for Diesel Tank & Inert Agent of 50-SUBST-001 - SUBSTATION - COCC | 2016-10-15 | 2016-12-01 | 2017-12-15 | 2018-01-26
6 |  |  |  | EOF SS : Shelter Foundation for Diesel Tank & Inert Agent of 52-SUBST-303 - SUBSTATION - LMM
Act | 2AI133CV99200-08090 | Not Started | Completed | EOF:Survey Marking, Excavation & Subgrade | 2017-01-14 | 2017-01-15 | 2017-09-30 | 2017-10-01
Act | 2AI133CV99200-08095 | Not Started | Completed | EOF:Blinding/PCC for Fnd | 2017-01-15 | 2017-01-17 | 2017-10-02 | 2017-10-02
Act | 2AI133CV99200-08100 | Not Started | Completed | EOF:Rebar, Formwork for Footing | 2017-01-17 | 2017-01-24 | 2017-10-03 | 2017-11-07
Act | 2AI133CV99200-08105 | Not Started | Completed | EOF:Rebar, Formwork, Install Embedments for Pedestal | 2017-01-28 | 2017-02-06 | 2017-10-03 | 2017-11-07
Act | 2AI133CV99200-08110 | Not Started | Completed | EOF:Concrete Potection for Fnd | 2017-02-14 | 2017-02-19 | 2017-11-16 | 2017-11-23
Act | 2AI133CV99200-08115 | Not Started | Completed | EOF:Backfilling & Compaction for Fnd | 2017-02-22 | 2017-02-28 | 2018-01-06 | 2018-01-21
Act | 2AI133CV99200-08101 | Not Started | Completed | EOF:Concrete Pouring - for Footing | 2017-01-24 | 2017-01-25 | 2017-11-08 | 2017-11-08
Act | 2AI133CV99200-08106 | Not Started | Completed | EOF:Concrete Pouring - for Pedestal | 2017-02-06 | 2017-02-07 | 2017-11-08 | 2017-11-08
Act | 2AI133CV99200-08015 | Not Started | Completed | EOF SS : Shelter Foundation for Diesel Tank & Inert Agent of 52-SUBST-303 - SUBSTATION - LMM | 2017-01-14 | 2017-02-28 | 2017-09-30 | 2018-01-21
5 |  |  |  | EOF SS : Shelter Erection for Transformer, Capacitor
Act | 2AI133CV99100 | Not Started | Completed | EOF SS : Shelter Erection for Transformer, Capacitor | 2017-01-15 | 2017-11-06 | 2017-12-26 | 2018-12-14
6 |  |  |  | EOF SS : Shelter Erection for Transformer, Capacitor of 52-SUBST-301 - SUBSTATION - FMM
Act | 2AI133CV99100-08001 | Not Started | Completed | EOF:Installation of Str. Steel | 2017-01-15 | 2017-01-25 | 2018-01-11 | 2018-05-08
Act | 2AI133CV99100-08006 | Not Started | Completed | EOF:Alignment & Bolting/Torqueing | 2017-01-25 | 2017-02-02 | 2018-01-21 | 2018-05-09
Act | 2AI133CV99100-08011 | Not Started | Completed | EOF:Grouting | 2017-02-02 | 2017-02-07 | 2018-05-07 | 2018-05-09
Act | 2AI133CV99100-08000 | Not Started | Completed | EOF SS : Shelter Erection for Transformer, Capacitor of 52-SUBST-301 - SUBSTATION - FMM | 2017-01-15 | 2017-02-20 | 2018-01-11 | 2018-05-15
Act | 2AI133CV99100-08021 | Not Started | Completed | Installation of gratings/handrail/stair/ladder (wherever applicable) | 2017-02-07 | 2017-02-14 | 2018-05-10 | 2018-05-15
Act | 2AI133CV99100-08031 | Not Started | Completed | Wall & Roof Cladding | 2017-02-14 | 2017-02-20 | 2018-05-10 | 2018-05-15
6 |  |  |  | EOF SS : Shelter Erection for Transformer, Capacitor of 52-SUBST-302 - SUBSTATION - STF
Act | 2AI133CV99100-08016 | Not Started | Completed | EOF:Installation of Str. Steel | 2017-01-15 | 2017-01-25 | 2018-02-11 | 2018-05-08
Act | 2AI133CV99100-08020 | Not Started | Completed | EOF:Alignment & Bolting/Torqueing | 2017-01-25 | 2017-02-02 | 2018-02-11 | 2018-05-09
Act | 2AI133CV99100-08025 | Not Started | Completed | EOF:Grouting | 2017-02-02 | 2017-02-07 | 2018-09-23 | 2018-09-23
Act | 2AI133CV99100-08005 | Not Started | Completed | EOF SS : Shelter Erection for Transformer, Capacitor of 52-SUBST-302 - SUBSTATION - STF | 2017-01-15 | 2017-02-20 | 2018-02-11 | 2018-09-23
Act | 2AI133CV99100-08065 | Not Started | Completed | Installation of gratings/handrail/stair/ladder (wherever applicable) | 2017-02-07 | 2017-02-14 | 2018-05-05 | 2018-05-12
Act | 2AI133CV99100-08075 | Not Started | Completed | Wall & Roof Cladding | 2017-02-14 | 2017-02-20 | 2018-05-05 | 2018-05-12
6 |  |  |  | EOF SS : Shelter Erection for Transformer, Capacitor of 50-SUBST-001 - SUBSTATION - COCC
Act | 2AI133CV99100-08030 | Not Started | Completed | EOF:Installation of Str. Steel | 2017-10-01 | 2017-10-11 | 2018-09-24 | 2018-09-27
Act | 2AI133CV99100-08035 | Not Started | Completed | EOF:Alignment & Bolting/Torqueing | 2017-10-11 | 2017-10-19 | 2018-09-26 | 2018-09-28
Act | 2AI133CV99100-08040 | Not Started | Completed | EOF:Grouting | 2017-10-19 | 2017-10-24 | 2018-09-26 | 2018-09-28
Act | 2AI133CV99100-08010 | Not Started | Completed | EOF SS : Shelter Erection for Transformer, Capacitor of 50-SUBST-001 - SUBSTATION - COCC | 2017-10-01 | 2017-11-06 | 2018-09-24 | 2018-10-09
Act | 2AI133CV99100-08060 | Not Started | Completed | Installation of gratings/handrail/stair/ladder (wherever applicable) | 2017-10-24 | 2017-10-31 | 2018-09-26 | 2018-09-28
Act | 2AI133CV99100-08070 | Not Started | Completed | Wall & Roof Cladding | 2017-10-31 | 2017-11-06 | 2018-10-02 | 2018-10-09
6 |  |  |  | EOF SS : Shelter Erection for Transformer, Capacitor of 52-SUBST-303 - SUBSTATION - LMM
Act | 2AI133CV99100-08045 | Not Started | Completed | EOF:Installation of Str. Steel | 2017-09-12 | 2017-09-23 | 2017-12-26 | 2017-12-27
Act | 2AI133CV99100-08050 | Not Started | Completed | EOF:Alignment & Bolting/Torqueing | 2017-09-23 | 2017-10-01 | 2018-01-22 | 2018-01-22
Act | 2AI133CV99100-08055 | Not Started | Completed | EOF:Grouting | 2017-10-01 | 2017-10-05 | 2018-08-27 | 2018-09-01
Act | 2AI133CV99100-08015 | Not Started | Completed | EOF SS : Shelter Erection for Transformer, Capacitor of 52-SUBST-303 - SUBSTATION - LMM | 2017-09-12 | 2017-10-18 | 2017-12-26 | 2018-12-14
Act | 2AI133CV99100-08085 | Not Started | Completed | Installation of gratings/handrail/stair/ladder (wherever applicable) | 2017-10-05 | 2017-10-12 | 2018-12-12 | 2018-12-14
Act | 2AI133CV99100-08095 | Not Started | Completed | Wall & Roof Cladding | 2017-10-12 | 2017-10-18 | 2018-08-18 | 2018-08-18
5 |  |  |  | EOF SS : Shelter Erection for Diesel Tank & Inert Agent
Act | 2AI133CV99300 | Not Started | Completed | EOF SS : Shelter Erection for Diesel Tank & Inert Agent | 2017-05-08 | 2017-11-04 | 2017-10-22 | 2018-12-23
6 |  |  |  | Shelter Erection for Diesel Tank & Inert Agent of 52-SUBST-301 - SUBSTATION - FMM
Act | 2AI133CV99300-08006 | Not Started | Completed | EOF:Installation of Str. Steel | 2017-05-08 | 2017-05-16 | 2017-10-22 | 2018-06-18
Act | 2AI133CV99300-08011 | Not Started | Completed | EOF:Alignment & Bolting/Torqueing | 2017-05-16 | 2017-05-23 | 2017-10-22 | 2018-06-21
Act | 2AI133CV99300-08016 | Not Started | Completed | EOF:Grouting | 2017-05-23 | 2017-05-28 | 2018-08-06 | 2018-08-08
Act | 2AI133CV99300-08000 | Not Started | Completed | Shelter Erection for Diesel Tank & Inert Agent of 52-SUBST-301 - SUBSTATION - FMM | 2017-05-08 | 2017-06-07 | 2017-10-22 | 2018-08-08
Act | 2AI133CV99300-08026 | Not Started | Completed | EOF:Installation of gratings/handrail/stair/ladder (wherever applicable) | 2017-05-28 | 2017-06-01 | 2018-08-06 | 2018-08-08
Act | 2AI133CV99300-08036 | Not Started | Completed | EOF:Wall & Roof Cladding | 2017-06-01 | 2017-06-07 | 2018-08-06 | 2018-08-08
6 |  |  |  | Shelter Erection for Diesel Tank & Inert Agent of 52-SUBST-302 - SUBSTATION - STF
Act | 2AI133CV99300-08021 | Not Started | Completed | EOF:Installation of Str. Steel | 2017-09-26 | 2017-10-04 | 2018-01-22 | 2018-02-06
Act | 2AI133CV99300-08022 | Not Started | Completed | EOF:Alignment & Bolting/Torqueing | 2017-10-04 | 2017-10-11 | 2018-01-22 | 2018-03-12
Act | 2AI133CV99300-08025 | Not Started | Completed | EOF:Grouting | 2017-10-11 | 2017-10-16 | 2018-06-08 | 2018-06-10
Act | 2AI133CV99300-08005 | Not Started | Completed | Shelter Erection for Diesel Tank & Inert Agent of 52-SUBST-302 - SUBSTATION - STF | 2017-09-26 | 2017-10-26 | 2018-01-22 | 2018-10-23
Act | 2AI133CV99300-08065 | Not Started | Completed | EOF:Installation of gratings/handrail/stair/ladder (wherever applicable) | 2017-10-16 | 2017-10-21 | 2018-06-08 | 2018-06-10
Act | 2AI133CV99300-08085 | Not Started | Completed | EOF:Wall & Roof Cladding | 2017-10-21 | 2017-10-26 | 2018-10-21 | 2018-10-23
6 |  |  |  | Shelter Erection for Diesel Tank & Inert Agent of 50-SUBST-001 - SUBSTATION - COCC
Act | 2AI133CV99300-08030 | Not Started | Completed | EOF:Installation of Str. Steel | 2017-10-04 | 2017-10-12 | 2018-06-23 | 2018-10-08
Act | 2AI133CV99300-08035 | Not Started | Completed | EOF:Alignment & Bolting/Torqueing | 2017-10-12 | 2017-10-19 | 2018-06-24 | 2018-10-15
Act | 2AI133CV99300-08040 | Not Started | Completed | EOF:Grouting | 2017-10-19 | 2017-10-24 | 2018-12-21 | 2018-12-23
Act | 2AI133CV99300-08010 | Not Started | Completed | Shelter Erection for Diesel Tank & Inert Agent of 50-SUBST-001 - SUBSTATION - COCC | 2017-10-04 | 2017-11-04 | 2018-06-23 | 2018-12-23
Act | 2AI133CV99300-08060 | Not Started | Completed | EOF:Installation of gratings/handrail/stair/ladder (wherever applicable) | 2017-10-24 | 2017-10-29 | 2018-12-15 | 2018-12-18
Act | 2AI133CV99300-08070 | Not Started | Completed | EOF:Wall & Roof Cladding | 2017-10-29 | 2017-11-04 | 2018-12-15 | 2018-12-18
6 |  |  |  | Shelter Erection for Diesel Tank & Inert Agent of 52-SUBST-303 - SUBSTATION - LMM
Act | 2AI133CV99300-08045 | Not Started | Completed | EOF:Installation of Str. Steel | 2017-09-26 | 2017-10-04 | 2017-11-15 | 2018-10-10
Act | 2AI133CV99300-08050 | Not Started | Completed | EOF:Alignment & Bolting/Torqueing | 2017-10-04 | 2017-10-11 | 2017-12-04 | 2018-10-15
Act | 2AI133CV99300-08055 | Not Started | Completed | EOF:Grouting | 2017-10-11 | 2017-10-16 | 2018-10-17 | 2018-10-26
Act | 2AI133CV99300-08015 | Not Started | Completed | Shelter Erection for Diesel Tank & Inert Agent of 52-SUBST-303 - SUBSTATION - LMM | 2017-09-26 | 2017-10-26 | 2017-11-15 | 2018-11-05
Act | 2AI133CV99300-08075 | Not Started | Completed | EOF:Installation of gratings/handrail/stair/ladder (wherever applicable) | 2017-10-16 | 2017-10-21 | 2018-10-17 | 2018-10-26
Act | 2AI133CV99300-08095 | Not Started | Completed | EOF:Wall & Roof Cladding | 2017-10-21 | 2017-10-26 | 2018-10-28 | 2018-11-05
4 |  |  |  | HSE
5 |  |  |  | EOF SS: Installation of Fire fighting & Safety Equipments
Act | 2AI133HS01150 | Not Started | Not Started | EOF SS: Installation of Fire fighting & Safety Equipments | 2017-10-21 | 2017-12-28
6 |  |  |  | EOF SS: Fire Fighting Equipment/ Deluge System / Safety Equipments and Gaseous Fire Fighting System
Act | 2AI133HS01150-08001 | Not Started | Not Started | Fabrication & Installation of Support Structures | 2017-10-21 | 2017-12-27
Act | 2AI133HS01150-08005 | Not Started | Not Started | Installation of Instruments on Support Structures | 2017-11-22 | 2017-12-28
Act | 2AI133HS01150-08010 | Not Started | Not Started | Alignment/Levelling and grouting | 2017-10-26 | 2017-12-02
Act | 2AI133HS01150-08000 | Not Started | Not Started | EOF SS: Installation of Fire fighting & Safety Equipments | 2017-10-21 | 2017-12-28
5 |  |  |  | EOF SS: Installation of Safety Sign Boards
Act | 2AI133HS01160-08001 | Not Started | Not Started | Fabrication & Installation of Support Structures | 2017-07-29 | 2017-12-16
Act | 2AI133HS01160-08005 | Not Started | Not Started | Installation of Instruments on Support Structures | 2017-08-01 | 2017-12-19
Act | 2AI133HS01160 | Not Started | Not Started | EOF SS: Installation of Safety Sign Boards | 2017-07-29 | 2017-12-21
Act | 2AI133HS01160-08000 | Not Started | Not Started | EOF SS: Installation of Safety Sign Boards | 2017-07-29 | 2017-12-21
Act | 2AI133HS01160-08015 | Not Started | Not Started | Alignment/Levelling and grouting | 2017-08-03 | 2017-12-21
3 |  |  |  | 52-SUBST-301 - SUBSTATION - FMM
4 |  |  |  | CIVIL / STRUCTURAL / ARCHITECTURAL
5 |  |  |  | EOF SS 52-SUBST-301 : Construct Foundation (Transformer) & Pit
Act | 2AI133CV03500 | Not Started | Completed | EOF SS 52-SUBST-301 : Construct Foundation (Transformer) & Pit | 2016-09-06 | 2016-11-19 | 2017-07-14 | 2018-01-22
6 |  |  |  | 621-SUBST-0301 : Foundation works for Transformer & Pit
Act | 2AI133CV03500-08000 | Not Started | Completed | EOF SS 52-SUBST-301 : Foundation works for Transformer & Pit | 2016-09-06 | 2016-11-19 | 2017-07-14 | 2018-01-22
Act | 2AI133CV03500-08005 | Not Started | Completed | EOF SS 52-SUBST-301 : Survey Marking, Excavation & Subgrade preparation | 2016-09-06 | 2016-09-12 | 2017-07-14 | 2017-07-14
Act | 2AI133CV03500-08010 | Not Started | Completed | EOF SS 52-SUBST-301 : Blinding/PCC | 2016-09-12 | 2016-09-13 | 2017-07-22 | 2017-07-22
Act | 2AI133CV03500-08015 | Not Started | Completed | EOF SS 52-SUBST-301 : Rebar & Formwork | 2016-09-15 | 2016-09-29 | 2017-07-23 | 2017-07-27
Act | 2AI133CV03500-08020 | Not Started | Completed | EOF SS 52-SUBST-301 : Concrete Pouring | 2016-09-29 | 2016-10-03 | 2017-08-03 | 2017-08-03
Act | 2AI133CV03500-08025 | Not Started | Completed | EOF SS 52-SUBST-301 : Concrete Protection | 2016-10-11 | 2016-10-17 | 2017-08-06 | 2018-01-21
Act | 2AI133CV03500-08030 | Not Started | Completed | EOF SS 52-SUBST-301 : Backfill / Compaction | 2016-10-20 | 2016-10-26 | 2017-12-22 | 2018-01-22
Act | 2AI133CV03500-08040 | Not Started | Completed | EOF SS 52-SUBST-301 : Construction of Pit | 2016-10-26 | 2016-11-19 | 2017-10-28 | 2018-01-17
4 |  |  |  | MECHANICAL
5 |  |  |  | EOF SS 52-SUBST-301 : Fire fighting works
4 |  |  |  | ELECTRICAL
5 |  |  |  | EOF SS 52-SUBST-301 : Install Distribution boards and Annunciator Panels
Act | 2AI133EL03500 | Not Started | Completed | EOF SS 52-SUBST-301 : Install Distribution boards and Annunciator Panels | 2017-06-17 | 2017-08-07 | 2018-01-01 | 2018-02-07
Act | 2AI133EL03500-08001 | Not Started | Completed | EOF:Installation of Supports | 2017-06-17 | 2017-07-10 | 2018-01-09 | 2018-02-04
Act | 2AI133EL03500-08005 | Not Started | Completed | EOF:Installation of Distribution Board | 2017-06-28 | 2017-07-22 | 2018-01-10 | 2018-02-05
Act | 2AI133EL03500-08010 | Not Started | Completed | EOF:Installation of Annunciator Panels | 2017-07-06 | 2017-07-30 | 2018-01-01 | 2018-01-03
Act | 2AI133EL03500-08015 | Not Started | Completed | EOF:Allignment | 2017-07-30 | 2017-08-07 | 2018-01-10 | 2018-02-07
Act | 2AI133EL03500-08000 | Not Started | Completed | EOF SS 52-SUBST-301 : Install Distribution boards and Annunciator Panels | 2017-06-17 | 2017-08-07 | 2018-01-01 | 2018-02-07
5 |  |  |  | EOF SS 52-SUBST-301 : Install HV Switchboard with RCP, Power Factor & Bus Ducts
Act | 2AI133EL03300 | Not Started | Completed | EOF SS 52-SUBST-301 : Install HV Switchboard with RCP, Power Factor & Bus Ducts (Including Modification work) | 2017-07-16 | 2017-12-11 | 2017-12-28 | 2018-12-18
Act | 2AI133EL03300-08001 | Not Started | Completed | EOF:Installation of Supports | 2017-07-16 | 2017-09-04 | 2017-12-28 | 2018-01-12
Act | 2AI133EL03300-08005 | Not Started | Completed | EOF:Installation of HV Switchgear, RCP | 2017-10-17 | 2017-11-09 | 2017-12-28 | 2018-01-12
Act | 2AI133EL03300-08010 | Not Started | Completed | EOF:Installation of Bus duct | 2017-11-09 | 2017-12-03 | 2017-12-28 | 2018-01-03
Act | 2AI133EL03300-08015 | Not Started | Completed | EOF:Allignment of HV Switchgear, RCP | 2017-11-09 | 2017-11-18 | 2017-12-28 | 2018-01-14
Act | 2AI133EL03300-08020 | Not Started | Completed | EOF:Allignment of Bus duct | 2017-12-03 | 2017-12-11 | 2018-12-18 | 2018-12-18
Act | 2AI133EL03300-08000 | Not Started | Completed | EOF SS 52-SUBST-301 : Install HV Switchboard with RCP, Power Factor & Bus Ducts (Including Modification work) | 2017-07-16 | 2017-12-11 | 2017-12-28 | 2018-12-18
5 |  |  |  | EOF SS 52-SUBST-301 : Earthing Lightning Protection Works
Act | 2AI133EL03200 | Not Started | Completed | EOF SS 52-SUBST-301 : Earthing Lightning Protection Works | 2017-07-20 | 2017-09-27 | 2018-02-12 | 2018-07-13
6 |  |  |  | EOF:Earthing Work
Act | 2AI133EL03200-08001 | Not Started | Completed | EOF SS 52-SUBST-301 : Earth rod Installation | 2017-07-20 | 2017-08-10 | 2018-03-28 | 2018-07-13
Act | 2AI133EL03200-08005 | Not Started | Completed | EOF SS 52-SUBST-301 : Earth Cable Laying | 2017-07-30 | 2017-09-03 | 2018-02-12 | 2018-02-12
Act | 2AI133EL03200-08010 | Not Started | Completed | EOF SS 52-SUBST-301 : Cad welding | 2017-08-10 | 2017-09-14 | 2018-03-28 | 2018-07-04
Act | 2AI133EL03200-08015 | Not Started | Completed | EOF SS 52-SUBST-301 : Earth Bus Installation | 2017-08-17 | 2017-09-16 | 2018-02-12 | 2018-04-20
Act | 2AI133EL03200-08020 | Not Started | Completed | EOF SS 52-SUBST-301 : Earth Boss Installation | 2017-08-19 | 2017-09-18 | 2018-03-28 | 2018-04-05
Act | 2AI133EL03200-08025 | Not Started | Completed | EOF SS 52-SUBST-301 : Earth cable Termination | 2017-09-06 | 2017-09-24 | 2018-02-12 | 2018-03-18
Act | 2AI133EL03200-08045 | Not Started | Completed | EOF SS 52-SUBST-301 : Earth Pit Installation | 2017-09-16 | 2017-09-27 | 2018-03-28 | 2018-04-06
Act | 2AI133EL03200-08000 | Not Started | Completed | EOF SS 52-SUBST-301 : Earthing Work | 2017-07-20 | 2017-09-27 | 2018-02-12 | 2018-07-13
6 |  |  |  | EOF:Lightining Protection
5 |  |  |  | EOF SS 52-SUBST-301 : Install LV Switchboards with RCP, MCC & Bus Ducts
Act | 2AI133EL03400 | Not Started | Completed | EOF SS 52-SUBST-301 : Install LV Switchboards with RCP, MCC & Bus Ducts(incl. Lighting/small power,Modification work) | 2017-07-17 | 2017-10-21 | 2017-12-14 | 2018-03-27
Act | 2AI133EL03400-08001 | Not Started | Completed | EOF:Installation of Supports | 2017-07-17 | 2017-08-09 | 2017-12-14 | 2018-01-19
Act | 2AI133EL03400-08005 | Not Started | Completed | EOF:Installation of LV Switchgear, RCP & MCC | 2017-07-29 | 2017-08-21 | 2017-12-16 | 2018-01-19
Act | 2AI133EL03400-08010 | Not Started | Completed | EOF:Installation of Bus duct | 2017-09-19 | 2017-10-12 | 2018-03-24 | 2018-03-27
Act | 2AI133EL03400-08015 | Not Started | Completed | EOF:Allignment of LV Switchgear, RCP & MCC | 2017-08-21 | 2017-08-29 | 2018-01-01 | 2018-01-19
Act | 2AI133EL03400-08020 | Not Started | Completed | EOF:Allignment of Bus duct | 2017-10-12 | 2017-10-21 | 2018-03-24 | 2018-03-27
Act | 2AI133EL03400-08030 | Not Started | Completed | EOF:Installation of Lighting & Small Power Panels | 2017-10-17 | 2017-10-21 | 2018-01-01 | 2018-01-03
Act | 2AI133EL03400-08000 | Not Started | Completed | EOF SS 52-SUBST-301 : Install LV Switchboards with RCP, MCC & Bus Ducts(incl. Lighting/small power,Modification work) | 2017-07-17 | 2017-10-21 | 2017-12-14 | 2018-03-27
5 |  |  |  | EOF SS 52-SUBST-301 : Install Transformers
Act | 2AI133EL03000 | Not Started | Completed | EOF SS 52-SUBST-301 : Install Transformers | 2017-07-17 | 2017-08-27 | 2017-12-23 | 2017-12-24
Act | 2AI133EL03000-08001 | Not Started | Completed | EOF:Installation of Supports | 2017-07-17 | 2017-08-09 | 2017-12-23 | 2017-12-23
Act | 2AI133EL03000-08005 | Not Started | Completed | EOF:Installation of Transformer | 2017-07-25 | 2017-08-15 | 2017-12-24 | 2017-12-24
Act | 2AI133EL03000-08010 | Not Started | Completed | EOF:Allignment | 2017-08-15 | 2017-08-27 | 2017-12-24 | 2017-12-24
Act | 2AI133EL03000-08000 | Not Started | Completed | 621-SUBST-0301 : Install Transformers | 2017-07-17 | 2017-08-27 | 2017-12-23 | 2017-12-24
5 |  |  |  | EOF SS 52-SUBST-301 : Install UPS with Battery bank and Isolator Switch
Act | 2AI133EL03600 | Not Started | Completed | EOF SS 52-SUBST-301 : Install UPS with Battery bank and Isolator Switch | 2017-09-17 | 2017-11-25 | 2018-01-20 | 2018-04-05
Act | 2AI133EL03600-08001 | Not Started | Completed | EOF:Installation of Supports | 2017-09-17 | 2017-10-04 | 2018-01-20 | 2018-04-04
Act | 2AI133EL03600-08005 | Not Started | Completed | EOF:Installation of UPS | 2017-11-16 | 2017-11-25 | 2018-01-22 | 2018-04-04
Act | 2AI133EL03600-08015 | Not Started | Completed | EOF:Installation of Isolator Switch | 2017-09-28 | 2017-10-07 | 2018-03-28 | 2018-04-05
Act | 2AI133EL03600-08020 | Not Started | Completed | EOF:Installation of Batteries | 2017-10-04 | 2017-10-16 | 2018-01-23 | 2018-04-04
Act | 2AI133EL03600-08010 | Not Started | Completed | EOF:Installation of battery Charger | 2017-09-25 | 2017-10-03 | 2018-01-20 | 2018-04-04
Act | 2AI133EL03600-08000 | Not Started | Completed | EOF SS 52-SUBST-301 : Install UPS with Battery bank and Isolator Switch | 2017-09-17 | 2017-11-25 | 2018-01-20 | 2018-04-05
5 |  |  |  | EOF SS 52-SUBST-301 : Install E-SCADA
Act | 2AI133EL03700 | Not Started | Completed | EOF SS 52-SUBST-301 : Install E-SCADA | 2017-11-25 | 2017-12-12 | 2018-04-15 | 2018-04-18
Act | 2AI133EL03700-08000 | Not Started | Completed | EOF SS 52-SUBST-301 : Install E-SCADA | 2017-11-25 | 2017-12-12 | 2018-04-15 | 2018-04-18
5 |  |  |  | EOF SS 52-SUBST-301 : Cable laying, glanding/termination,checks
Act | 2AI133EL03100 | Not Started | Completed | EOF SS 52-SUBST-301 : Cable laying, glanding/termination,checks (incl UG cable laying to Existing SS for Tie-in) | 2017-05-27 | 2017-09-11 | 2017-12-24 | 2018-09-28
6 |  |  |  | COCC: Cable Laying
Act | 2AI133EL03100-08006 | Not Started | Completed | EOF: Install Tray support and Hangers | 2017-05-27 | 2017-06-25 | 2017-12-24 | 2017-12-24
Act | 2AI133EL03100-08010 | Not Started | Completed | EOF: Install cable trays | 2017-06-07 | 2017-07-12 | 2017-12-24 | 2017-12-24
Act | 2AI133EL03100-08015 | Not Started | Completed | EOF: Installcable trays covers | 2017-08-28 | 2017-09-11 | 2018-01-13 | 2018-01-13
Act | 2AI133EL03100-08013 | Not Started | Completed | EOF: Cable Laying - LV | 2017-07-12 | 2017-08-28 | 2017-12-24 | 2018-07-04
Act | 2AI133EL03100-08014 | Not Started | Completed | EOF: Cable Laying - HV | 2017-05-27 | 2017-07-01 | 2018-01-13 | 2018-01-13
Act | 2AI133EL03100-08000 | Not Started | Completed | 621-SUBST-0301 : Cable laying | 2017-05-27 | 2017-09-11 | 2017-12-24 | 2018-07-04
6 |  |  |  | COCC: Glanding & termination. Checks
Act | 2AI133EL03100-08005 | Not Started | Completed | 621-SUBST-0301 : Cable glanding/termination,checks | 2017-07-01 | 2017-09-10 | 2018-01-06 | 2018-09-28
7 |  |  |  | COCC: Cable laying, glanding & termination for LV
Act | 2AI133EL03100-08020 | Not Started | Completed | EOF: Cable Glanding for LV cables | 2017-08-01 | 2017-09-03 | 2018-01-06 | 2018-09-27
Act | 2AI133EL03100-08025 | Not Started | Completed | EOF: Continuity Checks & Terminations for LV cables | 2017-08-20 | 2017-09-06 | 2018-01-08 | 2018-03-16
Act | 2AI133EL03100-08030 | Not Started | Completed | EOF: Tagging for LV cables | 2017-09-04 | 2017-09-10 | 2018-01-08 | 2018-09-28
7 |  |  |  | COCC: Cable laying, glanding & termination for HV
Act | 2AI133EL03100-08040 | Not Started | Completed | EOF: Cable Glanding for HV cables | 2017-07-01 | 2017-07-24 | 2018-01-21 | 2018-02-07
Act | 2AI133EL03100-08045 | Not Started | Completed | EOF: Continuity Checks & Terminations for HV cables | 2017-07-24 | 2017-08-07 | 2018-01-21 | 2018-02-07
Act | 2AI133EL03100-08050 | Not Started | Completed | EOF: Tagging for HV cables | 2017-08-07 | 2017-08-12 | 2018-01-21 | 2018-02-07
7 |  |  |  | COCC: Cable laying, glanding & termination for Lighting
4 |  |  |  | INSTRUMENTATION
5 |  |  |  | EOF SS 52-SUBST-301 : Install - IRP Cabinets
Act | 2AI133IC03100 | Not Started | Completed | EOF SS 52-SUBST-301 : Install - IRP Cabinets | 2017-10-17 | 2017-10-29 | 2019-04-08 | 2019-04-10
Act | 2AI133IC03100-08000 | Not Started | Completed | EOF SS 52-SUBST-301 : Install - IRP Cabinets | 2017-10-17 | 2017-10-29 | 2019-04-08 | 2019-04-10
5 |  |  |  | EOF SS 52-SUBST-301 : Install - ICSS related equipments
Act | 2AI133IC03200 | Not Started | Completed | EOF SS 52-SUBST-301 : Install - ICSS related equipments | 2017-10-17 | 2017-11-04 | 2019-04-08 | 2019-04-10
Act | 2AI133IC03200-08000 | Not Started | Completed | EOF SS 52-SUBST-301 : Install - ICSS related equipments & Other Instrument/Equipment | 2017-10-17 | 2017-11-04 | 2019-04-08 | 2019-04-10
5 |  |  |  | EOF SS 52-SUBST-301 : Cable laying, glanding, termination & continuity check
Act | 2AI133IC03000 | Not Started | Completed | EOF SS 52-SUBST-301 : Cable laying, glanding, termination & continuity check | 2017-05-27 | 2017-11-30 | 2018-03-17 | 2018-06-27
6 |  |  |  | EOF: Cable Laying
Act | 2AI133IC03000-08006 | Not Started | Completed | EOF:Cable laying | 2017-08-24 | 2017-11-08 | 2018-03-28 | 2018-05-11
Act | 2AI133IC03000-08001 | Not Started | Completed | EOF:Cable Tray Installation | 2017-05-27 | 2017-07-24 | 2018-03-17 | 2018-06-14
Act | 2AI133IC03000-08000 | Not Started | Completed | 621-SUBST-301 : Cable laying | 2017-05-27 | 2017-11-08 | 2018-03-17 | 2018-06-14
6 |  |  |  | EOF: Glanding & termination. Continuty Checks
Act | 2AI133IC03000-08010 | Not Started | Completed | EOF:Glanding & termination | 2017-11-04 | 2017-11-27 | 2018-03-22 | 2018-06-26
Act | 2AI133IC03000-08015 | Not Started | Completed | EOF:Continuity check | 2017-11-22 | 2017-11-30 | 2018-03-22 | 2018-06-27
Act | 2AI133IC03000-08005 | Not Started | Completed | 621-SUBST-301 : Glanding, termination & continuity check | 2017-11-04 | 2017-11-30 | 2018-03-22 | 2018-06-27
5 |  |  |  | EOF SS 52-SUBST-301 : Install - Fire Alarm & Testing
4 |  |  |  | TELECOM
5 |  |  |  | EOF SS 52-SUBST-301 : FO & Telephone Cabling, Telecom system install, Cable Terminations
Act | 2AI133TE03000 | Not Started | Completed | EOF SS 52-SUBST-301 : FO & Telephone Cabling, Telecom System install, Cable Terminations & continuity checks | 2017-07-17 | 2017-09-20 | 2018-01-01 | 2019-04-10
Act | 2AI133TE03000-08000 | Not Started | Completed | 621-SUBST-301 : FO & Telephone Cable Laying | 2017-07-17 | 2017-09-02 | 2018-06-04 | 2018-06-06
Act | 2AI133TE03000-08005 | Not Started | Completed | 621-SUBST-301 : Installation - Telecom System | 2017-08-10 | 2017-09-03 | 2018-01-01 | 2018-01-03
Act | 2AI133TE03000-08010 | Not Started | Completed | 621-SUBST-301 : Cable Terminations | 2017-09-03 | 2017-09-20 | 2019-04-08 | 2019-04-10
3 |  |  |  | 52-SUBST-302 - SUBSTATION - STF
4 |  |  |  | CIVIL / STRUCTURAL / ARCHITECTURAL
5 |  |  |  | EOF SS 52-SUBST-302 : Construct Foundation (Transformer) & Pit
Act | 2AI133CV05500 | Not Started | Completed | EOF SS 52-SUBST-302 : Construct Foundation (Transformer) & Pit | 2016-09-06 | 2016-11-05 | 2017-08-14 | 2018-01-24
6 |  |  |  | EOF SS 52-SUBST-302 : Foundation works for Transformer & Pit
Act | 2AI133CV05500-08000 | Not Started | Completed | EOF SS 52-SUBST-302 : Foundation works for Transformer & Pit | 2016-09-06 | 2016-11-05 | 2017-08-14 | 2018-01-24
Act | 2AI133CV05500-08010 | Not Started | Completed | EOF SS 52-SUBST-302 : Survey Marking, Excavation & Subgrade preparation | 2016-09-06 | 2016-09-12 | 2017-08-14 | 2017-08-26
Act | 2AI133CV05500-08020 | Not Started | Completed | EOF SS 52-SUBST-302 : Blinding/PCC | 2016-09-12 | 2016-09-13 | 2017-08-29 | 2017-08-29
Act | 2AI133CV05500-08030 | Not Started | Completed | EOF SS 52-SUBST-302 : Rebar & Formwork | 2016-09-15 | 2016-09-20 | 2017-08-30 | 2017-10-22
Act | 2AI133CV05500-08040 | Not Started | Completed | EOF SS 52-SUBST-302 :Concrete Pouring | 2016-09-20 | 2016-09-21 | 2017-09-12 | 2017-10-23
Act | 2AI133CV05500-08050 | Not Started | Completed | EOF SS 52-SUBST-302 :Concrete Protection | 2016-09-29 | 2016-10-05 | 2017-10-02 | 2018-01-21
Act | 2AI133CV05500-08060 | Not Started | Completed | EOF SS 52-SUBST-302 :Backfill / Compaction | 2016-10-09 | 2016-10-12 | 2018-01-22 | 2018-01-24
Act | 2AI133CV05500-08070 | Not Started | Completed | EOF SS 52-SUBST-302 :Construction of Pit | 2016-10-12 | 2016-11-05 | 2017-11-12 | 2017-11-24
4 |  |  |  | MECHANICAL
5 |  |  |  | EOF SS 52-SUBST-302 : Fire fighting works
4 |  |  |  | ELECTRICAL
5 |  |  |  | EOF SS 52-SUBST-302 : Cable laying, glanding, termination & continuity check
Act | 2AI133EL05100 | Not Started | Completed | EOF SS 52-SUBST-302 : Cable laying, glanding, termination & continuity check | 2017-06-07 | 2017-10-05 | 2018-02-05 | 2019-04-10
6 |  |  |  | 621-SUBST-0301 : Cable laying
Act | 2AI133EL05100-08015 | Not Started | Completed | EOF: Install Tray support and Hangers | 2017-06-07 | 2017-06-28 | 2018-02-07 | 2018-02-07
Act | 2AI133EL05100-08020 | Not Started | Completed | EOF: Install cable trays | 2017-06-19 | 2017-07-18 | 2018-08-08 | 2018-10-08
Act | 2AI133EL05100-08025 | Not Started | Completed | EOF: Installcable trays covers | 2017-09-03 | 2017-09-17 | 2018-09-03 | 2018-10-15
Act | 2AI133EL05100-08029 | Not Started | Completed | EOF: Cable Laying - LV | 2017-07-18 | 2017-09-03 | 2018-04-02 | 2018-09-10
Act | 2AI133EL05100-08045 | Not Started | Completed | EOF: Cable Laying - HV | 2017-07-20 | 2017-08-24 | 2019-04-08 | 2019-04-10
Act | 2AI133EL05100-08000 | Not Started | Completed | 621-SUBST-0302 : Cable laying | 2017-06-07 | 2017-09-17 | 2018-02-07 | 2019-04-10
6 |  |  |  | 621-SUBST-0301 : Cable glanding/termination,checks
Act | 2AI133EL05100-08005 | Not Started | Completed | 621-SUBST-0302 : Cable glanding, termination & continuity check | 2017-08-07 | 2017-10-05 | 2018-02-05 | 2018-10-10
7 |  |  |  | COCC: Glanding & termination for LV
Act | 2AI133EL05100-08030 | Not Started | Completed | EOF: Cable Glanding for LV cables | 2017-08-07 | 2017-09-09 | 2018-02-05 | 2018-10-10
Act | 2AI133EL05100-08035 | Not Started | Completed | EOF: Continuity Checks & Terminations for LV cables | 2017-08-26 | 2017-09-12 | 2018-07-02 | 2018-10-10
Act | 2AI133EL05100-08040 | Not Started | Completed | EOF: Tagging for LV cables | 2017-09-10 | 2017-09-16 | 2018-07-02 | 2018-10-10
7 |  |  |  | COCC: Glanding & termination for HV
Act | 2AI133EL05100-08050 | Not Started | Completed | EOF: Cable Glanding for HV cables | 2017-08-24 | 2017-09-17 | 2018-10-08 | 2018-10-10
Act | 2AI133EL05100-08055 | Not Started | Completed | EOF: Continuity Checks & Terminations for HV cables | 2017-09-17 | 2017-10-01 | 2018-10-08 | 2018-10-10
Act | 2AI133EL05100-08060 | Not Started | Completed | EOF: Tagging for HV cables | 2017-10-01 | 2017-10-05 | 2018-10-08 | 2018-10-10
6 |  |  |  | COCC: Cable Tray Installation
5 |  |  |  | EOF SS 52-SUBST-302 : Install Distribution boards and Annunciator Panels
Act | 2AI133EL05500-08001 | Not Started | Completed | EOF:Installation of Supports | 2017-08-16 | 2017-09-09 | 2018-01-16 | 2018-04-23
Act | 2AI133EL05500-08005 | Not Started | Completed | EOF:Installation of Distribution Board | 2017-08-28 | 2017-09-20 | 2018-01-16 | 2018-04-24
Act | 2AI133EL05500-08010 | Not Started | Completed | EOF:Installation of Annunciator Panels | 2017-09-05 | 2017-09-28 | 2018-01-01 | 2018-01-03
Act | 2AI133EL05500-08015 | Not Started | Completed | EOF:Allignment | 2017-09-28 | 2017-10-07 | 2018-01-16 | 2018-04-24
Act | 2AI133EL05500 | Not Started | Completed | EOF SS 52-SUBST-302 : Install Distribution boards and Annunciator Panels | 2017-08-16 | 2017-10-07 | 2018-01-01 | 2018-04-24
Act | 2AI133EL05500-08000 | Not Started | Completed | 621-SUBST-0302 : Install Distribution boards and Annunciator Panels | 2017-08-16 | 2017-10-07 | 2018-01-01 | 2018-04-24
5 |  |  |  | EOF SS 52-SUBST-302 : Install HV Switchboard with RCP, Power Factor & Bus Ducts
Act | 2AI133EL05300-08001 | Not Started | Completed | EOF:Installation of Supports | 2017-09-14 | 2017-11-06 | 2017-11-24 | 2017-12-06
Act | 2AI133EL05300-08005 | Not Started | Completed | EOF:Installation of HV Switchgear, RCP | 2017-10-17 | 2017-11-11 | 2017-11-24 | 2017-12-06
Act | 2AI133EL05300-08010 | Not Started | Completed | EOF:Installation of Bus duct | 2017-11-11 | 2017-12-05 | 2017-11-22 | 2017-12-05
Act | 2AI133EL05300-08015 | Not Started | Completed | EOF:Allignment of HV Switchgear, RCP | 2017-11-11 | 2017-11-22 | 2017-11-20 | 2017-12-06
Act | 2AI133EL05300 | Not Started | Completed | EOF SS 52-SUBST-302 : Install HV Switchboard with RCP, Capacitor & Bus Ducts | 2017-09-14 | 2017-12-17 | 2017-11-20 | 2018-04-04
Act | 2AI133EL05300-08020 | Not Started | Completed | EOF:Allignment of Bus duct | 2017-12-05 | 2017-12-17 | 2017-12-05 | 2018-04-04
Act | 2AI133EL05300-08000 | Not Started | Completed | 621-SUBST-0302 : Install HV Switchboard with RCP, Power Factor & Bus Ducts | 2017-09-14 | 2017-12-17 | 2017-11-20 | 2018-04-04
5 |  |  |  | EOF SS 52-SUBST-302 : Earthing Lightning Protection Works
Act | 2AI133EL05200 | Not Started | Completed | EOF SS 52-SUBST-302 : Earthing Lightning Protection Works | 2017-07-20 | 2017-09-30 | 2018-05-07 | 2019-04-10
6 |  |  |  | EOF:Earthing Work
Act | 2AI133EL05200-08001 | Not Started | Completed | COCC: Earth rod Installation | 2017-07-20 | 2017-08-10 | 2019-04-08 | 2019-04-10
Act | 2AI133EL05200-08005 | Not Started | Completed | COCC: Earth Cable Laying | 2017-08-10 | 2017-09-14 | 2018-05-07 | 2018-05-25
Act | 2AI133EL05200-08010 | Not Started | Completed | COCC: Cad welding | 2017-08-13 | 2017-09-17 | 2018-05-15 | 2018-10-19
Act | 2AI133EL05200-08015 | Not Started | Completed | COCC: Earth Bus Installation | 2017-08-20 | 2017-09-18 | 2019-01-07 | 2019-01-18
Act | 2AI133EL05200-08020 | Not Started | Completed | COCC: Earth Boss Installation | 2017-08-21 | 2017-09-20 | 2019-04-08 | 2019-04-10
Act | 2AI133EL05200-08025 | Not Started | Completed | COCC: Earth cable Termination | 2017-09-09 | 2017-09-26 | 2018-08-06 | 2018-08-08
Act | 2AI133EL05200-08045 | Not Started | Completed | COCC: Earth Pit Installation | 2017-09-18 | 2017-09-30 | 2019-04-08 | 2019-04-10
Act | 2AI133EL05200-08000 | Not Started | Completed | EOF:Earthing Work | 2017-07-20 | 2017-09-30 | 2018-05-07 | 2019-04-10
6 |  |  |  | EOF:Lightining Protection
5 |  |  |  | EOF SS 52-SUBST-302 : Install LV Switchboards with RCP, MCC & Bus Ducts(incl. Lighting/small power)
Act | 2AI133EL05400-08001 | Not Started | Completed | EOF:Installation of Supports | 2017-07-17 | 2017-08-09 | 2018-01-06 | 2018-03-18
Act | 2AI133EL05400-08005 | Not Started | Completed | EOF:Installation of LV Switchgear, RCP & MCC | 2017-07-29 | 2017-08-21 | 2018-01-06 | 2018-03-18
Act | 2AI133EL05400-08010 | Not Started | Completed | EOF:Installation of Bus duct | 2017-09-19 | 2017-10-12 | 2018-03-28 | 2018-07-13
Act | 2AI133EL05400-08015 | Not Started | Completed | EOF:Allignment of LV Switchgear, RCP & MCC | 2017-08-21 | 2017-08-29 | 2018-01-06 | 2018-03-18
Act | 2AI133EL05400 | Not Started | Completed | EOF SS 52-SUBST-302 : Install LV Switchboards with RCP, MCC & Bus Ducts(incl. Lighting/small power) | 2017-07-17 | 2017-10-21 | 2018-01-06 | 2018-07-27
Act | 2AI133EL05400-08020 | Not Started | Completed | EOF:Allignment of Bus duct | 2017-10-12 | 2017-10-21 | 2018-07-02 | 2018-07-27
Act | 2AI133EL05400-08000 | Not Started | Completed | 621-SUBST-0302 : Install LV Switchboards with RCP, MCC & Bus Ducts(incl. Lighting/small power) | 2017-07-17 | 2017-10-21 | 2018-01-06 | 2018-07-27
5 |  |  |  | EOF SS 52-SUBST-302 : Install Transformers
Act | 2AI133EL05000-08001 | Not Started | Completed | EOF:Installation of Supports | 2017-08-09 | 2017-09-02 | 2018-01-26 | 2018-01-27
Act | 2AI133EL05000-08005 | Not Started | Completed | EOF:Installation of Transformer | 2017-08-17 | 2017-09-07 | 2018-01-28 | 2018-02-07
Act | 2AI133EL05000-08010 | Not Started | Completed | EOF:Allignment | 2017-09-07 | 2017-09-19 | 2018-02-08 | 2018-02-08
Act | 2AI133EL05000 | Not Started | Completed | EOF SS 52-SUBST-302 : Install Transformers | 2017-08-09 | 2017-09-19 | 2018-01-26 | 2018-02-08
Act | 2AI133EL05000-08000 | Not Started | Completed | 621-SUBST-0302 : Install Transformers | 2017-08-09 | 2017-09-19 | 2018-01-26 | 2018-02-08
5 |  |  |  | EOF SS 52-SUBST-302 : Install UPS with Battery bank and Isolator Switch
Act | 2AI133EL05600-08001 | Not Started | Completed | EOF:Installation of Supports | 2017-09-17 | 2017-10-04 | 2018-03-28 | 2018-04-04
Act | 2AI133EL05600-08005 | Not Started | Completed | EOF:Installation of UPS | 2017-11-16 | 2017-11-25 | 2018-03-29 | 2018-04-05
Act | 2AI133EL05600-08010 | Not Started | Completed | EOF:Installation of Isolator Switch | 2017-09-28 | 2017-10-07 | 2018-03-30 | 2018-04-05
Act | 2AI133EL05600-08015 | Not Started | Completed | EOF:Installation of Batteries | 2017-10-04 | 2017-10-16 | 2018-03-23 | 2018-04-06
Act | 2AI133EL05600 | Not Started | Completed | EOF SS 52-SUBST-302 : Install UPS, Battery Charger with Battery bank and Isolator Switch | 2017-09-17 | 2017-11-25 | 2018-03-23 | 2018-04-06
Act | 2AI133EL05600-08006 | Not Started | Completed | EOF:Installation of battery Charger | 2017-09-25 | 2017-10-03 | 2018-03-30 | 2018-04-06
Act | 2AI133EL05600-08000 | Not Started | Completed | 621-SUBST-0302 : Install UPS with Battery bank and Isolator Switch | 2017-09-17 | 2017-11-25 | 2018-03-23 | 2018-04-06
5 |  |  |  | EOF SS 52-SUBST-302 : Install E-SCADA
Act | 2AI133EL05700-08000 | Not Started | Completed | EOF SS 52-SUBST-302 : Install E-SCADA | 2017-11-25 | 2017-12-12 | 2018-04-02 | 2018-04-04
Act | 2AI133EL05700 | Not Started | Completed | EOF SS 52-SUBST-302 : Install E-SCADA | 2017-11-25 | 2017-12-12 | 2018-04-02 | 2018-04-04
4 |  |  |  | INSTRUMENTATION
5 |  |  |  | EOF SS 52-SUBST-302 : Install - IRP Cabinets
Act | 2AI133IC05100-08000 | Not Started | Completed | EOF SS 52-SUBST-302 : Install - IRP Cabinets | 2017-10-17 | 2017-11-09 | 2018-03-18 | 2018-03-18
Act | 2AI133IC05100 | Not Started | Completed | EOF SS 52-SUBST-302 : Install - IRP Cabinets | 2017-10-17 | 2017-11-09 | 2018-03-18 | 2018-03-18
5 |  |  |  | EOF SS 52-SUBST-302 : Install - ICSS related equipments
Act | 2AI133IC05200-08000 | Not Started | Completed | EOF SS 52-SUBST-302 : Install - ICSS related equipments | 2017-10-17 | 2017-10-29 | 2018-03-28 | 2019-04-10
Act | 2AI133IC05200 | Not Started | Completed | EOF SS 52-SUBST-302 : Install - ICSS related equipments | 2017-10-17 | 2017-10-29 | 2018-03-28 | 2019-04-10
5 |  |  |  | EOF SS 52-SUBST-302 : Cable laying, glanding, termination & continuity check
Act | 2AI133IC05000 | Not Started | Completed | EOF SS 52-SUBST-302 : Cable laying, glanding, termination & continuity check | 2017-06-28 | 2017-12-07 | 2018-02-05 | 2018-10-04
6 |  |  |  | 621-SUBST-0302 : Cable laying
Act | 2AI133IC05000-08003 | Not Started | Completed | EOF:Cable laying | 2017-08-26 | 2017-11-15 | 2018-05-07 | 2018-10-04
Act | 2AI133IC05000-08001 | Not Started | Completed | EOF:Cable Tray Installation | 2017-06-28 | 2017-08-26 | 2018-02-05 | 2018-10-02
Act | 2AI133IC05000-08000 | Not Started | Completed | 621-SUBST-0302 : Cable laying | 2017-06-28 | 2017-11-15 | 2018-02-05 | 2018-10-04
6 |  |  |  | 621-SUBST-0302 : Cable glanding, termination & continuity check
Act | 2AI133IC05000-08006 | Not Started | Completed | EOF:Glanding | 2017-11-09 | 2017-11-27 | 2018-05-10 | 2018-08-02
Act | 2AI133IC05000-08010 | Not Started | Completed | EOF:Continuity check & termination | 2017-11-21 | 2017-11-29 | 2018-05-20 | 2018-08-03
Act | 2AI133IC05000-08020 | Not Started | Completed | EOF:Tagging | 2017-11-29 | 2017-12-07 | 2018-03-28 | 2018-08-03
Act | 2AI133IC05000-08005 | Not Started | Completed | 621-SUBST-0302 : Cable glanding, termination & continuity check | 2017-11-09 | 2017-12-07 | 2018-03-28 | 2018-08-03
5 |  |  |  | EOF SS 52-SUBST-302 : Install - Fire Alarm & Testing
4 |  |  |  | TELECOM
5 |  |  |  | EOF SS 52-SUBST-302 : FO & Telephone Cabling, Telecom system install, Cable Terminations
Act | 2AI133TE05000-08000 | Not Started | Completed | EOF:FO & Telephone Cable Laying | 2017-08-26 | 2017-10-11 | 2019-04-08 | 2019-04-10
Act | 2AI133TE05000-08005 | Not Started | Completed | EOF:Installation - Telecom System | 2017-09-19 | 2017-10-12 | 2018-04-02 | 2018-04-04
Act | 2AI133TE05000-08010 | Not Started | Completed | EOF:Cable Terminations & continuity checks | 2017-10-12 | 2017-10-30 | 2018-04-21 | 2018-04-24
Act | 2AI133TE05000 | Not Started | Completed | EOF SS 52-SUBST-302 : FO & Telephone Cabling, Telecom System install, Cable Terminations & continuity checks | 2017-08-26 | 2017-10-30 | 2018-04-02 | 2019-04-10
3 |  |  |  | 50-SUBST-001 - SUBSTATION - COCC
4 |  |  |  | CIVIL / STRUCTURAL / ARCHITECTURAL
5 |  |  |  | EOF SS 50-SUBST-001 :Construct Foundation (Transformer) & Pit
Act | 2AI133CV01500 | Not Started | Completed | EOF SS 50-SUBST-001 : Construct Foundation (Transformer) & Pit | 2016-09-26 | 2016-12-08 | 2017-12-05 | 2018-03-12
6 |  |  |  | EOF SS 50-SUBST-001 : Foundation works for Transformer & Pit
Act | 2AI133CV01500-08000 | Not Started | Completed | EOF SS 50-SUBST-001 : Foundation works for Transformer & Pit | 2016-09-26 | 2016-12-08 | 2017-12-05 | 2018-03-12
Act | 2AI133CV01500-08005 | Not Started | Completed | EOF SS 50-SUBST-001 : Survey Marking, Excavation & Subgrade preparation | 2016-09-26 | 2016-10-02 | 2017-12-05 | 2017-12-15
Act | 2AI133CV01500-08010 | Not Started | Completed | EOF SS 50-SUBST-001 : Blinding/PCC | 2016-10-02 | 2016-10-03 | 2017-12-17 | 2017-12-17
Act | 2AI133CV01500-08015 | Not Started | Completed | EOF SS 50-SUBST-001 : Rebar & Formwork | 2016-10-05 | 2016-10-19 | 2018-01-03 | 2018-01-06
Act | 2AI133CV01500-08020 | Not Started | Completed | EOF SS 50-SUBST-001 : Concrete Pouring | 2016-10-19 | 2016-10-23 | 2017-12-30 | 2017-12-30
Act | 2AI133CV01500-08025 | Not Started | Completed | EOF SS 50-SUBST-001 : Concrete Protection | 2016-10-31 | 2016-11-06 | 2018-03-07 | 2018-03-12
Act | 2AI133CV01500-08030 | Not Started | Completed | EOF SS 50-SUBST-001 : Backfill / Compaction | 2016-11-09 | 2016-11-15 | 2018-01-05 | 2018-01-25
Act | 2AI133CV01500-08035 | Not Started | Completed | EOF SS 50-SUBST-001 : Construction of Pit | 2016-11-15 | 2016-12-08 | 2018-01-10 | 2018-01-24
4 |  |  |  | MECHANICAL
5 |  |  |  | EOF SS 50-SUBST-001 :Fire fighting works
4 |  |  |  | ELECTRICAL
5 |  |  |  | EOF SS 50-SUBST-001 : Cable laying, glanding, termination & continuity check
Act | 2AI133EL01100 | Not Started | Completed | EOF SS 50-SUBST-001 : Cable laying, glanding, termination & continuity check | 2017-06-19 | 2017-10-10 | 2018-02-05 | 2019-04-10
6 |  |  |  | COCC CCR Field & Building : Install Electrical Cable trays & Supports
6 |  |  |  | COCC CCR Field & Building : Electrical Cable Laying
Act | 2AI133EL01100-08001 | Not Started | Completed | EOF:Fabricate Tray Supports | 2017-07-01 | 2017-07-30 | 2019-04-08 | 2019-04-10
Act | 2AI133EL01100-08006 | Not Started | Completed | EOF: Install cable trays | 2017-07-12 | 2017-08-10 | 2018-07-07 | 2019-03-06
Act | 2AI133EL01100-08011 | Not Started | Completed | EOF: Installcable trays covers | 2017-09-26 | 2017-10-10 | 2018-09-03 | 2019-03-06
Act | 2AI133EL01100-08015 | Not Started | Completed | EOF: Cable Laying - LV | 2017-08-10 | 2017-09-26 | 2018-02-07 | 2018-09-05
Act | 2AI133EL01100-08035 | Not Started | Completed | EOF: Cable Laying - HV | 2017-06-19 | 2017-07-24 | 2018-02-05 | 2018-02-07
Act | 2AI133EL01100-08000 | Not Started | Completed | 621-SUBST-0001 : Cable laying | 2017-06-19 | 2017-10-10 | 2018-02-05 | 2019-04-10
6 |  |  |  | COCC CCR Field & Building : Cable Glanding & Terminations
Act | 2AI133EL01100-08005 | Not Started | Completed | 621-SUBST-0001 : Cable glanding, termination & continuity check | 2017-07-24 | 2017-10-09 | 2018-05-14 | 2019-04-10
7 |  |  |  | COCC: Cable laying, glanding & termination for LV
Act | 2AI133EL01100-08020 | Not Started | Completed | EOF: Cable Glanding for LV cables | 2017-08-30 | 2017-10-02 | 2018-05-14 | 2018-06-23
Act | 2AI133EL01100-08025 | Not Started | Completed | EOF: Continuity Checks & Terminations for LV cables | 2017-09-18 | 2017-10-05 | 2018-05-15 | 2018-06-24
Act | 2AI133EL01100-08030 | Not Started | Completed | EOF: Tagging for LV cables | 2017-10-03 | 2017-10-09 | 2018-05-16 | 2018-06-25
7 |  |  |  | COCC: Cable laying, glanding & termination for HV
Act | 2AI133EL01100-08040 | Not Started | Completed | EOF: Cable Glanding for HV cables | 2017-07-24 | 2017-08-16 | 2019-04-08 | 2019-04-10
Act | 2AI133EL01100-08045 | Not Started | Completed | EOF: Continuity Checks & Terminations for HV cables | 2017-08-21 | 2017-09-04 | 2019-04-08 | 2019-04-10
Act | 2AI133EL01100-08050 | Not Started | Completed | EOF: Tagging for HV cables | 2017-09-04 | 2017-09-09 | 2019-04-08 | 2019-04-10
5 |  |  |  | EOF SS 50-SUBST-001 : Install Distribution boards and Annunciator Panels
Act | 2AI133EL01500-08001 | Not Started | Completed | EOF:Installation of Supports | 2017-10-17 | 2017-11-04 | 2018-03-24 | 2018-04-05
Act | 2AI133EL01500-08005 | Not Started | Completed | EOF:Installation of Distribution Board | 2017-10-23 | 2017-11-15 | 2018-03-25 | 2018-04-06
Act | 2AI133EL01500-08010 | Not Started | Completed | EOF:Installation of Annunciator Panels | 2017-10-31 | 2017-11-23 | 2018-04-02 | 2018-04-04
Act | 2AI133EL01500-08015 | Not Started | Completed | EOF:Allignment | 2017-11-23 | 2017-12-02 | 2018-03-23 | 2019-04-10
Act | 2AI133EL01500-08000 | Not Started | Completed | EOF SS 50-SUBST-001 : Install Distribution boards and Annunciator Panels | 2017-10-17 | 2017-12-02 | 2018-03-23 | 2019-04-10
Act | 2AI133EL01500 | Not Started | Completed | EOF SS 50-SUBST-001 : Install Distribution boards and Annunciator Panels | 2017-10-17 | 2017-12-02 | 2018-03-23 | 2019-04-10
5 |  |  |  | EOF SS 50-SUBST-001 : Install HV Switchboard with RCP, Power Factor & Bus Ducts
Act | 2AI133EL01300-08001 | Not Started | Completed | Foundation Checks/Preparation | 2017-07-17 | 2017-09-05 | 2017-11-24 | 2017-12-06
Act | 2AI133EL01300-08005 | Not Started | Completed | Installation on Foundation | 2017-08-13 | 2017-09-05 | 2017-11-25 | 2017-12-06
Act | 2AI133EL01300-08010 | Not Started | Completed | Preliminary Alignment & Grouting | 2017-09-05 | 2017-09-28 | 2017-11-26 | 2017-12-06
Act | 2AI133EL01300-08015 | Not Started | Completed | Final Alignment | 2017-09-28 | 2017-10-07 | 2017-11-27 | 2018-01-03
Act | 2AI133EL01300-08000 | Not Started | Completed | EOF SS 50-SUBST-001 : Install HV Switchboard with RCP, Power Factor & Bus Ducts | 2017-07-17 | 2017-10-07 | 2017-11-24 | 2018-01-03
Act | 2AI133EL01300 | Not Started | Completed | EOF SS 50-SUBST-001 : Install HV Switchboard with RCP, Power Factor & Bus Ducts | 2017-07-17 | 2017-10-07 | 2017-11-24 | 2018-01-03
5 |  |  |  | EOF SS 50-SUBST-001 : Earthing Lightning Protection Works
6 |  |  |  | EOF:Earthing Work
Act | 2AI133EL01200-08001 | Not Started | Completed | COCC: Earth rod Installation | 2017-07-01 | 2017-07-22 | 2018-10-13 | 2018-10-19
Act | 2AI133EL01200-08005 | Not Started | Completed | COCC: Earth Cable Laying | 2017-07-22 | 2017-08-26 | 2018-03-05 | 2019-04-10
Act | 2AI133EL01200-08010 | Not Started | Completed | COCC: Cad welding | 2017-07-24 | 2017-08-28 | 2018-03-28 | 2019-04-10
Act | 2AI133EL01200-08015 | Not Started | Completed | COCC: Earth Bus Installation | 2017-07-31 | 2017-08-29 | 2018-07-27 | 2018-08-03
Act | 2AI133EL01200-08020 | Not Started | Completed | COCC: Earth Boss Installation | 2017-08-01 | 2017-08-31 | 2018-07-21 | 2018-07-27
Act | 2AI133EL01200-08025 | Not Started | Completed | COCC: Earth cable Termination | 2017-08-20 | 2017-09-06 | 2018-07-11 | 2019-03-01
Act | 2AI133EL01200-08030 | Not Started | Completed | COCC: Earth Pit Installation | 2017-08-29 | 2017-09-10 | 2018-08-25 | 2019-04-10
Act | 2AI133EL01200-08000 | Not Started | Completed | EOF:Earthing Work | 2017-07-01 | 2017-09-10 | 2018-03-05 | 2019-04-10
Act | 2AI133EL01200 | Not Started | Completed | EOF:Earthing Work | 2017-07-01 | 2017-09-10 | 2018-03-05 | 2019-04-10
6 |  |  |  | EOF:Lightining Protection
5 |  |  |  | EOF SS 50-SUBST-001 : Install LV Switchboards with RCP, MCC & Bus Ducts(incl. Lighting/small power)
Act | 2AI133EL01400-08025 | Not Started | Completed | EOF:Installation of Supports | 2017-10-17 | 2017-11-15 | 2018-03-23 | 2018-04-04
Act | 2AI133EL01400-08030 | Not Started | Completed | EOF:Installation of LV Switchgear, RCP & MCC | 2017-10-29 | 2017-11-21 | 2018-03-25 | 2018-07-26
Act | 2AI133EL01400-08035 | Not Started | Completed | EOF:Installation of Bus duct | 2017-12-02 | 2017-12-26 | 2018-05-26 | 2019-01-25
Act | 2AI133EL01400-08040 | Not Started | Completed | EOF:Allignment of LV Switchgear, RCP & MCC | 2017-11-21 | 2017-12-02 | 2018-03-26 | 2018-07-27
Act | 2AI133EL01400-08045 | Not Started | Completed | EOF:Allignment of Bus duct | 2017-12-18 | 2017-12-28 | 2018-09-03 | 2019-02-08
Act | 2AI133EL01400-08000 | Not Started | Completed | EOF SS 50-SUBST-001 : Install LV Switchboards with RCP, MCC & Bus Ducts(incl. Lighting/small power) | 2017-10-17 | 2017-12-28 | 2018-03-23 | 2019-02-08
Act | 2AI133EL01400 | Not Started | Completed | EOF SS 50-SUBST-001 : Install LV Switchboards with RCP, MCC & Bus Ducts(incl. Lighting/small power) | 2017-10-17 | 2017-12-28 | 2018-03-23 | 2019-02-08
5 |  |  |  | EOF SS 50-SUBST-001 :Install Transformers
Act | 2AI133EL01000-08001 | Not Started | Completed | EOF:Installation of Supports | 2017-09-02 | 2017-09-25 | 2018-03-23 | 2018-03-26
Act | 2AI133EL01000-08005 | Not Started | Completed | EOF:Installation of Transformer | 2017-09-10 | 2017-10-01 | 2018-03-05 | 2018-03-27
Act | 2AI133EL01000-08010 | Not Started | Completed | EOF:Allignment | 2017-10-01 | 2017-10-12 | 2018-03-05 | 2018-03-27
Act | 2AI133EL01000-08000 | Not Started | Completed | EOF SS 50-SUBST-001 :Install Transformers | 2017-09-02 | 2017-10-12 | 2018-03-05 | 2018-03-27
Act | 2AI133EL01000 | Not Started | Completed | EOF SS 50-SUBST-001 :Install Transformers | 2017-09-02 | 2017-10-12 | 2018-03-05 | 2018-03-27
5 |  |  |  | EOF SS 50-SUBST-001 : Install UPS with Battery bank and Isolator Switch
Act | 2AI133EL01600-08001 | Not Started | Completed | EOF:Installation of Supports | 2017-09-17 | 2017-10-04 | 2018-03-23 | 2019-04-10
Act | 2AI133EL01600-08005 | Not Started | Completed | EOF:Installation of UPS | 2017-11-16 | 2017-11-25 | 2018-03-25 | 2018-04-04
Act | 2AI133EL01600-08015 | Not Started | Completed | EOF:Installation of Isolator Switch | 2017-09-28 | 2017-10-07 | 2018-05-13 | 2018-05-16
Act | 2AI133EL01600-08020 | Not Started | Completed | EOF:Installation of Batteries | 2017-10-04 | 2017-10-16 | 2018-05-14 | 2018-05-17
Act | 2AI133EL01600-08010 | Not Started | Completed | EOF:Installation of battery Charger | 2017-09-25 | 2017-10-03 | 2018-05-12 | 2018-05-15
Act | 2AI133EL01600-08000 | Not Started | Completed | EOF SS 50-SUBST-001 : Install UPS with Battery bank and Isolator Switch | 2017-09-17 | 2017-11-25 | 2018-03-23 | 2019-04-10
Act | 2AI133EL01600 | Not Started | Completed | EOF SS 50-SUBST-001 : Install UPS with Battery bank and Isolator Switch | 2017-09-17 | 2017-11-25 | 2018-03-23 | 2019-04-10
5 |  |  |  | EOF SS 50-SUBST-001 : Install E-SCADA
Act | 2AI133EL01700-08000 | Not Started | Completed | EOF SS 52-SUBST-302 : Install E-SCADA | 2017-08-28 | 2017-09-14 | 2018-03-28 | 2018-04-06
Act | 2AI133EL01700 | Not Started | Completed | EOF SS 52-SUBST-302 : Install E-SCADA | 2017-08-28 | 2017-09-14 | 2018-03-28 | 2018-04-06
4 |  |  |  | INSTRUMENTATION
5 |  |  |  | EOF SS 50-SUBST-001 : Install - IRP Cabinets
Act | 2AI133IC01100-08000 | Not Started | Completed | EOF SS 52-SUBST-302 : Install - IRP Cabinets | 2017-10-17 | 2017-10-29 | 2018-04-28 | 2018-05-15
Act | 2AI133IC01100 | Not Started | Completed | EOF SS 50-SUBST-001 : Install - IRP Cabinets | 2017-10-17 | 2017-10-29 | 2018-04-28 | 2018-05-15
5 |  |  |  | EOF SS 50-SUBST-001 : Install - ICSS related equipments
Act | 2AI133IC01200-08000 | Not Started | Completed | EOF SS 52-SUBST-302 : Install - ICSS related equipments | 2017-10-17 | 2017-10-29 | 2019-04-08 | 2019-04-10
Act | 2AI133IC01200 | Not Started | Completed | EOF SS 50-SUBST-001 : Install - ICSS related equipments | 2017-10-17 | 2017-10-29 | 2019-04-08 | 2019-04-10
5 |  |  |  | EOF SS 50-SUBST-001 : Cable laying, glanding, termination & continuity check
Act | 2AI133IC01000-08006 | Not Started | Completed | EOF:Cable laying | 2017-08-24 | 2017-10-10 | 2018-05-14 | 2018-05-18
Act | 2AI133IC01000-08010 | Not Started | Completed | EOF:Glanding & termination | 2017-10-29 | 2017-11-15 | 2018-05-05 | 2018-10-19
Act | 2AI133IC01000-08015 | Not Started | Completed | EOF:Continuity check | 2017-11-09 | 2017-11-18 | 2018-10-13 | 2018-10-20
Act | 2AI133IC01000-08001 | Not Started | Completed | EOF:Cable Tray Installation | 2017-06-25 | 2017-07-18 | 2018-05-12 | 2018-05-15
Act | 2AI133IC01000-08000 | Not Started | Completed | EOF SS 50-SUBST-001 : Cable laying, glanding, termination & continuity check | 2017-06-25 | 2017-11-18 | 2018-05-05 | 2018-10-20
Act | 2AI133IC01000 | Not Started | Completed | EOF SS 50-SUBST-001 : Cable laying, glanding, termination & continuity check | 2017-06-25 | 2017-11-18 | 2018-05-05 | 2018-10-20
Act | 2AI133IC01000-08005 | Not Started | Completed | EOF SS 50-SUBST-001 : Cable laying, glanding, termination & continuity check | 2017-06-25 | 2017-11-18 | 2018-05-05 | 2018-10-20
5 |  |  |  | EOF SS 50-SUBST-001 : Install - Fire Alarm & Testing
4 |  |  |  | TELECOM
5 |  |  |  | EOF SS 50-SUBST-001 : FO & Telephone Cabling, Telecom system install, Cable Terminations
Act | 2AI133TE01000 | Not Started | Completed | COCC: SS 50-SUBST-001 : FO & Telephone Cabling, Telecom System install, Cable Terminations & continuity checks | 2017-07-17 | 2017-12-18 | 2018-01-01 | 2019-04-10
6 |  |  |  | 621-SUBST-0301 : FO & Telephone Cabling Works
Act | 2AI133TE01000-08011 | Not Started | Completed | Cable Dressing & Fastening | 2017-11-04 | 2017-11-27 | 2019-04-08 | 2019-04-10
Act | 2AI133TE01000-08006 | Not Started | Completed | Cable Pulling | 2017-10-23 | 2017-11-15 | 2019-04-08 | 2019-04-10
Act | 2AI133TE01000-08001 | Not Started | Completed | Cable Drum Checks & Transport to Site | 2017-10-17 | 2017-11-04 | 2019-04-08 | 2019-04-10
Act | 2AI133TE01000-08000 | Not Started | Completed | 621-SUBST-0301 : FO & Telephone Cabling Works | 2017-10-17 | 2017-12-14 | 2019-04-08 | 2019-04-10
Act | 2AI133TE01000-08021 | Not Started | Completed | Cable Marking | 2017-11-27 | 2017-12-14 | 2019-04-08 | 2019-04-10
6 |  |  |  | 621-SUBST-0301 : Telephone System Installation
Act | 2AI133TE01000-08015 | Not Started | Completed | COCC: Installation - Telecom System | 2017-07-17 | 2017-08-03 | 2018-01-01 | 2018-01-03
Act | 2AI133TE01000-08005 | Not Started | Completed | 621-SUBST-0301 : Telephone System Installation | 2017-07-17 | 2017-08-03 | 2018-01-01 | 2018-01-03
6 |  |  |  | 621-SUBST-0301 : Cable Terminations
Act | 2AI133TE01000-08025 | Not Started | Completed | COCC: Cable Terminations & continuity checks | 2017-12-06 | 2017-12-18 | 2019-04-08 | 2019-04-10
Act | 2AI133TE01000-08010 | Not Started | Completed | 621-SUBST-0301 : Cable Terminations | 2017-12-06 | 2017-12-18 | 2019-04-08 | 2019-04-10
3 |  |  |  | 52-SUBST-303 - SUBSTATION - LMM
4 |  |  |  | CIVIL / STRUCTURAL / ARCHITECTURAL
5 |  |  |  | EOF SS 52-SUBST-303 : Construct Foundation (Transformer) & Pit
6 |  |  |  | 621-SUBST-0303 : Foundation works for Transformer & Pit
Act | 2AI133CV07500-08000 | Not Started | Completed | EOF SS 52-SUBST-303 : Foundation works for Transformer & Pit | 2016-10-11 | 2016-12-25 | 2017-06-01 | 2017-08-28
Act | 2AI133CV07500 | Not Started | Completed | EOF SS 52-SUBST-303 : Construct Foundation (Transformer) & Pit | 2016-10-11 | 2016-12-25 | 2017-06-01 | 2017-08-28
Act | 2AI133CV07500-08005 | Not Started | Completed | EOF SS 52-SUBST-303 : Survey Marking, Excavation & Subgrade preparation | 2016-10-11 | 2016-10-17 | 2017-06-01 | 2017-06-07
Act | 2AI133CV07500-08010 | Not Started | Completed | EOF SS 52-SUBST-303 : Blinding/PCC | 2016-10-17 | 2016-10-18 | 2017-06-08 | 2017-06-08
Act | 2AI133CV07500-08015 | Not Started | Completed | EOF SS 52-SUBST-303 : Rebar & Formwork | 2016-10-20 | 2016-11-07 | 2017-06-10 | 2017-06-22
Act | 2AI133CV07500-08020 | Not Started | Completed | EOF SS 52-SUBST-303 : Concrete Pouring | 2016-11-02 | 2016-11-08 | 2017-06-12 | 2017-06-22
Act | 2AI133CV07500-08025 | Not Started | Completed | EOF SS 52-SUBST-303 : Concrete Protection | 2016-11-16 | 2016-11-22 | 2017-06-27 | 2017-07-17
Act | 2AI133CV07500-08030 | Not Started | Completed | EOF SS 52-SUBST-303 : Backfill / Compaction | 2016-11-26 | 2016-12-01 | 2017-07-25 | 2017-08-28
Act | 2AI133CV07500-08035 | Not Started | Completed | EOF SS 52-SUBST-303 : Construction of Pit | 2016-12-01 | 2016-12-25 | 2017-06-12 | 2017-06-22
4 |  |  |  | MECHANICAL
5 |  |  |  | EOF SS 52-SUBST-303 : Fire fighting works
4 |  |  |  | ELECTRICAL
5 |  |  |  | EOF SS 52-SUBST-303 : Install HV Switchboard with RCP, Power Factor & Bus Ducts
Act | 2AI133EL07300-08001 | Not Started | Completed | Foundation Checks/Preparation | 2017-08-28 | 2017-09-14 | 2017-12-04 | 2017-12-06
Act | 2AI133EL07300-08005 | Not Started | Completed | Installation on Foundation | 2017-09-05 | 2017-09-28 | 2017-12-04 | 2017-12-06
Act | 2AI133EL07300-08010 | Not Started | Completed | Preliminary Alignment & Grouting | 2017-09-28 | 2017-10-07 | 2017-12-04 | 2017-12-06
Act | 2AI133EL07300-08015 | Not Started | Completed | Final Alignment | 2017-10-07 | 2017-10-24 | 2018-02-05 | 2018-02-07
Act | 2AI133EL07300 | Not Started | Completed | EOF SS 52-SUBST-303 : Install HV Switchboard with RCP, Power Factor & Bus Ducts | 2017-08-28 | 2017-10-24 | 2017-12-04 | 2018-02-07
Act | 2AI133EL07300-08000 | Not Started | Completed | EOF SS 52-SUBST-303 : Install HV Switchboard with RCP, Power Factor & Bus Ducts | 2017-08-28 | 2017-10-24 | 2017-12-04 | 2018-02-07
5 |  |  |  | EOF SS 52-SUBST-303 : Earthing Lightning Protection Works
Act | 2AI133EL07200 | Not Started | Completed | EOF SS 52-SUBST-303 : Earthing Lightning Protection Works | 2017-07-30 | 2017-10-09 | 2018-01-14 | 2019-04-25
6 |  |  |  | EOF:Earthing Work
Act | 2AI133EL07200-08001 | Not Started | Completed | COCC: Earth rod Installation | 2017-07-30 | 2017-08-20 | 2018-01-14 | 2018-01-19
Act | 2AI133EL07200-08005 | Not Started | Completed | COCC: Earth Cable Laying | 2017-08-20 | 2017-09-24 | 2018-01-15 | 2018-05-23
Act | 2AI133EL07200-08010 | Not Started | Completed | COCC: Cad welding | 2017-08-22 | 2017-09-26 | 2018-01-16 | 2018-08-24
Act | 2AI133EL07200-08015 | Not Started | Completed | COCC: Earth Bus Installation | 2017-08-29 | 2017-09-27 | 2018-01-23 | 2018-11-29
Act | 2AI133EL07200-08020 | Not Started | Completed | COCC: Earth Boss Installation | 2017-08-30 | 2017-09-30 | 2019-04-08 | 2019-04-25
Act | 2AI133EL07200-08025 | Not Started | Completed | COCC: Earth cable Termination | 2017-09-18 | 2017-10-05 | 2018-03-05 | 2019-04-25
Act | 2AI133EL07200-08030 | Not Started | Completed | COCC: Earth Pit Installation | 2017-09-27 | 2017-10-09 | 2018-02-04 | 2019-04-25
Act | 2AI133EL07200-08000 | Not Started | Completed | EOF:Earthing Work | 2017-07-30 | 2017-10-09 | 2018-01-14 | 2019-04-25
6 |  |  |  | EOF:Lightining Protection
5 |  |  |  | EOF SS 52-SUBST-303 : Install LV Switchboards with MCC & Bus Ducts (incl. Lighting/small power)
Act | 2AI133EL07400-08001 | Not Started | Completed | EOF:Installation of Supports | 2017-08-16 | 2017-09-09 | 2017-12-02 | 2018-01-03
Act | 2AI133EL07400-08005 | Not Started | Completed | EOF:Installation of LV Switchgear, MCC | 2017-09-09 | 2017-10-31 | 2017-12-05 | 2018-12-12
Act | 2AI133EL07400-08010 | Not Started | Completed | EOF:Allignment of LV Switchgear, MCC | 2017-09-28 | 2017-11-08 | 2017-12-08 | 2018-12-12
Act | 2AI133EL07400-08015 | Not Started | Completed | EOF:Installation of Bus duct | 2017-11-08 | 2017-11-16 | 2018-01-01 | 2018-01-03
Act | 2AI133EL07400 | Not Started | Completed | EOF SS 52-SUBST-303 : Install LV Switchboards with RCP, MCC & Bus Ducts(incl. Lighting/small power) | 2017-08-16 | 2017-11-25 | 2017-12-02 | 2018-12-12
Act | 2AI133EL07400-08025 | Not Started | Completed | EOF:Allignment of Bus duct | 2017-11-16 | 2017-11-25 | 2018-01-01 | 2018-01-03
Act | 2AI133EL07400-08000 | Not Started | Completed | EOF SS 52-SUBST-303 : Install LV Switchboards with RCP, MCC & Bus Ducts(incl. Lighting/small power) | 2017-08-16 | 2017-11-25 | 2017-12-02 | 2018-12-12
5 |  |  |  | EOF SS 52-SUBST-303 : Install Transformers
Act | 2AI133EL07000-08001 | Not Started | Completed | EOF:Installation of Supports | 2017-05-27 | 2017-06-25 | 2017-10-02 | 2017-10-12
Act | 2AI133EL07000-08005 | Not Started | Completed | EOF:Installation of Transformer | 2017-06-25 | 2017-07-24 | 2017-10-12 | 2017-10-12
Act | 2AI133EL07000-08010 | Not Started | Completed | EOF:Allignment | 2017-07-17 | 2017-07-27 | 2017-10-12 | 2017-10-12
Act | 2AI133EL07000 | Not Started | Completed | EOF SS 52-SUBST-303 : Install Transformers | 2017-05-27 | 2017-07-27 | 2017-10-02 | 2017-10-12
Act | 2AI133EL07000-08000 | Not Started | Completed | EOF SS 52-SUBST-303 : Install Transformers | 2017-05-27 | 2017-07-27 | 2017-10-02 | 2017-10-12
5 |  |  |  | EOF SS 52-SUBST-303 : Install UPS with Battery bank and Isolator Switch
Act | 2AI133EL07600-08001 | Not Started | Completed | EOF:Installation of Supports | 2017-09-17 | 2017-10-10 | 2018-01-20 | 2018-01-24
Act | 2AI133EL07600-08005 | Not Started | Completed | EOF:Installation of UPS | 2017-11-16 | 2017-12-04 | 2018-01-23 | 2019-04-10
Act | 2AI133EL07600-08010 | Not Started | Completed | EOF:Installation of Isolator Switch | 2017-10-02 | 2017-10-16 | 2019-04-08 | 2019-04-10
Act | 2AI133EL07600-08015 | Not Started | Completed | EOF:Installation of Batteries | 2017-10-10 | 2017-10-28 | 2018-01-23 | 2019-04-10
Act | 2AI133EL07600 | Not Started | Completed | EOF SS 52-SUBST-303 : Install UPS with Battery bank and Isolator Switch | 2017-09-17 | 2017-12-04 | 2018-01-20 | 2019-04-10
Act | 2AI133EL07600-08000 | Not Started | Completed | EOF SS 52-SUBST-303 : Install UPS with Battery bank and Isolator Switch | 2017-09-17 | 2017-12-04 | 2018-01-20 | 2019-04-10
5 |  |  |  | EOF SS 52-SUBST-303 : Install E-SCADA
Act | 2AI133EL07700-08000 | Not Started | Completed | EOF:Installation of E-SCADA Cabinet/Panel/Cabling | 2017-09-11 | 2017-10-22 | 2018-04-24 | 2018-04-27
Act | 2AI133EL07700 | Not Started | Completed | EOF SS 52-SUBST-303 : Install E-SCADA | 2017-09-11 | 2017-10-22 | 2018-04-24 | 2018-04-27
5 |  |  |  | EOF SS 52-SUBST-303 : Cable laying, glanding, termination & continuity check
Act | 2AI133EL07100 | Not Started | Completed | EOF SS 52-SUBST-303 : Cable laying, glanding, termination & continuity check | 2017-06-07 | 2017-09-27 | 2018-01-01 | 2019-04-10
6 |  |  |  | 621-SUBST-0303 : Cable laying .
Act | 2AI133EL07100-08001 | Not Started | Completed | EOF:Fabricate Tray Supports | 2017-06-07 | 2017-06-21 | 2018-01-01 | 2018-01-03
Act | 2AI133EL07100-08006 | Not Started | Completed | EOF: Install cable trays | 2017-06-19 | 2017-07-18 | 2018-01-01 | 2018-01-03
Act | 2AI133EL07100-08111 | Not Started | Completed | EOF: Installcable trays covers | 2017-09-13 | 2017-09-27 | 2018-01-22 | 2018-01-22
Act | 2AI133EL07100-08003 | Not Started | Completed | EOF: Install Tray support and Hangers | 2017-06-12 | 2017-06-26 | 2018-01-01 | 2018-01-03
Act | 2AI133EL07100-08000 | Not Started | Completed | 621-SUBST-0303 : Cable laying | 2017-06-07 | 2017-09-27 | 2018-01-01 | 2019-03-08
Act | 2AI133EL07100-08089 | Not Started | Completed | EOF: Cable Laying - LV | 2017-07-18 | 2017-09-03 | 2018-01-01 | 2019-03-08
Act | 2AI133EL07100-08109 | Not Started | Completed | EOF: Cable Laying - HV | 2017-06-21 | 2017-07-26 | 2018-01-22 | 2018-01-22
6 |  |  |  | 621-SUBST-0303 : Cable glanding, termination & continuity check
Act | 2AI133EL07100-08005 | Not Started | Completed | 621-SUBST-0303 : Cable glanding, termination & continuity check | 2017-07-26 | 2017-09-13 | 2018-01-01 | 2019-04-10
7 |  |  |  | COCC: Cable laying, glanding & termination for LV
Act | 2AI133EL07100-08090 | Not Started | Completed | EOF: Cable Glanding for LV cables | 2017-08-07 | 2017-09-09 | 2018-01-01 | 2019-04-10
Act | 2AI133EL07100-08095 | Not Started | Completed | EOF: Continuity Checks & Terminations for LV cables | 2017-08-24 | 2017-09-11 | 2018-01-01 | 2019-04-10
Act | 2AI133EL07100-08100 | Not Started | Completed | EOF: Tagging for LV cables | 2017-09-07 | 2017-09-13 | 2018-01-01 | 2019-04-10
7 |  |  |  | COCC: Cable laying, glanding & termination for HV
Act | 2AI133EL07100-08110 | Not Started | Completed | EOF: Cable Glanding for HV cables | 2017-07-26 | 2017-08-19 | 2019-04-08 | 2019-04-10
Act | 2AI133EL07100-08115 | Not Started | Completed | EOF: Continuity Checks & Terminations for HV cables | 2017-08-19 | 2017-09-02 | 2019-04-08 | 2019-04-10
Act | 2AI133EL07100-08120 | Not Started | Completed | EOF: Tagging for HV cables | 2017-09-02 | 2017-09-06 | 2019-04-08 | 2019-04-10
5 |  |  |  | EOF SS 52-SUBST-303 : Install Distribution boards and Annunciator Panels
Act | 2AI133EL07500-08001 | Not Started | Completed | EOF:Installation of Supports | 2017-06-17 | 2017-07-22 | 2018-01-16 | 2019-04-10
Act | 2AI133EL07500-08005 | Not Started | Completed | EOF:Installation of Distribution Board | 2017-07-10 | 2017-08-02 | 2018-01-17 | 2019-04-10
Act | 2AI133EL07500-08010 | Not Started | Completed | EOF:Installation of Annunciator Panels | 2017-10-17 | 2017-11-09 | 2018-01-01 | 2018-01-03
Act | 2AI133EL07500-08015 | Not Started | Completed | EOF:Allignment of Distribution Board | 2017-07-24 | 2017-08-05 | 2018-01-17 | 2019-04-10
Act | 2AI133EL07500 | Not Started | Completed | EOF SS 52-SUBST-303 : Install Distribution boards and Annunciator Panels | 2017-06-17 | 2017-11-12 | 2018-01-01 | 2019-04-10
Act | 2AI133EL07500-08025 | Not Started | Completed | EOF:Allignment of Annunciator Panels | 2017-10-31 | 2017-11-12 | 2018-01-01 | 2018-01-03
Act | 2AI133EL07500-08000 | Not Started | Completed | EOF SS 52-SUBST-303 : Install Distribution boards and Annunciator Panels | 2017-06-17 | 2017-11-12 | 2018-01-01 | 2019-04-10
4 |  |  |  | INSTRUMENTATION
5 |  |  |  | EOF SS 52-SUBST-303 : Install - IRP Cabinets
Act | 2AI133IC07100-08000 | Not Started | Not Started | EOF SS 52-SUBST-303 : Install - IRP Cabinets | 2017-10-17 | 2017-10-29
Act | 2AI133IC07100 | Not Started | Not Started | EOF SS 52-SUBST-303 : Install - IRP Cabinets | 2017-10-17 | 2017-10-29
5 |  |  |  | EOF SS 52-SUBST-303 : Install - ICSS related equipments
Act | 2AI133IC07200-08000 | Not Started | Completed | EOF SS 52-SUBST-303 : Install - ICSS related equipments | 2017-10-17 | 2017-11-09 | 2018-09-08 | 2019-02-15
Act | 2AI133IC07200 | Not Started | Completed | EOF SS 52-SUBST-303 : Install - ICSS related equipments | 2017-10-17 | 2017-11-09 | 2018-09-08 | 2019-02-15
5 |  |  |  | EOF SS 52-SUBST-303 : Cable laying, glanding, termination & continuity check
Act | 2AI133IC07000-08010 | Not Started | Completed | EOF:Cable laying | 2017-08-05 | 2017-09-26 | 2018-04-02 | 2019-04-10
Act | 2AI133IC07000-08015 | Not Started | Completed | EOF:Glanding & termination | 2017-09-26 | 2017-10-19 | 2018-04-02 | 2019-04-10
Act | 2AI133IC07000-08020 | Not Started | Completed | EOF:Continuity check | 2017-10-19 | 2017-11-06 | 2018-04-02 | 2019-04-10
Act | 2AI133IC07000 | Not Started | Completed | EOF SS 52-SUBST-303 : Cable laying, glanding, termination & continuity check | 2017-06-21 | 2017-11-06 | 2018-04-02 | 2019-04-10
Act | 2AI133IC07000-08001 | Not Started | Completed | EOF: Install Tray support and Hangers | 2017-06-21 | 2017-07-15 | 2018-04-02 | 2018-04-04
Act | 2AI133IC07000-08006 | Not Started | Completed | EOF: Install cable trays | 2017-07-03 | 2017-08-05 | 2018-04-02 | 2018-04-04
Act | 2AI133IC07000-08000 | Not Started | Completed | 621-SUBST-0303 : Cable laying | 2017-06-21 | 2017-11-06 | 2018-04-02 | 2019-04-10
Act | 2AI133IC07000-08005 | Not Started | Completed | 621-SUBST-0303 : Cable glanding, termination & continuity check | 2017-06-21 | 2017-11-06 | 2018-04-02 | 2019-04-10
5 |  |  |  | EOF SS 52-SUBST-303 : Install - Fire Alarm & Testing
4 |  |  |  | TELECOM
5 |  |  |  | EOF SS 52-SUBST-303 : FO & Telephone Cabling, Telecom system install, Cable Terminations
Act | 2AI133TE07000 | Not Started | Completed | EOF SS 52-SUBST-303 : FO & Telephone Cabling, Telecom System install, Cable Terminations & continuity checks | 2017-07-17 | 2017-09-20 | 2018-01-01 | 2019-04-10
Act | 2AI133TE07000-08000 | Not Started | Completed | EOF:FO & Telephone Cable Laying | 2017-07-17 | 2017-09-02 | 2018-11-05 | 2019-04-10
Act | 2AI133TE07000-08005 | Not Started | Completed | EOF:Installation - Telecom System | 2017-08-10 | 2017-09-03 | 2018-01-01 | 2018-01-03
Act | 2AI133TE07000-08010 | Not Started | Completed | EOF:Cable Terminations & continuity checks | 2017-09-03 | 2017-09-20 | 2018-04-02 | 2018-04-04
3 |  |  |  | 52-R-301 - EMERGENCY GENERATOR BUILDING (FMM)
4 |  |  |  | CIVIL / STRUCTURAL / ARCHITECTURAL
5 |  |  |  | EOF EG Building 52-R-301 : Diesel Day Tank Foundation
Act | 2AI133CV21300 | Not Started | Completed | EOF EG Building 52-R-301 : Construct Diesel Day Tank Foundation | 2016-09-17 | 2016-11-06 | 2017-01-14 | 2017-04-05
Act | 2AI133CV21300-08006 | Not Started | Completed | Survey Marking, Excavation & Subgrade preparation | 2016-09-17 | 2016-09-20 | 2017-01-14 | 2017-01-15
Act | 2AI133CV21300-08015 | Not Started | Completed | Blinding/PCC | 2016-09-20 | 2016-09-25 | 2017-01-18 | 2017-01-18
Act | 2AI133CV21300-08025 | Not Started | Completed | Rebar & Formwork - for Footing | 2016-09-28 | 2016-10-05 | 2017-01-19 | 2017-01-21
Act | 2AI133CV21300-08035 | Not Started | Completed | Concrete Pouring - for Footing | 2016-10-05 | 2016-10-06 | 2017-02-16 | 2017-03-08
Act | 2AI133CV21300-08045 | Not Started | Completed | Concrete Protection | 2016-10-22 | 2016-10-27 | 2017-03-28 | 2017-03-30
Act | 2AI133CV21300-08055 | Not Started | Completed | Backfill / Compaction | 2016-10-31 | 2016-11-06 | 2017-04-01 | 2017-04-05
Act | 2AI133CV21300-08005 | Not Started | Completed | EOF EG Building 52-R-301 : Diesel Day Tank Foundation | 2016-09-17 | 2016-11-06 | 2017-01-14 | 2017-04-05
Act | 2AI133CV21300-08036 | Not Started | Completed | Rebar, Formwork & Install Embedments - for Pedestal | 2016-10-09 | 2016-10-13 | 2017-03-06 | 2017-03-08
Act | 2AI133CV21300-08037 | Not Started | Completed | Concrete Pouring - for Pedestal | 2016-10-13 | 2016-10-15 | 2017-03-08 | 2017-03-08
4 |  |  |  | MECHANICAL
5 |  |  |  | EOF EG Building 52-R-301 : Diesel Day Tank Installation
Act | 2AI133MS21000-08001 | Not Started | Completed | EOF:Installation of Equipment | 2017-07-29 | 2017-08-02 | 2017-12-28 | 2018-02-08
Act | 2AI133MS21000 | Not Started | Completed | EOF EG Building 52-R-301 : Diesel Day Tank Installation | 2017-07-29 | 2017-08-08 | 2017-12-28 | 2018-02-22
Act | 2AI133MS21000-08010 | Not Started | Completed | EOF:Preliminary Allignment & Grouting of Equipment | 2017-08-02 | 2017-08-06 | 2018-02-08 | 2018-02-08
Act | 2AI133MS21000-08020 | Not Started | Completed | EOF:Final Allignment & Grouting of Equipment | 2017-08-06 | 2017-08-08 | 2018-02-10 | 2018-02-22
Act | 2AI133MS21000-08000 | Not Started | Completed | EOF EG Building 52-R-301 : Diesel Day Tank Installation | 2017-07-29 | 2017-08-08 | 2017-12-28 | 2018-02-22
4 |  |  |  | ELECTRICAL
5 |  |  |  | EOF EG Building 52-R-301 : Install Emergency Generator
Act | 2AI133EL21000-08001 | Not Started | Completed | EOF:Installation of Generators | 2017-07-29 | 2017-08-09 | 2018-06-23 | 2018-06-27
Act | 2AI133EL21000-08005 | Not Started | Completed | EOF:Allignment | 2017-08-09 | 2017-08-21 | 2018-06-25 | 2018-06-28
Act | 2AI133EL21000 | Not Started | Completed | EOF EG Building 52-R-301 : Install Emergency Generator | 2017-07-29 | 2017-08-21 | 2018-06-23 | 2018-06-28
Act | 2AI133EL21000-08000 | Not Started | Completed | EOF EG Building 52-R-301 : Install Emergency Generator | 2017-07-29 | 2017-08-21 | 2018-06-23 | 2018-06-28
5 |  |  |  | EOF EG Building 52-R-301 : Cable laying, glanding, termination & continuity check
Act | 2AI133EL21200 | Not Started | Completed | EOF EG Building 52-R-301 : Cable laying, glanding, termination & continuity check | 2017-07-31 | 2017-09-14 | 2018-04-02 | 2019-04-10
6 |  |  |  | EOF EG Building 52-R-301 : Cable laying
Act | 2AI133EL21200-08001 | Not Started | Completed | EOF:Fabricate Tray Supports | 2017-07-31 | 2017-08-08 | 2018-04-02 | 2018-04-04
Act | 2AI133EL21200-08010 | Not Started | Completed | EOF: Install cable trays | 2017-08-05 | 2017-08-21 | 2018-07-05 | 2018-07-13
Act | 2AI133EL21200-08015 | Not Started | Completed | EOF: Installcable trays covers | 2017-08-29 | 2017-09-05 | 2018-07-05 | 2018-07-14
Act | 2AI133EL21200-08014 | Not Started | Completed | EOF: Cable Laying | 2017-08-21 | 2017-09-02 | 2018-07-02 | 2019-04-10
Act | 2AI133EL21200-08006 | Not Started | Completed | EOF: Install Tray support and Hangers | 2017-08-02 | 2017-08-10 | 2018-04-02 | 2018-04-04
Act | 2AI133EL21200-08000 | Not Started | Completed | EOF EG Building 52-R-301 : Cable laying | 2017-07-31 | 2017-09-05 | 2018-04-02 | 2019-04-10
6 |  |  |  | EOF EG Building 52-R-301 : Cableglanding, termination & continuity check
Act | 2AI133EL21200-08020 | Not Started | Completed | EOF: Cable Glanding | 2017-08-23 | 2017-09-04 | 2018-07-06 | 2018-11-28
Act | 2AI133EL21200-08025 | Not Started | Completed | EOF: Continuity Checks & Terminations | 2017-09-04 | 2017-09-12 | 2018-07-07 | 2018-11-29
Act | 2AI133EL21200-08030 | Not Started | Completed | EOF: Tagging | 2017-09-09 | 2017-09-14 | 2018-07-08 | 2018-11-30
Act | 2AI133EL21200-08005 | Not Started | Completed | EOF EG Building 52-R-301 : Cable glanding, termination & continuity check | 2017-08-23 | 2017-09-14 | 2018-07-06 | 2018-11-30
5 |  |  |  | EOF EG Building 52-R-301 : Install Distribution boards, Lighting & small power
Act | 2AI133EL21100-08001 | Not Started | Completed | EOF:Installation of Supports | 2017-07-29 | 2017-07-31 | 2019-04-08 | 2019-04-10
Act | 2AI133EL21100-08005 | Not Started | Completed | EOF:Installation of Distribution Board | 2017-07-31 | 2017-08-02 | 2019-04-08 | 2019-04-10
Act | 2AI133EL21100-08010 | Not Started | Completed | EOF:Allignment | 2017-08-02 | 2017-08-03 | 2019-04-08 | 2019-04-10
Act | 2AI133EL21100 | Not Started | Completed | EOF EG Building 52-R-301 : Install Distribution boards, Lighting & small power | 2017-07-29 | 2017-08-03 | 2019-04-08 | 2019-04-10
Act | 2AI133EL21100-08000 | Not Started | Completed | EOF EG Building 52-R-301 : Install Distribution boards | 2017-07-29 | 2017-08-03 | 2019-04-08 | 2019-04-10
5 |  |  |  | EOF EG Building 52-R-301 : Install of Generator Control Panel
4 |  |  |  | INSTRUMENTATION
5 |  |  |  | EOF EG Building 52-R-301 : Instrument Cable laying, glanding, termination & continuity checks
Act | 2AI133IC21000-08001 | Not Started | Completed | EOF:Cable laying | 2017-08-24 | 2017-08-30 | 2018-09-29 | 2018-09-30
Act | 2AI133IC21000-08006 | Not Started | Completed | EOF:Glanding & termination | 2017-08-30 | 2017-09-05 | 2019-04-08 | 2019-04-10
Act | 2AI133IC21000-08010 | Not Started | Completed | EOF:Continuity check | 2017-09-05 | 2017-09-07 | 2019-04-08 | 2019-04-10
Act | 2AI133IC21000 | Not Started | Completed | EOF EG Building 52-R-301 : Instrument Cable laying, glanding, termination & continuity checks | 2017-08-24 | 2017-09-07 | 2018-09-29 | 2019-04-10
Act | 2AI133IC21000-08000 | Not Started | Completed | EOF EG Building 52-R-301 : Instrument Cable laying | 2017-08-24 | 2017-09-07 | 2018-09-29 | 2019-04-10
Act | 2AI133IC21000-08005 | Not Started | Completed | EOF EG Building 52-R-301 : Instrument Cable glanding, termination & continuity checks | 2017-08-24 | 2017-09-07 | 2018-09-29 | 2019-04-10
5 |  |  |  | EOF EG Building 52-R-301 : F&G Devices & Instrument Installation
4 |  |  |  | TELECOM
5 |  |  |  | EOF EG Building 52-R-301 : FO & Telephone Cabling, Telecom system install, Cable Terminations
Act | 2AI133TE21000-08000 | Not Started | Completed | EOF:FO & Telephone Cable Laying | 2017-07-29 | 2017-08-01 | 2018-04-22 | 2018-04-24
Act | 2AI133TE21000-08005 | Not Started | Completed | EOF EG Building 52-R-301 : Telecom system install, Cable Terminations & continuity checks | 2017-08-01 | 2017-08-03 | 2018-01-03 | 2018-01-03
Act | 2AI133TE21000 | Not Started | Completed | EOF EG Building 52-R-301 : FO & Telephone Cabling, Telecom System install, Cable Terminations & continuity checks | 2017-07-29 | 2017-08-03 | 2018-01-03 | 2018-04-24
3 |  |  |  | 52-R-302 - EMERGENCY GENERATOR BUILDING (STF)
4 |  |  |  | CIVIL / STRUCTURAL / ARCHITECTURAL
5 |  |  |  | EOF EG Building 52-R-302 : Diesel Day Tank Foundation
Act | 2AI133CV31300 | Not Started | Completed | EOF EG Building 52-R-302 : Diesel Day Tank Foundation | 2016-09-28 | 2016-11-05 | 2017-10-12 | 2018-01-22
Act | 2AI133CV31300-08006 | Not Started | Completed | Survey Marking, Excavation & Subgrade preparation | 2016-09-28 | 2016-10-02 | 2017-10-12 | 2017-10-21
Act | 2AI133CV31300-08015 | Not Started | Completed | Blinding/PCC | 2016-10-02 | 2016-10-06 | 2017-10-22 | 2017-10-22
Act | 2AI133CV31300-08020 | Not Started | Completed | Rebar & Formwork | 2016-10-10 | 2016-10-17 | 2017-10-28 | 2017-10-28
Act | 2AI133CV31300-08025 | Not Started | Completed | Concrete Pouring | 2016-10-17 | 2016-10-18 | 2017-10-30 | 2017-10-30
Act | 2AI133CV31300-08030 | Not Started | Completed | Concrete Protection | 2016-10-22 | 2016-10-26 | 2017-11-17 | 2018-01-20
Act | 2AI133CV31300-08035 | Not Started | Completed | Backfill / Compaction | 2016-10-30 | 2016-11-05 | 2018-01-22 | 2018-01-22
Act | 2AI133CV31300-08005 | Not Started | Completed | EOF EG Building 52-R-302 : Diesel Day Tank Foundation | 2016-09-28 | 2016-11-05 | 2017-10-12 | 2018-01-22
4 |  |  |  | MECHANICAL
5 |  |  |  | EOF EG Building 52-R-302 : Diesel Day Tank Installation
Act | 2AI133MS31000-08001 | Not Started | Completed | EOF:Installation of Diesel Day Tank Installation | 2017-09-17 | 2017-09-21 | 2018-01-31 | 2018-01-31
Act | 2AI133MS31000-08005 | Not Started | Completed | EOF:Preliminary Allignment & Grouting of Equipment | 2017-09-21 | 2017-09-26 | 2018-09-03 | 2018-09-03
Act | 2AI133MS31000-08010 | Not Started | Completed | EOF:Final Allignment & Grouting of Equipment | 2017-09-26 | 2017-10-01 | 2019-03-04 | 2019-03-05
Act | 2AI133MS31000 | Not Started | Completed | EOF EG Building 52-R-302 : Diesel Day Tank Installation | 2017-09-17 | 2017-10-01 | 2018-01-31 | 2019-03-05
Act | 2AI133MS31000-08000 | Not Started | Completed | EOF EG Building 52-R-302 : Diesel Day Tank Installation | 2017-09-17 | 2017-10-01 | 2018-01-31 | 2019-03-05
4 |  |  |  | ELECTRICAL
5 |  |  |  | EOF EG Building 52-R-302 : Install Emergency Generator
Act | 2AI133EL31000 | Not Started | Completed | EOF EG Building 52-R-302 : Install Emergency Generator | 2017-08-29 | 2017-09-21 | 2018-07-06 | 2018-07-15
Act | 2AI133EL31000-08001 | Not Started | Completed | EOF:Installation of Generators | 2017-08-29 | 2017-09-10 | 2018-07-06 | 2018-07-13
Act | 2AI133EL31000-08005 | Not Started | Completed | EOF:Allignment | 2017-09-10 | 2017-09-21 | 2018-07-09 | 2018-07-15
Act | 2AI133EL31000-08000 | Not Started | Completed | EOF:Installation of Generators | 2017-08-29 | 2017-09-21 | 2018-07-06 | 2018-07-15
5 |  |  |  | EOF EG Building 52-R-302 : Cable laying, glanding, termination & continuity check
Act | 2AI133EL31200 | Not Started | Completed | EOF EG Building 52-R-302 : Cable laying, glanding, termination & continuity check | 2017-08-31 | 2017-10-02 | 2018-04-24 | 2019-04-10
6 |  |  |  | EOF EG Building 52-R-302 :Cable laying
Act | 2AI133EL31200-08001 | Not Started | Completed | Cable Drum Checks & Transport to Site | 2017-08-31 | 2017-09-06 | 2018-04-24 | 2018-07-04
Act | 2AI133EL31200-08006 | Not Started | Completed | Cable Dressing & Fastening | 2017-09-06 | 2017-09-14 | 2018-04-25 | 2018-07-04
Act | 2AI133EL31200-08009 | Not Started | Completed | Cable Marking | 2017-09-14 | 2017-09-23 | 2018-04-26 | 2018-07-04
Act | 2AI133EL31200-08004 | Not Started | Completed | Cable Pulling | 2017-09-02 | 2017-09-13 | 2018-04-24 | 2018-07-04
Act | 2AI133EL31200-08000 | Not Started | Completed | EOF EG Building 52-R-302 :Cable laying | 2017-08-31 | 2017-09-23 | 2018-04-24 | 2018-07-04
6 |  |  |  | EOF EG Building 52-R-302 : Cableglanding, termination & continuity check
Act | 2AI133EL31200-08015 | Not Started | Completed | EOF: Cable Glanding | 2017-09-13 | 2017-09-25 | 2018-10-08 | 2018-10-10
Act | 2AI133EL31200-08020 | Not Started | Completed | EOF: Continuity Checks & Terminations | 2017-09-21 | 2017-09-30 | 2018-10-08 | 2019-03-06
Act | 2AI133EL31200-08025 | Not Started | Completed | EOF: Tagging | 2017-09-26 | 2017-10-02 | 2018-10-08 | 2019-04-10
Act | 2AI133EL31200-08005 | Not Started | Completed | EOF EG Building 52-R-302 : Cableglanding, termination & continuity check | 2017-09-13 | 2017-10-02 | 2018-10-08 | 2019-04-10
5 |  |  |  | EOF EG Building 52-R-302 : Install Distribution boards, Lighting & small power
Act | 2AI133EL31100 | Not Started | Completed | EOF EG Building 52-R-302 : Install Distribution boards, Lighting & small power | 2017-08-29 | 2017-09-04 | 2018-09-22 | 2018-09-28
Act | 2AI133EL31100-08001 | Not Started | Completed | EOF:Installation of Supports | 2017-08-29 | 2017-08-31 | 2018-09-22 | 2018-09-27
Act | 2AI133EL31100-08005 | Not Started | Completed | EOF:Installation of Distribution Board | 2017-08-31 | 2017-09-03 | 2018-09-23 | 2018-09-28
Act | 2AI133EL31100-08010 | Not Started | Completed | EOF:Allignment | 2017-09-03 | 2017-09-04 | 2018-09-24 | 2018-09-28
Act | 2AI133EL31100-08000 | Not Started | Completed | EOF EG Building 52-R-302 : Install Distribution boards, Lighting & small power | 2017-08-29 | 2017-09-04 | 2018-09-22 | 2018-09-28
4 |  |  |  | INSTRUMENTATION
5 |  |  |  | EOF EG Building 52-R-302 : Instrument Cable laying, glanding, termination & continuity checks
Act | 2AI133IC31000 | Not Started | In Progress | EOF EG Building 52-R-302 : Instrument Cable laying, glanding, termination & continuity checks | 2017-09-14 | 2017-09-28 | 2018-11-05
Act | 2AI133IC31000-08001 | Not Started | Completed | EOF:Cable laying | 2017-09-14 | 2017-09-20 | 2018-11-05 | 2018-11-22
Act | 2AI133IC31000-08006 | Not Started | In Progress | EOF:Glanding & termination | 2017-09-20 | 2017-09-26 | 2018-11-07
Act | 2AI133IC31000-08010 | Not Started | In Progress | EOF:Continuity check | 2017-09-26 | 2017-09-28 | 2018-11-07
Act | 2AI133IC31000-08000 | Not Started | In Progress | EOF EG Building 52-R-302 : Instrument Cable laying | 2017-09-14 | 2017-09-28 | 2018-11-05
Act | 2AI133IC31000-08005 | Not Started | In Progress | EOF EG Building 52-R-302 : Instrument Cable glanding, termination & continuity checks | 2017-09-14 | 2017-09-28 | 2018-11-05
5 |  |  |  | EOF EG Building 52-R-302 : F&G Devices & Instrument Installation
4 |  |  |  | TELECOM
5 |  |  |  | EOF EG Building 52-R-302 : FO & Telephone Cabling, Telecom system install, Cable Terminations
Act | 2AI133TE31000 | Not Started | Completed | EOF EG Building 52-R-302 : FO & Telephone Cabling, Telecom System install, Cable Terminations & continuity checks | 2017-08-29 | 2017-09-04 | 2018-01-01 | 2019-04-10
Act | 2AI133TE31000-08000 | Not Started | Completed | EOF:FO & Telephone Cable Laying | 2017-08-29 | 2017-09-02 | 2019-04-08 | 2019-04-10
Act | 2AI133TE31000-08005 | Not Started | Completed | EOF:Installation - Telecom System | 2017-09-02 | 2017-09-04 | 2018-01-01 | 2018-01-03
Act | 2AI133TE31000-08010 | Not Started | Completed | EOF:Cable Terminations & continuity checks | 2017-09-02 | 2017-09-03 | 2019-04-08 | 2019-04-10
3 |  |  |  | 50-R-002 - EMERGENCY GENERATOR BUILDING (COCC)
4 |  |  |  | CIVIL / STRUCTURAL / ARCHITECTURAL
5 |  |  |  | EOF EG Building 50-R-002 : Diesel Day Tank Foundation
Act | 2AI133CV11300 | Not Started | Completed | EOF EG Building 50-R-002 : Diesel Day Tank Foundation | 2016-08-24 | 2016-10-15 | 2017-12-23 | 2018-01-26
Act | 2AI133CV11300-08006 | Not Started | Completed | Survey Marking, Excavation & Subgrade preparation | 2016-08-24 | 2016-08-28 | 2017-12-23 | 2017-12-23
Act | 2AI133CV11300-08010 | Not Started | Completed | Blinding/PCC | 2016-08-28 | 2016-09-01 | 2017-12-23 | 2017-12-23
Act | 2AI133CV11300-08020 | Not Started | Completed | Rebar & Formwork - for Footing | 2016-09-05 | 2016-09-12 | 2017-12-25 | 2018-01-01
Act | 2AI133CV11300-08030 | Not Started | Completed | Concrete Pouring - for Footing | 2016-09-12 | 2016-09-13 | 2018-01-02 | 2018-01-02
Act | 2AI133CV11300-08040 | Not Started | Completed | Concrete Protection | 2016-10-01 | 2016-10-05 | 2018-01-18 | 2018-01-23
Act | 2AI133CV11300-08050 | Not Started | Completed | Backfill / Compaction | 2016-10-09 | 2016-10-15 | 2018-01-24 | 2018-01-26
Act | 2AI133CV11300-08005 | Not Started | Completed | EOF EG Building 50-R-002 : Diesel Day Tank Foundation | 2016-08-24 | 2016-10-15 | 2017-12-23 | 2018-01-26
Act | 2AI133CV11300-08031 | Not Started | Completed | Rebar, Formwork & Install Embedments - for Pedestal | 2016-09-14 | 2016-09-22 | 2018-01-06 | 2018-01-10
Act | 2AI133CV11300-08032 | Not Started | Completed | Concrete Pouring - for Pedestal | 2016-09-22 | 2016-09-24 | 2018-01-11 | 2018-01-11
4 |  |  |  | MECHANICAL
5 |  |  |  | EOF EG Building 50-R-002 : Diesel Day Tank Installation
Act | 2AI133MS11000-08001 | Not Started | Completed | EOF:Installation of Equipment | 2017-07-22 | 2017-07-26 | 2018-06-17 | 2018-06-22
Act | 2AI133MS11000-08005 | Not Started | Completed | EOF:Preliminary Allignment & Grouting of Equipment | 2017-07-26 | 2017-07-31 | 2018-06-23 | 2018-06-24
Act | 2AI133MS11000-08010 | Not Started | Completed | EOF:Final Allignment & Grouting of Equipment | 2017-07-31 | 2017-08-05 | 2018-12-03 | 2018-12-05
Act | 2AI133MS11000 | Not Started | Completed | EOF EG Building 50-R-002 : Diesel Day Tank Installation | 2017-07-22 | 2017-08-05 | 2018-06-17 | 2018-12-05
Act | 2AI133MS11000-08000 | Not Started | Completed | EOF EG Building 50-R-002 : Diesel Day Tank Foundation | 2017-07-22 | 2017-08-05 | 2018-06-17 | 2018-12-05
4 |  |  |  | ELECTRICAL
5 |  |  |  | EOF EG Building 50-R-002 : Install Emergency Generator
Act | 2AI133EL11000 | Not Started | Completed | EOF EG Building 50-R-002 : Install Emergency Generator | 2017-07-29 | 2017-08-21 | 2018-08-04 | 2018-08-13
Act | 2AI133EL11000-08001 | Not Started | Completed | EOF:Installation of Generators | 2017-07-29 | 2017-08-09 | 2018-08-04 | 2018-08-09
Act | 2AI133EL11000-08005 | Not Started | Completed | EOF:Allignment | 2017-08-09 | 2017-08-21 | 2018-08-10 | 2018-08-13
Act | 2AI133EL11000-08000 | Not Started | Completed | EOF EG Building 50-R-002 : Install Emergency Generator | 2017-07-29 | 2017-08-21 | 2018-08-04 | 2018-08-13
5 |  |  |  | EOF EG Building 50-R-002 : Cable laying, glanding, termination & continuity check
Act | 2AI133EL11100 | Not Started | Completed | EOF EG Building 50-R-002 : Cable laying, glanding, termination & continuity check | 2017-07-30 | 2017-08-31 | 2018-09-29 | 2019-04-10
6 |  |  |  | COCC: Cable Tray Installation
Act | 2AI133EL11100-08006 | Not Started | Completed | EOF:Fabricate Tray Supports | 2017-07-31 | 2017-08-01 | 2018-09-29 | 2018-10-10
Act | 2AI133EL11100-08010 | Not Started | Completed | EOF: Install cable trays | 2017-07-30 | 2017-08-07 | 2018-09-30 | 2018-10-02
Act | 2AI133EL11100-08015 | Not Started | Completed | EOF: Installcable trays covers | 2017-08-19 | 2017-08-22 | 2019-04-08 | 2019-04-10
Act | 2AI133EL11100-08014 | Not Started | Completed | EOF: Cable Laying - LV | 2017-08-07 | 2017-08-19 | 2018-09-30 | 2018-10-02
Act | 2AI133EL11100-08000 | Not Started | Completed | EOF EG Building 50-R-002 : Cable laying | 2017-07-30 | 2017-08-22 | 2018-09-29 | 2019-04-10
6 |  |  |  | COCC: Cable laying, glanding & termination for LV
Act | 2AI133EL11100-08020 | Not Started | Completed | EOF: Cable Glanding for LV cables | 2017-08-09 | 2017-08-21 | 2018-09-29 | 2019-03-14
Act | 2AI133EL11100-08025 | Not Started | Completed | EOF: Continuity Checks & Terminations for LV cables | 2017-08-21 | 2017-08-29 | 2018-09-30 | 2019-03-15
Act | 2AI133EL11100-08030 | Not Started | Completed | EOF: Tagging for LV cables | 2017-08-26 | 2017-08-31 | 2018-09-29 | 2019-03-16
Act | 2AI133EL11100-08005 | Not Started | Completed | EOF EG Building 50-R-002 : Cable glanding, termination & continuity check | 2017-08-09 | 2017-08-31 | 2018-09-29 | 2019-03-16
6 |  |  |  | COCC: Cable laying, glanding & termination for Lighting
5 |  |  |  | EOF EG Building 50-R-002 : Install Distribution boards, Lighting & small power
Act | 2AI133EL11200 | Not Started | Completed | EOF EG Building 50-R-002 : Install Distribution boards, Lighting & small power | 2017-07-29 | 2017-08-03 | 2018-09-22 | 2018-09-30
Act | 2AI133EL11200-08001 | Not Started | Completed | EOF:Installation of Supports | 2017-07-29 | 2017-07-31 | 2018-09-22 | 2018-09-27
Act | 2AI133EL11200-08005 | Not Started | Completed | EOF:Installation of Distribution Board | 2017-07-31 | 2017-08-02 | 2018-09-23 | 2018-09-28
Act | 2AI133EL11200-08010 | Not Started | Completed | EOF:Allignment | 2017-08-02 | 2017-08-03 | 2018-09-26 | 2018-09-30
Act | 2AI133EL11200-08000 | Not Started | Completed | EOF EG Building 50-R-002 : Install Distribution boards, Lighting & small power | 2017-07-29 | 2017-08-03 | 2018-09-22 | 2018-09-30
Act | 2AI133MS41000-08000 | Not Started | Completed | EOF EG Building 52-R-303 : Diesel Day Tank Installation | 2017-07-29 | 2017-08-03 | 2018-09-22 | 2018-09-30
Act | 2AI133EL41000-08000 | Not Started | Completed | EOF EG Building 52-R-303 : Install Emergency Generator | 2017-07-29 | 2017-08-03 | 2018-09-22 | 2018-09-30
4 |  |  |  | INSTRUMENTATION
5 |  |  |  | EOF EG Building 50-R-002 : Instrument Cable laying, glanding, termination & continuity checks
Act | 2AI133IC11000 | Not Started | Completed | EOF EG Building 50-R-002 : Instrument Cable laying, glanding, termination & continuity checks | 2017-08-07 | 2017-08-21 | 2018-09-29 | 2018-10-20
Act | 2AI133IC11000-08001 | Not Started | Completed | EOF:Cable laying | 2017-08-07 | 2017-08-13 | 2018-09-29 | 2018-10-12
Act | 2AI133IC11000-08006 | Not Started | Completed | EOF:Glanding & termination | 2017-08-13 | 2017-08-19 | 2018-10-13 | 2018-10-19
Act | 2AI133IC11000-08010 | Not Started | Completed | EOF:Continuity check | 2017-08-19 | 2017-08-21 | 2018-10-13 | 2018-10-20
Act | 2AI133IC11000-08000 | Not Started | Completed | EOF EG Building 50-R-002 : Instrument Cable laying | 2017-08-07 | 2017-08-21 | 2018-09-29 | 2018-10-20
Act | 2AI133IC11000-08005 | Not Started | Completed | EOF:Cable laying | 2017-08-07 | 2017-08-21 | 2018-09-29 | 2018-10-20
5 |  |  |  | EOF EG Building 50-R-002 : F&G Devices & Instrument Installation
4 |  |  |  | TELECOM
5 |  |  |  | EOF EG Building 50-R-002 : FO & Telephone Cabling, Telecom system install, Cable Terminations
Act | 2AI133TE11000 | Not Started | Completed | EOF EG Building 50-R-002 : FO & Telephone Cabling, Telecom System install, Cable Terminations & continuity checks | 2017-07-29 | 2017-08-03 | 2018-01-01 | 2019-04-10
Act | 2AI133TE11000-08000 | Not Started | Completed | EOF:FO & Telephone Cable Laying | 2017-07-29 | 2017-08-01 | 2019-04-08 | 2019-04-10
Act | 2AI133TE11000-08005 | Not Started | Completed | EOF:Installation - Telecom System | 2017-08-01 | 2017-08-03 | 2018-01-01 | 2018-01-03
Act | 2AI133TE11000-08010 | Not Started | Completed | EOF:Cable Terminations & continuity checks | 2017-08-01 | 2017-08-02 | 2019-04-08 | 2019-04-10
3 |  |  |  | 52-R-303 - EMERGENCY GENERATOR BUILDING (LMM)
4 |  |  |  | CIVIL / STRUCTURAL / ARCHITECTURAL
5 |  |  |  | EOF EG Building 52-R-303 : Diesel Day Tank Foundation
Act | 2AI133CV41300 | Not Started | Completed | EOF EG Building 52-R-303 : Construct Diesel Day Tank Foundation | 2016-12-07 | 2017-01-19 | 2017-07-02 | 2017-11-08
Act | 2AI133CV41300-08006 | Not Started | Completed | Survey Marking, Excavation & Subgrade preparation | 2016-12-07 | 2016-12-11 | 2017-07-02 | 2017-07-03
Act | 2AI133CV41300-08010 | Not Started | Completed | Blinding/PCC | 2016-12-11 | 2016-12-15 | 2017-07-06 | 2017-07-06
Act | 2AI133CV41300-08015 | Not Started | Completed | Rebar & Formwork - for Footing | 2016-12-19 | 2016-12-26 | 2017-07-07 | 2017-07-10
Act | 2AI133CV41300-08020 | Not Started | Completed | Concrete Pouring - for Footing | 2016-12-26 | 2016-12-27 | 2017-07-10 | 2017-07-10
Act | 2AI133CV41300-08025 | Not Started | Completed | Concrete Protection | 2017-01-05 | 2017-01-10 | 2017-08-18 | 2017-08-26
Act | 2AI133CV41300-08030 | Not Started | Completed | Backfill / Compaction | 2017-01-14 | 2017-01-19 | 2017-11-06 | 2017-11-08
Act | 2AI133CV41300-08021 | Not Started | Completed | Rebar, Formwork & Install Embedments - for Pedestal | 2016-12-27 | 2017-01-01 | 2017-08-03 | 2017-08-07
Act | 2AI133CV41300-08022 | Not Started | Completed | Concrete Pouring - for Pedestal | 2017-01-01 | 2017-01-05 | 2017-08-08 | 2017-08-08
Act | 2AI133CV41300-08005 | Not Started | Completed | EOF EG Building 52-R-303 : Diesel Day Tank Foundation | 2016-12-07 | 2017-01-19 | 2017-07-02 | 2017-11-08
4 |  |  |  | MECHANICAL
5 |  |  |  | EOF EG Building 52-R-303 : Diesel Day Tank Installation
Act | 2AI133MS41000-08001 | Not Started | Completed | EOF:Installation of Diesel Day Tank Installation | 2017-09-17 | 2017-09-21 | 2017-12-22 | 2017-12-22
Act | 2AI133MS41000-08005 | Not Started | Completed | EOF:Preliminary Allignment & Grouting of Equipment | 2017-09-21 | 2017-09-26 | 2018-01-22 | 2018-01-23
Act | 2AI133MS41000-08010 | Not Started | Completed | EOF:Final Allignment & Grouting of Equipment | 2017-09-26 | 2017-10-01 | 2018-05-04 | 2018-05-06
Act | 2AI133MS41000 | Not Started | Completed | EOF EG Building 52-R-303 : Diesel Day Tank Installation | 2017-09-17 | 2017-10-01 | 2017-12-22 | 2018-05-06
4 |  |  |  | ELECTRICAL
5 |  |  |  | EOF EG Building 52-R-303 : Install Emergency Generator
Act | 2AI133EL41000-08001 | Not Started | Completed | EOF:Installation of Generators | 2017-08-29 | 2017-09-10 | 2018-06-20 | 2018-06-20
Act | 2AI133EL41000-08005 | Not Started | Completed | EOF:Allignment | 2017-09-10 | 2017-09-21 | 2018-06-21 | 2018-06-21
Act | 2AI133EL41000 | Not Started | Completed | EOF EG Building 52-R-303 : Install Emergency Generator | 2017-08-29 | 2017-09-21 | 2018-06-20 | 2018-06-21
5 |  |  |  | EOF EG Building 52-R-303 : Cable laying, glanding, termination & continuity check
Act | 2AI133EL41100 | Not Started | Completed | EOF EG Building 52-R-303 : Cable laying, glanding, termination & continuity check | 2017-08-31 | 2017-10-02 | 2018-10-08 | 2019-04-10
6 |  |  |  | EOF EG Building 52-R-303 : Cable laying
Act | 2AI133EL41100-08001 | Not Started | Completed | EOF:Fabricate Tray Supports | 2017-08-31 | 2017-09-04 | 2019-04-08 | 2019-04-10
Act | 2AI133EL41100-08006 | Not Started | Completed | EOF: Install cable trays | 2017-09-05 | 2017-09-13 | 2018-10-08 | 2018-10-10
Act | 2AI133EL41100-08010 | Not Started | Completed | EOF: Installcable trays covers | 2017-09-25 | 2017-09-28 | 2018-11-05 | 2018-11-07
Act | 2AI133EL41100-08009 | Not Started | Completed | EOF: Cable Laying | 2017-09-13 | 2017-09-25 | 2018-10-08 | 2018-10-10
Act | 2AI133EL41100-08004 | Not Started | Completed | EOF: Install Tray support and Hangers | 2017-09-03 | 2017-09-07 | 2019-04-08 | 2019-04-10
Act | 2AI133EL41100-08000 | Not Started | Completed | EOF EG Building 52-R-303 : Cable laying | 2017-08-31 | 2017-09-28 | 2018-10-08 | 2019-04-10
6 |  |  |  | EOF EG Building 52-R-303 : Cableglanding, termination & continuity check
Act | 2AI133EL41100-08015 | Not Started | Completed | EOF: Cable Glanding | 2017-09-16 | 2017-09-27 | 2018-10-13 | 2018-10-19
Act | 2AI133EL41100-08020 | Not Started | Completed | EOF: Continuity Checks & Terminations | 2017-09-21 | 2017-09-30 | 2018-10-14 | 2019-04-10
Act | 2AI133EL41100-08025 | Not Started | Completed | EOF: Tagging | 2017-09-26 | 2017-10-02 | 2018-10-15 | 2019-04-10
Act | 2AI133EL41100-08005 | Not Started | Completed | EOF EG Building 52-R-303 : Cableglanding, termination & continuity check | 2017-09-16 | 2017-10-02 | 2018-10-13 | 2019-04-10
6 |  |  |  | COCC: Cable laying, glanding & termination for Lighting
5 |  |  |  | EOF EG Building 52-R-303 : Install Distribution boards, Lighting & small power
Act | 2AI133EL41200 | Not Started | Completed | EOF EG Building 52-R-303 : Install Distribution boards, Lighting & small power | 2017-08-29 | 2017-09-04 | 2018-11-05 | 2018-11-23
Act | 2AI133EL41200-08001 | Not Started | Completed | EOF:Installation of Supports | 2017-08-29 | 2017-08-31 | 2018-11-05 | 2018-11-22
Act | 2AI133EL41200-08005 | Not Started | Completed | EOF:Installation of Distribution Board | 2017-08-31 | 2017-09-03 | 2018-11-07 | 2018-11-23
Act | 2AI133EL41200-08010 | Not Started | Completed | EOF:Allignment | 2017-09-03 | 2017-09-04 | 2018-11-09 | 2018-11-23
Act | 2AI133EL41200-08000 | Not Started | Completed | EOF EG Building 52-R-303 : Install Distribution boards, Lighting & small power | 2017-08-29 | 2017-09-04 | 2018-11-05 | 2018-11-23
4 |  |  |  | INSTRUMENTATION
5 |  |  |  | EOF EG Building 52-R-303 : Instrument Cable laying, glanding, termination & continuity checks
Act | 2AI133IC41000 | Not Started | In Progress | EOF EG Building 52-R-303 : Instrument Cable laying, glanding, termination & continuity checks | 2017-09-13 | 2017-09-27 | 2018-11-08
Act | 2AI133IC41000-08001 | Not Started | Completed | EOF:Cable laying | 2017-09-13 | 2017-09-19 | 2018-11-08 | 2018-11-23
Act | 2AI133IC41000-08006 | Not Started | In Progress | EOF:Glanding & termination | 2017-09-19 | 2017-09-25 | 2018-11-10
Act | 2AI133IC41000-08010 | Not Started | In Progress | EOF:Continuity check | 2017-09-25 | 2017-09-27 | 2018-11-12
Act | 2AI133IC41000-08000 | Not Started | In Progress | EOF EG Building 52-R-303 : Instrument Cable laying | 2017-09-13 | 2017-09-27 | 2018-11-08
Act | 2AI133IC41000-08005 | Not Started | In Progress | EOF EG Building 52-R-303 : Instrument Cable glanding, termination & continuity checks | 2017-09-13 | 2017-09-27 | 2018-11-08
5 |  |  |  | EOF EG Building 52-R-303 : F&G Devices & Instrument Installation
4 |  |  |  | TELECOM
5 |  |  |  | EOF EG Building 52-R-303 : FO & Telephone Cabling, Telecom system install, Cable Terminations
Act | 2AI133TE41000-08000 | Not Started | Completed | EOF:FO & Telephone Cable Laying | 2017-08-29 | 2017-09-02 | 2019-04-08 | 2019-04-10
Act | 2AI133TE41000-08005 | Not Started | Completed | EOF:Installation - Telecom System | 2017-09-02 | 2017-09-04 | 2018-01-01 | 2018-01-03
Act | 2AI133TE41000-08010 | Not Started | Completed | EOF:Cable Terminations & continuity checks | 2017-09-04 | 2017-09-05 | 2019-04-08 | 2019-04-10
Act | 2AI133TE41000 | Not Started | Completed | EOF EG Building 52-R-303 : FO & Telephone Cabling, Telecom System install, Cable Terminations & continuity checks | 2017-08-29 | 2017-09-05 | 2018-01-01 | 2019-04-10
2 |  |  |  | PRE-COMMISSIONING: EXPORT OIL FACILITY - AREA 621
3 |  |  |  | EOF S/S - ENERGIZE
4 |  |  |  | 52-SUBST-301+ 52-R-301 EDG (FMM AREA)
5 |  |  |  | EOF SS 52-SUBST-301 : 110V DC Battery Charger
Act | 2AI102PC01000-08001 | Not Started | Completed | EOF:Polarity check | 2017-09-07 | 2017-09-10 | 2018-09-22 | 2018-09-27
Act | 2AI102PC01000-08005 | Not Started | Completed | EOF:Charging test | 2017-09-10 | 2017-09-12 | 2018-09-22 | 2018-09-28
Act | 2AI102PC01000-08010 | Not Started | Completed | EOF:Discharging test | 2017-09-12 | 2017-09-14 | 2018-09-22 | 2018-09-30
Act | 2AI102PC01000 | Not Started | Completed | EOF SS 52-SUBST-301 : 110V DC Battery Charger | 2017-09-07 | 2017-09-14 | 2018-09-22 | 2018-09-30
Act | 2AI102PC01000-08000 | Not Started | Completed | EOF SS 52-SUBST-301 : 110V DC Battery Charger | 2017-09-07 | 2017-09-14 | 2018-09-22 | 2018-09-30
5 |  |  |  | EOF SS 52-SUBST-301 : SS Earthing & Lightning
Act | 2AI102PC01100-08001 | Not Started | Completed | EOF:Continuity testing | 2017-09-24 | 2017-09-27 | 2018-09-22 | 2018-09-26
Act | 2AI102PC01100-08005 | Not Started | Completed | EOF:Earth resistance measurement | 2017-09-27 | 2017-10-01 | 2018-09-22 | 2018-09-30
Act | 2AI102PC01100 | Not Started | Completed | EOF SS 52-SUBST-301 : SS Earthing & Lightning | 2017-09-24 | 2017-10-01 | 2018-09-22 | 2018-09-30
Act | 2AI102PC01100-08000 | Not Started | Completed | EOF SS 52-SUBST-301 : SS Earthing & Lightning | 2017-09-24 | 2017-10-01 | 2018-09-22 | 2018-09-30
5 |  |  |  | EOF SS 52-SUBST-301 : HV Switchgear testing
Act | 2AI102PC01200-08005 | Not Started | Completed | EOF: CT,PT,Breaker Testing | 2017-11-18 | 2017-11-28 | 2018-09-22 | 2018-09-26
Act | 2AI102PC01200-08010 | Not Started | Completed | EOF: IR, Ductor testing | 2017-11-23 | 2017-12-02 | 2018-09-23 | 2018-09-28
Act | 2AI102PC01200-08015 | Not Started | Completed | EOF: Relay & Functional Testing | 2017-12-02 | 2017-12-10 | 2018-09-23 | 2018-09-28
Act | 2AI102PC01200 | Not Started | Completed | EOF SS 52-SUBST-301 : HV Switchgear testing | 2017-11-18 | 2017-12-17 | 2018-09-22 | 2018-10-01
Act | 2AI102PC01200-08025 | Not Started | Completed | EOF Primary Injection Testing | 2017-11-28 | 2017-12-09 | 2018-09-23 | 2018-09-29
Act | 2AI102PC01200-08035 | Not Started | Completed | EOF: Stability Testing | 2017-12-13 | 2017-12-17 | 2018-09-23 | 2018-10-01
Act | 2AI102PC01200-08034 | Not Started | Completed | EOF: Hi-pot Test | 2017-12-09 | 2017-12-13 | 2018-09-23 | 2018-09-30
Act | 2AI102PC01200-08000 | Not Started | Completed | EOF SS 52-SUBST-301 : HV Switchgear testing | 2017-11-18 | 2017-12-17 | 2018-09-22 | 2018-10-01
5 |  |  |  | EOF SS 52-SUBST-301 : 24V DC Battery Charger
Act | 2AI102PC01300-08001 | Not Started | Completed | EOF:Polarity check | 2017-09-06 | 2017-09-09 | 2018-09-23 | 2018-09-27
Act | 2AI102PC01300-08005 | Not Started | Completed | EOF:Charging test | 2017-09-09 | 2017-09-11 | 2018-09-23 | 2018-09-28
Act | 2AI102PC01300-08010 | Not Started | Completed | EOF:Discharging test | 2017-09-11 | 2017-09-13 | 2018-09-23 | 2018-09-30
Act | 2AI102PC01300 | Not Started | Completed | EOF SS 52-SUBST-301 : 24V DC Battery Charger | 2017-09-06 | 2017-09-13 | 2018-09-23 | 2018-09-30
Act | 2AI102PC01300-08000 | Not Started | Completed | EOF SS 52-SUBST-301 : 24V DC Battery Charger | 2017-09-06 | 2017-09-13 | 2018-09-23 | 2018-09-30
5 |  |  |  | EOF SS 52-SUBST-301 : LV Switchgear testing
Act | 2AI102PC01400 | Not Started | Completed | EOF SS 52-SUBST-301 : LV Switchgear testing | 2017-08-29 | 2017-10-23 | 2018-09-23 | 2018-11-07
Act | 2AI102PC01400-08001 | Not Started | Completed | EOF: CT,PT Testing | 2017-08-29 | 2017-08-31 | 2018-09-23 | 2018-09-26
Act | 2AI102PC01400-08005 | Not Started | Completed | EOF: IR, Ductor testing | 2017-08-30 | 2017-09-02 | 2018-09-23 | 2018-09-28
Act | 2AI102PC01400-08010 | Not Started | Completed | EOF: Relay & Functional Testing | 2017-09-02 | 2017-09-04 | 2018-09-23 | 2018-09-30
Act | 2AI102PC01400-08015 | Not Started | Completed | EOF Primary Injection Testing | 2017-09-04 | 2017-09-05 | 2018-09-24 | 2018-09-30
Act | 2AI102PC01400-08025 | Not Started | Completed | EOF: Stability Testing | 2017-10-22 | 2017-10-23 | 2018-09-24 | 2018-10-01
Act | 2AI102PC01400-08020 | Not Started | Completed | EOF: Hi-pot Test | 2017-10-21 | 2017-10-22 | 2018-11-05 | 2018-11-07
Act | 2AI102PC01400-08000 | Not Started | Completed | EOF SS 52-SUBST-301 : LV Switchgear testing | 2017-08-29 | 2017-10-23 | 2018-09-23 | 2018-11-07
5 |  |  |  | EOF SS 52-SUBST-301 : Fire Alarm / Fire Suppression
5 |  |  |  | EOF SS 52-SUBST-301 : 110V AC UPS
Act | 2AI102PC01600-08001 | Not Started | Completed | EOF:Polarity check | 2017-12-09 | 2017-12-12 | 2018-09-24 | 2018-09-27
Act | 2AI102PC01600-08005 | Not Started | Completed | EOF:Charging test | 2017-12-12 | 2017-12-16 | 2018-09-24 | 2018-09-28
Act | 2AI102PC01600-08010 | Not Started | Completed | EOF:Discharging test | 2017-12-16 | 2017-12-19 | 2018-09-24 | 2018-09-30
Act | 2AI102PC01600 | Not Started | Completed | EOF SS 52-SUBST-301 : 110V AC UPS | 2017-12-09 | 2017-12-19 | 2018-09-24 | 2018-09-30
Act | 2AI102PC01600-08000 | Not Started | Completed | EOF SS 52-SUBST-301 : 110V AC UPS | 2017-12-09 | 2017-12-19 | 2018-09-24 | 2018-09-30
5 |  |  |  | EOF SS 52-SUBST-301 : Transformer Testing
Act | 2AI102PC01700-08001 | Not Started | Completed | EOF:IR testing/WR testing/Turns ratio testing | 2017-08-27 | 2017-08-30 | 2018-09-24 | 2018-09-27
Act | 2AI102PC01700-08005 | Not Started | Completed | EOF:Functional Test | 2017-08-30 | 2017-09-03 | 2018-09-24 | 2018-09-28
Act | 2AI102PC01700-08010 | Not Started | Completed | EOF:BDV Testing | 2017-09-03 | 2017-09-04 | 2018-09-24 | 2018-09-30
Act | 2AI102PC01700 | Not Started | Completed | EOF SS 52-SUBST-301 : Transformer Testing | 2017-08-27 | 2017-09-04 | 2018-09-24 | 2018-09-30
Act | 2AI102PC01700-08000 | Not Started | Completed | EOF SS 52-SUBST-301 : Transformer Testing | 2017-08-27 | 2017-09-04 | 2018-09-24 | 2018-09-30
5 |  |  |  | EOF SS 52-SUBST-301 : Electrical Tie-ins for Permanent Power & Energize
Act | 2AI102PC01900-08001 | Not Started | Completed | EOF:Incoming cables IR and continuity test | 2017-08-27 | 2017-08-30 | 2018-09-24 | 2018-09-27
Act | 2AI102PC01900-08005 | Not Started | Completed | EOF:Incoming HV cables hipot testing | 2017-08-27 | 2017-08-29 | 2018-09-24 | 2018-09-28
Act | 2AI102PC01900 | Not Started | Completed | EOF SS 52-SUBST-301 : Electrical Tie-ins for Permanent Power & Energize | 2017-08-27 | 2017-12-19 | 2018-09-24 | 2019-01-13
Act | 2AI102PC01900-08010 | Not Started | Completed | Cable Termination | 2017-08-27 | 2017-08-30 | 2018-09-24 | 2018-09-29
Act | 2AI102PC01900-08045 | Not Started | Completed | EOF: Ready for Energisation of Substation 52-SUBST-301 | 2017-12-19 | 2017-12-19 | 2019-01-13 | 2019-01-13
Act | 2AI102PC01900-08000 | Not Started | Completed | EOF SS 52-SUBST-301 : Electrical Tie-ins for Permanent Power & Energize | 2017-08-27 | 2017-12-19 | 2018-09-24 | 2019-01-13
5 |  |  |  | EOF SS 52-SUBST-301 : Lighting & Small Power
Act | 2AI102PC02000-08001 | Not Started | Completed | EOF:Continuity & IR testing | 2017-10-21 | 2017-10-29 | 2017-12-04 | 2018-01-03
Act | 2AI102PC02000-08005 | Not Started | Completed | EOF:Lux testing | 2017-12-19 | 2017-12-21 | 2017-12-19 | 2017-12-21
Act | 2AI102PC02000 | Not Started | Completed | EOF SS 52-SUBST-301 : Lighting & Small Power | 2017-10-21 | 2017-12-21 | 2017-12-04 | 2018-01-03
Act | 2AI102PC02000-08000 | Not Started | Completed | EOF SS 52-SUBST-301 : Lighting & Small Power | 2017-10-21 | 2017-12-21 | 2017-12-04 | 2018-01-03
5 |  |  |  | EOF SS 52-SUBST-301 : Energize EDG 50-R-301
Act | 2AI102PC02100-08001 | Not Started | Completed | GCP Testing, Switch Gear Testing | 2017-09-12 | 2017-09-20 | 2019-03-09 | 2019-03-15
Act | 2AI102PC02100 | Not Started | Completed | EOF SS 52-SUBST-301 : Energize EDG 50-R-301 | 2017-09-12 | 2017-09-21 | 2019-03-09 | 2019-03-28
Act | 2AI102PC02100-08010 | Not Started | Completed | EOF SS 52-SUBST-301 : Energize EDG 50-R-301 | 2017-09-20 | 2017-09-21 | 2019-03-23 | 2019-03-28
Act | 2AI102PC02100-08000 | Not Started | Completed | EOF SS 52-SUBST-301 : Energize EDG 50-R-301 | 2017-09-12 | 2017-09-21 | 2019-03-09 | 2019-03-28
4 |  |  |  | 52-SUBST-303 + 52-R-303 EDG (LMM AREA)
5 |  |  |  | EOF SS 52-SUBST-303 : 110V DC Battery Charger
Act | 2AI102PC03000-08001 | Not Started | Not Started | EOF:Polarity check | 2017-09-11 | 2017-09-13
Act | 2AI102PC03000-08005 | Not Started | Not Started | EOF:Charging test | 2017-09-13 | 2017-09-16
Act | 2AI102PC03000-08010 | Not Started | Not Started | EOF:Discharging test | 2017-09-16 | 2017-09-18
Act | 2AI102PC03000 | Not Started | Not Started | EOF SS 52-SUBST-303 : 110V DC Battery Charger | 2017-09-11 | 2017-09-18
Act | 2AI102PC03000-08000 | Not Started | Not Started | EOF SS 52-SUBST-303 : 110V DC Battery Charger | 2017-09-11 | 2017-09-18
5 |  |  |  | EOF SS 52-SUBST-303 : SS Earthing & Lightning
Act | 2AI102PC03100-08001 | Not Started | Not Started | EOF:Continuity testing | 2017-10-05 | 2017-10-09
Act | 2AI102PC03100-08005 | Not Started | Not Started | EOF:Earth resistance measurement | 2017-10-09 | 2017-10-12
Act | 2AI102PC03100 | Not Started | Not Started | EOF SS 52-SUBST-303 : SS Earthing & Lightning | 2017-10-05 | 2017-10-12
Act | 2AI102PC03100-08000 | Not Started | Not Started | EOF SS 52-SUBST-303 : SS Earthing & Lightning | 2017-10-05 | 2017-10-12
5 |  |  |  | EOF SS 52-SUBST-303 : HV Switchgear testing
Act | 2AI102PC03200 | Not Started | Not Started | EOF SS 52-SUBST-303 : HV Switchgear testing | 2017-10-07 | 2017-11-05
Act | 2AI102PC03200-08001 | Not Started | Not Started | EOF: CT,PT,Breaker Testing | 2017-10-07 | 2017-10-17
Act | 2AI102PC03200-08005 | Not Started | Not Started | EOF: IR, Ductor testing | 2017-10-12 | 2017-10-21
Act | 2AI102PC03200-08010 | Not Started | Not Started | EOF: Relay & Functional Testing | 2017-10-21 | 2017-10-29
Act | 2AI102PC03200-08015 | Not Started | Not Started | EOF Primary Injection Testing | 2017-10-17 | 2017-10-28
Act | 2AI102PC03200-08025 | Not Started | Not Started | EOF: Stability Testing | 2017-11-01 | 2017-11-05
Act | 2AI102PC03200-08020 | Not Started | Not Started | EOF: Hi-pot Test | 2017-10-28 | 2017-11-01
Act | 2AI102PC03200-08000 | Not Started | Not Started | EOF SS 52-SUBST-303 : HV Switchgear testing | 2017-10-07 | 2017-11-05
5 |  |  |  | EOF SS 52-SUBST-303 : 24V DC Battery Charger
Act | 2AI102PC03300-08001 | Not Started | Not Started | EOF:Polarity check | 2017-09-11 | 2017-09-13
Act | 2AI102PC03300-08005 | Not Started | Not Started | EOF:Charging test | 2017-09-13 | 2017-09-16
Act | 2AI102PC03300-08010 | Not Started | Not Started | EOF:Discharging test | 2017-09-16 | 2017-09-18
Act | 2AI102PC03300 | Not Started | Not Started | EOF SS 52-SUBST-303 : 24V DC Battery Charger | 2017-09-11 | 2017-09-18
Act | 2AI102PC03300-08000 | Not Started | Not Started | EOF SS 52-SUBST-303 : 24V DC Battery Charger | 2017-09-11 | 2017-09-18
5 |  |  |  | EOF SS 52-SUBST-303 : LV Switchgear testing
Act | 2AI102PC03400 | Not Started | Not Started | EOF SS 52-SUBST-303 : LV Switchgear testing | 2017-10-31 | 2017-11-27
Act | 2AI102PC03400-08001 | Not Started | Not Started | EOF: CT,PT Testing | 2017-10-31 | 2017-11-02
Act | 2AI102PC03400-08005 | Not Started | Not Started | EOF: IR, Ductor testing | 2017-11-01 | 2017-11-04
Act | 2AI102PC03400-08010 | Not Started | Not Started | EOF: Relay & Functional Testing | 2017-11-04 | 2017-11-06
Act | 2AI102PC03400-08015 | Not Started | Not Started | EOF Primary Injection Testing | 2017-11-06 | 2017-11-07
Act | 2AI102PC03400-08025 | Not Started | Not Started | EOF: Stability Testing | 2017-11-26 | 2017-11-27
Act | 2AI102PC03400-08020 | Not Started | Not Started | EOF: Hi-pot Test | 2017-11-25 | 2017-11-26
Act | 2AI102PC03400-08000 | Not Started | Not Started | EOF SS 52-SUBST-303 : LV Switchgear testing | 2017-10-31 | 2017-11-27
5 |  |  |  | EOF SS 52-SUBST-303 : Fire Alarm / Fire Suppression
5 |  |  |  | EOF SS 52-SUBST-303 : 110V AC UPS
Act | 2AI102PC03600-08001 | Not Started | Not Started | EOF:Polarity check | 2017-10-19 | 2017-10-24
Act | 2AI102PC03600-08005 | Not Started | Not Started | EOF:Charging test | 2017-10-24 | 2017-10-29
Act | 2AI102PC03600-08010 | Not Started | Not Started | EOF:Discharging test | 2017-10-29 | 2017-11-02
Act | 2AI102PC03600 | Not Started | Not Started | EOF SS 52-SUBST-303 : 110V AC UPS | 2017-10-19 | 2017-11-02
Act | 2AI102PC03600-08000 | Not Started | Not Started | EOF SS 52-SUBST-303 : 110V AC UPS | 2017-10-19 | 2017-11-02
5 |  |  |  | EOF SS 52-SUBST-303 : Transformer Testing
Act | 2AI102PC03700 | Not Started | Not Started | EOF SS 52-SUBST-303 : Transformer Testing | 2017-07-27 | 2017-08-08
Act | 2AI102PC03700-08001 | Not Started | Not Started | EOF:IR testing/WR testing/Turns ratio testing | 2017-07-27 | 2017-08-01
Act | 2AI102PC03700-08005 | Not Started | Not Started | EOF:Functional Test | 2017-08-01 | 2017-08-06
Act | 2AI102PC03700-08010 | Not Started | Not Started | EOF:BDV Testing | 2017-08-06 | 2017-08-08
Act | 2AI102PC03700-08000 | Not Started | Not Started | EOF SS 52-SUBST-303 : Transformer Testing | 2017-07-27 | 2017-08-08
5 |  |  |  | EOF SS 52-SUBST-303 : Electrical Tie-ins for Permanent Power & Energize
Act | 2AI102PC03900-08001 | Not Started | Not Started | EOF:Incoming cables IR and continuity test | 2017-08-02 | 2017-08-06
Act | 2AI102PC03900-08005 | Not Started | Not Started | EOF:Incoming HV cables hipot testing | 2017-08-06 | 2017-08-08
Act | 2AI102PC03900 | Not Started | Not Started | EOF SS 52-SUBST-303 : Electrical Tie-ins for Permanent Power & Energize | 2017-08-02 | 2018-01-02
Act | 2AI102PC03900-08030 | Not Started | Not Started | EOF: Energisation of Substation 52-SUBST-303 | 2018-01-02 | 2018-01-02
Act | 2AI102PC03900-08015 | Not Started | Not Started | EOF: Cable Termination | 2017-08-08 | 2017-08-12
Act | 2AI102PC03900-08000 | Not Started | Not Started | EOF SS 52-SUBST-303 : Electrical Tie-ins for Permanent Power & Energize | 2017-08-02 | 2018-01-02
5 |  |  |  | EOF SS 52-SUBST-303 : Energize EDG 52-R-303
Act | 2AI102PC04000-08001 | Not Started | Not Started | EOF: GCP Testing, Switch Gear Testing | 2017-09-12 | 2017-09-20
Act | 2AI102PC04000 | Not Started | Not Started | EOF SS 52-SUBST-303 : Energize EDG 52-R-303 | 2017-09-12 | 2017-09-21
Act | 2AI102PC04000-08010 | Not Started | Not Started | EOF SS 52-SUBST-303 : Energize EDG 52-R-303 | 2017-09-20 | 2017-09-21
Act | 2AI102PC04000-08000 | Not Started | Not Started | EOF SS 52-SUBST-303 : Energize EDG 52-R-303 | 2017-09-12 | 2017-09-21
5 |  |  |  | EOF SS 52-SUBST-303 : Lighting & Small Power
Act | 2AI102PC04100-08001 | Not Started | Completed | EOF:Continuity & IR testing | 2017-09-04 | 2017-09-12 | 2017-09-04 | 2017-09-12
Act | 2AI102PC04100-08005 | Not Started | Completed | EOF:Lux testing | 2018-01-02 | 2018-01-04 | 2018-01-02 | 2018-01-04
Act | 2AI102PC04100 | Not Started | Completed | EOF SS 52-SUBST-303 : Lighting & Small Power | 2017-09-04 | 2018-01-04 | 2017-09-04 | 2018-01-04
Act | 2AI102PC04100-08000 | Not Started | Completed | EOF SS 52-SUBST-303 : Lighting & Small Power | 2017-09-04 | 2018-01-04 | 2017-09-04 | 2018-01-04
4 |  |  |  | 52-SUBST-302 + 52-R-302 EDG (STF AREA)
5 |  |  |  | EOF SS 52-SUBST-302 : SS Earthing & Lightning
Act | 2AI101PC01100-08001 | Not Started | Not Started | EOF:Continuity testing | 2017-09-26 | 2017-09-30
Act | 2AI101PC01100-08005 | Not Started | Completed | EOF:Earth resistance measurement | 2017-09-30 | 2017-10-03 | 2019-03-09 | 2019-03-15
Act | 2AI101PC01100 | Not Started | In Progress | EOF SS 52-SUBST-302 : SS Earthing & Lightning | 2017-09-26 | 2017-10-03 | 2019-03-09
Act | 2AI101PC01100-08000 | Not Started | In Progress | EOF SS 52-SUBST-302 : SS Earthing & Lightning | 2017-09-26 | 2017-10-03 | 2019-03-09
5 |  |  |  | EOF SS 52-SUBST-302 : 110V DC Battery Charger
Act | 2AI101PC01000-08001 | Not Started | Not Started | EOF:Polarity check | 2017-09-12 | 2017-09-14
Act | 2AI101PC01000-08005 | Not Started | Not Started | EOF:Charging test | 2017-09-14 | 2017-09-17
Act | 2AI101PC01000-08010 | Not Started | Not Started | EOF:Discharging test | 2017-09-17 | 2017-09-19
Act | 2AI101PC01000 | Not Started | Not Started | EOF SS 52-SUBST-302 : 110V DC Battery Charger | 2017-09-12 | 2017-09-19
Act | 2AI101PC01000-08000 | Not Started | Not Started | EOF SS 52-SUBST-302 : 110V DC Battery Charger | 2017-09-12 | 2017-09-19
5 |  |  |  | EOF SS 52-SUBST-302 : 110V AC UPS
Act | 2AI101PC01600-08001 | Not Started | Not Started | EOF:Polarity check | 2017-12-03 | 2017-12-07
Act | 2AI101PC01600-08005 | Not Started | Not Started | EOF:Charging test | 2017-12-07 | 2017-12-12
Act | 2AI101PC01600-08010 | Not Started | Not Started | EOF:Discharging test | 2017-12-12 | 2017-12-17
Act | 2AI101PC01600 | Not Started | Not Started | EOF SS 52-SUBST-302 : 110V AC UPS | 2017-12-03 | 2017-12-17
Act | 2AI101PC01600-08000 | Not Started | Not Started | EOF SS 52-SUBST-302 : 110V AC UPS | 2017-12-03 | 2017-12-17
5 |  |  |  | EOF SS 52-SUBST-302 : 24V DC Battery Charger
Act | 2AI101PC01300-08001 | Not Started | Not Started | EOF:Polarity check | 2017-09-12 | 2017-09-14
Act | 2AI101PC01300-08005 | Not Started | Not Started | EOF:Charging test | 2017-09-14 | 2017-09-17
Act | 2AI101PC01300-08010 | Not Started | Not Started | EOF:Discharging test | 2017-09-17 | 2017-09-19
Act | 2AI101PC01300 | Not Started | Not Started | EOF SS 52-SUBST-302 : 24V DC Battery Charger | 2017-09-12 | 2017-09-19
Act | 2AI101PC01300-08000 | Not Started | Not Started | EOF SS 52-SUBST-302 : 24V DC Battery Charger | 2017-09-12 | 2017-09-19
5 |  |  |  | EOF SS 52-SUBST-302 : HV Switchgear testing
Act | 2AI101PC01200 | Not Started | In Progress | EOF SS 52-SUBST-302 : HV Switchgear testing | 2017-11-22 | 2017-12-21 | 2019-03-23
Act | 2AI101PC01200-08001 | Not Started | Completed | EOF: CT,PT,Breaker Testing | 2017-11-22 | 2017-12-03 | 2019-03-23 | 2019-03-24
Act | 2AI101PC01200-08005 | Not Started | Completed | EOF: IR, Ductor testing | 2017-11-28 | 2017-12-06 | 2019-03-23 | 2019-03-25
Act | 2AI101PC01200-08010 | Not Started | Not Started | EOF: Relay & Functional Testing | 2017-12-06 | 2017-12-14
Act | 2AI101PC01200-08015 | Not Started | Completed | EOF Primary Injection Testing | 2017-12-03 | 2017-12-13 | 2019-03-25 | 2019-03-26
Act | 2AI101PC01200-08025 | Not Started | Not Started | EOF: Stability Testing | 2017-12-18 | 2017-12-21
Act | 2AI101PC01200-08020 | Not Started | Not Started | EOF: Hi-pot Test | 2017-12-13 | 2017-12-18
Act | 2AI101PC01200-08000 | Not Started | In Progress | EOF SS 52-SUBST-302 : HV Switchgear testing | 2017-11-22 | 2017-12-21 | 2019-03-23
5 |  |  |  | EOF SS 52-SUBST-302 : Transformer Testing
Act | 2AI101PC01700-08001 | Not Started | Completed | EOF:IR testing/WR testing/Turns ratio testing | 2017-09-19 | 2017-09-23 | 2019-03-10 | 2019-03-14
Act | 2AI101PC01700-08005 | Not Started | Completed | EOF:Functional Test | 2017-09-23 | 2017-09-26 | 2019-03-10 | 2019-03-15
Act | 2AI101PC01700-08010 | Not Started | Completed | EOF:BDV Testing | 2017-09-26 | 2017-09-27 | 2019-03-09 | 2019-03-15
Act | 2AI101PC01700 | Not Started | Completed | EOF SS 52-SUBST-302 : Transformer Testing | 2017-09-19 | 2017-09-27 | 2019-03-09 | 2019-03-15
Act | 2AI101PC01700-08000 | Not Started | Completed | EOF SS 52-SUBST-302 : Transformer Testing | 2017-09-19 | 2017-09-27 | 2019-03-09 | 2019-03-15
5 |  |  |  | EOF SS 52-SUBST-302 : LV Switchgear testing
Act | 2AI101PC01400 | Not Started | In Progress | EOF SS 52-SUBST-302 : LV Switchgear testing | 2017-08-21 | 2017-10-23 | 2019-03-16
Act | 2AI101PC01400-08001 | Not Started | In Progress | EOF: CT,PT Testing | 2017-08-21 | 2017-08-23 | 2019-03-16
Act | 2AI101PC01400-08005 | Not Started | In Progress | EOF: IR, Ductor testing | 2017-08-22 | 2017-08-24 | 2019-03-16
Act | 2AI101PC01400-08010 | Not Started | In Progress | EOF: Relay & Functional Testing | 2017-08-24 | 2017-08-27 | 2019-03-17
Act | 2AI101PC01400-08015 | Not Started | Not Started | EOF Primary Injection Testing | 2017-08-27 | 2017-08-28
Act | 2AI101PC01400-08025 | Not Started | Not Started | EOF: Stability Testing | 2017-10-22 | 2017-10-23
Act | 2AI101PC01400-08020 | Not Started | Not Started | EOF: Hi-pot Test | 2017-10-21 | 2017-10-22
Act | 2AI101PC01400-08000 | Not Started | In Progress | EOF SS 52-SUBST-302 : LV Switchgear testing | 2017-08-21 | 2017-10-23 | 2019-03-16
5 |  |  |  | EOF SS 52-SUBST-302 : Fire Alarm / Fire Suppression
5 |  |  |  | EOF SS 52-SUBST-302 : Lighting & Small Power
Act | 2AI101PC02000-08001 | Not Started | Completed | EOF:Continuity & IR testing | 2017-08-03 | 2017-08-12 | 2017-08-03 | 2017-08-12
Act | 2AI101PC02000-08005 | Not Started | Completed | EOF:Lux testing | 2017-12-21 | 2017-12-24 | 2017-12-21 | 2017-12-24
Act | 2AI101PC02000 | Not Started | Completed | EOF SS 52-SUBST-302 : Lighting & Small Power | 2017-08-03 | 2017-12-24 | 2017-08-03 | 2017-12-24
Act | 2AI101PC02000-08000 | Not Started | Completed | EOF SS 52-SUBST-302 : Lighting & Small Power | 2017-08-03 | 2017-12-24 | 2017-08-03 | 2017-12-24
5 |  |  |  | EOF SS 52-SUBST-302 : Energize EDG 60-R-706
Act | 2AI101PC02100-08001 | Not Started | Not Started | EOF: GCP Testing, Switch Gear Testing | 2017-09-12 | 2017-09-20
Act | 2AI101PC02100 | Not Started | Not Started | EOF SS 52-SUBST-302 : Energize EDG 60-R-706 | 2017-09-12 | 2017-09-21
Act | 2AI101PC02100-08010 | Not Started | Not Started | EOF SS 52-SUBST-302 : Energize EDG 60-R-706 | 2017-09-20 | 2017-09-21
Act | 2AI101PC02100-08000 | Not Started | Not Started | EOF SS 52-SUBST-302 : Energize EDG 60-R-706 | 2017-09-12 | 2017-09-21
5 |  |  |  | EOF SS 52-SUBST-302 : Electrical Tie-ins for Permanent Power & Energize
Act | 2AI101PC01900-08001 | Not Started | Not Started | EOF:Incoming cables IR and continuity test | 2017-09-19 | 2017-09-23
Act | 2AI101PC01900-08005 | Not Started | Not Started | EOF:Incoming HV cables hipot testing | 2017-09-23 | 2017-09-25
Act | 2AI101PC01900 | Not Started | Not Started | EOF SS 52-SUBST-302 : Electrical Tie-ins for Permanent Power & Energize | 2017-09-19 | 2017-12-21
Act | 2AI102PC03900-08020 | Not Started | Not Started | EOF: Energisation of Substation 52-SUBST-302 | 2017-12-21 | 2017-12-21
Act | 2AI102PC03900-08010 | Not Started | Not Started | EOF: Cable Termination | 2017-09-25 | 2017-09-28
Act | 2AI101PC01900-08000 | Not Started | Not Started | EOF SS 52-SUBST-302 : Electrical Tie-ins for Permanent Power & Energize | 2017-09-19 | 2017-12-21
3 |  |  |  | EOF - UTILITY System
4 |  |  |  | EOF:Fire Water Tie-In / Ring main & hydrants /Deluge System
Act | 2AI133PC01000-08000 | Not Started | Not Started | EOF:Fire Water Tie-In / Ring main & hydrants /Deluge System | 2017-08-24 | 2017-12-07
Act | 2AI133PC01000 | Not Started | Not Started | EOF:Fire Water Tie-In / Ring main & hydrants /Deluge System | 2017-08-24 | 2017-12-07
4 |  |  |  | EOF:Foam System Package/Overhead Water tank/Foam Concentrate tank/drains/Diesel Tanks/Foam Pumps
Act | 2AI133PC01100-08000 | Not Started | Not Started | EOF:Foam System Package / Overhead Water tank / Foam Concentrate tank / drains / Diesel Tanks/ Foam Pumps | 2017-08-07 | 2017-12-25
Act | 2AI133PC01100 | Not Started | Not Started | EOF:Foam System Package / Overhead Water tank / Foam Concentrate tank / drains / Diesel Tanks/ Foam Pumps | 2017-08-07 | 2017-12-25
3 |  |  |  | EOF -PROCESS System
4 |  |  |  | EOF:Floating Tanks / Mixers / Oily Water collection System / Drain / Oily Water transfer Pump
Act | 2AI133PC01400-08000 | Not Started | Not Started | EOF:Floating Tanks / Mixers / Oily Water collection System / Drain / Oily Water transfer Pump | 2017-07-31 | 2017-11-13
Act | 2AI133PC01400 | Not Started | Not Started | EOF:Floating Tanks / Mixers / Oily Water collection System / Drain / Oily Water transfer Pump | 2017-07-31 | 2017-11-13
4 |  |  |  | EOF:Loading Mixing manifold / Trim Pumps / Auto sampling Package / drain Sump & Pump
Act | 2AI133PC01300-08000 | Not Started | Not Started | EOF:Loading Mixing manifold / Trim Pumps / Auto sampling Package / drain Sump & Pump | 2017-12-26 | 2018-01-31
Act | 2AI133PC01300 | Not Started | Not Started | EOF:Loading Mixing manifold / Trim Pumps / Auto sampling Package / drain Sump & Pump | 2017-12-26 | 2018-01-31
4 |  |  |  | EOF/COCC: Liquidation of pre-comm punch points ('B' items)
Act | 2AI133PC01500-08000 | Not Started | In Progress | EOF/COCC: Liquidation of pre-comm punch points ('B' items) | 2017-12-26 | 2018-01-31 | 2019-04-08
Act | 2AI133PC01500 | Not Started | In Progress | EOF/COCC: Liquidation of pre-comm punch points ('B' items) | 2017-12-26 | 2018-01-31 | 2019-04-08
4 |  |  |  | EOF:Filling / mixing manifold / Auto sampling Package / Pig receiver /Drain
Act | 2AI133PC01200-08000 | Not Started | Not Started | EOF:Filling / mixing manifold / Auto sampling Package / Pig receiver /Drain | 2017-10-17 | 2017-12-26
Act | 2AI133PC01200 | Not Started | Not Started | EOF:Filling / mixing manifold / Auto sampling Package / Pig receiver /Drain | 2017-10-17 | 2017-12-26
2 |  |  |  | PRE-COMMISSIONING - CRUDE OIL CONTROL CENTER (COCC) - AREA 621
3 |  |  |  | EOF S/S - ENERGIZE
4 |  |  |  | 50-SUBST-001 + 50-R-002 EDG (COCC AREA)
5 |  |  |  | COCC: EOF SS 50-SUBST-001 : 110V DC Battery Charger
Act | 2AI141PC02000-08001 | Not Started | Completed | COCC: Polarity check | 2017-10-05 | 2017-10-08 | 2019-03-23 | 2019-03-25
Act | 2AI141PC02000-08005 | Not Started | Completed | COCC: Charging test | 2017-10-08 | 2017-10-10 | 2019-03-23 | 2019-03-25
Act | 2AI141PC02000-08010 | Not Started | Completed | COCC: Discharging test | 2017-10-10 | 2017-10-12 | 2019-03-24 | 2019-03-26
Act | 2AI141PC02000 | Not Started | Completed | COCC: EOF SS 50-SUBST-001 : 110V DC Battery Charger | 2017-10-05 | 2017-10-12 | 2019-03-23 | 2019-03-26
Act | 2AI141PC02000-08000 | Not Started | Completed | COCC: EOF SS 50-SUBST-001 : 110V DC Battery Charger | 2017-10-05 | 2017-10-12 | 2019-03-23 | 2019-03-26
5 |  |  |  | COCC: EOF SS 50-SUBST-001 : HV Switchgear testing
Act | 2AI141PC02200 | Not Started | Completed | COCC: EOF SS 50-SUBST-001 : HV Switchgear testing | 2017-10-07 | 2017-11-05 | 2018-12-29 | 2019-01-11
Act | 2AI141PC02200-08001 | Not Started | Completed | EOF: CT,PT,Breaker Testing | 2017-10-07 | 2017-10-17 | 2019-01-05 | 2019-01-10
Act | 2AI141PC02200-08005 | Not Started | Completed | EOF: IR, Ductor testing | 2017-10-12 | 2017-10-21 | 2019-01-06 | 2019-01-10
Act | 2AI141PC02200-08010 | Not Started | Completed | EOF: Relay & Functional Testing | 2017-10-21 | 2017-10-29 | 2018-12-29 | 2019-01-10
Act | 2AI141PC02200-08015 | Not Started | Completed | EOF Primary Injection Testing | 2017-10-17 | 2017-10-28 | 2018-12-30 | 2019-01-11
Act | 2AI141PC02200-08025 | Not Started | Completed | EOF: Stability Testing | 2017-11-01 | 2017-11-05 | 2019-01-06 | 2019-01-11
Act | 2AI141PC02200-08020 | Not Started | Completed | EOF: Hi-pot Test | 2017-10-28 | 2017-11-01 | 2019-01-05 | 2019-01-11
Act | 2AI141PC02200-08000 | Not Started | Completed | COCC: EOF SS 50-SUBST-001 : HV Switchgear testing | 2017-10-07 | 2017-11-05 | 2018-12-29 | 2019-01-11
5 |  |  |  | COCC: EOF SS 50-SUBST-001 : Transformer Testing
Act | 2AI141PC02700 | Not Started | Completed | COCC: EOF SS 50-SUBST-001 : Transformer Testing | 2017-10-12 | 2017-10-21 | 2018-12-22 | 2018-12-28
Act | 2AI141PC02700-08001 | Not Started | Completed | EOF:IR testing/WR testing/Turns ratio testing | 2017-10-12 | 2017-10-16 | 2018-12-22 | 2018-12-26
Act | 2AI141PC02700-08005 | Not Started | Completed | EOF:Functional Test | 2017-10-16 | 2017-10-19 | 2018-12-22 | 2018-12-27
Act | 2AI141PC02700-08010 | Not Started | Completed | EOF:BDV Testing | 2017-10-19 | 2017-10-21 | 2018-12-22 | 2018-12-28
Act | 2AI141PC02700-08000 | Not Started | Completed | COCC: EOF SS 50-SUBST-001 : Transformer Testing | 2017-10-12 | 2017-10-21 | 2018-12-22 | 2018-12-28
5 |  |  |  | COCC: EOF SS 50-SUBST-001 : LV Switchgear testing
Act | 2AI141PC02400 | Not Started | Completed | COCC: EOF SS 50-SUBST-001 : LV Switchgear testing | 2017-12-02 | 2018-01-20 | 2018-12-22 | 2019-02-01
Act | 2AI141PC02400-08001 | Not Started | Completed | EOF: CT,PT Testing | 2017-12-02 | 2017-12-04 | 2018-12-22 | 2018-12-26
Act | 2AI141PC02400-08005 | Not Started | Completed | EOF: IR, Ductor testing | 2017-12-03 | 2017-12-05 | 2018-12-23 | 2019-01-11
Act | 2AI141PC02400-08010 | Not Started | Completed | EOF: Relay & Functional Testing | 2017-12-05 | 2017-12-07 | 2018-12-23 | 2018-12-26
Act | 2AI141PC02400-08015 | Not Started | Completed | EOF Primary Injection Testing | 2017-12-07 | 2017-12-09 | 2019-01-03 | 2019-01-13
Act | 2AI141PC02400-08025 | Not Started | Completed | EOF: Stability Testing | 2018-01-17 | 2018-01-20 | 2019-01-26 | 2019-02-01
Act | 2AI141PC02400-08020 | Not Started | Completed | EOF: Hi-pot Test | 2018-01-15 | 2018-01-17 | 2019-01-26 | 2019-02-01
Act | 2AI141PC02400-08000 | Not Started | Completed | COCC: EOF SS 50-SUBST-001 : LV Switchgear testing | 2017-12-02 | 2018-01-20 | 2018-12-22 | 2019-02-01
5 |  |  |  | COCC: EOF SS 50-SUBST-001 : 24V DC Battery Charger
Act | 2AI141PC02300-08001 | Not Started | Completed | COCC: Polarity check | 2017-10-05 | 2017-10-08 | 2019-03-23 | 2019-03-25
Act | 2AI141PC02300-08005 | Not Started | Completed | COCC: Charging test | 2017-10-08 | 2017-10-10 | 2019-03-24 | 2019-03-26
Act | 2AI141PC02300-08010 | Not Started | Completed | COCC: Discharging test | 2017-10-10 | 2017-10-12 | 2019-03-27 | 2019-03-29
Act | 2AI141PC02300 | Not Started | Completed | COCC: EOF SS 50-SUBST-001 : 24V DC Battery Charger | 2017-10-05 | 2017-10-12 | 2019-03-23 | 2019-03-29
Act | 2AI141PC02300-08000 | Not Started | Completed | COCC: EOF SS 50-SUBST-001 : 24V DC Battery Charger | 2017-10-05 | 2017-10-12 | 2019-03-23 | 2019-03-29
5 |  |  |  | COCC: EOF SS 50-SUBST-001 : Fire Alarm / Fire Suppression
5 |  |  |  | COCC: EOF SS 50-SUBST-001 : Lighting & Small Power
Act | 2AI141PC03100-08001 | Not Started | Completed | COCC: Continuity & IR testing | 2017-08-03 | 2017-08-12 | 2017-08-03 | 2017-08-12
Act | 2AI141PC03100-08005 | Not Started | Completed | COCC: Lux testing | 2017-08-12 | 2017-08-14 | 2017-08-12 | 2017-08-14
Act | 2AI141PC03100 | Not Started | Completed | COCC: EOF SS 50-SUBST-001 : Lighting & Small Power | 2017-08-03 | 2017-08-14 | 2017-08-03 | 2017-08-14
Act | 2AI141PC03100-08000 | Not Started | Completed | COCC: EOF SS 50-SUBST-001 : Lighting & Small Power | 2017-08-03 | 2017-08-14 | 2017-08-03 | 2017-08-14
5 |  |  |  | COCC: EOF SS 50-SUBST-001 : SS Earthing & Lightning
Act | 2AI141PC02100-08001 | Not Started | Completed | COCC: Continuity testing | 2017-09-06 | 2017-09-10 | 2019-04-08 | 2019-04-10
Act | 2AI141PC02100-08005 | Not Started | Completed | COCC: Earth resistance measurement | 2017-09-10 | 2017-09-13 | 2019-01-26 | 2019-02-01
Act | 2AI141PC02100 | Not Started | Completed | COCC: EOF SS 50-SUBST-001 : SS Earthing & Lightning | 2017-09-06 | 2017-09-13 | 2019-01-26 | 2019-04-10
Act | 2AI141PC02100-08000 | Not Started | Completed | COCC: EOF SS 50-SUBST-001 : SS Earthing & Lightning | 2017-09-06 | 2017-09-13 | 2019-01-26 | 2019-04-10
5 |  |  |  | COCC: EOF SS 50-SUBST-001 : Energize EDG Building 50-R-002
Act | 2AI141PC03000-08001 | Not Started | Completed | COCC: GCP Testing, Switch Gear Testing | 2017-09-04 | 2017-09-09 | 2019-04-08 | 2019-04-10
Act | 2AI141PC03000 | Not Started | In Progress | COCC: EOF SS 50-SUBST-001 : Energize EDG Building 50-R-002 | 2017-09-04 | 2017-09-13 | 2019-04-08
Act | 2AI141PC03000-08010 | Not Started | Not Started | COCC: EOF SS 50-SUBST-001 : Energize EDG Building 50-R-002 | 2017-09-09 | 2017-09-13
Act | 2AI141PC03000-08000 | Not Started | In Progress | COCC: EOF SS 50-SUBST-001 : Energize EDG Building 50-R-002 | 2017-09-04 | 2017-09-13 | 2019-04-08
5 |  |  |  | COCC: EOF SS 50-SUBST-001 : 110V AC UPS
Act | 2AI141PC02600-08001 | Not Started | Completed | COCC: Polarity check | 2017-11-15 | 2017-11-18 | 2019-01-27 | 2019-02-01
Act | 2AI141PC02600-08005 | Not Started | Completed | COCC: Charging test | 2017-11-18 | 2017-11-20 | 2019-01-27 | 2019-02-01
Act | 2AI141PC02600-08010 | Not Started | Completed | COCC: Discharging test | 2017-11-20 | 2017-11-22 | 2019-01-28 | 2019-02-02
Act | 2AI141PC02600 | Not Started | Completed | COCC: EOF SS 50-SUBST-001 : 110V AC UPS | 2017-11-15 | 2017-11-22 | 2019-01-27 | 2019-02-02
Act | 2AI141PC02600-08000 | Not Started | Completed | COCC: EOF SS 50-SUBST-001 : 110V AC UPS | 2017-11-15 | 2017-11-22 | 2019-01-27 | 2019-02-02
5 |  |  |  | COCC: EOF SS 50-SUBST-001 : Electrical Tie-ins for Permanent Power & Energize
Act | 2AI141PC02900-08001 | Not Started | Not Started | COCC: Incoming cables IR and continuity test | 2017-08-02 | 2017-08-07
Act | 2AI141PC02900-08005 | Not Started | Not Started | COCC: Incoming HV cables hipot testing | 2017-08-07 | 2017-08-12
Act | 2AI141PC02900 | Not Started | Not Started | COCC: EOF SS 50-SUBST-001 : Electrical Tie-ins for Permanent Power & Energize | 2017-08-02 | 2018-01-20
Act | 2AI141PC02900-08015 | Not Started | Not Started | EOF: Ready for Energisation of Substation 50-SUBST-001 | 2018-01-20 | 2018-01-20
Act | 2AI141PC02900-08010 | Not Started | Not Started | EOF: Cable Termination | 2017-08-12 | 2017-08-15
Act | 2AI141PC02900-08000 | Not Started | Not Started | COCC: EOF SS 50-SUBST-001 : Electrical Tie-ins for Permanent Power & Energize | 2017-08-02 | 2018-01-20
3 |  |  |  | PRE-COMMISSIONING - CRUDE OIL CONTROL CENTER (COCC) BUILDING
4 |  |  |  | COCC CCR Building : ICSS SAT
Act | 2AI141PC01000 | Not Started | Not Started | COCC CCR Building : ICSS SAT | 2017-11-27 | 2017-12-20
Act | 2AI141PC01000-08000 | Not Started | Not Started | COCC CCR Building : ICSS SAT | 2017-11-27 | 2017-12-20
2 |  |  |  | MECHANICAL COMPLETION
3 |  |  |  | LIQUIDATION of 'A' PUNCH ITEMS
4 |  |  |  | EOF - Liquidation of construction punch points ('A' items)
Act | 2AI000GE00300-08005 | Not Started | In Progress | EOF - Liquidation of construction punch points ('A' items) | 2017-11-26 | 2017-12-26 | 2018-05-15
Act | 2AI000GE00300 | Not Started | In Progress | EOF - Liquidation of construction punch points ('A' items) | 2017-11-26 | 2017-12-26 | 2018-05-15
3 |  |  |  | MECHANICAL COMPLETION CERTIFICATE
4 |  |  |  | Portion2 : EOF Mechanical Completion Certificate - Submission to Company & Approval by Company
Act | 2AI000GE01300-08000 | Not Started | Not Started | Portion2 : EOF Mechanical Completion Certificate - Submission to Company & Approval by Company | 2017-12-31 | 2018-01-31
Act | 2AI000GE01300 | Not Started | Not Started | Portion2 : EOF Mechanical Completion Certificate - Submission to Company & Approval by Company | 2017-12-31 | 2018-01-31
2 |  |  |  | CONSTRUCTION COMPLETION
3 |  |  |  | CONSTRUCTION COMPLETION CERTIFICATE
4 |  |  |  | Portion2 : EOF Construction Completion Certificate - Submission to Company & Approval by Company
Act | 2AI000PC00300-08000 | Not Started | Not Started | Portion2 : EOF Construction Completion Certificate - Submission to Company & Approval by Company | 2018-01-31 | 2018-01-31
Act | 2AI000PC00300 | Not Started | Not Started | Portion2 : EOF Construction Completion Certificate - Submission to Company & Approval by Company | 2018-01-31 | 2018-01-31