## Window Analysis
CMEI WORKS WINDOWS ANALYSIS
Sr | Programme No | Programme Name | Data Date | Culpability | Net Effect | Date Change |  | Cumulative Delay
[6 empty] | From | To
1 | WA-01A | WA-01A - Delay Event between 06-Aug-2015 to 30-Sep-2015 | 2015-08-06 | Contractor | 0 | 2018-01-31 | 2018-01-31 | 0
| WA-01B | WA-01B - Progress Update as of 30-Sep-2015 | 2015-09-30 | Sub-Contractor | 0 | 2018-01-31 | 2018-01-31
2 | WA-02A | WA-02A - Delay Event between 30-Sep-2015 to 30-Nov-2015 | 2015-09-30 | Contractor | 0 | 2018-01-31 | 2018-01-31 | 0
| WA-02B | WA-02B - Progress Update as of 30-Nov-2015 | 2015-11-30 | Sub-Contractor | 0 | 2018-01-31 | 2018-01-31
3 | WA-03A | WA-03A - Delay Event between 30-Nov-2015 to 22-Jan-2016 | 2015-11-30 | Contractor | 0 | 2018-01-31 | 2018-01-31 | 0
| WA-03B | WA-03B - Progress Update as of 22-Jan-2016 | 2016-01-22 | Sub-Contractor | 0 | 2018-01-31 | 2018-01-31
4 | WA-04A | WA-04A - Delay Event between 22-Jan-2016 to 25-Mar-2016 | 2016-01-22 | Contractor | 0 | 2018-01-31 | 2018-01-31 | 0
| WA-04B | WA-04B - Progress Update as of 25-Mar-2016 | 2016-03-25 | Sub-Contractor | 0 | 2018-01-31 | 2018-01-31
5 | WA-05A | WA-05A - Delay Event between 25-Mar-2016 to 27-May-2016 | 2016-03-25 | Contractor | 0 | 2018-01-31 | 2018-01-31 | 0
| WA-05B | WA-05B - Progress Update as of 27-May-2016 | 2016-05-27 | Sub-Contractor | 0 | 2018-01-31 | 2018-01-31
6 | WA-06A | WA-06A - Delay Event between 27-May-2016 to 22-Jul-2016 | 2016-05-27 | Contractor | 0 | 2018-01-31 | 2018-01-31 | 0
| WA-06B | WA-06B - Progress Update as of 22-Jul-2016 | 2016-07-22 | Sub-Contractor | 0 | 2018-01-31 | 2018-01-31
7 | WA-07A | WA-07A - Delay Event between 22-Jul-2016 to 23-Sep-2016 | 2016-07-22 | Contractor | 32 | 2018-01-31 | 2018-03-04 | 24
| WA-07B | WA-07B - Progress Update as of 23-Sep-2016 | 2016-09-23 | Sub-Contractor | -8 | 2018-03-04 | 2018-02-24
8 | WA-08A | WA-08A - Delay Event between 23-Sep-2016 to 25-Nov-2016 | 2016-09-23 | Contractor | 63 | 2018-02-24 | 2018-04-28 | 87
| WA-08B | WA-08B - Progress Update as of 25-Nov-2016 | 2016-11-25 | Sub-Contractor | 0 | 2018-04-28 | 2018-04-28
9 | WA-09A | WA-09A - Delay Event between 25-Nov-2016 to 27-Jan-2017 | 2016-11-25 | Contractor | 63 | 2018-04-28 | 2018-06-30 | 126
| WA-09B | WA-09B - Progress Update as of 27-Jan-2017 | 2017-01-27 | Sub-Contractor | -24 | 2018-06-30 | 2018-06-06
10 | WA-10A | WA-10A - Delay Event between 27-Jan-2017 to 24-Mar-2017 | 2017-01-27 | Contractor | 35 | 2018-06-06 | 2018-07-11 | 131
| WA-10B | WA-10B - Progress Update as of 24-Mar-2017 | 2017-03-24 | Sub-Contractor | -30 | 2018-07-11 | 2018-06-11
11 | WA-11A | WA-11A - Delay Event between 24-Mar-2017 to 26-May-2017 | 2017-03-24 | Contractor | 52 | 2018-06-11 | 2018-08-02 | 164
| WA-11B | WA-11B - Progress Update as of 26-May-2017 | 2017-05-26 | Sub-Contractor | -19 | 2018-08-02 | 2018-07-14
12 | WA-12A | WA-12A - Delay Event between 26-May-2017 to 28-Jul-2017 | 2017-05-26 | Contractor | 59 | 2018-07-14 | 2018-09-11 | 193
| WA-12B | WA-12B - Progress Update as of 28-Jul-2017 | 2017-07-28 | Sub-Contractor | -30 | 2018-09-11 | 2018-08-12
13 | WA-13A | WA-13A - Delay Event between 28-Jul-2017 to 22-Sep-2017 | 2017-07-28 | Contractor | 41 | 2018-08-12 | 2018-09-22 | 231
| WA-13B | WA-13B - Progress Update as of 22-Sep-2017 | 2017-09-22 | Sub-Contractor | -3 | 2018-09-22 | 2018-09-19
14 | WA-14A | WA-14A - Delay Event between 22-Sep-2017 to 24-Nov-2017 | 2017-09-22 | Contractor | 62 | 2018-09-19 | 2018-11-20 | 293
| WA-14B | WA-14B - Progress Update as of 24-Nov-2017 | 2017-11-24 | Sub-Contractor | 0 | 2018-11-20 | 2018-11-20
15 | WA-15A | WA-15A - Delay Event between 24-Nov-2017 to 26-Jan-2018 | 2017-11-24 | Contractor | 63 | 2018-11-20 | 2019-01-22 | 351
| WA-15B | WA-15B - Progress Update as of 26-Jan-2018 | 2018-01-26 | Sub-Contractor | -5 | 2019-01-22 | 2019-01-17
16 | WA-16A | WA-16A - Delay Event between 26-Jan-2018 to 23-Mar-2018 | 2018-01-26 | Contractor | 56 | 2019-01-17 | 2019-03-14 | 407
| WA-16B | WA-16B - Progress Update as of 23-Mar-2018 | 2018-03-23 | Sub-Contractor | 0 | 2019-03-14 | 2019-03-14
17 | WA-17A | WA-17A - Delay Event between 23-Mar-2018 to 25-May-2018 | 2018-03-23 | Contractor | 54 | 2019-03-14 | 2019-05-07 | 461
| WA-17B | WA-17B - Progress Update as of 25-May-2018 | 2018-05-25 | Sub-Contractor | 0 | 2019-05-07 | 2019-05-07
18 | WA-18A | WA-18A - Delay Event between 25-May-2018 to 27-Jul-2018 | 2018-05-25 | Contractor | 61 | 2019-05-07 | 2019-07-07 | 497
| WA-18B | WA-18B - Progress Update as of 27-Jul-2018 | 2018-07-27 | Sub-Contractor | -25 | 2019-07-07 | 2019-06-12
19 | WA-19A | WA-19A - Delay Event between 27-Jul-2018 to 28-Sep-2018 | 2018-07-27 | Contractor | 63 | 2019-06-12 | 2019-08-14 | 560
| WA-19B | WA-19B - Progress Update as of 28-Sep-2018 | 2018-09-28 | Sub-Contractor | 0 | 2019-08-14 | 2019-08-14
20 | WA-20A | WA-20A - Delay Event between 28-Sep-2018 to 23-Nov-2018 | 2018-09-28 | Contractor | 56 | 2019-08-14 | 2019-10-09 | 616
| WA-20B | WA-20B - Progress Update as of 23-Nov-2018 | 2018-11-23 | Sub-Contractor | 0 | 2019-10-09 | 2019-10-09
21 | WA-21A | WA-21A - Delay Event between 23-Nov-2018 to 25-Jan-2019 | 2018-11-23 | Contractor | 63 | 2019-10-09 | 2019-12-11 | 679
| WA-21B | WA-21B - Progress Update as of 25-Jan-2019 | 2019-01-25 | Sub-Contractor | 0 | 2019-12-11 | 2019-12-11
22 | WA-22A | WA-22A - Delay Event between 25-Jan-2019 to 29-Mar-2019 | 2019-01-25 | Contractor | 4 | 2019-12-11 | 2019-12-15 | 683
| WA-22B | WA-22B - Progress Update as of 29-Mar-2019 | 2019-03-29 | Sub-Contractor | 0 | 2019-12-15 | 2019-12-15
23 | WA-23A | WA-23A - Delay Event between 29-Mar-2019 to 26-Apr-2019 | 2019-03-29 | Contractor | 13 | 2019-12-15 | 2019-12-28 | 696
| WA-23B | WA-23B - Progress Update as of 26-Apr-2019 | 2019-04-26 | Sub-Contractor | 0 | 2019-12-28 | 2019-12-28
Contractor Delay |  |  |  |  | 840
Sub-Contractor Delays |  |  |  |  | 0
Sub-Contractor Mitigation |  |  |  |  | -144
Total Delay Period |  |  |  |  | 696
Formulas:
Data Date = [Data Date, row above]

## Sheet1 (hidden)
| W-01 TO W-06 | W-07 | W-08 | W-09 | W-10 | W-11 | W-12 | W-13 | W-14 | W-15 | W-16 | W-17 | W-18 | W-19 | W-20 | W-21 | W-22 | W-23
Contractor Delay (Days) |  | 32 | 63 | 63 | 35 | 52 | 59 | 41 | 62 | 63 | 56 | 54 | 61 | 63 | 56 | 63 | 4 | 13
Sub-Contractor Delay (Days) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sub-Contractor Mitigation (Days) |  | W-07: -8; W-09: -24; W-10: -30; W-11: -19; W-12: -30; W-13: -3; W-14: 0; W-15: -5; W-18: -25
Total Delay per window (Days) | 0 | 24 | 63 | 39 | 5 | 33 | 29 | 38 | 62 | 58 | 56 | 54 | 36 | 63 | 56 | 63 | 4 | 13
Cumulative Delay (Days) | 0 | 24 | 87 | 126 | 131 | 164 | 193 | 231 | 293 | 351 | 407 | 461 | 497 | 560 | 616 | 679 | 683 | 696

## Sheet2 (hidden)
| W-01 TO W-06 | W-07 | W-08 | W-09 | W-10 | W-11 | W-12 | W-13 | W-14 | W-15 | W-16 | W-17 | W-18 | W-19 | W-20 | W-21 | W-22 | W-23
Slip Chart | 2018-01-31 | 2018-02-24 | 2018-04-28 | 2018-06-06 | 2018-06-11 | 2018-07-14 | 2018-08-12 | 2018-09-19 | 2018-11-20 | 2019-01-17 | 2019-03-14 | 2019-05-07 | 2019-06-12 | 2019-08-14 | 2019-10-09 | 2019-12-11 | 2019-12-15 | 2019-12-28

## Sheet3 (hidden)
Activity ID | Start | Finish
WET-DE-01 Delay due to poor Weather Conditions LOCATION STF : New Tank Area | 2016-02-17 | 2016-12-03
WET-DE-02 Delay due to poor Weather Conditions LOCATION -STF MG-01 COCC | 2016-03-18 | 2017-07-10
WET-DE-03 Delay due to poor Weather Conditions LOCATION -STF | 2017-03-13 | 2017-11-30
WET-DE-04 Delay due to poor Weather Conditions ALL AREA | 2017-11-27 | 2018-11-24
WET-DE-05 Delay due to poor Weather Conditions LOCATION -621-D-94 Tank Area | 2016-05-16 | 2016-05-16
WET-DE-06 Delay due to poor Weather Conditions LOCATION -Mechanical Piping Work | 2017-02-23 | 2017-02-23
Delay in finishing of AFC drawings for Pipe Cable trench at new tank Area | 2016-05-10 | 2018-05-06 | 11, 12
Delay in Start of AFC drawings for Car Park Shelters other Misc Shelter | 2016-04-27 | 2017-05-31 | 10
Delay in finishing of AFC drawings for Demolition of Existing road and Existing | 2016-03-17 | 2017-05-22
Delay in construction of Subgrade lvl for Bund wall around storage tank 52-D-93 52-D-94 | 2016-08-25 | 2019-01-27
Delay in construction of cast catch basing Valve Pit for bund wall around storage tank | 2016-09-19 | 2018-10-22
Delay in finailizing engienering - distance betw Concrete pipe and Metal Pipe | 2016-11-20 | 2018-05-03 | 13, 16,
Delay due to delayed issue drawings Free issue material | 2017-02-19 | 2019-01-18 | 17, 18
EOD-DE-01 Delay due to finding of EOD LOCATION STF : New Tank Area | 2016-01-10 | 2016-02-17
DE-02 Delay due to finding of EOD LOCATION STF : STF :621-D-95 Tank Area | 2016-04-28 | 2016-04-28
Delay in Start due to Delay in Issuance of Pill Free Issue RTRP Pipe / fitting Materials Tools | 2017-02-02 | 2019-02-15 | 14, 15
Delay in Delivery of UG Piping/Cabling Material | 2016-11-23 | 2019-04-10 | 19, 20, 21, 22, 23
Delay due to Area Clearence Sub-contractor obstraction VO revised drawings in COCC area | 2016-04-14 | 2018-06-18 | 7, 8, 9
PMT-DE-01 Delay due to nonissuance of work permit LOCATION STF : EOF: STF/COCC | 2016-04-17 | 2016-04-17
PMT-DE-02 Delay due to nonissuance of work permit LOCATION ALL AREA | 2016-07-21 | 2016-07-21
PMT-DE-03 Delay due to nonissuance of work permit LOCATION MG-01 to SUBS-301 | 2017-02-21 | 2017-08-04
PMT-DE-04 Delay due to nonissuance of work permit LOCATION STF SUBS-303 | 2016-04-13 | 2016-04-13
Delay due to non issues of AFC darwings | 2016-04-25 | 2017-05-12
Delay in issue of free issue material | 2017-01-29 | 2018-07-21
GEN-DE-01 Delay due to Subcontarctor Approval All Area | 2015-10-20 | 2015-10-20
GEN-DE-02 Delay due to receipt of Design All Area | 2016-01-24 | 2016-01-24
CIVIL/ PIPING Area 621-D-93 621-D-93621-D-94 621-D-95 621-D-96 | 2018-07-25 | 2018-09-30
EIT Area COCC | 2018-01-20 | 2018-07-23
EIT Area SUBST-301 | 2018-01-01 | 2018-06-25
EIT Area SUBST-302 | 2018-01-08 | 2018-07-12
EIT Area SUBST-303 | 2017-06-13 | 2017-11-15
CIV-COCC-DE-01 Delay in Issuance of Drawings Area-COCC | 2017-03-21 | 2018-11-27
CIV-STF-DE-02 Delay in Issuance of Drawings Area-STF | 2016-04-25 | 2018-05-06
CP Area -STF | 2016-07-31 | 2016-07-31
ELC-COO-DE-04 Delay in receipt of Drawings Area COCC | 2017-05-04 | 2017-10-17
ELC-STF-DE-05 Delay in receipt of Drawings Area STF | 2017-06-07 | 2017-10-18
ELC-SBTN-DE-06 Delay in receipt of Drawings Area SUBSTATION | 2017-05-04 | 2017-10-17
ELC-MG1-DE-07 Delay in receipt of Draiwngs | 2017-06-07 | 2017-06-07
Instrumentation - Delay in Receipt of Drawings | 2017-06-01 | 2017-10-17
Piping - Delay in Receipt of Drawings | 2017-06-01 | 2017-11-20
Telecom - Delay in Receipt of Drawings | 2017-05-31 | 2017-07-24
PROCUREMENT Delay - Delay in delivery of Free issue material (Piping) | 2017-04-16 | 2018-05-15
CIVIL-CONSTRCUTION At different Areas | 2016-08-31 | 2017-08-15
CIVIL-CONSTRCUTION At STF Areas | 2016-02-18 | 2018-05-06
PIPING-CONSTRCUTION At Different Areas | 2016-12-29 | 2018-12-24
PIPING-CONSTRCUTION At STF Areas | 2017-05-06 | 2018-12-24
COCC-DE-01 Delay in issuing drawing AREA-COCC | 2017-03-02 | 2018-04-05
SS-DE-02 Delay in issuing drawing AREA-SS-301302303001 | 2016-12-05 | 2018-04-05
EDG-DE-03 Delay in issuing drawing AREA-EDG-301302303 | 2017-03-12 | 2018-05-05
INSTU-DE-04 Delay in issuing drawing | 2017-05-17 | 2017-06-01
TEL-DE-05 Delay in issuing drawing | 2017-07-19 | 2017-07-19
CP-DE-06 Delay in issuing drawing | 2016-07-31 | 2017-03-19
PROCUREMENT Delay - Delay in delivery of Free issue material | 2017-04-15 | 2018-12-23
ELECTRICAL-DE-01 Delay in receipt of Bulk Materials | 2017-05-03 | 2018-12-12
INSTRUMENTATION -DE-02 Delay in receipt of Bulk Materials | 2017-07-09 | 2018-12-23
TELECOM-DE-03 Delay in receipt of Bulk Materials | 2017-09-01 | 2017-12-30
Delay In issuing CP material Including cables | 2018-04-12 | 2018-09-25

## Sheet7 (hidden)
Activity ID | Start | Finish | time axis 2018-01-31 to 2020-01-04
Delay due to Area Clearence Sub-contractor obstraction VO revised drawings in COCC area | 2016-04-14 | 2018-06-18 | 7, 8, 9
Delay in Start of AFC drawings for Car Park Shelters other Misc Shelter | 2016-04-27 | 2017-05-31 | 10
Delay in finishing of AFC drawings for Pipe Cable trench at new tank Area | 2016-05-10 | 2018-05-06 | 11, 12
Delay in finailizing engienering - distance betw Concrete pipe and Metal Pipe | 2016-11-20 | 2018-05-03 | 13, 16,
Delay in Start due to Delay in Issuance of Pill Free Issue RTRP Pipe / fitting Materials Tools | 2017-02-02 | 2019-02-15 | 14, 15
Delay due to delayed issue drawings Free issue material | 2017-02-19 | 2019-01-18 | 17, 18
Delay in Delivery of UG Piping/Cabling Material | 2016-11-23 | 2019-04-10 | 19, 20, 21, 22, 23

## Sheet4 (hidden)
Window Name | Window Start | Window Finish | Window Name | Window Start | Window Finish
Window 1 | 2015-08-06 | 2015-09-30 | Window 13 | 2017-07-28 | 2017-09-22
Window 2 | 2015-09-30 | 2015-11-30 | Window 14 | 2017-09-22 | 2017-11-24
Window 3 | 2015-11-30 | 2016-01-22 | Window 15 | 2017-11-24 | 2018-01-26
Window 4 | 2016-01-22 | 2016-03-25 | Window 16 | 2018-01-26 | 2018-03-23
Window 5 | 2016-03-25 | 2016-05-27 | Window 17 | 2018-03-23 | 2018-05-25
Window 6 | 2016-05-27 | 2016-07-22 | Window 18 | 2018-05-25 | 2018-07-27
Window 7 | 2016-07-22 | 2016-09-23 | Window 19 | 2018-07-27 | 2018-09-28
Window 8 | 2016-09-23 | 2016-11-25 | Window 20 | 2018-09-28 | 2018-11-23
Window 9 | 2016-11-25 | 2017-01-27 | Window 21 | 2018-11-23 | 2019-01-25
Window 10 | 2017-01-27 | 2017-03-24 | Window 22 | 2019-01-25 | 2019-03-29
Window 11 | 2017-03-24 | 2017-05-26 | Window 23 | 2019-03-29 | 2019-04-26
Window 12 | 2017-05-26 | 2017-07-28

## Sheet3 (2) (hidden)
Delay Event Name | Event Start | Event Finish | Delay Event Name | Event Start | Event Finish
WET-DE-01 Delay due to poor Weather Conditions LOCATION STF : New Tank Area | 2016-02-17 | 2016-12-03 | EIT Area SUBST-302 | 2018-01-08 | 2018-07-12
WET-DE-02 Delay due to poor Weather Conditions LOCATION -STF MG-01 COCC | 2016-03-18 | 2017-07-10 | EIT Area SUBST-303 | 2017-06-13 | 2017-11-15
WET-DE-03 Delay due to poor Weather Conditions LOCATION -STF | 2017-03-13 | 2017-11-30 | CIV-COCC-DE-01 Delay in Issuance of Drawings Area-COCC | 2017-03-21 | 2018-11-27
WET-DE-04 Delay due to poor Weather Conditions ALL AREA | 2017-11-27 | 2018-11-24 | CIV-STF-DE-02 Delay in Issuance of Drawings Area-STF | 2016-04-25 | 2018-05-06
WET-DE-05 Delay due to poor Weather Conditions LOCATION -621-D-94 Tank Area | 2016-05-16 | 2016-05-16 | CP Area -STF | 2016-07-31 | 2016-07-31
WET-DE-06 Delay due to poor Weather Conditions LOCATION -Mechanical Piping Work | 2017-02-23 | 2017-02-23 | ELC-COO-DE-04 Delay in receipt of Drawings Area COCC | 2017-05-04 | 2017-10-17
Delay in finishing of AFC drawings for Pipe Cable trench at new tank Area | 2016-05-10 | 2018-05-06 | ELC-STF-DE-05 Delay in receipt of Drawings Area STF | 2017-06-07 | 2017-10-18
Delay in Start of AFC drawings for Car Park Shelters other Misc Shelter | 2016-04-27 | 2017-05-31 | ELC-SBTN-DE-06 Delay in receipt of Drawings Area SUBSTATION | 2017-05-04 | 2017-10-17
Delay in finishing of AFC drawings for Demolition of Existing road and Existing | 2016-03-17 | 2017-05-22 | ELC-MG1-DE-07 Delay in receipt of Draiwngs | 2017-06-07 | 2017-06-07
Delay in construction of Subgrade lvl for Bund wall around storage tank 52-D-93 52-D-94 | 2016-08-25 | 2019-01-27 | Instrumentation - Delay in Receipt of Drawings | 2017-06-01 | 2017-10-17
Delay in construction of cast catch basing Valve Pit for bund wall around storage tank | 2016-09-19 | 2018-10-22 | Piping - Delay in Receipt of Drawings | 2017-06-01 | 2017-11-20
Delay in finailizing engienering - distance betw Concrete pipe and Metal Pipe | 2016-11-20 | 2018-05-03 | Telecom - Delay in Receipt of Drawings | 2017-05-31 | 2017-07-24
Delay due to delayed issue drawings Free issue material | 2017-02-19 | 2019-01-18 | PROCUREMENT Delay - Delay in delivery of Free issue material (Piping) | 2017-04-16 | 2018-05-15
EOD-DE-01 Delay due to finding of EOD LOCATION STF : New Tank Area | 2016-01-10 | 2016-02-17 | CIVIL-CONSTRCUTION At different Areas | 2016-08-31 | 2017-08-15
DE-02 Delay due to finding of EOD LOCATION STF : STF :621-D-95 Tank Area | 2016-04-28 | 2016-04-28 | CIVIL-CONSTRCUTION At STF Areas | 2016-02-18 | 2018-05-06
Delay in Start due to Delay in Issuance of Pill Free Issue RTRP Pipe / fitting Materials Tools | 2017-02-02 | 2019-02-15 | PIPING-CONSTRCUTION At Different Areas | 2016-12-29 | 2018-12-24
Delay in Delivery of UG Piping/Cabling Material | 2016-11-23 | 2019-04-10 | PIPING-CONSTRCUTION At STF Areas | 2017-05-06 | 2018-12-24
Delay due to Area Clearence Sub-contractor obstraction VO revised drawings in COCC area | 2016-04-14 | 2018-06-18 | COCC-DE-01 Delay in issuing drawing AREA-COCC | 2017-03-02 | 2018-04-05
PMT-DE-01 Delay due to nonissuance of work permit LOCATION STF : EOF: STF/COCC | 2016-04-17 | 2016-04-17 | SS-DE-02 Delay in issuing drawing AREA-SS-301302303001 | 2016-12-05 | 2018-04-05
PMT-DE-02 Delay due to nonissuance of work permit LOCATION ALL AREA | 2016-07-21 | 2016-07-21 | EDG-DE-03 Delay in issuing drawing AREA-EDG-301302303 | 2017-03-12 | 2018-05-05
PMT-DE-03 Delay due to nonissuance of work permit LOCATION MG-01 to SUBS-301 | 2017-02-21 | 2017-08-04 | INSTU-DE-04 Delay in issuing drawing | 2017-05-17 | 2017-06-01
PMT-DE-04 Delay due to nonissuance of work permit LOCATION STF SUBS-303 | 2016-04-13 | 2016-04-13 | TEL-DE-05 Delay in issuing drawing | 2017-07-19 | 2017-07-19
Delay due to non issues of AFC darwings | 2016-04-25 | 2017-05-12 | CP-DE-06 Delay in issuing drawing | 2016-07-31 | 2017-03-19
Delay in issue of free issue material | 2017-01-29 | 2018-07-21 | PROCUREMENT Delay - Delay in delivery of Free issue material | 2017-04-15 | 2018-12-23
GEN-DE-01 Delay due to Subcontarctor Approval All Area | 2015-10-20 | 2015-10-20 | ELECTRICAL-DE-01 Delay in receipt of Bulk Materials | 2017-05-03 | 2018-12-12
GEN-DE-02 Delay due to receipt of Design All Area | 2016-01-24 | 2016-01-24 | INSTRUMENTATION -DE-02 Delay in receipt of Bulk Materials | 2017-07-09 | 2018-12-23
CIVIL/ PIPING Area 621-D-93 621-D-93621-D-94 621-D-95 621-D-96 | 2018-07-25 | 2018-09-30 | TELECOM-DE-03 Delay in receipt of Bulk Materials | 2017-09-01 | 2017-12-30
EIT Area COCC | 2018-01-20 | 2018-07-23 | Delay In issuing CP material Including cables | 2018-04-12 | 2018-09-25
EIT Area SUBST-301 | 2018-01-01 | 2018-06-25

## Sheet6 (hidden)
Window Period | Delay Days
1 | 0 | Window Period | Window 1 to 6 | Window 7 | Window 8 | Window 9 | Window 10 | Window 11 | Window 12 | Window 13 | Window 14 | Window 15 | Window 16 | Window 17 | Window 18 | Window 19 | Window 20 | Window 21 | Window 22 | Window 23
2 | 0 | Delay Days | 0 | 24 | 63 | 39 | 5 | 33 | 29 | 38 | 62 | 58 | 56 | 54 | 36 | 63 | 56 | 63 | 4 | 13
3 | 0
4 | 0
5 | 0
6 | 0
7 | 24
8 | 63
9 | 39
10 | 5
11 | 33
12 | 29
13 | 38
14 | 62
15 | 58
16 | 56
17 | 54
18 | 36
19 | 63
20 | 56
21 | 63
22 | 4
23 | 13

## Sheet5 (hidden)
Project ID | Project Name | Total Activities | Data Date | Schedule Finish | Baseline
WA-01A | WA-01A - Delay Event between 06-Aug-15 to 30-Sep-15 | 0 | 2015-08-06 | 2018-01-31 | <Current Project>
WA-01B | WA-01B - Progress Update as of 30-Sep-15 | 0 | 2015-09-30 | 2018-01-31 | <Current Project>
WA-02A | WA-02A - Delay Event between 30-Sep-15 to 30-Nov-15 | 0 | 2015-09-30 | 2018-01-31 | <Current Project>
WA-02B | WA-02B - Progress Update as of 30-Nov-15 | 0 | 2015-11-30 | 2018-01-31 | <Current Project>
WA-03A | WA-03A - Delay Event between 30-Nov-15 to 22-Jan-16 | 0 | 2015-11-30 | 2018-01-31 | <Current Project>
WA-03B | WA-03B - Progress Update as of 22-Jan-16 | 0 | 2016-01-22 | 2018-01-31 | <Current Project>
WA-04A | WA-04A - Delay Event between 22-Jan-16 to 25-Mar-16 | 0 | 2016-01-22 | 2018-01-31 | <Current Project>
WA-04B | WA-04B - Progress Update as of 25-Mar-16 | 0 | 2016-03-25 | 2018-01-31 | <Current Project>
WA-05A | WA-05A - Delay Event between 25-Mar-16 to 27-May-16 | 0 | 2016-03-25 | 2018-01-31 | <Current Project>
WA-05B | WA-05B - Progress Update as of 27-May-16 | 0 | 2016-05-27 | 2018-01-31 | <Current Project>
WA-06A | WA-06A - Delay Event between 27-May-16 to 22-Jul-16 | 0 | 2016-05-27 | 2018-01-31 | <Current Project>
WA-06B | WA-06B - Progress Update as of 22-Jul-16 | 0 | 2016-07-22 | 2018-01-31 | <Current Project>
WA-07A | WA-07A - Delay Event between 22-Jul-16 to 23-Sep-16 | 0 | 2016-07-22 | 2018-03-04 | <Current Project>
WA-07B | WA-07B - Progress Update as of 23-Sep-16 | 0 | 2016-09-23 | 2018-02-24 | <Current Project>
WA-08A | WA-08A - Delay Event between 23-Sep-16 to 25-Nov-16 | 0 | 2016-09-23 | 2018-04-28 | <Current Project>
WA-08B | WA-08B - Progress Update as of 25-Nov-16 | 0 | 2016-11-25 | 2018-04-28 | <Current Project>
WA-09A | WA-09A - Delay Event between 25-Nov-16 to 27-Jan-17 | 0 | 2016-11-25 | 2018-06-30 | <Current Project>
WA-09B | WA-09B - Progress Update as of 27-Jan-17 | 0 | 2017-01-27 | 2018-06-06 | <Current Project>
WA-10A | WA-10A - Delay Event between 27-Jan-17 to 24-Mar-17 | 0 | 2017-01-27 | 2018-07-11 | <Current Project>
WA-10B | WA-10B - Progress Update as of 24-Mar-17 | 0 | 2017-03-24 | 2018-06-11 | <Current Project>
WA-11A | WA-11A - Delay Event between 24-Mar-17 to 26-May-17 | 0 | 2017-03-24 | 2018-08-02 | <Current Project>
WA-11B | WA-11B - Progress Update as of 26-May-17 | 0 | 2017-05-26 | 2018-07-14 | <Current Project>
WA-12A | WA-12A - Delay Event between 26-May-17 to 28-Jul-17 | 0 | 2017-05-26 | 2018-09-11 | <Current Project>
WA-12B | WA-12B - Progress Update as of 28-Jul-17 | 0 | 2017-07-28 | 2018-08-12 | <Current Project>
WA-13A | WA-13A - Delay Event between 28-Jul-17 to 22-Sep-17 | 0 | 2017-07-28 | 2018-09-22 | <Current Project>
WA-13B | WA-13B - Progress Update as of 22-Sep-17 | 0 | 2017-09-22 | 2018-09-19 | <Current Project>
WA-14A | WA-14A - Delay Event between 22-Sep-17 to 24-Nov-17 | 0 | 2017-09-22 | 2018-11-20 | <Current Project>
WA-14B | WA-14B - Progress Update as of 24-Nov-17 | 0 | 2017-11-24 | 2018-11-20 | <Current Project>
WA-15A | WA-15A - Delay Event between 24-Nov-17 to 26-Jan-18 | 0 | 2017-11-24 | 2019-01-22 | <Current Project>
WA-15B | WA-15B - Progress Update as of 26-Jan-18 | 0 | 2018-01-26 | 2019-01-17 | <Current Project>
WA-16A | WA-16A - Delay Event between 26-Jan-18 to 23-Mar-18 | 0 | 2018-01-26 | 2019-03-14 | <Current Project>
WA-16B | WA-16B - Progress Update as of 23-Mar-18 | 0 | 2018-03-23 | 2019-03-14 | <Current Project>
WA-17A | WA-17A - Delay Event between 23-Mar-18 to 25-May-18 | 0 | 2018-03-23 | 2019-05-07 | <Current Project>
WA-17B | WA-17B - Progress Update as of 25-May-18 | 0 | 2018-05-25 | 2019-05-07 | <Current Project>
WA-18A | WA-18A - Delay Event between 25-May-18 to 27-Jul-18 | 0 | 2018-05-25 | 2019-07-07 | <Current Project>
WA-18B | WA-18B - Progress Update as of 27-Jul-18 | 0 | 2018-07-27 | 2019-06-12 | <Current Project>
WA-19A | WA-19A - Delay Event between 27-Jul-18 to 28-Sep-18 | 0 | 2018-07-27 | 2019-08-14 | <Current Project>
WA-19B | WA-19B - Progress Update as of 28-Sep-18 | 0 | 2018-09-28 | 2019-08-14 | <Current Project>
WA-20A | WA-20A - Delay Event between 28-Sep-18 to 23-Nov-18 | 0 | 2018-09-28 | 2019-10-09 | <Current Project>
WA-20B | WA-20B - Progress Update as of 23-Nov-18 | 0 | 2018-11-23 | 2019-10-09 | <Current Project>
WA-21A | WA-21A - Delay Event between 23-Nov-18 to 25-Jan-19 | 0 | 2018-11-23 | 2019-12-11 | <Current Project>
WA-21B | WA-21B - Progress Update as of 25-Jan-19 | 0 | 2019-01-25 | 2019-12-11 | <Current Project>
WA-22A | WA-22A - Delay Event between 25-Jan-19 to 29-Mar-19 | 0 | 2019-01-25 | 2019-12-15 | <Current Project>
WA-22B | WA-22B - Progress Update as of 29-Mar-19 | 0 | 2019-03-29 | 2019-12-15 | <Current Project>
WA-23A | WA-23A - Delay Event between 29-Mar-2019 to 26-Apr-2019 | 0 | 2019-03-29 | 2019-12-28 | <Current Project>
WA-23B | WA-23B - Progress Update as of 26-Apr-2019 | 0 | 2019-04-26 | 2019-12-28 | <Current Project>