## Concurrency Report
|  |  |  | Practical Impact |  | Pull Back Impact | [15 empty] | Practical Impact |  | Pull Back Impact | [34 empty] | Practical Impact |  | Pull Back Impact | [22 empty] | Practical Impact |  | Pull Back Impact | [5 empty] | Practical Impact |  | Pull Back Impact | [19 empty] | Practical Impact |  | Pull Back Impact | [17 empty] | Practical Impact |  | Pull Back Impact | [21 empty] | Practical Impact |  | Pull Back Impact | [33 empty] | Practical Impact |  | Pull Back Impact | [31 empty] | Practical Impact |  | Pull Back Impact | [30 empty] | Practical Impact |  | Pull Back Impact | [29 empty] | Practical Impact |  | Pull Back Impact | [20 empty] | Practical Impact |  | Pull Back Impact | [24 empty] | Practical Impact |  | Pull Back Impact | [40 empty] | Practical Impact |  | Pull Back Impact | [34 empty] | Practical Impact |  | Pull Back Impact |  |  |  |  | Practical Impact |  | Pull Back Impact
|  |  | Client | 2018-03-04 | 32 | 2018-02-24 | 24 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Client | 2018-04-28 | 63 | 2018-04-28 | 63 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Client | 2018-06-30 | 63 | 2018-06-06 | 39 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Client | 2018-07-11 | 35 | 2018-06-11 | 5 | 1 | 1 | 1 | Client | 2018-08-02 | 52 | 2018-07-14 | 33 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Client | 2018-09-11 | 59 | 2018-08-12 | 29 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Client | 2018-09-22 | 41 | 2018-09-19 | 38 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Client | 2018-11-20 | 62 | 2018-11-20 | 62 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Client | 2019-01-22 | 63 | 2019-01-17 | 58 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Client | 2019-03-14 | 56 | 2019-03-14 | 56 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Client | 2019-05-07 | 54 | 2019-05-07 | 54 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Client | 2019-07-07 | 61 | 2019-06-12 | 36 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Client | 2019-08-14 | 63 | 2019-08-14 | 63 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Client | 2019-10-09 | 56 | 2019-10-09 | 56 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Client | 2019-12-11 | 63 | 2019-12-11 | 63 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Client | 2019-12-15 | 4 | 2019-12-15 | 4 | 1 | 1 | Client | 2019-12-28 | 13 | 2019-12-28 | 13 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Contractor |  | 0 |  | 0 | C | C | C | C | C | C | C | C | C | C | C | C | C | Contractor |  | 0 |  | 0 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | Contractor |  | 0 |  | 0 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | Contractor |  | 0 |  | 0 | C | C | C | Contractor |  | 0 |  | 0 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | Contractor |  | 0 |  | 0 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | Contractor |  | 0 |  | 0 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | Contractor |  | 0 |  | 0 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | Contractor |  | 0 |  | 0 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | Contractor |  | 0 |  | 0 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | Contractor |  | 0 |  | 0 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | Contractor |  | 0 |  | 0 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | Contractor |  | 0 |  | 0 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | Contractor |  | 0 |  | 0 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | Contractor |  | 0 |  | 0 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | Contractor |  | 0 |  | 0 | C | C | Contractor |  | 0 |  | 0 | C | C | C | C | C | C | C
| 696 | Total Compensable Delay | Compensable Delay |  |  |  | 24 | [13 empty] | Compensable Delay |  |  |  | 63 | [32 empty] | Compensable Delay |  |  |  | 39 | [20 empty] | Compensable Delay |  |  |  | 5 |  |  |  | Compensable Delay |  |  |  | 33 | [17 empty] | Compensable Delay |  |  |  | 29 | [15 empty] | Compensable Delay |  |  |  | 38 | [19 empty] | Compensable Delay |  |  |  | 62 | [31 empty] | Compensable Delay |  |  |  | 58 | [29 empty] | Compensable Delay |  |  |  | 56 | [28 empty] | Compensable Delay |  |  |  | 54 | [27 empty] | Compensable Delay |  |  |  | 36 | [18 empty] | Compensable Delay |  |  |  | 63 | [22 empty] | Compensable Delay |  |  |  | 56 | [38 empty] | Compensable Delay |  |  |  | 63 | [32 empty] | Compensable Delay |  |  |  | 4 |  |  | Compensable Delay |  |  |  | 13
| 0 | Total Non-Compensable Delay | Non-Compensable Delay |  |  |  | 0 | [13 empty] | Non-Compensable Delay |  |  |  | 0 | [32 empty] | Non-Compensable Delay |  |  |  | 0 | [20 empty] | Non-Compensable Delay |  |  |  | 0 |  |  |  | Non-Compensable Delay |  |  |  | 0 | [17 empty] | Non-Compensable Delay |  |  |  | 0 | [15 empty] | Non-Compensable Delay |  |  |  | 0 | [19 empty] | Non-Compensable Delay |  |  |  | 0 | [31 empty] | Non-Compensable Delay |  |  |  | 0 | [29 empty] | Non-Compensable Delay |  |  |  | 0 | [28 empty] | Non-Compensable Delay |  |  |  | 0 | [27 empty] | Non-Compensable Delay |  |  |  | 0 | [18 empty] | Non-Compensable Delay |  |  |  | 0 | [22 empty] | Non-Compensable Delay |  |  |  | 0 | [38 empty] | Non-Compensable Delay |  |  |  | 0 | [32 empty] | Non-Compensable Delay |  |  |  | 0 |  |  | Non-Compensable Delay |  |  |  | 0
|  |  | Project Finish Date Shift | 2018-01-31 |  | 2018-02-24 | [14 empty] | Project Finish Date Shift | 2018-02-24 |  | 2018-04-28 | [33 empty] | Project Finish Date Shift | 2018-04-28 |  | 2018-06-06 | [21 empty] | Project Finish Date Shift | 2018-06-06 |  | 2018-06-11 |  |  |  |  | Project Finish Date Shift | 2018-06-11 |  | 2018-07-14 | [18 empty] | Project Finish Date Shift | 2018-07-14 |  | 2018-08-12 | [16 empty] | Project Finish Date Shift | 2018-08-12 |  | 2018-09-19 | [20 empty] | Project Finish Date Shift | 2018-09-19 |  | 2018-11-20 | [32 empty] | Project Finish Date Shift | 2018-11-20 |  | 2019-01-17 | [30 empty] | Project Finish Date Shift | 2019-01-17 |  | 2019-03-14 | [29 empty] | Project Finish Date Shift | 2019-03-14 |  | 2019-05-07 | [28 empty] | Project Finish Date Shift | 2019-05-07 |  | 2019-06-12 | [19 empty] | Project Finish Date Shift | 2019-06-12 |  | 2019-08-14 | [23 empty] | Project Finish Date Shift | 2019-08-14 |  | 2019-10-09 | [39 empty] | Project Finish Date Shift | 2019-10-09 |  | 2019-12-11 | [33 empty] | Project Finish Date Shift | 2019-12-11 |  | 2019-12-15 |  |  |  | Project Finish Date Shift | 2019-12-15 |  | 2019-12-28
|  |  | Window Start |  | 2016-07-22 | [15 empty] | Window Start |  | 2016-09-23 | [34 empty] | Window Start |  | 2016-11-25 | [22 empty] | Window Start |  | 2017-01-27 | [5 empty] | Window Start |  | 2017-03-24 | [19 empty] | Window Start |  | 2017-05-26 | [17 empty] | Window Start |  | 2017-07-28 | [21 empty] | Window Start |  | 2017-09-22 | [33 empty] | Window Start |  | 2017-11-24 | [31 empty] | Window Start |  | 2018-01-26 | [30 empty] | Window Start |  | 2018-03-23 | [29 empty] | Window Start |  | 2018-05-25 | [20 empty] | Window Start |  | 2018-07-27 | [24 empty] | Window Start |  | 2018-09-28 | [40 empty] | Window Start |  | 2018-11-23 | [34 empty] | Window Start |  | 2019-01-25 |  |  |  |  | Window Start |  | 2019-03-29
|  |  | Window Finish |  | 2016-09-23 | [15 empty] | Window Finish |  | 2016-11-25 | [34 empty] | Window Finish |  | 2017-01-27 | [22 empty] | Window Finish |  | 2017-03-24 | [5 empty] | Window Finish |  | 2017-05-26 | [19 empty] | Window Finish |  | 2017-07-28 | [17 empty] | Window Finish |  | 2017-09-22 | [21 empty] | Window Finish |  | 2017-11-24 | [33 empty] | Window Finish |  | 2018-01-26 | [31 empty] | Window Finish |  | 2018-03-23 | [30 empty] | Window Finish |  | 2018-05-25 | [29 empty] | Window Finish |  | 2018-07-27 | [20 empty] | Window Finish |  | 2018-09-28 | [24 empty] | Window Finish |  | 2018-11-23 | [40 empty] | Window Finish |  | 2019-01-25 | [34 empty] | Window Finish |  | 2019-03-29 |  |  |  |  | Window Finish |  | 2019-04-26
|  |  | TIME SLICE 07 | [17 empty] | TIME SLICE 08 | [36 empty] | TIME SLICE 09 | [24 empty] | TIME SLICE 10 | [7 empty] | TIME SLICE 11 | [21 empty] | TIME SLICE 12 | [19 empty] | TIME SLICE 13 | [23 empty] | TIME SLICE 14 | [35 empty] | TIME SLICE 15 | [33 empty] | TIME SLICE 16 | [32 empty] | TIME SLICE 17 | [31 empty] | TIME SLICE 18 | [22 empty] | TIME SLICE 19 | [26 empty] | TIME SLICE 20 | [42 empty] | TIME SLICE 21 | [36 empty] | TIME SLICE 22 | [6 empty] | TIME SLICE 23
Level | Activity ID | Activity Name | Culpability By | Practical Impact |  | Pull Back Impact | [14 empty] | Culpability By | Practical Impact |  | Pull Back Impact | [33 empty] | Culpability By | Practical Impact |  | Pull Back Impact | [21 empty] | Culpability By | Practical Impact |  | Pull Back Impact |  |  |  |  | Culpability By | Practical Impact |  | Pull Back Impact | [18 empty] | Culpability By | Practical Impact |  | Pull Back Impact | [16 empty] | Culpability By | Practical Impact |  | Pull Back Impact | [20 empty] | Culpability By | Practical Impact |  | Pull Back Impact | [32 empty] | Culpability By | Practical Impact |  | Pull Back Impact | [30 empty] | Culpability By | Practical Impact |  | Pull Back Impact | [29 empty] | Culpability By | Practical Impact |  | Pull Back Impact | [28 empty] | Culpability By | Practical Impact |  | Pull Back Impact | [19 empty] | Culpability By | Practical Impact |  | Pull Back Impact | [23 empty] | Culpability By | Practical Impact |  | Pull Back Impact | [39 empty] | Culpability By | Practical Impact |  | Pull Back Impact | [33 empty] | Culpability By | Practical Impact |  | Pull Back Impact |  |  |  | Culpability By | Practical Impact |  | Pull Back Impact
|  |  |  | Impact Date | Impact Day | Impact Date | Impact Day | 2018-01-31 | 2018-02-02 | 2018-02-04 | 2018-02-06 | 2018-02-08 | 2018-02-10 | 2018-02-12 | 2018-02-14 | 2018-02-16 | 2018-02-18 | 2018-02-20 | 2018-02-22 | 2018-02-24 |  | Impact Date | Impact Day | Impact Date | Impact Day | 2018-02-26 | 2018-02-28 | 2018-03-02 | 2018-03-04 | 2018-03-06 | 2018-03-08 | 2018-03-10 | 2018-03-12 | 2018-03-14 | 2018-03-16 | 2018-03-18 | 2018-03-20 | 2018-03-22 | 2018-03-24 | 2018-03-26 | 2018-03-28 | 2018-03-30 | 2018-04-01 | 2018-04-03 | 2018-04-05 | 2018-04-07 | 2018-04-09 | 2018-04-11 | 2018-04-13 | 2018-04-15 | 2018-04-17 | 2018-04-19 | 2018-04-21 | 2018-04-23 | 2018-04-25 | 2018-04-27 | 2018-04-28 |  | Impact Date | Impact Day | Impact Date | Impact Day | 2018-04-30 | 2018-05-02 | 2018-05-04 | 2018-05-06 | 2018-05-08 | 2018-05-10 | 2018-05-12 | 2018-05-14 | 2018-05-16 | 2018-05-18 | 2018-05-20 | 2018-05-22 | 2018-05-24 | 2018-05-26 | 2018-05-28 | 2018-05-30 | 2018-06-01 | 2018-06-03 | 2018-06-05 | 2018-06-06 |  | Impact Date | Impact Day | Impact Date | Impact Day | 2018-06-08 | 2018-06-10 | 2018-06-11 |  | Impact Date | Impact Day | Impact Date | Impact Day | 2018-06-13 | 2018-06-15 | 2018-06-17 | 2018-06-19 | 2018-06-21 | 2018-06-23 | 2018-06-25 | 2018-06-27 | 2018-06-29 | 2018-07-01 | 2018-07-03 | 2018-07-05 | 2018-07-07 | 2018-07-09 | 2018-07-11 | 2018-07-13 | 2018-07-14 |  | Impact Date | Impact Day | Impact Date | Impact Day | 2018-07-16 | 2018-07-18 | 2018-07-20 | 2018-07-22 | 2018-07-24 | 2018-07-26 | 2018-07-28 | 2018-07-30 | 2018-08-01 | 2018-08-03 | 2018-08-05 | 2018-08-07 | 2018-08-09 | 2018-08-11 | 2018-08-12 |  | Impact Date | Impact Day | Impact Date | Impact Day | 2018-08-14 | 2018-08-16 | 2018-08-18 | 2018-08-20 | 2018-08-22 | 2018-08-24 | 2018-08-26 | 2018-08-28 | 2018-08-30 | 2018-09-01 | 2018-09-03 | 2018-09-05 | 2018-09-07 | 2018-09-09 | 2018-09-11 | 2018-09-13 | 2018-09-15 | 2018-09-17 | 2018-09-19 |  | Impact Date | Impact Day | Impact Date | Impact Day | 2018-09-21 | 2018-09-23 | 2018-09-25 | 2018-09-27 | 2018-09-29 | 2018-10-01 | 2018-10-03 | 2018-10-05 | 2018-10-07 | 2018-10-09 | 2018-10-11 | 2018-10-13 | 2018-10-15 | 2018-10-17 | 2018-10-19 | 2018-10-21 | 2018-10-23 | 2018-10-25 | 2018-10-27 | 2018-10-29 | 2018-10-31 | 2018-11-02 | 2018-11-04 | 2018-11-06 | 2018-11-08 | 2018-11-10 | 2018-11-12 | 2018-11-14 | 2018-11-16 | 2018-11-18 | 2018-11-20 |  | Impact Date | Impact Day | Impact Date | Impact Day | 2018-11-22 | 2018-11-24 | 2018-11-26 | 2018-11-28 | 2018-11-30 | 2018-12-02 | 2018-12-04 | 2018-12-06 | 2018-12-08 | 2018-12-10 | 2018-12-12 | 2018-12-14 | 2018-12-16 | 2018-12-18 | 2018-12-20 | 2018-12-22 | 2018-12-24 | 2018-12-26 | 2018-12-28 | 2018-12-30 | 2019-01-01 | 2019-01-03 | 2019-01-05 | 2019-01-07 | 2019-01-09 | 2019-01-11 | 2019-01-13 | 2019-01-15 | 2019-01-17 |  | Impact Date | Impact Day | Impact Date | Impact Day | 2019-01-19 | 2019-01-21 | 2019-01-23 | 2019-01-25 | 2019-01-27 | 2019-01-29 | 2019-01-31 | 2019-02-02 | 2019-02-04 | 2019-02-06 | 2019-02-08 | 2019-02-10 | 2019-02-12 | 2019-02-14 | 2019-02-16 | 2019-02-18 | 2019-02-20 | 2019-02-22 | 2019-02-24 | 2019-02-26 | 2019-02-28 | 2019-03-02 | 2019-03-04 | 2019-03-06 | 2019-03-08 | 2019-03-10 | 2019-03-12 | 2019-03-14 |  | Impact Date | Impact Day | Impact Date | Impact Day | 2019-03-16 | 2019-03-18 | 2019-03-20 | 2019-03-22 | 2019-03-24 | 2019-03-26 | 2019-03-28 | 2019-03-30 | 2019-04-01 | 2019-04-03 | 2019-04-05 | 2019-04-07 | 2019-04-09 | 2019-04-11 | 2019-04-13 | 2019-04-15 | 2019-04-17 | 2019-04-19 | 2019-04-21 | 2019-04-23 | 2019-04-25 | 2019-04-27 | 2019-04-29 | 2019-05-01 | 2019-05-03 | 2019-05-05 | 2019-05-07 |  | Impact Date | Impact Day | Impact Date | Impact Day | 2019-05-09 | 2019-05-11 | 2019-05-13 | 2019-05-15 | 2019-05-17 | 2019-05-19 | 2019-05-21 | 2019-05-23 | 2019-05-25 | 2019-05-27 | 2019-05-29 | 2019-05-31 | 2019-06-02 | 2019-06-04 | 2019-06-06 | 2019-06-08 | 2019-06-10 | 2019-06-12 |  | Impact Date | Impact Day | Impact Date | Impact Day | 2019-06-14 | 2019-06-16 | 2019-06-18 | 2019-06-20 | 2019-06-22 | 2019-06-24 | 2019-06-26 | 2019-06-28 | 2019-06-30 | 2019-07-02 | 2019-07-04 | 2019-07-06 | 2019-07-08 | 2019-07-10 | 2019-07-12 | 2019-07-14 | 2019-07-16 | 2019-07-18 | 2019-07-20 | 2019-07-22 | 2019-07-24 | 2019-07-25 |  | Impact Date | Impact Day | Impact Date | Impact Day | 2019-07-27 | 2019-07-29 | 2019-07-31 | 2019-08-02 | 2019-08-04 | 2019-08-06 | 2019-08-08 | 2019-08-10 | 2019-08-12 | 2019-08-14 | 2019-08-16 | 2019-08-18 | 2019-08-20 | 2019-08-22 | 2019-08-24 | 2019-08-26 | 2019-08-28 | 2019-08-30 | 2019-09-01 | 2019-09-03 | 2019-09-05 | 2019-09-07 | 2019-09-09 | 2019-09-11 | 2019-09-13 | 2019-09-15 | 2019-09-17 | 2019-09-19 | 2019-09-21 | 2019-09-23 | 2019-09-25 | 2019-09-27 | 2019-09-29 | 2019-10-01 | 2019-10-03 | 2019-10-05 | 2019-10-07 | 2019-10-09 |  | Impact Date | Impact Day | Impact Date | Impact Day | 2019-10-11 | 2019-10-13 | 2019-10-15 | 2019-10-17 | 2019-10-19 | 2019-10-21 | 2019-10-23 | 2019-10-25 | 2019-10-27 | 2019-10-29 | 2019-10-31 | 2019-11-02 | 2019-11-04 | 2019-11-06 | 2019-11-08 | 2019-11-10 | 2019-11-12 | 2019-11-14 | 2019-11-16 | 2019-11-18 | 2019-11-20 | 2019-11-22 | 2019-11-24 | 2019-11-26 | 2019-11-28 | 2019-11-30 | 2019-12-02 | 2019-12-04 | 2019-12-06 | 2019-12-08 | 2019-12-10 | 2019-12-11 |  | Impact Date | Impact Day | Impact Date | Impact Day | 2019-12-13 | 2019-12-15 |  | Impact Date | Impact Day | Impact Date | Impact Day | 2019-12-17 | 2019-12-19 | 2019-12-21 | 2019-12-23 | 2019-12-25 | 2019-12-27 | 2019-12-28
0 |  | CMEI WORKS FOR EOF PACKAGE
1 |  | DELAY EVENT
2 |  | Delay in finishing of AFC drawings for Pipe Cable trench at new tank Area
Act | DE25-1000 | Delay in finishing of AFC drawings for Pipe Cable trench at new tank Area | [88 empty] | Client | 2018-08-02 | 52 | 2018-07-14 | 33 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Client | 2018-09-11 | 59 | 2018-08-12 | 29 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Client | 2018-09-19 | 38 | 2018-09-19 | 38 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Client | 2018-11-11 | 53 | 2018-11-11 | 53 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | Client | 2019-01-13 | 54 | 2019-01-13 | 54 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | Client | 2019-03-10 | 52 | 2019-03-10 | 52 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | [32 empty] | Client | 2019-07-07 | 61 | 2019-06-12 | 36 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [27 empty] | Client | 2019-10-01 | 48 | 2019-10-01 | 48 | bar: 2019-07-27 to 2019-10-09
2 |  | Delay in Start of AFC drawings for Car Park Shelters other Misc Shelter
Act | DE26-1000 | Delay in Start of AFC drawings for Car Park Shelters other Misc Shelter | [18 empty] | Client | 2018-03-18 | 22 | 2018-03-18 | 22 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | Client | 2018-05-20 | 22 | 2018-05-20 | 22 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | Client | 2018-07-11 | 35 | 2018-06-11 | 5 | 1 | 1 | 1 | Client | 2018-07-01 | 20 | 2018-07-01 | 20 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C
2 |  | Delay in finishing of AFC drawings for Demolition of Existing road and Existing
Act | DE27-1000 | Delay in finishing of AFC drawings for Demolition of Existing road and Existing | Client | 2018-02-21 | 21 | 2018-02-21 | 21 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | Client | 2018-03-26 | 30 | 2018-03-26 | 30 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C
2 |  | Delay in construction of Subgrade lvl for Bund wall around storage tank 52-D-93 52-D-94
Act | DE28-1000 | Delay in construction of Subgrade lvl for Bund wall around storage tank 52-D-93 52-D-94 | [130 empty] | Client | 2018-08-15 | 3 | 2018-08-15 | 3 | 1 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | Client | 2018-10-17 | 28 | 2018-10-17 | 28 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | Client | 2018-12-19 | 29 | 2018-12-19 | 29 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | Client | 2019-02-13 | 27 | 2019-02-13 | 27 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | Client | 2019-04-17 | 34 | 2019-04-17 | 34 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | Client | 2019-06-02 | 26 | 2019-06-02 | 26 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | [70 empty] | Client | 2019-11-13 | 35 | 2019-11-13 | 35 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C
2 |  | Delay in construction of cast catch basing Valve Pit for bund wall around storage tank
Act | DE29-1000 | Delay in construction of cast catch basing Valve Pit for bund wall around storage tank | [130 empty] | Client | 2018-09-06 | 25 | 2018-09-06 | 25 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | Client | 2018-11-08 | 50 | 2018-11-08 | 50 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | Client | 2019-01-10 | 51 | 2019-01-10 | 51 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | Client | 2019-03-07 | 49 | 2019-03-07 | 49 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | Client | 2019-05-07 | 54 | 2019-05-07 | 54 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2 |  | Delay in finailizing engienering - distance betw Concrete pipe and Metal Pipe
Act | DE30-1000 | Delay in finailizing engienering - distance betw Concrete pipe and Metal Pipe | [88 empty] | Client | 2018-08-02 | 52 | 2018-07-14 | 33 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Client | 2018-08-19 | 36 | 2018-08-12 | 29 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Client | 2018-09-19 | 38 | 2018-09-19 | 38 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Client | 2018-11-11 | 53 | 2018-11-11 | 53 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | Client | 2019-01-13 | 54 | 2019-01-13 | 54 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | Client | 2019-03-10 | 52 | 2019-03-10 | 52 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | Client | 2019-04-20 | 37 | 2019-04-20 | 37 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C
Act | DE30-1010 | Delay in finailizing engienering - distance betw Concrete pipe and Metal Pipe | [88 empty] | Client | 2018-07-24 | 43 | 2018-07-14 | 33 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Client | 2018-08-18 | 35 | 2018-08-12 | 29 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Client | 2018-09-22 | 41 | 2018-09-19 | 38 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Client | 2018-11-18 | 60 | 2018-11-18 | 60 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | Client | 2019-01-20 | 61 | 2019-01-17 | 58 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Client | 2019-03-14 | 56 | 2019-03-14 | 56 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Client | 2019-04-24 | 41 | 2019-04-24 | 41 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C
2 |  | Delay due to delayed issue drawings Free issue material
Act | DE31-1000 | Delay due to delayed issue drawings Free issue material | [130 empty] | Client | 2018-09-02 | 21 | 2018-09-02 | 21 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | Client | 2018-11-04 | 46 | 2018-11-04 | 46 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | Client | 2019-01-06 | 47 | 2019-01-06 | 47 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | Client | 2019-03-03 | 45 | 2019-03-03 | 45 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | Client | 2019-05-05 | 52 | 2019-05-05 | 52 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | Client | 2019-07-07 | 61 | 2019-06-12 | 36 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [27 empty] | Client | 2019-10-01 | 48 | 2019-10-01 | 48 | bar: 2019-07-27 to 2019-10-09
Act | DE31-1010 | Delay due to delayed issue drawings Free issue material | [130 empty] | Client | 2018-08-28 | 16 | 2018-08-28 | 16 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | C | Client | 2018-10-30 | 41 | 2018-10-30 | 41 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | C | Client | 2019-01-01 | 42 | 2019-01-01 | 42 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | Client | 2019-02-26 | 40 | 2019-02-26 | 40 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | Client | 2019-04-30 | 47 | 2019-04-30 | 47 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | Client | 2019-07-02 | 56 | 2019-06-12 | 36 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [27 empty] | Client | 2019-09-19 | 36 | 2019-09-19 | 36 | bar: 2019-07-27 to 2019-10-09
Act | DE31-1020 | Delay due to delayed issue drawings Free issue material | [154 empty] | Client | 2018-10-13 | 24 | 2018-10-13 | 24 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | Client | 2018-12-15 | 25 | 2018-12-15 | 25 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | Client | 2019-02-09 | 23 | 2019-02-09 | 23 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | Client | 2019-04-13 | 30 | 2019-04-13 | 30 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | C | C | Client | 2019-06-15 | 39 | 2019-06-12 | 36 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Act | DE31-1030 | Delay due to delayed issue drawings Free issue material | [154 empty] | Client | 2018-10-01 | 12 | 2018-10-01 | 12 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | Client | 2018-12-03 | 13 | 2018-12-03 | 13 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | Client | 2019-01-28 | 11 | 2019-01-28 | 11 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | Client | 2019-04-01 | 18 | 2019-04-01 | 18 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | Client | 2019-06-03 | 27 | 2019-06-03 | 27 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | [27 empty] | Client | 2019-09-19 | 36 | 2019-09-19 | 36 | bar: 2019-07-27 to 2019-10-09
2 |  | Delay in Start due to Delay in Issuance of Pill Free Issue RTRP Pipe / fitting Materials Tools
Act | DE32-1000 | Delay in Start due to Delay in Issuance of Pill Free Issue RTRP Pipe / fitting Materials Tools | [110 empty] | Client | 2018-07-24 | 10 | 2018-07-24 | 10 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | Client | 2018-09-18 | 37 | 2018-09-18 | 37 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | Client | 2018-11-20 | 62 | 2018-11-20 | 62 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Client | 2019-01-22 | 63 | 2019-01-17 | 58 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Client | 2019-02-16 | 30 | 2019-02-16 | 30 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | C | C | C
Act | DE32-1010 | Delay in Start due to Delay in Issuance of Pill Free Issue RTRP Pipe / fitting Materials Tools | [130 empty] | Client | 2018-08-20 | 8 | 2018-08-20 | 8 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | Client | 2018-10-22 | 33 | 2018-10-22 | 33 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | Client | 2018-12-24 | 34 | 2018-12-24 | 34 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | C | C
Act | DE32-1020 | Delay in Start due to Delay in Issuance of Pill Free Issue RTRP Pipe / fitting Materials Tools | [130 empty] | Client | 2018-08-15 | 3 | 2018-08-15 | 3 | 1 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | Client | 2018-10-17 | 28 | 2018-10-17 | 28 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | Client | 2018-12-19 | 29 | 2018-12-19 | 29 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | Client | 2019-02-13 | 27 | 2019-02-13 | 27 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | Client | 2019-04-11 | 28 | 2019-04-11 | 28 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | C | C | C
2 |  | Delay in Delivery of UG Piping/Cabling Material
Act | DE33-1000 | Delay in Delivery of UG Piping/Cabling Material | [154 empty] | Client | 2018-10-10 | 21 | 2018-10-10 | 21 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | Client | 2018-12-12 | 22 | 2018-12-12 | 22 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | Client | 2019-02-06 | 20 | 2019-02-06 | 20 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | Client | 2019-04-10 | 27 | 2019-04-10 | 27 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | Client | 2019-06-12 | 36 | 2019-06-12 | 36 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [70 empty] | Client | 2019-12-11 | 63 | 2019-12-11 | 63 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Client | 2019-12-15 | 4 | 2019-12-15 | 4 | 1 | 1
Act | DE33-1010 | Delay in Delivery of UG Piping/Cabling Material | [154 empty] | Client | 2018-10-04 | 15 | 2018-10-04 | 15 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | Client | 2018-12-06 | 16 | 2018-12-06 | 16 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | Client | 2019-01-31 | 14 | 2019-01-31 | 14 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | Client | 2019-04-04 | 21 | 2019-04-04 | 21 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | Client | 2019-06-06 | 30 | 2019-06-06 | 30 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | [70 empty] | Client | 2019-12-05 | 57 | 2019-12-05 | 57 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | Client | 2019-12-15 | 4 | 2019-12-15 | 4 | 1 | 1 | Client | 2019-12-28 | 13 | 2019-12-28 | 13 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2 |  | Delay due to Area Clearence Sub-contractor obstraction VO revised drawings in COCC area
Act | DE34-1000 | Delay in Excavation Subgrade | [154 empty] | Client | 2018-09-22 | 3 | 2018-09-22 | 3 | 1 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | Client | 2018-11-24 | 4 | 2018-11-24 | 4 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | Client | 2019-01-19 | 2 | 2019-01-19 | 2 | 1 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | Client | 2019-03-23 | 9 | 2019-03-23 | 9 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C
Act | DE34-1010 | Delay in Blinding PCC works | [257 empty] | Client | 2019-03-17 | 3 | 2019-03-17 | 3 | 1 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C
Act | DE34-1060 | Delay in Grading cutting stockpilling | [18 empty] | Client | 2018-04-28 | 63 | 2018-04-28 | 63 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Client | 2018-06-30 | 63 | 2018-06-06 | 39 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Client | 2018-07-11 | 35 | 2018-06-11 | 5 | 1 | 1 | 1
2 |  | Delay in issue of free issue material
Act | DE36-1000 | EOF : Delivery of SS/SDSS pipes Seemless - Lot -1 | [130 empty] | Client | 2018-09-02 | 21 | 2018-09-02 | 21 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | Client | 2018-11-04 | 46 | 2018-11-04 | 46 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | Client | 2019-01-06 | 47 | 2019-01-06 | 47 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | Client | 2019-03-03 | 45 | 2019-03-03 | 45 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | Client | 2019-05-05 | 52 | 2019-05-05 | 52 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | Client | 2019-06-30 | 54 | 2019-06-12 | 36 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Act | DE36-1010 | EOF : Delivery of SS/SDSS pipes Seemless - Lot -1 | [130 empty] | Client | 2018-09-02 | 21 | 2018-09-02 | 21 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | Client | 2018-11-04 | 46 | 2018-11-04 | 46 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | Client | 2019-01-06 | 47 | 2019-01-06 | 47 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | Client | 2019-03-03 | 45 | 2019-03-03 | 45 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | Client | 2019-05-05 | 52 | 2019-05-05 | 52 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | Client | 2019-06-30 | 54 | 2019-06-12 | 36 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Act | DE36-1020 | EOF : Delivery of SS/SDSS pipes Welded - Lot -1 | [130 empty] | Client | 2018-09-02 | 21 | 2018-09-02 | 21 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | Client | 2018-11-04 | 46 | 2018-11-04 | 46 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | Client | 2019-01-06 | 47 | 2019-01-06 | 47 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | Client | 2019-03-03 | 45 | 2019-03-03 | 45 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | Client | 2019-05-05 | 52 | 2019-05-05 | 52 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | Client | 2019-06-30 | 54 | 2019-06-12 | 36 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Act | DE36-1030 | EOF : Delivery of SS/SDSS pipes Welded - Lot -1 | [130 empty] | Client | 2018-09-02 | 21 | 2018-09-02 | 21 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | Client | 2018-11-04 | 46 | 2018-11-04 | 46 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | Client | 2019-01-06 | 47 | 2019-01-06 | 47 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | Client | 2019-03-03 | 45 | 2019-03-03 | 45 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | Client | 2019-05-05 | 52 | 2019-05-05 | 52 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | Client | 2019-06-30 | 54 | 2019-06-12 | 36 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Act | DE36-1040 | EOF : Delivery of non-metallic pipes fitting GRE/ FBE/HBE - Lot -1 | [110 empty] | Client | 2018-07-24 | 10 | 2018-07-24 | 10 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | Client | 2018-09-18 | 37 | 2018-09-18 | 37 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | Client | 2018-10-17 | 28 | 2018-10-17 | 28 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C
1 |  | PROJECT MANAGEMENT
2 |  | PROJECT WIDE/GENERAL - AREA 000
3 |  | MILESTONE
4 |  | Tank Release By other Subcontractor
Act | 2AI101MS02600-08035 | EOF: Sorage Tank tank 52-D-96: Release After completion of Erection by other sub contractor
Act | 2AI101MS02600-08040 | EOF: PIG Release Release After completion of Erection by other sub contractor
1 |  | ENGINEERING BY PIL
2 |  | ENGINEERING (EXPORT OIL FACILITY - AREA 621 -(100)
3 |  | ENGINEERING INPUTS FROM PIL
4 |  | PIPING
5 |  | ISOMETRICS
Act | 2AE100PI01400-08100 | EOF : Isometrics Book for South Tank Farm | [130 empty] | Client | 2018-08-14 | 2 | 2018-08-14 | 2 | 1 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | Client | 2018-10-15 | 26 | 2018-10-15 | 26 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C
4 |  | CIVIL / STRUCTURAL / ARCHITECTURAL
5 |  | EOF - FOUNDATION DRAWINGS
6 |  | EOF: AFC drawings for Bund Wall of LFHO Storage Tank
Act | 2AE101CV01300-08100 | EOF: AFC drawings for Bund Wall of LFHO Storage Tank | [154 empty] | Client | 2018-09-27 | 8 | 2018-09-27 | 8 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | Client | 2018-11-28 | 8 | 2018-11-28 | 8 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | Client | 2019-01-23 | 6 | 2019-01-23 | 6 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C
5 |  | EOF - TRENCHES & ROAD CROSSINGS DRAWINGS
Act | 2AE100CV02400-08110 | EOF: AFC Drawing for Pipe & Cable trench at new Tank Area | [88 empty] | Client | 2018-08-02 | 52 | 2018-07-14 | 33 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Client | 2018-09-11 | 59 | 2018-08-12 | 29 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Client | 2018-09-20 | 39 | 2018-09-19 | 38 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Client | 2018-11-12 | 54 | 2018-11-12 | 54 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | Client | 2019-01-14 | 55 | 2019-01-14 | 55 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | Client | 2019-03-10 | 52 | 2019-03-10 | 52 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | [32 empty] | Client | 2019-07-07 | 61 | 2019-06-12 | 36 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
5 |  | COCC - FOUNDATION DRAWINGS
Act | 2AE133CV04000-08105 | COCC: AFC drawings for Car Park Shelters & Other Misc. Shelters | [18 empty] | Client | 2018-03-17 | 21 | 2018-03-17 | 21 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | Client | 2018-05-15 | 17 | 2018-05-15 | 17 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | C | C | Client | 2018-06-19 | 13 | 2018-06-11 | 5 | 1 | 1 | 1
5 |  | EOF - DEMOLISHION/MODIFICATION WORKS
Act | 2AE142CV01000-08100 | EOF: AFC drawings for Demolition of Existing Road and Exisitng Fence Relocation | Client | 2018-02-24 | 24 | 2018-02-24 | 24 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Client | 2018-03-27 | 31 | 2018-03-27 | 31 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C
1 |  | PROCUREMENT BY PIL
2 |  | EQUIPMENT & PACKAGES - STF Area
3 |  | SAFETY
Act | 2AP000HS00107-08100 | EOF: Delivery of Fire fighting Equipments - First Lot
Act | 2AP000HS00207-08100 | EOF: Delivery of Safety Equipments - First Lot
Act | 2AP000HS00107-08105 | EOF: Delivery of Fire fighting Equipments - Last Lot
Act | 2AP000HS00207-08105 | EOF: Delivery of Safety Equipments - Last Lot
2 |  | BULK MATERIALS
3 |  | PIPING
4 |  | Pipes - Metalic - Shipment
Act | 2AP000PI00107-08030 | EOF : Delivery of SS/SDSS Pipes (Seemless) - Lot -1 | [130 empty] | Client | 2018-09-05 | 24 | 2018-09-05 | 24 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | Client | 2018-11-07 | 49 | 2018-11-07 | 49 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | Client | 2019-01-08 | 49 | 2019-01-08 | 49 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | Client | 2019-03-04 | 46 | 2019-03-04 | 46 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | Client | 2019-05-05 | 52 | 2019-05-05 | 52 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | Client | 2019-06-30 | 54 | 2019-06-12 | 36 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Act | 2AP000PI00107-08045 | EOF : Delivery of SS/SDSS Pipes (Welded) - Lot -1 | [130 empty] | Client | 2018-09-05 | 24 | 2018-09-05 | 24 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | Client | 2018-11-07 | 49 | 2018-11-07 | 49 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | Client | 2019-01-09 | 50 | 2019-01-09 | 50 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | Client | 2019-03-05 | 47 | 2019-03-05 | 47 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | Client | 2019-05-06 | 53 | 2019-05-06 | 53 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | Client | 2019-06-30 | 54 | 2019-06-12 | 36 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
4 |  | Pipes - Non Metalic - Shipment
Act | 2AP000PI00207-08000 | EOF : Delivery of non-metallic pipes & fitting (GRE/ FBE/HBE) - Lot -1 | [110 empty] | Client | 2018-07-26 | 12 | 2018-07-26 | 12 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | Client | 2018-09-18 | 37 | 2018-09-18 | 37 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | Client | 2018-10-17 | 28 | 2018-10-17 | 28 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C
Act | 2AP000PI00207-08005 | EOF : Delivery of non-metallic pipes & fitting (GRE/ FBE/HBE) - Lot -2
Act | 2AP000PI00207-08010 | EOF : Delivery of non-metallic pipes & fitting (GRE/ FBE/HBE) - Lot -3
4 |  | Pipe Fittings and Flanges - Shipment
Act | 2AP000PI00307-08025 | EOF : Delivery of Pipe Fittings, Flanges and Blinds - Lot -3
4 |  | Piping Valves - Shipment
Act | 2AP000PI00407-08010 | EOF : Delivery of Piping Valves (Ball/GGC type) - Lot -3
Act | 2AP000PI00407-08025 | EOF : Delivery of Other Piping Valves (Butterfly/Plug/Check/Special type) - Lot -3
4 |  | Pipe Supports and Miscellaneous Items - Shipment
Act | 2AP000PI00507-08005 | EOF : Delivery of Piping supports (Primary) - Lot -2
Act | 2AP000PI00507-08010 | EOF : Delivery of Piping supports (Primary) - Lot -3
Act | 2AP000PI00507-08020 | EOF : Delivery Of Misc. Piping Items (Gaskets/Fasteners/Springs/Strut/Hanger /Sliding Plate/Etc) - Lot -2
Act | 2AP000PI00507-08025 | EOF : Delivery Of Misc. Piping Items (Gaskets/Fasteners/Springs/Strut/Hanger /Sliding Plate/Etc) - Lot -3
3 |  | SAFETY
Act | 2AP000SE00607-08000 | EOF : Delivery of Safety Signs - First Lot 1
Act | 2AP000SE00607-08005 | EOF : Delivery of Safety Signs - Lot 2
Act | 2AP000SE00607-08010 | EOF : Delivery of Safety Signs - Last Lot 3
2 |  | RAM ITEMS (FOR CONSTRUCTION)
3 |  | CIVIL / STRUCTURAL / ARCHITECTURAL
Act | 2AP100CV08100-08065 | Submition & Approval of RAM FOR HIGH SECURITY FENCE | Client | 2018-02-24 | 24 | 2018-02-24 | 24 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
1 |  | CONSTRUCTION/PRE-COMM
2 |  | EXPORT OIL FACILITY - AREA 621
3 |  | NEW STORAGE TANKS
4 |  | ELECTRICAL
5 |  | EOF: UG Electrical cable Works
Act | 2AI101EL01000 | EOF: UG Electrical cable Works
6 |  | EOF: UG Electrical cable Works
Act | 2AI101EL01000-08000 | EOF: UG Electrical cable Works
7 |  | EOF: UG Electrical cable Works - LV
Act | 2AI101EL01000-08001 | EOF: Cable Drum Checks & Transport to Site- LV Cables
Act | 2AI101EL01000-08005 | EOF: Cable Pulling - LV Cables
Act | 2AI101EL01000-08010 | EOF: Cable Dressing & Fastening - LV Cables
Act | 2AI101EL01000-08040 | EOF: Cable Marking
7 |  | EOF: UG Electrical cable Works - Earthing
Act | 2AI101EL01000-08025 | EOF: Cable Pulling - Base/Insulated earthing
Act | 2AI101EL01000-08024 | EOF: Cable Drum Checks & Transport to Site- earthing Cables
5 |  | EOF: AG Cable laying, CP, DB'S/JB, Panels, Lighting Pole, Fixtures, Cable Glaning & Termination
Act | 2AI101EL01100 | EOF:AG Cable laying, CP, DB'S/JB, Panels, Lighting Pole, Fixtures, Cable Glaning & Termination Electrical Works
6 |  | EOF:Installation of Lighting Poles & Fixtures
Act | 2AI101EL01100-08040 | EOF:Installation of supports
Act | 2AI101EL01100-08045 | EOF:Install light pole
Act | 2AI101EL01100-08050 | EOF:Install Lighting fixtures
Act | 2AI101EL01100-08015 | EOF:Installation of Lighting Poles & Fixtures
6 |  | EOF:Installation of DB'S / JB & Panels
Act | 2AI101EL01100-08140 | EOF:Install JB's/DB's
Act | 2AI101EL01100-08150 | EOF:Leveling & Grouting
Act | 2AI101EL01100-08138 | EOF:Installation of supports
Act | 2AI101EL01100-08005 | EOF:Installation of DB'S / JB & Panels
6 |  | EOF: CP Works
Act | 2AI101EL01100-08020 | EOF: CP Works
7 |  | EOF:Cathodic Prottection for Tank 52-D-93
Act | 2AI101EL01100-08060 | EOF:Installation of Transformer/JBs
Act | 2AI101EL01100-08065 | EOF:Cable laying & Termination
7 |  | EOF:Cathodic Prottection for Tank 52-D-94
Act | 2AI101EL01100-08080 | EOF:Cable laying & Termination
7 |  | EOF:Cathodic Prottection for Tank 52-D-95
Act | 2AI101EL01100-08090 | EOF:Installation of Transformer/JBs
Act | 2AI101EL01100-08095 | EOF:Cable laying & Termination
7 |  | EOF:Cathodic Prottection for Tank 52-D-96
Act | 2AI101EL01100-08105 | EOF:Installation of Transformer/JBs
Act | 2AI101EL01100-08110 | EOF:Cable laying & Termination
6 |  | EOF:Cable Glanding & Terminations
Act | 2AI101EL01100-08115 | EOF:Cable Glanding
Act | 2AI101EL01100-08113 | EOF: Cable Laying
Act | 2AI101EL01100-08025 | EOF:Cable Glanding & Terminations
4 |  | INSTRUMENTATION
5 |  | EOF: UG Instrumentation cable works
Act | 2AI101IC01000 | EOF: UG Instrumentation cable works
6 |  | EOF: UG Instrumentation cable works
Act | 2AI101IC01000-08001 | Cable Drum Checks & Transport to Site
Act | 2AI101IC01000-08010 | Cable Pulling
Act | 2AI101IC01000-08020 | Cable Dressing & Fastening
Act | 2AI101IC01000-08030 | Cable Marking
Act | 2AI101IC01000-08000 | EOF: UG Instrumentation cable works
5 |  | EOF: AG cable laying,Tubing, Field&Inline Inst. Installation, Cable Glading &Termination (Incl. F&G)
Act | 2AI101IC01100 | EOF: AG cable laying,Tubing, Field&Inline Inst. Installation, Cable Glading & Termination (incl. F&G System)
6 |  | EOF: Install Instrument Cable trays & Supports
Act | 2AI101IC01100-08001 | EOF:Fabricate Tray Supports
Act | 2AI101IC01100-08011 | EOF:Install Tray Supports
6 |  | EOF: Install Instrument JBs
Act | 2AI101IC01100-08120 | EOF: Supports Installation
Act | 2AI101IC01100-08130 | EOF: Mounting JB's
Act | 2AI101IC01100-08140 | EOF: Leveling & Grouting
Act | 2AI101IC01100-08005 | EOF:Install Instrument JBs
6 |  | EOF: Calibration of Valves/Instruments
Act | 2AI101IC01100-08021 | Receipt of Valves/Instruments at Calibration shop
Act | 2AI101IC01100-08031 | Testing of Valves/Instruments at Calibration shop
Act | 2AI101IC01100-08040 | QC checks & clearance for installation
Act | 2AI101IC01100-08015 | EOF: Calibration of Valves/Instruments
6 |  | EOF: Fabricate/Install Inst. tubing & Instrument Hookup
Act | 2AI101IC01100-08080 | EOF: Installation of Instruments on Support Structures
Act | 2AI101IC01100-08090 | EOF: Alignment/Levelling and grouting
Act | 2AI101IC01100-08025 | EOF: Fabricate/Install Inst. tubing & Instrument Hookup
4 |  | PIPING
5 |  | EOF: UG Piping works
6 |  | EOF: UG Piping works for Non Metallic
Act | 2AI101PI01000-08000 | EOF: UG Piping works for Non Metallic
7 |  | Oily Water Line
Act | 2AI101PI01000-08090 | EOF:Laying of Piping Spools | [110 empty] | Client | 2018-07-26 | 12 | 2018-07-26 | 12 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | Client | 2018-09-18 | 37 | 2018-09-18 | 37 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | Client | 2018-11-19 | 61 | 2018-11-19 | 61 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | Client | 2018-12-20 | 30 | 2018-12-20 | 30 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | C | C | C | C
Act | 2AI101PI01000-08095 | EOF:Jointing/Fusion Welding | [110 empty] | Client | 2018-07-26 | 12 | 2018-07-26 | 12 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | Client | 2018-09-18 | 37 | 2018-09-18 | 37 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | Client | 2018-11-19 | 61 | 2018-11-19 | 61 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | Client | 2018-12-20 | 30 | 2018-12-20 | 30 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | C | C | C | C
Act | 2AI101PI01000-08100 | EOF:NDE/QC Checks of Pipes | [110 empty] | Client | 2018-07-26 | 12 | 2018-07-26 | 12 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | Client | 2018-09-18 | 37 | 2018-09-18 | 37 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | Client | 2018-11-19 | 61 | 2018-11-19 | 61 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | Client | 2018-12-20 | 30 | 2018-12-20 | 30 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | Client | 2019-02-12 | 26 | 2019-02-12 | 26 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C
7 |  | Other Lines
Act | 2AI101PI01000-08001 | EOF:Laying of Piping Spools
Act | 2AI101PI01000-08006 | EOF:Jointing/Fusion Welding
Act | 2AI101PI01000-08011 | EOF:NDE/QC Checks of Pipes
6 |  | EOF: UG Piping works for Metallic (CS/LTCS)
Act | 2AI101PI01000-08005 | EOF: UG Piping works for Metallic (CS/LTCS)
7 |  | EOF: UG Piping works Fire Water Line
8 |  | EOF: UG Piping works Fire Water Line: Main Header inside Bund Wall
Act | 2AI101PI01000-08105 | EOF:Installation of pipes
Act | 2AI101PI01000-08110 | EOF:Alignment/Fit-up
Act | 2AI101PI01000-08115 | EOF:NDE/PWHT/QC Checks of Pipes
Act | 2AI101PI01000-08111 | EOF:Welding/Bolting of Pipes
8 |  | EOF: UG Piping works Fire Water Line: Fire Water Ring Out side Bund wall
Act | 2AI101PI01000-08315 | EOF:Installation of pipes
Act | 2AI101PI01000-08320 | EOF:Alignment/Fit-up
Act | 2AI101PI01000-08325 | EOF:NDE/PWHT/QC Checks of Pipes
Act | 2AI101PI01000-08321 | EOF:Welding/Bolting of Pipes
7 |  | EOF: UG Piping works Foam Pumping System Line
8 |  | EOF: UG Piping works Foam Line to Tank 52-D-93
Act | 2AI101PI01000-08041 | EOF:Coating/Wrapping
8 |  | EOF: UG Piping works Foam Line to Tank 52-D-94
Act | 2AI101PI01000-08053 | EOF:Coating/Wrapping
8 |  | EOF: UG Piping works Foam Line to Tank 52-D-95
Act | 2AI101PI01000-08069 | EOF:Coating/Wrapping
8 |  | EOF: UG Piping works Foam Line to Tank 52-D-96
Act | 2AI101PI01000-08079 | EOF:Coating/Wrapping
6 |  | EOF: UG Piping works for Metallic (SS/SDSS)
Act | 2AI101PI01000-08040 | EOF:Installation of pipes | [130 empty] | Client | 2018-09-15 | 34 | 2018-09-15 | 34 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | Client | 2018-11-17 | 59 | 2018-11-17 | 59 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | Client | 2019-01-16 | 57 | 2019-01-16 | 57 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | Client | 2019-03-13 | 55 | 2019-03-13 | 55 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | Client | 2019-05-06 | 53 | 2019-05-06 | 53 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | Client | 2019-05-08 | 1 | 2019-05-08 | 1 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | [27 empty] | Client | 2019-10-09 | 56 | 2019-10-09 | 56 | bar: 2019-07-27 to 2019-10-09
Act | 2AI101PI01000-08045 | EOF:Alignment/Fit-up | [130 empty] | Client | 2018-09-15 | 34 | 2018-09-15 | 34 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | Client | 2018-11-17 | 59 | 2018-11-17 | 59 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | Client | 2019-01-16 | 57 | 2019-01-16 | 57 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | Client | 2019-03-13 | 55 | 2019-03-13 | 55 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | Client | 2019-05-06 | 53 | 2019-05-06 | 53 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | Client | 2019-05-08 | 1 | 2019-05-08 | 1 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | [27 empty] | Client | 2019-10-09 | 56 | 2019-10-09 | 56 | bar: 2019-07-27 to 2019-10-09
Act | 2AI101PI01000-08050 | EOF:NDE/PWHT/QC Checks of Pipes | [154 empty] | Client | 2018-11-17 | 59 | 2018-11-17 | 59 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | Client | 2019-01-16 | 57 | 2019-01-16 | 57 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | Client | 2019-03-13 | 55 | 2019-03-13 | 55 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | Client | 2019-05-06 | 53 | 2019-05-06 | 53 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | Client | 2019-06-02 | 26 | 2019-06-02 | 26 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | Client | 2019-07-25 | 43 | 2019-07-25 | 43 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Act | 2AI101PI01000-08046 | EOF:Welding/Bolting of Pipes | [154 empty] | Client | 2018-11-17 | 59 | 2018-11-17 | 59 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | Client | 2019-01-16 | 57 | 2019-01-16 | 57 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | Client | 2019-03-13 | 55 | 2019-03-13 | 55 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | Client | 2019-05-06 | 53 | 2019-05-06 | 53 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | Client | 2019-05-08 | 1 | 2019-05-08 | 1 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C
5 |  | EOF: AG Piping works
Act | 2AI101PI01100 | EOF: AG Piping works
6 |  | EOF: AG Piping works for Non Metallic
Act | 2AI101PI01100-08001 | EOF:Installation of pipes
Act | 2AI101PI01100-08000 | EOF: AG Piping works for Non Metallic
6 |  | EOF: AG Piping works for Metallic (CS/LTCS)
Act | 2AI101PI01100-08005 | EOF: AG Piping works Metallic (CS/LTCS)
7 |  | Fire Water Line
8 |  | EOF: AG Piping works: Fire Water Line on Tank 52-D-94
Act | 2AI101PI01100-08200 | EOF:Installation of pipes
Act | 2AI101PI01100-08205 | EOF:Alignment/Fit-up
Act | 2AI101PI01100-08210 | EOF:NDE/PWHT/QC Checks of Pipes
Act | 2AI101PI01100-08215 | EOF:Install Permanent Supporting for Pipes
Act | 2AI101PI01100-08206 | EOF:Welding/Bolting of Pipes
8 |  | EOF: AG Piping works: Fire Water Line on Tank 52-D-93
Act | 2AI101PI01100-08225 | EOF:Installation of pipes
Act | 2AI101PI01100-08230 | EOF:Alignment/Fit-up
Act | 2AI101PI01100-08235 | EOF:NDE/PWHT/QC Checks of Pipes
Act | 2AI101PI01100-08240 | EOF:Install Permanent Supporting for Pipes
Act | 2AI101PI01100-08231 | EOF:Welding/Bolting of Pipes
8 |  | EOF: AG Piping works: Fire Water Line on Tank 52-D-95
Act | 2AI101PI01100-08250 | EOF:Installation of pipes
Act | 2AI101PI01100-08255 | EOF:Alignment/Fit-up
Act | 2AI101PI01100-08260 | EOF:NDE/PWHT/QC Checks of Pipes
Act | 2AI101PI01100-08265 | EOF:Install Permanent Supporting for Pipes
Act | 2AI101PI01100-08256 | EOF:Welding/Bolting of Pipes
8 |  | EOF: AG Piping works: Fire Water Line on Tank 52-D-96
Act | 2AI101PI01100-08275 | EOF:Installation of pipes
Act | 2AI101PI01100-08280 | EOF:Alignment/Fit-up
Act | 2AI101PI01100-08285 | EOF:NDE/PWHT/QC Checks of Pipes
Act | 2AI101PI01100-08290 | EOF:Install Permanent Supporting for Pipes
Act | 2AI101PI01100-08281 | EOF:Welding/Bolting of Pipes
7 |  | Foam Pumping System Line
8 |  | EOF: AG Piping works: Foam line on Tank 52-D-94
Act | 2AI101PI01100-08100 | EOF:Installation of pipes
Act | 2AI101PI01100-08105 | EOF:Alignment/Fit-up
Act | 2AI101PI01100-08110 | EOF:NDE/PWHT/QC Checks of Pipes
Act | 2AI101PI01100-08115 | EOF:Install Permanent Supporting for Pipes
Act | 2AI101PI01100-08106 | EOF:Welding/Bolting of Pipes
8 |  | EOF: AG Piping works: Foam Line on Tank 52-D-93
Act | 2AI101PI01100-08125 | EOF:Installation of pipes
Act | 2AI101PI01100-08130 | EOF:Alignment/Fit-up
Act | 2AI101PI01100-08135 | EOF:NDE/PWHT/QC Checks of Pipes
Act | 2AI101PI01100-08140 | EOF:Install Permanent Supporting for Pipes
Act | 2AI101PI01100-08145 | EOF:Install piping valves
Act | 2AI101PI01100-08131 | EOF:Welding/Bolting of Pipes
8 |  | EOF: AG Piping works: Foam Line on Tank 52-D-95
Act | 2AI101PI01100-08150 | EOF:Installation of pipes
Act | 2AI101PI01100-08155 | EOF:Alignment/Fit-up
Act | 2AI101PI01100-08160 | EOF:NDE/PWHT/QC Checks of Pipes
Act | 2AI101PI01100-08165 | EOF:Install Permanent Supporting for Pipes
Act | 2AI101PI01100-08156 | EOF:Welding/Bolting of Pipes
8 |  | EOF: AG Piping works: Foam Line on Tank 52-D-96
Act | 2AI101PI01100-08175 | EOF:Installation of pipes
Act | 2AI101PI01100-08180 | EOF:Alignment/Fit-up
Act | 2AI101PI01100-08185 | EOF:NDE/PWHT/QC Checks of Pipes
Act | 2AI101PI01100-08181 | EOF:Welding/Bolting of Pipes
7 |  | Miscellanies Line
8 |  | EOF: AG Piping Work Near Trim Pump
Act | 2AI101PI01100-08335 | EOF:NDE/PWHT/QC Checks of Pipes
Act | 2AI101PI01100-08340 | EOF:Install Permanent Supporting for Pipes
8 |  | EOF: AG Piping Work Near PIG
Act | 2AI101PI01100-08300 | EOF:Installation of pipes
Act | 2AI101PI01100-08310 | EOF:NDE/PWHT/QC Checks of Pipes
Act | 2AI101PI01100-08315 | EOF:Install Permanent Supporting for Pipes
7 |  | EOF: AG Piping Work: Oily Water Drine Line
8 |  | EOF: AG Oily Water Drine Line For Tank 52-D-94 Area
Act | 2AI101PI01100-08460 | EOF:NDE/PWHT/QC Checks of Pipes
8 |  | EOF: AG Oily Water Drine Line For Tank 52-D-95 Area
Act | 2AI101PI01100-08510 | EOF:NDE/PWHT/QC Checks of Pipes
7 |  | Other Line
Act | 2AI101PI01100-08025 | EOF:Installation of pipes
Act | 2AI101PI01100-08030 | EOF:Alignment/Fit-up
Act | 2AI101PI01100-08035 | EOF:NDE/PWHT/QC Checks of Pipes
Act | 2AI101PI01100-08040 | EOF:Install Permanent Supporting for Pipes
Act | 2AI101PI01100-08031 | EOF:Welding/Bolting of Pipes
6 |  | EOF: AG Piping works for Metallic (SS/SDSS)
Act | 2AI101PI01100-08050 | EOF:Installation of pipes
Act | 2AI101PI01100-08065 | EOF:Install Permanent Supporting for Pipes
Act | 2AI101PI01100-08010 | EOF: AG Piping works for Metallic (SS/SDSS)
5 |  | EOF: Hydrotesting
6 |  | EOF: Pressure testing for Non Metallic
Act | 2AI101PI01300-08000 | EOF: Pressure testing for Non Metallic
7 |  | EOF: Hydrotesting-Effluent Water Line
Act | 2AI101PI01300-08100 | EOF:Test pack preparation & Ready for Test
Act | 2AI101PI01300-08105 | EOF:Reinstatement
Act | 2AI101PI01300-08101 | EOF:Pressure testing & Approval
Act | 2AI101PI01300-08106 | EOF:Flange management
7 |  | EOF: Hydrotesting-Oily Water Line
Act | 2AI101PI01300-08080 | EOF:Test pack preparation & Ready for Test
Act | 2AI101PI01300-08085 | EOF:Reinstatement
Act | 2AI101PI01300-08081 | EOF:Pressure testing & Approval
Act | 2AI101PI01300-08086 | EOF:Flange management
6 |  | EOF: Pressure testing for Metallic (CS/LTCS)
Act | 2AI101PI01300-08005 | EOF: Pressure testing for Metallic (CS/LTCS)
7 |  | EOF: Hydrotesting-Foam Line
Act | 2AI101PI01300-08040 | EOF:Test pack preparation & Ready for Test
Act | 2AI101PI01300-08045 | EOF:Reinstatement
Act | 2AI101PI01300-08041 | EOF:Pressure testing & Approval
Act | 2AI101PI01300-08046 | EOF:Flange management
7 |  | EOF: Hydrotesting-Fillling Line
Act | 2AI101PI01300-08070 | EOF:Test pack preparation & Ready for Test
Act | 2AI101PI01300-08075 | EOF:Reinstatement
Act | 2AI101PI01300-08071 | EOF:Pressure testing & Approval
7 |  | Miscellanies Line
8 |  | EOF: AG Piping Work Near Trim Pump
Act | 2AI101PI01300-08400 | EOF:Test pack preparation & Ready for Test
4 |  | CIVIL / STRUCTURAL / ARCHITECTURAL
5 |  | TANK FOUNDATION
6 |  | EOF:Lot-1-J : LFHO Storage Tank (52-D-93 & 52-D-94) : Backfilling
Act | 2AI101CV01500 | EOF:Lot-1-J : LFHO Storage Tank (52-D-93 & 52-D-94) : Backfilling
7 |  | LFHO Storage Tank (52-D-93) : Backfilling
Act | 2AI101CV01500-08005 | LFHO Storage Tank (52-D-93) : Backfilling
8 |  | EOF:LFHO Storage Tank 52-D-93 : Backfilling & Compaction (External) for Fnd of Tank
Act | 2AI101CV01500-08035 | Compacted Gatch fill & Blinding for HDPE drain canister (External)
Act | 2AI101CV01500-08040 | Crushed Gravel w/ Gatch Mix Layer (External)
Act | 2AI101CV01500-08045 | Concreting for Access staircases & Service platforms (External)
Act | 2AI101CV01500-08050 | Asphaltic Concrete layer (External)
Act | 2AI101CV01500-08055 | Install PVC leak detection pipes & HDPE drain canister (External)
Act | 2AI101CV01500-08042 | Rebar & Formwork for Access staircases & Service platforms (External)
7 |  | LFHO Storage Tank (52-D-94) : Backfilling
Act | 2AI101CV01500-08010 | LFHO Storage Tank (52-D-94) : Backfilling
8 |  | EOF:LFHO Storage Tank 52-D-94 : Backfilling & Compaction (External) for Fnd of Tank
Act | 2AI101CV01500-08105 | Compacted Gatch fill & Blinding for HDPE drain canister (External)
Act | 2AI101CV01500-08110 | Crushed Gravel w/ Gatch Mix Layer (External)
Act | 2AI101CV01500-08115 | Concreting for Access staircases & Service platforms (External)
Act | 2AI101CV01500-08120 | Asphaltic Concrete layer (External)
Act | 2AI101CV01500-08125 | Install PVC leak detection pipes & HDPE drain canister (External)
Act | 2AI101CV01500-08112 | Rebar & Formwork for Access staircases & Service platforms (External)
6 |  | EOF:Lot-1-J : LFHO Storage Tank (52-D-95 & 52-D-96) : Backfilling
Act | 2AI101CV01900 | EOF:Lot-1-J : LFHO Storage Tank (52-D-95 & 52-D-96) : Backfilling
7 |  | LFHO Storage Tank (52-D-95) : Backfilling
Act | 2AI101CV01900-08005 | LFHO Storage Tank (52-D-95) : Backfilling
8 |  | EOF:LFHO Storage Tank 52-D-95 : Backfilling & Compaction (External) for Fnd of Tank
Act | 2AI101CV01900-08035 | Compacted Gatch fill & Blinding for HDPE drain canister (External)
Act | 2AI101CV01900-08040 | Crushed Gravel w/ Gatch Mix Layer (External)
Act | 2AI101CV01900-08045 | Concreting for Access staircases & Service platforms (External)
Act | 2AI101CV01900-08050 | Asphaltic Concrete layer (External)
Act | 2AI101CV01900-08055 | Install PVC leak detection pipes & HDPE drain canister (External)
Act | 2AI101CV01900-08042 | Rebar & Formwork for Access staircases & Service platforms (External)
7 |  | LFHO Storage Tank (52-D-96) : Backfilling
Act | 2AI101CV01900-08010 | LFHO Storage Tank (52-D-96) : Backfilling
8 |  | EOF:LFHO Storage Tank 52-D-96 : Backfilling & Compaction (External) for Fnd of Tank
Act | 2AI101CV01900-08105 | Compacted Gatch fill & Blinding for HDPE drain canister (External)
Act | 2AI101CV01900-08110 | Crushed Gravel w/ Gatch Mix Layer (External)
Act | 2AI101CV01900-08112 | Rebar & Formwork for Access staircases & Service platforms (External)
Act | 2AI101CV01900-08115 | Concreting for Access staircases & Service platforms (External)
Act | 2AI101CV01900-08120 | Asphaltic Concrete layer (External)
Act | 2AI101CV01900-08125 | Install PVC leak detection pipes & HDPE drain canister (External)
5 |  | DYKE WALL/BUND WALL
6 |  | Lot-1-J : LFHO Storage Tank (52-D-93 & 52-D-94) : Construct Bund Wall
Act | 2AI101CV01700 | EOF:Lot-1-J : LFHO Storage Tank (52-D-93 & 52-D-94) : Construct Bund Wall
7 |  | LFHO Storage Tank (52-D-93) & (52-D-94): Construct Bund Wall
Act | 2AI101CV01700-08010 | EOF:Survey Marking, Excavation & Disposal of unsutiable Material for Bund Wall around Storage tank (52-D-93 & 52-D-94) | [154 empty] | Client | 2018-09-27 | 8 | 2018-09-27 | 8 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | Client | 2018-11-28 | 8 | 2018-11-28 | 8 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | Client | 2019-01-23 | 6 | 2019-01-23 | 6 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | [32 empty] | Client | 2019-05-14 | 7 | 2019-05-14 | 7 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | [70 empty] | Client | 2019-11-11 | 33 | 2019-11-11 | 33 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C
Act | 2AI101CV01700-08015 | EOF: Prepare Subgrade lvl for Bund Wall around Storage tank (52-D-93 & 52-D-94) | [130 empty] | Client | 2018-08-14 | 2 | 2018-08-14 | 2 | 1 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | Client | 2018-10-16 | 27 | 2018-10-16 | 27 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | Client | 2018-12-18 | 28 | 2018-12-18 | 28 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | Client | 2019-02-12 | 26 | 2019-02-12 | 26 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | Client | 2019-03-30 | 16 | 2019-03-30 | 16 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | Client | 2019-06-02 | 26 | 2019-06-02 | 26 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | [70 empty] | Client | 2019-11-11 | 33 | 2019-11-11 | 33 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C
Act | 2AI101CV01700-08020 | EOF:Slope Preparation for Bund Wall around Storage tank (52-D-93 & 52-D-94) | [130 empty] | Client | 2018-08-14 | 2 | 2018-08-14 | 2 | 1 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | Client | 2018-10-16 | 27 | 2018-10-16 | 27 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | Client | 2018-12-18 | 28 | 2018-12-18 | 28 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | Client | 2019-02-12 | 26 | 2019-02-12 | 26 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | Client | 2019-03-30 | 16 | 2019-03-30 | 16 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | Client | 2019-06-02 | 26 | 2019-06-02 | 26 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | [70 empty] | Client | 2019-11-11 | 33 | 2019-11-11 | 33 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C
Act | 2AI101CV01700-08025 | EOF:Install/Cast Catch basin (inside) & Valve pit (outside) for Bund Wall around Storage tank (52-D-93 & 52-D-94) | [130 empty] | Client | 2018-09-05 | 24 | 2018-09-05 | 24 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | Client | 2018-11-07 | 49 | 2018-11-07 | 49 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | Client | 2019-01-09 | 50 | 2019-01-09 | 50 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | Client | 2019-03-06 | 48 | 2019-03-06 | 48 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C
Act | 2AI101CV01700-08035 | EOF:Sand layer (Inside) upto Linear Menbrane Lvl for Bund Wall around Storage tank (52-D-93 & 52-D-94)
Act | 2AI101CV01700-08005 | LFHO Storage Tank (52-D-93) & (52-D-94): Construct Bund Wall
6 |  | Lot-1-J : LFHO Storage Tank (52-D-95 & 52-D-96) : Construct Bund Wall
Act | 2AI101CV02100 | EOF:Lot-1-J : LFHO Storage Tank (52-D-95 & 52-D-96) : Construct Bund Wall
7 |  | LFHO Storage Tank (52-D-95) & (52-D-96) : Construct Bund Wall
Act | 2AI101CV02100-08005 | LFHO Storage Tank (52-D-95) & (52-D-96) : Construct Bund Wall
Act | 2AI101CV02100-08015 | EOF: Survey Marking, Excavation & Disposal of unsutiable Material for Bund Wall around Storage tank 52-D-96 & 52-D-95
Act | 2AI101CV02100-08020 | EOF: Prepare Subgrade lvl for Bund Wall around Storage tank 52-D-96 & 52-D-95
Act | 2AI101CV02100-08025 | EOF:Slope Preparation for Bund Wall around Storage tank 52-D-96 & 52-D-95
Act | 2AI101CV02100-08030 | EOF:Install/Cast Catch basin (inside) & Valve pit (outside) for Bund Wall around Storage tank 52-D-96 & 52-D-95
Act | 2AI101CV02100-08040 | EOF:Sand layer (Inside) upto Linear Menbrane Lvl for Bund Wall around Storage tank 52-D-96 & 52-D-95
5 |  | STRUCTURAL STEEL
6 |  | EOF: Foam Pump House Building structural works
Act | 2AI101CV01200 | EOF: Foam Pump House Building structural works
7 |  | EOF: 621-G-302 C/D Foam Pump House Building structural works
Act | 2AI101CV01200-08015 | EOF:Installation of Str. Steel for 621-G-302 C/D Foam Pump House Building
Act | 2AI101CV01200-08020 | EOF:Alignment & Bolting/Torqueing for 621-G-302 C/D Foam Pump House Building
Act | 2AI101CV01200-08005 | EOF: 621-G-302 C/D Foam Pump House Building structural works
5 |  | MISCELLANEOUS CIVIL WORKS
6 |  | EOF: UG Trench and Other Civl Worrks
Act | 2AI101CV18400 | EOF: UG Trench and Other Civl Worrks
7 |  | EOF: Pipe Trench
Act | 2AI101CV18400-08000 | EOF: Pipe Trench
8 |  | EOF:Pipe Trench - Main Filling/Loading Pipe Line (Incl. Fire Water Main line) to Storage Tank
Act | 2AI101CV18400-08001 | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material
Act | 2AI101CV18400-08006 | EOF: Bedding (incl. clean sand layer)
8 |  | EOF:Pipe Trench - Loading Line from Storage Tank till Trim Pump
Act | 2AI101CV18400-08015 | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material
Act | 2AI101CV18400-08020 | EOF: Bedding (incl. clean sand layer)
8 |  | EOF:Pipe Trench - 12" Pipe Line from Storage Tank till Oily Water Vessel
Act | 2AI101CV18400-08030 | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material | [110 empty] | Client | 2018-07-22 | 8 | 2018-07-22 | 8 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | C
Act | 2AI101CV18400-08035 | EOF: Bedding (incl. clean sand layer) | [110 empty] | Client | 2018-07-22 | 8 | 2018-07-22 | 8 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | C
Act | 2AI101CV18400-08041 | EOF:Install Route/saftey Markers
Act | 2AI101CV18400-08036 | EOF: Backfilling and Compaction
8 |  | EOF: Pipe Trench Fire Water Line to Tank 52-5-95
Act | 2AI101CV18400-08455 | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material
Act | 2AI101CV18400-08460 | EOF: Bedding (incl. clean sand layer)
8 |  | EOF: Pipe Trench Fire Water Line to Tank 52-5-96
Act | 2AI101CV18400-08470 | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material
Act | 2AI101CV18400-08475 | EOF: Bedding (incl. clean sand layer)
8 |  | EOF: Pipe Trench Fire Water Ring Line out side Bund Wall
Act | 2AI101CV18400-08485 | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material
Act | 2AI101CV18400-08490 | EOF: Bedding (incl. clean sand layer)
8 |  | EOF: Effluent water(WK) Line
Act | 2AI101CV18400-08500 | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material
Act | 2AI101CV18400-08505 | EOF: Bedding (incl. clean sand layer)
Act | 2AI101CV18400-08510 | EOF: Backfilling and Compaction
Act | 2AI101CV18400-08511 | EOF:Install Route/saftey Markers
8 |  | EOF:Pipe Trench - Foam line
Act | 2AI101CV18400-08045 | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material
Act | 2AI101CV18400-08050 | EOF: Bedding (incl. clean sand layer)
Act | 2AI101CV18400-08055 | EOF: Backfilling and Compaction
Act | 2AI101CV18400-08056 | EOF:Install Route/saftey Markers
8 |  | EOF:Pipe Trench - Other Lines
Act | 2AI101CV18400-08060 | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material | [88 empty] | Client | 2018-07-12 | 31 | 2018-07-12 | 31 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | Client | 2018-07-26 | 12 | 2018-07-26 | 12 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | Client | 2018-09-10 | 29 | 2018-09-10 | 29 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | Client | 2018-11-12 | 54 | 2018-11-12 | 54 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | Client | 2019-01-13 | 54 | 2019-01-13 | 54 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | Client | 2019-03-10 | 52 | 2019-03-10 | 52 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | Client | 2019-04-16 | 33 | 2019-04-16 | 33 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | C
Act | 2AI101CV18400-08065 | EOF: Bedding (incl. clean sand layer) | [88 empty] | Client | 2018-07-12 | 31 | 2018-07-12 | 31 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | Client | 2018-08-11 | 28 | 2018-08-11 | 28 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | Client | 2018-09-15 | 34 | 2018-09-15 | 34 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | Client | 2018-11-17 | 59 | 2018-11-17 | 59 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | Client | 2019-01-16 | 57 | 2019-01-16 | 57 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | Client | 2019-03-13 | 55 | 2019-03-13 | 55 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | Client | 2019-04-13 | 30 | 2019-04-13 | 30 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | C | C
7 |  | EOF: EIT Cable Trench
Act | 2AI101CV18400-08005 | EOF: EIT Cable Trench
8 |  | EOF: Instrumentation Cable Trench (Inside STF Area)
Act | 2AI101CV18400-08125 | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material
Act | 2AI101CV18400-08130 | EOF:Sand bedding
Act | 2AI101CV18400-08135 | EOF:Install Cable Tile Laying & warning Tapes
Act | 2AI101CV18400-08131 | EOF:Sand Padding
8 |  | EOF:Electrical Cable Trench (STF Inside Area)
Act | 2AI101CV18400-08150 | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material
Act | 2AI101CV18400-08155 | EOF:Sand bedding
Act | 2AI101CV18400-08160 | EOF:Install Cable Tile Laying & warning Tapes
Act | 2AI101CV18400-08165 | EOF:Backfilling & Compaction
Act | 2AI101CV18400-08170 | EOF:Install Route/saftey Markers
Act | 2AI101CV18400-08156 | EOF:Sand Padding
5 |  | ROADS & PAVING
6 |  | EOF: Roads, Crossing & Paving Works
Act | 2AI101CV01100 | EOF: Roads, Crossing & Paving Works
7 |  | EOF: Gutch Road Work
Act | 2AI101CV01100-08021 | EOF:Excavation
Act | 2AI101CV01100-08026 | EOF:Grading & leveling
Act | 2AI101CV01100-08000 | EOF: Gutch Road Work
7 |  | EOF: Reinforced Concrete Paving
Act | 2AI101CV01100-08040 | EOF:Excavation
Act | 2AI101CV01100-08045 | EOF:Grading & leveling
Act | 2AI101CV01100-08050 | EOF:Preparation of sub grade
Act | 2AI101CV01100-08055 | EOF:Concrete Work
Act | 2AI101CV01100-08010 | EOF: Reinforced Concrete Paving
7 |  | EOF: Asphalt Paving
Act | 2AI101CV01100-08060 | EOF:Excavation
Act | 2AI101CV01100-08065 | EOF:Grading & leveling
Act | 2AI101CV01100-08070 | EOF:Preparation of sub grade
Act | 2AI101CV01100-08015 | EOF: Asphalt Paving
7 |  | EOF: Grade slab for Pump shelters/Mobile shelters
Act | 2AI101CV01100-08029 | EOF: Reinforcement
Act | 2AI101CV01100-08025 | EOF: Grade slab for Pump shelters/Mobile shelters
4 |  | MECHANICAL - ROTATING
5 |  | EOF: Pump Erection
Act | 2AI101MS03000 | EOF: Pump Erection
6 |  | EOF: 621-G-303 A Oily Water Transfer Pump Erection
Act | 2AI101MS03000-08065 | EOF:Final Allignment & Grouting of Equipment 621-G-303 A Oily Water Transfer Pump
Act | 2AI101MS03000-08070 | EOF:QC checks & clearance for Equipment 621-G-303 A Oily Water Transfer Pump
Act | 2AI101MS03000-08010 | EOF: 621-G-303 A Oily Water Transfer Pump Erection
6 |  | EOF: 621-G-303 B Oily Water Transfer Pump Erection
Act | 2AI101MS03000-08090 | EOF:Final Allignment & Grouting of Equipment 621-G-303 B Oily Water Transfer Pump
Act | 2AI101MS03000-08095 | EOF:QC checks & clearance for Equipment 621-G-303 B Oily Water Transfer Pump
Act | 2AI101MS03000-08015 | EOF: 621-G-303 B Oily Water Transfer Pump Erection
4 |  | FIRE-PROOFING
5 |  | EOF: Fire Proofing of Structures/equipments
Act | 2AI101CV03100 | EOF: Fire Proofing of Structures/equipments
Act | 2AI101CV03100-08020 | EOF: Fire Proofing of Diesel Generator Day Tank - 50-R-002
Act | 2AI101CV03100-08025 | EOF: Fire Proofing of Diesel Generator Day Tank - 52-R-302
Act | 2AI101CV03100-08030 | EOF: Fire Proofing of Trimp Pump - 621-G-301
Act | 2AI101CV03100-08040 | EOF: Fire Proofing of Diesel Generator Day Tank - 52-R-303
Act | 2AI101CV03100-08035 | EOF: Fire Proofing of Diesel Generator Day Tank - 52-R-301
4 |  | PAINTING
5 |  | EOF: Touch-up painting of Structures
Act | 2AI101CV18200-08000 | EOF: Touch-up painting of Structures
Act | 2AI101CV18200 | EOF: Touch-up painting of Structures
3 |  | OTHER WORKS - EOF
4 |  | CIVIL / STRUCTURAL / ARCHITECTURAL
5 |  | FOUNDATION
6 |  | EOF: Ground Supported Platforms Foundation
Act | 2AI103CV19600 | EOF: Ground Supported Platforms Foundation
7 |  | EOF: Ground Supported Platforms Foundation
Act | 2AI103CV19600-08001 | EOF:Survey Marking, Excavation & Subgrade
Act | 2AI103CV19600-08005 | EOF:Blinding/PCC for Fnd
Act | 2AI103CV19600-08015 | EOF:Rebar, Formwork, Install Embedments for Pedestal
Act | 2AI103CV19600-08020 | EOF:Concrete Potection for Fnd
Act | 2AI103CV19600-08025 | EOF:Backfilling & Compaction for Fnd
Act | 2AI103CV19600-08011 | Concrete Pouring - for Footing
Act | 2AI103CV19600-08016 | Concrete Pouring - for Pedestal
Act | 2AI103CV19600-08010 | EOF:Rebar, Formwork for Footing
Act | 2AI103CV19600-08000 | EOF: Ground Supported Platforms Foundation
5 |  | STRUCTURAL STEEL
6 |  | EOF: Structural Steel of Ground Supported Platforms
Act | 2AI103CV01200 | EOF: Structural Steel of Ground Supported Platforms
7 |  | EOF: Structural Steel of Ground Supported /Equipment Mounted Platforms
Act | 2AI103CV01200-08001 | EOF:Installation of Str. Steel of Ground Supported Platforms
Act | 2AI103CV01200-08006 | EOF:Alignment & Bolting/Torqueing of Ground Supported Platforms
Act | 2AI103CV01200-08010 | EOF:Grouting of Ground Supported Platforms
Act | 2AI103CV01200-08000 | EOF: Structural Steel of Ground Supported /Equipment Mounted Platforms
7 |  | EOF: Pipe Support & EIT Supports Erection
Act | 2AI103CV01200-08005 | EOF: Pipe Support & EIT Supports Erection
Act | 2AI103CV01200-08015 | EOF:Installation of Str. Steel of Ground Supported Platforms
Act | 2AI103CV01200-08020 | EOF:Alignment & Bolting/Torqueing of Ground Supported Platforms
Act | 2AI103CV01200-08025 | EOF:Grouting of Ground Supported Platforms
6 |  | EOF: Structural Steel Erection
Act | 2AI103CV18700 | EOF: Structural Steel Erection
7 |  | EOF: Tank Stairways - Structural Steel Erection
Act | 2AI103CV18700-08000 | EOF: Tank Stairways - Structural Steel Erection
8 |  | EOF: Tank Stairways - Structural Steel Erection 52-D-94
Act | 2AI103CV18700-08025 | Installation of gratings/handrail/ladder
8 |  | EOF: Tank Stairways - Structural Steel Erection 52-D-93
Act | 2AI103CV18700-08045 | Installation of gratings/handrail/ladder
8 |  | EOF: Tank Stairways - Structural Steel Erection 52-D-95
Act | 2AI103CV18700-08070 | Installation of gratings/handrail/ladder
8 |  | EOF: Tank Stairways - Structural Steel Erection 52-D-96
Act | 2AI103CV18700-08095 | Installation of gratings/handrail/ladder
5 |  | MISCELLANEOUS CIVIL WORKS
6 |  | TRENCH WORKS
7 |  | EOF: RCC Cable trench
Act | 2AI103CV18300 | EOF: RCC Cable trench
8 |  | EOF: Cable Trench
Act | 2AI103CV18300-08000 | EOF: Cable trench
9 |  | EOF: MG-1 SUBSTATION TIE-INS CABLE TRENCH
10 |  | Cable Trench from MG-1 Substation to 52-SUBST-301
Act | 2AI103CV18300-08055 | EOF:Install Route/saftey Markers
9 |  | EOF: POWER CABLE FROM SUBSTATION
10 |  | LV Power Cable laying from 52-SUBST-302 to Storage Tanks Transformer
Act | 2AI103CV18300-08160 | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material
Act | 2AI103CV18300-08165 | EOF:Sand bedding
Act | 2AI103CV18300-08170 | EOF:Install Cable Tile Laying & warning Tapes
Act | 2AI103CV18300-08175 | EOF:Backfilling & Compaction
Act | 2AI103CV18300-08166 | EOF:Sand Padding
9 |  | EOF: INSTRUMENTATION CABLE FROM SUBSTATION
10 |  | Instrument Cable laying from 52-SUBST-302 to Storage Tank Junction Boxes
Act | 2AI103CV18300-08285 | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material
Act | 2AI103CV18300-08290 | EOF:Sand bedding
Act | 2AI103CV18300-08295 | EOF:Install Cable Tile Laying & warning Tapes
Act | 2AI103CV18300-08300 | EOF:Backfilling & Compaction
Act | 2AI103CV18300-08305 | EOF:Install Route/saftey Markers
Act | 2AI103CV18300-08291 | EOF:Sand Padding
9 |  | EOF: TELECOM CABLE LAYING TO COCC
10 |  | Fiber Optic Cable Laying from in boundery Limt of COCC Area
Act | 2AI103CV18300-08360 | EOF:Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material
Act | 2AI103CV18300-08365 | EOF:Sand bedding
Act | 2AI103CV18300-08370 | EOF:Install Cable Tile Laying & warning Tapes
Act | 2AI103CV18300-08375 | EOF:Backfilling & Compaction
Act | 2AI103CV18300-08380 | EOF:Install Route/saftey Markers
Act | 2AI103CV18300-08366 | EOF:Sand Padding
5 |  | EOF: UG, Trenches & other Civil Works
Act | 2AI102CV01500 | EOF: UG, Trenches & other Civil Works
6 |  | EOF: HSE Safety Equipments & Safety Misc. Foundation
Act | 2AI102CV01500-08000 | EOF: HSE Safety Equipments & Safety Misc. Foundation
Act | 2AI102CV01500-08121 | EOF: HSE Safety Equipments & Safety Misc. Foundation
6 |  | EOF: EIT Supports
Act | 2AI102CV01500-08020 | EOF: EIT items Misc. Foundation
Act | 2AI102CV01500-08123 | EOF: EIT items Misc. Foundation
5 |  | U/G WORKS: SUMP/DRAIN PITS, MH, etc.
6 |  | EOF: Construction of Sumps
7 |  | EOF: Manholes & Miscellaneous Drain Pits
Act | 2AI103CV19700-08001 | EOF:Excavation & Subgrade
Act | 2AI103CV19700-08006 | EOF:Blinding/PCC for Sump
Act | 2AI103CV19700-08010 | EOF:Rebar, Formwork for base
Act | 2AI103CV19700-08015 | EOF:Rebar, Formwork for wall
Act | 2AI103CV19700-08020 | EOF:Concrete Potection
Act | 2AI103CV19700-08025 | EOF:Coverslab
Act | 2AI103CV19700-08030 | EOF:Backfilling & Compaction
Act | 2AI103CV19700 | EOF: Miscellaneous Drain Pits
Act | 2AI103CV19700-08011 | EOF:Concrete Pouring for base
Act | 2AI103CV19700-08016 | EOF:Concrete Pouring for wall
Act | 2AI103CV19700-08005 | EOF: Miscellaneous Drain Pits
5 |  | DEMOLISION/ MODIFICATION WORK
6 |  | EOF: Existing Road & Fence Demolition Works
Act | 2AI103CV28220 | EOF: Existing Road & Fence Demolition Works
7 |  | EOF:Demolition Work - New Tank Area - 621
Act | 2AI103CV28220-08006 | EOF:Demolition Works - Existing Fence
Act | 2AI103CV28220-08000 | EOF:Demolition Work Existing Road & Existing Fence- New Tank Area - 621
7 |  | EOF:New Fencing Work - New Tank Area - 621
Act | 2AI103CV28220-08015 | EOF:Survey marking & Excavation for Fence Post
Act | 2AI103CV28220-08020 | EOF:Fence Post installation
Act | 2AI103CV28220-08025 | EOF:Fence Mesh Installation
Act | 2AI103CV28220-08016 | EOF:Sub grade & Blinding | [426 empty] | Client | 2019-12-28 | 13 | 2019-12-28 | 13 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Act | 2AI103CV28220-08017 | EOF:Install/Cast insitu fencing fnds
Act | 2AI103CV28220-08026 | EOF:Gate Installation & Speed bumbs
Act | 2AI103CV28220-08005 | EOF:New Fencing Work - New Tank Area - 621
5 |  | ROADS & PAVING
6 |  | EOF: Roads, Crossing & Paving Works
Act | 2AI103CV19100 | EOF: Roads, Crossing & Paving Works
7 |  | EOF:Asphalt Road Work
Act | 2AI103CV19100-08001 | EOF:Grading & leveling | [130 empty] | Client | 2018-08-14 | 2 | 2018-08-14 | 2 | 1 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | Client | 2018-10-16 | 27 | 2018-10-16 | 27 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | Client | 2018-12-18 | 28 | 2018-12-18 | 28 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | Client | 2019-02-12 | 26 | 2019-02-12 | 26 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | Client | 2019-04-09 | 26 | 2019-04-09 | 26 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | Client | 2019-06-11 | 35 | 2019-06-11 | 35 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | Client | 2019-08-14 | 63 | 2019-08-14 | 63 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [43 empty] | Client | 2019-12-10 | 62 | 2019-12-10 | 62 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | Client | 2019-12-15 | 4 | 2019-12-15 | 4 | 1 | 1
Act | 2AI103CV19100-08006 | EOF:Preparation of sub grade | [130 empty] | Client | 2018-08-14 | 2 | 2018-08-14 | 2 | 1 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | Client | 2018-10-16 | 27 | 2018-10-16 | 27 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | Client | 2018-12-18 | 28 | 2018-12-18 | 28 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | Client | 2019-02-12 | 26 | 2019-02-12 | 26 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | Client | 2019-04-09 | 26 | 2019-04-09 | 26 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | Client | 2019-06-11 | 35 | 2019-06-11 | 35 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | Client | 2019-08-08 | 57 | 2019-08-08 | 57 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [43 empty] | Client | 2019-12-10 | 62 | 2019-12-10 | 62 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | Client | 2019-12-14 | 3 | 2019-12-14 | 3 | 1 | C
Act | 2AI103CV19100-08011 | EOF:Asphalt Work | [339 empty] | Client | 2019-10-08 | 55 | 2019-10-08 | 55 | bar: 2019-07-27 to 2019-10-09
Act | 2AI103CV19100-08016 | EOF:Kerb-stone installation | [339 empty] | Client | 2019-10-08 | 55 | 2019-10-08 | 55 | bar: 2019-07-27 to 2019-10-09
Act | 2AI103CV19100-08005 | EOF:Asphalt Road Work
7 |  | EOF:Gutch Road Work
Act | 2AI103CV19100-08025 | EOF:Excavation
Act | 2AI103CV19100-08030 | EOF:Grading & leveling
Act | 2AI103CV19100-08000 | EOF:Gutch Road Work
7 |  | EOF:Reinforced Concrete Paving
Act | 2AI103CV19100-08045 | EOF:Excavation
Act | 2AI103CV19100-08050 | EOF:Grading & leveling
Act | 2AI103CV19100-08010 | EOF:Reinforced Concrete Paving
7 |  | EOF:Asphalt Paving
Act | 2AI103CV19100-08065 | EOF:Excavation
Act | 2AI103CV19100-08015 | EOF:Asphalt Paving
4 |  | HSE
5 |  | EOF: Installation of Fire fighting & Safety Equipments
Act | 2AI103HS01110-08001 | EOF: Installation of Fire fighting & Safety Equipments
Act | 2AI103HS01110 | EOF: Installation of Fire fighting & Safety Equipments
Act | 2AI103HS01110-08000 | EOF: Installation of Fire fighting & Safety Equipments
5 |  | EOF: Installation of Safety Sign Boards
Act | 2AI103HS01120-08001 | EOF:Installation - Indoor Safety Signs
Act | 2AI103HS01120-08005 | EOF:Installation - Outdoor Safety Signs
Act | 2AI103HS01120 | EOF: Installation of Safety Sign Boards
Act | 2AI103HS01120-08000 | EOF: Installation of Safety Sign Boards
4 |  | MECHANICAL - STATIC
5 |  | EOF: Tank Erection
Act | 2AI103MS19900 | EOF: Tank Erection
6 |  | EOF: Diesel Fuel Tank 621-D307 A/B Erection
Act | 2AI103MS19900-08001 | EOF:Foundation checks/Preparation for Equipment
Act | 2AI103MS19900-08006 | EOF:Installation of Structural Support, Platforms & ladders of Equipment
Act | 2AI103MS19900-08010 | EOF:Installation of Diesel Fuel Tank 621-D307 A/B
Act | 2AI103MS19900-08015 | EOF:Preliminary Allignment & Grouting of Equipment
Act | 2AI103MS19900-08020 | EOF:Final Allignment & Grouting of Equipment
Act | 2AI103MS19900-08025 | EOF:Install internals of Equipment
Act | 2AI103MS19900-08030 | EOF:QC checks & clearance for Equipment
Act | 2AI103MS19900-08000 | EOF: Erection of Diesel Fuel Tank (52-D-307 A/B)
6 |  | EOF: Diesel Fuel Tank 621-D307 C/D Erection
Act | 2AI103MS19900-08035 | EOF:Foundation checks/Preparation for Equipment
Act | 2AI103MS19900-08040 | EOF:Installation of Structural Support, Platforms & ladders of Equipment
Act | 2AI103MS19900-08045 | EOF:Installation of Diesel Fuel Tank 621-D307 C/D
Act | 2AI103MS19900-08050 | EOF:Preliminary Allignment & Grouting of Equipment
Act | 2AI103MS19900-08055 | EOF:Final Allignment & Grouting of Equipment
Act | 2AI103MS19900-08060 | EOF:Install internals of Equipment
Act | 2AI103MS19900-08065 | EOF:QC checks & clearance for Equipment
Act | 2AI103MS19900-08005 | EOF: Erection of Diesel Fuel Tank (52-D-307 C/D)
5 |  | EOF: Other Equipments (H2S Scrubber, PIG Receiver, Vessel etc)
Act | 2AI103MS20000 | EOF: Other Equipments (H2S Scrubber, PIG Receiver, Vessel etc)
6 |  | EOF: Oily Water Transfer Vessel 621-V-301Erection
Act | 2AI103MS20000-08025 | EOF:Install internals of Equipment
Act | 2AI103MS20000-08000 | EOF: Oily Water Transfer Vessel 621-V-301Erection
4 |  | MECHANICAL - ROTATING
5 |  | EOF: Pump Erection
Act | 2AI103MR18900 | EOF: Pump Erection
6 |  | EOF: 621-G-302 A Foam Pump Erection
Act | 2AI103MR18900-08016 | EOF:QC checks & clearance for Equipment 621-G-302 A Foam Pump Erection
Act | 2AI103MR18900-08000 | EOF: 621-G-302 A Foam Pump Erection
6 |  | EOF: 621-G-302 B Foam Pump Erection
Act | 2AI103MR18900-08045 | EOF:QC checks & clearance for Equipment 621-G-302 B Foam Pump Erection
Act | 2AI103MR18900-08005 | EOF: 621-G-302 B Foam Pump Erection
5 |  | EOF: Foam System Package (52-Z-301 A/B) Erection
Act | 2AI103MR19300 | EOF: Foam System Package (52-Z-301 A/B) Erection
6 |  | EOF: Foam System Package (52-Z-301 A) Erection
Act | 2AI103MR19300-08020 | EOF:QC checks & clearance for Equipment
Act | 2AI103MR19300-08000 | EOF: Foam System Package (52-Z-301 A) Erection
6 |  | EOF: Foam System Package (52-Z-301 B) Erection
Act | 2AI103MR19300-08045 | EOF:QC checks & clearance for Equipment
Act | 2AI103MR19300-08005 | EOF: Foam System Package (52-Z-301 B) Erection
3 |  | TIE-INS : EOF AREA
4 |  | PIPING
5 |  | EOF: Piping Tie-Ins works (Fire water line & Oily water line)
Act | 2AI104PI20100-08005 | EOF:Piping Tie-Ins works Oily Water line
Act | 2AI104PI20100 | EOF: Piping Tie-Ins works (Fire Water line & Oily Water line)
4 |  | ELECTRICAL, INSTRUMENTATION & TELECOM
5 |  | EOF: E,I&T Tie-Ins works associated with 52-SUBST-301& MG-1 Substation and other EIT Tie-in scope
Act | 2AI104EL20100 | EOF: E,I&T Tie-Ins works associated with 52-SUBST-301& MG-1 Substation and Other EIT Tie-in scope in EOF Area
Act | 2AI104EL20100-08000 | EOF : Tie-Ins works associated with 11KV Power Cable from MG-1 Substation to 52-SUBST-301
5 |  | EOF: Power Cable from Substation
Act | 2AI102EL01100 | EOF: AG Cable laying, CP, DB'S/JB, Panels, Lighting Pole, Fixtures, Cable Glaning & Termination Electrical Works
Act | 2AI102EL01100-08142 | LV Power Cable laying from 50-SUBST-001
Act | 2AI102EL01100-08141 | LV Power Cable laying from 52-SUBST-302
5 |  | EOF: Instrument Cable from Substation
Act | 2AI102IC01000 | EOF: Instrument Cable from Substation
Act | 2AI102IC01000-08141 | Instrument Cable laying from 52-SUBST-302 to Storage Tank Junction Boxes
5 |  | EOF: Telecom Cable Laying to COCC
Act | 2AI102TE01000 | EOF: Telecom Cable Laying to COCC
Act | 2AI102TE01000-08141 | Fiber Optic Cable Laying in boudery Limit of COCC Area
5 |  | EOF: Telecom Cable Laying from COCC to Substation
Act | 2AI102TE01100 | EOF: Telecom Cable Laying from COCC to Substation
Act | 2AI102TE01100-08141 | Fiber Optic Cable Laying from Boundery Limit to 52-SUBST-302
2 |  | CRUDE OIL CONTROL CENTER (COCC) - AREA 621
3 |  | BUILDINGS - COCC
4 |  | COCC :SITE PREPARATION
5 |  | COCC : Site preparation
6 |  | COCC : Site preparation (Including COCC Buliding,Carparking & Subsatation)
Act | 2AI141CV01000-08020 | COCC : Grading, Cutting & Stockpiling | Client | 2018-03-04 | 32 | 2018-02-24 | 24 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Client | 2018-04-26 | 61 | 2018-04-26 | 61 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | Client | 2018-06-28 | 61 | 2018-06-06 | 39 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Client | 2018-07-11 | 35 | 2018-06-11 | 5 | 1 | 1 | 1
Act | 2AI141CV01000-08025 | COCC : Grading, Filling & Compaction | Client | 2018-02-22 | 22 | 2018-02-22 | 22 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | Client | 2018-04-26 | 61 | 2018-04-26 | 61 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | Client | 2018-06-05 | 38 | 2018-06-05 | 38 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | Client | 2018-07-11 | 35 | 2018-06-11 | 5 | 1 | 1 | 1
5 |  | COCC : Trench (Manual Excavation) & other Civil Works
Act | 2AI141CV01100 | COCC : Trench & other Civil Works (including construction scope for migration readiness)
6 |  | COCC : Trench (Manual Excavation)
Act | 2AI141CV01100-08000 | COCC : Trench (Manual Excavation)
Act | 2AI141CV01100-08025 | COCC: Survey Marking, Excavation (Hand/Machine) & Disposal of Unsuitable Material
Act | 2AI141CV01100-08035 | COCC:Bedding (incl. clean sand layer)
Act | 2AI141CV01100-08045 | COCC:Backfilling with clean sand layer
Act | 2AI141CV01100-08055 | COCC:Install Cable Tiles & Warning Tapes
Act | 2AI141CV01100-08065 | COCC:Backfilling and Compaction
Act | 2AI141CV01100-08075 | COCC:Install Route/saftey Markers
6 |  | COCC : Pipe Supports
Act | 2AI141CV01100-08010 | COCC : Pipe Supports
7 |  | COCC :Install Pre-Cast Fnds - Pipe Supports/Sleepers
Act | 2AI141CV01100-08050 | COCC : Survey Marking, Excavation & Subgrade preparation
Act | 2AI141CV01100-08060 | COCC : Blinding/PCC
Act | 2AI141CV01100-08070 | COCC : Installation of pre-cast foundations and Leveling
Act | 2AI141CV01100-08080 | COCC : Backfill and Compaction (wherever applicable)
6 |  | COCC : EIT Supports
Act | 2AI141CV01100-08015 | COCC : EIT Supports
7 |  | COCC :Install Pre-Cast Fnds - EIT Supports
Act | 2AI141CV01100-08120 | COCC : Survey Marking, Excavation & Subgrade preparation
Act | 2AI141CV01100-08130 | COCC : Blinding/PCC
Act | 2AI141CV01100-08140 | COCC : Installation of pre-cast foundations and Leveling
Act | 2AI141CV01100-08145 | COCC : Backfill and Compaction (wherever applicable)
4 |  | CIVIL / STRUCTURAL / ARCHITECTURAL
5 |  | ROADS & PAVING
6 |  | COCC :Roads, Crossing & Paving Works
Act | 2AI102CV01600 | COCC :Roads, Crossing & Paving Works
7 |  | COCC: Roads including Crossing Works
Act | 2AI102CV01600-08141 | COCC: Roads including Crossing Works
8 |  | COCC: Roads upto Grade
Act | 2AI102CV01600-08010 | COCC: Rough Grading for Road Works
Act | 2AI102CV01600-08020 | COCC: Fine Grading (Gatch Subgrade)
Act | 2AI102CV01600-08030 | COCC: Finish Grading (Crushed gravel layer & Grading Top soil)
8 |  | COCC: Roads Finishing works
Act | 2AI102CV01600-08040 | COCC: Re-combaction of sub-grade
Act | 2AI102CV01600-08050 | COCC: Base Preparation & Kerbing (incl. Filling/Comp with Gatch & Crushed gravel layer)
Act | 2AI102CV01600-08060 | COCC: Asphalt base course
Act | 2AI102CV01600-08070 | COCC: Asphalt binding course
7 |  | COCC: Paving Works
Act | 2AI102CV01600-08142 | COCC: Paving Work
8 |  | COCC: Concrete Paving
Act | 2AI102CV01600-08025 | COCC: Sub base & Base preparation
Act | 2AI102CV01600-08035 | COCC: Formwork
Act | 2AI102CV01600-08045 | COCC: Reinforcement
Act | 2AI102CV01600-08055 | COCC: Concrete Pouring
Act | 2AI102CV01600-08065 | COCC: Finishing
8 |  | COCC: Interlock Paving/walkways
Act | 2AI102CV01600-08075 | COCC: Excavation/trimming
Act | 2AI102CV01600-08085 | COCC: Compacted Sub base preparation
Act | 2AI102CV01600-08095 | COCC: Install Kerb stone
Act | 2AI102CV01600-08105 | COCC: Sand/gatch layer
Act | 2AI102CV01600-08115 | COCC: Laying of Interlock Paving blocks
3 |  | PIPING
4 |  | UG Piping works
Act | 2AI102PI01000 | UG Piping works
5 |  | Metallic (CS/LTCS) Piping Works
Act | 2AI102PI01000-08145 | COCC: Installation of pipes
Act | 2AI102PI01000-08150 | COCC:Alignment/Fit-up
Act | 2AI102PI01000-08160 | COCC:NDE/PWHT/QC Checks of Pipes
Act | 2AI102PI01000-08155 | COCC:Welding/Bolting
Act | 2AI102PI01000-08165 | COCC:Coating/Wrapping
Act | 2AI102PI01000-08141 | COCC: Metallic (CS/LTCS) Piping Works
4 |  | AG Piping works
Act | 2AI102PI01100 | AG Piping works
5 |  | Metallic (CS/LTCS) Piping Works
Act | 2AI102PI01100-08145 | EOF:Installation of pipes
Act | 2AI102PI01100-08160 | EOF:NDE/PWHT/QC Checks of Pipes
Act | 2AI102PI01100-08165 | EOF:Install Permanent Supporting for Pipes
Act | 2AI102PI01100-08170 | COCC:Install piping valves
Act | 2AI102PI01100-08141 | Metallic (CS/LTCS) Piping Works
5 |  | Metallic (SS/SDSS) Piping Works
Act | 2AI102PI01100-08175 | EOF:Installation of pipes
Act | 2AI102PI01100-08180 | COCC:Alignment/Fit-up
Act | 2AI102PI01100-08190 | EOF:NDE/PWHT/QC Checks of Pipes
Act | 2AI102PI01100-08195 | COCC: Install Permanent Supporting for Pipes
Act | 2AI102PI01100-08185 | COCC:Welding/Bolting
Act | 2AI102PI01100-08142 | Metallic (SS/SDSS) Piping Works
4 |  | EOF: Hydrotesting
Act | 2AI102PI01300 | EOF: Hydrotesting
5 |  | Metallic (CS/LTCS) Piping Works
Act | 2AI102PI01300-08000 | EOF:Test pack preparation & Ready for Test
Act | 2AI102PI01300-08002 | EOF:Pressure Testing & Approval
Act | 2AI102PI01300-08141 | Metallic (CS/LTCS) Piping Works
5 |  | Metallic (SS/SDSS) Piping Works
Act | 2AI102PI01300-08010 | COCC: Test pack preparation & Ready for Test
Act | 2AI102PI01300-08015 | COCC: Pressure Testing & Approval
Act | 2AI102PI01300-08142 | Metallic (SS/SDSS) Piping Works
4 |  | PAINTING
5 |  | EOF: Touch-up painting of Piping
Act | 2AI102PI01400 | EOF: Touch-up painting of Piping
Act | 2AI102PI01400-08010 | COCC: Touch-up painting of SS Pipe
Act | 2AI102PI01400-08141 | COCC: Touch-up painting of Piping
3 |  | 50-R-001 : CONTROL ROOM BUILDING
4 |  | ELECTRICAL
5 |  | COCC CCR Building : Earthing Lightning Protection Works
Act | 2AI141EL01000 | COCC CCR Field & Building : Earthing & Lightning Protection Works
6 |  | COCC: Earthing Work
Act | 2AI141EL01000-08010 | COCC: Cad welding
Act | 2AI141EL01000-08000 | COCC CCR Field & Building : Earthing & Lightning Protection Works(outside the Building)
5 |  | COCC CCR Building : Cable laying, glanding & termination
Act | 2AI141EL01100 | COCC CCR Building : Cable laying, glanding & termination
6 |  | COCC CCR Field & Building : Electrical Cable Laying
Act | 2AI141EL01100-08005 | COCC CCR Field & Building : Electrical Cable Laying
7 |  | COCC: Cable laying for LV
Act | 2AI141EL01100-08006 | COCC: Cable Laying - LV
6 |  | COCC CCR Field & Building : Cable Glanding & Terminations
Act | 2AI141EL01100-08010 | COCC CCR Field & Building : Electrical Cable Laying
7 |  | COCC: Cable laying, glanding & termination for LV
Act | 2AI141EL01100-08015 | COCC: Cable Glanding for LV cables
Act | 2AI141EL01100-08020 | COCC: Continuity Checks & Terminations for LV cables
Act | 2AI141EL01100-08025 | COCC: Tagging for LV cables
5 |  | COCC CCR Building : Electrical Equipment & Panels Installation
Act | 2AI141EL01200-08000 | COCC: Electrical Equipment Installation
Act | 2AI141EL01200-08005 | COCC: Electrical Panels Installation
Act | 2AI141EL01200 | COCC CCR Building : Electrical Equipment & Panels Installation
4 |  | INSTRUMENTATION
5 |  | COCC CCR Building : Field Junction Boxes
Act | 2AI141IC01100 | COCC CCR Building : Field Junction Boxes
Act | 2AI141IC01100-08010 | COCC:Leveling & Grouting
Act | 2AI141IC01100-08000 | COCC CCR Field & Building : Junction Boxes
5 |  | COCC CCR Building : Field & Building Cable laying, glanding & termination
Act | 2AI141IC01200-08005 | COCC: Cable Glanding and Termination
Act | 2AI141IC01200 | COCC CCR Building : Field & Building Cable laying, glanding & termination
5 |  | COCC CCR Building : Equipment & Panels Installation (ICSS)
Act | 2AI141IC01500-08005 | COCC CCR Building : Other Equipment & Panels Installation
Act | 2AI141IC01500 | COCC CCR Building : Equipment & Panels Installation (ICSS)
4 |  | TELECOMMUNICATION
5 |  | COCC CCR Building : FO & Telephone Cabling, Cable Terminations & continuity checks
Act | 2AI141TE01100 | COCC CCR Building : FO & Telephone Cabling, Cable Terminations & continuity checks
6 |  | COCC CCR Building : FO & Telephone Cabling works
Act | 2AI141TE01100-08001 | Cable Drum Checks & Transport to Site
Act | 2AI141TE01100-08006 | COCC: Cable Laying (FO, Coaxial, bare etc)
Act | 2AI141TE01100-08010 | COCC: Splicing of FO Cable
Act | 2AI141TE01100-08000 | COCC CCR Building : FO & Telephone Cabling works
3 |  | Car Park Shelter
4 |  | COCC : Construct Car Shelter Foundation & Miscellanious Shelter Foundation
Act | 2AI133CV99400-08000 | COCC: Excavation & Subgrade | [110 empty] | Client | 2018-07-23 | 9 | 2018-07-23 | 9 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | C | Client | 2018-09-02 | 21 | 2018-09-02 | 21 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | Client | 2018-11-04 | 46 | 2018-11-04 | 46 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | Client | 2018-12-29 | 39 | 2018-12-29 | 39 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | Client | 2019-02-09 | 23 | 2019-02-09 | 23 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | Client | 2019-04-13 | 30 | 2019-04-13 | 30 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | C | C
Act | 2AI133CV99400-08005 | COCC: Blinding/PCC for Fnd | [110 empty] | Client | 2018-07-23 | 9 | 2018-07-23 | 9 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | C | Client | 2018-09-02 | 21 | 2018-09-02 | 21 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | Client | 2018-11-04 | 46 | 2018-11-04 | 46 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | Client | 2018-12-29 | 39 | 2018-12-29 | 39 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | Client | 2019-02-09 | 23 | 2019-02-09 | 23 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | Client | 2019-04-13 | 30 | 2019-04-13 | 30 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | C | C
Act | 2AI133CV99400-08010 | COCC: Rebar, Formwork for Footing | [110 empty] | Client | 2018-07-23 | 9 | 2018-07-23 | 9 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | C | Client | 2018-09-02 | 21 | 2018-09-02 | 21 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | Client | 2018-11-04 | 46 | 2018-11-04 | 46 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | Client | 2018-12-29 | 39 | 2018-12-29 | 39 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | Client | 2019-02-09 | 23 | 2019-02-09 | 23 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | Client | 2019-04-13 | 30 | 2019-04-13 | 30 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | C | C
Act | 2AI133CV99400-08015 | COCC: Rebar, Formwork & Install Embedments for Pedestal | [110 empty] | Client | 2018-07-23 | 9 | 2018-07-23 | 9 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | C | [24 empty] | Client | 2018-11-04 | 46 | 2018-11-04 | 46 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | Client | 2018-12-29 | 39 | 2018-12-29 | 39 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | Client | 2019-02-09 | 23 | 2019-02-09 | 23 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | Client | 2019-04-13 | 30 | 2019-04-13 | 30 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | C | C
Act | 2AI133CV99400-08020 | COCC: Concrete Potection for Fnd | [154 empty] | Client | 2018-11-04 | 46 | 2018-11-04 | 46 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | Client | 2018-12-29 | 39 | 2018-12-29 | 39 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | Client | 2019-02-09 | 23 | 2019-02-09 | 23 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | Client | 2019-04-13 | 30 | 2019-04-13 | 30 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | C | C
Act | 2AI133CV99400-08025 | COCC: Backfilling & Compaction for Fnd | [154 empty] | Client | 2018-11-04 | 46 | 2018-11-04 | 46 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | Client | 2018-12-29 | 39 | 2018-12-29 | 39 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | Client | 2019-02-09 | 23 | 2019-02-09 | 23 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | Client | 2019-04-13 | 30 | 2019-04-13 | 30 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | C | C
Act | 2AI133CV99400-08011 | COCC:Concrete Pouring for Footing | [110 empty] | Client | 2018-07-23 | 9 | 2018-07-23 | 9 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | C | Client | 2018-09-02 | 21 | 2018-09-02 | 21 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | Client | 2018-11-04 | 46 | 2018-11-04 | 46 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | Client | 2018-12-29 | 39 | 2018-12-29 | 39 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | Client | 2019-02-09 | 23 | 2019-02-09 | 23 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | Client | 2019-04-13 | 30 | 2019-04-13 | 30 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | C | C
Act | 2AI133CV99400-08016 | COCC:Concrete Pouring for Pedestal | [154 empty] | Client | 2018-11-04 | 46 | 2018-11-04 | 46 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | Client | 2018-12-29 | 39 | 2018-12-29 | 39 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | Client | 2019-02-09 | 23 | 2019-02-09 | 23 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | C | Client | 2019-04-13 | 30 | 2019-04-13 | 30 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | C | C | C | C | C | C | C | C | C | C | C | C
4 |  | COCC : Car Shelter Erection & Miscellanious Shelter
Act | 2AI133CV99500 | COCC : Car Shelter Erection & Miscellanious Shelter
Act | 2AI133CV99500-08141 | COCC : Shelter Erection for Car park
Act | 2AI133CV99500-08005 | COCC: Alignment/Welding/Bolting for Shelter
Act | 2AI133CV99500-08010 | COCC: Grouting of Shelter
Act | 2AI133CV99500-08006 | COCC:Torque Bolts
Act | 2AI133CV99500-08011 | COCC:Installation of gratings/handrail/stair/ladder
Act | 2AI133CV99500-08012 | COCC:Wall & Roof Cladding
Act | 2AI133CV99500-08000 | COCC: Installation of Main steel structure
2 |  | SUBSTATIONS
3 |  | EOF SUBSTATIONS (PART OF AREA 621)
4 |  | CIVIL / STRUCTURAL / ARCHITECTURAL
5 |  | EOF SS : Shelter Erection for Transformer, Capacitor
Act | 2AI133CV99100 | EOF SS : Shelter Erection for Transformer, Capacitor
6 |  | EOF SS : Shelter Erection for Transformer, Capacitor of 50-SUBST-001 - SUBSTATION - COCC
Act | 2AI133CV99100-08010 | EOF SS : Shelter Erection for Transformer, Capacitor of 50-SUBST-001 - SUBSTATION - COCC
Act | 2AI133CV99100-08070 | Wall & Roof Cladding
6 |  | EOF SS : Shelter Erection for Transformer, Capacitor of 52-SUBST-303 - SUBSTATION - LMM
Act | 2AI133CV99100-08015 | EOF SS : Shelter Erection for Transformer, Capacitor of 52-SUBST-303 - SUBSTATION - LMM
Act | 2AI133CV99100-08085 | Installation of gratings/handrail/stair/ladder (wherever applicable)
5 |  | EOF SS : Shelter Erection for Diesel Tank & Inert Agent
Act | 2AI133CV99300 | EOF SS : Shelter Erection for Diesel Tank & Inert Agent
6 |  | Shelter Erection for Diesel Tank & Inert Agent of 52-SUBST-302 - SUBSTATION - STF
Act | 2AI133CV99300-08005 | Shelter Erection for Diesel Tank & Inert Agent of 52-SUBST-302 - SUBSTATION - STF
Act | 2AI133CV99300-08085 | EOF:Wall & Roof Cladding
6 |  | Shelter Erection for Diesel Tank & Inert Agent of 50-SUBST-001 - SUBSTATION - COCC
Act | 2AI133CV99300-08030 | EOF:Installation of Str. Steel
Act | 2AI133CV99300-08035 | EOF:Alignment & Bolting/Torqueing
Act | 2AI133CV99300-08040 | EOF:Grouting
Act | 2AI133CV99300-08010 | Shelter Erection for Diesel Tank & Inert Agent of 50-SUBST-001 - SUBSTATION - COCC
Act | 2AI133CV99300-08060 | EOF:Installation of gratings/handrail/stair/ladder (wherever applicable)
Act | 2AI133CV99300-08070 | EOF:Wall & Roof Cladding
6 |  | Shelter Erection for Diesel Tank & Inert Agent of 52-SUBST-303 - SUBSTATION - LMM
Act | 2AI133CV99300-08045 | EOF:Installation of Str. Steel
Act | 2AI133CV99300-08050 | EOF:Alignment & Bolting/Torqueing
Act | 2AI133CV99300-08055 | EOF:Grouting
Act | 2AI133CV99300-08015 | Shelter Erection for Diesel Tank & Inert Agent of 52-SUBST-303 - SUBSTATION - LMM
Act | 2AI133CV99300-08075 | EOF:Installation of gratings/handrail/stair/ladder (wherever applicable)
Act | 2AI133CV99300-08095 | EOF:Wall & Roof Cladding
4 |  | HSE
5 |  | EOF SS: Installation of Fire fighting & Safety Equipments
Act | 2AI133HS01150 | EOF SS: Installation of Fire fighting & Safety Equipments
6 |  | EOF SS: Fire Fighting Equipment/ Deluge System / Safety Equipments and Gaseous Fire Fighting System
Act | 2AI133HS01150-08001 | Fabrication & Installation of Support Structures
Act | 2AI133HS01150-08005 | Installation of Instruments on Support Structures
Act | 2AI133HS01150-08010 | Alignment/Levelling and grouting
Act | 2AI133HS01150-08000 | EOF SS: Installation of Fire fighting & Safety Equipments
5 |  | EOF SS: Installation of Safety Sign Boards
Act | 2AI133HS01160-08001 | Fabrication & Installation of Support Structures
Act | 2AI133HS01160-08005 | Installation of Instruments on Support Structures
Act | 2AI133HS01160 | EOF SS: Installation of Safety Sign Boards
Act | 2AI133HS01160-08000 | EOF SS: Installation of Safety Sign Boards
Act | 2AI133HS01160-08015 | Alignment/Levelling and grouting
3 |  | 52-SUBST-301 - SUBSTATION - FMM
4 |  | ELECTRICAL
5 |  | EOF SS 52-SUBST-301 : Install HV Switchboard with RCP, Power Factor & Bus Ducts
Act | 2AI133EL03300 | EOF SS 52-SUBST-301 : Install HV Switchboard with RCP, Power Factor & Bus Ducts (Including Modification work)
Act | 2AI133EL03300-08020 | EOF:Allignment of Bus duct
Act | 2AI133EL03300-08000 | EOF SS 52-SUBST-301 : Install HV Switchboard with RCP, Power Factor & Bus Ducts (Including Modification work)
4 |  | INSTRUMENTATION
5 |  | EOF SS 52-SUBST-301 : Install - IRP Cabinets
Act | 2AI133IC03100 | EOF SS 52-SUBST-301 : Install - IRP Cabinets
Act | 2AI133IC03100-08000 | EOF SS 52-SUBST-301 : Install - IRP Cabinets
5 |  | EOF SS 52-SUBST-301 : Install - ICSS related equipments
Act | 2AI133IC03200 | EOF SS 52-SUBST-301 : Install - ICSS related equipments
Act | 2AI133IC03200-08000 | EOF SS 52-SUBST-301 : Install - ICSS related equipments & Other Instrument/Equipment
4 |  | TELECOM
5 |  | EOF SS 52-SUBST-301 : FO & Telephone Cabling, Telecom system install, Cable Terminations
Act | 2AI133TE03000 | EOF SS 52-SUBST-301 : FO & Telephone Cabling, Telecom System install, Cable Terminations & continuity checks
Act | 2AI133TE03000-08010 | 621-SUBST-301 : Cable Terminations
3 |  | 52-SUBST-302 - SUBSTATION - STF
4 |  | ELECTRICAL
5 |  | EOF SS 52-SUBST-302 : Cable laying, glanding, termination & continuity check
Act | 2AI133EL05100 | EOF SS 52-SUBST-302 : Cable laying, glanding, termination & continuity check
6 |  | 621-SUBST-0301 : Cable laying
Act | 2AI133EL05100-08045 | EOF: Cable Laying - HV
Act | 2AI133EL05100-08000 | 621-SUBST-0302 : Cable laying
5 |  | EOF SS 52-SUBST-302 : Earthing Lightning Protection Works
Act | 2AI133EL05200 | EOF SS 52-SUBST-302 : Earthing Lightning Protection Works
6 |  | EOF:Earthing Work
Act | 2AI133EL05200-08001 | COCC: Earth rod Installation
Act | 2AI133EL05200-08015 | COCC: Earth Bus Installation
Act | 2AI133EL05200-08020 | COCC: Earth Boss Installation
Act | 2AI133EL05200-08045 | COCC: Earth Pit Installation
Act | 2AI133EL05200-08000 | EOF:Earthing Work
4 |  | INSTRUMENTATION
5 |  | EOF SS 52-SUBST-302 : Install - ICSS related equipments
Act | 2AI133IC05200-08000 | EOF SS 52-SUBST-302 : Install - ICSS related equipments
Act | 2AI133IC05200 | EOF SS 52-SUBST-302 : Install - ICSS related equipments
5 |  | EOF SS 52-SUBST-302 : Cable laying, glanding, termination & continuity check
6 |  | 621-SUBST-0302 : Cable laying
Act | 2AI133IC05000-08001 | EOF:Cable Tray Installation
4 |  | TELECOM
5 |  | EOF SS 52-SUBST-302 : FO & Telephone Cabling, Telecom system install, Cable Terminations
Act | 2AI133TE05000-08000 | EOF:FO & Telephone Cable Laying
Act | 2AI133TE05000 | EOF SS 52-SUBST-302 : FO & Telephone Cabling, Telecom System install, Cable Terminations & continuity checks
3 |  | 50-SUBST-001 - SUBSTATION - COCC
4 |  | ELECTRICAL
5 |  | EOF SS 50-SUBST-001 : Cable laying, glanding, termination & continuity check
Act | 2AI133EL01100 | EOF SS 50-SUBST-001 : Cable laying, glanding, termination & continuity check
6 |  | COCC CCR Field & Building : Electrical Cable Laying
Act | 2AI133EL01100-08001 | EOF:Fabricate Tray Supports
Act | 2AI133EL01100-08006 | EOF: Install cable trays
Act | 2AI133EL01100-08011 | EOF: Installcable trays covers
Act | 2AI133EL01100-08000 | 621-SUBST-0001 : Cable laying
6 |  | COCC CCR Field & Building : Cable Glanding & Terminations
Act | 2AI133EL01100-08005 | 621-SUBST-0001 : Cable glanding, termination & continuity check
7 |  | COCC: Cable laying, glanding & termination for HV
Act | 2AI133EL01100-08040 | EOF: Cable Glanding for HV cables
Act | 2AI133EL01100-08045 | EOF: Continuity Checks & Terminations for HV cables
Act | 2AI133EL01100-08050 | EOF: Tagging for HV cables
5 |  | EOF SS 50-SUBST-001 : Install Distribution boards and Annunciator Panels
Act | 2AI133EL01500-08015 | EOF:Allignment
Act | 2AI133EL01500-08000 | EOF SS 50-SUBST-001 : Install Distribution boards and Annunciator Panels
Act | 2AI133EL01500 | EOF SS 50-SUBST-001 : Install Distribution boards and Annunciator Panels
5 |  | EOF SS 50-SUBST-001 : Earthing Lightning Protection Works
6 |  | EOF:Earthing Work
Act | 2AI133EL01200-08001 | COCC: Earth rod Installation
Act | 2AI133EL01200-08005 | COCC: Earth Cable Laying
Act | 2AI133EL01200-08010 | COCC: Cad welding
Act | 2AI133EL01200-08025 | COCC: Earth cable Termination
Act | 2AI133EL01200-08030 | COCC: Earth Pit Installation
Act | 2AI133EL01200-08000 | EOF:Earthing Work
Act | 2AI133EL01200 | EOF:Earthing Work
5 |  | EOF SS 50-SUBST-001 : Install LV Switchboards with RCP, MCC & Bus Ducts(incl. Lighting/small power)
Act | 2AI133EL01400-08035 | EOF:Installation of Bus duct
Act | 2AI133EL01400-08045 | EOF:Allignment of Bus duct
Act | 2AI133EL01400-08000 | EOF SS 50-SUBST-001 : Install LV Switchboards with RCP, MCC & Bus Ducts(incl. Lighting/small power)
Act | 2AI133EL01400 | EOF SS 50-SUBST-001 : Install LV Switchboards with RCP, MCC & Bus Ducts(incl. Lighting/small power)
5 |  | EOF SS 50-SUBST-001 : Install UPS with Battery bank and Isolator Switch
Act | 2AI133EL01600-08001 | EOF:Installation of Supports
Act | 2AI133EL01600-08000 | EOF SS 50-SUBST-001 : Install UPS with Battery bank and Isolator Switch
Act | 2AI133EL01600 | EOF SS 50-SUBST-001 : Install UPS with Battery bank and Isolator Switch
4 |  | INSTRUMENTATION
5 |  | EOF SS 50-SUBST-001 : Install - ICSS related equipments
Act | 2AI133IC01200-08000 | EOF SS 52-SUBST-302 : Install - ICSS related equipments
Act | 2AI133IC01200 | EOF SS 50-SUBST-001 : Install - ICSS related equipments
5 |  | EOF SS 50-SUBST-001 : Cable laying, glanding, termination & continuity check
Act | 2AI133IC01000-08010 | EOF:Glanding & termination
Act | 2AI133IC01000-08015 | EOF:Continuity check
Act | 2AI133IC01000-08000 | EOF SS 50-SUBST-001 : Cable laying, glanding, termination & continuity check
Act | 2AI133IC01000 | EOF SS 50-SUBST-001 : Cable laying, glanding, termination & continuity check
Act | 2AI133IC01000-08005 | EOF SS 50-SUBST-001 : Cable laying, glanding, termination & continuity check
4 |  | TELECOM
5 |  | EOF SS 50-SUBST-001 : FO & Telephone Cabling, Telecom system install, Cable Terminations
Act | 2AI133TE01000 | COCC: SS 50-SUBST-001 : FO & Telephone Cabling, Telecom System install, Cable Terminations & continuity checks
6 |  | 621-SUBST-0301 : FO & Telephone Cabling Works
Act | 2AI133TE01000-08011 | Cable Dressing & Fastening
Act | 2AI133TE01000-08006 | Cable Pulling
Act | 2AI133TE01000-08001 | Cable Drum Checks & Transport to Site
Act | 2AI133TE01000-08000 | 621-SUBST-0301 : FO & Telephone Cabling Works
Act | 2AI133TE01000-08021 | Cable Marking
3 |  | 52-SUBST-303 - SUBSTATION - LMM
4 |  | ELECTRICAL
5 |  | EOF SS 52-SUBST-303 : Earthing Lightning Protection Works
Act | 2AI133EL07200 | EOF SS 52-SUBST-303 : Earthing Lightning Protection Works
6 |  | EOF:Earthing Work
Act | 2AI133EL07200-08015 | COCC: Earth Bus Installation
Act | 2AI133EL07200-08020 | COCC: Earth Boss Installation
Act | 2AI133EL07200-08025 | COCC: Earth cable Termination
Act | 2AI133EL07200-08030 | COCC: Earth Pit Installation
Act | 2AI133EL07200-08000 | EOF:Earthing Work
5 |  | EOF SS 52-SUBST-303 : Install LV Switchboards with MCC & Bus Ducts (incl. Lighting/small power)
Act | 2AI133EL07400-08005 | EOF:Installation of LV Switchgear, MCC
Act | 2AI133EL07400-08010 | EOF:Allignment of LV Switchgear, MCC
Act | 2AI133EL07400 | EOF SS 52-SUBST-303 : Install LV Switchboards with RCP, MCC & Bus Ducts(incl. Lighting/small power)
Act | 2AI133EL07400-08000 | EOF SS 52-SUBST-303 : Install LV Switchboards with RCP, MCC & Bus Ducts(incl. Lighting/small power)
5 |  | EOF SS 52-SUBST-303 : Install UPS with Battery bank and Isolator Switch
Act | 2AI133EL07600-08005 | EOF:Installation of UPS
Act | 2AI133EL07600-08010 | EOF:Installation of Isolator Switch
Act | 2AI133EL07600-08015 | EOF:Installation of Batteries
Act | 2AI133EL07600 | EOF SS 52-SUBST-303 : Install UPS with Battery bank and Isolator Switch
Act | 2AI133EL07600-08000 | EOF SS 52-SUBST-303 : Install UPS with Battery bank and Isolator Switch
5 |  | EOF SS 52-SUBST-303 : Cable laying, glanding, termination & continuity check
Act | 2AI133EL07100 | EOF SS 52-SUBST-303 : Cable laying, glanding, termination & continuity check
6 |  | 621-SUBST-0303 : Cable laying .
Act | 2AI133EL07100-08000 | 621-SUBST-0303 : Cable laying
Act | 2AI133EL07100-08089 | EOF: Cable Laying - LV
6 |  | 621-SUBST-0303 : Cable glanding, termination & continuity check
Act | 2AI133EL07100-08005 | 621-SUBST-0303 : Cable glanding, termination & continuity check
7 |  | COCC: Cable laying, glanding & termination for LV
Act | 2AI133EL07100-08090 | EOF: Cable Glanding for LV cables
Act | 2AI133EL07100-08095 | EOF: Continuity Checks & Terminations for LV cables
Act | 2AI133EL07100-08100 | EOF: Tagging for LV cables
7 |  | COCC: Cable laying, glanding & termination for HV
Act | 2AI133EL07100-08110 | EOF: Cable Glanding for HV cables
Act | 2AI133EL07100-08115 | EOF: Continuity Checks & Terminations for HV cables
Act | 2AI133EL07100-08120 | EOF: Tagging for HV cables
5 |  | EOF SS 52-SUBST-303 : Install Distribution boards and Annunciator Panels
Act | 2AI133EL07500-08001 | EOF:Installation of Supports
Act | 2AI133EL07500-08005 | EOF:Installation of Distribution Board
Act | 2AI133EL07500-08015 | EOF:Allignment of Distribution Board
Act | 2AI133EL07500 | EOF SS 52-SUBST-303 : Install Distribution boards and Annunciator Panels
Act | 2AI133EL07500-08000 | EOF SS 52-SUBST-303 : Install Distribution boards and Annunciator Panels
4 |  | INSTRUMENTATION
5 |  | EOF SS 52-SUBST-303 : Install - IRP Cabinets
Act | 2AI133IC07100-08000 | EOF SS 52-SUBST-303 : Install - IRP Cabinets
Act | 2AI133IC07100 | EOF SS 52-SUBST-303 : Install - IRP Cabinets
5 |  | EOF SS 52-SUBST-303 : Install - ICSS related equipments
Act | 2AI133IC07200-08000 | EOF SS 52-SUBST-303 : Install - ICSS related equipments
Act | 2AI133IC07200 | EOF SS 52-SUBST-303 : Install - ICSS related equipments
5 |  | EOF SS 52-SUBST-303 : Cable laying, glanding, termination & continuity check
Act | 2AI133IC07000-08010 | EOF:Cable laying
Act | 2AI133IC07000-08015 | EOF:Glanding & termination
Act | 2AI133IC07000-08020 | EOF:Continuity check
Act | 2AI133IC07000 | EOF SS 52-SUBST-303 : Cable laying, glanding, termination & continuity check
Act | 2AI133IC07000-08000 | 621-SUBST-0303 : Cable laying
Act | 2AI133IC07000-08005 | 621-SUBST-0303 : Cable glanding, termination & continuity check
4 |  | TELECOM
5 |  | EOF SS 52-SUBST-303 : FO & Telephone Cabling, Telecom system install, Cable Terminations
Act | 2AI133TE07000 | EOF SS 52-SUBST-303 : FO & Telephone Cabling, Telecom System install, Cable Terminations & continuity checks
Act | 2AI133TE07000-08000 | EOF:FO & Telephone Cable Laying
3 |  | 52-R-301 - EMERGENCY GENERATOR BUILDING (FMM)
4 |  | ELECTRICAL
5 |  | EOF EG Building 52-R-301 : Cable laying, glanding, termination & continuity check
Act | 2AI133EL21200 | EOF EG Building 52-R-301 : Cable laying, glanding, termination & continuity check
6 |  | EOF EG Building 52-R-301 : Cable laying
Act | 2AI133EL21200-08014 | EOF: Cable Laying
Act | 2AI133EL21200-08000 | EOF EG Building 52-R-301 : Cable laying
6 |  | EOF EG Building 52-R-301 : Cableglanding, termination & continuity check
Act | 2AI133EL21200-08020 | EOF: Cable Glanding
Act | 2AI133EL21200-08025 | EOF: Continuity Checks & Terminations
Act | 2AI133EL21200-08030 | EOF: Tagging
Act | 2AI133EL21200-08005 | EOF EG Building 52-R-301 : Cable glanding, termination & continuity check
5 |  | EOF EG Building 52-R-301 : Install Distribution boards, Lighting & small power
Act | 2AI133EL21100-08001 | EOF:Installation of Supports
Act | 2AI133EL21100-08005 | EOF:Installation of Distribution Board
Act | 2AI133EL21100-08010 | EOF:Allignment
Act | 2AI133EL21100 | EOF EG Building 52-R-301 : Install Distribution boards, Lighting & small power
Act | 2AI133EL21100-08000 | EOF EG Building 52-R-301 : Install Distribution boards
4 |  | INSTRUMENTATION
5 |  | EOF EG Building 52-R-301 : Instrument Cable laying, glanding, termination & continuity checks
Act | 2AI133IC21000-08006 | EOF:Glanding & termination
Act | 2AI133IC21000-08010 | EOF:Continuity check
Act | 2AI133IC21000 | EOF EG Building 52-R-301 : Instrument Cable laying, glanding, termination & continuity checks
Act | 2AI133IC21000-08000 | EOF EG Building 52-R-301 : Instrument Cable laying
Act | 2AI133IC21000-08005 | EOF EG Building 52-R-301 : Instrument Cable glanding, termination & continuity checks
3 |  | 52-R-302 - EMERGENCY GENERATOR BUILDING (STF)
4 |  | ELECTRICAL
5 |  | EOF EG Building 52-R-302 : Cable laying, glanding, termination & continuity check
Act | 2AI133EL31200 | EOF EG Building 52-R-302 : Cable laying, glanding, termination & continuity check
6 |  | EOF EG Building 52-R-302 : Cableglanding, termination & continuity check
Act | 2AI133EL31200-08015 | EOF: Cable Glanding
Act | 2AI133EL31200-08020 | EOF: Continuity Checks & Terminations
Act | 2AI133EL31200-08025 | EOF: Tagging
Act | 2AI133EL31200-08005 | EOF EG Building 52-R-302 : Cableglanding, termination & continuity check
4 |  | INSTRUMENTATION
5 |  | EOF EG Building 52-R-302 : Instrument Cable laying, glanding, termination & continuity checks
Act | 2AI133IC31000 | EOF EG Building 52-R-302 : Instrument Cable laying, glanding, termination & continuity checks
Act | 2AI133IC31000-08001 | EOF:Cable laying
Act | 2AI133IC31000-08006 | EOF:Glanding & termination
Act | 2AI133IC31000-08010 | EOF:Continuity check
Act | 2AI133IC31000-08000 | EOF EG Building 52-R-302 : Instrument Cable laying
Act | 2AI133IC31000-08005 | EOF EG Building 52-R-302 : Instrument Cable glanding, termination & continuity checks
4 |  | TELECOM
5 |  | EOF EG Building 52-R-302 : FO & Telephone Cabling, Telecom system install, Cable Terminations
Act | 2AI133TE31000 | EOF EG Building 52-R-302 : FO & Telephone Cabling, Telecom System install, Cable Terminations & continuity checks
Act | 2AI133TE31000-08000 | EOF:FO & Telephone Cable Laying
Act | 2AI133TE31000-08010 | EOF:Cable Terminations & continuity checks
4 |  | MECHANICAL
5 |  | EOF EG Building 52-R-302 : Diesel Day Tank Installation
Act | 2AI133MS31000-08010 | EOF:Final Allignment & Grouting of Equipment
Act | 2AI133MS31000 | EOF EG Building 52-R-302 : Diesel Day Tank Installation
Act | 2AI133MS31000-08000 | EOF EG Building 52-R-302 : Diesel Day Tank Installation
3 |  | 50-R-002 - EMERGENCY GENERATOR BUILDING (COCC)
4 |  | ELECTRICAL
5 |  | EOF EG Building 50-R-002 : Cable laying, glanding, termination & continuity check
Act | 2AI133EL11100 | EOF EG Building 50-R-002 : Cable laying, glanding, termination & continuity check
6 |  | COCC: Cable Tray Installation
Act | 2AI133EL11100-08006 | EOF:Fabricate Tray Supports
Act | 2AI133EL11100-08015 | EOF: Installcable trays covers
Act | 2AI133EL11100-08000 | EOF EG Building 50-R-002 : Cable laying
6 |  | COCC: Cable laying, glanding & termination for LV
Act | 2AI133EL11100-08020 | EOF: Cable Glanding for LV cables
Act | 2AI133EL11100-08025 | EOF: Continuity Checks & Terminations for LV cables
Act | 2AI133EL11100-08030 | EOF: Tagging for LV cables
Act | 2AI133EL11100-08005 | EOF EG Building 50-R-002 : Cable glanding, termination & continuity check
5 |  | EOF EG Building 50-R-002 : Install Distribution boards, Lighting & small power
Act | 2AI133EL11200 | EOF EG Building 50-R-002 : Install Distribution boards, Lighting & small power
Act | 2AI133EL11200-08010 | EOF:Allignment
Act | 2AI133EL11200-08000 | EOF EG Building 50-R-002 : Install Distribution boards, Lighting & small power
Act | 2AI133MS41000-08000 | EOF EG Building 52-R-303 : Diesel Day Tank Installation
Act | 2AI133EL41000-08000 | EOF EG Building 52-R-303 : Install Emergency Generator
4 |  | INSTRUMENTATION
5 |  | EOF EG Building 50-R-002 : Instrument Cable laying, glanding, termination & continuity checks
Act | 2AI133IC11000-08001 | EOF:Cable laying
Act | 2AI133IC11000-08006 | EOF:Glanding & termination
4 |  | TELECOM
5 |  | EOF EG Building 50-R-002 : FO & Telephone Cabling, Telecom system install, Cable Terminations
Act | 2AI133TE11000 | EOF EG Building 50-R-002 : FO & Telephone Cabling, Telecom System install, Cable Terminations & continuity checks
Act | 2AI133TE11000-08000 | EOF:FO & Telephone Cable Laying
Act | 2AI133TE11000-08010 | EOF:Cable Terminations & continuity checks
4 |  | MECHANICAL
5 |  | EOF EG Building 50-R-002 : Diesel Day Tank Installation
Act | 2AI133MS11000-08010 | EOF:Final Allignment & Grouting of Equipment
Act | 2AI133MS11000 | EOF EG Building 50-R-002 : Diesel Day Tank Installation
Act | 2AI133MS11000-08000 | EOF EG Building 50-R-002 : Diesel Day Tank Foundation
3 |  | 52-R-303 - EMERGENCY GENERATOR BUILDING (LMM)
4 |  | ELECTRICAL
5 |  | EOF EG Building 52-R-303 : Cable laying, glanding, termination & continuity check
Act | 2AI133EL41100 | EOF EG Building 52-R-303 : Cable laying, glanding, termination & continuity check
6 |  | EOF EG Building 52-R-303 : Cable laying
Act | 2AI133EL41100-08001 | EOF:Fabricate Tray Supports
Act | 2AI133EL41100-08010 | EOF: Installcable trays covers
Act | 2AI133EL41100-08004 | EOF: Install Tray support and Hangers
Act | 2AI133EL41100-08000 | EOF EG Building 52-R-303 : Cable laying
6 |  | EOF EG Building 52-R-303 : Cableglanding, termination & continuity check
Act | 2AI133EL41100-08020 | EOF: Continuity Checks & Terminations
Act | 2AI133EL41100-08025 | EOF: Tagging
Act | 2AI133EL41100-08005 | EOF EG Building 52-R-303 : Cableglanding, termination & continuity check
5 |  | EOF EG Building 52-R-303 : Install Distribution boards, Lighting & small power
Act | 2AI133EL41200 | EOF EG Building 52-R-303 : Install Distribution boards, Lighting & small power
Act | 2AI133EL41200-08001 | EOF:Installation of Supports
Act | 2AI133EL41200-08005 | EOF:Installation of Distribution Board
Act | 2AI133EL41200-08010 | EOF:Allignment
Act | 2AI133EL41200-08000 | EOF EG Building 52-R-303 : Install Distribution boards, Lighting & small power
4 |  | INSTRUMENTATION
5 |  | EOF EG Building 52-R-303 : Instrument Cable laying, glanding, termination & continuity checks
Act | 2AI133IC41000 | EOF EG Building 52-R-303 : Instrument Cable laying, glanding, termination & continuity checks
Act | 2AI133IC41000-08001 | EOF:Cable laying
Act | 2AI133IC41000-08006 | EOF:Glanding & termination
Act | 2AI133IC41000-08010 | EOF:Continuity check
Act | 2AI133IC41000-08000 | EOF EG Building 52-R-303 : Instrument Cable laying
Act | 2AI133IC41000-08005 | EOF EG Building 52-R-303 : Instrument Cable glanding, termination & continuity checks
4 |  | TELECOM
5 |  | EOF EG Building 52-R-303 : FO & Telephone Cabling, Telecom system install, Cable Terminations
Act | 2AI133TE41000-08000 | EOF:FO & Telephone Cable Laying
Act | 2AI133TE41000-08010 | EOF:Cable Terminations & continuity checks
Act | 2AI133TE41000 | EOF EG Building 52-R-303 : FO & Telephone Cabling, Telecom System install, Cable Terminations & continuity checks
2 |  | PRE-COMMISSIONING: EXPORT OIL FACILITY - AREA 621
3 |  | EOF S/S - ENERGIZE
4 |  | 52-SUBST-301+ 52-R-301 EDG (FMM AREA)
5 |  | EOF SS 52-SUBST-301 : 110V DC Battery Charger
Act | 2AI102PC01000-08010 | EOF:Discharging test
Act | 2AI102PC01000 | EOF SS 52-SUBST-301 : 110V DC Battery Charger
Act | 2AI102PC01000-08000 | EOF SS 52-SUBST-301 : 110V DC Battery Charger
5 |  | EOF SS 52-SUBST-301 : SS Earthing & Lightning
Act | 2AI102PC01100-08005 | EOF:Earth resistance measurement
Act | 2AI102PC01100 | EOF SS 52-SUBST-301 : SS Earthing & Lightning
Act | 2AI102PC01100-08000 | EOF SS 52-SUBST-301 : SS Earthing & Lightning
5 |  | EOF SS 52-SUBST-301 : 24V DC Battery Charger
Act | 2AI102PC01300-08010 | EOF:Discharging test
Act | 2AI102PC01300 | EOF SS 52-SUBST-301 : 24V DC Battery Charger
Act | 2AI102PC01300-08000 | EOF SS 52-SUBST-301 : 24V DC Battery Charger
5 |  | EOF SS 52-SUBST-301 : LV Switchgear testing
Act | 2AI102PC01400 | EOF SS 52-SUBST-301 : LV Switchgear testing
Act | 2AI102PC01400-08010 | EOF: Relay & Functional Testing
Act | 2AI102PC01400-08015 | EOF Primary Injection Testing
Act | 2AI102PC01400-08025 | EOF: Stability Testing
Act | 2AI102PC01400-08020 | EOF: Hi-pot Test
Act | 2AI102PC01400-08000 | EOF SS 52-SUBST-301 : LV Switchgear testing
5 |  | EOF SS 52-SUBST-301 : Transformer Testing
Act | 2AI102PC01700-08010 | EOF:BDV Testing
Act | 2AI102PC01700 | EOF SS 52-SUBST-301 : Transformer Testing
Act | 2AI102PC01700-08000 | EOF SS 52-SUBST-301 : Transformer Testing
5 |  | EOF SS 52-SUBST-301 : Electrical Tie-ins for Permanent Power & Energize
Act | 2AI102PC01900 | EOF SS 52-SUBST-301 : Electrical Tie-ins for Permanent Power & Energize
Act | 2AI102PC01900-08045 | EOF: Ready for Energisation of Substation 52-SUBST-301
Act | 2AI102PC01900-08000 | EOF SS 52-SUBST-301 : Electrical Tie-ins for Permanent Power & Energize
5 |  | EOF SS 52-SUBST-301 : Energize EDG 50-R-301
Act | 2AI102PC02100-08001 | GCP Testing, Switch Gear Testing
Act | 2AI102PC02100 | EOF SS 52-SUBST-301 : Energize EDG 50-R-301
Act | 2AI102PC02100-08010 | EOF SS 52-SUBST-301 : Energize EDG 50-R-301
Act | 2AI102PC02100-08000 | EOF SS 52-SUBST-301 : Energize EDG 50-R-301
4 |  | 52-SUBST-303 + 52-R-303 EDG (LMM AREA)
5 |  | EOF SS 52-SUBST-303 : 110V DC Battery Charger
Act | 2AI102PC03000-08001 | EOF:Polarity check
Act | 2AI102PC03000-08005 | EOF:Charging test
Act | 2AI102PC03000-08010 | EOF:Discharging test
Act | 2AI102PC03000 | EOF SS 52-SUBST-303 : 110V DC Battery Charger
Act | 2AI102PC03000-08000 | EOF SS 52-SUBST-303 : 110V DC Battery Charger
5 |  | EOF SS 52-SUBST-303 : SS Earthing & Lightning
Act | 2AI102PC03100-08001 | EOF:Continuity testing
Act | 2AI102PC03100-08005 | EOF:Earth resistance measurement
Act | 2AI102PC03100 | EOF SS 52-SUBST-303 : SS Earthing & Lightning
Act | 2AI102PC03100-08000 | EOF SS 52-SUBST-303 : SS Earthing & Lightning
5 |  | EOF SS 52-SUBST-303 : HV Switchgear testing
Act | 2AI102PC03200 | EOF SS 52-SUBST-303 : HV Switchgear testing
Act | 2AI102PC03200-08001 | EOF: CT,PT,Breaker Testing
Act | 2AI102PC03200-08005 | EOF: IR, Ductor testing
Act | 2AI102PC03200-08010 | EOF: Relay & Functional Testing
Act | 2AI102PC03200-08015 | EOF Primary Injection Testing
Act | 2AI102PC03200-08025 | EOF: Stability Testing
Act | 2AI102PC03200-08020 | EOF: Hi-pot Test
Act | 2AI102PC03200-08000 | EOF SS 52-SUBST-303 : HV Switchgear testing
5 |  | EOF SS 52-SUBST-303 : 24V DC Battery Charger
Act | 2AI102PC03300-08001 | EOF:Polarity check
Act | 2AI102PC03300-08005 | EOF:Charging test
Act | 2AI102PC03300-08010 | EOF:Discharging test
Act | 2AI102PC03300 | EOF SS 52-SUBST-303 : 24V DC Battery Charger
Act | 2AI102PC03300-08000 | EOF SS 52-SUBST-303 : 24V DC Battery Charger
5 |  | EOF SS 52-SUBST-303 : LV Switchgear testing
Act | 2AI102PC03400 | EOF SS 52-SUBST-303 : LV Switchgear testing
Act | 2AI102PC03400-08001 | EOF: CT,PT Testing
Act | 2AI102PC03400-08005 | EOF: IR, Ductor testing
Act | 2AI102PC03400-08010 | EOF: Relay & Functional Testing
Act | 2AI102PC03400-08015 | EOF Primary Injection Testing
Act | 2AI102PC03400-08025 | EOF: Stability Testing
Act | 2AI102PC03400-08020 | EOF: Hi-pot Test
Act | 2AI102PC03400-08000 | EOF SS 52-SUBST-303 : LV Switchgear testing
5 |  | EOF SS 52-SUBST-303 : 110V AC UPS
Act | 2AI102PC03600-08001 | EOF:Polarity check
Act | 2AI102PC03600-08005 | EOF:Charging test
Act | 2AI102PC03600-08010 | EOF:Discharging test
Act | 2AI102PC03600 | EOF SS 52-SUBST-303 : 110V AC UPS
Act | 2AI102PC03600-08000 | EOF SS 52-SUBST-303 : 110V AC UPS
5 |  | EOF SS 52-SUBST-303 : Transformer Testing
Act | 2AI102PC03700 | EOF SS 52-SUBST-303 : Transformer Testing
Act | 2AI102PC03700-08001 | EOF:IR testing/WR testing/Turns ratio testing
Act | 2AI102PC03700-08005 | EOF:Functional Test
Act | 2AI102PC03700-08010 | EOF:BDV Testing
Act | 2AI102PC03700-08000 | EOF SS 52-SUBST-303 : Transformer Testing
5 |  | EOF SS 52-SUBST-303 : Electrical Tie-ins for Permanent Power & Energize
Act | 2AI102PC03900-08001 | EOF:Incoming cables IR and continuity test
Act | 2AI102PC03900-08005 | EOF:Incoming HV cables hipot testing
Act | 2AI102PC03900 | EOF SS 52-SUBST-303 : Electrical Tie-ins for Permanent Power & Energize
Act | 2AI102PC03900-08015 | EOF: Cable Termination
Act | 2AI102PC03900-08000 | EOF SS 52-SUBST-303 : Electrical Tie-ins for Permanent Power & Energize
5 |  | EOF SS 52-SUBST-303 : Energize EDG 52-R-303
Act | 2AI102PC04000-08001 | EOF: GCP Testing, Switch Gear Testing
Act | 2AI102PC04000 | EOF SS 52-SUBST-303 : Energize EDG 52-R-303
Act | 2AI102PC04000-08010 | EOF SS 52-SUBST-303 : Energize EDG 52-R-303
Act | 2AI102PC04000-08000 | EOF SS 52-SUBST-303 : Energize EDG 52-R-303
4 |  | 52-SUBST-302 + 52-R-302 EDG (STF AREA)
5 |  | EOF SS 52-SUBST-302 : SS Earthing & Lightning
Act | 2AI101PC01100-08001 | EOF:Continuity testing
Act | 2AI101PC01100-08005 | EOF:Earth resistance measurement
Act | 2AI101PC01100 | EOF SS 52-SUBST-302 : SS Earthing & Lightning
Act | 2AI101PC01100-08000 | EOF SS 52-SUBST-302 : SS Earthing & Lightning
5 |  | EOF SS 52-SUBST-302 : 110V DC Battery Charger
Act | 2AI101PC01000-08001 | EOF:Polarity check
Act | 2AI101PC01000-08005 | EOF:Charging test
Act | 2AI101PC01000-08010 | EOF:Discharging test
Act | 2AI101PC01000 | EOF SS 52-SUBST-302 : 110V DC Battery Charger
Act | 2AI101PC01000-08000 | EOF SS 52-SUBST-302 : 110V DC Battery Charger
5 |  | EOF SS 52-SUBST-302 : 110V AC UPS
Act | 2AI101PC01600-08001 | EOF:Polarity check
Act | 2AI101PC01600-08005 | EOF:Charging test
Act | 2AI101PC01600-08010 | EOF:Discharging test
Act | 2AI101PC01600 | EOF SS 52-SUBST-302 : 110V AC UPS
Act | 2AI101PC01600-08000 | EOF SS 52-SUBST-302 : 110V AC UPS
5 |  | EOF SS 52-SUBST-302 : 24V DC Battery Charger
Act | 2AI101PC01300-08001 | EOF:Polarity check
Act | 2AI101PC01300-08005 | EOF:Charging test
Act | 2AI101PC01300-08010 | EOF:Discharging test
Act | 2AI101PC01300 | EOF SS 52-SUBST-302 : 24V DC Battery Charger
Act | 2AI101PC01300-08000 | EOF SS 52-SUBST-302 : 24V DC Battery Charger
5 |  | EOF SS 52-SUBST-302 : HV Switchgear testing
Act | 2AI101PC01200 | EOF SS 52-SUBST-302 : HV Switchgear testing
Act | 2AI101PC01200-08001 | EOF: CT,PT,Breaker Testing
Act | 2AI101PC01200-08005 | EOF: IR, Ductor testing
Act | 2AI101PC01200-08010 | EOF: Relay & Functional Testing
Act | 2AI101PC01200-08015 | EOF Primary Injection Testing
Act | 2AI101PC01200-08025 | EOF: Stability Testing
Act | 2AI101PC01200-08020 | EOF: Hi-pot Test
Act | 2AI101PC01200-08000 | EOF SS 52-SUBST-302 : HV Switchgear testing
5 |  | EOF SS 52-SUBST-302 : Transformer Testing
Act | 2AI101PC01700-08001 | EOF:IR testing/WR testing/Turns ratio testing
Act | 2AI101PC01700-08005 | EOF:Functional Test
Act | 2AI101PC01700-08010 | EOF:BDV Testing
Act | 2AI101PC01700 | EOF SS 52-SUBST-302 : Transformer Testing
Act | 2AI101PC01700-08000 | EOF SS 52-SUBST-302 : Transformer Testing
5 |  | EOF SS 52-SUBST-302 : LV Switchgear testing
Act | 2AI101PC01400 | EOF SS 52-SUBST-302 : LV Switchgear testing
Act | 2AI101PC01400-08001 | EOF: CT,PT Testing
Act | 2AI101PC01400-08005 | EOF: IR, Ductor testing
Act | 2AI101PC01400-08010 | EOF: Relay & Functional Testing
Act | 2AI101PC01400-08015 | EOF Primary Injection Testing
Act | 2AI101PC01400-08025 | EOF: Stability Testing
Act | 2AI101PC01400-08020 | EOF: Hi-pot Test
Act | 2AI101PC01400-08000 | EOF SS 52-SUBST-302 : LV Switchgear testing
5 |  | EOF SS 52-SUBST-302 : Energize EDG 60-R-706
Act | 2AI101PC02100-08001 | EOF: GCP Testing, Switch Gear Testing
Act | 2AI101PC02100 | EOF SS 52-SUBST-302 : Energize EDG 60-R-706
Act | 2AI101PC02100-08010 | EOF SS 52-SUBST-302 : Energize EDG 60-R-706
Act | 2AI101PC02100-08000 | EOF SS 52-SUBST-302 : Energize EDG 60-R-706
5 |  | EOF SS 52-SUBST-302 : Electrical Tie-ins for Permanent Power & Energize
Act | 2AI101PC01900-08001 | EOF:Incoming cables IR and continuity test
Act | 2AI101PC01900-08005 | EOF:Incoming HV cables hipot testing
Act | 2AI101PC01900 | EOF SS 52-SUBST-302 : Electrical Tie-ins for Permanent Power & Energize
Act | 2AI102PC03900-08020 | EOF: Energisation of Substation 52-SUBST-302
Act | 2AI102PC03900-08010 | EOF: Cable Termination
Act | 2AI101PC01900-08000 | EOF SS 52-SUBST-302 : Electrical Tie-ins for Permanent Power & Energize
3 |  | EOF - UTILITY System
4 |  | EOF:Fire Water Tie-In / Ring main & hydrants /Deluge System
Act | 2AI133PC01000-08000 | EOF:Fire Water Tie-In / Ring main & hydrants /Deluge System
Act | 2AI133PC01000 | EOF:Fire Water Tie-In / Ring main & hydrants /Deluge System
4 |  | EOF:Foam System Package/Overhead Water tank/Foam Concentrate tank/drains/Diesel Tanks/Foam Pumps
Act | 2AI133PC01100-08000 | EOF:Foam System Package / Overhead Water tank / Foam Concentrate tank / drains / Diesel Tanks/ Foam Pumps
Act | 2AI133PC01100 | EOF:Foam System Package / Overhead Water tank / Foam Concentrate tank / drains / Diesel Tanks/ Foam Pumps
3 |  | EOF -PROCESS System
4 |  | EOF:Floating Tanks / Mixers / Oily Water collection System / Drain / Oily Water transfer Pump
Act | 2AI133PC01400-08000 | EOF:Floating Tanks / Mixers / Oily Water collection System / Drain / Oily Water transfer Pump
Act | 2AI133PC01400 | EOF:Floating Tanks / Mixers / Oily Water collection System / Drain / Oily Water transfer Pump
2 |  | PRE-COMMISSIONING - CRUDE OIL CONTROL CENTER (COCC) - AREA 621
3 |  | EOF S/S - ENERGIZE
4 |  | 50-SUBST-001 + 50-R-002 EDG (COCC AREA)
5 |  | COCC: EOF SS 50-SUBST-001 : 110V DC Battery Charger
Act | 2AI141PC02000-08001 | COCC: Polarity check
Act | 2AI141PC02000-08005 | COCC: Charging test
Act | 2AI141PC02000-08010 | COCC: Discharging test
Act | 2AI141PC02000 | COCC: EOF SS 50-SUBST-001 : 110V DC Battery Charger
Act | 2AI141PC02000-08000 | COCC: EOF SS 50-SUBST-001 : 110V DC Battery Charger
5 |  | COCC: EOF SS 50-SUBST-001 : HV Switchgear testing
Act | 2AI141PC02200 | COCC: EOF SS 50-SUBST-001 : HV Switchgear testing
Act | 2AI141PC02200-08001 | EOF: CT,PT,Breaker Testing
Act | 2AI141PC02200-08005 | EOF: IR, Ductor testing
Act | 2AI141PC02200-08010 | EOF: Relay & Functional Testing
Act | 2AI141PC02200-08015 | EOF Primary Injection Testing
Act | 2AI141PC02200-08025 | EOF: Stability Testing
Act | 2AI141PC02200-08020 | EOF: Hi-pot Test
Act | 2AI141PC02200-08000 | COCC: EOF SS 50-SUBST-001 : HV Switchgear testing
5 |  | COCC: EOF SS 50-SUBST-001 : Transformer Testing
Act | 2AI141PC02700 | COCC: EOF SS 50-SUBST-001 : Transformer Testing
Act | 2AI141PC02700-08001 | EOF:IR testing/WR testing/Turns ratio testing
Act | 2AI141PC02700-08005 | EOF:Functional Test
Act | 2AI141PC02700-08010 | EOF:BDV Testing
Act | 2AI141PC02700-08000 | COCC: EOF SS 50-SUBST-001 : Transformer Testing
5 |  | COCC: EOF SS 50-SUBST-001 : LV Switchgear testing
Act | 2AI141PC02400 | COCC: EOF SS 50-SUBST-001 : LV Switchgear testing
Act | 2AI141PC02400-08001 | EOF: CT,PT Testing
Act | 2AI141PC02400-08005 | EOF: IR, Ductor testing
Act | 2AI141PC02400-08010 | EOF: Relay & Functional Testing
Act | 2AI141PC02400-08015 | EOF Primary Injection Testing
Act | 2AI141PC02400-08025 | EOF: Stability Testing
Act | 2AI141PC02400-08020 | EOF: Hi-pot Test
Act | 2AI141PC02400-08000 | COCC: EOF SS 50-SUBST-001 : LV Switchgear testing
5 |  | COCC: EOF SS 50-SUBST-001 : 24V DC Battery Charger
Act | 2AI141PC02300-08001 | COCC: Polarity check
Act | 2AI141PC02300-08005 | COCC: Charging test
Act | 2AI141PC02300-08010 | COCC: Discharging test
Act | 2AI141PC02300 | COCC: EOF SS 50-SUBST-001 : 24V DC Battery Charger
Act | 2AI141PC02300-08000 | COCC: EOF SS 50-SUBST-001 : 24V DC Battery Charger
5 |  | COCC: EOF SS 50-SUBST-001 : SS Earthing & Lightning
Act | 2AI141PC02100-08001 | COCC: Continuity testing
Act | 2AI141PC02100-08005 | COCC: Earth resistance measurement
Act | 2AI141PC02100 | COCC: EOF SS 50-SUBST-001 : SS Earthing & Lightning
Act | 2AI141PC02100-08000 | COCC: EOF SS 50-SUBST-001 : SS Earthing & Lightning
5 |  | COCC: EOF SS 50-SUBST-001 : Energize EDG Building 50-R-002
Act | 2AI141PC03000-08001 | COCC: GCP Testing, Switch Gear Testing
Act | 2AI141PC03000 | COCC: EOF SS 50-SUBST-001 : Energize EDG Building 50-R-002
Act | 2AI141PC03000-08010 | COCC: EOF SS 50-SUBST-001 : Energize EDG Building 50-R-002
Act | 2AI141PC03000-08000 | COCC: EOF SS 50-SUBST-001 : Energize EDG Building 50-R-002
5 |  | COCC: EOF SS 50-SUBST-001 : 110V AC UPS
Act | 2AI141PC02600-08001 | COCC: Polarity check
Act | 2AI141PC02600-08005 | COCC: Charging test
Act | 2AI141PC02600-08010 | COCC: Discharging test
Act | 2AI141PC02600 | COCC: EOF SS 50-SUBST-001 : 110V AC UPS
Act | 2AI141PC02600-08000 | COCC: EOF SS 50-SUBST-001 : 110V AC UPS
5 |  | COCC: EOF SS 50-SUBST-001 : Electrical Tie-ins for Permanent Power & Energize
Act | 2AI141PC02900-08001 | COCC: Incoming cables IR and continuity test
Act | 2AI141PC02900-08005 | COCC: Incoming HV cables hipot testing
Act | 2AI141PC02900 | COCC: EOF SS 50-SUBST-001 : Electrical Tie-ins for Permanent Power & Energize
Act | 2AI141PC02900-08015 | EOF: Ready for Energisation of Substation 50-SUBST-001
Act | 2AI141PC02900-08010 | EOF: Cable Termination
Act | 2AI141PC02900-08000 | COCC: EOF SS 50-SUBST-001 : Electrical Tie-ins for Permanent Power & Energize
3 |  | PRE-COMMISSIONING - CRUDE OIL CONTROL CENTER (COCC) BUILDING
4 |  | COCC CCR Building : ICSS SAT
Act | 2AI141PC01000 | COCC CCR Building : ICSS SAT
Act | 2AI141PC01000-08000 | COCC CCR Building : ICSS SAT
Formulas:
Practical Impact = [Pull Back Impact]
Pull Back Impact = IF([Practical Impact]>CQ10,CQ10,[Practical Impact])
Pull Back Impact = IF([Practical Impact]>DM10,DM10,[Practical Impact])